## Apr ME
MCAP | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total EAC
2023 EAC
11+1
10+2
9+3
8+4
7+5
6+6
5+7
4+8 | 11186816 | 12882311 | 15241859 | 16293114 | 16871797 | 26396716 | 23925774 | 23898040 | 24962498 | 22640521 | 13777658 | 10161175 | 218238279.21
3+9 | 11186816.36 | 12882311.31 | 15333548.93 | 14166241 | 22613792 | 26996924 | 26852769 | 25532178 | 21626986 | 19346977 | 11798863 | 10647179 | 218984585.6 | $8.2M Topside Reduction included
2+10 | 11186816.36 | 12882311.31 | 13049833 | 19410632 | 23835009 | 28916795 | 26415070 | 23140614 | 22007546 | 19161602 | 10584412 | 8278153 | 218868793.67 | -$200K in IT Program
1+11 | 11186816.36 | 12105043 | 19891229 | 22706578 | 23734342 | 23562626 | 26036063 | 22462849 | 21286164 | 17156289 | 10433805 | 8037781 | 218599585.36 | - $3.8M in Operating Infrastructure
2023 Baseline | 10594523 | 10559633 | 15976981 | 17718441 | 22863870 | 30385688 | 31973112 | 24141220 | 19160117 | 13348947 | 12718141 | 9014102 | 218454775 | - $7.6M in Integrity Programs
2022 Final EAC | 8679673.45 | 10092210.79 | 10554938.24 | 12491612.27 | 14271771.96 | 18518897 | 20118601 | 22921565 | 25817679 | 26898448 | 21430625 | 20924150 | 212720171.71
2021 Final EAC | 4327797.63 | 7370316.86 | 8100588.44 | 9683264.58 | 13797328.98 | 14437457.3 | 14115877.23 | 13733245.56 | 16276033.53 | 14037215.17 | 18059094.58 | 19950437 | 153888656.86
MCAP | Jan: Q1; Feb: Q2; Mar: Q3; Apr: Q4; May: Total EAC; Jun: Check
2023 EAC | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 0
11+1 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 0
10+2 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 0
9+3 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 0
8+4 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 0
7+5 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 0
6+6 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 0
5+7 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 0
4+8 | Jan: 39310986; Feb: 59561627; Mar: 72786312; Apr: 46579354; May: 218238279; Jun: -0.21
3+9 | Jan: 39402676.6; Feb: 63776957; Mar: 74011933; Apr: 41793019; May: 218984585.6; Jun: 0
2+10 | Jan: 37118960.67; Feb: 72162436; Mar: 71563230; Apr: 38024167; May: 218868793.67; Jun: 0
1+11 | Jan: 43183088.36; Feb: 70003546; Mar: 69785076; Apr: 35627875; May: 218599585.36; Jun: 0
2023 Baseline | Jan: 37131137; Feb: 70967999; Mar: 75274449; Apr: 35081190; May: 218454775; Jun: 0
2022 Final EAC | Jan: 29326822.48; Feb: 45282281.23; Mar: 68857845; Apr: 69253223; May: 212720171.71; Jun: 0
2021 Final EAC | Jan: 19798702.93; Feb: 37918050.86; Mar: 44125156.32; Apr: 52046746.75; May: 153888656.86; Jun: 0
MEXP | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total EAC
2023 EAC | [13 empty] | 0
11+1
10+2
9+3
8+4
7+5
6+6
5+7
4+8 | 1399460 | 1262687 | 4359012 | 3874394 | 6138754 | 6084567 | 5264034 | 4790106 | 5054232 | 5285909 | 3484406 | 2519344 | 49516905.1
3+9 | 1407043.76 | 1256686.72 | 4257972.32 | 4579773 | 7305562 | 4898296 | 5439352 | 5133621 | 5085497 | 4264849 | 3270951 | 2509956 | 49409559.8 | $6M Topside Adjustments Entered as Follows
2+10 | 1407043.76 | 1256686.72 | 2888546 | 5258846 | 7454576 | 5764082 | 6079437 | 5930455 | 6093906 | 4593578 | 3474768 | 2534111 | 52736035.48 | - $3.7M in Station/Terminal
1+11 | 1407326.94 | 2056583 | 4151649 | 5201294 | 6165938 | 6433901 | 5754893 | 5058435 | 5994572 | 4640927 | 3604934 | 2711448 | 53181900.94 | - $1.7M in Tank Integrity
2023 Baseline | 2379500 | 2147164 | 3599037 | 5586409 | 5458900 | 5860352 | 6316542 | 6263361 | 5793462 | 3836408 | 3365213 | 2384511 | 52990859 | - $600K in Pipeline Integrity
2022 Final EAC | 1319518.78 | 2763747.76 | 3811708.6 | 2728843.46 | 4494817.79 | 4665440 | 4330702 | 5172913 | 5607376 | 3778791 | 5703493 | 7153440 | 51530791.39
2021 Final EAC | 1653647.6 | 2807732.85 | 5009746.06 | 4861856.12 | 4408639.06 | 2993334.51 | 2429787.12 | 2107596.24 | 2905301.69 | 3891736.82 | 4799783.49 | 5094150 | 42963311.56
MEXP | Jan: Q1; Feb: Q2; Mar: Q3; Apr: Q4; May: Total EAC; Jun: Check
2023 EAC | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 0
11+1 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 0
10+2 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 0
9+3 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 0
8+4 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 0
7+5 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 0
6+6 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 0
5+7 | Jan: 0; Feb: 0; Mar: 0; Apr: 0; May: 0; Jun: 0
4+8 | Jan: 7021159; Feb: 16097715; Mar: 15108372; Apr: 11289659; May: 49516905; Jun: -0.1
3+9 | Jan: 6921702.8; Feb: 16783631; Mar: 15658470; Apr: 10045756; May: 49409559.8; Jun: 0
2+10 | Jan: 5552276.48; Feb: 18477504; Mar: 18103798; Apr: 10602457; May: 52736035.48; Jun: 0 |  | `
1+11 | Jan: 7615558.94; Feb: 17801133; Mar: 16807900; Apr: 10957309; May: 53181900.94; Jun: 0
2023 Baseline | Jan: 8125701; Feb: 16905661; Mar: 18373365; Apr: 9586132; May: 52990859; Jun: 0
2022 Final EAC | Jan: 7894975.14; Feb: 11889101.25; Mar: 15110991; Apr: 16635724; May: 51530791.39; Jun: 0
2021 Final EAC | Jan: 9471126.51; Feb: 12263829.69; Mar: 7442685.05; Apr: 13785670.31; May: 42963311.56; Jun: 0

## Pipeline Integrity
Row Labels | Sum of CY Budget Year Amount | Sum of CY Tot EAC | Sum of CY 01 Jan Act | Sum of CY 02 Feb Act | Sum of CY 03 Mar Act | Sum of CY 04 Apr Act | Sum of CY 05 May Fcst | Sum of CY 06 Jun Fcst | Sum of CY 07 Jul Fcst | Sum of CY 08 Aug Fcst | Sum of CY 09 Sep Fcst | Sum of CY 10 Oct Fcst | Sum of CY 11 Nov Fcst | Sum of CY 12 Dec Fcst
Exposed Pipe Evaluation & Remediation | 500000 | 519758.31 | 62601.94 | 13927.06 | 21737.31 | -2008 | 20000 | 35000 | 45000 | 82500 | 121000 | 50000 | 40000 | 30000
Exposure Remediation | 13950000 | 14784369.43 | 52514.21 | 115237.55 | 221663.32 | 291953.35 | 855000 | 2284000 | 1504000 | 1425000 | 1710000 | 5225000 | 500000 | 600001
Pipeline Digs | 63909001 | 67242729.9 | 3729301.49 | 4657867.83 | 5533189.66 | 4720693.92 | 4287871 | 5895801 | 7574000 | 9295000 | 6716000 | 5506000 | 5051000 | 4276005
Pipeline Replacements | 3500000 | 3747981.24 | 183273.02 | 113230 | 328536.94 | 185440.28 | 1282000 | 920000 | 700000 | 30500 | 5000 |  |  | 1
Shallow Pipe Remediation | 3700000 | 2436416.86 | 77031.37 | 19604.82 | 51332.4 | 28448.27 | 10000 | 1000000 | 1250000
Grand Total | 85559001 | 88731255.74 | 4104722.03 | 4919867.26 | 6156459.63 | 5224527.82 | 6454871 | 10134801 | 11073000 | 10833000 | 8552000 | 10781000 | 5591000 | 4906007
IT Program | YTD Actuals | Jan Actuals | Feb Actuals | Mar Actuals | Sum of CY 04 Apr Act
Exposed Pipe Evaluation & Remediation | 96258.31 | 62601.94 | 13927.06 | 21737.31 | -2008
Exposure Remediation | 681368.43 | 52514.21 | 115237.55 | 221663.32 | 291953.35
Pipeline Digs | 18564548.81 | 3729301.49 | 4657786.83 | 5456766.57 | 4720693.92
Pipeline Replacements | 810480.24 | 183273.02 | 113230 | 328536.94 | 185440.28
Shallow Pipe Remediation | 176416.86 | 77031.37 | 19604.82 | 51332.4 | 28448.27
Grand Total | 20329072.65 | 4104722.03 | 4919786.26 | 6080036.54 | 5224527.82

## IT Program
Row Labels | Sum of CY Budget Year Amount | Sum of CY Tot EAC | Sum of CY 01 Jan Act | Sum of CY 02 Feb Act | Sum of CY 03 Mar Act | Sum of CY 04 Apr Fcst | Sum of CY 05 May Fcst | Sum of CY 06 Jun Fcst | Sum of CY 07 Jul Fcst | Sum of CY 08 Aug Fcst | Sum of CY 09 Sep Fcst | Sum of CY 10 Oct Fcst | Sum of CY 11 Nov Fcst | Sum of CY 12 Dec Fcst
Enterprise Business Apps | 3259578 | 3354402.26 | 204291.59 | 269803.28 | 521488.72 | 545521 | 450884 | 382576 | 320676 | 258975 | 106500 | 140001 | 130000 | 124999
Infrastructure & IT Ops | 6589500 | 6446408.95 | 356951.62 | 171737.93 | 538967.02 | 151356 | 244776 | 1203289 | 1111803 | 411683 | 388166 | 490000 | 381666 | 1009999
OT & IT Field Ops | 8781819 | 8886246.41 | 280600.18 | 199320.07 | 503622.27 | 595477 | 641780 | 1002890 | 933881 | 1051002 | 1055886 | 1008372 | 839991 | 720053
Grand Total | 18630897 | 18687057.62 | 841843.39 | 640861.28 | 1564078.01 | 1292354 | 1337440 | 2588755 | 2366360 | 1721660 | 1550552 | 1638373 | 1351657 | 1855051
IT Program | YTD Actuals | Jan Actuals | Feb Actuals | Mar Actuals | Apr Actuals
Enterprise Business Apps | 1541104.59 | 204291.59 | 269803.28 | 521488.72 | 545521
Infrastructure & IT Ops | 1219012.57 | 356951.62 | 171737.93 | 538967.02 | 151356
OT & IT Field Ops | 1579019.52 | 280600.18 | 199320.07 | 503622.27 | 595477
Grand Total | 4610860.69 | 841843.39 | 640861.28 | 1564078.01 | 1564078.01
Row Labels | Sum of CY Tot EAC | Sum of CY Budget Year Amount | Sum of EAC vs Budget | Sum of CY 04 Apr Act | Sum of CY 04 Apr Fcst (asOf Cut-off) | Sum of CY 04 Apr Var Value
OT & IT Field Ops | 8886246.41 | 8781819 | 104427.41 | 648848.89 | 595477 | 53373
Enterprise Business Apps | 3354402.26 | 3259578 | 94824.26 | 444207.67 | 545521 | -101313
Infrastructure & IT Ops | 6446408.95 | 6589500 | -143091.05 | 137370.38 | 151356 | -13986
Grand Total | 18687057.62 | 18630897 | 56160.62 | 1230426.94 | 1292354 | -61926

## Reason Code Summary
Project Type | MCAP | Project Type | MEXP
Row Labels | Sum of CY 04 Apr Var Value | Row Labels | Sum of CY 04 Apr Var Value
(blank) | 1303608 | (blank) | -368501
WorkAhead of Schedule | 1108946 | Forecasting | -283990
Other | 672780 | Buckeye/Customer Schedule | -206607
Engineering or Scope Change | 233030 | Contractor/Vendor Issue | -129060
Supply Chain | 33494 | Other | -35755
Savings from AFE Estimate | -51417 | Savings from AFE Estimate | -27766
Forecasting | -104340 | Weather | -10000
Weather | -109657 | Engineering or Scope Change | 34204
Buckeye/Customer Schedule | -358533 | WorkAhead of Schedule | 247403
Contractor/Vendor Issue | -701029 | Grand Total | -780072
Grand Total | 2026882
Row Labels | Sum of CY 04 Apr Var Value | Row Labels | Sum of CY 04 Apr Var Value
(blank) | 1303608 | (blank) | -368501
WorkAhead of Schedule | 1108946 | Forecasting | -283990
Other | 672780 | Buckeye/Customer Schedule | -206607
Engineering or Scope Change | 233030 | Contractor/Vendor Issue | -129060
Supply Chain | 33494 | Other | -35755
Savings from AFE Estimate | -51417 | Savings from AFE Estimate | -27766
Forecasting | -104340 | Weather | -10000
Weather | -109657 | Engineering or Scope Change | 34204
Buckeye/Customer Schedule | -358533 | WorkAhead of Schedule | 247403
Contractor/Vendor Issue | -701029 | Grand Total | -780072
Grand Total | 2026882

## Monthly Variance
April Variance vs 3+9
Row Labels | Sum of CY 04 Apr Act | Sum of CY 04 Apr Fcst (asOf Cut-off) | Sum of CY 04 Apr Var Value
MCAP | 16293113.64 | 14266241 | 2026882
West | 4591723.33 | 3282741 | 1308984
South | 3478268.04 | 2995181 | 483090
East | 6950876.55 | 6495403 | 455477
Corporate - Pipes and Terminals | 124014.54 | 200000 | -75985
Corporate | 1148231.18 | 1292916 | -144684
MEXP | 3874394.42 | 4654466 | -780072
West | 1096178.71 | 1076843 | 19338
Corporate | -600 | 15000 | -15600
East | 2081223.79 | 2217773 | -136552
Corporate - Pipes and Terminals | 321512.21 | 487057 | -165544
South | 376079.71 | 857793 | -481714
Grand Total | 20167508.06 | 18920707 | 1246810

## Data Set
Items | Type | Status | Project Type | Project # | Governance Framework | Project WO #s | Project Manager | PM Region | Project Status | Budget Type | Program | CY Actuals | CY Rem Fcst | Remaining Contingency | CY Tot EAC | CY Tot Fcst 3+9 Baseline | CY Tot EAC vs 3+9 Base Value | CY Tot EAC vs 3+9 Base Indicator | CY Budget Year Amount | CY Budget Adjustment | CY Bud incl Adj | CY Variance with Adjustments Value | CY Variance with Adjustments Indicator | Variance Explanation AFE vs CY Budget | Full or Phase 1 AFE | Phase 2 AFE | Supplemental AFE Amount | Total Approved AFE | AFE Stage | Total Requested AFE | Inception to Date Actuals | Project Rem Fcst | Project EAC | Supplemental AFE Required? Value | Supplemental AFE Required? Indicator | Cash Flow Start (Fcst) | Full or Phase 1 AFE Approved Date | Full or Phase 1 AFE Approved Date P/D | Baseline Operational Date | Operational Date | AFE Past Due Days Value | AFE Past Due Days Indicator | CY 01 Jan Act | CY 02 Feb Act | CY 03 Mar Act | CY 04 Apr Act | CY 04 Apr Fcst | CY 04 Apr Fcst (asOf Cut-off) | CY 04 Apr Var Value | CY 04 Apr Var Indicator | IT - Accruals | Monthly Variance Explanation | CY 05 May Fcst | CY 06 Jun Fcst | CY 07 Jul Fcst | CY 08 Aug Fcst | CY 09 Sep Fcst | CY 10 Oct Fcst | CY 11 Nov Fcst | CY 12 Dec Fcst | Remaining Contingency | Project Status Notes | Project Status Notes Updated On | PCA | PM Designate | PMO-Region | PMO-Division | Financial Reporting Category 2022 | Financial Reporting Category 2022 Override | PMO-Asset Team | PMO-Location Business Unit | Parent Project Number | CY Q1 EAC | CY Q2 EAC | CY Q3 EAC | CY Q4 EAC | CY-1 Tot Act | CY+1 Tot Fcst | Program Manager | Project Sponsor | WS Drawdown Class | JV SubProgram | IT Count | OPPM Project Item ID | RCAP Financial Model | Created By | Parent / Child Value | Parent / Child Indicator | Creation Date | Maintenance Reporting Categories
BNTNX 85East Hot Oil Heater Refurbishment | Item | Open | MCAP | BNTNX00M2305 | Maintenance Framework | 2119809 |  |  | 2. Pending AFE |  | Boilers |  | 75000 |  | 75000 | 75000 | 0 | Green |  |  |  | 75000 | [6 empty] | Interim |  |  | 375000 | 375000 | No | Green | 2023-10-01 |  |  |  | 2024-03-15 | [17 empty] | 75000 | [7 empty] | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNX - New Haven 85 East Terminal |  |  | 0 |  | 75000 |  | 300000 | Stine, Carlton |  |  |  | 1 | 46876 |  | StaplesLassiter, Gina | Independent | Aqua | 2023-04-04
BTXPP - 100 PSV 1901 Replacement | Item | Open | MCAP | BTXPP00M2307 | Maintenance Framework | 2119881 | Burke, Joshua |  | 2. Pending AFE |  | South |  | 106573 |  | 106573 |  | 106573 | Red |  |  |  | 106573 | [6 empty] | Interim |  |  | 106573 | 106573 | No | Green | 2023-05-01 |  |  |  | 2023-05-24 | [12 empty] | 106573 | [8 empty] | 5.3.23 JHB - HPC selected for hot tap/isolation scope. PSV to be ordered and arrive in ~1 week. Preparing hot tap books for stakeholder review. Target execution the week of 5/15. FC adjusted up to AFE amount. | 2023-05-03 |  |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 106573 |  |  |  |  | Johnson, AJ |  |  |  | 1 | 46981 |  | Guest, ProSight | Independent | Aqua | 2023-04-24
Muncie Block Valve Pressure Transmitter Install | Item | Candidate | MCAP |  | Maintenance Framework |  | Smith, Kyle |  | 1. Proposed |  | West |  | 20000 |  | 20000 |  | 20000 | Red |  |  |  | 20000 | [9 empty] | 20000 | 20000 | No | Green | 2023-07-01 |  |  |  | 1900-07-31 | [14 empty] | 20000 | [10 empty] | West | Pipelines and Terminals | Operating Infrastructure |  | Huntington | BETMN - BET MUNCIE TERMINAL |  |  | 0 | 20000 |  |  |  | Gardner, Travis |  |  |  | 1 | 47021 |  | Guest, ProSight | Independent | Aqua | 2023-05-02
Raritan Bay Decommissioning 2023 | Item | Open | MCAP | BFRQF00M2302 | Maintenance Framework | 2120028 | Bodner, Jordan |  | 2. Pending AFE |  | East |  | 250000 |  | 250000 |  | 250000 | Red |  |  |  | 250000 | [6 empty] | Interim |  |  | 250000 | 250000 | No | Green | 2023-05-01 |  |  |  | 2023-08-31 | [12 empty] | 100000 | 150000 | [9 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BFRQF - BFR RARITAN BAY TERMINAL |  |  | 250000 |  |  |  |  | Orischak, Bob | Orischak, Bob |  |  | 1 | 47005 |  | Bodner, Jordan | Independent | Aqua | 2023-05-01
165/166L MP 13.7 Exposure / Shallow Pipe Remediation | Item | Open | MEXP | WO165EFE2301 | Project Framework | 2096636 | Hurley, Brian | Asset Integrity | 3. Active | Drawdown | Exposed Pipe Evaluation & Remediation |  | 5000 |  | 5000 | 5000 | 0 | Green |  |  |  | 5000 |  |  | 5000 |  |  | 5000 | Full | 5000 |  | 5000 | 5000 | No | Green | 2023-05-01 | 2023-03-31 | 2023-03-31 | 2023-06-30 | 2023-06-30 | [6 empty] | 5000 | 5000 | -5000 | Red |  | Forecasting | 5000 | [10 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | St. Louis | WO165EF - WOOD RIVER TO EFFINGHAM |  |  | 5000 |  |  |  |  | Hurley, Brian | Bartal, Nick | N/A |  | 1 | 46855 |  | Hurley, Brian | JDE Child | Burnt Orange | 2023-03-29
2022 BUCKEYE ENERGY SERVICES EXTERNAL INSPECTIONS | Item | Open | MEXP | 6710000E2201 | Exempt | 1916327 | Cole, Caitlyn | Asset Integrity | 6. Operational | Defined | Tanks | 1640 |  |  | 1640 | 1640 | 0 | Green |  |  |  | 1640 |  | Other | 15000 |  |  | 15000 | Full | 15000 | 10725 |  | 10725 | No | Green | 2022-01-01 | 2021-12-13 | 2021-12-13 | 2022-12-31 | 2022-08-02 |  |  |  | 1640 | [17 empty] | 8/2/22 CNC- inspections complete. Project operational. 6/29/22 CNC- all inspections complete and invoiced. 3/2/22 CNC- BESZM and BESZG inspections complete and invoiced. 2 remaining at BESRG and 1 BESAM in June. | 2022-08-02 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Tank Integrity |  | Corporate | Corporate |  | 1640 | 0 |  |  | 9085 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 42565 |  | Meitzler, Antoinette | Independent | Aqua | 2021-12-03 | Int - Tanks
2022 BUCKEYE PERTH AMBOY TERMINAL EXTERNAL INSPECTIONS | Item | Open | MEXP | BPTPC00E2201 | Exempt | 1916330 | Cole, Caitlyn | Asset Integrity | 6. Operational | Defined | Tanks | 0 |  |  | 0 | 0 | 0 | Green |  |  |  | 0 |  | Other | 39000 |  | 4570 | 43570 | Full | 43570 | 43885 |  | 43885 | No | Green | 2022-01-01 | 2021-12-13 | 2021-12-13 | 2022-12-31 | 2022-12-31 |  |  | 3060 | -3060 | [17 empty] | 3/3/23 CNC - all inspections and invoices completed. Cost savings. 1/5/2023 CNC- all inspections completed. 10/4/22 CNC - 13 inspections remain. 8/2/22 CNC- 22 remaining inspections 5/18/22 CNC- 22 remaining inspections | 2023-03-03 | Schultz, Amy |  | East | Pipelines and Terminals | Tank Integrity |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 0 | 0 |  |  | 43885 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 42568 |  | Meitzler, Antoinette | Independent | Aqua | 2021-12-03 | Int - Tanks
2022 BUCKEYE PIPE LINE CO EXTERNAL INSPECTIONS | Item | Open | MEXP | 1000000E2201 | Exempt | 1916338 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tanks | 2000 |  |  | 2000 | 2000 | 0 | Green |  |  |  | 2000 |  | Other | 62000 |  |  | 62000 | Full | 62000 | 56770 |  | 56770 | No | Green | 2022-04-01 | 2021-12-13 | 2021-12-13 | 2022-12-31 | 2022-12-31 |  |  |  |  | 2000 | [16 empty] | 4/5/23 CNC - ready to close 1/5/2023 - all inspections complete 11/30/22 CNC - 3 inspections remain, pushing out November $1500 forecast 10/4/22 CNC - 5 inspections remain. 8/2/22 CNC 33 remaining inspections 5/18/22 CNC- 43 remaining inspections | 2023-04-05 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Tank Integrity |  | Corporate | Corporate |  | 2000 | 0 |  |  | 54770 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 42569 |  | Meitzler, Antoinette | Independent | Aqua | 2021-12-03 | Int - Tanks
2022 BUCKEYE PT TERMINALS EXTERNAL INSPECTIONS | Item | Open | MEXP | 1760000E2201 | Exempt | 1916341 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tanks | 15100 |  |  | 15100 | 15100 | 0 | Green |  |  |  | 15100 |  | Other | 24000 |  | 18400 | 42400 | Full | 42400 | 43400 |  | 43400 | No | Green | 2022-04-01 | 2021-12-13 | 2021-12-13 | 2022-12-31 | 2022-12-31 |  |  | 14100 | 0 | 1000 | [16 empty] | 4/5/23 CNC - ready to close 11/30/2022 CNC-pushing out November forecast of $1500 10/4/22 CNC - 11 inspections remaining. 8/2/22 CNC- 22 remaining inspections 5/18/22 CNC- 22 remaining inspections | 2023-04-05 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Tank Integrity |  | Corporate | Corporate |  | 15100 | 0 |  |  | 28300 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 42574 |  | Meitzler, Antoinette | Independent | Aqua | 2021-12-03 | Int - Tanks
2022 BUCKEYE TERMINALS EXTERNAL INSPECTIONS | Item | Open | MEXP | 1550000E2201 | Exempt | 1916342 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tanks | 3090 |  |  | 3090 | 3090 | 0 | Green |  |  |  | 3090 |  | Other | 289000 |  | 55000 | 344000 | Supplemental | 344000 | 352677 |  | 352677 | No | Green | 2022-01-01 | 2021-12-13 | 2021-12-13 |  | 2022-12-31 |  |  | 1790 | -1800 | 3100 | [16 empty] | 4/5/23 CNC - ready to close 1/5/2023 CNC - all inspections complete, awaiting final invoices 3/2/22 CNC- Richmond Terminal inspections complete and invoiced. | 2023-04-05 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Tank Integrity |  | Corporate | Corporate |  | 3090 | 0 |  |  | 349587 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 42577 |  | Meitzler, Antoinette | Independent | Aqua | 2021-12-03 | Int - Tanks
2022 CLOSE INTERVAL SURVEY OF BUCKEYE PIPE LINE CO. L.P. | Item | Open | MEXP | 1000000E2202 | Exempt | 1956921 | Miller, Sean | Asset Integrity | 6. Operational | Drawdown | Cathodic Protection | 4958 |  |  | 4958 |  | 4958 | Red |  |  |  | 4958 |  |  | 260000 |  |  | 260000 | Full | 260000 | 259066 |  | 259066 | No | Green | 2022-04-01 | 2022-03-24 | 2022-03-24 | 2022-12-31 | 2022-12-31 | [5 empty] | 4958 |  |  | 4958 | Red | [11 empty] | 12/2/22 - Issues finding 3rd party inspectors. Work pushed into December per Sean Miller (AS) 11/2/22 - Missed forecasting per Sean Miller (AS) | 2022-12-02 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corrosion |  | Corporate | Corporate |  |  | 4958 |  |  | 254108 |  | Geib, Rob | Shook, Mark B. | N/A |  | 1 | 43250 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-03-24 | Int - Planned Corr & FI
2022 CLOSE INTERVAL SURVEY OF BUCKEYE PIPE LINE TRANSPORTATION | Item | Open | MEXP | 1220000E2202 | Exempt | 1956969 | Miller, Sean | Asset Integrity | 6. Operational | Drawdown | Cathodic Protection | 20368 |  |  | 20367.5 | 20368 | 0 | Green |  |  |  | 20368 |  |  | 104000 |  |  | 104000 | Full | 104000 | 137773 |  | 137773 | No | Green | 2022-07-01 | 2022-03-24 | 2022-03-24 | 2022-12-31 | 2022-12-31 |  |  | 20367.5 | [18 empty] | 1/4/23 - Invoice submitted by vendor after deadline (AS) 12/2/22 - Issues finding 3rd party inspectors. Work pushed into December per Sean Miller (AS) 11/2/22 - Missed Forecasting per Sean Miller (AS) | 2023-01-04 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corrosion |  | Corporate | Corporate |  | 20368 | 0 |  |  | 117406 |  | Geib, Rob | Shook, Mark B. | N/A |  | 1 | 43257 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-03-24 | Int - Planned Corr & FI
2022 CLOSE INTERVAL SURVEY OF BUCKEYE TERMINALS LLC | Item | Open | MEXP | 1348250E2229 | Exempt | 1956965 | Miller, Sean | Asset Integrity | 6. Operational | Drawdown | Cathodic Protection | 650 |  |  | 650 | 650 | 0 | Green |  |  |  | 650 |  |  | 8800 |  |  | 8800 | Full | 8800 | 9222 |  | 9222 | No | Green | 2022-08-01 | 2022-03-24 | 2022-03-24 | 2022-12-31 | 2022-12-31 |  |  | 650 | [20 empty] | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corrosion |  | Corporate | Corporate |  | 650 | 0 |  |  | 8572 |  | Geib, Rob | Shook, Mark B. | N/A |  | 1 | 43256 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-03-24 | Int - Planned Corr & FI
2022 Magellan Acquisition Tanks (BSE Terminals) Tank External API 653 Inspections | Item | Open | MEXP | 1790000E2202 | Maintenance Framework | 1989643 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tanks | 16397 |  |  | 16396.6 | 16397 | 0 | Green |  |  |  | 16397 |  |  | 50000 |  |  | 50000 | Full | 50000 | 42144 |  | 42144 | No | Green | 2022-08-01 | 2022-06-06 | 2022-06-06 | 2022-12-31 | 2022-12-31 |  |  | 1640 | 14756.6 | [17 empty] | 4/5/23 CNC - ready to close 12/2/22-CES- Project under budget due to validation that external inspections were completed prior to acquisition. 11/30/22 CNC - 1 inspection remaining, pushing out November $1500 forecast 11/3/22 CNC - 1 inspection remaining. 8/2/22 CNC - Tanks acquired July, Inserv to inspect | 2023-04-05 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Tank Integrity |  | Southeast Terminals |  |  | 16397 | 0 |  |  | 25748 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 43533 |  | Stine, Carlton | Independent | Aqua | 2022-04-25 | Int - Tanks
2022 PORT READING TERMINAL EXTERNAL INSPECTIONS | Item | Open | MEXP | BPRPR00E2201 | Exempt | 1916334 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tanks | 0 |  |  | 0 | 0 | 0 | Green |  |  |  | 0 |  | Other | 26000 |  | 9065 | 35065 | Full | 35065 | 30450 |  | 30450 | No | Green | 2022-04-01 | 2021-12-13 | 2021-12-13 | 2022-12-31 | 2022-12-31 |  |  | 4615 | -4615 | [17 empty] | 4/5/23 CNC - ready to close 3/3/23 CNC - all inspections and invoices complete. Cost savings. 1/5/2023 CNC - all inspections complete, waiting on final invoice 10/4/22 CNC - 10 inspections remaining. 8/2/22 CNC- 2 inspections in August and 10 in 2023 6/8/22 CNC- 2 inspections in August and 10 in 2023 5/18/22 CNC- 12 remaining inspections | 2023-04-05 | Schultz, Amy |  | East | Pipelines and Terminals | Tank Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 0 | 0 |  |  | 30450 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 42573 |  | Meitzler, Antoinette | Independent | Aqua | 2021-12-03 | Int - Tanks
2022 Seam Susceptibility and Fatigue | Item | Open | MEXP | 1348250E2224 | Exempt | 1916958 | Hurley, Brian | Asset Integrity | 6. Operational | Drawdown | Pipeline Digs | 103 |  |  | 103 | 103 | 0 | Green |  |  |  | 103 |  |  | 200000 |  |  | 200000 | Full | 200000 | 214074 |  | 214074 | No | Green | 2022-02-01 | 2021-12-22 | 2021-12-22 | 2022-12-31 | 2022-12-31 |  |  | 103 | [18 empty] | 12/9/22 - Work in process, will be accrued in 2022. 10/7/22 - reforecast variance, awaiting invoices. 9/12/22 - reforecast variance, awaiting invoices. 7/12/22 - Additional scope completed in June. 6/8/22 - reduced forecast to offset May variance. 5/9/22 - Reforecast April variance. 4/8/22 - no change. 3/8/22 - Reforecast Feb variance later in year | 2022-12-09 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Pipeline Integrity |  | Corporate | Corporate |  | 103 | 0 |  |  | 213971 |  | Bartal, Nick | Shook, Mark B. |  |  | 1 | 40982 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
2022 TEXAS HUB EXTERNAL INSPECTIONS | Item | Open | MEXP | BTXHF00E2201 | Exempt | 1916337 | Cole, Caitlyn | Asset Integrity | 6. Operational | Unplanned | Tanks | 0 |  |  | 0 | 0 | 0 | Green |  |  |  | 0 |  |  | 2000 |  | 890 | 5390 | Full | 5390 | 2890 |  | 2890 | No | Green | 2022-03-01 | 2021-12-13 | 2021-12-13 |  | 2022-08-02 |  |  | 2500 | -2500 | [17 empty] | 4/5/23 CNC - ready to close 8/2/22 CNC- inspections complete. Project operational. 5/18/22 CNC- all inspections complete | 2023-04-05 | Schultz, Amy |  | South | Pipelines and Terminals | Tank Integrity |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 0 | 0 |  |  | 2890 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 42578 |  | Meitzler, Antoinette | Independent | Aqua | 2021-12-03 | Int - Tanks
2023 - East Region - Navigable Waterway Inspections | Item | Open | MEXP | 1348250E2321 | Maintenance Framework | 2095176 | Hurley, Brian | Asset Integrity | 3. Active | Defined | Navigable Waterway Inspection | 114320 | 5000 |  | 119320 | 138500 | -19180 | Red | 138500 |  | 138500 | -19180 |  |  | 138500 |  |  | 138500 | Full | 138500 | 114320 | 5000 | 119320 | No | Green | 2023-04-01 | 2023-03-16 | 2023-03-16 | 2023-12-31 | 2023-06-30 | [5 empty] | 114320 | 118500 | 118500 | -4180 | Yellow |  |  |  | 5000 | [7 empty] | 5/9/23 - One remaining east region waterway inspection. 4/11/23 - Work started 4/10 and should wrap up first week of May. | 2023-05-09 | Schultz, Amy |  | East | Pipelines and Terminals | Pipeline Integrity |  | Corporate | Corporate |  |  | 119320 |  |  |  |  | Bassani, Joel | Bartal, Nick |  |  | 1 | 44570 |  | Guest, ProSight | Independent | Aqua | 2022-08-12 | Int - Assessments
2023 - East Region - Risk Based Waterway Inspections | Item | Candidate | MEXP |  | Maintenance Framework |  | Hurley, Brian | Asset Integrity | 1. Proposed |  | Navigable Waterway Inspection |  | 19800 |  | 19800 | 19800 | 0 | Green | 19800 |  | 19800 | 0 | [9 empty] | 19800 | 19800 | No | Green | 2023-10-01 |  |  |  | 2023-06-30 | [17 empty] | 19800 | [5 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Pipeline Integrity |  | Corporate | Corporate |  |  | 0 |  | 19800 |  |  | Bassani, Joel |  |  |  | 1 | 44574 |  | Guest, ProSight | Independent | Aqua | 2022-08-12 | Int - Assessments
2023 - Waterway Evaluations of 2023 Inspections | Item | Candidate | MEXP |  | Maintenance Framework |  | Hurley, Brian | Asset Integrity | 1. Proposed |  | Navigable Waterway Inspection |  | 75000 |  | 75000 | 75000 | 0 | Green | 75000 |  | 75000 | 0 | [9 empty] | 75000 | 75000 | No | Green | 2023-11-01 |  |  |  | 2023-11-30 | [18 empty] | 75000 |  |  |  |  | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Pipeline Integrity |  | Corporate | Corporate |  |  | 0 |  | 75000 |  |  | Bassani, Joel |  |  |  | 1 | 44578 |  | Guest, ProSight | Independent | Aqua | 2022-08-12 | Int - Assessments
2023 - West - Navigable Waterway Inspections | Item | Open | MEXP | 1348250E2320 | Exempt | 2095179 | Hurley, Brian | Asset Integrity | 3. Active | Defined | Navigable Waterway Inspection | 38710 | 6600 |  | 45310 | 28600 | 16710 | Red | 28600 |  | 28600 | 16710 |  |  | 28600 |  |  | 28600 | Full | 28600 | 38710 | 6600 | 45310 | Yes | Red | 2023-04-01 | 2023-03-16 | 2023-03-16 | 2023-12-31 | 2023-06-30 | [5 empty] | 38710 | 22000 | 22000 | 16710 | Red |  | Engineering or Scope Change | 6600 | [8 empty] | 5/9/23 - Additional crossings inspected at Maumee River (7 total 3 were budgeted) | 2023-05-09 | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | West Region Work Team | 20185 - WEST DISTRICT WORK TEAM |  |  | 45310 |  |  |  |  | Bassani, Joel | Bartal, Nick |  |  | 1 | 44569 |  | Guest, ProSight | Independent | Aqua | 2022-08-12 | Int - Assessments
2023 - West Region - Risk Based Waterway Inspections | Item | Candidate | MEXP |  | Exempt |  | Hurley, Brian | Asset Integrity | 2. Pending AFE |  | Navigable Waterway Inspection |  | 35200 |  | 35200 | 35200 | 0 | Green | 35200 |  | 35200 | 0 | [9 empty] | 35200 | 35200 | No | Green | 2023-10-01 |  |  |  | 2023-06-30 | [17 empty] | 35200 | [5 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | Corporate | Corporate |  |  | 0 |  | 35200 |  |  | Bassani, Joel |  |  |  | 1 | 44573 |  | Guest, ProSight | Independent | Aqua | 2022-08-12 | Int - Assessments
2023 850 On TP Coupon Test Stations Allocation | Item | Candidate | MCAP |  | Maintenance Framework |  | Miller, Sean | Asset Integrity | 1. Proposed |  | Cathodic Protection |  | 75000 |  | 75000 | 75000 | 0 | Green | 75000 |  | 75000 | 0 | [9 empty] | 75000 | 75000 | No | Green | 2023-06-01 |  |  |  | 2023-03-31 | [13 empty] | 75000 | [8 empty] | 2022-10-12 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Integrity |  | Corporate | Corporate |  |  | 75000 |  |  |  |  | Geib, Rob |  |  |  | 1 | 45229 |  | Guest, ProSight | Independent | Aqua | 2022-08-23 | Int - Planned Corr & FI
2023 Annual Criteria Digs - ZG701JC | Item | Open | MCAP |  | Maintenance Framework |  | Gebert, Clint | Asset Integrity | 1. Proposed |  | Pipeline Digs |  | 900000 |  | 900000 | 900000 | 0 | Green | 900000 |  | 900000 | 0 | [9 empty] | 900000 | 900000 | No | Green | 2023-08-01 |  |  |  | 2023-07-31 | [12 empty] | 0 | 0 | 0 | 300000 | 300000 | 300000 | [7 empty] | East | Pipelines and Terminals | Integrity |  | Corporate | Corporate |  |  | 0 | 600000 | 300000 |  |  | Bartal, Nick |  |  |  | 1 | 44925 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int- Planned Digs
2023 Annual Criteria Digs - ZG714SN | Item | Open | MCAP |  | Maintenance Framework |  | Keppel, Nicholas | Asset Integrity | 1. Proposed |  | Pipeline Digs |  | 375000 |  | 375000 | 375000 | 0 | Green | 375000 |  | 375000 | 0 | [9 empty] | 375000 | 375000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 100000 | 275000 | [9 empty] | East | Pipelines and Terminals | Integrity |  | Corporate | Corporate |  |  | 0 | 375000 |  |  |  | Bartal, Nick |  |  |  | 1 | 44926 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int- Planned Digs
2023 Atmospheric Action Item Re-Inspection Allocation | Item | Open | MEXP | 1348250E2317 | Maintenance Framework |  | Geib, Rob | Asset Integrity | 3. Active | Defined | Atmospheric Corrosion |  | 150000 |  | 150000 | 150000 | 0 | Green | 150000 |  | 150000 | 0 |  |  | 150000 |  |  | 150000 | Full | 150000 |  | 150000 | 150000 | No | Green | 2023-07-01 | 2023-03-13 | 2023-03-13 | 2023-12-31 | 2023-07-31 | [14 empty] | 150000 | [6 empty] | 3/7/23 On Track, Pending AFE | 2023-03-07 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corrosion |  | Corporate | Corporate |  |  | 0 | 150000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45439 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
2023 Bend Strain Analysis | Item | Open | MEXP |  | Maintenance Framework |  | Bartal, Nick | Asset Integrity | 1. Proposed |  | Assessments |  | 60000 |  | 60000 | 60000 | 0 | Green | 75000 |  | 75000 | -15000 | [9 empty] | 60000 | 60000 | No | Green | 2023-05-01 |  |  |  | 2023-12-31 | 8 | Yellow | [10 empty] | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | [5 empty] | Corporate - Pipes and Terminals | Pipelines and Terminals | Pipeline Integrity |  | Corporate | Corporate |  |  | 15000 | 22500 | 22500 |  |  | Bartal, Nick |  |  |  | 1 | 44672 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 Caribbean Terminal Risk Based Inspection (RBI) Project | Item | Open | MEXP | 1348250E2312 | Maintenance Framework | 2076579 | Stine, Carlton | Asset Integrity | 3. Active | Drawdown | Tanks | 50000 | 60000 |  | 110000 | 140000 | -30000 | Red |  |  |  | 110000 |  |  | 175000 |  |  | 175000 | Full | 175000 | 50000 | 60000 | 110000 | No | Green | 2023-02-01 | 2023-01-26 | 2023-01-26 | 2023-09-30 | 2023-09-30 |  |  |  | 20000 | 20000 | 10000 | 10000 | 10000 | 0 | Green |  |  | 20000 | 20000 | 20000 | [6 empty] | 5/3/23-CES-Accrue $50,000 to DNV. Yabucoa is complete and BBH is 50% complete.4/4/23-CES-RE/New accrue $40,000 to DNV. Yabucoa pending results and BBH underway. 3/2/23-CES-Accrue $20,000 to DNV. Project has kicked off and Yabucoa is underway. | 2023-05-03 | Schultz, Amy |  | Corporate | Pipelines and Terminals | Tank Integrity |  | Corporate | Corporate |  | 40000 | 50000 | 20000 |  |  |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 46513 |  | Stine, Carlton | JDE Child | Burnt Orange | 2023-01-23 | Int - Tanks
2023 Cathodic Protection Groundbed & Rectifier Budget Allocation | Item | Candidate | MCAP |  | Maintenance Framework |  | Geib, Rob | Asset Integrity | 2. Pending AFE |  | Cathodic Protection |  | 215000 |  | 215000 | 215000 | 0 | Green | 265000 |  | 265000 | -50000 | [9 empty] | 215000 | 215000 | No | Green | 2023-05-01 |  |  |  | 2023-08-31 | 8 | Yellow |  |  |  |  | 0 | 0 | 0 | Green |  |  | 70000 | 100000 | 45000 | [6 empty] | 3/7/23 - Forecast adjust for March, On Track. 3.2.23.DLC: Removed $50k to fund BBH offshore piping CP upgrades | 2023-03-07 |  |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Integrity |  | Corporate | Corporate |  |  | 170000 | 45000 |  |  |  | Geib, Rob |  |  |  | 1 | 45909 |  | Clark, David | Independent | Aqua | 2022-09-25 | Int - Planned Corr & FI
2023 Cathodic Protection Repair Budget Allocation | Item | Open | MEXP | 1348250E2319 | Maintenance Framework |  | Geib, Rob | Asset Integrity | 3. Active | Defined | Cathodic Protection |  | 229500 |  | 229500 | 229500 | 0 | Green | 280000 |  | 280000 | -50500 |  |  | 280000 |  |  | 280000 | Full | 280000 |  | 229500 | 229500 | No | Green | 2023-05-01 | 2023-03-14 | 2023-03-14 | 2023-12-31 | 2023-08-31 | [12 empty] | 19500 | 70000 | 70000 | 70000 | [5 empty] | 3.30.23 - $17,000 - BETFF00E2302 (AS) 3.17.23 - $15,000 BETHY00E2303 (AS) 3.17.23 - $15,000 - CGNONFSE2301 (AS) 3.17.23 - $3,500 - UT534YTE2302 (AS) 3/7/23 - On Track, Pending AFE | 2023-03-30 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corrosion |  | Corporate | Corporate |  |  | 89500 | 140000 |  |  |  | Geib, Rob | Shook, Mark B. |  |  | 1 | 45908 |  | Clark, David | JDE Parent | Yellow | 2022-09-25 | Int - Planned Corr & FI
2023 Close Interval Survey Budget Allocation | Item | Open | MEXP | 1348250E2314 | Maintenance Framework |  | Miller, Sean | Asset Integrity | 3. Active | Defined | Cathodic Protection |  |  |  | 0 | 37252 | -37252 | Red | 700000 |  | 700000 | -700000 |  |  | 700000 |  |  | 700000 | Full | 700000 |  |  |  | No | Green |  | 2023-02-08 | 2023-02-08 | 2023-03-01 | 2023-10-31 | [21 empty] | 4.25.23.DLC: Removed balance for 1Q23 MEXP reductions...3.9.23 - $65,000 - 1310000E2301 (AS) 3.9.23 - $10,000 - 1560000E2301 (AS) 3.9.23 - $6,748 - 1550000E2304 (AS) 3.9.23 - $290,000 - 1220000E2301 (AS) 3.9.23 - $5,000 - 1200000E2301 (AS) 3.9.23 - $6,000 - 1050000E2301 (AS) 3.9.23 - $225,000 - 1000000E2301(AS) 3.9.23 - $55,000 - 1790000E2301 (AS) | 2023-04-24 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corrosion |  | Corporate | Corporate |  |  | 0 |  |  |  |  | Geib, Rob | Shook, Mark B. |  |  | 1 | 45910 |  | Clark, David | JDE Parent | Yellow | 2022-09-26 | Int - Planned Corr & FI
2023 CLOSE INTERVAL SURVEY OF BUCKEYE PIPE LINE CO LP | Item | Open | MEXP | 1000000E2301 | Maintenance Framework | 2094313 | Miller, Sean | Asset Integrity | 3. Active | Drawdown | Cathodic Protection | 42425 | 172076 |  | 214500.55 | 225000 | -10499 | Yellow |  |  |  | 214501 |  |  | 225000 |  |  | 225000 | Full | 225000 | 42425 | 172076 | 214501 | No | Green | 2023-04-01 | 2023-03-09 | 2023-03-09 | 2023-12-31 | 2023-12-31 | [5 empty] | 42424.55 | 42424 | 42424 | 1 | Yellow |  |  | 37500 | 37500 | 37500 | 37500 | 22076 |  |  |  |  | 4.25.23.DLC: Removed $10,500 for 1Q23 MEXP reductions... | 2023-04-24 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corrosion |  | Corporate | Corporate |  |  | 117425 | 97076 |  |  |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 46735 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-03-09
2023 CLOSE INTERVAL SURVEY OF BUCKEYE PIPE LINE HOLDINGS LP | Item | Open | MEXP | 1050000E2301 | Maintenance Framework | 2094320 | Miller, Sean | Asset Integrity | 3. Active | Drawdown | Cathodic Protection |  | 6000 |  | 6000 | 6000 | 0 | Green |  |  |  | 6000 |  |  | 6000 |  |  | 6000 | Full | 6000 |  | 6000 | 6000 | No | Green | 2023-05-01 | 2023-03-09 | 2023-03-09 | 2023-12-31 | 2023-12-31 | [12 empty] | 2000 | 1000 | 1000 | 1000 | 1000 | [6 empty] | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corrosion |  | Corporate | Corporate |  |  | 3000 | 3000 |  |  |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 46736 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-03-09
2023 CLOSE INTERVAL SURVEY OF BUCKEYE PIPE LINE TRANSPORTATION LLC | Item | Open | MEXP | 1220000E2301 | Maintenance Framework | 2094336 | Miller, Sean | Asset Integrity | 3. Active | Drawdown | Cathodic Protection |  | 277000 |  | 277000 | 290000 | -13000 | Yellow |  |  |  | 277000 |  |  | 290000 |  |  | 290000 | Full | 290000 |  | 277000 | 277000 | No | Green | 2023-05-01 | 2023-03-09 | 2023-03-09 | 2023-12-31 | 2023-12-31 | [12 empty] | 58000 | 58000 | 58000 | 58000 | 45000 |  |  |  |  | 4.25.23.DLC: Removed $13kfor 1Q23 MEXP reductions... | 2023-04-24 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corrosion |  | Corporate | Corporate |  |  | 116000 | 161000 |  |  |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 46738 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-03-09
2023 CLOSE INTERVAL SURVEY OF BUCKEYE SE TERMINALS LP | Item | Open | MEXP | 1790000E2301 | Maintenance Framework | 2094303 | Miller, Sean | Asset Integrity | 3. Active | Drawdown | Cathodic Protection | 32511 | 22488 |  | 54999.46 | 55000 | -1 | Yellow |  |  |  | 54999 |  |  | 15000 |  | 40000 | 55000 | Supplemental | 55000 | 32511 | 22488 | 54999 | No | Green | 2023-04-01 | 2023-03-09 | 2023-03-09 | 2023-12-31 | 2023-12-31 | [5 empty] | 32511.46 | 32512 | 32512 | -1 | Yellow |  |  | 22488 | 0 | 0 | 0 | 0 | [6 empty] | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corrosion |  | Corporate | Corporate |  |  | 54999 | 0 |  |  |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 46734 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-03-09
2023 CLOSE INTERVAL SURVEY OF BUCKEYE TERMINALS LLC | Item | Open | MEXP | 1550000E2304 | Maintenance Framework | 2094338 | Miller, Sean | Asset Integrity | 3. Active | Drawdown | Cathodic Protection | 6748 |  |  | 6747.9 | 6748 | 0 | Yellow |  |  |  | 6748 |  |  | 5000 |  | 1748 | 6748 | Full | 6748 | 6748 |  | 6748 | No | Green | 2023-04-01 | 2023-03-09 | 2023-03-09 | 2023-12-31 | 2023-12-31 | [5 empty] | 6747.9 | 6748 | 6748 | 0 | Yellow | [13 empty] | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corrosion |  | Corporate | Corporate |  |  | 6748 |  |  |  |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 46739 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-03-09
2023 CLOSE INTERVAL SURVEY OF LAUREL PIPELINE CO LP | Item | Open | MEXP | 1310000E2301 | Maintenance Framework | 2094347 | Miller, Sean | Asset Integrity | 3. Active | Drawdown | Cathodic Protection |  | 65000 |  | 65000 | 65000 | 0 | Green |  |  |  | 65000 |  |  | 65000 |  |  | 65000 | Full | 65000 |  | 65000 | 65000 | No | Green | 2023-05-01 | 2023-03-09 | 2023-03-09 | 2023-12-31 | 2023-12-31 | [12 empty] | 13000 | 13000 | 13000 | 13000 | 13000 | [6 empty] | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corrosion |  | Corporate | Corporate |  |  | 26000 | 39000 |  |  |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 46742 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-03-09
2023 CLOSE INTERVAL SURVEY OF NORCO PIPE LINE COMPANY LLC | Item | Open | MEXP | 1560000E2301 | Maintenance Framework | 2094341 | Miller, Sean | Asset Integrity | 3. Active | Drawdown | Cathodic Protection |  | 10000 |  | 10000 | 10000 | 0 | Green |  |  |  | 10000 |  |  | 10000 |  |  | 10000 | Full | 10000 |  | 10000 | 10000 | No | Green | 2023-05-01 | 2023-03-09 | 2023-03-09 | 2023-12-31 | 2023-12-31 | [12 empty] | 2000 | 2000 | 2000 | 2000 | 2000 | [6 empty] | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corrosion |  | Corporate | Corporate |  |  | 4000 | 6000 |  |  |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 46741 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-03-09
2023 CLOSE INTERVAL SURVEY OF WOOD RIVER PIPE LINES LLC | Item | Open | MEXP | 1200000E2301 | Maintenance Framework | 2094324 | Miller, Sean | Asset Integrity | 3. Active | Drawdown | Cathodic Protection |  | 5000 |  | 5000 | 5000 | 0 | Green |  |  |  | 5000 |  |  | 5000 |  |  | 5000 | Full | 5000 |  | 5000 | 5000 | No | Green | 2023-05-01 | 2023-03-09 | 2023-03-09 | 2023-12-31 | 2023-12-31 | [12 empty] | 1000 | 1000 | 1000 | 1000 | 1000 | [6 empty] | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corrosion |  | Corporate | Corporate |  |  | 2000 | 3000 |  |  |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 46737 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-03-09
2023 Drawdown Facility Integrity MCAP | Item | Open | MCAP |  | Maintenance Framework |  | Aiken, Elaine | Asset Integrity | 3. Active |  | Facility Integrity |  | 158000 |  | 158000 | 510000 | -352000 | Red | 660000 | -159000 | 501000 | -343000 | [9 empty] | 158000 | 158000 | No | Green | 2023-06-01 |  |  |  | 2023-10-31 | [13 empty] | 8000 | 50000 | 50000 | 50000 |  |  |  |  | 2023-05-09 - EKA - Reduced forecast by $60k to cover additional funds needed for Taylor East pipe replacement project. Reduced forecast by $192k to cover BBH P4 repairs ($175k) and boiler piping replacement ($17k). 2023-05-08 - EKA - $150k forecast in May is for 2 projects at BBH. 1) P4 piping replacements/repairs 2) Boiler #2 fuel line replacement. Both projects were entered 5/8/2023 and once projects are in OPPM, forecast will be shifted to those projects. 2023-04027 - reduced by $100k to cover additional funds needed for Rensselaer daylighting project. 2023-03-07 - reduced by $150k to fund Port Reading D&K Line replacement project. 3.2.23.DLC: Removed $100k to fund BBH offshore piping CP upgrades | 2023-05-09 |  |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Integrity | Integrity | Corporate | Corporate |  |  | 8000 | 150000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45220 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Int - Planned Corr & FI
2023 Drawdown Facility Integrity MEXP | Item | Open | MEXP | 1348250E2315 | Maintenance Framework |  | Aiken, Elaine | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 600000 |  | 600000 | 600000 | 0 | Green | 600000 |  | 600000 | 0 |  |  | 600000 |  |  | 600000 | Full | 600000 |  | 600000 | 600000 | No | Green | 2023-06-01 | 2023-02-16 | 2023-02-16 | 2023-12-31 | 2023-10-31 | [13 empty] | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 |  |  |  |  | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corrosion | Corrosion | Corporate | Corporate |  |  | 100000 | 300000 | 200000 |  |  | Aiken, Elaine | Shook, Mark B. |  |  | 1 | 45221 |  | Administrator, System | Independent |  | 2022-08-23 | Other Programs
2023 Drawdown Tanks MCAP | Item | Open | MCAP |  | Maintenance Framework |  | Stine, Carlton | Asset Integrity | 1. Proposed |  | Tanks |  | 680000 |  | 680000 | 680000 | 0 | Green | 1000000 |  | 1000000 | -320000 | [9 empty] | 680000 | 680000 | No | Green | 2023-07-01 |  |  |  | 2023-11-30 | [14 empty] | 100000 | 100000 | 100000 | 100000 | 100000 | 180000 |  | 1/25/23-CES-Reducing drawdown by $500,000 and transferring funds over to BTP tanks 1006, 1004, 1002, 3003, and 2004 for roof replacements and repair. 10/21/22-CES-Increasing drawdown after canceling Albany tanks 17 and 18. 9/23/22-CES-Requesting increased drawdown this year due to increased Magellan tank count. | 2023-01-25 |  |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Integrity | Integrity | Corporate | Corporate |  |  | 0 | 300000 | 380000 |  |  | Stine, Carlton |  |  |  | 1 | 45218 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Int - Tanks
2023 ER Corrosion Probe Replacement Allocation | Item | Candidate | MEXP |  | Maintenance Framework |  | Geib, Rob | Asset Integrity | 1. Proposed |  | Cathodic Protection |  | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 | [9 empty] | 30000 | 30000 | No | Green | 2023-09-01 |  |  |  | 2023-09-30 | [16 empty] | 30000 | [8 empty] | Corporate - Pipes and Terminals | Pipelines and Terminals | Corrosion |  | Corporate | Corporate |  |  | 0 | 30000 |  |  |  | Geib, Rob |  |  |  | 1 | 45257 |  | Guest, ProSight | Independent | Aqua | 2022-08-24 | Int - Planned Corr & FI
2023 External API 653 Inspections | Item | Open | MEXP | 1348250E2307 | Maintenance Framework | 2073905 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tanks | 138350 | 595000 |  | 733350 | 739505 | -6155 | Yellow | 690000 |  | 690000 | 43350 |  |  | 690000 |  |  | 690000 | Full | 690000 | 138350 | 595000 | 733350 | No | Green | 2023-01-01 | 2023-01-03 | 2023-01-03 | 2023-12-31 | 2023-10-31 |  |  | 47.08 | 15375 | 54083.31 | 68844.61 | 75000 | 75000 | -6155 | Yellow |  |  | 100000 | 100000 | 100000 | 100000 | 100000 | 70000 | 25000 |  |  | 4/5/23 CNC - inspections 16% complete 3/9/23 CNC - inspections are under way. 20 inspections completed at this time. | 2023-04-05 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Tank Integrity |  | Corporate | Corporate |  | 69505 | 268845 | 300000 | 95000 |  |  | Stine, Carlton | Shook, Mark B. |  |  | 1 | 44758 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
2023 Lab Analysis | Item | Open | MEXP | 1348250E2306 | Maintenance Framework |  | Bartal, Nick | Asset Integrity | 3. Active | Defined | Pipeline Digs |  | 81000 |  | 81000 | 81000 | 0 | Green | 300000 |  | 300000 | -219000 |  |  | 300000 |  |  | 300000 | Full | 300000 |  | 81000 | 81000 | No | Green | 2023-07-01 | 2022-12-16 | 2022-12-16 | 2023-12-31 | 2023-12-31 | [14 empty] | 13500 | 13500 | 13500 | 13500 | 13500 | 13500 |  | 12/20/22 - Forecast reduced by $120,000 to fund RX751BXE2301. (AS) 12/20/22 - Forecast reduced by $99,100 to cover the following 2022 Lab Analysis Projects - BH724SNE2201, IJ162JUE2201 and BB999A3E2202. (AS) | 2022-12-20 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Pipeline Integrity |  | Corporate | Corporate |  |  | 0 | 40500 | 40500 |  |  | Bartal, Nick | Shook, Mark B. |  |  | 1 | 45207 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Int - Assessments
2023 MCAP Def_Mloss Budget Allocation | Item | Open | MCAP |  | Maintenance Framework |  | Bartal, Nick | Asset Integrity | 1. Proposed |  | Pipeline Digs |  | 8595500 |  | 8595500 | 12745500 | -4150000 | Red | 30700000 |  | 30700000 | -22104500 | [9 empty] | 8595500 | 8595500 | No | Green | 2023-06-01 |  |  |  | 2023-12-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 500000 | 795500 | 1750000 | 1750000 | 1300000 | 1300000 | 1200000 |  | 5/8/23 - Reduced by $4.15MM to cover L913 digs, L803 digs, L203 digs, L718 digs, L534 digs, etc. 4/10/23 - Reduced by $5.245MM to cover L714 cutouts, L203 digs, L415 digs, L751 digs, PP999A3 digs, L718 cutout, L601 digs, L806 digs, and L163 digs. 3/7/23 - reduced by $733k to cover L718 immediate digs and L402 UCD digs. 2/9/23 - reduced as follows (total of $8.717MM): $3.5MM - L751 digs $2.0MM - L601 digs $1.9MM - L163 digs $540k - L601 cutouts $402k - L701 cutouts $188k - L718 cutouts $77k - L751 immediate digs $55k - L700 cutouts $55k - L603 like and similar Had previously reduced by $3.25MM to cover L601, L402, and L163 digs | 2023-05-08 |  |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Integrity |  | Corporate | Corporate |  |  | 500000 | 4295500 | 3800000 |  |  | Bartal, Nick |  |  |  | 1 | 44914 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int- Planned Digs
2023 MCAP Seam Budget Allocation | Item | Open | MCAP |  | Maintenance Framework |  | Bartal, Nick | Asset Integrity | 1. Proposed |  | Pipeline Digs |  | 0 |  | 0 | 0 | 0 | Green | 4000000 |  | 4000000 | -4000000 | [9 empty] | 0 | 0 | No | Green |  |  |  |  | 2023-12-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4/10/23 - Reduced by $1.2MM to cover L714 cutouts. 3/7/23 - Reduced by $1.87MM to cover L203 issued digs. 2/9/23 - reduced by $600k to cover L714 digs and $90k to cover L714 cutout costs | 2023-04-10 |  |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Integrity |  | Corporate | Corporate |  |  | 0 | 0 | 0 |  |  | Bartal, Nick |  |  |  | 1 | 44915 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int- Planned Digs
2023 MEXP Budget Allocation - Def_Mloss | Item | Open | MEXP | 1348250E2303 | Maintenance Framework |  | Bartal, Nick | Asset Integrity | 3. Active | Defined | Pipeline Digs |  | 990000 |  | 990000 | 1280331 | -290331 | Red | 2500000 |  | 2500000 | -1510000 |  |  | 2500000 |  |  | 2500000 | Full | 2500000 |  | 990000 | 990000 | No | Green | 2023-06-01 | 2022-12-20 | 2022-12-20 | 2023-12-31 | 2023-12-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 200000 | 200000 | 130000 | 130000 | 110000 | 110000 | 110000 |  | 5.8.23 - May forecast reduced by $270,000 for MEXP Flips (AS) 5/8/23 - May forecast is for planned flips. 4/10/23 - Added back $600k for Mar/April flips that have not posted yet. 4.6.23 - Forecast reduced by $626,669 for Additional March MEXP Flips (AS) 3.7.23 - March MEXP Flips $693,402. Reduced March Forecast by this amount (AS) 1/9/23 - Jan flips were back-dated to Dec by Accounting. Redistributed Jan forecast in Q1/Q2 | 2023-05-09 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Pipeline Integrity |  | Corporate | Corporate |  |  | 200000 | 460000 | 330000 |  |  | Bartal, Nick | Shook, Mark B. |  |  | 1 | 45208 |  | Administrator, System | JDE Parent | Yellow | 2022-08-23 | Int- Planned Digs
2023 MEXP Exposed Pipe Budget Allocation | Item | Open | MEXP | 1348250E2308 | Maintenance Framework |  | Hurley, Brian | Asset Integrity | 3. Active | Drawdown | Exposed Pipe Evaluation & Remediation |  | 308500 |  | 308500 | 283500 | 25000 | Yellow | 500000 |  | 500000 | -191500 |  |  | 500000 |  |  | 500000 | Full | 500000 |  | 308500 | 308500 | No | Green | 2023-05-01 | 2023-01-05 | 2023-01-05 | 2023-12-31 | 2023-11-30 | [6 empty] | 5000 | 5000 | -5000 | Red |  | Forecasting | 10000 | 35000 | 45000 | 43500 | 55000 | 50000 | 40000 | 30000 |  | 3/9/23 - Allocated ~$50k into projects from allocation. | 2023-03-09 | Schultz, Amy |  | Corporate | Pipelines and Terminals | Pipeline Integrity |  | Corporate | Corporate |  |  | 45000 | 143500 | 120000 |  |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 44582 |  | Guest, ProSight | JDE Parent | Yellow | 2022-08-12 | Int - Assessments
2023 New HCA Digs Budget Allocation | Item | Open | MCAP |  | Maintenance Framework |  | Bartal, Nick | Asset Integrity | 1. Proposed |  | Pipeline Digs |  | 300000 |  | 300000 | 300000 | 0 | Green | 300000 |  | 300000 | 0 | [9 empty] | 300000 | 300000 | No | Green | 2023-08-01 |  |  |  | 2023-10-31 | [15 empty] | 100000 | 100000 | 100000 | [7 empty] | Corporate - Pipes and Terminals | Pipelines and Terminals | Integrity |  | Corporate | Corporate |  |  | 0 | 200000 | 100000 |  |  | Bartal, Nick |  |  |  | 1 | 44928 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int- Planned Digs
2023 Piggability Allocation | Item | Open | MEXP |  | Maintenance Framework |  | Bartal, Nick | Asset Integrity | 1. Proposed |  | Assessments |  | 100000 |  | 100000 | 100000 | 0 | Green | 125000 |  | 125000 | -25000 | [9 empty] | 100000 | 100000 | No | Green | 2023-05-01 |  |  |  | 2023-12-31 | 8 | Yellow | [10 empty] | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | [5 empty] | Corporate - Pipes and Terminals | Pipelines and Terminals | Pipeline Integrity |  | Corporate | Corporate |  |  | 25000 | 37500 | 37500 |  |  | Bartal, Nick |  |  |  | 1 | 44698 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 Seam Susceptibility and Fatigue | Item | Open | MEXP | 1348250E2305 | Maintenance Framework | 2074816 | Hurley, Brian | Asset Integrity | 3. Active | Drawdown | Pipeline Digs | 88374 | 140000 |  | 228374 | 230271 | -1897 | Yellow | 210000 |  | 210000 | 18374 |  |  | 210000 |  |  | 210000 | Full | 210000 | 88374 | 140000 | 228374 | No | Green | 2023-03-01 | 2022-12-16 | 2022-12-16 | 2023-12-31 | 2023-12-31 |  |  |  |  | 55271 | 33103 | 35000 | 35000 | -1897 | Yellow |  |  | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 |  | 4/11/23 - Accrued first quarter of seam work to March. Forecast corrected moving forward. 4.4.23 - Accrual $55,217 (AS) | 2023-04-11 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Pipeline Integrity |  | Corporate | Corporate |  | 55271 | 68103 | 52500 | 52500 |  |  | Bartal, Nick | Shook, Mark B. |  |  | 1 | 45206 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Int - Assessments
2023 Third Party Terminal Software Tank Strapping Data Update | Item | Open | MEXP | 1550000E2302 | Maintenance Framework | 2084469 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tanks | 6075 | 16000 |  | 22075 | 22725 | -650 | Yellow | 24000 |  | 24000 | -1925 |  |  | 24000 |  |  | 24000 | Full | 24000 | 6075 | 16000 | 22075 | No | Green | 2023-02-01 | 2023-02-02 | 2023-02-02 | 2023-12-31 | 2023-12-31 |  |  |  | 5058 | -333 | 1350 | 2000 | 2000 | -650 | Red |  |  | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 |  | 5/4/23 CNC - accrue $1350 4.4.23 - Accrual $675 (AS) 3/9/23 CNC - Triad monthly bill for strapping chart uploads. | 2023-05-03 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Tank Integrity |  | Corporate | Corporate |  | 4725 | 5350 | 6000 | 6000 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44762 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
2023 USCG Dock Line API-570 Inspection Budget Allocation | Item | Open | MEXP | 1348250E2316 | Maintenance Framework | NA | Aiken, Elaine | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 310000 |  | 310000 | 450000 | -140000 | Red | 450000 |  | 450000 | -140000 |  |  | 450000 |  |  | 450000 | Full | 450000 |  | 310000 | 310000 | No | Green | 2023-06-01 | 2023-02-18 | 2023-02-18 | 2023-12-31 | 2023-08-31 | [13 empty] | 30000 | 80000 | 100000 | 100000 |  |  |  |  | 2023-05-08 - Reduced forecast for the following dock line inspections that were entered as projects: Charleston ($55k) and Wilmington ($35k). Also reduced forecast for USCG dock line inspection plan development project ($50k). | 2023-05-08 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  |  | 30000 | 280000 |  |  |  | Aiken, Elaine | Shook, Mark B. |  |  | 1 | 44974 |  | Administrator, System | JDE Parent | Yellow | 2022-08-18 | Int - Planned Corr & FI
415 Sinkhole Survey | Item | Open | MEXP | GK415GAE2202 | Maintenance Framework | 2044314 | Hurley, Brian | Asset Integrity | 3. Active | Drawdown | Exposed Pipe Evaluation & Remediation | 2500 |  |  | 2500 | 2500 | 0 | Green |  |  |  | 2500 |  |  | 5000 |  |  | 5000 | Full | 5000 | 4000 |  | 4000 | No | Green | 2022-11-01 | 2022-11-08 | 2022-11-08 | 2022-12-31 | 2022-12-31 |  |  |  |  | 2500 | [16 empty] | 1/12/23 - mrk - pushed forecast to Feb 2023 for design workplan | 2023-01-12 | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | Mantua | GK415GA - BRECKSVILLE TO AURORA-#1-E |  | 2500 | 0 |  |  | 1500 |  | Hurley, Brian | Shook, Mark B. | N/A |  | 1 | 46206 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-11-08 | Int - Planned Exposures
714L Lab Analysis | Item | Open | MEXP | ZG714RGE2302 | Maintenance Framework | 2077110 | Bartal, Nick | Asset Integrity | 3. Active | Drawdown | Pipeline Digs | 11226 | 32160 |  | 43385.9 | 43386 | 0 | Green |  |  |  | 43386 |  |  | 43386 |  |  | 43386 | Full | 43386 | 11226 | 32160 | 43386 | No | Green | 2023-03-01 | 2023-01-31 | 2023-01-31 | 2023-03-31 | 2023-03-31 |  |  |  |  | 11225.9 | 0 | 32160 | 32160 | -32160 | Red |  | Contractor/Vendor Issue | 32160 | [8 empty] | 5/8/23 - Work still in process, refrorecast for May | 2023-05-08 | Schultz, Amy |  | East | Pipelines and Terminals | Pipeline Integrity |  | Macungie Pipe | ZG714RG - MACUNGIE TO TUCKERTON |  | 11226 | 32160 |  |  |  |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 46564 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-01-31 | Int- Planned Digs
AC Mitigation Site RMU Order and Installation | Item | Open | MCAP | XB003XXM2302 | Maintenance Framework | 2085665 | Miller, Sean | Asset Integrity | 3. Active | Defined | Cathodic Protection |  |  |  | 0 |  | 0 | Green |  | 4400 | 4400 | -4400 |  |  | 24400 |  |  | 24400 | Full | 24400 |  | 20000 | 20000 | No | Green | 2024-05-01 | 2023-02-21 | 2023-02-21 | 2023-03-01 | 2023-03-31 | [23 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Integrity |  | Huntington | XB003XX - HUNTINGTON TO OHIO S/L- EAST |  |  | 0 |  |  |  | 20000 | Geib, Rob | Shook, Mark B. |  |  | 1 | 45426 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
API-570 Inspection Plan Development for USCG Dock Lines | Item | Open | MEXP | 1550000E2303 | Maintenance Framework | 2094006 | Aiken, Elaine | Asset Integrity | 3. Active | Drawdown | Facility Integrity |  | 50000 |  | 50000 | 50000 | 0 | Green |  |  |  | 50000 |  |  | 50000 |  |  | 50000 | Full | 50000 |  | 50000 | 50000 | No | Green | 2023-05-01 | 2023-03-06 | 2023-03-06 | 2023-12-31 | 2023-12-31 | [6 empty] | 10000 | 10000 | -10000 | Red |  | Forecasting | 15000 | 20000 | 15000 | [6 empty] | 2023-05-08 - EKA - project kicked off later than anticipated due to workload and staff level. PO was issued at the start of May. | 2023-05-08 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  |  | 35000 | 15000 |  |  |  | Aiken, Elaine | Stine, Carlton | N/A |  | 1 | 46630 |  | Aiken, Elaine | JDE Child | Burnt Orange | 2023-02-23
API-570 Inspection Report Processing | Item | Open | MEXP | 1348250E2318 | Maintenance Framework | 2094352 | Aiken, Elaine | Asset Integrity | 3. Active | Drawdown | Facility Integrity | 61617 | 53000 |  | 114616.7 | 99590 | 15027 | Red |  |  |  | 114617 |  |  | 115000 |  |  | 115000 | Full | 115000 | 61617 | 53000 | 114617 | No | Green | 2023-03-01 | 2023-03-09 | 2023-03-09 |  | 2023-12-31 |  |  |  |  | 34590 | 27026.7 | 20000 | 20000 | 7027 | Red |  | WorkAhead of Schedule | 15000 | 20000 | 10000 | 8000 | [5 empty] | 4.4.23 - Accrual $20,000 (AS) | 2023-04-04 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  | 34590 | 62027 | 18000 |  |  |  | Aiken, Elaine | Stine, Carlton | N/A |  | 1 | 46698 |  | Aiken, Elaine | JDE Child | Burnt Orange | 2023-03-04
Arcadis Exposure Program Developments | Item | Open | MEXP | 1348250E2242 | Maintenance Framework | 2036668 | Hurley, Brian | Asset Integrity | 3. Active | Drawdown | Exposed Pipe Evaluation & Remediation | 4364 |  |  | 4364 | 2590 | 1774 | Red |  |  |  | 4364 |  |  | 25000 |  |  | 25000 | Full | 25000 | 5864 |  | 5864 | No | Green | 2022-12-01 | 2022-10-11 | 2022-10-11 | 2022-12-31 | 2023-06-30 |  |  | -1089 | 887 | 2792 | 1774 |  |  | 1774 | Red | [11 empty] | 1.4.23 - Project carrying over to 2023. $23,500 will be funded from 2023 Drawdown (AS) 11/9/22 - PO held up due to accounting review. Work should take place in Nov/Dec | 2023-01-04 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Pipeline Integrity |  | Corporate | Corporate |  | 2590 | 1774 |  |  | 1500 |  | Hurley, Brian | Shook, Mark B. | N/A |  | 1 | 46035 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-10-11 | Int - Planned Exposures
Bahamas CP Upgrades for Tanks | Item | Open | MCAP | 8410811M2130 | Maintenance Framework | 1901787 | Geib, Rob | Asset Integrity | 7. Closed | Emergent | Cathodic Protection | -2877 |  |  | -2877.25 |  | -2877 | Red |  |  |  | -2877 |  |  | 250000 |  |  | 250000 | Full | 250000 | 265109 |  | 265109 | No | Green | 2021-10-01 | 2021-10-11 | 2021-10-11 | 2021-12-31 | 2022-05-01 | [5 empty] | -2877.25 |  |  | -2877 | Red | [11 empty] | 12/8/21 - sTILL EXPECT TO BE COMPLETE BY END OF YEAR. | 2021-12-08 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | -2877 |  |  | 37224 |  | Geib, Rob | Geib, Robert |  |  | 1 | 42248 |  | Perry, Betty | Independent | Aqua | 2021-10-04 | Int - Tanks
Baltimore State Regulation Review | Item | Open | MEXP | BETQB00E2303 | Maintenance Framework | 2110058 | Aiken, Elaine | Asset Integrity | 3. Active | Drawdown | Facility Integrity |  | 18000 |  | 18000 | 18000 | 0 | Green |  |  |  | 18000 |  |  | 18000 |  |  | 18000 | Full | 18000 |  | 18000 | 18000 | No | Green | 2023-05-01 | 2023-04-07 | 2023-04-07 | 2023-10-01 | 2023-10-01 | [6 empty] | 9000 | 9000 | -9000 | Red |  | Forecasting | 9000 | 9000 | [9 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Station/Terminal |  | Baltimore | BETQB - BET BALTIMORE TERMINAL |  |  | 18000 |  |  |  |  | Aiken, Elaine | Orischak, Bob | N/A |  | 1 | 46883 |  | Aiken, Elaine | JDE Child | Burnt Orange | 2023-04-06
Bangor Terminal API 570 Inspection 2023 | Item | Open | MEXP | BETBM00E2301 | Maintenance Framework | 2093443 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 31000 |  | 31000 | 31000 | 0 | Green | 31000 |  | 31000 | 0 |  |  | 31000 |  |  | 31000 | Phase | 31000 |  | 31000 | 31000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-07-31 | [14 empty] | 31000 | [8 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Station/Terminal |  | Maine | BETBM - BET BANGOR TERMINAL |  |  | 0 | 31000 |  |  |  | Aiken, Elaine | Shook, Mark B. |  |  | 1 | 45024 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Bayonne Insulated Pipe Phase 2 Inspection | Item | Open | MEXP |  | Maintenance Framework |  | Aiken, Elaine | Asset Integrity | 2. Pending AFE |  | Facility Integrity |  | 110000 |  | 110000 | 110000 | 0 | Green | 110000 |  | 110000 | 0 | [9 empty] | 110000 | 110000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 50000 | 60000 | [9 empty] | East | Pipelines and Terminals | Station/Terminal |  | Harbor North Terminals | BBTQY - BBT BAYONNE TERMINAL |  |  | 0 | 110000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45063 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
BET Toledo Terminal API 570 Inspection | Item | Open | MEXP | BETTO00E2301 | Exempt | 2093446 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 33000 |  | 33000 | 33000 | 0 | Green | 33000 |  | 33000 | 0 |  |  | 33000 |  |  | 33000 | Phase | 33000 |  | 33000 | 33000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-07-31 | [14 empty] | 33000 | [6 empty] | 4/25/23 SL - Project to start in May | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Toledo | BETTO - BET TOLEDO TERMINAL |  |  | 0 | 33000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45014 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Boiler Plant Energy Assessments and Follow up | Item | Open | MEXP | 1348250E2238 | Maintenance Framework | 2022212 | Stine, Carlton | Asset Integrity | 6. Operational | Defined | Boilers | 4950 |  |  | 4950 | 4950 | 0 | Green | 15000 |  | 15000 | -10050 |  |  | 50000 |  |  | 50000 | Full | 50000 | 29950 |  | 29950 | No | Green | 2022-11-01 | 2022-09-09 | 2022-09-09 | 2023-01-31 | 2023-01-31 |  |  | 5000 | -50 | [17 empty] | 3/2/23-CES-Final invoice received from Cleaver Brooks. Project Ready to close. 2/3/23-CES-Reaccrue costs to Cleaver Brooks. Will be invoiced in February. 1/4/23-Cleaver Brooks visit to BBH complete. Awaiting invocing. Additional visit planned for January.12/2/2022-CES-Accrue $15,000 for Cleaver Brooks Boiler Assessments. 11/3/22-BBH Boiler Assessment starting in November. 9/27/22 - Forecast removed from Q1 and Q2 2025 per request from Carlton (AS) 9/7/22-CES-Anticipating $15k carryover. Routing AFE on 9/7. 7.13.22.DLC: Pushed fcst into Sept-Dec | 2023-03-02 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  | 4950 | 0 |  |  | 25000 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41633 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
Boiler Program Site Visits, Engineering Review, and Roadmap Development | Item | Open | MEXP | 1348250E2309 | Maintenance Framework | 2074904 | Stine, Carlton | Asset Integrity | 3. Active | Defined | Boilers | 22211 | 70000 |  | 92210.5 | 91958 | 253 | Yellow | 200000 |  | 200000 | -107790 |  |  | 84000 |  |  | 84000 | Phase | 84000 | 22211 | 70000 | 92211 | No | Green | 2023-02-01 | 2023-01-05 | 2023-01-05 | 2023-12-31 | 2023-07-31 |  |  |  | 12601.5 | 4356 | 5253 | 5000 | 5000 | 253 | Yellow |  |  | 10000 | 10000 |  |  |  | 50000 |  |  |  | 5/3/23-CES-Accrue $4,000 to Midstream Engineers. Forecast $10,000 in May for Midstream and American Thermal. Planning kick off of hot oil heater site visits.4/4/23-CES-Delay due to approval from IT to create BEST module. Interviews in progress. 3/2/23-CES-Accrue $10,000 to Midstream for Boiler Interviews | 2023-05-03 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  | 16958 | 25253 |  | 50000 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44741 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Other Programs
Booth Station Baseline Facility Assessment | Item | Open | MEXP | BH00000E2204 | Maintenance Framework | 2045183 | Aiken, Elaine | Asset Integrity | 6. Operational | Defined | Facility Integrity | -3295 |  |  | -3294.77 | 0 | -3295 | Red |  |  |  | -3295 |  |  | 15000 |  |  | 15000 | Full | 15000 | 4705 |  | 4705 | No | Green | 2022-12-01 | 2022-11-17 | 2022-11-17 | 2022-12-31 | 2022-12-31 |  |  | 0 | 0 | 0 | -3294.77 |  |  | -3295 | Red |  | Forecasting | [9 empty] | 4.4.23 - Accrual $$8,000. Waiting on invoicing (AS) 3.2.23 - Accrual $8,000. Waiting on invoicing (AS) | 2023-04-04 | Schultz, Amy |  | East | Pipelines and Terminals | Station/Terminal |  | Booth | BH - BOOTH STATION |  | 0 | -3295 |  |  | 8000 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 41198 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
Booth Tank 1 Painting | Item | Open | MCAP | BH00000M2305 | Maintenance Framework | 2112564 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting |  | 105000 |  | 105000 | 105000 | 0 | Green |  |  |  | 105000 |  |  | 127490 |  |  | 127490 | Full | 127490 |  | 105000 | 105000 | No | Green | 2023-05-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-06-30 | [12 empty] | 55000 | 50000 | [7 empty] | 5/4/23 CNC - project scheduled for May 15 3/20/23 CNC - project bid out for 2023 (shell and roof) | 2023-05-03 | Schultz, Amy |  | East | Pipelines and Terminals | Integrity |  | Booth | BH - BOOTH STATION |  |  | 105000 |  |  |  |  | Cole, Caitlyn | Stine, Carlton |  |  | 1 | 24518 |  | Administrator, System | Independent | Aqua | 2017-07-27 | Int - Tanks
Bradley Road Terminal API 570 Inspection | Item | Open | MEXP | BD00000E2301 | Exempt | 2093441 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 31000 |  | 31000 | 31000 | 0 | Green | 31000 |  | 31000 | 0 |  |  | 31000 |  |  | 31000 | Phase | 31000 |  | 31000 | 31000 | No | Green | 2023-08-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-08-31 | [15 empty] | 31000 | [5 empty] | 4/25/23 SL - Project to start in May | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Mantua | BD - BRADLEY ROAD TERMINAL |  |  | 0 | 31000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45017 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
BTP Floating Roof Root Cause Failure Analysis | Item | Open | MEXP | BTXPP00E2206 | Maintenance Framework | 2021910 | Stine, Carlton | Asset Integrity | 3. Active | Drawdown | Tanks | 9892 |  |  | 9891.83 | 2398 | 7494 | Red |  |  |  | 9892 |  |  | 110000 |  | 35000 | 145000 | Supplemental | 145000 | 147607 |  | 147607 | No | Green | 2022-09-01 | 2022-09-07 | 2022-09-07 | 2022-12-31 | 2022-12-31 |  |  | 798.08 | 21094 | -19494 | 7493.75 |  |  | 7494 | Red |  | Engineering or Scope Change | [9 empty] | 4/4/23-CES-Variance due to accidental double accrual. Project is finished awaiting final invoice. 3/3/23 CNC- Accrue $21,494 to BECHT for RCA. 2/3/23-CES-Reaccrue costs to BECHT for RCA. 1/4/23-BECHT RCA nearing completion. Total actuals in 2022 were $130,000. Accrue $22,000 for December. 12/2/2022-CES-Accrue $10,000 for BECHT Engineering. 11/3/2022-Accrue $90,000 to BECHT Engineering for RCA. 10/4/22-Accrue $20,000 to BECHT Engineering for RCA kick-off. Site visit next week and RCA progression in October. Early November anticipated finish. | 2023-04-04 | Schultz, Amy |  | South | Pipelines and Terminals | Tank Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 2398 | 7494 |  |  | 137715 |  | Stine, Carlton | Shook, Mark B. | N/A |  | 1 | 45752 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-09-07 | Int - Tanks
BTXHF - Underground piping CP and isolation | Item | Open | MCAP | BTXHF00M1706 | Exempt | 1358771 | Wirfs, Mike | Asset Integrity | 7. Closed | Emergent | Cathodic Protection |  |  |  | 0 |  | 0 | Green | 120000 |  | 120000 | -120000 |  |  | 12000 |  |  | 12000 | Phase | 12000 | 0 |  | 0 | No | Green |  | 2017-07-23 | 2017-07-23 | 2017-07-21 | 2017-09-29 | [23 empty] | Schultz, Amy |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXHF - Buckeye Texas Hub | 6200187M1700 |  | 0 |  |  |  |  | Geib, Rob | Charles, Jeffrey |  |  | 1 | 16757 |  | Simmons, Lourdes | Child (Major Project) | Olive | 2015-09-16 | Int - Planned Corr & FI
BTXHF LPG Tanks Onstream Inspections | Item | Open | MEXP | BTXHF00E2301 | Maintenance Framework | 2093555 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Pressure Vessels | 24000 | 12000 |  | 36000 | 60000 | -24000 | Red | 60000 |  | 60000 | -24000 |  |  | 66000 |  |  | 66000 | Full | 66000 | 24000 | 12000 | 36000 | No | Green | 2023-04-01 | 2023-03-01 | 2023-03-01 | 2023-12-31 | 2023-06-30 | [5 empty] | 24000 |  |  | 24000 | Red |  |  | 12000 | [8 empty] | 5/3/23 CNC - inspections completed in April. BECHT to perform on stream analysis in May. 4/5/23 CNC - Rosen will be on site 4/11/23 for inspection 3/16/2023 CNC - $60k forecast to be moved to April. | 2023-05-03 | Schultz, Amy |  | South | Pipelines and Terminals | Tank Integrity |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  |  | 36000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44744 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
BTXPP LPG Tanks Onstream Inspections | Item | Open | MEXP | BTXPP00E2303 | Maintenance Framework | 2093556 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Pressure Vessels | 6000 | 3000 |  | 9000 | 15000 | -6000 | Red | 15000 |  | 15000 | -6000 |  |  | 16500 |  |  | 16500 | Full | 16500 | 6000 | 3000 | 9000 | No | Green | 2023-04-01 | 2023-03-02 | 2023-03-02 | 2023-12-31 | 2023-07-31 | [5 empty] | 6000 |  |  | 6000 | Red |  |  | 3000 | [8 empty] | 5/3/23 CNC - inspections completed in April. BECHT to perform on stream analysis in May. 4/5/23 CNC - Rosen will be on site 4/11/23 for inspection 3/16/23 CNC - $15k forecast to be moved to April. | 2023-05-03 | Schultz, Amy |  | South | Pipelines and Terminals | Tank Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 9000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44745 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
BTXPP OWS Piping Replacement | Item | Open | MCAP | BTXPP00M2212 | Maintenance Framework | 2011052 | Aiken, Elaine | Asset Integrity | 6. Operational | Drawdown | Facility Integrity | -1 |  |  | -0.9 | -1 | 0 | Green |  |  |  | -1 |  |  | 84000 |  |  | 84000 | Full |  | 86826 |  | 86826 | No | Green | 2022-10-01 | 2022-08-01 | 2022-08-01 |  | 2022-12-31 |  |  | -0.9 | 0 | 0 | 0 |  |  | 0 | Green | [11 empty] | 4.4.23 - Accrual $74,000. Waiting on Invoicing (AS) 3.3.23 - Accrual $74,000. Waiting on Invoicing (AS) 2022-10-10 - work was completed in September, missed accrual. | 2023-04-04 | Schultz, Amy |  | South | Pipelines and Terminals | Integrity |  | South Texas |  |  | -1 | 0 |  |  | 86827 |  | Aiken, Elaine | Shook, Mark B. |  |  | 1 | 44196 |  | Perry, Betty | Independent |  | 2022-07-22 | Int - Planned Corr & FI
Buffalo Terminal - Paint Tank 99 | Item | Open | MCAP | BETBO00M2302 | Maintenance Framework | 2112565 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting |  | 65000 |  | 65000 | 65000 | 0 | Green |  |  |  | 65000 |  |  | 80465 |  |  | 80465 | Full | 80465 |  | 65000 | 65000 | No | Green | 2023-12-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-07-31 | [19 empty] | 65000 |  | 3/20/23 CNC - project bid out for 2023 | 2023-03-20 | Schultz, Amy |  | East | Pipelines and Terminals | Integrity |  | Auburn Terminals | BETBO - BET BUFFALO TERMINAL |  |  | 0 |  | 65000 |  |  | Cole, Caitlyn | Stine, Carlton | N/A |  | 1 | 30842 |  | Guest, ProSight | Independent | Aqua | 2018-08-23 | Int - Tanks
Charleston Dock Line API-570 Inspection | Item | Open | MEXP | BETQH00E2303 | Maintenance Framework | 2120112 | Aiken, Elaine | Asset Integrity | 3. Active | Drawdown | Facility Integrity |  | 55000 |  | 55000 |  | 55000 | Red |  |  |  | 55000 |  |  | 55000 |  |  | 55000 | Full | 55000 |  | 55000 | 55000 | No | Green | 2023-05-01 | 2023-05-04 | 2023-05-04 | 2023-12-31 | 2023-12-31 | [12 empty] | 40000 | 15000 | [9 empty] | Schultz, Amy |  | South | Pipelines and Terminals | Station/Terminal |  | South Carolina | BETQH - BET NORTH CHARLESTON TERMINAL |  |  | 55000 |  |  |  |  | Aiken, Elaine | Shook, Mark B. | N/A |  | 1 | 47000 |  | Aiken, Elaine | JDE Child | Burnt Orange | 2023-04-28
Charlotte I (BSEVC) Tank 12 Painting | Item | Open | MCAP | BSEVC00M2301 | Maintenance Framework | 2112566 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting |  | 35000 |  | 35000 | 35000 | 0 | Green |  |  |  | 35000 |  |  | 45458 |  |  | 45458 | Full | 45458 |  | 35000 | 35000 | No | Green | 2023-12-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-12-31 | [19 empty] | 35000 |  | 4/5/2023 CNC - project bid out for 2023 (shell) | 2023-04-05 | Schultz, Amy |  | South | Pipelines and Terminals | Integrity |  | North Carolina | BSEVC - CHARLOTTE I TERMINAL |  |  | 0 |  | 35000 |  |  | Cole, Caitlyn | Stine, Carlton |  |  | 1 | 46812 |  | Cole, Caitlyn | Independent | Aqua | 2023-03-20
Charlotte I (BSEVC) Tank 15 Painting | Item | Open | MCAP | BSEVC00M2302 | Maintenance Framework | 2112568 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting |  | 35000 |  | 35000 | 35000 | 0 | Green |  |  |  | 35000 |  |  | 45458 |  |  | 45458 | Full | 45458 |  | 35000 | 35000 | No | Green | 2023-12-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-12-31 | [19 empty] | 35000 |  | 4/5/2023 CNC - project bid out for 2023 (shell) | 2023-04-05 | Schultz, Amy |  | South | Pipelines and Terminals | Integrity |  | North Carolina | BSEVC - CHARLOTTE I TERMINAL |  |  | 0 |  | 35000 |  |  | Cole, Caitlyn | Stine, Carlton |  |  | 1 | 46813 |  | Cole, Caitlyn | Independent | Aqua | 2023-03-20
Chattanooga II Terminal (BSEVF) LPG Tanks Onstream Inspections | Item | Open | MEXP | BSEVF00E2304 | Maintenance Framework | 2093558 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Pressure Vessels |  | 28000 |  | 28000 | 28000 | 0 | Green | 28000 |  | 28000 | 0 |  |  | 30800 |  |  | 30800 | Full | 30800 |  | 28000 | 28000 | No | Green | 2023-05-01 | 2023-03-02 | 2023-03-02 | 2023-12-31 | 2023-04-30 | [6 empty] | 28000 | 28000 | -28000 | Red |  | Forecasting | 28000 | [8 empty] | 5/43/23 CNC - project scheduled for May. 3/16/23 CNC - $28k forecast to be moved to May | 2023-05-03 | Schultz, Amy |  | South | Pipelines and Terminals | Tank Integrity |  | Tennessee | BSEVF - CHATTANOOGA II TERMINAL |  |  | 28000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44748 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Columbus East Insulated Pipe Phase 2 Inspection | Item | Open | MEXP |  | Exempt |  | Aiken, Elaine | Asset Integrity | 2. Pending AFE |  | Facility Integrity |  | 110000 |  | 110000 | 110000 | 0 | Green | 110000 |  | 110000 | 0 | [9 empty] | 110000 | 110000 | No | Green | 2023-08-01 |  |  |  | 2023-07-31 | [15 empty] | 50000 | 60000 | [8 empty] | West | Pipelines and Terminals | Station/Terminal |  | Southern Ohio | BETCE - BET COLUMBUS EAST TERMINAL |  |  | 0 | 110000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45060 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Coraopolis Terminal (BPL) and station API 570 Inspection | Item | Open | MEXP | CP00000E2301 | Exempt | 2093466 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 95000 |  | 95000 | 95000 | 0 | Green | 95000 |  | 95000 | 0 |  |  | 95000 |  |  | 95000 | Phase | 95000 |  | 95000 | 95000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-07-31 | [14 empty] | 95000 | [6 empty] | 4/25/23 SL - Project to start in June | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Coraopolis | CP - CORAOPOLIS TERMINAL BPL |  |  | 0 | 95000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45005 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Council Bluffs API 570 Inspection | Item | Open | MEXP | BETNB00E2302 | Exempt | 2093456 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity | 4267 | 44433 |  | 48699.5 | 38000 | 10700 | Red | 38000 |  | 38000 | 10700 |  |  | 38000 |  |  | 38000 | Phase | 38000 | 4267 | 44433 | 48700 | No | Green | 2023-04-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-08-31 | [5 empty] | 4266.5 |  |  | 4267 | Red |  | Forecasting | 22000 | 22433 | [7 empty] | 4/25/23 SL - 1st site visit and drawings complete, inspection visit to follow | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Sugar Creek | BETNB - BET COUNCIL BLUFFS |  |  | 48700 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45012 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Dearborn API 570 Inspection | Item | Open | MEXP | BETIT00E2301 | Exempt | 2093447 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 33000 |  | 33000 | 33000 | 0 | Green | 33000 |  | 33000 | 0 |  |  | 33000 |  |  | 33000 | Phase | 33000 |  | 33000 | 33000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-07-31 | [14 empty] | 33000 | [6 empty] | 4/25/23 SL - Project to start in May | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Terminals | BETIT - BET DEARBORN |  |  | 0 | 33000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45018 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Dearborn API 570 Inspection 2023 | Item | Open | MEXP | BETIT00E2302 | Exempt | 2093444 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 31000 |  | 31000 | 31000 | 0 | Green | 31000 |  | 31000 | 0 |  |  | 31000 |  |  | 31000 | Phase | 31000 |  | 31000 | 31000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-07-31 | [14 empty] | 31000 | [6 empty] | 4/25/23 SL - Project to start in May | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Terminals | BETIT - BET DEARBORN |  |  | 0 | 31000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45021 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Des Moines API 570 Inspection | Item | Open | MEXP | BETOI00E2304 | Exempt | 2093458 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity | 3188 | 39000 |  | 42187.5 | 39000 | 3188 | Yellow | 39000 |  | 39000 | 3188 |  |  | 39000 |  |  | 39000 | Phase | 39000 | 3188 | 39000 | 42188 | No | Green | 2023-04-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-07-31 | [5 empty] | 3187.5 |  |  | 3188 | Red |  | Forecasting | 39000 | [8 empty] | 4/25/23 SL - 1st site visit and drawings complete, inspection visit to follow | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Sugar Creek | BETOI - BET DES MOINES |  |  | 42188 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45011 |  | Administrator, System | Independent |  | 2022-08-18 | Int - Planned Corr & FI
East Chicago East API 570 inspection (EU, BETEU) | Item | Open | MEXP | BETEU00E2301 | Exempt | 2093470 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 256000 |  | 256000 | 256000 | 0 | Green | 256000 |  | 256000 | 0 |  |  | 25600 |  |  | 25600 | Phase | 25600 |  | 256000 | 256000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-08-31 | [14 empty] | 256000 | [6 empty] | 4/25/23 SL - 1st site visit and drawings complete, inspection visit to follow | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  |  | 0 | 256000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45047 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
East Chicago East Tank 204 New Coating | Item | Open | MCAP | BETEU00M2306 | Maintenance Framework | 2112567 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting |  | 40000 |  | 40000 | 40000 | 0 | Green |  |  |  | 40000 |  |  | 54340 |  |  | 54340 | Full | 54340 |  | 40000 | 40000 | No | Green | 2023-12-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-08-31 | [19 empty] | 40000 |  | 3/20/23 CNC - project bid out for 2023 (shell and roof) | 2023-03-20 | Schultz, Amy |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  |  | 0 |  | 40000 |  |  | Cole, Caitlyn | Stine, Carlton |  |  | 1 | 34953 |  | Guest, ProSight | Independent | Aqua | 2019-08-30 | Int - Tanks
East Chicago West API 570 (EQ, BETEG, EQ, EC) | Item | Open | MEXP | BETEG00E2301 | Maintenance Framework | 2093469 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 143000 |  | 143000 | 143000 | 0 | Green | 143000 |  | 143000 | 0 |  |  | 143000 |  |  | 143000 | Phase | 143000 |  | 143000 | 143000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-08-31 | [14 empty] | 143000 | [6 empty] | 4/25/23 SL - 1st site visit and drawings complete, inspection visit to follow | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | E. Chicago Terminals | BETEG - BET EAST CHICAGO TERMINAL |  |  | 0 | 143000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45048 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
East St. Louis Station Coat Relief Tank 2018 | Item | Open | MCAP | ES00000M2301 | Maintenance Framework | 2112569 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting |  | 10000 |  | 10000 | 10000 | 0 | Green |  |  |  | 10000 |  |  | 22370 |  |  | 22370 | Full | 22370 |  | 10000 | 10000 | No | Green | 2023-12-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-08-31 | [19 empty] | 10000 |  | 3/20/23 CNC - project bid out for 2023 | 2023-03-20 | Schultz, Amy |  | West | Pipelines and Terminals | Integrity |  | St. Louis | ES - EAST ST LOUIS (MARATHON ASHLAN) |  |  | 0 |  | 10000 |  |  | Cole, Caitlyn | Stine, Carlton | N/A |  | 1 | 20235 |  | Guest, ProSight | Independent | Aqua | 2016-08-12 | Int - Tanks
Ferrysburg East Terminal API 570 Inspection | Item | Open | MEXP | BETFG00E2301 | Exempt | 2093433 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 26000 |  | 26000 | 26000 | 0 | Green | 26000 |  | 26000 | 0 |  |  | 26000 |  |  | 26000 | Phase | 26000 |  | 26000 | 26000 | No | Green | 2023-06-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-08-31 | [13 empty] | 26000 | [7 empty] | 4/25/23 SL - Project to start in May | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Michiana | BETFG - BET FERRYSBURG TERMINAL |  |  | 26000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45038 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Flint Terminal TK15 Exterior Recoat | Item | Open | MCAP | BETWF00M2303 | Maintenance Framework | 2112570 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting |  | 55000 |  | 55000 | 55000 | 0 | Green |  |  |  | 55000 |  |  | 70015 |  |  | 70015 | Full | 70015 |  | 55000 | 55000 | No | Green | 2023-12-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-08-31 | [19 empty] | 55000 |  | 3/20/23 CNC - project bid out for 2023 (shell) | 2023-03-20 | Schultz, Amy |  | West | Pipelines and Terminals | Integrity |  | Wayne Terminals | BETWF - BET FLINT TERMINAL |  |  | 0 |  | 55000 |  |  | Cole, Caitlyn | Stine, Carlton | N/A |  | 1 | 31105 |  | Guest, ProSight | Independent | Aqua | 2018-08-28 | Int - Tanks
Granger Insulated Pipe Phase 2 Inspection | Item | Open | MEXP |  | Exempt |  | Aiken, Elaine | Asset Integrity | 2. Pending AFE |  | Facility Integrity |  | 110000 |  | 110000 | 110000 | 0 | Green | 110000 |  | 110000 | 0 | [9 empty] | 110000 | 110000 | No | Green | 2023-08-01 |  |  |  | 2023-07-31 | [15 empty] | 50000 | 60000 | [8 empty] | West | Pipelines and Terminals | Station/Terminal |  | Michiana | BETAI - BET GRANGER |  |  | 0 | 110000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45064 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Granger Terminal API 570 Inspection | Item | Open | MEXP | BETAI00E2301 | Exempt | 2093448 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 33000 |  | 33000 | 33000 | 0 | Green | 33000 |  | 33000 | 0 |  |  | 33000 |  |  | 33000 | Phase | 33000 |  | 33000 | 33000 | No | Green | 2023-06-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-07-31 | [13 empty] | 33000 | [7 empty] | 4/25/23 SL - Project to start in May | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Michiana | BETAI - BET GRANGER |  |  | 33000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45013 |  | Administrator, System | Independent |  | 2022-08-18 | Int - Planned Corr & FI
Greensboro II Terminal (BSEVV) LPG Tanks Onstream Inspections | Item | Open | MEXP | BSEVV00E2302 | Maintenance Framework | 2093561 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Pressure Vessels |  | 28000 |  | 28000 | 28000 | 0 | Green | 28000 |  | 28000 | 0 |  |  | 30800 |  |  | 30800 | Full | 30800 |  | 28000 | 28000 | No | Green | 2023-05-01 | 2023-03-02 | 2023-03-02 | 2023-12-31 | 2023-04-30 | [6 empty] | 28000 | 28000 | -28000 | Red |  | Forecasting | 28000 | [8 empty] | 5/43/23 CNC - project scheduled for May. 3/16/23 CNC - $28k forecast to be moved to June. | 2023-05-03 | Schultz, Amy |  | South | Pipelines and Terminals | Tank Integrity |  | North Carolina | BSEVV - GREENSBORO II TERMINAL |  |  | 28000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44747 |  | Administrator, System | Independent | Aqua | 2022-08-18 | Int - Tanks
Greensburg Terminal API 570 Inspection | Item | Open | MEXP | BETGM00E2301 | Exempt | 2093434 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 29000 |  | 29000 | 29000 | 0 | Green | 29000 |  | 29000 | 0 |  |  | 29000 |  |  | 29000 | Phase | 29000 |  | 29000 | 29000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-09-30 | [14 empty] | 29000 | [6 empty] | 4/25/23 SL - Project to start in June | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Duncansville | BETGM - BET GREENSBURG |  |  | 0 | 29000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45025 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Hartsdale Terminal (BETHD) Tank 1619 Painting | Item | Open | MCAP | BETHD00M2304 | Maintenance Framework | 2112571 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting |  | 115000 |  | 115000 | 115000 | 0 | Green |  |  |  | 115000 |  |  | 137940 |  |  | 137940 | Full | 137940 |  | 115000 | 115000 | No | Green | 2023-12-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-12-31 | [19 empty] | 115000 |  | 4/5/2023 CNC - project bid out for 2023 (shell and roof) | 2023-04-05 | Schultz, Amy |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETHD - BET HARTSDALE TERMINAL |  |  | 0 |  | 115000 |  |  | Cole, Caitlyn | Stine, Carlton |  |  | 1 | 46814 |  | Cole, Caitlyn | Independent | Aqua | 2023-03-20
Huntington BDL API 570 Inspection | Item | Open | MEXP | BDLHN00E2301 | Exempt | 2093431 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 18000 |  | 18000 | 18000 | 0 | Green | 18000 |  | 18000 | 0 |  |  | 18000 |  |  | 18000 | Phase | 18000 |  | 18000 | 18000 | No | Green | 2023-05-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-06-30 | [12 empty] | 18000 | [8 empty] | 4/25/23 SL - 1st site visit and drawings complete, inspection visit to follow | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Huntington | BDLHN - HUNTINGTON - BDL |  |  | 18000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45030 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
L001 2023 MEXP FLIPS | Item | Open | MEXP | KZ001LKE2301 | Maintenance Framework | 2094181 | Bartal, Nick | Asset Integrity | 3. Active | Drawdown | Pipeline Digs | 34151 |  |  | 34150.58 | 34151 | 0 | Green |  |  |  | 34151 |  |  | 34151 |  |  | 34151 | Full | 34151 | 34151 |  | 34151 | No | Green | 2023-03-01 | 2023-03-07 | 2023-03-07 | 2023-12-31 | 2023-12-31 |  |  |  |  | 34150.58 | [16 empty] | 3.7.23 - $34,151 March forecast due to flip from KZ001LKM2202 (AS) | 2023-03-07 |  |  | West | Pipelines and Terminals | Pipeline Integrity |  | Michiana | KZ001LK - KOUTS TO LAKETON |  | 34151 | 0 |  |  |  |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 46715 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-03-07
L003 2022 MEXP Flips | Item | Open | MEXP | XB003XXE2201 | Maintenance Framework | 1970339 | Bartal, Nick | Asset Integrity | 3. Active | Drawdown | Pipeline Digs | 196952 |  |  | 196952.34 | 196952 | 0 | Green |  |  |  | 196952 |  |  | 52000 |  |  | 52000 | Full | 52000 | 240359 |  | 240359 | No | Green | 2022-03-01 | 2022-04-05 | 2022-04-05 | 2022-12-31 | 2022-12-31 |  |  |  |  | 196952.34 | [16 empty] | 4.6.23 - Forecast $195,952 in March due to Flip from XB003XXM2202 (AS) 4/8/22 - flips from MCAP | 2023-04-06 | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | Huntington | XB003XX - HUNTINGTON TO OHIO S/L- EAST |  | 196952 | 0 |  |  | 43407 |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 43344 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-04-05 | Int- Planned Digs
L150 2022 MEXP Flips | Item | Open | MEXP | HD150WHE2201 | Maintenance Framework | 1989677 | Bartal, Nick | Asset Integrity | 3. Active | Drawdown | Pipeline Digs | 291701 |  |  | 291701.24 | 291701 | 0 | Green |  |  |  | 291701 |  |  | 276000 |  |  | 276000 | Full | 276000 | 579540 |  | 579540 | No | Green | 2022-06-01 | 2022-06-06 | 2022-06-06 | 2022-07-31 | 2022-12-31 |  |  |  |  | 291701.24 | [16 empty] | 4.6.23 - Added $179,433 to March forecast due to flip from HD150WHE2201 (AS) 11 3.7.23 - March forecast $112,269 due to flip from HD150WHM2201 (AS) 9/12/22 - $8465 related to Sept Flip (AS) 6/8/22 - project added for planned flips to MEXP | 2023-04-06 | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | Michiana | HD150WH - HARTSDALE TO WHEELER |  | 291701 | 0 |  |  | 287839 |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 43883 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-06-06 | Int - Accel Digs
L156 2022 MEXP FLIPS | Item | Open | MEXP | HD156KGE2201 | Maintenance Framework | 2036226 | Bartal, Nick | Asset Integrity | 3. Active | Drawdown | Pipeline Digs | 44870 |  |  | 44870.07 | 44870 | 0 | Green |  |  |  | 44870 |  |  | 3512 |  |  | 3512 | Full | 3512 | 1562358 |  | 1562358 | No | Green | 2022-11-01 | 2022-10-07 | 2022-10-07 | 2022-10-31 | 2022-12-31 |  |  | -0.1 | 42536.02 | 2334.15 | [16 empty] | 4.6.23 - Added $6,381 to March forecast due to flip from HD156KGM2201 (AS) 3.7.23 - March forecast $2,334 due to flip from HD156KGM2201 (AS) 3.2.23 - Added $42,536 to February forecast due to flip from HD156KGM2201 (AS) 1/6/23 - Added $17,367 to December forecast due to Flip from HD156KGM2201 (AS) 12/6/22 - December forecast $1,421,798 due to Flip from HD156KGE2201 (AS) 11/8/22 - November forecast $3,512 due to Flip from HD156KGE2201 (AS) 10/7/22 - $3,512 in October due to Flip from HD156KGM2201 (AS) | 2023-04-06 | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | HD156KG - HARTSDALE TO LAKE GEORGE |  | 44870 | 0 |  |  | 1517488 |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 46011 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-10-07 | Int- Planned Digs
L162-L164 Lab Analysis | Item | Open | MEXP | IJ162JUE2201 | Maintenance Framework | 2051852 | Bartal, Nick | Asset Integrity | 3. Active | Drawdown | Pipeline Digs | 21000 | 31000 |  | 52000 | 21000 | 31000 | Red |  |  |  | 52000 |  |  | 42000 |  |  | 42000 | Full | 42000 | 31000 | 31000 | 62000 | No | Green | 2022-12-01 | 2022-12-09 | 2022-12-09 | 2023-02-28 | 2023-02-28 |  |  | 0 | 21000 | 0 | 0 |  |  | 0 | Green |  | Other | 31000 | [8 empty] | 5/8/23 - Accrual didn't post, reforecast for May. 4.4.23 - Accrual $31,000 (AS) 3.2.23 - Accrual $31,000 (AS) 2/7/23 - lab work still in process - forecast moved to Feb. 1/9/23 - Work began and accrued in Dec | 2023-05-08 | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | IJ - INDIANAOPOLIS BLVD JCT |  | 21000 | 31000 |  |  | 10000 |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 46345 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-12-09 | Int- Planned Digs
L163 2023 MEXP FLIPS | Item | Open | MEXP | EU163JUE2301 | Maintenance Framework | 2109963 | Bartal, Nick | Asset Integrity | 3. Active | Drawdown | Pipeline Digs | 91690 | 409 |  | 92099.03 | 91690 | 409 | Yellow |  |  |  | 92099 |  |  | 91690 |  |  | 91690 | Full | 91690 | 91690 | 409 | 92099 | No | Green | 2023-03-01 | 2023-04-06 | 2023-04-06 | 2023-12-31 | 2023-12-31 |  |  |  |  | 91690.03 | [7 empty] | 409 | [8 empty] | 5.8.23 - $409 forecast in May due to flip from EU163JUM2201 (AS) 4.6.23 - $91,690 in March due to Flip from EU163JUM2201 (AS) | 2023-05-08 | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | Michiana | EU163JU - E CHICAGO B/G TO HAMMOND J B/G |  | 91690 | 409 |  |  |  |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 46885 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-04-06
L201 2022 MEXP Flips | Item | Open | MEXP | WD201WJE2201 | Maintenance Framework | 1970337 | Bartal, Nick | Asset Integrity | 3. Active | Drawdown | Pipeline Digs | 167 |  |  | 166.95 | 167 | 0 | Green |  |  |  | 167 |  |  | 172000 |  |  | 172000 | Full | 172000 | 178803 |  | 178803 | No | Green | 2022-03-01 | 2022-04-05 | 2022-04-05 | 2022-12-31 | 2022-12-31 |  |  | 166.95 | [18 empty] | 9/12/22 - $3,964 related to Flip (AS) 4/8/22 - flips from MCAP | 2022-09-12 | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | Wayne Pipeline | WD201WJ - DETROIT TO JOAN RD JCT 10IN |  | 167 | 0 |  |  | 178636 |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 43343 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-04-05 | Int- Planned Digs
L302 2022 MEXP Flips | Item | Open | MEXP | DS302CGE2203 | Exempt | 1948138 | Bartal, Nick | Asset Integrity | 3. Active | Drawdown | Pipeline Digs | 544945 | 5500 |  | 550445.49 | 544945 | 5500 | Yellow |  |  |  | 550445 |  |  | 188000 |  |  | 188000 | Full | 188000 | 1556387 | 5500 | 1561887 | No | Green | 2022-02-01 | 2022-02-28 | 2022-02-28 | 2022-12-31 | 2022-12-31 |  |  |  |  | 544945.49 | [7 empty] | 5500 | [8 empty] | 5.8.23 - $5,500 forecasted in May due to flip from DS302CGE2203 (AS) 4.6.23 - Added $297 to March forecast for additional flip from DS302CGM2201 (AS) 3.7.23 - March forecast of $554,648 due to flips from DS302CGM2201 $128,635 and DS302CGM2103 $416,013 (AS) 9/12/22 - $542,331 related to Flip DS302CGM2103 (AS) 3/8/22 - Flips from MCAP projects. Covered by budget allocation | 2023-05-08 | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | Toledo | DS302CG - TOLEDO TO CYGNET 10IN SOUTH |  | 544945 | 5500 |  |  | 1011441 |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 43039 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-02-28 | Int- Planned Digs
L403 2023 MEXP FLIPS | Item | Open | MEXP | XB403CLE2301 | Maintenance Framework | 2109972 | Bartal, Nick | Asset Integrity | 3. Active | Drawdown | Pipeline Digs | 52345 |  |  | 52345.16 | 52345 | 0 | Green |  |  |  | 52345 |  |  | 52345 |  |  | 52345 | Full | 52345 | 52345 |  | 52345 | No | Green | 2023-03-01 | 2023-04-06 | 2023-04-06 | 2023-12-31 | 2023-12-31 |  |  |  |  | 52345.16 | [16 empty] | 4.6.23 - $52,345 March forecast due to Flip from XB4CLM2201(AS) | 2023-04-06 | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | Huntington | XB403CL - HUNTINGTON TO CLERMONT |  | 52345 | 0 |  |  |  |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 46888 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-04-06
L521 2021 MEXP Flips | Item | Open | MEXP | GE521ZCE2102 | Exempt | 1910752 | Bartal, Nick | Asset Integrity | 7. Closed | Drawdown | Pipeline Digs | 81 |  |  | 81 | 81 | 0 | Green |  |  |  | 81 |  |  | 27000 |  |  | 27000 | Full | 27000 | 26911 |  | 26911 | No | Green | 2021-11-01 | 2021-11-29 | 2021-11-29 | 2021-12-31 | 2021-12-31 |  |  |  | 81 | [19 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | Mantua | GE521ZC - MANTUA TO COLUMBIANA |  | 81 | 0 |  |  |  |  | Bartal, Nick | Bassani, Joel D. | N/A |  | 1 | 42513 |  | Schultz, Amy | JDE Child | Burnt Orange | 2021-11-29
L531 2023 MEXP FLIPS | Item | Open | MEXP | OD531YOE2301 | Maintenance Framework | 2109969 | Bartal, Nick | Asset Integrity | 3. Active | Drawdown | Pipeline Digs | 72600 | 95666 |  | 168266.05 | 72600 | 95666 | Red |  |  |  | 168266 |  |  | 72600 |  |  | 72600 | Full | 72600 | 72600 | 95666 | 168266 | No | Green | 2023-03-01 | 2023-04-06 | 2023-04-06 | 2023-12-31 | 2023-12-31 |  |  |  |  | 72600.05 | [7 empty] | 95666 | [8 empty] | 5.8.23 - $95,666 forecast in May due to flip from OD531YOM2202 (AS) 4.6.23 - March forecast $72,600 due to flip from OD531YOM2202 (AS) | 2023-05-08 | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | Mantua | OD531YO - MOGADORE STA TO YOUNGSTOWN TER |  | 72600 | 95666 |  |  |  |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 46886 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-04-06
L601 ILI DATA COMPARISON | Item | Open | MEXP | LZ601XXE2301 |  | 2120209 | Bartal, Nick | Asset Integrity | 3. Active | Drawdown | Pipeline Digs |  | 18000 |  | 18000 |  | 18000 | Red |  |  |  | 18000 |  |  | 18000 |  |  | 18000 | Full | 18000 |  | 18000 | 18000 | No | Green | 2023-05-01 | 2023-05-05 | 2023-05-05 | 2023-06-30 | 2023-06-30 | [12 empty] | 18000 | [10 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Pipeline Integrity |  | Long Island | LZ601XX - LINDEN TO NY S/L (FUEL) LIPL |  |  | 18000 |  |  |  |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 47031 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-05-05
L751 SLEEVE ANALYSIS | Item | Open | MEXP | RX751BXE2301 | Maintenance Framework | 2052938 | Bartal, Nick | Asset Integrity | 3. Active | Drawdown | Pipeline Digs | 60000 | 30000 |  | 90000 | 90000 | 0 | Green |  |  |  | 90000 |  |  | 120000 |  |  | 120000 | Full | 120000 | 60000 | 30000 | 90000 | No | Green | 2023-02-01 | 2022-12-20 | 2022-12-20 | 2023-03-31 | 2023-03-31 |  |  |  | 30000 | 0 | 30000 | 60000 | 60000 | -30000 | Red |  | Other | 30000 | [8 empty] | 5/8/23 - Accrual didn't post, reforecast for May. 4.4.23 - Accrual $30,000 (AS) 3/7/23 - work slightly behind schedule, lab was waiting on hydrotest pump repairs. 3.2.23 - Accrual $30,000 (AS) | 2023-05-08 | Schultz, Amy |  | East | Pipelines and Terminals | Pipeline Integrity |  | Auburn Pipeline | RX751BX - ROCHESTER JCT - BATAVIA STATIO |  | 30000 | 60000 |  |  |  |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 46392 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-12-20 | Int- Planned Digs
L760 2022 MEXP Flips | Item | Open | MEXP | HH760OTE2202 | Exempt | 1948134 | Bartal, Nick | Asset Integrity | 3. Active | Drawdown | Pipeline Digs | 145 |  |  | 144.63 | 145 | 0 | Green |  |  |  | 145 |  |  | 121000 |  |  | 121000 | Full | 121000 | 80900 |  | 80900 | No | Green | 2022-02-01 | 2022-02-28 | 2022-02-28 | 2022-12-31 | 2022-12-31 |  |  | 144.63 | [18 empty] | 12/6/22 - $145 forecast in December due to Flip from HH760OTM2201 (AS) 9/14/22 - $5,285 related to Flip XX760IMM2201 (AS) 9/12/22 - $16,588 related to Flip HH760OTM2201 (AS) 4/8/22 - flips from MCAP 3/8/22 - Flips from MCAP projects. Covered by budget allocation | 2022-12-06 | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | Eastern Iowa | HH760OT - HARPER STA TO OTTUMWA STA |  | 145 | 0 |  |  | 80755 |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 43034 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-02-28 | Int- Planned Digs
L760 2023 MEXP FLIPS | Item | Open | MEXP | AR760HHE2302 | Maintenance Framework | 2109960 | Bartal, Nick | Asset Integrity | 3. Active | Drawdown | Pipeline Digs | 33351 | 2088 |  | 35439.49 | 33351 | 2088 | Yellow |  |  |  | 35439 |  |  | 33351 |  |  | 33351 | Full | 33351 | 33351 | 2088 | 35439 | No | Green | 2023-03-01 | 2023-04-06 | 2023-04-06 | 2023-12-31 | 2023-12-31 |  |  |  |  | 33351.49 | [7 empty] | 2088 | [8 empty] | 5.8.23 - $2,088 forecast in May due to flip from AR760HHM2302 (AS) 4.6.23 - $33,351 forecast in March due to Flip from AR760HHM2302 (AS) | 2023-05-08 | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | Eastern Iowa | AR760HH - CEDER RAPIDS TO HARPER STA |  | 33351 | 2088 |  |  |  |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 46884 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-04-06
L999 2023 MEXP FLIPS | Item | Open | MEXP | EH999A1E2301 | Maintenance Framework | 2109971 | Bartal, Nick | Asset Integrity | 3. Active | Drawdown | Pipeline Digs |  |  |  | 0 |  | 0 | Green | [6 empty] | 6381 |  |  | 6381 | Full | 6381 |  |  |  | No | Green |  | 2023-04-06 | 2023-04-06 | 2023-12-31 | 2023-12-31 | [21 empty] | 4.6.23 - $6,381 March forecast due to flip from EH999A1M2101 (AS) | 2023-04-06 | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | EH999A1 - HAMMOND - NORTH PROP GAS |  |  | 0 |  |  |  |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 46887 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-04-06
Lima North Insulated Pipe Phase 2 Inspection | Item | Open | MEXP |  | Exempt |  | Aiken, Elaine | Asset Integrity | 2. Pending AFE |  | Facility Integrity |  | 110000 |  | 110000 | 110000 | 0 | Green | 110000 |  | 110000 | 0 | [9 empty] | 110000 | 110000 | No | Green | 2023-09-01 |  |  |  | 2023-07-31 | [16 empty] | 50000 | 60000 | [7 empty] | West | Pipelines and Terminals | Station/Terminal |  | Lima Terminals | BETLM - BET MA NORTH TERMINAL |  |  | 0 | 50000 | 60000 |  |  | Aiken, Elaine |  |  |  | 1 | 45059 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Lima North Insulated Pipe Priority 2 Repairs | Item | Open | MEXP |  | Exempt |  | Aiken, Elaine | Asset Integrity | 2. Pending AFE |  | Facility Integrity |  | 45000 |  | 45000 | 45000 | 0 | Green | 45000 |  | 45000 | 0 | [9 empty] | 45000 | 45000 | No | Green | 2023-07-01 |  |  |  | 2023-05-31 | [14 empty] | 45000 | [10 empty] | West | Pipelines and Terminals | Station/Terminal |  | Lima Terminals | BETLM - BET MA NORTH TERMINAL |  |  | 0 | 45000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45068 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Lima North Priority 3 API 570 Refurbishments | Item | Open | MCAP |  | Exempt |  | Aiken, Elaine | Asset Integrity | 2. Pending AFE |  | Facility Integrity |  | 45000 |  | 45000 | 45000 | 0 | Green | 45000 |  | 45000 | 0 | [9 empty] | 45000 | 45000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 25000 | 20000 | [9 empty] | West | Pipelines and Terminals | Integrity |  | Lima Terminals | BETLM - BET MA NORTH TERMINAL |  |  | 0 | 45000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45050 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Lima Station API 570 Inspection | Item | Open | MEXP | LA00000E2301 | Exempt | 2093459 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 47000 |  | 47000 | 47000 | 0 | Green | 47000 |  | 47000 | 0 |  |  | 47000 |  |  | 47000 | Phase | 47000 |  | 47000 | 47000 | No | Green | 2023-06-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-06-30 | [13 empty] | 47000 | [7 empty] | 4/25/23 SL - Project to start in May | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Lima Pipelines | LA - LIMA STATION |  |  | 47000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45007 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Lima Station Tank 400 | Item | Open | MCAP | LA00000M2306 | Maintenance Framework | 2112572 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting |  | 65000 |  | 65000 | 65000 | 0 | Green |  |  |  | 65000 |  |  | 85690 |  |  | 85690 | Full | 85690 |  | 65000 | 65000 | No | Green | 2023-12-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-08-31 | [19 empty] | 65000 |  | 3/20/23 CNC - project bid out for 2023 (shell and roof) | 2023-03-20 | Schultz, Amy |  | West | Pipelines and Terminals | Integrity |  | Lima Pipelines | LA - LIMA STATION |  |  | 0 |  | 65000 |  |  | Cole, Caitlyn | Stine, Carlton | N/A |  | 1 | 25060 |  | Guest, ProSight | Independent | Aqua | 2017-08-18 | Int - Tanks
Linden Station (LN) Tank 101 Painting | Item | Open | MCAP | LN00000M2316 | Maintenance Framework | 2112596 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting |  | 55000 |  | 55000 | 55000 | 0 | Green |  |  |  | 55000 |  |  | 77852 |  |  | 77852 | Full | 77852 |  | 55000 | 55000 | No | Green | 2023-07-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-12-31 | [14 empty] | 55000 | [6 empty] | 4/5/2023 CNC - project bid out for 2023 (shell and roof) | 2023-04-05 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Linden | LN - LINDEN STATION |  |  | 0 | 55000 |  |  |  | Cole, Caitlyn | Stine, Carlton |  |  | 1 | 46815 |  | Cole, Caitlyn | Independent | Aqua | 2023-03-20
Linden Station (LN) Tank 119 Painting | Item | Open | MCAP | LN00000M2317 | Maintenance Framework | 2112573 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting |  | 75000 |  | 75000 | 75000 | 0 | Green |  |  |  | 75000 |  |  | 77852 |  |  | 77852 | Full | 77852 |  | 75000 | 75000 | No | Green | 2023-07-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-12-31 | [14 empty] | 75000 | [6 empty] | 4/5/2023 CNC - project bid out for 2023 (shell and roof) | 2023-04-05 | Schultz, Amy |  | East | Pipelines and Terminals | Integrity |  | Linden | LN - LINDEN STATION |  |  | 0 | 75000 |  |  |  | Cole, Caitlyn | Stine, Carlton |  |  | 1 | 46816 |  | Cole, Caitlyn | Independent | Aqua | 2023-03-20
Linden VFD Pump Tubing Failure Analysis | Item | Open | MEXP | LN00000E2212 | Maintenance Framework | 2051764 | Aiken, Elaine | Asset Integrity | 3. Active | Emergent | Facility Integrity | 4500 |  |  | 4500 | 3250 | 1250 | Red |  |  |  | 4500 |  |  | 14000 |  |  | 14000 | Full | 14000 | 12500 |  | 12500 | No | Green | 2022-12-01 | 2022-12-08 | 2022-12-08 | 2023-01-31 | 2023-01-31 |  |  | 3250 | 0 | 0 | 1250 |  |  | 1250 | Red | [11 empty] | 4.4.23 - Accrual $11,250. Waiting on invoicing (AS) 3.2.23 - Accrual $11,250. Waiting on invoicing (AS) | 2023-04-04 | Schultz, Amy |  | East | Pipelines and Terminals | Station/Terminal |  | Linden | LN - LINDEN STATION |  | 3250 | 1250 |  |  | 8000 |  | Aiken, Elaine | Shook, Mark B. |  |  | 1 | 46287 |  | Aiken, Elaine | Independent | Aqua | 2022-12-02 | Int - Planned Corr & FI
Louisville API 570 Inspection | Item | Open | MEXP | BETVL00E2301 | Exempt | 2093442 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 33600 |  | 33600 | 31000 | 2600 | Yellow | 31000 |  | 31000 | 2600 |  |  | 31000 |  |  | 31000 | Phase | 31000 |  | 33600 | 33600 | No | Green | 2023-06-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-09-30 | [13 empty] | 33600 | [7 empty] | 4/25/23 SL - Project to start in May | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Southern Ohio | BETVL - BET LOUISVILLE |  |  | 33600 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45023 |  | Administrator, System | Independent |  | 2022-08-18 | Int - Planned Corr & FI
Macungie South Tank 224 Painting | Item | Open | MCAP | BETZG00M2303 | Maintenance Framework | 2112598 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting |  | 50000 |  | 50000 | 50000 | 0 | Green |  |  |  | 50000 |  |  | 64790 |  |  | 64790 | Full | 64790 |  | 50000 | 50000 | No | Green | 2023-06-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-06-30 | [13 empty] | 50000 | [7 empty] | 5/43/23 CNC - project scheduled for May 22 3/20/23 CNC - project bid out for 2023 (shell) | 2023-05-03 | Schultz, Amy |  | East | Pipelines and Terminals | Integrity |  | Macungie Terminal | BETZG - BET MACUNGIE TERMINAL |  |  | 50000 |  |  |  |  | Cole, Caitlyn | Stine, Carlton |  |  | 1 | 37208 |  | Guest, ProSight | Independent | Aqua | 2020-07-22 | Int - Tanks
Macungie Station (ZG) - Repaint Tank 203 | Item | Open | MCAP | ZG00000M2309 | Maintenance Framework | 2112597 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting |  | 60000 |  | 60000 | 60000 | 0 | Green |  |  |  | 60000 |  |  | 75240 |  |  | 75240 | Full | 75240 |  | 60000 | 60000 | No | Green | 2023-06-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-07-31 | [13 empty] | 60000 | [7 empty] | 5/43/23 CNC - project scheduled for May 22 3/20/23 CNC - project bid out for 2023 (shell and roof) 7/15/21 BH: Tank coating condition is marginal with significant signs of rust. Delaying repainting this tank will result in additional expense to blast the tank shell to remove rust. | 2023-05-03 | Schultz, Amy |  | East | Pipelines and Terminals | Integrity |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 60000 |  |  |  |  | Cole, Caitlyn | Stine, Carlton |  |  | 1 | 40173 |  | Guest, ProSight | Independent | Aqua | 2021-05-26 | Int - Tanks
Macungie Station (ZG) Tank 230 - OOS Corr + Seal Insp & Refurb | Item | Open | MCAP | ZG00000M2201 | Maintenance Framework | 1937279 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tanks | 9290 |  |  | 9290.06 | 7435 | 1855 | Red |  |  |  | 9290 |  |  | 263000 |  |  | 263000 | Phase | 263000 | 300274 |  | 300274 | No | Green | 2022-08-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-12-31 |  |  | 3069.8 | 2831.59 | 1533.32 | 1855.35 |  |  | 1855 | Red | [11 empty] | 11/3/22 CNC - RTS MOC issued. 10/4/22-CES Minor piping modifications planned for October. 10/4/22 CNC - accruing Barr None $29k (late approval) 9/2/2022-CNC-accruing $20,000 for PCMS Group and $7,000 for DJA in August. 8/29/22-CNC-$90,191 budgeted for repairs. Lowering forecast due to minor repairs. 8/25/22-CNC-inspection completed. 20 patches, liner repair, and other minor repairs anticipated. 8/2/22-CES-Plan for tank cleaning and inspection in August, Repairs in September/October.7/12/22 CNC- tank planned to be emptied by 8/8/22 and cleaned that week. 6/2/22-CES-Per alignment with Regional PM team, transition project to Caitlyn Cole. 6/2/22 - Push forecast to July. Plan to take OOS late-July. | 2022-11-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Macungie Pipe | ZG - MACUNGIE STATION |  | 7435 | 1855 |  |  | 290983 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41285 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Macungie Station API 570 Inspection | Item | Open | MEXP | BETZG00E2301 | Maintenance Framework | 2093465 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 63000 |  | 63000 | 63000 | 0 | Green | 63000 |  | 63000 | 0 |  |  | 63000 |  |  | 63000 | Phase | 63000 |  | 63000 | 63000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-05-31 | [14 empty] | 63000 | [6 empty] | 4/25/23 SL - Project to start in June | 2023-04-25 | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | Macungie Terminal | BETZG - BET MACUNGIE TERMINAL |  |  | 0 | 63000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45003 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Macungie Station Baseline Facility Assessment | Item | Open | MEXP | BETZG00E2201 | Exempt | 2045716 | Aiken, Elaine | Asset Integrity | 6. Operational | Defined | Facility Integrity | 1579 |  |  | 1578.57 | 1579 | 0 | Green |  |  |  | 1579 |  |  | 30000 |  |  | 30000 | Full | 30000 | 17579 |  | 17579 | No | Green | 2022-12-01 | 2022-11-22 | 2022-11-22 | 2022-12-31 | 2022-12-31 |  |  | 1578.57 | [20 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Station/Terminal |  | Macungie Terminal | BETZG - BET MACUNGIE TERMINAL |  | 1579 | 0 |  |  | 16000 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 41197 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
Malvern Terminal (BETMX) Tank 1-A Tank Painting | Item | Open | MCAP | BETMX00M2301 | Maintenance Framework | 2093299 | Cole, Caitlyn | Asset Integrity | 2. Pending AFE | Defined | Tank Painting | 6997 |  |  | 6996.6 | 6695 | 301 | Yellow |  | 58000 | 58000 | -51003 |  |  | 6061 |  |  | 6061 | Full | 6061 | 6997 |  | 6997 | No | Green | 2023-03-01 | 2023-03-01 | 2023-03-01 | 2023-12-31 | 2023-03-31 |  |  |  |  | 6695.32 | 301.28 |  |  | 301 | Red | [11 empty] | 3/9/23 CNC - painting began 6/7/23 with Barr None. To be completed today. This tank was called out during an external inspection and would have received an NOV from PADEP without painting. | 2023-03-20 | Schultz, Amy |  | East | Pipelines and Terminals | Integrity |  | Malvern | BETMX - BET MALVERN TERMINAL |  | 6695 | 301 |  |  |  |  | Cole, Caitlyn | Stine, Carlton |  |  | 1 | 46625 |  | Cole, Caitlyn | Independent | Aqua | 2023-02-22
Mantua Station API 570 Inspection | Item | Open | MEXP | GE00000E2303 | Exempt | 2093440 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 |  |  | 30000 |  |  | 30000 | Phase | 30000 |  | 30000 | 30000 | No | Green | 2023-05-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-06-30 | [12 empty] | 30000 | [8 empty] | 4/25/23 SL - Project to start in May | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Mantua | GE - MANTUA STATION |  |  | 30000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45019 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Milan API 570 Inspection | Item | Open | MEXP | IM00000E2301 | Exempt | 2093435 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 29000 |  | 29000 | 29000 | 0 | Green | 29000 |  | 29000 | 0 |  |  | 29000 |  |  | 29000 | Phase | 29000 |  | 29000 | 29000 | No | Green | 2023-05-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-04-30 | [12 empty] | 29000 | [8 empty] | 4/25/23 SL - 1st site visit and drawings complete, inspection visit to follow | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Sugar Creek | IM - MILAN STATION |  |  | 29000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45036 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Napoleon API 570 Inspection | Item | Open | MEXP | BETNP00E2301 | Exempt | 2093450 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 33000 |  | 33000 | 33000 | 0 | Green | 33000 |  | 33000 | 0 |  |  | 33000 |  |  | 33000 | Phase | 33000 |  | 33000 | 33000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-07-31 | [14 empty] | 33000 | [6 empty] | 4/25/23 SL - Project to start in May | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Terminals | BETNP - BET NAPOLEON |  |  | 0 | 33000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45016 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
New Haven 85 East Terminal API 570 Inspection | Item | Open | MEXP | BNTNX00E2301 | Maintenance Framework | 2093451 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 33000 |  | 33000 | 33000 | 0 | Green | 33000 |  | 33000 | 0 |  |  | 33000 |  |  | 33000 | Phase | 33000 |  | 33000 | 33000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-06-30 | [14 empty] | 33000 | [6 empty] | 4/25/23 SL - Project to start in June | 2023-04-25 | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | New Haven Harbor | BNTNX - New Haven 85 East Terminal |  |  | 0 | 33000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45033 |  | Administrator, System | Independent |  | 2022-08-18 | Int - Planned Corr & FI
New Haven Dock Line API-570 Inspections | Item | Open | MEXP | BNTNV00E2205 | Maintenance Framework | 2022750 | Wojton, Brian | Asset Integrity | 6. Operational | Drawdown | Facility Integrity | 5760 |  |  | 5760.27 | 13570 | -7810 | Red |  |  |  | 5760 |  |  | 100000 |  |  | 100000 | Full | 100000 | 127303 |  | 127303 | No | Green | 2022-09-01 | 2022-09-16 | 2022-09-16 | 2022-12-31 | 2023-03-31 |  |  | 13570.27 | 0 | 0 | -7810 |  |  | -7810 | Red | [11 empty] | 4.3.23 - Accrual $7,810. Waiting on Invoicing (AS) 3.2.23 - Accrual $7,810. Waiting on Invoicing (AS) 2/2/23 - $7,810 accrued for December by Max Bragg (AS) 1/5/23 - $7,810 accrued for December by Max Bragg (AS) 12/2/2022 - Accrual error by Facility Integrity, and vendor invoiced in full. 11/2/22 - Waiting on invoicing (AS) 2022-09-23 - Additional $10,000 will be needed to fund the inspections. Will be sourced from Underground Tank Inspection project which will be under budget. | 2023-04-04 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  | 13570 | -7810 |  |  | 121543 |  | Aiken, Elaine | Shook, Mark B. | N/A |  | 1 | 45431 |  | Aiken, Elaine | JDE Child | Burnt Orange | 2022-08-26 | Int - Planned Corr & FI
New Haven Forbes Street API 570 Inspection | Item | Open | MEXP | BNTNF00E2303 | Maintenance Framework | 2093452 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 33000 |  | 33000 | 33000 | 0 | Green | 33000 |  | 33000 | 0 |  |  | 33000 |  |  | 33000 | Phase | 33000 |  | 33000 | 33000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-06-30 | [14 empty] | 33000 | [6 empty] | 4/25/23 SL - Project to start in June | 2023-04-25 | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | New Haven Harbor | BNTNF - New Haven Forbes Termina |  |  | 0 | 33000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45034 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
New Haven Hamden Terminal API 570 Inspection | Item | Open | MEXP | BNTNH00E2301 | Maintenance Framework | 2093505 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 33000 |  | 33000 | 33000 | 0 | Green | 33000 |  | 33000 | 0 |  |  | 33000 |  |  | 33000 | Phase | 33000 |  | 33000 | 33000 | No | Green | 2023-06-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-06-30 | [13 empty] | 33000 | [7 empty] | 4/25/23 SL - Project to start in May | 2023-04-25 | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | New Haven Harbor | BNTNH - New Haven Hamden Terminal |  |  | 33000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45032 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
New Haven Station API 570 Inspection | Item | Open | MEXP | EW00000E2301 | Maintenance Framework | 2093430 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 17000 |  | 17000 | 17000 | 0 | Green | 17000 |  | 17000 | 0 |  |  | 17000 |  |  | 17000 | Phase | 17000 |  | 17000 | 17000 | No | Green | 2023-07-01 | 2023-02-24 | 2023-02-24 | 2023-12-31 | 2023-07-31 | [14 empty] | 17000 | [6 empty] | 4/25/23 SL - Project to start in June | 2023-04-25 | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | Jet Lines | EW - NEW HAVEN STATION |  |  | 0 | 17000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45031 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
New Haven Waterfront API 570 Inspection | Item | Open | MEXP | BNTNV00E2301 | Maintenance Framework | 2093453 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 33000 |  | 33000 | 33000 | 0 | Green | 33000 |  | 33000 | 0 |  |  | 33000 |  |  | 33000 | Phase | 33000 |  | 33000 | 33000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-07-31 | [14 empty] | 33000 | [6 empty] | 4/25/23 SL - Project to start in June | 2023-04-25 | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  |  | 0 | 33000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45035 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Niles Terminal API 570 Inspection | Item | Open | MEXP | BETNM00E2301 | Exempt | 2093461 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 48000 |  | 48000 | 48000 | 0 | Green | 48000 |  | 48000 | 0 |  |  | 48000 |  |  | 48000 | Phase | 48000 |  | 48000 | 48000 | No | Green | 2023-06-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-12-31 | [13 empty] | 24000 |  |  | 24000 |  |  |  |  | 4/25/23 SL - Project to start in May | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Michiana | BETNM - BET NILES TERMINAL |  |  | 24000 | 24000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45028 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
North Augusta API 570 Inspection | Item | Open | MEXP | BETTW00E2301 | Maintenance Framework | 2093445 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity | 7475 | 24525 |  | 32000 | 32000 | 0 | Green | 32000 |  | 32000 | 0 |  |  | 32000 |  |  | 32000 | Phase | 32000 | 7475 | 24525 | 32000 | No | Green | 2023-04-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-03-31 | [5 empty] | 7475 | 32000 | 32000 | -24525 | Red |  |  |  | 24525 | [7 empty] | 4/25/23 SL - 1st site visit and drawings complete, inspection visit to follow | 2023-04-25 | Nguyen, Tong |  | South | Pipelines and Terminals | Station/Terminal |  | South Carolina | BETTW - BET NORTH AUGUSTA |  |  | 32000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45022 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Pennsauken API 570 Remediations | Item | Open | MCAP | BPNQP00M2207 | Maintenance Framework | 2011972 | Aiken, Elaine | Asset Integrity | 6. Operational | Drawdown | Facility Integrity | 2143 |  |  | 2143.09 | 2143 | 0 | Green |  |  |  | 2143 |  |  | 60000 |  |  |  | Full | 60000 | 95513 |  | 95513 | Yes | Red | 2022-11-01 |  |  | 2022-12-31 | 2022-12-31 |  |  | 1915.55 | 227.54 | 0 | 0 |  |  | 0 | Green | [11 empty] | 4.4.23 - Accrual $45,764. Waiting on invoicing (AS) 3.3.23 - Accrual $45,764. Waiting on invoicing (AS) 01/06/2023 - $45K coded to wrong project, BPNQP00M2201... Point Integrity invoices $45,764 to be reclassed to this project. 2022-11-03 - Work began 11/2 and forecasting led to negative October variance. 2022-08-05 - AFE has been submitted to workflow for approval. | 2023-04-04 | Schultz, Amy |  | East | Pipelines and Terminals | Integrity |  | Pennsauken | BPNQP - BPN PENNSAUKEN TERMINAL |  | 2143 | 0 |  |  | 93370 |  | Aiken, Elaine | Shook, Mark B. |  |  | 1 | 44321 |  | Meitzler, Antoinette | Independent | Aqua | 2022-07-29 | Int - Planned Corr & FI
Perth Amboy Circuit 14 Phase 2 Insulated Piping Inspection | Item | Open | MEXP | BPTPC00E2218 | Maintenance Framework | 2036929 | Aiken, Elaine | Asset Integrity | 6. Operational | Defined | Facility Integrity | -3480 |  |  | -3480 | -3480 | 0 | Green |  |  |  | -3480 |  |  | 55000 |  |  | 55000 | Full | 55000 | 20848 |  | 20848 | No | Green | 2022-11-01 | 2022-10-14 | 2022-10-14 | 2022-12-31 | 2022-12-31 |  |  | -3480 | [18 empty] | 2022-10-11 - Contractor scheduled to start end of October and complete the majority of the work in November. | 2022-10-11 | Schultz, Amy |  | East | Pipelines and Terminals | Station/Terminal |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | -3480 | 0 |  |  | 24328 |  | Aiken, Elaine | Hoover, Bret |  |  | 1 | 41175 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Accel Corr & FI
Perth Amboy Terminal (BPTPC) Tank 772 Painting | Item | Open | MCAP | BPTPC00M2304 | Maintenance Framework | 2112599 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting |  | 120000 |  | 120000 | 120000 | 0 | Green |  |  |  | 120000 |  |  | 143165 |  |  | 143165 | Full | 143165 |  | 120000 | 120000 | No | Green | 2023-12-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-12-31 | [19 empty] | 120000 |  | 4/5/2023 CNC - project bid out for 2023 (shell and roof) | 2023-04-05 | Schultz, Amy |  | East | Pipelines and Terminals | Integrity |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 0 |  | 120000 |  |  | Cole, Caitlyn | Stine, Carlton |  |  | 1 | 46818 |  | Cole, Caitlyn | Independent | Aqua | 2023-03-20
Pilot Repair Strategy Budget Allocation | Item | Open | MCAP |  | Maintenance Framework |  | Bartal, Nick | Asset Integrity | 1. Proposed |  | Pipeline Digs |  | 1250000 |  | 1250000 | 1500000 | -250000 | Red | 2500000 |  | 2500000 | -1250000 | [9 empty] | 1250000 | 1250000 | No | Green | 2023-08-01 |  |  |  | 2023-12-31 | [13 empty] | 0 | 0 | 500000 | 500000 | 250000 |  |  |  | 5/8/23 - Reduced by $250k to cover L001 cutouts forecast increase. 4/10/23 - Reduced by $1MM to cover L415 cutout forecast increase | 2023-05-08 |  |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Integrity |  | Corporate | Corporate |  |  | 0 | 1000000 | 250000 |  |  | Bartal, Nick |  |  |  | 1 | 44930 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Advanced Strategy
Pittsburgh API 570 Inspection | Item | Open | MEXP | BETRN00E2301 | Exempt | 2093457 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 38000 |  | 38000 | 38000 | 0 | Green | 38000 |  | 38000 | 0 |  |  | 38000 |  |  | 38000 | Phase | 38000 |  | 38000 | 38000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-05-31 | [14 empty] | 38000 | [6 empty] | 4/25/23 SL - Project to start in June | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Coraopolis | BETRN - BET PITTSBURGH |  |  | 0 | 38000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45010 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Port Reading Dock Line API-570 Inspection | Item | Open | MEXP | BPRPR00E2221 | Maintenance Framework | 2013794 | Aiken, Elaine | Asset Integrity | 6. Operational | Drawdown | Facility Integrity | 10671 |  |  | 10671.27 | 10671 | 0 | Green |  |  |  | 10671 |  |  | 100000 |  |  | 100000 | Full | 100000 | 106671 |  | 106671 | No | Green | 2022-10-01 | 2022-08-29 | 2022-08-29 | 2022-12-31 | 2022-12-31 |  |  | 10566.27 | 105 | [17 empty] | 11/2/22 - Waiting on invoicing (AS) 2022-10-11 - Inspection pushed to beginning of November due to construction work on the dock. | 2023-03-02 | Schultz, Amy |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 10671 | 0 |  |  | 96000 |  | Aiken, Elaine | Shook, Mark B. | N/A |  | 1 | 45420 |  | Aiken, Elaine | JDE Child | Burnt Orange | 2022-08-26 | Int - Planned Corr & FI
Port Wilmington API 570 Inspection | Item | Open | MEXP | BNTUE00E2301 | Maintenance Framework | 2093468 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 |  |  | 100000 |  |  | 100000 | Phase | 100000 |  | 100000 | 100000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-08-31 | [14 empty] | 100000 | [6 empty] | 4/25/23 SL - Project to start in June | 2023-04-25 | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | Port Wilmington | BNTUE - WIlmington(DE) Terminal |  |  | 0 | 100000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45000 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Port Wilmington Insulated Pipe Phase 2 Inspection | Item | Open | MEXP |  | Maintenance Framework |  | Aiken, Elaine | Asset Integrity | 2. Pending AFE |  | Facility Integrity |  | 145000 |  | 145000 | 145000 | 0 | Green | 145000 |  | 145000 | 0 | [9 empty] | 145000 | 145000 | No | Green | 2023-08-01 |  |  |  | 2023-09-30 | [15 empty] | 75000 | 70000 | [8 empty] | East | Pipelines and Terminals | Station/Terminal |  | Port Wilmington | BNTUE - WIlmington(DE) Terminal |  |  | 0 | 145000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45067 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Pressure Vessel Relief Valve Program Development | Item | Open | MEXP | 1348250E2243 | Maintenance Framework | 2045789 | Stine, Carlton | Asset Integrity | 3. Active | Emergent | Tanks | -12500 | 15000 |  | 2500 | -7500 | 10000 | Red |  |  |  | 2500 |  |  | 50000 |  |  | 50000 | Full | 50000 | 0 | 15000 | 15000 | No | Green | 2022-12-01 | 2022-11-23 | 2022-11-23 | 2023-03-31 | 2023-03-31 |  |  | 0 | -7500 | 0 | -5000 |  |  | -5000 | Red |  |  | 10000 | 5000 | [7 empty] | 5/3/23-CES-Accrue $5,000 to Diamond Z Engineering. Forecast $10,000 in May for Midstream. Working through PRDs in BEST.4.4.23 - Accrual $5,000 (AS) 3/2/23-CES-Accrue $5,000 to BECHT for relief valve development. 2/3/23-CES-Reaccrue work completed to BECHT. 1/4/23-CES-Pressure Vessel review underway. Accrue $12,500 for December. | 2023-05-03 | Sautter, Maureen |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Tank Integrity |  | Corporate | Corporate |  | -7500 | 10000 |  |  | 12500 |  | Stine, Carlton | Shook, Mark B. |  |  | 1 | 46260 |  | Meitzler, Antoinette | Independent | Aqua | 2022-11-22
Remediation Sangamon River Waterway Exposure 1 - DH162DU/DH163DU | Item | Open | MEXP |  | Exempt |  | Hurley, Brian | Asset Integrity | 2. Pending AFE |  | Navigable Waterway Inspection |  | 45000 |  | 45000 | 45000 | 0 | Green | 45000 |  | 45000 | 0 | [9 empty] | 45000 | 45000 | No | Green | 2023-06-01 |  |  |  | 2023-06-30 | [13 empty] | 45000 | [7 empty] | 2/1/23 - during review of projects, Senior Leadership asked if this was necessary for an idled line? | 2023-02-01 |  |  | West | Pipelines and Terminals | Pipeline Integrity |  | St. Louis | DU162DH - DUPO TO DECATUR TERM |  |  | 45000 |  |  |  |  | Bassani, Joel |  |  |  | 1 | 40976 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int - Assessments
Rensselaer API-570 Inspection | Item | Open | MEXP | BETQE00E2204 | Maintenance Framework | 2002776 | Aiken, Elaine | Asset Integrity | 7. Closed | Drawdown | Facility Integrity | -61 |  |  | -60.66 | -61 | 0 | Green |  |  |  | -61 |  |  | 60000 |  |  | 60000 | Full | 60000 | 77214 |  | 77214 | No | Green | 2022-07-01 | 2022-07-12 | 2022-07-12 | 2022-10-31 | 2022-10-31 |  |  | -60.66 | [18 empty] | 11/2/22 - Change order needed. Subcontractor had to spend additional time on site (AS) 2022-08-04 - Inspection work was completed in July. Remainder of work related to drawings/reporting. | 2022-11-02 | Schultz, Amy |  | East | Pipelines and Terminals | Station/Terminal |  | Roseton and Rensselaer | BETQE - BET RENSSELAER TERMINAL |  | -61 | 0 |  |  | 77275 |  | Aiken, Elaine | Shook, Mark B. | N/A |  | 1 | 44108 |  | Aiken, Elaine | JDE Child | Burnt Orange | 2022-07-12 | Int - Planned Corr & FI
Richmond Terminal (BETRH) Tank 14 Painting | Item | Open | MCAP | BETRH00M2303 | Maintenance Framework | 2112600 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting |  | 30000 |  | 30000 | 30000 | 0 | Green |  |  |  | 30000 |  |  | 43890 |  |  | 43890 | Full | 43890 |  | 30000 | 30000 | No | Green | 2023-08-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-12-31 | [15 empty] | 30000 | [5 empty] | 4/5/2023 CNC - project bid out for 2023 (shell and roof) | 2023-04-05 | Schultz, Amy |  | East | Pipelines and Terminals | Integrity |  | Virginia | BETRH - BET RICHMOND |  |  | 0 | 30000 |  |  |  | Cole, Caitlyn | Stine, Carlton |  |  | 1 | 46817 |  | Cole, Caitlyn | Independent | Aqua | 2023-03-20
Richmond Terminal API 570 Inspection | Item | Open | MEXP | BETRH00E2302 | Maintenance Framework | 2093436 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 29000 |  | 29000 | 29000 | 0 | Green | 29000 |  | 29000 | 0 |  |  | 29000 |  |  | 29000 | Phase | 29000 |  | 29000 | 29000 | No | Green | 2023-08-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-09-30 | [15 empty] | 29000 | [5 empty] | 4/25/23 SL - Project to start in June | 2023-04-25 | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | Virginia | BETRH - BET RICHMOND |  |  | 0 | 29000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45027 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
River Rouge API 570 Inspection 2023 | Item | Open | MEXP | BETHY00E2302 | Exempt | 2093437 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 29000 |  | 29000 | 29000 | 0 | Green | 29000 |  | 29000 | 0 |  |  | 29000 |  |  | 29000 | Phase | 29000 |  | 29000 | 29000 | No | Green | 2023-06-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-08-31 | [13 empty] | 29000 | [7 empty] | 4/25/23 SL - Project to start in May | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  |  | 29000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45026 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
River Rouge Insulated Pipe Phase 2 Inspection | Item | Open | MEXP |  | Exempt |  | Aiken, Elaine | Asset Integrity | 2. Pending AFE |  | Facility Integrity |  | 110000 |  | 110000 | 110000 | 0 | Green | 110000 |  | 110000 | 0 | [9 empty] | 110000 | 110000 | No | Green | 2023-08-01 |  |  |  | 2023-07-31 | [15 empty] | 50000 | 60000 | [8 empty] | West | Pipelines and Terminals | Station/Terminal |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  |  | 0 | 110000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45061 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
RMU LTE Antenna Upgrade Phase I - 2020 | Item | Open | MCAP | 1348260M2002 | Exempt | 1680853 | Geib, Rob | Asset Integrity | 7. Closed | Unplanned | Atmospheric Corrosion | -29090 |  |  | -29089.84 | -29090 | 0 | Green |  |  |  | -29090 |  |  | 166000 |  |  | 166000 | Phase | 166000 | 204556 |  | 204556 | No | Green | 2020-03-01 | 2020-02-12 | 2020-02-12 | 2020-12-31 | 2020-12-31 |  |  | -29089.84 | [20 empty] | Schultz, Amy |  | South | Pipelines and Terminals | Integrity |  | Corporate | Corporate |  | -29090 | 0 |  |  |  |  | Geib, Rob | Shook, Mark B. |  |  | 1 | 34881 |  | Administrator, System | Independent |  | 2019-08-30 | Int - Planned Corr & FI
Rockford Priority 3 API 570 Refurbishments | Item | Open | MCAP |  | Exempt |  | Aiken, Elaine | Asset Integrity | 2. Pending AFE |  | Facility Integrity |  | 148000 |  | 148000 | 148000 | 0 | Green | 148000 |  | 148000 | 0 | [9 empty] | 148000 | 148000 | No | Green | 2023-09-01 |  |  |  | 2023-10-31 | [16 empty] | 100000 | 48000 | [7 empty] | West | Pipelines and Terminals | Integrity |  | West Shore Terminals | BETRK - BET ROCKFORD TERMINAL |  |  | 0 | 100000 | 48000 |  |  | Aiken, Elaine |  |  |  | 1 | 45056 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
South Williamsport Phase 1 Insulated Piping Inspection | Item | Open | MEXP |  | Maintenance Framework |  | Aiken, Elaine | Asset Integrity | 8. Canceled |  | Facility Integrity |  | 8000 |  | 8000 | 8000 | 0 | Green | 8000 |  | 8000 | 0 | [9 empty] | 8000 | 8000 | No | Green | 2023-08-01 |  |  |  | 2023-08-31 | [15 empty] | 8000 | [9 empty] | East | Pipelines and Terminals | Station/Terminal |  | Macungie Terminal | BESAM - BES SOUTH WILLIAMSPORT FH 4 |  |  | 0 | 8000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 41183 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
Spartanburg API 570 Inspection | Item | Open | MEXP | BETNU00E2301 | Maintenance Framework | 2093467 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity | 11150 | 96000 |  | 107150 | 96000 | 11150 | Red | 96000 |  | 96000 | 11150 |  |  | 96000 |  |  | 96000 | Phase | 96000 | 11150 | 96000 | 107150 | No | Green | 2023-04-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-05-30 | [5 empty] | 11150 |  |  | 11150 | Red |  | WorkAhead of Schedule | 48000 | 48000 | [7 empty] | 4/25/23 SL - 1st site visit and drawings complete, inspection visit to follow | 2023-04-25 | Nguyen, Tong |  | South | Pipelines and Terminals | Station/Terminal |  | South Carolina | BETNU - BET SPARTANBURG |  |  | 107150 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45001 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Springfield Terminal API 570 Inspection | Item | Open | MEXP | BETXS00E2301 | Maintenance Framework | 2093438 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 29000 |  | 29000 | 29000 | 0 | Green | 29000 |  | 29000 | 0 |  |  | 29000 |  |  | 29000 | Phase | 29000 |  | 29000 | 29000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-07-31 | [14 empty] | 29000 | [6 empty] | 4/25/23 SL - Project to start in May | 2023-04-25 | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | Jet Lines | BETXS - BET SPRINGFIELD TERMINAL |  |  | 0 | 29000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45037 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Sugar Creek Terminal API 570 Inspection | Item | Open | MEXP | BTTUG00E2301 | Exempt | 2093464 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 59000 |  | 59000 | 59000 | 0 | Green | 59000 |  | 59000 | 0 |  |  | 59000 |  |  | 59000 | Phase | 59000 |  | 59000 | 59000 | No | Green | 2023-06-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-09-30 | [13 empty] | 59000 | [7 empty] | 4/25/23 SL - 1st site visit and drawings complete, inspection visit to follow | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Sugar Creek | BTTUG - BTT SUGAR CREEK |  |  | 59000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45006 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Tampa Butane Rail (BETKX) LPG Tanks Onstream Inspections | Item | Open | MEXP | BETKK00E2302 | Maintenance Framework | 2093563 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Pressure Vessels |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 |  |  | 11000 |  |  | 11000 | Full | 11000 |  | 10000 | 10000 | No | Green | 2023-09-01 | 2023-03-02 | 2023-03-02 | 2023-12-31 | 2023-03-31 | [6 empty] | 10000 | 10000 | -10000 | Red |  | Forecasting |  |  |  |  | 10000 |  |  |  |  | 3/16/23 CNC - $10k forecast to be moved to October. | 2023-03-16 | Schultz, Amy |  | South | Pipelines and Terminals | Tank Integrity |  | Florida | BETTK - BET TAMPA |  |  | 0 | 10000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44746 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Tank Painting Budget Allocation | Item | Candidate | MCAP |  | Maintenance Framework |  | Cole, Caitlyn | Asset Integrity | 1. Proposed | Defined | Tank Painting |  |  |  | 0 |  | 0 | Green | 2000000 |  | 2000000 | -2000000 | [6 empty] | Full |  |  |  |  | No | Green |  |  |  |  | 2023-10-31 | [21 empty] | 3/23/23-CES-Reducing $1.5MM forecast and spreading amongst individual projects. 1/25/23-CES-Original approved budget was $2MM. Reducing forecast by $500,000 to offset $2.4MM need for BTP floating roof replacements. This budget allocation will be broken down into individual projects in February with a total forecast of $1.5MM for 2023. 10.03 - Reduced by $1M to $2.5M per budget meeting | 2023-03-23 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Integrity |  | Corporate | Corporate |  |  | 0 |  |  |  |  | Cole, Caitlyn | Stine, Carlton |  |  | 1 | 45946 |  | Clark, David | Independent | Aqua | 2022-10-01 | Int - Tanks
Taylor East Terminal (BETAD) Tank 6 Painting | Item | Open | MCAP | BETAD00M2301 | Maintenance Framework | 2112601 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting |  | 50000 |  | 50000 | 50000 | 0 | Green |  |  |  | 50000 |  |  | 64790 |  |  | 64790 | Full | 64790 |  | 50000 | 50000 | No | Green | 2023-12-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-05-31 | [19 empty] | 50000 |  | 3/20/23 CNC - project bid out for 2023 (shell) | 2023-03-20 | Schultz, Amy |  | West | Pipelines and Terminals | Integrity |  | Wayne Terminals | BETAD - BET TAYLOR EAST TERMINAL |  |  | 0 |  | 50000 |  |  | Cole, Caitlyn | Stine, Carlton |  |  | 1 | 44498 |  | Guest, ProSight | Independent | Aqua | 2022-08-10 | Int - Tanks
Taylor Terminal Release Metallurgical Failure Analysis | Item | Open | MEXP | BTTDB00E2102 | Exempt | 1909406 | Aiken, Elaine | Asset Integrity | 6. Operational | Drawdown | Facility Integrity | -1 |  |  | -0.75 | -1 | 0 | Green |  |  |  | -1 |  |  | 16100 |  | 12820 | 28920 | Full | 28920 | 28920 |  | 28920 | No | Green | 2021-12-01 | 2021-11-12 | 2021-11-12 | 2022-02-15 | 2022-02-15 |  |  | -0.75 | [20 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Pipeline | BTTDB - BTT TAYLOR TERMINAL |  | -1 | 0 |  |  | 26262 |  | Aiken, Elaine | Bassani, Joel D. | N/A |  | 1 | 42423 |  | Aiken, Elaine | Independent | Aqua | 2021-11-11 | Int - Planned Corr & FI
Trenton Terminal I API 570 Inspection | Item | Open | MEXP | BETHK00E2301 | Maintenance Framework | 2093432 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 24000 |  | 24000 | 24000 | 0 | Green | 24000 |  | 24000 | 0 |  |  | 24000 |  |  | 24000 | Phase | 24000 |  | 24000 | 24000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-09-30 | [14 empty] | 24000 | [6 empty] | 4/25/23 SL - Project to start in June | 2023-04-25 | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | Pennsauken | BETHK - BET Trenton Terminal (formerly Duck Island I) |  |  | 0 | 24000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45029 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Tuscola API 570 Inspection | Item | Open | MEXP | BETBV00E2301 | Exempt | 2093463 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 57000 |  | 57000 | 57000 | 0 | Green | 57000 |  | 57000 | 0 |  |  | 57000 |  |  | 57000 | Phase | 57000 |  | 57000 | 57000 | No | Green | 2023-05-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-05-31 | [12 empty] | 57000 | [8 empty] | 4/25/23 SL - 1st site visit and drawings complete, inspection visit to follow | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Central-Illinois | BETBV - BET BARTONSVILLE TERMINAL |  |  | 57000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45004 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Tuscola Insulated Pipe Phase 2 Inspection | Item | Open | MEXP |  | Exempt |  | Aiken, Elaine | Asset Integrity | 2. Pending AFE |  | Facility Integrity |  | 110000 |  | 110000 | 110000 | 0 | Green | 110000 |  | 110000 | 0 | [9 empty] | 110000 | 110000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 50000 | 60000 | [9 empty] | West | Pipelines and Terminals | Station/Terminal |  | Central-Illinois | BDLTU - TUSCOLA - BDL |  |  | 0 | 110000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45062 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Underground Tank Inspections Phase 1 | Item | Open | MEXP | 1348250E2239 | Exempt | 2022550 | Aiken, Elaine | Asset Integrity | 6. Operational | Defined | Facility Integrity | 30379 |  |  | 30378.75 | 32199 | -1820 | Yellow |  |  |  | 30379 |  |  | 140000 |  |  | 140000 | Full | 140000 | 53164 |  | 53164 | No | Green | 2022-10-01 | 2022-09-13 | 2022-09-13 | 2022-12-31 | 2022-12-31 |  |  | 10740 | 10315 | 11143.75 | -1820 |  |  | -1820 | Red |  | Forecasting | [9 empty] | 4.4.23 - Accrual $6,500. Waiting on invoicing (AS) 3.2.23 - Accrual $14,000. Waiting on Invoicing (AS) 11/2/22 - Waiting on invoice (AS) 9/16/22 - $43,000 reduced to cover BNTNV00E2205 (AS) 2022-09-12 - AFE submitted to workflow. Proposal received from consultant to begin tank inventory review. 2022-08-24 - $60k was reallocated from this project to the BBH Cat Island Repairs project in order to address repairs needed after daylighting piping. | 2023-04-04 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  | 32199 | -1820 |  |  | 22785 |  | Aiken, Elaine | Shook, Mark B. |  |  | 1 | 41207 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
Unit Pricing Welding Procedure and Qualification Review | Item | Open | MEXP | 1348250E2208 | Exempt | 1910729 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tanks | 4590 |  |  | 4590 | 4590 | 0 | Green |  |  |  | 4590 |  |  | 30000 |  |  | 30000 | Full | 30000 | 20910 |  | 20910 | No | Green | 2022-02-01 | 2021-11-29 | 2021-11-29 | 2022-06-30 | 2023-12-31 |  |  | 4590 | 0 | [17 empty] | 1/5/2023 CNC - project is ongoing 3/7/22 - 50% allocation to 155 Buckeye Terminals and 50% allocation to 100 Buckeye Pipeline (AS) | 2023-01-05 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Tank Integrity |  | Corporate | Corporate |  | 4590 | 0 |  |  | 16320 |  | Stine, Carlton | Shook, Mark B. |  |  | 1 | 41084 |  | Stine, Carlton | Independent | Aqua | 2021-08-06 | Int - Tanks
WA751RX MEXP Dig Flips | Item | Candidate | MEXP |  | Exempt | 1620951 | Bartal, Nick | Asset Integrity | 7. Closed | Drawdown | Pipeline Digs |  | 1 |  | 1 | 1 | 0 | Green | 1 |  | 1 | 0 | [9 empty] | 1 | 1 | No | Green | 2023-12-01 |  |  | 2020-11-30 | 2023-12-31 | [19 empty] | 1 | [5 empty] | East | Pipelines and Terminals | Pipeline Integrity |  | Auburn Pipeline | WA751WX - WATERLOO TO WEEDSPORT JCT |  |  | 0 |  | 1 |  |  | Bartal, Nick | Bartal, Nick | N/A |  | 1 | 38939 |  | Bartal, Nick | Independent | Aqua | 2020-10-29 | Int- Planned Digs
Warren API 570 Inspection | Item | Open | MEXP | BETYO00E2301 | Exempt | 2093462 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 55000 |  | 55000 | 55000 | 0 | Green | 55000 |  | 55000 | 0 |  |  | 55000 |  |  | 55000 | Phase | 55000 |  | 55000 | 55000 | No | Green | 2023-06-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-06-30 | [13 empty] | 55000 | [7 empty] | 4/25/23 SL - Project to start in May | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | North East Ohio | BETYO - BET WARREN |  |  | 55000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45008 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Waterway Evaluations of 2022 Navigable Waterway Inspections | Item | Open | MEXP | 1348250E2237 | Exempt | 2013774 | Karl, Marissa | Asset Integrity | 7. Closed | Defined | Navigable Waterway Inspection | 30250 |  |  | 30250 | 30250 | 0 | Green |  |  |  | 30250 |  |  | 64000 |  |  | 64000 | Full | 64000 | 60500 |  | 60500 | No | Green | 2022-11-01 | 2022-08-26 | 2022-08-26 | 2022-12-31 | 2022-12-31 |  |  | 33000 | -17875 | 15125 | [16 empty] | 3.3.23 - Waiting for final documentation prior to close (AS) 2/2/23 - waiting on final invoicing (AS) 1/4/2023 - mrk - 44k variance due to pushing 33k into January. Work is underway and will wrap up in Jan. 12/27/22 - Adjusted December forecast to $5,000 and January forecast to $33,000 per instruction from Marissa Karl (AS) 12/27/222 - mrk - Paid 15k of the 60k in November and did not update December forecast downward. Supplemental is NOT needed, but missed the deadline to adjust forecasts. Will be pushing 33k out into January due to work timeline slip. 11/2/22 - mrk - $60k moved to December for work originally intended to be complete in Oct. Work is in progress and expected to complete in December. 11/2/22 - Moved $60,000 to December per Marissa (AS) | 2023-03-03 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Pipeline Integrity |  | Corporate | Corporate |  | 30250 | 0 |  |  | 30250 |  | Bassani, Joel | Shook, Mark B. |  |  | 1 | 40973 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int - Exposure Evals
Wayne Station API 570 Inspection | Item | Open | MEXP | WW00000E2302 | Exempt | 2093439 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity |  | 29000 |  | 29000 | 29000 | 0 | Green | 29000 |  | 29000 | 0 |  |  | 29000 |  |  | 29000 | Phase | 29000 |  | 29000 | 29000 | No | Green | 2023-07-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-07-31 | [14 empty] | 29000 | [8 empty] | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Pipeline | WW - WAYNE STATION |  |  | 0 | 29000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45020 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Wilmington Dock Line API-570 Inspection | Item | Open | MEXP | BETQM00E2303 | Maintenance Framework | 2120118 | Aiken, Elaine | Asset Integrity | 3. Active | Drawdown | Facility Integrity |  | 35000 |  | 35000 |  | 35000 | Red |  |  |  | 35000 |  |  | 35000 |  |  | 35000 | Full | 35000 |  | 35000 | 35000 | No | Green | 2023-05-01 | 2023-05-04 | 2023-05-04 | 2023-12-31 | 2023-12-31 | [12 empty] | 20000 | 15000 | [9 empty] | Schultz, Amy |  | South | Pipelines and Terminals | Station/Terminal |  | North Carolina | BETQM - BET WILMINGTON TERMINAL |  |  | 35000 |  |  |  |  | Aiken, Elaine | Shook, Mark B. | N/A |  | 1 | 47001 |  | Aiken, Elaine | JDE Child | Burnt Orange | 2023-04-28
Wood River Station API 570 Inspection | Item | Open | MEXP | WO00000E2301 | Exempt | 2093454 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity | 0 | 33000 |  | 33000 | 33000 | 0 | Green | 33000 |  | 33000 | 0 |  |  | 33000 |  |  | 33000 | Phase | 33000 | 0 | 33000 | 33000 | No | Green | 2023-05-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-05-31 | [5 empty] | 0 |  |  | 0 | Green |  |  | 33000 | [8 empty] | 4/25/23 SL - Project to start in May | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | St. Louis | WO - WOOD RIVER STATION |  |  | 33000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45015 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Woodhaven Terminal TK 130 & TK131 Pre-Audit Recoat | Item | Open | MCAP | BETWS00M2302 | Maintenance Framework | 2112602 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting | 0 | 160000 |  | 160000 | 160000 | 0 | Green |  |  |  | 160000 |  |  | 187055 |  |  | 187055 | Full | 187055 | 0 | 160000 | 160000 | No | Green | 2023-12-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-08-31 | [5 empty] | 0 |  |  | 0 | Green | [9 empty] | 160000 |  | 3/20/23 CNC - project bid out for 2023 (shell) | 2023-03-20 | Schultz, Amy |  | West | Pipelines and Terminals | Integrity |  | Wayne Terminals | BETWS - BET WOODDHAVEN TERMINAL |  |  | 0 |  | 160000 |  |  | Cole, Caitlyn | Stiles, Mark |  |  | 1 | 41478 |  | Guest, ProSight | Independent | Aqua | 2021-08-17 | Int - Tanks
Zionsville Tank 60 Paint | Item | Open | MCAP | BETZI00M2304 | Maintenance Framework | 2112603 | Cole, Caitlyn | Asset Integrity | 3. Active | Defined | Tank Painting | 0 | 80000 |  | 80000 | 80000 | 0 | Green |  |  |  | 80000 |  |  | 96140 |  |  | 96140 | Full | 96140 | 0 | 80000 | 80000 | No | Green | 2023-12-01 | 2023-04-21 | 2023-04-21 | 2023-12-31 | 2023-08-31 | [5 empty] | 0 |  |  | 0 | Green | [9 empty] | 80000 |  | 3/20/23 CNC - project bid out for 2023 (shell and roof) | 2023-03-20 | Schultz, Amy |  | West | Pipelines and Terminals | Integrity |  | Indianapolis | BETZI - BET ZIONSVILLE TERMINAL |  |  | 0 |  | 80000 |  |  | Cole, Caitlyn | Stiles, Mark | N/A |  | 1 | 31043 |  | Clark, David | Independent | Aqua | 2018-08-27 | Int - Tanks
Zionsville Terminal API 570 Inspection | Item | Open | MEXP | BETZI00E2302 | Exempt | 2093460 | Logan, Sam | Asset Integrity | 3. Active | Defined | Facility Integrity | 0 | 47000 |  | 47000 | 47000 | 0 | Green | 47000 |  | 47000 | 0 |  |  | 47000 |  |  | 47000 | Phase | 47000 | 0 | 47000 | 47000 | No | Green | 2023-05-01 | 2023-02-28 | 2023-02-28 | 2023-12-31 | 2023-04-30 | [5 empty] | 0 |  |  | 0 | Green |  |  | 47000 | [8 empty] | 4/25/23 SL - 1st site visit and drawings complete, inspection visit to follow | 2023-04-25 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Indianapolis | BETZI - BET ZIONSVILLE TERMINAL |  |  | 47000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45009 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
*2023 MCAP Leadership Contingency | Item | Candidate | MCAP |  | Exempt |  | Walton, Kathleen | Corporate | 2. Pending AFE |  | Corporate |  | 550000 |  | 550000 | 550000 | 0 | Green |  |  |  | 550000 | [9 empty] | 550000 | 550000 | No | Green | 2023-08-01 |  |  |  | 1900-12-31 | [15 empty] | 200000 | 200000 | 150000 |  |  |  | Placeholder added per Ben Clark |  |  |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corporate | [5 empty] | 0 | 400000 | 150000 |  |  | Clark, Dave | Sauger, Joseph M. |  |  | 1 | 46690 |  | Administrator, System | Independent | Aqua | 2023-03-02
*MCAP Confidence Adjustment - Integrity | Item | Candidate | MCAP |  | Exempt |  | Walton, Kathleen | Corporate | 3. Active | Drawdown | Corporate |  | -1 |  | -1 | -1 | 0 | Green | 1 |  | 1 | -2 | [9 empty] | -1 | -1 | No | Green |  |  |  |  | 2025-12-31 | [19 empty] | -1 |  | 4.27 - Topsides removed ahead of 4+8 forecast 4.13 $6M Topside entere for 3+9 baseline 4.3 - Topsides Removed for 3+9 3.14 - $12M Topside entered to revert back 1+11 3.2 KW removed topside for Feb month end review 2.15 KW entered topside to maintain budget |  |  |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Integrity | Integrity | Corporate | Corporate |  |  | 0 |  | -1 |  |  | Clark, Dave |  | N/A |  | 1 | 26846 |  | Samilo, Gregory | Independent | Aqua | 2017-11-03 | Int - Accel Cutouts
*MCAP Confidence Adjustment - OI | Item | Candidate | MCAP |  | Exempt |  | Walton, Kathleen | Corporate | 3. Active | Drawdown | Corporate |  | -1 |  | -1 | -1 | 0 | Green | 1 |  | 1 | -2 | [9 empty] | -1 | -1 | No | Green |  |  |  |  | 2022-12-31 | [19 empty] | -1 |  | 4.27 - Topsides removed ahead of 4+8 forecast 4/13 - $2.2M Topside reduction to get to baseline 4.3 - Topsides removed for the 3+9 3.2 KW removed topsside for Feb month end review 02.15 KW added June topside to maintain budget |  |  |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Operating Infrastructure | Operating Infrastructure | Corporate | Corporate |  |  | 0 |  | -1 |  |  | Clark, Dave |  | N/A |  | 1 | 23843 |  | Samilo, Gregory | Independent | Aqua | 2017-07-12 | Other Programs
*MCAP IT Confidence Adjustment | Item | Candidate | MCAP |  | Exempt |  | Clark, Dave | Corporate | 1. Proposed | Drawdown | Infrastructure & IT Ops |  | -1 |  | -1 | -1 | 0 | Green |  |  |  | -1 | [9 empty] | -1 | -1 | No | Green |  |  |  |  | 2025-12-31 | [19 empty] | -1 |  | 3.2 KW removed topside for Feb month end review 2.15 - KW added $795K reduction to maintain 2023 budget | 2023-03-08 |  |  | Corporate | Corporate | IT | IT | Information Systems | Corporate |  |  | 0 |  | -1 |  |  | Gingras, Stephan |  |  |  | 1 | 41376 |  | Administrator, System | Independent | Aqua | 2021-08-11 | IT
*MEXP Confidence Adjustment - Domestic Station | Item | Open | MEXP |  | Exempt |  | Walton, Kathleen | Corporate | 3. Active | Emergent | Corporate |  | -1 |  | -1 | -1 | 0 | Green | 1 |  | 1 | -2 | [9 empty] | -1 | -1 | No | Green |  |  |  | 2017-12-31 | 2023-12-31 | [19 empty] | -1 |  | 4.27 - Topsides removed ahead of 4+8 forecast 4.13 $2.3M topside to baseline 4.3 Removed Topside for 3+9 3.14 - Added -$2.3M topisde to maintain 1+11 3.2 KW removed topside for Feb month end review 2.15 KW added topside to maintain budget |  | Meitzler, Antoinette |  | Corporate | Corporate | Station/Terminal | Station/Terminal | Corporate | Corporate |  |  | 0 |  | -1 |  |  | Clark, Dave | Ostach, Carl A. |  |  | 1 | 23133 |  | Inman, Connie L. | Independent | Aqua | 2017-04-18 | IT
*MEXP Confidence Adjustment - Pipeline Integrity | Item | Candidate | MEXP |  | Exempt |  | Walton, Kathleen | Corporate | 1. Proposed | Defined | Corporate |  | -1 |  | -1 | -1 | 0 | Green | 1 |  | 1 | -2 | [9 empty] | -1 | -1 | No | Green |  |  |  |  | 2021-12-31 | [19 empty] | -1 |  | 4.27 - Topsides removed ahead of 4+8 forecast 4.3 Removed Topside for 3+9 3.14 KW - Added -$94K topisde to maintain 1+11 3.2 KW removed topside for Feb month end review |  |  |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Pipeline Integrity | Pipeline Integrity | Corporate | Corporate |  |  | 0 |  | -1 |  |  | Clark, Dave |  | N/A |  | 1 | 26849 |  | Samilo, Gregory | Independent | Aqua | 2017-11-03 | Other Programs
2023 Dock Line API-570 Inspection Plan Development | Item | Open | MEXP | 1550000E2301 | Maintenance Framework | 2051760 | Aiken, Elaine | Corporate | 3. Active | Emergent | Facility Integrity | 3510 |  |  | 3510 | 3510 | 0 | Green |  |  |  | 3510 |  |  | 11000 |  | 1380 | 12380 | Full | 12380 | 3510 |  | 3510 | No | Green | 2023-01-01 | 2022-12-07 | 2022-12-07 | 2023-02-28 | 2023-02-28 |  |  | 2380 | 1130 | [17 empty] | This project replaces 1348250E2244 which was created in error (AS) | 2023-01-30 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  | 3510 | 0 |  |  |  |  | Aiken, Elaine | Shook, Mark B. |  |  | 1 | 46560 |  | Schultz, Amy | Independent | Aqua | 2023-01-30 | Int - Planned Corr & FI
2023 MEXP Budget Allocation - Seam | Item | Open | MEXP | 1348250E2302 | Maintenance Framework |  | Bartal, Nick | Corporate | 3. Active | Defined | Pipeline Digs |  | 250000 |  | 250000 | 250000 | 0 | Green | 300000 |  | 300000 | -50000 |  |  | 300000 |  |  | 300000 | Full | 300000 |  | 250000 | 250000 | No | Green | 2023-06-01 | 2022-12-19 | 2022-12-19 | 2023-12-31 | 2023-12-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 50000 | 50000 | 50000 | 25000 | 25000 | 25000 | 25000 |  | 3/7/23 - no budget allocaiton utilized yet, pushed forecast out. 2/7/23 - No budget allocation utilized yet; pushed forecast out | 2023-03-07 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Pipeline Integrity | Pipeline Integrity | Corporate | Corporate |  |  | 50000 | 125000 | 75000 |  |  | Bartal, Nick | Shook, Mark B. |  |  | 1 | 45209 |  | Administrator, System | JDE Parent | Yellow | 2022-08-23 | Int- Planned Digs
2023 Probabilistic Crack Program Development | Item | Open | MEXP | 1348250E2304 | Maintenance Framework |  | Hurley, Brian | Corporate | 3. Active | Defined | Pipeline Digs |  | 60000 |  | 60000 | 60000 | 0 | Green | 60000 |  | 60000 | 0 |  |  | 60000 |  |  | 60000 | Full | 60000 |  | 60000 | 60000 | No | Green | 2023-06-01 | 2022-12-16 | 2022-12-16 | 2023-12-31 | 2023-09-30 | [6 empty] | 10000 | 10000 | -10000 | Red |  | Forecasting | 0 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 |  |  | 5/8/23 - no budget allocation utilized yet, pushed forecast out. 2/7/23 - No budget allocation utilized yet; pushed forecast out | 2023-05-08 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Pipeline Integrity |  | Corporate | Corporate |  |  | 10000 | 30000 | 20000 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 45210 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Int - Assessments
BTXHF - 115 Series High Level Switches Phase I MEXP Flip | Item | Open | MEXP | BTXHF00E2302 | Exempt |  | Clark, Dave | Corporate | 6. Operational | Emergent | South | 5550 |  |  | 5550.03 | 5550 | 0 | Green |  |  |  | 5550 |  |  | 14314 |  |  | 14314 | Full | 14314 | 5550 |  | 5550 | No | Green | 2023-03-01 | 2023-03-07 | 2023-03-07 | 2023-03-07 | 2023-03-07 |  |  |  |  | 5550.03 | [18 empty] | Carter, Paige |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 5550 | 0 |  |  |  |  | Johnson, AJ | Clark, David |  |  | 1 | 46709 |  | Meitzler, Antoinette | Independent | Aqua | 2023-03-07
Checkpoint Log Server Replacement | Item | Open | MCAP | 1348171M2301 | Exempt |  | Geier, John | Corporate | 8. Canceled | Defined | Infrastructure & IT Ops |  |  |  | 0 |  | 0 | Green | 110000 | -110000 | 0 | 0 |  |  | 2419 |  |  |  | Phase | 2419 |  |  |  | No | Green |  |  |  | 2023-08-15 | 2023-12-31 | [21 empty] | 2/17/23: This project to be Cxld. Charges from Checkpoint Log Server will be coded to 2022 projec since Equipment was already purchased on this AFE in 2022. $110k not needed for 2023 Budget. Funds moved to WEBSITE REDESIGN//bo | 2023-03-28 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 |  |  |  |  | Gingras, Stephan | Virupakshi, Sudhakar |  |  | 1 | 45494 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
CRM Implementation | Item | Open | MCAP | 1348174M2301 | Exempt | 2073919 | Aili, Suresh | Corporate | 3. Active | Defined | Enterprise Business Apps | 336370 | 9811 |  | 346181.33 | 344763 | 1418 | Yellow | 500000 |  | 500000 | -153819 |  |  | 493662 |  |  | 493662 | Full | 493662 | 336370 | 9811 | 346181 | No | Green | 2023-01-01 | 2023-01-02 | 2023-01-02 | 2023-05-31 | 2023-05-31 |  |  | 29000 | 61000 | 135025.13 | 111345.2 | 109927 | 109927 | 1418 | Yellow |  |  | 9811 | [8 empty] | 4/10/23: Invoice incorrectly coded to Expense. Will be reclassed by Becca in April to reflect April actuals. Added +$29.5k to April forecast of $80k per Sai.//bo 3/7 No internal labor billed in Jan and Feb due to work order issues that were resolved 3/3. Reclass will be submitted for time. Hitachi had $16K less in services billed in Feb. Reduced March forecast by $4K due to less vendor hours planned. -KS 2/9 Updated forecast based post kickoff. -KS -1/25/23: Updated Operational Date based on forecast. Also changed name to CRM Implementation per KS.//bo 1/9/23 AFE approved and SOW signed. Updated initial forecast. Planning and kickoff underway for implementation. KS | 2023-04-24 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 225025 | 121156 |  |  |  |  | Gingras, Stephan | Gardner, Dale |  |  | 1 | 45509 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
Houston Office Relocation Moving Expenses | Item | Open | MEXP | 1348811E2103 | Exempt | 1888442 | Loethen, Kris | Corporate | 6. Operational | Emergent | Corporate | 106367 |  | 212143 | 106367.31 | 65089 | 41278 | Red |  |  |  | 106367 |  |  | 354000 |  |  | 354000 | Full | 354000 | 223841 | 212143 | 435984 | Yes | Red | 2022-01-01 | 2021-09-21 | 2021-09-21 | 2022-02-09 | 2022-02-09 |  |  | 12514.79 | 11868.53 |  | 81983.99 | 25873 | 25873 | 56111 | Red | [10 empty] | 212143 | 05.04.23 KB: Art purchase cancelled for 2023; mandatory spending only has been enforced. Currently, negotiating to apply down payment to next year spending. 04.07.23 KB: 50% Milestone payment will be required on receipt of art design approval; art design drawings submitted for approval on 4/5/23. 03.06.23 KB: Final proposal of artwork has not been presented. Review and approval expected in April at which time milestone payment will be requested. 02.06.23 KB - Visitor Kiosk completed billing. Design Art downpayment completed meetings om concepts continue with approval drawings due in March. 01.09.23 KB: Initial meeting with Design Art scheduled for 1/19/23. 12.07.22 KB: PO for Artwork executed for $55.2k; 20% DP, 50% upon design approval and balance at installation, appx 5/23. 10.10.22 KB: No $30K PO created for Deluxe Art 9.8.22 KB: Only pending approved art for the offices from Deluxe Art Design. 8.4.22 KDB: Still pending final move expense from vendor Daryl Flood expected to close August 2022. 6.8.22 KDB: Schedule for vendor Daryl Flood pushed out one month. May forecast reduced; $20k paid in April under BU# 1348811M2102 for upcoming AV installation. IT relocation forecasted in March has been rescheduled to May with decommissioning to follow. 4/7/22 KB Reclass submitted to move current actuals $4.8k to IT. KB 2/7/22 | 2023-05-04 | Boyd, Kim |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal | Station/Terminal | Corporate | Corporate |  | 24383 | 81984 |  |  | 117474 |  | Clark, Dave | Hollis, Bill |  |  | 1 | 41482 |  | Meitzler, Antoinette | Independent | Aqua | 2021-08-17 | Office Relocation
Houston Office Space Relocation Construction Buckeye | Item | Open | MCAP | 1348811M2102 | Exempt | 1888426 | Loethen, Kris | Corporate | 6. Operational | Defined | Corporate | -81984 |  | 300353 | -81983.99 |  | -81984 | Red |  |  |  | -81984 |  |  | 454000 |  |  | 454000 | Full | 454000 | 71663 | 300353 | 372016 | No | Green | 2021-10-01 | 2021-09-21 | 2021-09-21 | 2022-02-07 | 2022-02-09 | [5 empty] | -81983.99 |  |  | -81984 | Red | [10 empty] | 300353 | 9.8.22 KB: Added forecast for new hire accommodations and upgrades. 8.4.22 finalizing individual move requests. 6.8.22 KB: June forecast reduced by half only two requests for additional work were approve by J. Sauger for the month of June. Remaining requests have been forecasted for July still pending approval. In April, paid $20k for upcoming AV installation. Forecasted for MAY 22 under Move Expense BU# 1348811E2103. TI allowance exhausted in April 22. Add'l $45.5k forecasted for HVAC, DASH (cellphone booster) and other building construction. 5/6/22 KB $19k remaining in TI bucket as of 4/1/22; therefore, $300k forecasted for add'l construction has been released to contingency. $14k accrual covers CMCI incurred cost through March with add'l $17k of additional work associated with the IT move and trash removal. 4/7/22 KB $204K remaining in TI bucket and the general contractor agreement expires 3/21/22. All additional work forecasted in April & May. Packing and trash removal week of Jan 24th. Occupy new space set for week of Feb. 14th. This is the full AFE pending re-class of actuals from BU 1348811M2101. | 2022-09-08 | Boyd, Kim |  | Corporate | Corporate | Corporate |  | Corporate | Corporate |  |  | -81984 |  |  | 115543 |  | Clark, Dave | Hollis, Bill |  |  | 1 | 41458 |  | Meitzler, Antoinette | Independent | Aqua | 2021-08-16 | Office Relocation
Houston Office Space Relocation Furniture | Item | Open | MCAP | 1348811M2103 | Exempt | 1879056 | Loethen, Kris | Corporate | 6. Operational | Defined | Corporate | 483 |  | 372786 | 482.64 | 1045 | -562 | Red |  |  |  | 483 |  |  | 3192000 |  |  | 3192000 | Full | 3192000 | 1819215 | 372786 | 2192001 | No | Green | 2021-09-01 | 2021-08-25 | 2021-08-25 | 2022-02-07 | 2022-02-09 |  |  |  |  | 482.64 |  | 562 | 562 | -562 | Red | [10 empty] | 372786 | 05.04.23 KB: Second guest chair not ordered. No additional spend 04.07.23 KB: Second guest chair forecasted in March now expected to be ordered in April. 03.06.23 KB: Office chair finally purchased for guest executive office in suite C. 1.09.23 KB - Office chair received in Dec. no additional cost anticipated. 12.07.22 KB - Office chair ordered 10.10.22 KB - No additional spend anticipated. 9.8.22 KB: $45k accrual submitted for remaining furniture install. Additional $77k to cover final office furniture upgrades. 8.4.22 KDB: T Russo office and furniture change requests finalized. 6.8.22 KDB: Still pending delivery of remaining furniture. Additional credit of $(42,598) is outstanding. Additional costs for AV equipment and signage were applied after the reimbursement agreement was executed. 5/17/22 KB IFM will be invoiced 105% of the cost for their furniture. JE 1250606 for -419,825.51 is 100% of the reimbursed cost. 5/16/22 KB $521k removed from contingency by PMO on 4/13/22 KB Remaining 7% of Buckeye furniture will be delivered with remaining IFM furniture estimated for the end of May. 4/7/22 KB 93% of Buckeye furniture was delivered and paid, the remaining 7% will be delivered in March. IFM furniture continues to be scheduled for May delivery. KB 3/9/22 Furniture for IFM will be delayed until May 2022. This may impact final billing for furniture. Current payment scheduled is 50% down and 50% at completion. KB 2/7/22 | 2023-05-04 | Boyd, Kim |  | Corporate | Corporate | Corporate |  | Corporate | Corporate |  | 483 | 0 |  |  | 747858 |  | Clark, Dave | Hollis, Bill |  |  | 1 | 41459 |  | Meitzler, Antoinette | Independent | Aqua | 2021-08-16 | Office Relocation
Managed Printer Project | Item | Open | MCAP | 1348174M2303 | Exempt | 2096640 | Bartlett, Hilary | Corporate | 3. Active | Emergent | Infrastructure & IT Ops | 717 | 6700 |  | 7416.66 | 8100 | -683 | Yellow |  | 8486 | 8486 | -1069 |  |  | 8486 |  |  | 8486 | Full | 8486 | 717 | 6700 | 7417 | No | Green | 2023-04-01 | 2023-03-30 | 2023-03-30 | 2023-05-31 | 2023-05-31 | [5 empty] | 716.66 | 2000 | 2000 | -1283 | Red |  | Forecasting | 6200 | 500 | [7 empty] | 5/4/23: Adjusted forecast to reflect purchase of badge readers to occur post POC 4/6/23: Entered forecast for project | 2023-05-04 | IT |  | Corporate | Pipelines and Terminals | IT |  | Corporate | Corporate |  |  | 7417 |  |  |  |  | Gingras, Stephan | Tran, Hung |  |  | 1 | 46857 |  | Meitzler, Antoinette | Independent | Aqua | 2023-03-29
River Rouge Test/Replace Pressure Safety Valves | Item | Candidate | MCAP |  | Maintenance Framework |  | Skelly, Mark | Corporate | 2. Pending AFE |  | Pressure Vessels |  |  |  | 0 | 15000 | -15000 | Red | 15000 |  | 15000 | -15000 | [11 empty] | No | Green |  |  |  |  | 2023-04-30 | [6 empty] | 15000 | 15000 | -15000 | Red | [15 empty] | West | Pipelines and Terminals | Integrity |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  |  | 0 |  |  |  |  | Stine, Carlton |  |  |  | 1 | 41675 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Int - Tanks
TAA/OT Windows10 upgrades | Item | Open | MCAP | 1348181M2302 | Exempt | 2095186 | Gay, Elena | Corporate | 3. Active | Defined | OT & IT Field Ops | 240148 | 668000 |  | 908148.12 | 908000 | 148 | Yellow | 1013066 |  | 1013066 | -104918 |  |  | 976502 |  |  | 976502 | Full | 976502 | 240148 | 668000 | 908148 | No | Green | 2023-04-01 | 2023-03-17 | 2023-03-17 | 2023-09-30 | 2023-12-31 | [5 empty] | 240148.12 | 240000 | 240000 | 148 | Yellow |  |  | 25000 | 70000 |  | 60000 | 253000 | 60000 |  | 200000 |  | 4/10/23: Per EG, contingency on project is $80k. AFE less than budget amount. Forecast is not including Contingency (which is not expected to be used).//bo | 2023-04-12 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 335148 | 313000 | 260000 |  |  | Gingras, Stephan | Tran, Hung |  |  | 1 | 45484 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
Vendor Remote Access Management | Item | Open | MCAP |  | Exempt |  |  | Corporate | 8. Canceled | Defined | Infrastructure & IT Ops |  |  |  | 0 |  | 0 | Green | 30000 | -30000 | 0 | 0 | [6 empty] | Full |  |  |  |  | No | Green |  |  |  | 2023-08-15 | 2023-07-31 | [21 empty] | 3/28/2023: $30k budget moved to Website Redesign. Cancelling project.//bo 2/22/23: This project will be cancelled and coded to Expense 1348171.66120.//bo 2/5/23 - Product is installed. First vendor migration expected within the next 30 days // JG | 2023-03-28 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 |  |  |  |  | Gingras, Stephan |  |  |  | 1 | 45482 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
2015 ALBANY EXT TK INSP | Item | Open | MEXP | BATNY00E1501 | Exempt |  | Tallarida, Frank | East | 7. Closed | Drawdown | East | 0 |  |  | 0 | 0 | 0 | Green |  |  |  | 0 | [8 empty] | 1158 |  | 1158 | No | Green | 2023-01-01 | [6 empty] | 1328.98 | -1328.98 | [17 empty] | The 1.3K hitting in January was McGill Hose & Coupling invoice 3343633. Somehow this 2015 project never got closed. Asking Gail Vanalystyne if she is able to do the flip.. | 2023-02-06 |  |  | East | Pipelines and Terminals | Station/Terminal |  | Albany | BATNY - BAT ALBANY |  | 0 | 0 |  |  |  |  | Orischak, Bob |  |  |  | 1 | 14374 |  | Borra, Brian | Independent | Aqua | 2015-02-21
2015 TUCKERTON TERM EXT TK INSP | Item | Open | MEXP | BETRG00E1501 | Exempt |  | Tallarida, Frank | East | 7. Closed | Drawdown | East | 75 |  |  | 75 | 75 | 0 | Green |  |  |  | 75 | [8 empty] | 23358 |  | 23358 | No | Green | 2022-12-01 | [6 empty] | 75 | [18 empty] | The $75 hitting (hit in Dec 2022?) was Penn Pride invoice 298. Somehow this 2015 project never got closed. Asking Melissa Hill if she is able to do the flip. | 2023-02-06 |  |  | East | Pipelines and Terminals | Station/Terminal |  | Macungie Terminal | BETRG - BET TUCKERTON |  | 75 | 0 |  |  | 75 |  | Orischak, Bob |  |  |  | 1 | 14399 |  | Borra, Brian | Independent | Aqua | 2015-02-21
2020 NSJ Pipeline Inspections | Item | Open | MEXP | 8410811E2111 | Exempt | 1902501 | McDonald, Carnetta | East | 7. Closed | Unplanned | Facility Integrity | -71 |  |  | -70.6 | 239 | -310 | Red |  |  |  | -71 |  |  | 550000 |  |  | 550000 | Full | 550000 | 516045 |  | 516045 | No | Green | 2021-11-01 | 2021-10-19 | 2021-10-19 | 2021-12-31 | 2022-05-30 |  |  | 27.86 |  | 211.14 | -309.6 |  |  | -310 | Red | [11 empty] | 05/08/2023 - All 2023 cost were related to VAT reclasses. Project closed. 08/22/22 - Reclass to remove $36,361.00 was submitted on 08/18/22. Project will be closed once reclass has been processed. KDB 08/01/2022 - All outstanding invoices have been submitting for final approval. This project is now ready for close. CLM 07/01/2022 - Awaiting one (1) outstanding invoice from G.B. Insulators. CLM 06/01/2022 - This project is completed, with all outstanding invoices now being processed. CLM 05/01/2022 - Project on schedule with an end of May completion, 2022. CLM 04/01/2022 - I had major weather delays and Port closure. The project will continue in order to complete the wrapping at the OLJ risers. NLJ risers will be delayed due to the ongoing structural project at that platform. CLM 02/01/2022 - Project is on schedule. OLJ Riser splash zone area will be wrapped this month in order to slow down the corrosion on that Jetty. NLJ will be addressed as well in the month of February and March, 2022. CLM 01/01/2022 - Final inspection reports received and pending review with vendor January 12, 2022. The carryover funds is split between January and February 2022. This project is on schedule and invoices from 4th qtr. 2021 have been submitted for final approval. CLM 1/5/22 Operational date pushed back to February 2022 BL 12/01/2021 - API-570 Riser field inspections completed ,pending final reports end of this week December 10th, 2021. Preliminary reporting on the OLJ Riser, only concern they had during the site visual was coating issues, that will be address. As for the NLJ Risers, they had some major concerns, that will be outlined in the report. CM 11/01/2021 - This project is on schedule. Inspectors will arrive on island Sunday November 7th, 2021 with inspection starting Monday November 8th, 2021. Once the inspection has been completed, a preliminary report willbe issued for review. Once the reports are reviewed, it will determine the recommended type of Diamond Wrap to apply. CM 09/7/2020 - COVID-19 travel restrictions preventingvendor from travelling to Freeport unless additional funding is provided to support accommodations during the 14 day quarantine. 08/04/2020 - COVID-19 travel restrictions preventing vendor from travelling to Freeport. 07/06/2020 - Project estimated to begin in August. 04/15/20 - Per Antoine: I reviewed this project with the Director and the Ops Manager and based on the COVID19 travel restrictions in place that would affect required contract personnel, we are comfortable adjusting this forecast to Q3. August – 300K September – 250K | 2023-05-08 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 239 | -310 |  |  | 266466 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 34556 |  | Bassani, Joel | Independent | Aqua | 2019-08-27 | Int - Assessments
2022 - AB803RC - ILI | Item | Open | MEXP | AB803WLE2201 | Maintenance Framework | 2002064 | Keppel, Nicholas | East | 7. Closed | Defined | Assessments | 11700 |  |  | 11700 | 11700 | 0 | Green |  |  |  | 11700 |  |  | 187000 |  |  | 187000 | Full | 187000 | 152660 |  | 152660 | No | Green | 2022-08-01 | 2022-07-05 | 2022-07-05 | 2022-09-30 | 2022-09-22 |  |  | 11700 | [18 empty] | 3/14/2023 - Closed WO/PO and set OPPM status to 'Closed'. MCS Can close. | 2023-03-14 | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Auburn Pipeline | AB803WL - AUBURN TO WATERLOO |  | 11700 | 0 |  |  | 140960 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40616 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Assessments
2022 - LD913SR - ILI | Item | Open | MEXP | LD913SRE2201 | Maintenance Framework | 2011991 | Keppel, Nicholas | East | 6. Operational | Defined | Assessments | 0 |  |  | 0 | 719 | -719 | Red |  |  |  | 0 |  |  | 144000 |  |  | 144000 | Full | 144000 | 63038 |  | 63038 | No | Green | 2022-10-01 | 2022-08-11 | 2022-08-11 | 2022-10-31 | 2022-11-03 |  |  | 719 | -13071 | 13071 | -719 |  |  | -719 | Red | [11 empty] | 12/2/2022 - Project completed on 11/3/2022; variance due to savings on field costs | 2022-12-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Jet Lines | LD913SR - LUDLOW TO WESTOVER |  | 719 | -719 |  |  | 63038 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40626 |  | Administrator, System | Independent |  | 2021-07-24 | Int - Assessments
2022 - LN999A1 - Pressure Test and Go/No-Go ILI | Item | Open | MEXP | LN999A1E2201 | Maintenance Framework | 2011989 | Keppel, Nicholas | East | 7. Closed | Defined | Assessments | 697 |  |  | 697.01 | 697 | 0 | Green |  |  |  | 697 |  |  | 134000 |  |  | 134000 | Full | 134000 | 77966 |  | 77966 | No | Green | 2022-09-01 | 2022-08-11 | 2022-08-11 | 2022-10-31 | 2022-10-04 |  |  | 4556.12 | -3859.11 | [17 empty] | 3/9/2023 - Closed WO/PO, and set OPPM status to 'Closed'. MCS Can close. 10/6/2022 - This pressure test project was successfully executed on 10/4/2022 | 2023-03-09 | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Linden | LN999A1 - HUMBLE TO LINDEN |  | 697 | 0 |  |  | 77269 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40627 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Assessments
2022 - LY999D3 - Pressure Test | Item | Open | MEXP | LY999D3E2301 | Maintenance Framework | 2077048 | Keppel, Nicholas | East | 6. Operational | Defined | Assessments | 91040 |  |  | 91039.99 | 91040 | 0 | Green | 70000 |  | 70000 | 21040 |  |  | 144000 |  |  | 144000 | Full | 144000 | 91040 | 0 | 91040 | No | Green | 2023-03-01 | 2023-03-20 | 2023-03-20 | 2023-03-15 | 2023-03-14 |  |  |  |  | 91039.99 | [16 empty] | 3/3/2023 - Pressure Test completed on 3/1/2023 | 2023-03-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Long Island | LY999D3 - APOLLO JCT TO BP/AMOCO (FUEL) |  | 91040 | 0 |  |  |  | 0 | Bartal, Nick | Bartal, Nick |  |  | 1 | 40628 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Assessments
2022 - PY999A2 - Pressure Test and Go/No-Go ILI | Item | Open | MEXP | PY999A2E2201 | Maintenance Framework | 2023842 | Keppel, Nicholas | East | 7. Closed | Defined | Assessments | -3850 |  |  | -3849.67 | -3850 | 0 | Green |  |  |  | -3850 |  |  | 136000 |  |  | 136000 | Full | 136000 | 115447 |  | 115447 | No | Green | 2022-10-01 | 2022-10-24 | 2022-10-24 | 2022-11-14 | 2022-11-14 |  |  | -3849.67 | [18 empty] | 3/9/2023 - Closed WO/PO, and set OPPM status to 'Closed'. MCS Can close. 12/2/2022-Project completed 11/8/2022, awaiting final invoices. | 2023-03-09 | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Malvern | PY999A2 - PAULSBORO TO WOODBURY |  | -3850 | 0 |  |  | 119297 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40636 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Assessments
2022 - ZL999A3 - Pressure Test and Go/No-Go ILI | Item | Open | MEXP | ZL999A3E2201 | Maintenance Framework | 2002081 | Keppel, Nicholas | East | 7. Closed | Defined | Assessments | 2900 |  |  | 2900 | 2900 | 0 | Green |  |  |  | 2900 |  |  | 95000 |  |  | 95000 | Full | 95000 | 97804 |  | 97804 | No | Green | 2022-07-01 | 2022-07-06 | 2022-07-06 | 2022-08-31 | 2022-07-26 |  |  |  | 2900 | [17 empty] | 2/6/2023 - Closed WO/PO, set OPPM project status to 'Closed/ MCS. 1/5/2023-Can close. 10/10/2022 - September variance due to missed accrual in August | 2023-02-06 | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Auburn Pipeline | ZL999A3 - VESTAL TO BET VESTAL #2 DIESEL |  | 2900 | 0 |  |  | 94904 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40644 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Assessments
2022 BBH Warehouse Floor Replacement | Item | Open | MEXP | 8410811E2219 | Maintenance Framework | 2051094 | Herry, Ryan | East | 6. Operational | Unplanned | East | 3078 |  |  | 3078 | 3078 | 0 | Green | 50000 |  | 50000 | -46922 |  |  | 52000 |  |  | 52000 | Full | 52000 | 51194 |  | 51194 | No | Green | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2022-12-31 | 2023-01-05 |  |  | 1688 | 1390 | [17 empty] | 03/03/2023 - This project is ready to be closed. 02/2/2023 - Project is operational. 11/23/2022 - Project pulled forward by PMO office, Forecast adjusted. RH | 2023-03-03 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 3078 | 0 |  |  | 48116 |  | Orischak, Bob | Nash, Tom |  |  | 1 | 45607 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
2022 EW913LD - P-0122485 Anomaly Dig | Item | Open | MCAP | EW913RWM2203 | Maintenance Framework | 2053900 | Keppel, Nicholas | East | 6. Operational | Emergent | Pipeline Digs | 159444 |  |  | 159443.94 | 157242 | 2202 | Yellow |  |  |  | 159444 |  |  | 194000 |  |  | 194000 | Interim | 194000 | 159444 |  | 159444 | No | Green | 2023-01-01 | 2023-02-03 | 2023-02-03 | 2023-01-31 | 2023-01-31 |  |  | 97457.38 | 24553.19 | 35231.71 | 2201.66 |  |  | 2202 | Red | [11 empty] | 3/3/2023 - Work completed in January 2023; minor costs still anticipated (and forecasted) for Q1 2023 | 2023-03-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Jet Lines | EW913RW - NEW HAVEN TO MIDDLETOWN JCT |  | 157242 | 2202 |  |  |  |  | Bartal, Nick | Orischak, Bob |  |  | 1 | 46399 |  | Perry, Betty | Independent | Aqua | 2022-12-21 | Int- Planned Digs
2022 St. Lucia External API 653 Inspections | Item | Open | MEXP | BSLQL00E2206 | Maintenance Framework | 1955660 | Campbell, Jamie | East | 6. Operational | Defined | Tanks | -13920 |  |  | -13920 | -13920 | 0 | Green |  |  |  | -13920 |  |  | 46000 |  | 14934 | 60934 | Supplemental | 60934 | 23350 |  | 23350 | No | Green | 2022-05-01 | 2022-03-10 | 2022-03-10 | 2022-04-01 | 2022-04-01 |  |  | -13920 | [18 empty] | 2/3/2023 -$13.9K accrual being dropped per Bob Orishack to close project. HMT completed all 2022 external inspection in March. 6/24/22-CES-Additional inspection requested by CATSI while onsite at St Lucia for July. | 2023-02-12 | Coverley, Colleen |  | East | Pipelines and Terminals | Tank Integrity |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  | -13920 | 0 |  |  | 37270 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41219 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
2023 AB803RC - UCC | Item | Open | MEXP | AB803WLE2301 | Maintenance Framework | 2084611 | Keppel, Nicholas | East | 3. Active | Defined | Assessments |  | 550604 |  | 550604 | 550604 | 0 | Green | 552604 |  | 552604 | -2000 |  |  | 547474 |  |  | 547474 | Full | 547474 |  | 550604 | 550604 | No | Green | 2023-09-01 | 2023-02-03 | 2023-02-03 | 2023-12-31 | 2023-04-30 | [16 empty] | 550604 | [6 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Auburn Pipeline | AB803WL - AUBURN TO WATERLOO |  |  | 0 | 550604 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44668 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 AJ999A1 - Pressure Test | Item | Open | MEXP |  | Maintenance Framework |  | Keppel, Nicholas | East | 1. Proposed |  | Assessments |  | 53000 |  | 53000 | 53000 | 0 | Green | 55000 |  | 55000 | -2000 | [9 empty] | 53000 | 53000 | No | Green | 2023-10-01 |  |  |  | 2023-10-31 | [17 empty] | 53000 | [7 empty] | East | Pipelines and Terminals | Pipeline Integrity |  | Jet Lines | AJ999A1 - MAIN STREET JCT TO NORA |  |  | 0 |  | 53000 |  |  | Bartal, Nick |  |  |  | 1 | 44669 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 BA913EW - ILI | Item | Open | MEXP | BA913HVE2301 | Maintenance Framework | 2084610 | Keppel, Nicholas | East | 6. Operational | Defined | Assessments | 54478 | 10000 |  | 64478.14 | 90123 | -25645 | Red | 105615 |  | 105615 | -41137 |  |  | 97334 |  |  | 97334 | Full | 97334 | 54478 | 10000 | 64478 | No | Green | 2023-03-01 | 2023-02-03 | 2023-02-03 | 2023-12-31 | 2023-04-03 |  |  |  |  | 20123.01 | 34355.13 | 60000 | 60000 | -25645 | Red |  | Other | 10000 | [8 empty] | 5/3/2023 - ILI run was completed on 4/3/2023; variance due to field costs coming in less than anticipated. Minor trap restoration work scheduled for May/June 2023 | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Jet Lines | BA913HV - BOOSTER #2 TO N HAVEN TERM |  | 20123 | 44355 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44671 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 BS913GW - ILI | Item | Open | MEXP | BS913AYE2301 | Maintenance Framework | 2084614 | Keppel, Nicholas | East | 6. Operational | Defined | Assessments | 54073 | 10000 |  | 64072.9 | 92346 | -28273 | Red | 114600 |  | 114600 | -50527 |  |  | 96724 |  |  | 96724 | Full | 96724 | 54073 | 10000 | 64073 | No | Green | 2023-03-01 | 2023-02-03 | 2023-02-03 | 2023-12-31 | 2023-04-04 |  |  |  |  | 22345.89 | 31727.01 | 60000 | 60000 | -28273 | Red |  | Other | 10000 | [8 empty] | 5/3/2023 - ILI run was completed on 4/4/2023; variance due to field costs coming in less than anticipated. Minor trap restoration work scheduled for May/June 2023 | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Jet Lines | BS913AY - BAY ST JCT-ALBANY ST JCT |  | 22346 | 41727 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44673 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 Drawdown East Region MCAP | Item | Open | MCAP |  | Maintenance Framework |  | Orischak, Bob | East | 3. Active |  | East |  | 415000 |  | 415000 | 535000 | -120000 | Red | 1000000 | -52868 | 947132 | -532132 | [9 empty] | 415000 | 415000 | No | Green | 2023-07-01 |  |  |  | 2023-11-30 | [12 empty] | 0 |  | 172000 | 100000 | 100000 | 30000 | 13000 |  |  | 5/3/2023 RLO Removed 100k from Bald Mt. Gravitometer to fund the repairs to the pipeline in BBH that leaked. 5/1/23 RLO Moved 50k to drawdown canceled Rensellear building refirb. 4/29/2023 RLO Hamdon Roof Leaking Replacement 28k 4/25/23 RLO - Fire line replacement at Richmond South. Emergent and needed to be replaced to stay in business 150k 4/18/23 RLO Supplment the costs for Renseleer terminal piping for Hunter 88K 4/14/2020 RLO Needed 6.5k to support the replacement transformer project in New Haven. 3/29/2023 RLO Added 30k back to drawdown due to canceled roeston bathroom project. 3/20/23 RLO: Linden Pressure Transmitter Re-Range 68k 3/20/23 RLO: Fairfax HVAC 70k 3.2.23.DLC: Removed $70k to fund BBH offshore piping CP upgrades;... 202.14.23.DLC: Reduced drawdown to cover carryover... 01/31/2023 - RLO Bayonne transformer replacement 13K 01/13/2023 RLO Baltimore Feeder Replacement 104K | 2023-05-03 |  |  | East | Pipelines and Terminals | Operating Infrastructure | Operating Infrastructure | Corporate | Corporate |  |  | 0 | 372000 | 43000 |  |  | Orischak, Bob |  |  |  | 1 | 45212 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
2023 Drawdown East Region MEXP | Item | Open | MEXP | 1348683E2300 | Maintenance Framework |  | Orischak, Bob | East | 3. Active | Defined | East |  | 158000 |  | 158000 | 280000 | -122000 | Red | 500000 |  | 500000 | -342000 |  |  | 500000 |  |  | 500000 | Full | 500000 |  | 158000 | 158000 | No | Green | 2023-06-01 | 2023-01-13 | 2023-01-13 | 2023-12-31 | 2023-11-30 | [12 empty] | 0 | 58000 | 100000 | [6 empty] | 5/2/23 RLO 45k of funding added to supplement BBH Boiler 2 tube re-roll 5/1/23 RLO Rochester West Pump Rebuild 31k 4/18/2023 RLO BBH DP8115 Caterpillar engine repairs 30k 4/17/23 RLO Repair the prover at LIC for gene at 20k 4/14/23 RLO evaluate the fire pump truck in Pt. Reading to possible move to yabucoa 6k 4/14/2023 RLO This is to fund the Butane Relief study in Pt. reading per regulatory requirement 85k 3/21/23 RLO BBH Boiler 2 Tube scan 85k 2/22/2023 RLO Lighting System Repair Chesapeake Terminal 33k 2/17/2023 RLO Ridley Park Krohne Meter replacement with turbine meter. 30k 2/15/2023 RLO Mechanicsburg Unit 2 Repair. 67k 1/18/2023 RLO Linden Station Repair VFD HVAC 45k | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal | Station/Terminal | Corporate | Corporate |  |  | 58000 | 100000 |  |  |  | Orischak, Bob | Serra, William R. |  |  | 1 | 45213 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
2023 FA999A1 - Pressure Test | Item | Open | MEXP |  | Maintenance Framework |  | Keppel, Nicholas | East | 1. Proposed |  | Assessments |  | 53000 |  | 53000 | 53000 | 0 | Green | 55000 |  | 55000 | -2000 | [9 empty] | 53000 | 53000 | No | Green | 2023-10-01 |  |  |  | 2023-11-30 | [17 empty] | 53000 | [7 empty] | East | Pipelines and Terminals | Pipeline Integrity |  | Jet Lines | FA999A1 - ENFIELD JCT TO TROIANO |  |  | 0 |  | 53000 |  |  | Bartal, Nick |  |  |  | 1 | 44683 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 JH725HS - ILI | Item | Open | MEXP | JH725HSE2301 | Maintenance Framework | 2084619 | Gebert, Clint | East | 3. Active | Defined | Assessments |  | 83960 |  | 83960 | 83960 | 0 | Green | 85960 |  | 85960 | -2000 |  |  | 85960 |  |  | 85960 | Full | 85960 |  | 83960 | 83960 | No | Green | 2023-11-01 | 2023-02-03 | 2023-02-03 | 2023-12-31 | 2023-11-30 | [18 empty] | 83960 |  |  |  |  | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Mechanicsburg | JH725HS - HIGHSPIRE JCT-HIGHSPIRE |  |  | 0 |  | 83960 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44690 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 JM723MG - ILI | Item | Open | MEXP | JM723MGE2301 | Maintenance Framework | 2084618 | Gebert, Clint | East | 3. Active | Defined | Assessments |  | 85740 |  | 85740 | 85740 | 0 | Green | 87740 |  | 87740 | -2000 |  |  | 87740 |  |  | 87740 | Full | 87740 |  | 85740 | 85740 | No | Green | 2023-10-01 | 2023-02-03 | 2023-02-03 | 2023-12-31 | 2023-10-31 | [17 empty] | 85740 | [5 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Mechanicsburg | JM723MG - MECHANIC JCT - MECHANIC EAST |  |  | 0 |  | 85740 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44691 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 LN620ZG - ILI | Item | Open | MEXP | LN620FZE2301 | Maintenance Framework | 2084612 | Keppel, Nicholas | East | 3. Active | Defined | Assessments | 38638 | 142858 |  | 181496 | 180858 | 638 | Yellow | 182858 |  | 182858 | -1362 |  |  | 170919 |  |  | 170919 | Full | 170919 | 38638 | 142858 | 181496 | No | Green | 2023-04-01 | 2023-02-03 | 2023-02-03 | 2023-12-31 | 2023-04-30 | [5 empty] | 38638 | 38000 | 38000 | 638 | Yellow |  |  | 142858 | [8 empty] | 5/3/2023 - GPS survey of AGM locations completed in April; ILI run scheduled for 5/24/2023 | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Linden | LN - LINDEN STATION |  |  | 181496 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44694 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 MX751ZP - ILI | Item | Open | MEXP | MX751REE2302 | Maintenance Framework | 2084616 | Gebert, Clint | East | 3. Active | Defined | Assessments |  | 116704 |  | 116704 | 116704 | 0 | Green | 65000 |  | 65000 | 51704 |  |  | 116703 |  |  | 116703 | Full | 116703 |  | 116704 | 116704 | No | Green | 2023-07-01 | 2023-02-03 | 2023-02-03 | 2023-12-31 | 2023-09-30 | [14 empty] | 26852 | 26852 | 63000 | [6 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Malvern | MX - MALVERN STATION TERMINAL |  |  | 0 | 116704 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44695 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 PC605LN - ILI | Item | Open | MEXP | PC605LNE2301 | Maintenance Framework | 2084617 | Keppel, Nicholas | East | 3. Active | Defined | Assessments |  | 99613 |  | 99613 | 99613 | 0 | Green | 101613 |  | 101613 | -2000 |  |  | 93178 |  |  | 93178 | Full | 93178 |  | 99613 | 99613 | No | Green | 2023-05-01 | 2023-02-03 | 2023-02-03 | 2023-12-31 | 2023-11-30 | [12 empty] | 4000 | [5 empty] | 95613 |  |  |  |  | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Perth Amboy | PC606QF - PERTH AMBOY TO RARITAN BAY |  |  | 4000 |  | 95613 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44696 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 PC606QF - ILI | Item | Open | MEXP | PC606QFE2301 | Maintenance Framework | 2084615 | Keppel, Nicholas | East | 3. Active | Defined | Assessments |  | 83285 |  | 83285 | 83285 | 0 | Green | 85285 |  | 85285 | -2000 |  |  | 85960 |  |  | 85960 | Full | 85960 |  | 83285 | 83285 | No | Green | 2023-08-01 | 2023-02-03 | 2023-02-03 | 2023-12-31 | 2023-08-31 | [15 empty] | 83285 | [7 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Perth Amboy | PC606QF - PERTH AMBOY TO RARITAN BAY |  |  | 0 | 83285 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44697 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 RG999A1 - Pressure Test | Item | Open | MEXP | RG999A1E2302 | Maintenance Framework | 2112973 | Keppel, Nicholas | East | 3. Active | Defined | Assessments |  | 118000 |  | 118000 | 116000 | 2000 | Yellow | 118000 |  | 118000 | 0 |  |  | 127650 |  |  | 127650 | Full | 127650 |  | 118000 | 118000 | No | Green | 2023-06-01 | 2023-04-28 | 2023-04-28 | 2023-06-30 | 2023-05-31 | [13 empty] | 118000 | [9 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Macungie Pipe | RG999A1 - TUCKERTON TO FARM & HOME |  |  | 118000 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44700 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 St Lucia External API 653 Inspections | Item | Open | MEXP | BSLQL00E2301 | Maintenance Framework | 2053012 | Campbell, Jamie | East | 3. Active | Defined | Tanks | 31065 | 38945 | 6990 | 70010 | 70000 | 10 | Yellow | 70000 |  | 70000 | 10 |  |  | 77000 |  |  | 77000 | Full | 77000 | 31065 | 45935 | 77000 | No | Green | 2023-04-01 | 2022-12-21 | 2022-12-21 | 2023-12-31 | 2023-06-30 | [5 empty] | 31065 | 30000 | 30000 | 1065 | Yellow |  |  | 20000 | 18945 | [6 empty] | 6990 | 5/1/2023 Tank 1017 & 1030 inpections completed by TESTEX. HMT completed Tanks FOX 44 and 02 FSS, waiting on HMT final invoice. 04/03/2023 - TesTex inspection are schedule to arrive terminal on April 10, 2023 to complete in Tanks 1017 & 1030 inspections. 03/02/2023 - Per commercial push back, the forecast is being pushed back a month (to April) to accommodate T1030 and T1017 in a single mobilization. 2/3/2023 - RFP has be send out to Contractors. Inspections are scheduled to start in March 2023. | 2023-05-01 |  |  | East | Pipelines and Terminals | Tank Integrity |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  |  | 70010 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44759 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
2023 SV913DY - ILI | Item | Open | MEXP | SV913DYE2301 | Maintenance Framework | 2084609 | Keppel, Nicholas | East | 6. Operational | Defined | Assessments | 59673 |  |  | 59673.04 | 104535 | -44862 | Red | 112575 |  | 112575 | -52902 |  |  | 104222 |  |  | 104222 | Full | 104222 | 59673 |  | 59673 | No | Green | 2023-03-01 | 2023-02-03 | 2023-02-03 | 2023-12-31 | 2023-04-05 |  |  |  |  | 9534.98 | 50138.06 | 95000 | 95000 | -44862 | Red |  | Other | [9 empty] | 5/3/2023 - ILI run was completed on 4/5/2023; variance due to field costs coming in less than anticipated. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Jet Lines | SV913DY - SULLIVAN AVE TO BRADELY TK FM |  | 9535 | 50138 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44703 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 VR999A1 - Pressure Test | Item | Open | MEXP |  | Maintenance Framework |  | Gebert, Clint | East | 1. Proposed |  | Assessments |  | 88000 |  | 88000 | 88000 | 0 | Green | 90000 |  | 90000 | -2000 | [9 empty] | 88000 | 88000 | No | Green | 2023-10-01 |  |  |  | 2023-10-31 | [17 empty] | 88000 |  |  |  | 5/5/23 - Test planning on hold while regulatory determination is reviewed. Not yet canceled | 2023-05-05 |  |  | East | Pipelines and Terminals | Pipeline Integrity |  | Virginia | BSEVR - ROANOKE TERMINAL |  |  | 0 |  | 88000 |  |  | Bartal, Nick |  |  |  | 1 | 44726 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 VR999A2 - Pressure Test | Item | Open | MEXP |  | Maintenance Framework |  | Gebert, Clint | East | 1. Proposed |  | Assessments |  | 88000 |  | 88000 | 88000 | 0 | Green | 90000 |  | 90000 | -2000 | [9 empty] | 88000 | 88000 | No | Green | 2023-10-01 |  |  |  | 2023-10-31 | [17 empty] | 88000 |  |  |  | 5/5/23 - Test planning on hold while regulatory determination is reviewed. Not yet canceled | 2023-05-05 |  |  | East | Pipelines and Terminals | Pipeline Integrity |  | Virginia | BSEVR - ROANOKE TERMINAL |  |  | 0 |  | 88000 |  |  | Bartal, Nick |  |  |  | 1 | 44727 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 VR999A3 - Pressure Test | Item | Open | MEXP | VR999A3E2301 | Maintenance Framework | 2112785 | Gebert, Clint | East | 2. Pending AFE |  | Assessments |  | 90000 |  | 90000 | 90000 | 0 | Green |  |  |  | 90000 | [6 empty] | Interim |  |  | 90000 | 90000 | No | Green | 2023-10-01 |  |  | 2023-12-31 | 2023-12-31 | [17 empty] | 90000 |  |  |  | 5/5/23 - Test planning on hold while regulatory determination is reviewed. Not yet canceled | 2023-05-05 | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Virginia | BSEVR - ROANOKE TERMINAL |  |  | 0 |  | 90000 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46517 |  | Schultz, Amy | Independent | Aqua | 2023-01-23 | Int - Assessments
2023 Yabucoa External API 653 Inspections | Item | Open | MEXP | BCTYA00E2304 | Maintenance Framework | 2053011 | Campbell, Jamie | East | 3. Active | Defined | Tanks | 58452 | 28548 |  | 87000 | 87000 | 0 | Green | 85000 |  | 85000 | 2000 |  |  | 87000 |  |  | 87000 | Full | 87000 | 58452 | 28548 | 87000 | No | Green | 2023-03-01 | 2022-12-21 | 2022-12-21 | 2023-12-31 | 2023-09-30 |  |  |  |  | 29226 | 29226 | 29226 | 29226 | 0 | Green |  |  | 28548 | [8 empty] | 5/1/2023 - Project Specialist have completed the second set of external inspection (Tanks 03,04, 18, 30,37) 4/3/2023 - Tank 003-33, 41, & 42 inspections are completed. 3/8/23 Project Specialist is scheduled to start tanks inspection 3/13/223. 03/02/2023 - Project remains on schedule to meet forecasts. 2/3/2023 - RFP was send out to Contractors and project is scheduled to begin in March 2023. | 2023-05-01 |  |  | East | Pipelines and Terminals | Tank Integrity |  | Yabucoa | 51YABUCOA - YABUCOA DUE DILIGENCE |  | 29226 | 57774 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44763 |  | Administrator, System | Independent |  | 2022-08-18 | Int - Tanks
2023 ZG701JC - Seam ILI | Item | Open | MEXP | ZG701GZE2301 | Maintenance Framework | 2084613 | Keppel, Nicholas | East | 3. Active | Defined | Assessments |  | 898170 |  | 898170 | 898170 | 0 | Green | 900170 |  | 900170 | -2000 |  |  | 1048162 |  |  | 1048162 | Full | 1048162 |  | 898170 | 898170 | No | Green | 2023-07-01 | 2023-02-03 | 2023-02-03 | 2023-12-31 | 2023-07-31 | [14 empty] | 898170 | [8 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Macungie Pipe | ZG701GZ - MACUNGIE -GUTHSVILLE-16IN |  |  | 0 | 898170 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44736 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
601/602 CP Upgrades | Item | Open | MCAP | JK00000M2201 | Maintenance Framework | 1946433 | Occhi, Edward | East | 7. Closed | Defined | Cathodic Protection | -546 |  |  | -546.18 | -546 | 0 | Green |  |  |  | -546 |  |  | 55000 |  |  | 55000 | Full | 55000 | 60747 |  | 60747 | No | Green | 2022-02-01 | 2022-02-10 | 2022-02-10 | 2022-12-31 | 2022-11-30 |  |  | -636.8 | 90.62 | [17 empty] | 01/27/2023 - CWIP charges for Dec. and additional costs triggered supplement; $2,700 Reclass submitted to BPTPC00M2202. | 2023-01-27 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Long Island | JK - JFK TERMINAL |  | -546 | 0 |  |  | 61293 |  | Geib, Rob | Geib, Robert |  |  | 1 | 40909 |  | Guest, ProSight | Independent | Aqua | 2021-08-03 | Other Programs
603/620 CP Upgrade | Item | Open | MCAP | LN603FZM2301 | Maintenance Framework | 2094812 | Occhi, Edward | East | 3. Active | Defined | Cathodic Protection |  | 40000 |  | 40000 | 45000 | -5000 | Red | 45000 |  | 45000 | -5000 |  |  | 45552 |  |  | 45552 | Full | 45552 |  | 40000 | 40000 | No | Green | 2023-07-01 | 2023-03-09 | 2023-03-09 | 2023-11-15 | 2023-04-30 | [6 empty] | 0 | 0 | 0 | Green |  |  |  | 0 | 40000 | 0 | [5 empty] | 4/4/2023 Delay due to Contractor availability. | 2023-04-04 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Linden | LN603FZ - LINDEN TO FLEM VALVE -16IN |  |  | 0 | 40000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45076 |  | Guest, ProSight | Independent | Aqua | 2022-08-18 | Int - Planned Corr & FI
607 Pipeline CP Upgrades | Item | Open | MCAP | LN607NWM2201 | Maintenance Framework | 1939408 | Occhi, Edward | East | 7. Closed | Defined | Cathodic Protection | 3077 |  |  | 3076.63 | 3077 | 0 | Green |  |  |  | 3077 |  |  | 30000 |  |  | 30000 | Full | 30000 | 32932 |  | 32932 | No | Green | 2022-02-01 | 2022-01-21 | 2022-01-21 | 2022-12-31 | 2022-11-30 |  |  | 2964 | 112.63 | [17 empty] | 01/04/2023 Reclass still pending. 12/8/2022 Reclass submitted to move $9,313.96 of payroll charges to MEXP project BETWE00E2202. | 2023-01-04 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Linden | LN607NW - LINDEN TO NEWARK AIRPORT |  | 3077 | 0 |  |  | 29855 |  | Geib, Rob | Geib, Robert |  |  | 1 | 40738 |  | Guest, ProSight | Independent | Aqua | 2021-07-26 | Other Programs
702 Macungie Booster Check Valve | Item | Open | MCAP | ZG00000M2213 | Maintenance Framework | 2003293 | Gebert, Clint | East | 3. Active | Defined | Transient/Surge Mitigation | 15098 | 10000 |  | 25097.73 | 38100 | -13003 | Red |  |  |  | 25098 |  |  | 75000 |  |  | 75000 | Full | 75000 | 51394 | 10000 | 61394 | No | Green | 2022-10-01 | 2022-12-08 | 2022-12-08 | 2023-03-31 | 2023-03-31 |  |  | 1318.67 | 2493.47 | 2288.16 | 8997.43 | 32000 | 32000 | -23003 | Red |  |  | 10000 | [8 empty] | 5/3/23-CGG- spring check was installed. project is expected to be under budget. waiting on trailing costs.4/4/23-CGG- Install scheduled for April. 3/3/2023-Pressure test performed, hoping for April install. 2/3/2023-Variance due to a several week delay because the material ordered to conduct pressure test had not arrived. 12/1/22-CGG-spring check has been received. Needs to be hydrotested and install will most likely be in 2023. 8/3/22-CGG- Spring check has been ordered. May not be installed this year due to workload/timing. 7/6/22-CGG- Have had meetings and site visits to define problem statement and scope. Waiting on quotes for 2 different styles of spring checks. It is likely that budget will be mostly used to order material. lead time is significant. Once quotes are received, I will make a determination which spring check can be used and whether hot work will be required for install. A full AFE/estimate will be generated at that time.5/27/22-CGG- I have talked to Asset Team and Corporate regarding a surge study. No one knows what the scope of this project is. I believe it was entered into OPPM by an employee that has since retired. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | ZG - MACUNGIE STATION |  | 6100 | 18997 |  |  | 36297 |  | DiPillo, Evan | Orischak, Bob |  |  | 1 | 41470 |  | Guest, ProSight | Independent | Aqua | 2021-08-17 | Other Programs
AB802CY - 2022 Buckeye Criteria Digs | Item | Open | MCAP | DJ802ZRM2202 | Maintenance Framework | 1989695 | Keppel, Nicholas | East | 6. Operational | Defined | Pipeline Digs | 18349 |  |  | 18348.74 | 18349 | 0 | Green |  |  |  | 18349 |  |  | 241000 |  |  | 241000 | Full | 241000 | 197144 |  | 197144 | No | Green | 2022-10-01 | 2022-06-07 | 2022-06-07 | 2022-11-30 | 2022-12-31 |  |  | 17677.01 | 671.73 | [17 empty] | 2/2/2022-Trailing invoice from December 2022. 1/5/2023 - Project completed in December 2022; variance due to additional days spent pumping water out of work area due to recent precipitation | 2023-02-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | AB - AUBURN STATION |  | 18349 | 0 |  |  | 178796 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40997 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
AB802CY - Digs from 2022 GEO+MFL ILI | Item | Open | MCAP | LP802SJM2201 | Exempt | 2045139 | Keppel, Nicholas | East | 6. Operational | Defined | Pipeline Digs | 89627 |  |  | 89627.16 | 89627 | 0 | Green |  |  |  | 89627 |  |  | 204000 |  |  | 204000 | Full | 204000 | 89627 |  | 89627 | No | Green | 2023-01-01 | 2022-11-17 | 2022-11-17 | 2023-01-31 | 2022-12-31 |  |  | 82526.64 | 6794.76 | 305.76 | [16 empty] | 2/2/2023 - Work completed in January 2023 | 2023-02-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | LP802SJ - LIVERPOOL TO SYRACUSE JCT |  | 89627 | 0 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 41015 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
AB803RC DOT 60 and BPL Other Digs | Item | Open | MCAP | AB803WLM2301 | Maintenance Framework | 2109837 | Gebert, Clint | East | 2. Pending AFE |  | Pipeline Digs | 81915 | 1200001 |  | 1281915.93 | 85001 | 1196915 | Red |  |  |  | 1281916 | [6 empty] | Interim |  | 81915 | 1200001 | 1281916 | No | Green | 2023-04-01 |  |  |  | 2023-12-31 | [5 empty] | 81914.93 | 85000 | 85000 | -3085 | Yellow |  |  |  |  | 200000 | 400000 | 400000 | 200000 |  | 1 |  | 5/3/2023-the DOT-60 dig is done. The 15 BPL-Other digs are expected to start in summer and finish by December. 4/4/23-CGG- Forecast entered for April to complete DOT 60 site. Remaining sites will be completed later in the year. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | AB803WL - AUBURN TO WATERLOO |  |  | 81915 | 1000000 | 200001 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46864 |  | Meitzler, Antoinette | Independent | Aqua | 2023-03-31
Albany Air to ground coating phase 1 | Item | Open | MCAP | BATNY00M2305 | Maintenance Framework | 2085619 | Norton, Bill | East | 3. Active | Defined | Atmospheric Corrosion |  | 45000 |  | 45000 | 45000 | 0 | Green | 45000 |  | 45000 | 0 |  |  | 45435 |  |  | 45435 | Full | 45435 |  | 45000 | 45000 | No | Green | 2023-10-01 | 2023-02-21 | 2023-02-21 | 2023-11-01 | 2023-11-30 | [17 empty] | 45000 | [5 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Albany | BATNY - BAT ALBANY |  |  | 0 |  | 45000 |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44343 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
Albany Alternate Steam Supply Engineering Study - 2022 | Item | Open | MCAP | BATNY00M2301 | Maintenance Framework | 2074860 | DeSocio, David | East | 7. Closed | Defined | Boilers | 26187 |  |  | 26187 | 25059 | 1128 | Yellow | 25000 |  | 25000 | 1187 |  |  | 25048 |  |  | 25048 | Full | 25048 | 26187 |  | 26187 | No | Green | 2023-03-01 | 2023-01-10 | 2023-01-10 | 2023-06-01 | 2023-03-31 |  |  |  |  | 25059.34 | 1127.66 |  |  | 1128 | Red | [13 empty] | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Albany | BATNY - BAT ALBANY |  | 25059 | 1128 |  |  |  |  | Stine, Carlton | Tracey, Steve |  |  | 1 | 44534 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Other Programs
Albany Asphalt Loading Arm Replacement 2023 | Item | Open | MCAP | BATNY00M2308 | Maintenance Framework | 2111951 | Orischak, Bob | East | 3. Active | Defined | Truck Racks |  | 70000 |  | 70000 |  | 70000 | Red |  | 70000 | 70000 | 0 |  |  | 70090 |  |  | 70090 | Full | 70090 |  | 70000 | 70000 | No | Green | 2023-06-01 | 2023-04-19 | 2023-04-19 | 2023-07-01 | 2023-06-29 | [13 empty] | 50000 | 20000 | [8 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Albany | BATNY - BAT ALBANY |  |  | 50000 | 20000 |  |  |  | Younce, Michael | Tracey, Steve |  |  | 1 | 46936 |  | Orischak, Bob | Independent | Aqua | 2023-04-14
Albany Asphalt Replace Rail Offload pump | Item | Open | MCAP | BATNY00M2307 | Maintenance Framework | 2096641 | Wing, Hunter | East | 3. Active | Defined | Rotating Equipment | 35091 | 58085 |  | 93176.27 | 93821 | -645 | Yellow | 80000 |  | 80000 | 13176 |  |  | 93821 |  |  | 93821 | Full | 93821 | 35091 | 58085 | 93176 | No | Green | 2023-04-01 | 2023-03-31 | 2023-03-31 | 2023-05-22 | 2023-05-31 | [5 empty] | 35091.27 | 60000 | 60000 | -24909 | Red |  | Contractor/Vendor Issue | 41835 | 16250 | [7 empty] | 5/1/2023 - HJW - Contractor to begin SOW week of 5/1, now that they are caught up with Daylight Project. Missed forecast due to a delay in Daylighting Project and Operational shutdown window for rail yard. Work expected to be completed before end of May. Forecast has been updated to represent corrected forecast 4/4/2023-PO issued today. 3.02.23 - Doing bid walks on Tues. Expecting work to be done in April/May. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Albany | BATNY - BAT ALBANY |  |  | 93176 |  |  |  |  | Posipanko, Dan | Fetchko, Mark |  |  | 1 | 44155 |  | Guest, ProSight | Independent | Aqua | 2022-07-15 | Other Programs
Albany HVAC Replacement | Item | Open | MCAP | BATNY00M2306 | Maintenance Framework | 2096555 | Schwindt, Joseph | East | 6. Operational | Defined | East | 25044 | 0 |  | 25044.12 | 33000 | -7956 | Red | 35000 |  | 35000 | -9956 |  |  | 31615 |  |  | 31615 | Full | 31615 | 25044 | 0 | 25044 | No | Green | 2023-04-01 | 2023-03-30 | 2023-03-30 | 2023-06-01 | 2023-04-21 | [5 empty] | 25044.12 | 0 | 0 | 25044 | Red |  |  | 0 | [8 empty] | 4/26/23: HVAC unit installed by contractor on 4/21/23. Project is complete and operational. 4/2/203 - PO imminent to Colonie. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Albany | BATNY - BAT ALBANY |  |  | 25044 |  |  |  |  | Orischak, Bob | Orischak, Bob |  |  | 1 | 41491 |  | Guest, ProSight | Independent | Aqua | 2021-08-18 | Other Programs
Albany Insulated Pipe Priority 2 Repairs | Item | Open | MEXP |  | Maintenance Framework |  | Wing, Hunter | East | 8. Canceled |  | Facility Integrity |  | 0 |  | 0 | 15000 | -15000 | Red | 15000 |  | 15000 | -15000 | [9 empty] | 0 | 0 | No | Green |  |  |  |  | 2023-05-31 | [12 empty] | 0 | [8 empty] | 2.2.2023 - HW - Site Walkdown completed with operations on 1.30.23. During the walk down it was determined that the P2 item was already completed by operations. Working with Facility Integrity to determine if a P3 requirement is needed. | 2023-02-02 |  |  | East | Pipelines and Terminals | Station/Terminal |  | Albany | BATNY - BAT ALBANY |  |  | 0 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45071 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Albany North & Asphalt Rail repair | Item | Open | MEXP | BATNY00E2206 | Maintenance Framework | 1955569 | Keppel, Nicholas | East | 6. Operational | Defined | Rail | 9342 |  |  | 9342 | 9342 | 0 | Green |  |  |  | 9342 |  |  | 48000 |  |  | 48000 | Full | 48000 | 47942 |  | 47942 | No | Green | 2022-04-01 | 2022-03-09 | 2022-03-09 | 2022-05-31 | 2022-04-30 |  |  |  |  | 9342 | [16 empty] | 3/6/2023 - Re-set Project back to operational, since there is an additional ~9K PO that was just entered against the project that may be accomodated here. 2/6/2023 - Closed WO/PO, set OPPM project status to 'Closed'. 1/5/2023-Can close. 5/4/2022 - Project completed in April 2022 | 2023-03-06 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Albany | BATNY - BAT ALBANY |  | 9342 | 0 |  |  | 38600 |  | Clark, Dave | Younce, Michael |  |  | 1 | 41527 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
Albany PCW bypass of TKS 10 & 11 | Item | Open | MCAP | BATNY00M2310 | Maintenance Framework | 2112632 | Schwindt, Joseph | East | 3. Active | Defined | Storm Water Management |  | 55000 |  | 55000 | 55000 | 0 | Green | 55000 |  | 55000 | 0 |  |  | 60521 |  |  | 60521 | Full | 60521 |  | 55000 | 55000 | No | Green | 2023-06-01 | 2023-04-25 | 2023-04-25 | 2023-06-30 | 2023-06-30 | [6 empty] | 0 | 0 | 0 | Green |  |  |  | 55000 | [7 empty] | 5/3/23-Quotes received. AFE approved. POs pending. Working w/Teminal to coordinate. 4/3/2023-Getting quotes. 2/23/23 - JTS: Pushed $55K forecast to May, project to start working in March. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Albany | BATNY - BAT ALBANY |  |  | 55000 |  |  |  |  | Bonenberger, Mark | Bonenberger, Mark |  |  | 1 | 44535 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Other Programs
Albany Phase 1 Insulated Piping Inspection | Item | Open | MEXP |  | Maintenance Framework |  | Wing, Hunter | East | 8. Canceled |  | Facility Integrity |  | 0 |  | 0 | 8000 | -8000 | Red | 8000 |  | 8000 | -8000 | [9 empty] | 0 | 0 | No | Green |  |  |  |  | 2023-07-31 | [14 empty] | 0 | [6 empty] | 2.2.2023 - HW - After discussions with Facility Integrity, it appears this project will be returned to the program to be redistributed. | 2023-02-02 |  |  | East | Pipelines and Terminals | Station/Terminal |  | Albany | BATNY - BAT ALBANY |  |  | 0 | 0 |  |  |  | Aiken, Elaine |  |  |  | 1 | 41182 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
Albany Slips Trips and Fall Piping and Controls Refurbishments | Item | Open | MCAP | BATNY00M2309 | Maintenance Framework | 2111164 | Orischak, Bob | East | 3. Active | Defined | East |  | 70000 |  | 70000 |  | 70000 | Red |  | 70000 | 70000 | 0 |  |  | 70090 |  |  | 70090 | Full | 70090 |  | 70000 | 70000 | No | Green | 2023-06-01 | 2023-04-17 | 2023-04-17 | 2023-07-01 | 2023-06-07 | [13 empty] | 70000 | [9 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Albany | BATNY - BAT ALBANY |  |  | 70000 |  |  |  |  | Orischak, Bob | Tracey, Steve |  |  | 1 | 46938 |  | Orischak, Bob | Independent | Aqua | 2023-04-13
Albany Terminal (BATNY) Tank 2 - OOS API 653, MOSF & Insulation Refurb | Item | Open | MCAP | BATNY00M2302 | Maintenance Framework | 2074855 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 1000000 |  | 1000000 | 1000000 | 0 | Green | 1425000 |  | 1425000 | -425000 |  |  | 497688 |  |  | 497688 | Phase | 497688 |  | 1425000 | 1425000 | No | Green | 2023-09-01 | 2023-01-10 | 2023-01-10 | 2023-05-30 | 2023-12-31 | [6 empty] | 0 | 0 | 0 | Green | [6 empty] | 20000 | 355000 | 400000 | 225000 |  | 2/13/23-CES-Need to adjust forecast and find savings within tank MCAP program. Moving $425k from this project into 1Q 2024. 2/1/23 - Variance due to planned OOS pushed back to late-Q3 per customer request. Updated forecast. 1/4/23 - Preparing phase 1 AFE for submission. Adjusted forecast with planned spend starting in February. | 2023-02-13 | Allen, Wandell |  | East | Pipelines and Terminals | Integrity |  | Albany | BATNY - BAT ALBANY |  |  | 0 | 20000 | 980000 |  | 425000 | Stine, Carlton | Stine, Carlton |  |  | 1 | 44769 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Albany Terminal (BATNY) Tank 31 - OOS API 653, MOSF + Seal Insp & Refurb | Item | Open | MCAP | BATNY00M2303 | Maintenance Framework | 2077112 | Yoder, Michael | East | 3. Active | Defined | Tanks | 501441 | 172377 |  | 673818.14 | 610526 | 63292 | Red | 607377 |  | 607377 | 66441 |  |  | 225777 |  |  | 225777 | Phase | 225777 | 501441 | 172377 | 673818 | No | Green | 2023-02-01 | 2023-01-30 | 2023-01-30 | 2023-06-30 | 2023-05-31 |  |  |  | 79012.71 | 164136.4 | 258292.03 | 250000 | 250000 | 8292 | Yellow |  |  | 117377 | 55000 | [7 empty] | 5/1/23 - IFR install in progress. Preparing phase 2 AFE for submission. 4/4/23 - IFR install in progress. 3/1/23 - Variance due to completing IFR demo in February. Inspection complete. Repair contractor to mobilize late March. 2/1/23 - Tank previously cleaned. Plan to start removing failed IFR in February. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Albany | BATNY - BAT ALBANY |  | 243149 | 430669 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44766 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Albany Terminal (BATNY) Tank 33 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | BATNY00E2301 | Maintenance Framework | 2093481 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 |  |  | 11000 |  |  | 11000 | Phase | 11000 |  | 10000 | 10000 | No | Green | 2023-07-01 | 2023-03-01 | 2023-03-01 | 2023-12-31 | 2023-07-31 | [14 empty] | 10000 | [8 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Albany | BATNY - BAT ALBANY |  |  | 0 | 10000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44767 |  | Administrator, System | JDE Child | Burnt Orange | 2022-08-17 | Int - Tanks
Albany Terminal (BATNY) Tank 35 - OOS API 653, MOSF + Seal Insp & Refurb | Item | Open | MCAP | BATNY00M2304 | Maintenance Framework | 2086165 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 550509 |  | 550509 | 550509 | 0 | Green | 550509 |  | 550509 | 0 |  |  | 209138 |  |  | 209138 | Phase | 209138 |  | 550509 | 550509 | No | Green | 2023-07-01 | 2023-02-24 | 2023-02-24 | 2023-12-31 | 2023-09-30 | [14 empty] | 144877 | 289755 | 115877 | [8 empty] | East | Pipelines and Terminals | Integrity |  | Albany | BATNY - BAT ALBANY |  |  | 0 | 550509 |  |  |  | Stine, Carlton |  |  |  | 1 | 44768 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Albany Terminal (BATNY) Tank 35 Out of Service Support Project | Item | Open | MEXP | BATNY00E2302 | Maintenance Framework | 2120129 | Yoder, Michael | East | 3. Active | Defined | Tank Outage |  | 55000 |  | 55000 | 150000 | -95000 | Red | 150000 |  | 150000 | -95000 |  |  | 61875 |  |  | 61875 | Full | 61875 |  | 55000 | 55000 | No | Green | 2023-06-01 | 2023-05-04 | 2023-05-04 | 2023-09-30 | 2023-08-31 | [13 empty] | 35000 | 20000 | [6 empty] | 5/3/23 - AFE submitted. 5/1/23 - Preparing AFE for submission. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Albany | BATNY - BAT ALBANY |  |  | 35000 | 20000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44754 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Albany Terminal (BATNY) Tank 37 - OOS Corr + Seal Insp & Refurb | Item | Open | MCAP | BATNY00M2202 | Maintenance Framework | 1937274 | Marrocco, Alex | East | 6. Operational | Defined | Tanks | 29232 |  |  | 29231.67 | 29593 | -361 | Yellow |  |  |  | 29232 |  |  | 280000 |  |  | 280000 | Phase | 280000 | 435987 |  | 435987 | No | Green | 2022-08-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2023-03-31 |  |  | 27562.17 | 2437.92 | -407.48 | -360.94 |  |  | -361 | Red | [11 empty] | 12/5/2022 Working with vendor to provide more timely billing. 9/2/22 - AFE for support project to be submitted week of 9/6. Work expected to start on tank 37 in October. | 2023-02-08 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Albany | BATNY - BAT ALBANY |  | 29593 | -361 |  |  | 406756 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41229 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Albany Terminal (BATNY) Tank 37 - Support Project | Item | Open | MCAP | BATNY00M2203 | Maintenance Framework | 2022473 | Marrocco, Alex | East | 7. Closed | Emergent | Tank Outage | 12042 |  |  | 12041.9 | 12042 | 0 | Green |  |  |  | 12042 |  |  | 261000 |  |  | 261000 | Full | 261000 | 268526 |  | 268526 | No | Green | 2022-09-01 | 2022-09-12 | 2022-09-12 | 2022-10-07 | 2022-10-31 |  |  |  | 11523.35 | 518.55 | [16 empty] | 11/3/2022 payroll charges approx 12K coded to project. 9/11/2022-CES-Emergent AFE being routed for $261,000. Forecasting for September-November. | 2022-11-03 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Albany | BATNY - BAT ALBANY |  | 12042 | 0 |  |  | 256484 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 45757 |  | Meitzler, Antoinette | Independent | Aqua | 2022-09-07 | Int - Tanks
Albany Truck Rack Fall Protection | Item | Candidate | MCAP |  | Maintenance Framework |  | Schwindt, Joseph | East | 1. Proposed |  | Truck Racks |  | 100000 |  | 100000 | 240000 | -140000 | Red | 240000 |  | 240000 | -140000 | [9 empty] | 100000 | 100000 | No | Green | 2023-08-01 |  |  |  | 2023-10-31 | [15 empty] | 30000 | 70000 | 0 |  |  |  | 04/13/2023 Project is being canceled due to work that was completed in previous years. Money will get allocated to albany alphalt loading arm replacement and asphalt pump upgrade.RLO Project should have been entered as a 2023 | 2023-04-13 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Albany | BATNY - BAT ALBANY |  |  | 0 | 100000 | 0 |  |  | Younce, Michael |  |  |  | 1 | 45372 |  | Clark, David | Independent | Aqua | 2022-08-26 | Other Programs
Albany USCG API 570 Priority 2 Refurbishments | Item | Open | MCAP |  | Maintenance Framework |  | Wing, Hunter | East | 1. Proposed |  | Facility Integrity |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 | [9 empty] | 40000 | 40000 | No | Green | 2023-05-01 |  |  |  | 2023-06-30 | 8 | Yellow | [10 empty] | 20000 | 20000 | [7 empty] | 5/1/2023 - HW - Project expected to be completed by end of May. Project will be completed during Daylight and Asphalt Projects. FPI to provide quote for Mechanical SOW the week of 5/1 and Painting contractor soon after. Supply Chain to coordinate small bid event for painting contractors. 2.2.2023 - HW - Site Walkdown completed with Operations on 1.30.23. Some items on the list will be handled by operations. For the items that need to be completed by a contractor, a work plan will be developed, and a contractor walkthrough will take place. Expected to start scope of work in April/May. | 2023-05-01 |  |  | East | Pipelines and Terminals | Integrity |  | Albany | BATNY - BAT ALBANY |  |  | 40000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45057 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Albany, Roseton and Rensselaer terminals annual survey | Item | Open | MEXP | 1348250E2310 | Maintenance Framework | 2084404 | Norton, Bill | East | 8. Canceled | Defined | Cathodic Protection |  | 15000 |  | 15000 | 15000 | 0 | Green | 15000 |  | 15000 | 0 |  |  | 14715 |  |  | 14715 | Full | 14715 |  | 15000 | 15000 | No | Green | 2023-08-01 | 2023-02-01 | 2023-02-01 | 2023-11-01 | 2023-11-30 | [15 empty] | 15000 | [5 empty] | 3/2/2023 - Project is cancelled due to being funded through Local Operations Budget. | 2023-03-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Corrosion |  | Albany | BATNY - BAT ALBANY |  |  | 0 | 15000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44340 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
Asbestos Abatement Reclass from MCAP to MEXP Pt Reading | Item | Open | MEXP | BPRPR00E2301 | Maintenance Framework |  | Keppel, Nicholas | East | 6. Operational | Unplanned | East | 194106 |  |  | 194105.91 | 194106 | 0 | Green |  |  |  | 194106 |  |  | 194000 |  |  | 194000 | Full | 194000 | 194106 |  | 194106 | No | Green | 2023-01-01 | 2023-01-25 | 2023-01-25 | 2023-01-31 | 2023-01-31 |  |  | 194105.91 | [18 empty] | 1/27/2023 - Flip ticket put in for this (# 453090) on Jan 26. Hoping flip (from BPRPR00M2110 to this project BPRPR00E2301) takes place in Jan business. The WO (1856111) was already at status 95. I put in a ticket (#453081) to ask that it be re-opened to status 80. I made a new WO for this project (2076556) and set it to status 80 for expediency purposes in case the closed WO is a hangup. -MCS | 2023-01-27 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 194106 | 0 |  |  |  |  | Orischak, Bob | Orischak, Bob |  |  | 1 | 46535 |  | Orischak, Bob | Independent | Aqua | 2023-01-25 | Other Programs
Auburn 802 Unit 3 Bearing Housing Upgrade | Item | Open | MCAP | AB00000M2203 | Maintenance Framework | 1980316 | Mohr, David | East | 3. Active | Defined | Rotating Equipment | 33546 |  | 16000 | 33545.94 | 17394 | 16152 | Red |  |  |  | 33546 |  |  | 101000 |  | 67000 | 168000 | Supplemental | 168000 | 185532 | 16000 | 201532 | Yes | Red | 2022-05-01 | 2022-05-12 | 2022-05-12 | 2022-07-31 | 2023-05-31 |  |  | 365.76 | 272.54 | 16755.69 | 16151.95 |  |  | 16152 | Red |  | Buckeye/Customer Schedule | [8 empty] | 16000 | 5/1/2023 Supplemental approved. Variance is due to installation and rigging labor. 4/3/2023 Supplemental submitted 3/1/2023 Pump in for hydrotest then shipping this week. DRM 2/2/2023 Pump to ship week of 2/13 1/3/2023 Waiting for shipping. Estimated week of 1/15. 12/1/2022 Issue with PO resolved and pump shaft being scanned. Expect to have returned 2 week in Jan 2023. Supplemental required. 11/1/2022 Correct PO's issued to Goulds Canada. Awaiting shipping. Expecting to install in November. 10/1/2022 PO's will need to be re-cut since work being done in Canada. ITT/Goulds needs to be added as a vendor in COUPA. Supplemental required and funding coming from the program group. DRM 9/2/2022-The Work will be done in September. 8/1/2022 Motor and pump required additional work on bearings. Estimate 4-6 weeks for return. DRM 7/5/2022 Working with HSSE and AAI to get a waiver completed so they can start the work. DRM 6/2/2022 Pump and Motor to be removed by mid-June and sent to vendors for overhaul. DRM 5/2/2022 Working with vendor to get second quote 4/1/2022 DRM Received quotes from Hydroeast and ITT Goulds. Have call 4/4 with Nate Frey and Auburn mechs to discuss best course of action. 3/1/2022 DRM Met with Hydro East to develop scope with asset team. and requested quote to complete the AFE. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Pipeline | AB - AUBURN STATION |  | 17394 | 16152 |  |  | 151986 |  | Posipanko, Dan | Tracey, Steve |  |  | 1 | 40852 |  | Frey, Nathaniel | Independent | Aqua | 2021-07-29 | Other Programs
Auburn Mainline Unit 1 East Pump Base Refurbishment | Item | Open | MCAP | AB00000M2305 | Maintenance Framework | 2094884 | Pepe, David | East | 3. Active | Defined | Rotating Equipment |  | 120000 |  | 120000 | 120000 | 0 | Green | 120000 |  | 120000 | 0 |  |  | 143753 |  |  |  | Full | 143753 |  | 120000 | 120000 | No | Green | 2023-08-01 |  |  | 2023-12-31 | 2023-08-31 | [15 empty] | 120000 | [5 empty] | 2022/12/20 DJP Working with Alloy Mechanical to pull the pump, motor, base and refurbish new base. Looking for direction on pump service. | 2022-12-20 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Pipeline | AB - AUBURN STATION |  |  | 0 | 120000 |  |  |  | Posipanko, Dan | Posipanko, Daniel A. |  |  | 1 | 37390 |  | Guest, ProSight | Independent | Aqua | 2020-07-31 | Other Programs
Auburn Mainline Unit 3 East Pump Base Refurbishment | Item | Open | MCAP | AB00000M2204 | Maintenance Framework | 1981491 | Mohr, David | East | 6. Operational | Defined | Rotating Equipment | 273 |  |  | 272.84 | 273 | 0 | Green |  |  |  | 273 |  |  | 101000 |  | 104000 | 205000 | Supplemental | 205000 | 206302 |  | 206302 | No | Green | 2022-07-01 | 2022-05-24 | 2022-05-24 | 2022-08-31 | 2022-09-30 |  |  | 272.84 | [18 empty] | 4/1/2023 Supplemental Submitted2/3/2023-Closed WO/PO, POs already closed. 2/2/2023-Can close. 10/5/2022-Project is completed, late invoice. 9/1/2022 Baseplate to be ground week of 9/12. Forecasting 81K in September for the milling work. Total EAC will be about $200K including baseplate,rework, and resurfacing. Will contact PMO to pull funds from Macungie project. DRM 8/1/2022-One week-delay in scheduling. Baseplate needs additional work. Foundation was OK. Repair to take place mid August. May pull dollars from ZG Unit #8 Rerate.DRM 7/5/2022-Work is starting week of 7/11. 6/2/2022 Sole Source was rejected. Working with Supply Chain to locate a quote from another vendor.. DRM 5/2/2022 Working with grouting contractor to get quote.DRM 4/1/2022 DRM Received quotes from Hydroeast and ITT Goulds. Have call 4/4 with Nate Frey and Auburn mechs to discuss best course of action. 3/1/2022 DRM Met with Hydro East to develop scope with asset team. and requested quote to complete the AFE. | 2023-04-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Pipeline | AB - AUBURN STATION |  | 273 | 0 |  |  | 206029 |  | Posipanko, Dan | Tracey, Steve |  |  | 1 | 37394 |  | Guest, ProSight | Independent | Aqua | 2020-07-31 | Other Programs
Auburn Replace Office Building roof | Item | Open | MCAP | AB00000M2301 | Maintenance Framework | 2076601 | Orischak, Bob | East | 3. Active | Defined | East |  | 75000 |  | 75000 | 75000 | 0 | Green | 75000 |  | 75000 | 0 |  |  | 76890 |  |  | 76890 | Full | 76890 |  | 75000 | 75000 | No | Green | 2023-06-01 | 2023-01-23 | 2023-01-23 | 2023-04-25 | 2023-05-31 | [12 empty] | 0 | 75000 | [9 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Pipeline | AB - AUBURN STATION |  |  | 75000 |  |  |  |  | Orischak, Bob | Tracey, Steve |  |  | 1 | 44536 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Other Programs
Auburn Rotork Valve Operator Upgrade | Item | Open | MCAP | AB00000M2202 | Maintenance Framework | 1945823 | Mohr, David | East | 7. Closed | Defined | Valves | 3266 |  |  | 3266.48 | 3266 | 0 | Green |  |  |  | 3266 |  |  | 70000 |  |  | 70000 | Full | 70000 | 80215 |  | 80215 | No | Green | 2022-02-01 | 2022-02-03 | 2022-02-03 | 2022-05-01 | 2022-12-31 |  |  | 3146.9 | 119.58 | [17 empty] | 1/10/2023 - Closed WO/PO and set OPPM project status to 'Closed'. MCS Can close. 12/1/2022 Valve installations will be completed this month. 11/1/2022 Variance due to Stem nuts received and shutdowns scheduled this month for installation. 10/1/2022 Stem nuts were shipped wrong from manufacturer causing delay in installation. New shafts being fabricated. DRM 9/1/2022 Techs unable to complete installation due to PM load. DRM 8/1/2022 Received remaining actuators in mid-July. Techs to installation to be completed over this and next month. DRM 7/5/2022 Received 2 actuators in June. DRM 6/2/2022-Delay in actuator delivery. 5/3/2022-Actuators expected wk of 5/10, install in June. 4/4/2022 - Actuators expected in 2 months. 3/2/2022 DRM Actuators on order 12 week lead time. 2/1/2022 Received quotes from vendor, AFE to follow | 2023-01-10 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Pipeline | AB - AUBURN STATION |  | 3266 | 0 |  |  | 76949 |  | Oey, Alex | Tracey, Steve |  |  | 1 | 34121 |  | Guest, ProSight | Independent | Aqua | 2019-08-19 | Other Programs
Auburn Station (AB) Tank 304 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | AB00000E2301 | Maintenance Framework | 2093484 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 |  |  | 11000 |  |  | 11000 | Phase | 11000 |  | 10000 | 10000 | No | Green | 2023-09-01 | 2023-03-01 | 2023-03-01 | 2023-12-31 | 2023-09-30 | [16 empty] | 10000 | [6 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Auburn Pipeline | AB - AUBURN STATION |  |  | 0 | 10000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44771 |  | Administrator, System | JDE Child | Burnt Orange | 2022-08-17 | Int - Tanks
Auburn Station (AB) Tank 306 - OOS API 653 Insp Seal Insp & Refurb | Item | Open | MCAP | AB00000M2303 | Maintenance Framework | 2086166 | Yoder, Michael | East | 3. Active | Defined | Tanks | 1693 | 378919 |  | 380611.86 | 378919 | 1693 | Yellow | 378919 |  | 378919 | 1693 |  |  | 190498 |  |  | 190498 | Phase | 190498 | 1693 | 378919 | 380612 | No | Green | 2023-04-01 | 2023-02-24 | 2023-02-24 | 2023-12-31 | 2023-08-31 | [5 empty] | 1692.86 |  |  | 1693 | Red |  |  | 28919 | 150000 | 150000 | 50000 | [5 empty] | 5/1/23 - Preparing to set legs and clean tank in May. April variance due to internal labor. 9/23/22-CES-Reviewing budget and can drop mechanical budget from $215,000 to $175,000. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | AB - AUBURN STATION |  |  | 180612 | 200000 |  |  |  | Stine, Carlton |  |  |  | 1 | 44772 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Auburn Station (AB) Tank 310 - OOS Seal Insp | Item | Open | MEXP | AB00000E2302 | Maintenance Framework | 2093477 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 25000 |  | 25000 | 35000 | -10000 | Red | 102000 |  | 102000 | -77000 |  |  | 25300 |  |  | 25300 | Phase | 25300 |  | 25000 | 25000 | No | Green | 2023-05-01 | 2023-03-01 | 2023-03-01 | 2023-12-31 | 2023-05-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 25000 | [8 empty] | 5/1/23 - Seal inspection moved to 5/3. Reduced forecast assuming there will be no/minimal repairs. 4/4/23 - Moved forecast to May. Contractor plans to mobilize 5/3. 2/9/23 - Updated forecast assuming seal inspection will be completed in-service and no repairs required. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Auburn Pipeline | AB - AUBURN STATION |  |  | 25000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44773 |  | Administrator, System | JDE Child | Burnt Orange | 2022-08-17 | Int - Tanks
Auburn Station (AB) Tank 304 Secondary Seal Replacement | Item | Open | MCAP | AB00000M2205 | Maintenance Framework | 2021563 | Yoder, Michael | East | 7. Closed | Emergent | Tanks | 1882 |  |  | 1881.86 | 1882 | 0 | Green |  |  |  | 1882 |  |  | 81000 |  |  | 81000 | Full | 81000 | 83928 |  | 83928 | No | Green | 2022-09-01 | 2022-09-02 | 2022-09-02 | 2022-10-30 | 2022-09-30 |  |  | 320.23 | 1561.63 | [17 empty] | 3/14/2023 - Closed WO/PO, and set OPPM status to 'Closed'. MCS 3/1/23 - Trailing disposal invoice hit in February. Should now be able to close. 2/1/23 - Keep open for one more month then close. 1/4/23 - Variance due to additional disposal costs for Haz material. 12/2/22 - Variance due to awaiting seal disposal. Moved forecast to December. 11/1/22 - Added 5k to November forecast for seal disposal. 10/4/22 - Variance due to completing work prior to end of September. Updated forecast. 9/1/22 - Emergent AFE out for approval. Forecast October spend. | 2023-03-14 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | AB - AUBURN STATION |  | 1882 | 0 |  |  | 82046 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 45702 |  | Meitzler, Antoinette | Independent | Aqua | 2022-08-30 | Int - Tanks
Auburn Station tank line CP replacement | Item | Open | MCAP | AB00000M2302 | Maintenance Framework | 2085676 | Norton, Bill | East | 3. Active | Defined | Cathodic Protection |  | 85000 |  | 85000 | 85000 | 0 | Green | 85000 |  | 85000 | 0 |  |  | 85045 |  |  | 85045 | Full | 85045 |  | 85000 | 85000 | No | Green | 2023-07-01 | 2023-02-21 | 2023-02-21 | 2023-11-01 | 2023-11-30 | [14 empty] | 50000 |  |  | 35000 |  |  |  | 4/20/23 Lake Superior consulting to perform installation. Rick Davis from Spyglass to be inspector. work scheduled for July 2023 | 2023-04-20 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | AB - AUBURN STATION |  |  | 0 | 50000 | 35000 |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44344 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
Auburn Station Transformer Pole Inspection & Cross Member Replace | Item | Open | MEXP | AB00000E2303 | Maintenance Framework | 2112551 | Mohr, David | East | 3. Active | Defined | Electrical |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 |  |  | 99000 |  |  | 99000 | Full | 99000 |  | 100000 | 100000 | No | Green | 2023-06-01 | 2023-04-24 | 2023-04-24 | 2023-06-30 | 2023-06-30 | [13 empty] | 70000 | 30000 | [6 empty] | 5/1/2023 Quotes received and PO's to be cut. 4/1/2023 AFE to be submitted 2/2/2023 Discussion held with Auburn Asset team and Black and McDonald to provide quote. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Auburn Pipeline | AB - AUBURN STATION |  |  | 70000 | 30000 |  |  |  | Ashley, Robert | Tracey, Steve | N/A |  | 1 | 25321 |  | Guest, ProSight | Independent | Aqua | 2017-08-29 | Other Programs
Bahamas CP Upgrade for piping - 2023 | Item | Open | MCAP | 8410811M2315 |  | 2095053 | Occhi, Edward | East | 3. Active | Defined | Cathodic Protection |  | 120000 |  | 120000 | 150000 | -30000 | Red | 150001 |  | 150001 | -30001 |  |  | 151840 |  |  | 151840 | Full | 151840 |  | 120000 | 120000 | No | Green | 2023-06-01 | 2023-03-14 | 2023-03-14 | 2023-12-20 | 2023-12-31 | [13 empty] | 20000 | 0 | 90000 | 10000 | [6 empty] | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 20000 | 100000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45989 |  | Clark, David | Independent | Aqua | 2022-10-05 | Int - Planned Corr & FI
Bahamas Hub - Tk 8080 - OOS Corr Insp & Refurb | Item | Open | MCAP | 8410811M1901 | Exempt | 1549125 | Campbell, Jamie | East | 6. Operational | Defined | Tanks | 2175 |  |  | 2174.58 |  | 2175 | Red |  |  |  | 2175 |  |  | 251000 | 1093000 |  | 1344000 | Full | 1344000 | 1431245 |  | 1431245 | No | Green | 2020-09-01 | 2019-01-07 | 2019-01-07 | 2019-05-20 | 2019-07-05 | [5 empty] | 2174.58 |  |  | 2175 | Red | [11 empty] | 08/02/2019 - Project completed and ready to close. 07/01/2019 - Tank scheduled to return to service on July 5th. 05/03/2019 - 90% completed mechanically. VCI and coating scheduled to take place in May. 04/08/2019 - Progress at 80% mechanically. Coating materials on order. 02/05/2019 delayed due to tank not being isolated, currently waiting on inspection report. Pending TRC 2/1/2019 - Tank 8080 was cleaned and inspected. Scope of work has been developed and awaiting proposals from contractors. Phase II AFE is being developed for submittal. | 2019-08-02 | Cheng, Debra |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 2175 |  |  |  |  | Stine, Carlton | Charles, Jeffrey | N/A |  | 1 | 29271 |  | Guest, ProSight | Independent | Aqua | 2018-06-11
Bahamas Hub (BORCO) Tank 7401 - OOS Corr Insp & Refurb | Item | Open | MCAP | 8410811M2214 | Maintenance Framework | 1955604 | Campbell, Jamie | East | 6. Operational | Defined | Tanks | 573118 | 5928 |  | 579045.84 | 530249 | 48797 | Yellow | 91000 |  | 91000 | 488046 |  |  | 216000 | 546000 |  | 762000 | Full | 762000 | 804870 | 5928 | 810798 | No | Green | 2022-04-01 | 2022-03-10 | 2022-03-10 | 2022-12-31 | 2023-03-05 |  |  | 106381.47 | 252229.66 | 117855.45 | 96651.26 | 45000 | 45000 | 51651 | Red |  | WorkAhead of Schedule | 5928 | [8 empty] | 05/01/2023 - Tank final clean-up in progress. 04/04/2023 - Tank hydrotested and coating completed. Piping coating and abrasive material removal and drainage regrade to be completed in April. 03/02/2023 - Tank mechanical repairs are all completed, resulting in a small variance for February. The tank EFR and bottom coating will be completed in March, along with minor civil, E&I, and clean-up. 2/3/2023 QSL has accelerated the project to bring it back on schedule. The mechanical repairs are approximately 80% completed. The EFR seal is schedule to arrive on 2/16/2023. Accrual has been made for QSL, since they did not submit an invoice. 1/9/2023 Mechanical repairs are delayed two weeks due to site foreman illness. 1/9/2023 -Forecast updated per PM. 1/5/2023 - QSL has procured all materials and has completed fabrication of keys items in their shop during Christmas Holiday. They will be back on-site Jan 9 to start the repairs to the tank. 12/4/2022 - AFE approval completed. Tank awarded to QSL for mechanical repairs. QSL have procured the long lead material and start fabrication of the item at their shop. Plans to mobilize at the tank for January 3, 2023. 11/01/2022 Contractors bids received, Waiting BBH Management decision to proceed or defer tank. 10/12/2022 - DNV/Albacore reclass and dropped accrual cause of variance. DC 10/3/2022 Tank inspection are completed. Inspection called out an extensive list of items that shall be completed before returning the Tank to service. Scope development in progress. 9/5/2022 Tank cleaning and inspection blast completed. Inspector is schedule to arrive September 20, 2022. 8/4/2022 - Tank became available earlier then expected. Tank to be handed over for OOS inspection and repairs on August 12, 2022. I will clean the Tank and get it ready for inspection in September. 5/01/2022- Project schedule to began in 4th quarter 4/30/22 - Project is schedule to begin in October 2022. TankVCI was purchase ahead of projectstart, due tomaterial cost increase in May. Tank and Corrosion Integrity was aware of price increase. | 2023-05-05 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 476467 | 102579 |  |  | 231752 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41230 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Bahamas Hub (BORCO) Tank 8006 – OOS Corr Insp & Refurb | Item | Open | MCAP | 8410811M2129 | Maintenance Framework | 1889082 | Campbell, Jamie | East | 6. Operational | Defined | Tanks | 1142 |  |  | 1141.82 | 1142 | 0 | Green |  |  |  | 1142 |  | Scope Increase | 225000 | 1331000 |  | 1556000 | Phase | 1556000 | 1757325 |  | 1757325 | No | Green | 2021-10-01 | 2021-09-28 | 2021-09-28 | 2021-12-31 | 2022-05-15 |  |  |  |  | 1141.82 | [16 empty] | 6/01/2022 - Tank return to Operations, a waiting final invoices to close project 4/30/22 - The secondary seal installed and tank is currently under hydrotest. Tank Strapping is Schedule May 10, 20222. 4/5/22 - Forecasting error from previous PCA. DC 4/1/22 - All of tank mechanical repairs are completed, The EFR secondary seal is outstanding to be installed, It is scheduled to be installed on April 14, 2022. The tank bottom coating in progress. 3.11.22.DLC: Align forecast with total phase 2 budget with program owner...3/1/22 Tank Bottom repairs completed, Water draw sumps and steam coils installed. Roof repairs are 50% completed, Tank shell nozzles are schedule to be installed in a week. 2/1/22 - Tank scope of work developed and out for bidding. The following items will be completed during this outage: EFR and bottom patches/ sheet replacement - replacement of spiral staircase - VCI installation - Steam coil Installations. 12/20/21 - Tank cleaning completed. API 653 OOS inspection in process. 12/3/21- The tank cleaning is 80% completed. The project is behind due to rain and tank bottom having to be mixed before land farming. Internal inspection company schedule to be on island the first week of 2022. 11/1/21 Tank cleaning is in progress. Tank bottoms have to be mixed and land farm. | 2022-09-15 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 1142 | 0 |  |  | 1504749 |  | Stine, Carlton | Stanisich, Carla D. |  |  | 1 | 41231 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Bahamas Hub (BORCO) Tank F4 – OOS Corr Insp & Refurb | Item | Open | MCAP | 8410811M2213 | Maintenance Framework | 1956019 | Campbell, Jamie | East | 6. Operational | Defined | Tanks | 23209 |  |  | 23208.69 | 23209 | 0 | Green |  |  |  | 23209 |  |  | 107000 | 448000 |  | 555000 | Phase | 555000 | 668636 |  | 668636 | No | Green | 2022-04-01 | 2022-03-14 | 2022-03-14 | 2022-10-31 | 2022-10-31 |  |  | 19735.17 | 3323.94 | 149.58 | 0 |  |  | 0 | Green | [11 empty] | 05/01/2023 - Awaiting final Sanitation invoice posting to close project 2/3/2023 Awaiting final Sanitation invoice posting to close project. $3.1K VAT reclasses and $7.7K CWIP. 12/4/2022 - Tank mechanical repairs completed, Wrapping up tank external piping repairs and final site clean up. 11/07/2022 Tank mechanical repair are 80% completed. Tank bottom coating material shipping delayed due to hurricane Nicole. 10/4/2022 Tank Inspection completed, scope of work developed and RFP are due on 10/7/22. Extensive bottom repairs resulting from the severe topside pitting (Existing bottom was not coated. Repairs are schedule to begin in October. 9/5/2022 Tank cleaning and inspection blast completed. Bottom Inspection is schedule for September 20, 2022. Repair scope is being develop. 8/4/2022 Operation plans to release tank for API OOS inspection & repairs on August 16, 2022. Tank will be cleaned in August and inspected in September. 6/1/2022 Tank schedule to be taken out of service in August. 4/30/22 - Tank is schedule to be out of service in August. VCI material was purchase ahead of project start date due to price increase in May. Tank and Corrosion integrity was made aware of price increase. | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 23209 | 0 |  |  | 645428 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41234 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Bahamas Hub Fire Pump Replacement -2021 | Item | Open | MCAP | 8410811M2105 | Exempt | 1804089 | Herry, Ryan | East | 7. Closed | Unplanned | Fire Protection | 508 |  | 7700 | 508.48 | 24 | 484 | Red |  |  |  | 508 |  |  | 390000 |  |  | 390000 | Full | 390000 | 383023 | 7700 | 390723 | No | Green | 2021-05-01 | 2021-01-25 | 2021-01-25 | 2021-10-30 | 2022-08-02 |  |  | 24.48 |  |  | 484 |  |  | 484 | Red | [10 empty] | 7700 | 02/2/2023 - Project is Ready to Close. 07/12/2022 - Pump has been installed and awaiting commissioning. [RH] 05/10/22 - Pump set on base and piping installed. exhaust being tied in. Pump to be commissioned 5/20/22. 03/08/22 - Final Pump Installation ongoing, previously delayed due to Operational Challenged with other Fire Pumps. [R - Herry] 01/03/22 - Shipping Delays - Awaiting delivery of the pump and Engine at the terminal.. This was expected late November. - [R. Herry] 12/2/21 Operational date moved back to Dec 31 2021 BL 10/20/2021 - Diesel pump was shipping from Wisconsin to Houston today to mate to pump. Pump now expected on site in BBH towards end of November (GJ) 9/30/2021 - Fire Pump expected on site in October; Installation and Commissioning to be executed in Oct 21. [R. Herry] 7/7/21 - Tank 11 Upgrades Inspections Complete BL 6/08/2021 - Pump In Manufacturing stage. [RH] 5/07/2021 - Forecast adjusted - drawings received. 4/07/2021 - Awaiting final pump drawings (expected this month). Discharge flange changed from a 125# to a 250# to meet NFPA rating. 3/15/2021 - OP-214385 Fire Pump Ordered [34 week lead time] 3/15/2021 - Pump expected October 5th 2021 | 2023-02-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 24 | 484 |  |  | 21506 |  | Jakubowski, Gregory | Nash, Tom |  |  | 1 | 38063 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
Bahamas Hub Stripping Pumps 2021 | Item | Open | MCAP | 8410811M2119 | Exempt | 1847874 | Herry, Ryan | East | 7. Closed | Unplanned | Rotating Equipment | -2741 |  |  | -2741.08 | -2741 | 0 | Green |  |  |  | -2741 |  |  | 736000 |  | 124000 | 860000 | Supplemental | 860000 | 887737 |  | 887737 | No | Green | 2021-06-01 | 2021-05-27 | 2021-05-27 | 2021-12-31 | 2022-09-15 |  |  | 0 | -2741.08 | [17 empty] | 03/03/2023 - Accrual dropped per PM. Project is ready to be closed. 2/2/2023 - Pending final freight invoices before closing. 07/12/2022 - No addition spend expected on this project, only awaiting the last 4 " pump delayed due to Mfg and Shipping delays. 05/10/22 - Supplemental AFE approved. 3 Stripping pumps arrived at the terminal 05/05/22 03/08/22 - Shipping Delays continue to be experienced - Vendor confirmed delivery End of March. Pumps only need to be slipped into the base. Ops dates adjusted to reflect new shipping ETA [R -Herry] 01/03/22 - Shipping Delays for 3 Stripping Pumps, however they have been completed and shipped to BBH's Freight Forwarder - [R. Herry] 01/03/22 - Operational Date shifted due to shipping delays. 12/2/21 - Operational date moved to january 15, 2022 BL 9/30/2021 - R Herry Notes Updated - Pumps for MP-8125 and MP 8180 expected in October - Pumps for MP8126 and MP8081 installed and complete - awaiting low flow switch installation - Mobile Pumps 8" Stripping pumps ordered in Sept. - Fuel Oil Stripping Pump transferred from Inventory expected to be applied for September - Transfer pump ordered awaiting delivery. 9/1/2021 - Project moved to active BL 6/7/2021 - AFE approved; Two pumps to be installed in June, with associated cable and instrumentation. [RH] 4/7/2021 - Pump quotes being sourced to finalize quote and AFE. 3/3/2021 - AFE and Project Execution plan being developed | 2023-03-03 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | -2741 | 0 |  |  | 33388 |  | Posipanko, Dan | Posipanko, Daniel A. |  |  | 1 | 38139 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
Bahamas Hub Substation #4 Upgrades | Item | Open | MCAP | 8410811M2123 | Maintenance Framework | 1869708 | Cooper, Greg | East | 6. Operational | Defined | Electrical | 0 |  |  | 0.09 | 0 | 0 | Green |  |  |  | 0 |  |  | 125000 |  | 40000 | 165000 | Supplemental | 165000 | 165358 |  | 165358 | No | Green | 2021-09-01 | 2021-07-26 | 2021-07-26 | 2021-10-30 | 2022-10-31 |  |  | 0.09 | [18 empty] | 102822 - The WEG Transformer has been installed and commissioned. The electrics for MP-8006A has been completed and the pump has been test ran successfully. 100722 - The WEG transformer has been shipped and is expected at BBH by 101222 - 092022 - The WEG 750KVA transformer is expected to complete the final testing this week and should be ready to ship out by the end of September. 070722 - The WEG 750KVA transformer is further delayed due to the delivery of copper. Shipment is now expected at the end of August pending the timely receipt of copper. Presently in the process of providing a PO to install electrical equipment within Substation #4 and cabling out to MP-8006A.. 053122 - Supplemental AFE approved to install electrics from Substation #4 to MP-8006A 05/04/22 The delivery of the WEG transformer to SEACOR is now scheduled for June 30th due to supply chain delays with materials. Installation is scheduled for the month of July. 3/29/22 New 750KVA power transformer due to arrive on island May 20th, Operational date expected on June 10th; 9/1/21 - Project delays due to availability of custom-made transformer. Set operational date to 4/30/22 BL 6/1/21 - AFE to be submitted week of 6/1/21. Thank you, DC 5/3/21 - Awaiting finalization of AFE. Forecast pushed one month. DC 3/17/21 - Greenlit for progress. Forecast inputted April-August due to long lead time for procurement. DC 3/8/21 - Need to talk to Bob Ashley about funding. | 2022-10-28 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 0 | 0 |  |  | 46576 |  | Ashley, Robert | Nash, Tom |  |  | 1 | 38154 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
Bahamas Hub Tank 8025 - OOS Corr Insp & Refurb | Item | Open | MCAP | 8410811M2012 | Exempt | 1755089 | Campbell, Jamie | East | 6. Operational | Unplanned | Tanks | -5625 |  | 17479 | -5625 |  | -5625 | Red |  |  |  | -5625 |  |  | 1350000 |  |  | 1350000 | Full | 1350000 | 1257121 | 17479 | 1274600 | No | Green | 2020-11-01 | 2020-09-21 | 2020-09-21 | 2020-07-15 | 2021-01-04 | [5 empty] | -5625 |  |  | -5625 | Red | [10 empty] | 17479 | 4/12/21 - Invoices in process. Awaiting corrections from vendor. Per Jamie Campbell, dropping remaining Sanitation Services PO. DC 4/6/21 - Final invoices still accruing for Ferguson, QSL, and Sanitation Services. DC 2/9/2021 - Awaiting final invoicing for close of project. DC 10/01/2020 Tank AFE approved in September. Tank is schedule to be taken out of service middle of October for cleaning and mechanical Upgrades. 5/27/2020 Sr. DD holding on the AFE until finalize path forward on the tank. Given the current deferral into Q3 until district works through tanks 8027/8037 05/08/2020 - Tank was deferred per operational requirements. 4/10/20 Pull in from 2022 0401/2020 - Project pulled to Q2 as per Senior Management and Commercial Request. Project forecast reflects same. 03/04/2020 - Project scheduled to begin Q4 2020 per commercial release. 02/05/2020 - Project scheduled to begin Q4 2020. 01/08/2020 - Project scheduled to begin Q4 2020. internal due 9/13/2022 | 2021-04-12 | Lienemann, Berend |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | -5625 |  |  |  |  | Stine, Carlton | Nash, Tom |  |  | 1 | 34166 |  | Administrator, System | Independent |  | 2019-08-20
Bahamas Hub Tank Repairs (2023 External Inspections) | Item | Open | MEXP | 8410811E2307 | Maintenance Framework | 2095097 | Campbell, Jamie | East | 3. Active | Drawdown | Tanks | 29215 | 70785 |  | 100000 | 100000 | 0 | Green |  |  |  | 100000 |  |  | 100000 |  |  | 100000 | Full | 100000 | 29215 | 70785 | 100000 | No | Green | 2023-04-01 | 2023-03-16 | 2023-03-16 | 2023-06-30 | 2023-07-31 | [5 empty] | 29215 | 30000 | 30000 | -785 | Yellow |  |  | 50000 | 20785 | [7 empty] | 05/01/2023 - Tampa completed repairs to Tank 3007. Tampa is making repairs to Tanks 8002,3, 7, & 11 handrail system. 4/3/2023 - Tampa mobilized a crew at the tank to start repairs to tank 3007 shell and wind girger. Project was created to address repairs required as a result of the 2023 External Inspections completed. | 2023-05-05 | Coverley, Colleen |  | East | Pipelines and Terminals | Tank Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 100000 |  |  |  |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 46753 |  | Stine, Carlton | JDE Child | Burnt Orange | 2023-03-10
Bahamas Triennial Survey | Item | Open | MEXP | 8410811E2306 | Maintenance Framework | 2095141 | Occhi, Edward | East | 3. Active | Defined | Atmospheric Corrosion |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 |  |  | 50600 |  |  | 50600 | Full | 50600 |  | 50000 | 50000 | No | Green | 2023-07-01 | 2023-03-16 | 2023-03-16 | 2023-12-20 | 2023-06-30 | [12 empty] | 0 | 0 | 50000 | [8 empty] | Coverley, Colleen |  | East | Pipelines and Terminals | Corrosion |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 0 | 50000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45706 |  | Guest, ProSight | Independent |  | 2022-08-31 | Other Programs
BALTIMORE - BOILER RE-TUBE | Item | Open | MCAP | BETQB00M2206 | Maintenance Framework | 2023330 | Schwindt, Joseph | East | 6. Operational | Defined | Boilers | 444723 |  |  | 444722.5 | 435917 | 8806 | Yellow |  | 410000 | 410000 | 34723 |  |  | 410000 |  | 384000 | 794000 | Supplemental | 794000 | 677693 |  | 677693 | No | Green | 2022-10-01 | 2022-09-22 | 2022-09-22 | 2022-11-30 | 2023-02-28 |  |  | 134016.21 | 326875.26 | -24974.97 | 8806 |  |  | 8806 | Red | [11 empty] | 5/3/23-DelVal has submitted invoice for $8800 - last invoice expect for this project. 5/1/2023 - Accruing 8800 for Delval. 4/2/2023-Operational and significant savings from AFE. Can close. . 2/17/2023 JTS - Project completed 2/11/23. Invoices being submitted and should all be received by end of February. 1/31/2023 RLO - Can accrue the 100k. Work will be completed by the end of Feb.. 1/25/23: Project is working. Supplemental AFE submitted 1/25/23. Total Full Cost to be ~$790K due to expanded scope. Project on track and expected to end Mid March 1/3/2023-Scope has expanded, working on supplemental, due to need to replace tube sheets. Expecting project costs to be roughly $625K. Expecting that the project will end mid-March 2023. Accruing 96K for Delval (tubes) and $22K for Delval (JetBlast) 12/1/2022-Work had to be stopped due to additional findings expanding scope, but is now back on-track, Project will probably not finish until mid-January. 11/21/2022 - Joe Schwindt recognizes that this needs a supplemental & will put one in after Thanksgiving. As noted below, Dave Clark is aware of this extra spend. 11-10-22- Dave Clark - added $200k in for new tubesheets. 11/2/2022-Accruing for Delval. Project is being worked on, estimating will be close to budget by end. 9/12/2022 - RLO AFE Submitted. Additional Funding of 120k coming from the Baltimore - Outfall NEED to add 120k to Nov forecast 9/1/2022 - Project scoped by Joe and are awaiting contractor bid for AFE. A bid event through COUPA will need to occur. RLO 8/1/2022-Project was scoped out by Joe Schwint, contract PM,last week. 5/4/2022 - Planning on meeting with Andrew Blow in May to scope out. ek5507 | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Baltimore | BETQB - BET BALTIMORE TERMINAL |  | 435917 | 8806 |  |  | 232970 |  | Stine, Carlton | Blow, Andrew |  |  | 1 | 36820 |  | Guest, ProSight | Independent | Aqua | 2020-06-03 | Other Programs
Baltimore - Breasting Dolphin Replacement - 2022 | Item | Open | MCAP | BETQB00M2303 | Project Framework | 2094189 | Wojton, Brian | East | 3. Active | Defined | Marine | 15921 | 260000 |  | 275921.12 | 262308 | 13614 | Yellow | 600000 |  | 600000 | -324079 |  |  | 250790 |  |  | 250790 | Phase | 250790 | 15921 | 260000 | 275921 | No | Green | 2023-03-01 | 2023-03-07 | 2023-03-07 | 2024-12-30 | 2023-05-31 |  |  |  |  | 12307.61 | 3613.51 | 10000 | 10000 | -6386 | Red |  |  | 20000 | 25000 | 25000 | 0 |  | 75000 | 90000 | 25000 |  | 05/05/2023 - Markella, Brian, Andrew met with Bowman and finalized the BOD for new dolphin. Also reviewed other repairs needed. Permits shall be submitted for both projects in 2 weeks. 04/05/23 - Preliminary BOD under review. Permitting package due in April for permit submittal. 01/05/2023 - PM (Brian Wojton) recently assigned. | 2023-05-08 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Baltimore | BETQB - BET BALTIMORE TERMINAL |  | 12308 | 48614 | 25000 | 190000 |  |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 44502 |  | Clark, David | Independent | Aqua | 2022-08-10 | Marine
Baltimore - OWS Upgrades - 2022 FEED | Item | Open | MCAP | BETQB00M2208 | Maintenance Framework | 2045665 | Schwindt, Joseph | East | 7. Closed | Defined | Storm Water Management | 828 |  |  | 828.4 | 828 | 0 | Green |  |  |  | 828 |  |  | 25000 |  |  | 25000 | Full | 25000 | 22628 |  | 22628 | No | Green | 2022-12-01 | 2022-11-18 | 2022-11-18 | 2022-12-31 | 2022-12-31 |  |  | 828.4 | [18 empty] | 1/30/2023 - Closed WO/PO and I set OPPM project status to 'Closed'. MCS. 1/3/2022 - Can close. 12/1/2022-PO was created yesterday, work to be done and invoiced in Dec. 11/2/2022-AFE will be submitted this week. 10/3/2022-AFE was just approved, found an engineering company to do it. 9/1/2022 RLO - Project to be completed and billed in Sept. 8/1/2022 RLO - This project will be given to Joe Schwindt handed off from Ed Keeth 7/12/22 - MPB spoke to Clint. Scoping with contractor PM is scheduled for 7/27/22. | 2023-01-30 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Baltimore | BETQB - BET BALTIMORE TERMINAL |  | 828 | 0 |  |  | 21800 |  | Bonenberger, Mark | Blow, Andrew |  |  | 1 | 40741 |  | Guest, ProSight | Independent | Aqua | 2021-07-26 | Other Programs
Baltimore - Remove waterfront dead legs | Item | Candidate | MCAP |  | Maintenance Framework |  | Schwindt, Joseph | East | 1. Proposed |  | Facility Integrity |  | 110000 |  | 110000 | 110000 | 0 | Green | 110000 |  | 110000 | 0 | [9 empty] | 110000 | 110000 | No | Green | 2023-05-01 |  |  |  | 2023-05-31 | 8 | Yellow | [10 empty] | 55000 | 55000 | [7 empty] | 5/3/23 - Bid Event held. Awaiting vendor bids. 4/3/2023 - In process of setting up bid event. | 2023-05-03 |  |  | East | Pipelines and Terminals | Integrity |  | Baltimore | BETQB - BET BALTIMORE TERMINAL |  |  | 110000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 44333 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
Baltimore OWS Refurbishment 2023-' | Item | Open | MCAP | BETQB00M2304 | Maintenance Framework | 2119873 | Schwindt, Joseph | East | 3. Active | Defined | Storm Water Management |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 | 17000 | 117000 | -17000 |  |  | 117000 |  |  | 117000 | Full | 117000 |  | 100000 | 100000 | No | Green | 2023-08-01 | 2023-05-02 | 2023-05-02 | 2023-07-31 | 2023-08-31 | [15 empty] | 100000 | [5 empty] | 5/8/23 - looking for replacement coalescer pads - Highland Tank not compatible. 4/27/23 - waiting on MDE for approval to route Small Tank water from OWS to Outfall 003. 4/3/2023 - In process of getting quotes. | 2023-05-09 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Baltimore | BETQB - BET BALTIMORE TERMINAL |  |  | 0 | 100000 |  |  |  | Bonenberger, Mark | Blow, Andrew |  |  | 1 | 45831 |  | Orischak, Bob | Independent | Aqua | 2022-09-13 | Other Programs
Baltimore Permeability Study | Item | Open | MEXP | BETQB00E2301 | Maintenance Framework | 2086161 | Schwindt, Joseph | East | 3. Active |  | Secondary Containment |  | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 |  |  | 35750 |  |  | 35750 | Full | 35750 |  | 30000 | 30000 | No | Green | 2023-05-01 | 2023-02-27 | 2023-02-27 | 2023-06-13 | 2023-05-31 | [12 empty] | 30000 | 0 | [7 empty] | 5/3/23-waiting approval of sampling points from MDE (JTS) 5/1/2023-Must be done in May. 4/3/2023-PO issued and vendor will be on site in April. 2/23/23 - JTS AFE submitted for approval on 2/21/23. Moved $30k forecast from March to May. Work needs to be completed by 6/13/23 to meet regulatory requirements. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Baltimore | BETQB - BET BALTIMORE TERMINAL |  |  | 30000 |  |  |  |  | Spari, Markella | Mengel, Jason L. |  |  | 1 | 45881 |  | Clark, David | Independent | Aqua | 2022-09-20 | Other Programs
Baltimore Terminal (BETQB) Tank 1941 - OOS API 653 Insp | Item | Open | MEXP | BETQB00E2302 | Maintenance Framework | 2093471 | Yoder, Michael | East | 3. Active | Defined | Tanks | 27134 | 580000 |  | 607134.08 | 600000 | 7134 | Yellow | 400000 |  | 400000 | 207134 |  |  | 607200 |  |  | 607200 | Phase | 607200 | 27134 | 580000 | 607134 | No | Green | 2023-04-01 | 2023-03-01 | 2023-03-01 | 2023-12-31 | 2023-09-30 | [5 empty] | 27134.08 |  |  | 27134 | Red |  | WorkAhead of Schedule | 50000 | 150000 | 200000 | 180000 | [5 empty] | 5/1/23 - April variance due to isolating tank ahead of schedule. Plan to bid tank cleaning and start in May. 3/30/23 - Phase 1 AFE approved. Updated forecast. Plan to open up tank early May begin cleaning around 5/22. 10/5/22-CES-Per commercial, Plan to clean and idle tank for 2023. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity | Tank Integrity | Baltimore | BETQB - BET BALTIMORE TERMINAL |  |  | 227134 | 380000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44779 |  | Administrator, System | JDE Child | Burnt Orange | 2022-08-18 | Int - Tanks
Baltimore Terminal Air-to-Ground Transition Recoats 2023 | Item | Open | MCAP | BETQB00M2302 | Maintenance Framework | 2085589 | Gable, Rob | East | 3. Active | Defined | Atmospheric Corrosion |  | 35000 |  | 35000 | 35000 | 0 | Green | 35000 |  | 35000 | 0 |  |  | 35080 |  |  | 35080 | Full | 35080 |  | 35000 | 35000 | No | Green | 2023-08-01 | 2023-02-21 | 2023-02-21 | 2023-10-30 | 2023-09-30 | [15 empty] | 20000 | 15000 |  |  |  |  | 5/2/2023 RAG - Work to begin during Q3. 4/4/2023 RAG - Work to begin during Q3. 3/2/2023 RAG - Work to begin during Q3. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Baltimore | BETQB - BET BALTIMORE TERMINAL |  |  | 0 | 35000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45384 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Baltimore Terminal Gate Replacement 2022 | Item | Open | MCAP | BETQB00M2209 | Maintenance Framework | 2051073 | Orischak, Bob | East | 6. Operational | Drawdown | East | 67908 |  |  | 67907.88 | 72455 | -4547 | Yellow |  |  |  | 67908 |  |  | 68000 |  |  | 68000 | Full | 68000 | 68007 |  | 68007 | No | Green | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2023-01-25 | 2023-01-13 |  |  | 69117.09 | 3792.14 | -454.35 | -4547 |  |  | -4547 | Red | [11 empty] | 5/1/2023 RLO. Ready to Close. 4/3/23 RLO - Still waiting on contractor to submit invoice. Must Accrue again. 3/1/2023 RLO - Waiting for contractor to submit invoice... Reaccrued total cost. 01/31/2023 RLO - Gate System installed. Can accru the full cost 01/03/2023 RLO -Due to weather the contractor has not started work. Will start the week of 01/03/23 12/1/22 RLO Project was just approved, expecting 45K will hit this year. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Baltimore | BETQB - BET BALTIMORE TERMINAL |  | 72455 | -4547 |  |  | 99 |  | Orischak, Bob | Blow, Andrew |  |  | 1 | 46270 |  | Orischak, Bob | Independent | Aqua | 2022-11-29 | Other Programs
Baltimore Terminal Stripper Pump Wiring and Panel Replacement 2023 | Item | Open | MCAP | BETQB00M2301 | Maintenance Framework | 2076606 | Orischak, Bob | East | 3. Active | Drawdown | Electrical |  | 104000 |  | 104000 | 104000 | 0 | Green |  |  |  | 104000 |  |  | 104850 |  |  | 104850 | Full | 104850 |  | 104000 | 104000 | No | Green | 2023-06-01 | 2023-01-23 | 2023-01-23 | 2023-02-10 | 2023-01-19 | [6 empty] | 4000 | 4000 | -4000 | Red |  |  |  | 104000 | [7 empty] | 5/1/2023 RLO Contractor finally chosen and will be starting in June. 04/3/23 RLO Issues finding alternate contractors to bid work. Bid was awarded on 3/29 and work to occur through April and May. 2/22/23 RLO Project still waiting for contractor to show up. They are doing other buckeye work. Maybe starting first week of March. 01/31/2023 RLO Project just approved mid Jan Spends to occur in February | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Baltimore | BETQB - BET BALTIMORE TERMINAL |  |  | 104000 |  |  |  |  | Ashley, Robert | Blow, Andrew |  |  | 1 | 46458 |  | Orischak, Bob | Independent | Aqua | 2023-01-12 | Other Programs
Baltimore Truck Rack Fall Protection | Item | Candidate | MCAP |  | Maintenance Framework |  | Schwindt, Joseph | East | 8. Canceled |  | Truck Racks |  |  |  | 0 |  | 0 | Green | 235000 |  | 235000 | -235000 | [11 empty] | No | Green |  |  |  |  | 2023-10-31 | [21 empty] | 12/1/2022 - Nothing has yet happened on this project - will cancel the project because there is another project for this scope. | 2022-12-01 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Baltimore | BETQB - BET BALTIMORE TERMINAL |  |  | 0 |  |  |  |  | Younce, Michael |  |  |  | 1 | 45373 |  | Clark, David | Independent | Aqua | 2022-08-26 | Other Programs
Bayonne Stormwater Engineering Analysis 2022 | Item | Open | MEXP | BBTQY00E2211 | Maintenance Framework | 2043743 | DeSocio, David | East | 3. Active | Drawdown | Secondary Containment | -16300 |  |  | -16300 | 0 | -16300 | Red |  |  |  | -16300 |  |  | 26750 |  |  | 26750 | Full | 26750 | 10700 |  | 10700 | No | Green | 2022-12-01 | 2022-11-03 | 2022-11-03 | 2023-01-13 | 2023-03-31 |  |  | 0 | 0 | 0 | -16300 |  |  | -16300 | Red |  | Contractor/Vendor Issue | [9 empty] | 3/2/23 - Engineering Firm accounting changes caused billing delays. Invoices will be submitted this week. | 2023-03-02 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor North Terminals | BBTQY - BBT BAYONNE TERMINAL |  | 0 | -16300 |  |  | 27000 |  | Spari, Markella | Mengel, Jason L. | N/A |  | 1 | 46163 |  | Orischak, Bob | JDE Child | Burnt Orange | 2022-11-03
Bayonne Stormwater Flume Evaluation | Item | Open | MEXP | BBTQY00E2103 | Maintenance Framework | 1855486 | Keppel, Nicholas | East | 6. Operational | Defined | East | -9000 |  |  | -9000 | 0 | -9000 | Red |  |  |  | -9000 |  |  | 40000 |  |  | 40000 | Full | 40000 | 25177 |  | 25177 | No | Green | 2021-06-01 | 2021-06-03 | 2021-06-03 | 2021-08-31 | 2021-12-31 |  |  | 0 | -9000 | 9000 | -9000 |  |  | -9000 | Red | [11 empty] | 1/5/2022 - Additional sampling completed in December 2021; PROJECT COMPLETE | 2022-01-05 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor North Terminals | BBTQY - BBT BAYONNE TERMINAL |  | 0 | -9000 |  |  | 987 |  | Orischak, Bob | Orischak, Bob |  |  | 1 | 37888 |  | DeSocio, David | Independent | Aqua | 2020-08-13 | Other Programs
Bayonne Tank 2608 Support Project | Item | Open | MEXP | BBTQY00E2301 | Maintenance Framework | 2095611 | Marrocco, Alex | East | 6. Operational | Drawdown | Tank Outage | 87100 | 9000 |  | 96100 | 88000 | 8100 | Yellow |  | 88000 | 88000 | 8100 |  |  | 88000 |  |  | 88000 | Full | 88000 | 87100 | 9000 | 96100 | No | Green | 2023-04-01 | 2023-03-20 | 2023-03-20 | 2023-05-01 | 2023-05-01 | [5 empty] | 87100 | 60000 | 60000 | 27100 | Red |  |  | 9000 | [10 empty] | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | Harbor North Terminals | BBTQY - BBT BAYONNE TERMINAL |  |  | 96100 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46755 |  | Meitzler, Antoinette | Independent | Aqua | 2023-03-10
Bayonne Terminal (BBTQY) Tank 2608 - OOS API 653 Insp | Item | Open | MCAP | BBTQY00M2303 | Maintenance Framework | 2095904 | Marrocco, Alex | East | 3. Active | Defined | Tanks |  | 995000 |  | 995000 | 995000 | 0 | Green | 996783 |  | 996783 | -1783 |  |  | 362495 |  |  |  | Phase | 362495 |  | 995000 | 995000 | No | Green | 2023-05-01 |  |  | 2023-08-15 | 2023-09-30 | [12 empty] | 75000 | 150000 | 200000 | 285000 | 285000 | [6 empty] | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Harbor North Terminals | BBTQY - BBT BAYONNE TERMINAL |  |  | 225000 | 770000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44780 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Bayonne Terminal (BBTQY) Tank 2696 – OOS Corr Insp & Refurb | Item | Open | MEXP | BBTQY00E2202 | Maintenance Framework | 1937899 | Marrocco, Alex | East | 7. Closed | Defined | Tanks | 880 |  |  | 879.66 | 880 | 0 | Green |  |  |  | 880 |  |  | 44000 |  |  | 44000 | Phase | 44000 | 45591 |  | 45591 | No | Green | 2022-06-01 | 2022-01-05 | 2022-01-05 | 2022-12-31 | 2022-08-31 |  |  | 879.66 | [18 empty] | 9/2/22 - Operational. 8/3/22 - Tank inspection in progress. | 2022-09-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Harbor North Terminals | BBTQY - BBT BAYONNE TERMINAL |  | 880 | 0 |  |  | 44711 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41237 |  | Administrator, System | JDE Child | Burnt Orange | 2021-08-09 | Int - Tanks
Bayonne Terminal Stormwater System Upgrade | Item | Open | MCAP | BBTQY00M2301 | Maintenance Framework | 2076553 | DeSocio, David | East | 3. Active | Defined | Storm Water Management | 10450 | 605000 |  | 615450 | 575000 | 40450 | Yellow | 575000 |  | 575000 | 40450 |  |  | 575510 |  |  | 575510 | Full | 575510 | 10450 | 605000 | 615450 | No | Green | 2023-03-01 | 2023-01-24 | 2023-01-24 | 2023-09-01 | 2023-06-30 |  |  |  |  | 10000 | 450 | 0 | 0 | 450 | Red |  |  | 10000 | 15000 | 175000 | 135000 | 95000 | 175000 | [5 empty] | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor North Terminals | BBTQY - BBT BAYONNE TERMINAL |  | 10000 | 25450 | 405000 | 175000 |  |  | Bonenberger, Mark | Orischak, Bob |  |  | 1 | 45742 |  | Clark, David | Independent | Aqua | 2022-09-02 | Other Programs
Bayonne Transformer Replacement 2023 | Item | Open | MCAP | BBTQY00M2302 | Maintenance Framework | 2083825 | Orischak, Bob | East | 7. Closed | Drawdown | Electrical | 12591 |  |  | 12591.08 | 12591 | 0 | Green |  | 13020 | 13020 | -429 |  |  | 13980 |  |  | 13980 | Full | 13980 | 12591 |  | 12591 | No | Green | 2023-02-01 | 2023-02-03 | 2023-02-03 | 2023-02-06 | 2023-02-06 |  |  |  | 12048.88 | 542.2 | [16 empty] | 3/6/2023 - Closed WO/PO, and set OPPM project status to 'Closed'. 02/22/23 RLO invoice paid in 2/17. All work is completed and project can be closed. | 2023-03-06 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor North Terminals | BBTQY - BBT BAYONNE TERMINAL |  | 12591 | 0 |  |  |  |  | Ashley, Robert | Janesy, Ryan |  |  | 1 | 46563 |  | Orischak, Bob | Independent |  | 2023-02-01 | Other Programs
BB999A3 METALLURGICAL ANALYSIS | Item | Open | MEXP | BB999A3E2202 | Maintenance Framework | 2051855 | Bartal, Nick | East | 3. Active | Drawdown | Pipeline Digs | 12500 |  |  | 12500 | 12500 | 0 | Green |  |  |  | 12500 |  |  | 17500 |  |  | 17500 | Full | 17500 | 17500 |  | 17500 | No | Green | 2022-12-01 | 2022-12-09 | 2022-12-09 | 2023-02-28 | 2023-02-28 |  |  | 0 | 12500 | 0 | [16 empty] | 3.2.23 - Accrual $17,500 (AS) 2/7/23 - lab work still in process - forecast moved to Feb. 1/9/23 - Work began and accrued in Dec | 2023-03-02 | Schultz, Amy |  | East | Pipelines and Terminals | Pipeline Integrity |  | Jet Lines | BB999A3 - BOOSTER #3 TO GULF |  | 12500 | 0 |  |  | 5000 |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 46346 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-12-09 | Int- Planned Digs
BBH - 2022 Vehicle Replacement | Item | Open | MCAP | 8410811M2133 | Maintenance Framework | 1902502 | Herry, Ryan | East | 6. Operational | Unplanned | East | 1010 |  |  | 1009.65 | 987 | 23 | Yellow |  |  |  | 1010 |  |  | 250000 |  |  | 250000 | Full | 250000 | 269494 |  | 269494 | No | Green | 2021-12-01 | 2021-10-19 | 2021-10-19 | 2021-12-31 | 2022-03-15 |  |  | 29.27 | 935.38 | 22.5 | 22.5 |  |  | 23 | Red | [11 empty] | 03/08/22 - Vehicles on site at BBH. Slight change order requested due to incorrect amounts being used at PO. - [ Herry] 01/01/22 - 5 F-150s arrived at BBH's Freight Forwarder, awaiting proper documentation to be exported. Supply chain to follow up! - [R. Herry] 01/01/22 - An Additional 2 Utility Vehicles ordered and arrived at Freight Forwarder. [R. Herry] 11/25/21 - 4/5 Vehicles ordered through Element. 10/7/21 - Ryan working with Procurement. AFE in soon. | 2022-03-09 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 987 | 23 |  |  | 33391 |  | Orischak, Bob | Nash, Tom |  |  | 1 | 41048 |  | Guest, ProSight | Independent | Aqua | 2021-08-05 | Other Programs
BBH - #2 pump house Canopy | Item | Open | MCAP | 8410811M2312 | Maintenance Framework | 2083819 | Hernandez, Andres | East | 3. Active | Defined | Rotating Equipment | 40592 | 20500 |  | 61092.04 | 60047 | 1045 | Yellow | 60000 |  | 60000 | 1092 |  |  | 60580 |  |  | 60580 | Full | 60580 | 40592 | 20500 | 61092 | No | Green | 2023-03-01 | 2023-02-08 | 2023-02-08 | 2023-04-30 | 2023-05-31 |  |  |  |  | 20047.47 | 20544.57 | 30000 | 30000 | -9455 | Red |  | Forecasting | 10000 | 5250 | 5250 | [6 empty] | 5/1/23 Canopy will be installed on the week May/8. Civil originally forecasted for April completion to be completed in May 2023. 3/1/23- AFE was approved, Canopy was assigned to Mechanical engineering. they will have the design ready this month, April we will be ready for installation. AH 2/1/2023 - AFE submitted for approval. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 20047 | 35795 | 5250 |  |  |  | Posipanko, Dan | Nash, Tom |  |  | 1 | 41056 |  | Guest, ProSight | Independent | Aqua | 2021-08-05 | Other Programs
BBH - #2 Pump House Electrical Switch Rack Upgrades | Item | Open | MCAP | 8410811M2319 | Maintenance Framework | 2110018 | Wildgoose Thompsona, Tanya | East | 3. Active | Defined | Electrical | 14532 | 50657 |  | 65189.18 | 50000 | 15189 | Red | 50000 |  | 50000 | 15189 |  |  | 65155 |  |  | 65155 | Full | 65155 | 14532 | 50657 | 65189 | No | Green | 2023-04-01 | 2023-04-06 | 2023-04-06 | 2023-12-31 | 2023-08-31 | [5 empty] | 14532.18 | 10000 | 10000 | 4532 | Red |  |  | 15000 | 15000 | 15000 | 5657 | [5 empty] | 4/25/2023-Electrical equipment ordered. Equipment lead time 2-4 weeks. 50% prepayment made. 4/01/2023 - AFE submitted for approval. Electrical Equipment to be ordered upon approval. 03/01/2023 - Site visit slated for week of March 3rd. AFE will be submitted following site visit. Project will potentially be pulled forward. | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 44532 | 20657 |  |  |  | Ashley, Robert | Nash, Tom |  |  | 1 | 45610 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
BBH - API-570 Inspection Zone 1 | Item | Open | MEXP | 8410811E2309 | Maintenance Framework | 2096410 | Wildgoose Thompsona, Tanya | East | 3. Active | Defined | Facility Integrity | 62646 | 100000 |  | 162646 | 150000 | 12646 | Yellow | 150000 |  | 150000 | 12646 |  |  | 150150 |  |  | 150150 | Full | 150150 | 62646 | 100000 | 162646 | No | Green | 2023-04-01 | 2023-03-28 | 2023-03-28 | 2023-12-31 | 2023-12-31 | [5 empty] | 62646 | 50000 | 50000 | 12646 | Red |  | WorkAhead of Schedule | 30000 | 50000 | 20000 | [6 empty] | 05/01/2023 - 04/04/2023 - Contractor on site conducting LRUT inspection on the P4 Crude line 02-2023 - Conducted site walk with approved inspection company. Currently awaiting quotes for proposed scope of works. | 2023-05-09 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 142646 | 20000 |  |  |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 44985 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
BBH - Berth 11 - Seawall Repairs | Item | Open | MEXP | 8410811E2211 | Project Framework | 1955335 | Hernandez, Andres | East | 3. Active | Defined | Marine | 211400 | 16546 |  | 227945.78 | 227409 | 537 | Yellow |  |  |  | 227946 |  |  | 300000 | 162000 | 381000 | 843000 | Supplemental | 843000 | 826990 | 16546 | 843536 | No | Green | 2022-04-01 | 2022-03-04 | 2022-03-04 | 2022-08-01 | 2023-05-31 |  |  | 3955.68 | 171.8 | 103367.5 | 103904.8 | 103368 | 103368 | 537 | Yellow |  |  | 16546 | [8 empty] | 5/1/23, we are pouring concrete, we had some delays on materials due to concrete plant issues, we still thinking that the project will be ready by the end of the month. AH 4-11-23 Project will continue starting this month, we expect to finish the repairs in May, AH 2/22/23 Extra funds were approved on Feb-16, after the last Monthly meeting, the project will stand now : Initial project : 462k, extra funds 160k (Mexp program), 221k from the New Haven 85 East Dredging project, Total: 843K, suplemental AFE was submited on Feb 20th. AH 2/8/23 2/8/23 Lloyd estimation was not correct, voids are much bigger, than the estimation reflex.. we are calculating voids dimensions again.. 02/01/2023-Final approval of the additional funding request for supplemental is being requested. Project Operational date. 01/17/2023 - The initial supplemental for $160K is being reworked to account for additional final costs. Once final costs are calculated, a revised supplemental will be submitted accounting for the true final numbers. The January forecast of -150K was entered in error. 12-06-22 KB: Supplemental and ECO submitted for $160k to cover additional spend for concrete. 9-30-22 Project on going... working on wall repairs, estimated time to finish it November 30th.. AH 8-10-22 Seawall repairs stared on the deck, we found out that the existing deck does not have internal steel, we had to reinforce the section that we have to repair, AH 7-7-22 Phase 2 AFE was submitted and approved, to repair the sea wall.. Project may have delays due to, concrete mix company in bahamas stop concrete mix production. we are looking into other supplier. 6-7-22 more money needed to repair seawall, phase 2 request was submitted for 162k. AH 5-4-22 project planned to start next month AH 3-8-22 Phase AFE was submitted on march 1, waiting for approval. AH | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 107495 | 120451 |  |  | 615591 |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 41962 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Marine
BBH - Berth 11 and 12 Seawall restoration | Item | Open | MCAP | 8410811M2321 | Project Framework | 2112819 | Hernandez, Andres | East | 3. Active | Defined | Marine |  | 150000 |  | 150000 | 150000 | 0 | Green | 150000 |  | 150000 | 0 |  |  | 150930 |  |  | 150930 | Phase | 150930 |  | 6150000 | 6150000 | No | Green | 2023-09-01 | 2023-04-27 | 2023-04-27 | 2023-10-30 | 2023-10-31 | [16 empty] | 50000 | 100000 |  |  |  | 5/1/23, we are coordinating with Arc surveyors, to perform hydrographic survey, geotech study and side wall scan, after information is collected, we will design the wall. project will be limited to berth 11 side. AH Qotes estimated to received May with possible pull forward in 2023 forecast. 4-11-23, we are working with hudson engineering to prepare engineering and design project, AFE will be submitted any time soon AH | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 0 | 50000 | 100000 |  | 3000000 | Spari, Markella | Spari, Markella | N/A |  | 1 | 31574 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Marine
BBH - Berth 6 L/A Major Refurbishment | Item | Open | MCAP | 8410811M2120 | Project Framework | 1855487 | Hernandez, Andres | East | 6. Operational | Defined | Marine | 131 |  |  | 131.37 | 131 | 0 | Green |  |  |  | 131 |  | CY Budget Estimate Incorrect | 908000 | 1600000 |  | 2508000 | Full | 2508000 | 2574180 |  | 2574180 | No | Green | 2021-06-01 | 2021-06-18 | 2021-06-18 | 2021-12-15 | 2022-08-31 |  |  | 131.37 | 0 | 0 | 0 |  |  | 0 | Green | [11 empty] | 05/02/2023 - Meetings underway with Property Accounting. Assets have been split in preperation for tthe retirement and moved to MS Inventory. Stock Identification numbers from warehouse are needed and have been requested to complete transfer. 03/09/2023 - Parts have been returned to warehouse. Awaiting placement confirmation to complete working with Property on inventory reclass. Working with Kanon regarding invoice. 02/01/2023 - Project is operational. Awaiting Kanon invoice to clear accrual. Physical receipt of Kanon parts being confirmed and potential reclass of $52K to happen, offsetting an invoice of $30K that will be posted to this project. 12/7/2022 - RLO Work continues and finding funding for addtional work. ECO is submitted and approved and supplemental is approved. 11/10/22 - Variance is project savings recouped from fuel charge and labor reductions. DC11/4/22 Phase 2 AFE was approved, we are paying the pending invoices, project total cost was 2.508M. AH8/10/22 Arms were installed, we had extra charge on the installation and weather delays, 250k between both, working on phase 2 AFE.7-11-22 EAC = $2.3M. Phase I = $908k Phase II = $950k MCAP portfolio $300k Marine Program $166k AFE submitted7-7-22 Money was approved to continue the arms installation.. installation is expected on July 18.. AH6-9-22 Project needs more funds to install the arm.. the shipping was about 200k more expensive than expected.... installation is programed on July.. AH5/4/22 MLA Arrived to freeport on April 1st, we are waiting Kanon inspector confirmation dates to come to the bahamas to inspect arms installation . possible date July. AH 04/01/2022 DNM- Transport vessel switched to MV Lone. Arms in transit for the month of April. Scheduled arrival is April 25-26 into GBPA. Project forecast adjusted to process freight invoice in April along with MLA management upon arrival. Project PM will be switched to Andres Hernandez in April for field installation execution.03/02/2022 DNM-MLAs to ship from Rotterdam the week of March 7th based on vessel charter schedule. Offload services at Freeport Harbour are being managed by Freeport ShipServices. GBPA has set up the direct discharge site as Barbour 2. BIT will coordinate with Freeport ShipServices for land transport to their facility for temporary storage in April until installation which is planned in June. Project bidding of installation to commence later March/early April.02/02/2022 DNM- FAT completing on MLAs. Shipment has been scheduled. Coordinating bonding requirements through Freeport Ship Services, LTD. Anticipated delivery of MLAs to island is mid to late March depending on Shipping. MLAs will go into storage upon delivery to island and customs clearance.Working with BBH PM on installation bid process. Anticipate MLA installation in July 2022.01/03/21 DNM- New MLAs being crated for shipping. Developing plan of MLA receipt and storage at BBH.12/2/21 DNM-Planning MLA testing schedule and transportation plan for 2022.11/2/2021 DNM-Loading arm installation part of 2022 Marine MCAP to be managed by others.10/3/2021 DNM- Planning for MLA installation bid in 2022 underway. Anticipate issuance of bidpackage in December.8/2/2021 DNM- MLA Inspection/Repairs completed. Reviewing ongoing monthly service plan with BBH Operations/Maintenance on August 4th. New 6-1 and 6-2 MLA fabrication progressing.7/1/2021 DNM- Field Assessment began on 6/12. MLA Fabrication for replacement of 6-1 and 6-2 underway with material procurement and design review of the operating envelope.05/12/21 DNM- Review of repair costs for loading arms with known cost and risk review potential additional costs exceed the cost of new purchase/replace costs. Discussions with Operations has determined the best course of action is develop a phased AFE for inspections/repairs of remaining BBH Kanon loading arms and undertake contracting for two replacement loading arms over the 2021 and 2022 Marine MCAP Program.04/10/2021 DNM- Conference call shifted to 4/12 to allow Kanon Engineering to participate and present C/B options to scaffold versus remove/repair.04/05/2021- DNM Swivel joints on MLA 6-1 and 6-2 have excess grease loss. Original plan was to mobilize derrick barge from Freeport Harbor to remove MLAs for reconditioning on shore. Kanon engineering is assessing scaffolding and repair place. Conference call being held the week of April 5th to determine course of action prior to AFE processing. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 131 | 0 |  |  | 1484561 |  | Spari, Markella | Nash, Tom |  |  | 1 | 34976 |  | Guest, ProSight | Independent | Aqua | 2019-08-30 | Marine
BBH - Boiler Perform Engineering study | Item | Open | MCAP | 8410811M2322 | Maintenance Framework | 2119760 | Hernandez, Andres | East | 3. Active | Defined | Boilers |  | 25000 |  | 25000 | 25000 | 0 | Green | 25000 |  | 25000 | 0 |  |  | 25145 |  |  | 25145 | Full | 25145 |  | 25000 | 25000 | No | Green | 2023-07-01 | 2023-05-01 | 2023-05-01 | 2023-08-30 | 2023-07-31 | [14 empty] | 16000 | 9000 | [5 empty] | 5/1/23, we will issue steam and condensate lines drawings, to locate key spots to recover condensate and improve our steam operation. AH 4-11-23, Developing a plan with boiler program and management team to study our steam and condensate operations, project may start in June. AH 3/1/23 Cleaver Brooks change the visit to March. we will discuss engineering studies on march 10th.Forecast adjusted to April to reflect change in visit. AH 2/2/2023 cleaver Brooks will come at the end of february to walk the project.. AFE will be submit in march.. | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 0 | 25000 |  |  |  | Stine, Carlton | Orischak, Bob |  |  | 1 | 45604 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
BBH - Cat Island Repairs Phase 3 | Item | Open | MEXP | 8410811E2204 | Maintenance Framework | 1937376 | Wildgoose Thompsona, Tanya | East | 7. Closed | Defined | Facility Integrity | 280 |  |  | 279.57 | 280 | 0 | Green |  |  |  | 280 |  |  | 500000 |  | 62000 | 562000 | Supplemental | 562000 | 608755 |  | 608755 | No | Green | 2022-01-01 | 2022-01-06 | 2022-01-06 | 2022-12-31 | 2022-12-31 |  |  | 279.57 | [18 empty] | 03/28/2023 - Project closed out. 03/01/2023 -Project is ready to be closed 10/22 - 12/22 Supplemental approved to continue high-priority repairs ahead of the 2023 schedule. Supplemental work in progress until yearend. 08/22 - EKA - Planned work complete three months ahead of schedule. $60,000 reallocated to the BBH Cat Island Project from the Underground Tank Inspections Phase 1 project in order to support additional work on the daylighting and repairs project to keep the crew moving on the daylighting efforts without having to demobilize and remobilize next year. Additionally, the daylighting work is the first step in order to make the pipe accessible for API-570 inspections to begin next year. 8/22 - Planned support sleeper repairs for 2022 approaching completion three months ahead of schedule due to simultaneous work on Cat Island Road section B and at Acklin’s Road section D. This effort was to ensure the majority of the civil work was complete ahead of the rainy/hurricane season. 7/22 - Support repairs are ongoing as planned. There is no adjustment required to the schedule or to the forecast. · Concrete support sleeper repairs on section B and section currently ongoing simultaneously to ensure civil work is complete ahead of the rainy season. 02/22 - P226 pipeline replacement at Pinder's Point Complete – Line hydrotested and returned-to-service. 01/22 - concrete support sleeper repairs commenced on Cat Island Road section B and at Pinder's Points section D. This work is currently ongoing. | 2023-03-28 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 280 | 0 |  |  | 608475 |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 41205 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
BBH - Cat Island to Acklins and Inagua Road Repairs Phase 4 | Item | Open | MEXP | 8410811E2301 | Maintenance Framework | 2076594 | Wildgoose Thompsona, Tanya | East | 3. Active | Defined | Facility Integrity | 181658 | 182017 |  | 363674.6 | 352888 | 10787 | Yellow | 350000 |  | 350000 | 13675 |  |  | 349250 |  |  | 349250 | Full | 349250 | 181658 | 182017 | 363675 | No | Green | 2023-02-01 | 2023-01-23 | 2023-01-23 | 2023-12-31 | 2023-08-31 |  |  |  | 57233 | 63637.8 | 60786.8 | 50000 | 50000 | 10787 | Red |  | WorkAhead of Schedule | 60000 | 50000 | 60000 | 12017 | [5 empty] | 04/2023 - concrete support sleeper repairs and pipe alignments resumes on Cat Island Road section B & C and Acklin's Road section D. 03/2023 - concrete support sleeper repairs and pipe alignments resumes on Cat Island Road section B and Acklin's Road section D. 02/2023 - concrete support sleeper repairs and pipe alignments resumes on Cat Island Road section B and resumes on Acklin's Road section D. | 2023-05-08 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 120871 | 170787 | 72017 |  |  |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 44984 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
BBH - Catwalk Installation - 10 areas | Item | Open | MCAP | 8410811M2318 | Maintenance Framework | 2095013 | McPhee, Jaylon | East | 3. Active | Defined | East | 77015 | 111435 |  | 188450.34 | 231565 | -43115 | Red | 200000 |  | 200000 | -11550 |  |  | 233000 |  |  | 233000 | Phase | 233000 | 77015 | 161435 | 238450 | No | Green | 2023-03-01 | 2023-03-14 | 2023-03-14 | 2023-03-01 | 2023-08-31 |  |  |  |  | 51564.91 | 25450.43 | 25000 | 25000 | 450 | Yellow |  |  | 25000 | 60000 | 26435 | [6 empty] | 05/2/2023 - This project will be phased out. The final number of catwalks to be fabricated and installed is 8 given the approved funding. Fabrication has begun, but awaiting additional materials to continue fabricating remainder of catwalks. 04/04/2023 - There will be nine catwalks completed and phased. Materials have been ordered for fabrication. Project is on schedule. 03/09/2023 - PM confirmed approval was received to carry out the initial 10 catwalks remaining within budget and scope. AFE being drafted. 3/1//2023 - Project scope changed to include 12 catwalks as opposed to the original 10 as Operations added an additional two.Bid walk was completed Feb 24th with Bids to be returned March 3rd, 2023. AFE is being drafted to account for additional two catwalks and expected submittal first week of March 2023. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 51565 | 110450 | 26435 |  |  | 50000 | Orischak, Bob | Orischak, Bob |  |  | 1 | 45615 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
BBH - Complete to Fire Main | Item | Open | MCAP | 8410811M2201 | Maintenance Framework | 1915890 | Campbell, Jamie | East | 7. Closed | Defined | Fire Protection | 1666 |  |  | 1666.31 | 1666 | 0 | Green |  |  |  | 1666 |  |  | 327000 |  | 34000 | 361000 | Supplemental | 361000 | 360265 |  | 360265 | No | Green | 2022-01-01 | 2021-12-10 | 2021-12-10 | 2022-06-01 | 2022-12-30 |  |  | 1666.31 | [18 empty] | 03/28/2023 - Project closed out and supplemental AFE driven by VAT reclasses was submitted. 2/2/2023 Project ready to close. 9/14/2022 KB: Operational date updated to 12/30/22; the contractor has been delayed based on ship blocking the jetties. 7/5/2022 Project progressing slowly due to weather and platform usage. 6/01/22 Fire main project progressing slow due to weather and contractor can only work when the no ship along side the Jetty. 4/30/22 Fire main project was impacted by ships along jetty, along with bad weather and crane out of service for repairs. 1/1/22 Piping material procured for replacement of fire system. 2/1/22 Prefabrication of sections of fire system in progress. 3/1/22 Prefabrication continues to eliminate down time of the system when installation begin. 4/1/22 Repairs are in progress 4/30/22 - Fire main repairs were impacted this month by ships along side jetty, the crane not working and port closures due to weather. | 2023-03-28 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 1666 | 0 |  |  | 358599 |  | Jakubowski, Gregory | Nash, Tom |  |  | 1 | 41728 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
BBH - Daylighting and Inspections | Item | Open | MEXP | 8410811E2302 | Maintenance Framework | 2076593 | Wildgoose Thompsona, Tanya | East | 3. Active | Defined | Facility Integrity | 56263 | 100000 |  | 156262.5 | 149400 | 6863 | Yellow | 150000 |  | 150000 | 6263 |  |  | 147439 |  |  | 147439 | Full | 147439 | 56263 | 100000 | 156263 | No | Green | 2023-02-01 | 2023-01-23 | 2023-01-23 | 2023-12-31 | 2023-12-31 |  |  |  | 17750 | 21650 | 16862.5 | 10000 | 10000 | 6863 | Red |  |  | 10000 | 20000 | 10000 | 10000 | 20000 | 10000 | 20000 |  |  | 04-2023 - Daylighting resumes in Inagua Road West Sec B and commences in Sec E west of pump house bridge. 03-2023 - Inspections resume on emergent defects (leak near pump house along Inagua road, P4 west of P1420 tie in @ Pinders Point, NLJ electrical riser support beam) 02-2023 - Daylighting resumes in Inagua Road West Sec B - Inspections resume for emergent repairs (P4; 2" drains to T-8062, T8075, 8076, 8080; leak in Inagua Road West Sect E) | 2023-05-08 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 39400 | 46863 | 40000 | 30000 |  |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 45616 |  | Administrator, System | Independent | Aqua | 2022-08-30 | Int - Planned Corr & FI
BBH - Dock 1 Fire pump rebuild and dry hydrants | Item | Open | MCAP | 8410811M2320 | Maintenance Framework | 2119754 | Hernandez, Andres | East | 3. Active | Defined | Fire Protection |  | 120000 |  | 120000 | 120000 | 0 | Green | 120000 |  | 120000 | 0 |  |  | 120450 |  |  | 120450 | Full | 120450 |  | 120000 | 120000 | No | Green | 2023-07-01 | 2023-04-29 | 2023-04-29 | 2023-07-30 | 2023-09-30 | [14 empty] | 45000 | 75000 | [5 empty] | 5/1/23 We will design, fabricate, and install the dry hydrants. The existing pump engine is obsolete, and parts are not available in the market, We will design other options for the 2024 pump / engine replacement. AH 4-11-23 we are working on a possible plan for 2023-2024, AH 3/1/23Dock 1 fire pump is obsolete, we are looking the best way to replace this equipment, rebuild is not a good option at the moment . Forecast adjusted to reflect current actions.AH | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 0 | 120000 |  |  |  | Jakubowski, Gregory | Orischak, Bob |  |  | 1 | 41041 |  | Guest, ProSight | Independent | Aqua | 2021-08-05 | Other Programs
BBH - DP 8004 and DP 8005Fin Fan Radiator Installation | Item | Open | MCAP | 8410811M2314 | Maintenance Framework | 2095620 | Hernandez, Andres | East | 3. Active | Defined | Rotating Equipment | 65000 | 185235 |  | 250235 | 250235 | 0 | Green | 240000 |  | 240000 | 10235 |  |  | 250235 |  |  | 250235 | Phase | 250235 | 65000 | 185235 | 250235 | No | Green | 2023-04-01 | 2023-03-20 | 2023-03-20 | 2023-11-30 | 2023-11-30 | [5 empty] | 65000 | 65000 | 65000 | 0 | Green |  |  |  |  | 65000 |  | 50000 | 30000 | 40235 |  |  | 5/1/23 we approved the drawings for the heat exchangers, equipment is under fabrication, ETA october AH 4-11-23 Heat exchangers were ordered, forecast was modified according to the contractor charge break down AH 3/1/23 Heat exchangers has a 30 weeks delivery time, we will buy 2 heat exchangers units this year, and phase the installation for next year 2024 AH | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 65000 | 115000 | 70235 |  |  | Posipanko, Dan | Nash, Tom |  |  | 1 | 41049 |  | Guest, ProSight | Independent | Aqua | 2021-08-05 | Other Programs
BBH - Electrical Upgrades to conduit and wire feeding the NLJ through the concrete cap. | Item | Open | MCAP | 8410811M2307 | Maintenance Framework | 2076604 | Wildgoose Thompsona, Tanya | East | 3. Active | Defined | Electrical | 27457 | 60000 |  | 87456.5 | 85000 | 2457 | Yellow | 85000 |  | 85000 | 2457 |  |  | 86109 |  |  | 86109 | Full | 86109 | 27457 | 60000 | 87457 | No | Green | 2023-04-01 | 2023-01-23 | 2023-01-23 | 2023-12-31 | 2023-08-31 | [5 empty] | 27456.5 | 40000 | 40000 | -12544 | Red |  | Other | 55000 | 5000 | [7 empty] | 04/20/2023 - Materials on island. Fabrication commences. Awaiting quotes to blast and paint jetty piles and support beams. Fabrication was delayed due to materials arriving on island late. 04/03/2023 - Awaiting stainless steel materials to arrive on island. 03-2023 - Contractor selected, Materials ordered. 02-2023 - conducted site visit with contractor discuss scope of work. Currently awaiting parts arrival on island before scheduling repairs. Repairs will require an 8 hour power outage to the NLJ. | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 87457 |  |  |  |  | Ashley, Robert | Nash, Tom |  |  | 1 | 45611 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
BBH - Emergent Pipeline Repairs | Item | Open | MEXP | 8410811E2216 | Maintenance Framework | 2043759 | Wildgoose Thompsona, Tanya | East | 7. Closed | Emergent | Facility Integrity | 3851 |  |  | 3851.35 | 3851 | 0 | Green |  |  |  | 3851 |  |  | 190000 |  |  | 190000 | Full | 190000 | 258805 |  | 258805 | No | Green | 2022-11-01 | 2022-11-03 | 2022-11-03 | 2022-12-31 | 2022-12-31 |  |  | 5366.7 |  | -1515.35 | [16 empty] | 4/19/2023 - Closed WO/PO (WO to stat 80, POs already closed). Set OPPM project status to 'Closed'. MCS. 03/01/2023 - Project ready to be closed. Supplemental being updated week of March 3rd for submittal. 121/2023-OPPM to be updated by Tanya (also any accruals). 12/22 - P666 repaired and returned to service - P228 repaired and returned to service -P161&P156 Fabrication of parts complete, ordered parts received, earliest available outage for installation scheduled for Jan during 2023 pipeline repairs. 11/22 - P666 out of service, repairs in progress - P228 - replaced failed line section. Civil repairs to road complete. Line returned to service - 20" Ballast line repaired - repaired failed line section. Line returned to service - P161 - Fabrication complete- awaiting scheduled outage - P156 - Fabrication complete- awaiting scheduled outage | 2023-04-19 | Coverley, Colleen | Orischak, Bob | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 3851 | 0 |  |  | 254954 |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 46115 |  | Guest, ProSight | Independent |  | 2022-10-25 | Int - Planned Corr & FI
BBH - External API 653 Inspections 2023 | Item | Open | MEXP | 8410811E2217 | Maintenance Framework | 2045859 | Campbell, Jamie | East | 3. Active | Defined | Tanks | 24081 | 91269 |  | 115350.15 | 115350 | 0 | Green | 230000 |  | 230000 | -114650 |  |  | 228000 |  |  | 228000 | Full | 228000 | 136731 | 91269 | 228000 | No | Green | 2022-12-01 | 2022-11-25 | 2022-11-25 | 2022-12-31 | 2023-05-31 |  |  | 920 | 0 | -6838.85 | 30000 | 30000 | 30000 | 0 | Green |  |  | 30000 | 0 |  |  | 30000 | 31269 |  |  |  | 05/01/2023 - 04/02/2023 - This project may not need all of funding due to only inspecting small Jetty tanks.RLO HMT inspectors are schedule to arrive at the terminal on April 11, to conclude external inspection of tank on the Jetties. 2/2/2023 Tank inspections are completed and reports uploaded into BEST. Compiling all required repairs into a spreadsheet to submit to integrity and BBH Management. Waiting on HMT to submit their invoice. 12/9/22-CES-Pull forward project. | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Tank Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | -5919 | 60000 | 30000 | 31269 | 112650 |  | Stine, Carlton | Nash, Tom |  |  | 1 | 44757 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
BBH - Install Shore power to Tug Boats at Berth 11 Phase 2 | Item | Open | MCAP | 8410811M2208 | Maintenance Framework | 1945674 | Cooper, Greg | East | 6. Operational | Defined | Electrical | 825 |  |  | 824.95 | 70 | 755 | Red |  |  |  | 825 |  |  | 185000 |  |  | 185000 | Full | 185000 | 192982 |  | 192982 | No | Green | 2022-02-01 | 2022-02-02 | 2022-02-02 | 2022-05-31 | 2022-10-31 |  |  | 22.45 |  | 47.5 | 755 |  |  | 755 | Red | [11 empty] | 102822 - Generator has been tested and commissioned.100722 - Expect to complete final testing of generator with two (2) Tug boats by 102122 -092022 - The frequency generator has been installed, wired and should be ready for operation by 093022. 070722 - The frequency generator is in the process of being picked up by Unishippers for transport to Seacor. Delivery to BBH is estimated for the week of July 18. Generator to be operational during August.050422 - The frequency generator is now scheduled to be at BBH by May 27th. The delay is attributed to the enclosure manufacturer of the generator set. The enclosure has not been delivered to the generator manufacturer. 033122 - Generator now expected to be on site by May 13th - 3/29/22 - Concrete foundation and conduit work for generator in progress; 3/9/22 - Electrical infrastructure and Concrete foundation to be installed. Generator has been ordered and expected at end of April. [Herry] | 2022-10-28 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 70 | 755 |  |  | 192157 |  | Ashley, Robert | Nash, Tom |  |  | 1 | 41059 |  | Guest, ProSight | Independent | Aqua | 2021-08-05 | Other Programs
BBH - Jetties Maseration Systems | Item | Open | MCAP | 8410811M2204 | Maintenance Framework | 1916297 | Hernandez, Andres | East | 6. Operational | Defined | East | 1548 |  |  | 1547.78 | 1548 | 0 | Green |  |  |  | 1548 |  |  | 164000 |  |  | 164000 | Full | 164000 | 160523 |  | 160523 | No | Green | 2022-03-01 | 2021-12-14 | 2021-12-14 | 2023-07-31 | 2022-09-30 |  |  | 1547.78 | 0 | 0 | 0 |  |  | 0 | Green | [11 empty] | 03/01/2023 - Project is ready to close pending clearing of final accrual of $4K. 12/28/2022 - Project marked operational per PM confirmation. 11/4/22 2 treatment plants were installed, one plant is pending for installation, to close the project. we had some delays, related to weather and ships AH 9-30-22 plants are being installed, plumbing delays due tu hurricane Ian. AH 8/10/22 Shipping was delay in july, plants are being transported to bahamas in august. AH 7-7-22 Treatment plants are fabricated,shipping will be made in july. AH 6-8-22 project delays on fabrication, manufacture had delays on materials. all materials are in place. fabrication process just stared AH 5/4/22 Treatment plants were approved by our environmental team, manufacture had delays with the materials, plants ETA end of May.. AH 4/7/22 treatment plant design is under Buckeye environmental team approval. AH 3/8/22 company included in our system, waiting from soulsource approval AH 2/2/22 Delays in obtaining quotes from recommended companies. Need marine capable vendors. BL | 2023-03-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 1548 | 0 |  |  | 158975 |  | Orischak, Bob | Nash, Tom |  |  | 1 | 41394 |  | Guest, ProSight | Independent | Aqua | 2021-08-12 | Other Programs
BBH - Jetty Cathodic Protection | Item | Open | MCAP | 8410811M2125 | Project Framework | 1878462 | McPhee, Jaylon | East | 7. Closed | Unplanned | Marine | 559 |  |  | 559.06 | 559 | 0 | Green |  |  |  | 559 |  |  | 300000 |  | 67000 | 367000 | Supplemental | 367000 | 408462 |  | 408462 | No | Green | 2021-10-01 | 2021-08-19 | 2021-08-19 | 2021-12-31 | 2022-04-30 |  |  | 0.99 |  | 558.07 | [16 empty] | 5/6/22 - NSJ Cathodic protection project is completed. all 23 cathodic protection installed. 4/6/22 - Weather delays pushed anode replacement labor back to complete in full by month of April. DC 2/2/22 Delays in shipping, pushing the forecast back 2 months. Anodes will be shipped towards the end of February BL 1/11/22 - Progress payment pushed to January. Forecast updated. DC 12/8/21 - Plan to make progress payment in December.BSK 12/2/21 Delay in receiving quote and estimate operational date is moved back to the end of february 2022 BL 11/5/21 - Survey has been completed. Bid package to be issued soon. Materials 1 to 2 weeks lead time.10/7/21 - Survey to be completed soon and then will bid. | 2022-08-08 | Boyd, Kim |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 559 | 0 |  |  | 398798 |  | Spari, Markella | Nash, Tom |  |  | 1 | 35007 |  | Guest, ProSight | Independent | Aqua | 2019-08-30 | Marine
BBH - Jetty Cathodic Protection Upgrades 2023 | Item | Open | MCAP | 8410811M2310 | Project Framework |  | McDonald, Carnetta | East | 2. Pending AFE | Defined | Marine |  | 500000 |  | 500000 | 500000 | 0 | Green | 500000 |  | 500000 | 0 |  |  | 500000 |  |  |  | Full | 500000 |  | 1000000 | 1000000 | No | Green | 2023-06-01 |  |  | 2023-12-31 | 2023-12-31 | [13 empty] | 17000 | 150000 | 100000 | 233000 |  |  |  |  | 05/01/2023 - Deepwater Corrosion inspector set to visit BBH Marine this month to conduct a site inspection to determine scope of work for the additional Cathodic protection at NLJ Platform. Also, to assess the new anodes that were installed in 2022 at the New Small Jetty. CLM 04/02/2023 - Project framework to be submitted. I am awaiting the confirmation if a Project Framework is required since the cost for this phase 1 is 500k for 2023. I am also working with Deepwater to indentify the areas that need new cathothic protection at the Jetties. CLM 3/1/2023 - Vendor selected and scope completed. AFE has been submitted. Project Framework pending submission 2/2/2023 - AFE has been submitted. Project Framework pending submission. CLM | 2023-05-03 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 17000 | 483000 |  |  | 500000 | Spari, Markella | Mirandi, Angela |  |  | 1 | 45328 |  | Spari, Markella | Independent | Aqua | 2022-08-25 | Marine
BBH - Jetty Pile Wrapping | Item | Open | MCAP | 8410811M2005 | Exempt | 1672044 | McDonald, Carnetta | East | 7. Closed | Unplanned | Marine | 4 |  |  | 4.36 | 4 | 0 | Green |  |  |  | 4 |  |  | 238000 |  |  | 238000 | Full | 238000 | 260579 |  | 260579 | No | Green | 2020-10-01 | 2020-01-08 | 2020-01-08 | 2021-12-31 | 2022-04-30 |  |  |  |  | 4.36 | [16 empty] | 9/15/22 KB: Closed per C. McDonald 3/1/2022 Project delayed to March due to weather BL 3/01/2022 - Wrapping has been installed with final report submitted. All invoices are now being process, before final close out of project. CLM 1/01/2022 - Project is completed with vendor invoices pending submission. CLM 12/1/2021 - Project is delayed until end of December 2021 BL 12/1/2021 - Project is delayed due to replacement material not delivered as yet to BBH Marine. Once materials arrive, I will push to complete by end of December 2021. CM 11/01/2021 - This project is slightly delayed due to the Denso Wrap Supplier shipping the wrong size for the Mooring Dolphin Pile. I am now in contact with them, in order to expedite the replacement ASAP. CM 10/01/2021 - Project had a slight delay on purchasing additional wrapping materials to commence work. CM 9/01/2021 - Project is on target and on schedule. New Small Jetty riser pipelines wrapped and completed this month. CM 8/03/2021 - Project to start this month with wrapping of the NSJ Riser Pipelines. CM 6/1/2021 - Forecast has been pushed to August 2021, due to severe weather delays and sea level. CM 5/1/2021 - Purchasing was delayed due to vendor not supplying quote in time to purchase material. CM 4/6/21 - Lloyd inspection complete. Risk assessment and purchasing in process.DC 03/03/2021 - Discussions to proceed concerning effective maximization of quality lifespan of wrappings. DC 02/01/2021 - Project awaiting final Dock Feed Study results before work can commence. 11/10/2020 - Project delayed due to Dock Inspection and Feed study project delay. 11/4/2020 - Further delays due to COVID-19, quarantine coordination. 10/01/2020 - Project remains scheduled for Q4 November-December, 2020 due to delay in Contractors Mobilization because of the onset of Covid-19. 02/01/2020 - Inspection in progress for jetty piles to determine scope of work. 01/08/2020 - AFE is being routed for approval. Project scope being prepared in preparation for bid walk. | 2022-09-15 | Boyd, Kim |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 4 | 0 |  |  | 2832 |  | Spari, Markella | Nash, Tom | N/A |  | 1 | 31573 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Marine
BBH - Jetty Pile Wrapping 2022 | Item | Open | MCAP | 8410811M2210 | Project Framework | 1947158 | McDonald, Carnetta | East | 7. Closed | Defined | Marine | 2945 |  |  | 2945 | 2945 | 0 | Green |  |  |  | 2945 |  |  | 238000 |  | 32000 | 270000 | Supplemental | 270000 | 277029 |  | 277029 | No | Green | 2022-04-01 | 2022-02-18 | 2022-02-18 | 2022-07-31 | 2022-12-30 |  |  | 2837.19 | 107.81 | [17 empty] | 03/28/2023 - Project closed out. 01/01/2023 - Project completed and scaffolding removed as of December 2022. CLM 12/1/2022 - Project was delayed due to incorrect Denso Wrap size delivered. Project is now back on schedule with an end of December 2022 completion. 9/13/22 - Accrual dropped due to lower than anticipated cost of completed work. DC 09/01/2022 - The Final Denso order has been delivered to our freight forwarder Seacor. The tool is now here and the work shall resume, pending weather conditions. CLM 08/01/2022 - Delay regarding denso wrap tool in order to continue with wrapping. The tool is a banding buckle and stainless steel straps in order to secure the wrap. The vendor is working to retrieve this tool, since its not a stock item. This tool is causing severe delay at the moment but hopefully this is rectified ASAP. CLM 07/01/2022 - Minor delay with sea tide and preparing surface for denso wrapping but overall on schedule. CLM 06/01/2022 - Delay with vendor on order for Denso Wrapping & Tools. This delay is caused for my missed forecast, which furthered push the project back. Scaffolding to commence this week in order to surface prep the piles, for Denso wrap installation. All installation of wrap is subject to the weather. CLM 05/01/2022 - Installation of Denso wrap schedule for this month, May 2022. Accrual submitted for Denso North America. CLM 04/01/2022- Denso wrap will be purchase this month. CLM 03/01/2022 - AFE is approved. 02/01/2022 - AFE will be submitted this month February, 2022 for approval. CLM | 2023-03-28 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 2945 | 0 |  |  | 274084 |  | Spari, Markella | Nash, Tom |  |  | 1 | 41580 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Marine
BBH - Jetty Piping 2022 Inspections | Item | Open | MEXP | 8410811E2202 | Maintenance Framework | 1938099 | McDonald, Carnetta | East | 3. Active | Defined | Facility Integrity | 428498 | 577391 |  | 1005888.63 | 1006193 | -304 | Yellow |  | 295000 | 295000 | 710889 |  |  | 600000 |  |  | 600000 | Full | 600000 | 622609 | 577391 | 1200000 | Yes | Red | 2022-05-01 | 2022-01-12 | 2022-01-12 | 2022-12-31 | 2023-05-31 |  |  | 800 |  | 255525.8 | 172171.83 | 157449 | 157449 | 14723 | Yellow |  | Forecasting | 273038 | 304353 | [7 empty] | 05/01/2023 - The ILI Inspection for all eleven (11) pipelines is now completed. Only field preliminary reports were issued by Applus on site. Final reports are outstanding and should be submitted by end of this month, May 2023. During this time, for the month of May and June 2023, all final invoices will be submitted to ensure a complete project close out for the end of June 2023. CLM 04/03/2023 - We encountered a delay while inspecting P222 NSJ but were able to successfully complete the inspection April 2nd, 2023. The P3-42" is now being inspected and forecast for completion April 7th 2023. The overall project is now on schedule eventhough we faced some delays early in the beginning of the project. I anticipate end of April 2023 completion for all eleven (11) pipelines. CLM 3/1/2023 - Additional $600K being added to this project to account for additional six pipelines The full project amount will be $1.2M with the $600K being funded from Facility Integrity (Elaine Aiken). 02/07/2023 - ILI Inspection start date set for March 27th 2023. The scope has been confirmed by Applus and BBH Operations Planning. Eleven (11) pipelines will be inspection, at the NSJ, NLJ and OLJ; Pinders Point. CLM 12/1/2022 - This project has been pushed in end of Q1 into Q2, March 20 - April 2023. Project was delayed due to Applus schedule and BBH Operational constraints. CLM 10/01/2022 - Based on the new schedule date, Applus has agreed to November 25th to start Inspection at the NLJ & NSJ. CLM 09/01/2022 - The September 12-15 date has been cancelled again due to Applus scheduling conflict. They have proposed a new date November 25th, 2022, in which I have recanted back to a new time, October 24th - November 4th, 2022. BBH is trying not to schedule an inspection end of 4th quarter with a possibility of another delay from Applus. In which can result in a carry over to 2023. Applus has not yet agreed to the new dates propose. CLM 08/01/2022 - Applus RTD gavean update on August 5, 2022. The inspection tools required for the project here in freeport, is currently delayed in Chile on another project. Applus will have another update this week, as to when they see this project officially starting here in Freeport, Grand Bahama. Applus will continue to update us weekly on the delivery of the equipment/tools for this upcoming in September 12-15,2022. CLM 2022-06-02 - Contractor had to push start date to September due to workload/Covid cases. 04/01/02022 - Bids received March 31st, 2022. A bid review exercise will take place April 8th, 2022. The project is still on path for a June 6th, 2022 start day. CLM 3/1/2022 $250k is removed from forecast to cover for carryover on 2020 NSJ Inspections AFE BL | 2023-05-03 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 256326 | 749563 |  |  | 194111 |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 41157 |  | Aiken, Elaine | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
BBH - Main Comms Tower Repairs | Item | Open | MEXP | 8410811E2218 | Maintenance Framework | 2046206 | Hernandez, Andres | East | 7. Closed | Drawdown | East | 10995 |  |  | 10995.45 | 10995 | 0 | Green | 30000 |  | 30000 | -19005 |  |  | 81000 |  |  | 81000 | Full | 81000 | 84420 |  | 84420 | No | Green | 2022-12-01 | 2022-11-28 | 2022-11-28 | 2022-12-31 | 2023-02-01 |  |  | 8990.27 | 2005.18 | [17 empty] | 03/28/2023 - Project is closed out. 03/01/2023 - Project is ready to be closed. 2/1/2023 - Project is operational. No more POs are expected. Once actuals are posted in February, project can be closed. | 2023-03-28 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 10995 | 0 |  |  | 73424 |  | Orischak, Bob | Nash, Tom |  |  | 1 | 45621 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
BBH - NLJ & NSJ Landing Stage - Fender, Grating, Railing Repairs | Item | Open | MEXP | 8410811E2214 | Maintenance Framework | 2002634 | McDonald, Carnetta | East | 7. Closed | Emergent | Marine | 22714 |  |  | 22713.89 | 22714 | 0 | Green |  |  |  | 22714 |  |  | 266000 |  | 45000 | 311000 | Supplemental | 311000 | 323221 |  | 323221 | No | Green | 2022-07-01 | 2022-07-11 | 2022-07-11 | 2022-10-01 | 2022-12-30 |  |  | 6398.3 | 16315.59 | [17 empty] | 03/28/2023 - Project closed out. 03/01/2023 - Project is ready to close. $14.8K of February actuals is VAT reclass. 01/01/2023 - Project completed and has been return back to service. Operations and HSSE has been notified. CLM 12/1/2022 - Supplemental AFE was approved. Project is set for completion December 16th, 2022. As of today, H2S ship is on the Berth for 5 working days. But that will not disrupt the schedule to meet completion date. CLM 10/10/22 KB - This project is still pending the adjustment of $30k by Angela Mirandi which was approved on 9/9/22. 09/09/22 - Additional 30K added in November for scaffolding costs. MKS to adjust another project. 09/01/2022 - Project is on schedule, with no delays at this time. CLM 08/01/2022 - Project is on schedule, with no delays at this time. CLM 07/01/2022 - The AFE was approve June 30th, 2022. Forecast will be schedule for August and September 2022. CLM | 2023-03-28 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 22714 | 0 |  |  | 300507 |  | Spari, Markella | Orischak, Bob |  |  | 1 | 44049 |  | Meitzler, Antoinette | Independent | Aqua | 2022-06-29 | Marine
BBH - NLJ Fire Pump MP9003 | Item | Open | MCAP | 8410811M2306 | Maintenance Framework |  | McDonald, Carnetta | East | 2. Pending AFE | Defined | Fire Protection |  | 260000 |  | 260000 | 260000 | 0 | Green | 260000 |  | 260000 | 0 |  |  | 260000 |  |  |  | Full | 260000 |  | 260000 | 260000 | No | Green | 2023-06-01 |  |  | 2023-09-01 | 2023-07-31 | [13 empty] | 50000 | 50000 | 50000 | 50000 | 60000 |  |  |  | 05/01/2023 - Meeting being held this week. Forecast will be updated based on results of meeting and prior to forecasts being locked. 4/3/2023 - AFE submitted but held based on the requirements from HSSE the engine and pump is $322K budget is $260K. Dave DeSocio has been updated. Upon receipt of quotations, a meeting will be scheduled. March forecast push to May. Project is underfunded due to size of new pump requested by HSSE. I am currently working with Greg Jakubowski, along with Greg Cooper (Electrical) and David DeSoc. CLM 3/1/2023 - AFE submitted but held based on the requirements from HSSE the engine and pump is $322K budget is $260K. Dave DeSocio has been updated. Upon receipt of quotations, a meeting will be scheduled. March forecast push to July. Project is underfunded due to size of new pump requested by HSSE. I am currently working with Greg Jakubowski, along with Greg Cooper (Electrical) and David DeSocio regarding a path forward. CLM 2/2/2023 - AFE has been submitted. Forecast set for end of Q1, 2023 Start. CLM | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 50000 | 150000 | 60000 |  |  | Jakubowski, Gregory | Nash, Tom |  |  | 1 | 45618 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
BBH - NSJ Landing Stage Replacement | Item | Open | MCAP | 8410811M2126 | Project Framework | 1878464 | McDonald, Carnetta | East | 7. Closed | Unplanned | Marine | 19 |  |  | 19.27 | 19 | 0 | Green |  |  |  | 19 |  |  | 320000 |  |  | 320000 | Full | 320000 | 323212 |  | 323212 | No | Green | 2021-08-01 | 2021-08-19 | 2021-08-19 | 2021-11-30 | 2022-04-30 |  |  | 2.04 |  | 17.23 | [16 empty] | 03/01/2022 - The tracking information has been updated to March 12th 2022 for delivery into Florida, and then expedited to Freeport for installation. CLM 02/01/2022 - QSL is the local contractor responsible for the completion of this replacement. They are currently awaiting an update from the vendor out of England that's supplying the fenders; shipping update. Supply Chain Delay is with I'm faced with currently regarding the completion of this work. Project now 80% completed. CLM 01/01/2022 - Minor delay but overall 70% completed. Delayed due to remaining long fenders not delivered as yet. Forecast was submitted and operational date push back to end of January 2022. CLM 1/5/22 Estimated Operational Date is pushed back to the end of january BL 12/1/2021 - Estimated operational date is pushed back to end of this month BL 12/1/2021 - Fender Supplier is now proposing the 20th of December 2021 for delivery of the new fenders, needed for the Landing Stage. CM 11/01/2021 - I had several delays due to operations, high tide and shipping delays from Fender Supplier. The contractor is now anticipating an additional 3-4 weeks for delivery for completion. But this Project will be completed in 2021. CM 10/01/2021 - Work is in progress but slightly delayed due to high tides. CM 9/1/2021 - AFE received final approval on August 19th, 2021. Therefore, the demolishing work of the existing Landing Stage & Fenders was pending removal. The work started August 31st. due to high tide and temporary Port Closure. The works has begun and now on schedule. 8/9/21 - Funds coming from Perth Amboy project. DC | 2023-05-08 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841810 - BOR - OPERATIONS |  | 19 | 0 |  |  | 43875 |  | Spari, Markella | Martin, David N. |  |  | 1 | 40920 |  | Clark, David | Independent | Aqua | 2021-08-04 | Marine
BBH - NSJ Sealine Concrete Casing Repairs | Item | Open | MEXP | 8410811E2203 | Maintenance Framework | 1937505 | McDonald, Carnetta | East | 6. Operational | Defined | Facility Integrity | 119554 |  |  | 119553.57 | 119554 | 0 | Green |  |  |  | 119554 |  |  | 200000 |  | 49500 | 249500 | Supplemental | 249500 | 342433 |  | 342433 | Yes | Red | 2022-03-01 | 2022-01-07 | 2022-01-07 | 2022-03-31 | 2022-12-30 |  |  | 114015.69 | 5537.88 | [17 empty] | 05/01/2023 - Supplmental documents will be issue this month for the additional freight charges. CLM 03/01/2023 - Direction is pending from Elaine for funding to cover the supplemental, but also potential funding for the installation of the mats. The direction would determine if a new project will be created for the installation or will this project be used to complete the installation as well.Supplemental will be submitted pending Elaine's feedback. 02/07/2023 - Frieght on concrete mats delivery from Seacor Island LLC Fort Lauderdale to Freeport Grand Bahama, exceeded the the overall budget. The estimated charge was given by local Procurement in November 2022 at 25-30k (1st Supplemental was submitted to cover freight cost) based on one voyage. Seventy Five Mats (75) – Total weight: 465,000Ibs was expected to be transported to the island. Final Total After delivery to Island; G.B.: $80,036.89 (Based on final delivery cost, the first supplemental approval did not cover the final invoice). The plan was to have one shipping voyage to island but it took five (5) voyages in order to accommodate this delivery, resulting in the final overage charges. Awaiting final word from Integrity (EA) on whether to reclass or submit a supplemental based on available funding within program.(CLM) 01/10/2023 - Concrete mats have been delivered to our freight forwarder Seacor, Fort Lauderdale. Mats starting delivery efforts from Fort Lauderdale to Freeport G.B. January 4th 2023. All mats will be delivered to Freeport G.B. (BBH) before January 15, 2023. CLM 12/1/2022 - The Concrete Mats are now in production with Submar and expected to be delivered to our freight forwarder Seacor December 15th, 2022. CLM 10/10/22 KB - Per Elaine Aiken $42k has been reallocated from the Underground Tank Inspection to cover the variance in this project. 10/01/2022 - Bid award for October 13th, 2022 to purchase concrete mats. CLM 09/01/2022 - Based on bids received, the installation of the concrete mats will be deferred to year 2023. The purchase of the concrete mats, will take place in September through 4th quarter 2022. CLM 08/01/2022 - Delay regarding shipping some of the concrete mats. The bids are now in and will be evaluated this week. CLM 07/01/2022 - Bid walk set to commence July 15, 2022. CLM 06/01/2022 - Another meeting was held June 2nd, 2022 to inform the team regarding Applus ILI rescheduling, that would impactP222 (NSJ).Because of this reschedule, this project has been pushed back as well, and also to now inspect and or replace the anodes at the NSJ before the Mats can be install. I will too, purchase the Mats to have them on island, to avoid any delay, once clearance is good for the NSJ Concrete project to begin. CLM 5/11/22 - Rescheduled to Q2 pending scheduling of P222. Slated to begin after P222 ILI run. DC 05/01/2022 - I had another follow-up meeting April 29th 2022, with Integrity, Tom, Markella, Lloyd and myself and no final decision was made to move forward. Integrity advise me to complete the upcoming ILI for the P222 first in June of this year, also both integrity and Markella asked for additional data on all the NSJ pipelines before a final decision to install the concrete mats. Because of this uncertainty, I advised everyone that I will push the forecast to July 2022, in order to avoid any additional disruption with the forecast and the PMO Office. CLM 04/01/2022- This project is still in the development stages and I am being assisted by M. Spari, Integrity Group, Lloyd Engineering, D. Martin, and T. Nash, in order to make the final choice for the underwater concrete repair at the NSJ. CLM 4/1/22 - Project delayed pending engineering details from Integrity. DC 03/01/2022 - Project on track. Scope of workbeing developed with Lloyd Engineering Group & Dave Martin. CLM 02/01/2022 - Preparing Scope of work. CLM | 2023-05-03 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 119554 | 0 |  |  | 222879 |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 38087 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Int - Planned Corr & FI
BBH - Offshore Coating 2021 | Item | Open | MCAP | 8410811M2111 | Exempt | 1812201 | McDonald, Carnetta | East | 6. Operational | Defined | Marine | 180 |  |  | 179.55 | 20 | 160 | Red |  |  |  | 180 |  |  | 600000 |  |  | 600000 | Full | 600000 | 625583 |  | 625583 | No | Green | 2021-03-01 | 2021-02-12 | 2021-02-12 | 2021-12-31 | 2022-02-28 |  |  |  |  | 19.55 | 160 |  |  | 160 | Red | [11 empty] | 08/01/2022 - Outstanding invoices are now being finalized in the system for hard close. CLM 06/01/2022 - The weather delayed the completion by 15% but overall majority of the work is completed. All final invoices are now being processed in preparation to close this project. CLM 05/01/2022 - The remaining coating should be completed by end of this Month, May 2022; without any major weather or berthing schedule delays. CLM 04/01/2022 - Major weather delays and Port closure, slowed down the completion process for this project. I am aggressively pushing, and in constant communication with the planning department in order to complete the remaining coating sections. CLM 02/01/2022 - Submitting all outstanding invoices. CLM 01/01/2022 - Contractors are wrapping up outstanding work, so the operational date was pushed back to end of January 2022. Weather played a major role in this delay but nonetheless, the work will be completed. CLM 1/5/22 Operational date pushed back to 1/31/22 BL 12/01/2021 - All painting contractors are working based on availability of the Berths and weather conditions. I am still aiming for the end of this month. Dec 2021 for completion. CM 11/01/2021 - I am working aggressively with contractors and operations planning, in order to complete this project on time and on budget. Weather delays is beyond my control. CM 10/01/2021 - Work is ongoing with slight delays awaiting scaffolding to be erected and dismantle. CM 09/01/2021 - Offshore Coating on schedule with minor delays but I am aggressively pushing this work. All coating work will be completed by end of year. CM 08/03/2021 - Offshore Coating on schedule with slight delays due to the shipping schedule from planning dept. CM 07/01/2021 - Offshore Coating forecast not met due to minor weather delays this month, scaffolding availability in order to start coating on Jetties. The work that was completed, invoices were not processed by DC in time but included in accruals for this month. CM 06/01/2021 - I was faced with severe weather delays and Port Closure as it relates to coating. Berthing schedule have also impacted this project. CM 05/01/2021 - This project is on budget and on schedule. Minor delays with weather and high H2s on the platforms but the scheduling department is helping out as much as they could. 02/01/2021 - AFE is now being submitted for approval. Project startdate set for March 2021. | 2022-09-15 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 20 | 160 |  |  | -35918 |  | Spari, Markella | Nash, Tom |  |  | 1 | 38025 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Marine
BBH - Offshore Piping CP Upgrade | Item | Open | MCAP | 8410811M2317 | Maintenance Framework | 2095052 | Occhi, Edward | East | 3. Active | Defined | Cathodic Protection | 7557 | 198000 |  | 205557 | 216600 | -11043 | Yellow |  |  |  | 205557 |  |  | 233600 |  |  | 233600 | Full | 233600 | 7557 | 198000 | 205557 | No | Green | 2023-03-01 | 2023-03-14 | 2023-03-14 | 2023-11-15 | 2023-11-30 |  |  |  |  | 6600 | 957 |  |  | 957 | Red |  |  | 63000 | 0 | 135000 | 0 | [7 empty] | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841817 - BOR - MARINE OPERATIONS |  | 6600 | 63957 | 135000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45154 |  | Guest, ProSight | Independent | Aqua | 2022-08-23 | Marine
BBH - Oily Water Sewer Unit Upgrades | Item | Open | MCAP | 8410811M2311 | Maintenance Framework | 2083843 | McDonald, Carnetta | East | 3. Active | Defined | Storm Water Management | 20900 | 155000 | 12097 | 175900 | 175000 | 900 | Yellow | 180000 |  | 180000 | -4100 |  |  | 187097 |  |  | 187097 | Full | 187097 | 20900 | 167097 | 187997 | No | Green | 2023-03-01 | 2023-02-01 | 2023-02-01 | 2023-05-31 | 2023-09-30 |  |  |  |  | 20000 | 900 |  |  | 900 | Red |  |  |  | 50000 | 50000 | 55000 |  |  |  |  | 12097 | 05/01/2023 - Geosyntec Group visited BBH April 2023, to assess the East, Center and West Skimmers including the API & Wastewater Treatment. This visit was to assess and give BBH recommendations to help with the operating parameters for each system. All locations identified are not solely eradicated as a standalone system but with the help of a Vac Truck daily or as requested by Operations etc. CLM 04/03/2023 - Geosyntec Group has been awarded this project to complete an overall field assessment, engineering and recommendations for the East, Center and West Skimmers including the API Upgrade. An establish scope of work will be needed, once Geosyntec has completed the assessment, that will help determine a way forward with this project. Therefore, I have pushed my forecast from April to June through August 2023. CLM 03/1/2023 - AFE has been submitted. March forecast will be met. Quotes already in hand. PO for site assessment (East, Center, West Skimmers including the API) will be issue this week, March 10, 2023. CLM 01/11/2023 - Based on the review of this project, I have adjusted my forecast from February to March 2023, at $50,000, April for $25,000; and May $105,000. CLM | 2023-05-03 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 20000 | 50900 | 105000 |  |  |  | Bonenberger, Mark | Bohnsack, Gary |  |  | 1 | 45196 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
BBH - OLJ Oily Water Separator New Installation Phase 2 | Item | Open | MCAP | 8410811M2309 | Maintenance Framework | 2076597 | McDonald, Carnetta | East | 3. Active | Defined | Storm Water Management | 69227 | 159507 | 20773 | 228733.54 | 249507 | -20773 | Yellow | 190000 |  | 190000 | 38734 |  |  | 249507 |  |  | 249507 | Full | 249507 | 69227 | 180280 | 249507 | No | Green | 2023-03-01 | 2023-01-24 | 2023-01-24 | 2023-12-12 | 2023-06-30 |  |  |  |  | 27190 | 42036.54 | 62810 | 62810 | -20773 | Red |  | Other | 50000 | 59507 | 50000 | [5 empty] | 20773 | 05/01/2023 - Forecast will be adjusted prior to forecast being locked. Forecast for the month of April not met due to delay by BBH and Port Closure; due to weather. Therefore, this resulted in the contractor not being able to complete more task based on project scope. CLM 04/03/2023 - The site visit for this project was on April 4th 2023 with Marine Maintenance, scaffolders, and Contractor QSL to finalize all onsite concerns before the disconnection phase starts on the existing sump tank. Marine Maintenance will prep system before handing over to QSL (contractor) to start with the removal of the old tank, and install new tank skid. Once the area has been prepare, the new OWS will be transported from BBH Warehouse to the OLJ. This project is on schedule for an end of June 2023 completion. CLM 03/01/2023 - Full $249K received Bob's approval. Walk about completed and forecast adjusted to reflect full AFE approval. Marine maintenance is completing prep work in March for contractor to start removal of old sump tank and install new. CLM 02/07/2023 - Bid walk schedule for Thursday February 16th, 2023. This work will include demo of existing holding tank, install new oily water separator including electrical, pipeline tie-ins, structural modification; OLJ. CLM | 2023-05-03 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 27190 | 151544 | 50000 |  |  |  | Bonenberger, Mark | Nash, Tom |  |  | 1 | 41583 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
BBH - Pipe Daylighting and Inspection | Item | Open | MEXP | 8410811E2205 | Maintenance Framework | 1937297 | Wildgoose Thompsona, Tanya | East | 7. Closed | Defined | Facility Integrity | 5236 |  |  | 5235.79 | 5236 | 0 | Green |  |  |  | 5236 |  |  | 100000 |  | 157000 | 291000 | Supplemental | 291000 | 290071 |  | 290071 | No | Green | 2022-01-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-10-31 |  |  | 4250 | 912 | 73.79 | [16 empty] | 04/11/2023 Supplemental for VAT overage submitted. 03/01/2023 -Current supplemental alert driven heavily by VAT reclasses. To be resubmitted week of March 6th. See 11/22 note for initial supplemental reasoning. 12-12-2022 - Project work completed ahead of previous 2023 forecast scheduling in favor of delayed work in other projects (Jetty Piping ILI) DC 2022-12-09 - November variance due to funds being reallocated to this project in order to offset the negative variance from the jetty piping ILI runs that were delayed due to vendor issues and line availability for pigging. 11/22 - Supplemental approved to continue daylighting and inspections in the Acklin’s Road pipe track (sect D) and Inagua Rd west (sect B) ahead of the 2023 schedule. Supplemental work in progress until yearend. 9/22 - Inspections of the Inagua Road pipe track (west-section A) commenced the week of September 19th. Inspections of this entire section will carry on until the end of the year. Emergent repairs identified during inspection will be reported immediately upon discovery, all other findings will be classified and prioritized for future budget review. 8/22 - Daylighting crew completing first section of Inagua Road (west). Final 6/22 - daylighting crew working on second half of section D on Acklin's Road. 5/22 - daylighting crew completed the first half of section D on Acklin's Road. The second section is scheduled to begin early June 1/22 - daylighting commenced at pipe tracks on Acklin’s Road section D and west Inagua Road. This work is ongoing and is coordinated with the necessary inspections. | 2023-04-11 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 5236 | 0 |  |  | 284836 |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 41206 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
BBH - Pipe Support Refurbishment at Pinder's Point | Item | Open | MCAP | 8410811M2207 | Maintenance Framework | 1937243 | Wildgoose Thompsona, Tanya | East | 7. Closed | Defined | Facility Integrity | 20188 |  |  | 20188.08 | 13369 | 6819 | Red |  |  |  | 20188 |  |  | 285000 |  | 52000 | 373368 | Supplemental | 373368 | 398413 |  | 398413 | No | Green | 2022-02-01 | 2022-01-05 | 2022-01-05 | 2022-10-31 | 2022-12-16 |  |  | 1123.28 | 6123.09 | 6123.09 | 6818.62 |  |  | 6819 | Red | [11 empty] | 03/28/2023 - Project closed out and supplemental as prepared in January submitted through Remedyforce. 12/28/2022- Project marked operational per PM confirmation. 9/22 - P4 out of service in preparation for saddle repairs 8/22 - T-8031 26" Suction line repairs and re-insulation complete 7/22 - Repairs to P666 24" Pipeline and T-8031 26" Suction line pending scheduled outage. 6/22 - Saddle repairs and pipe repairs on P1152 and P4 on hold pending Commercial confirmation of potential crude customer. 5/22 - Completed abrasive blasting and painting of recently repaired line sections (Effluent Line/P226/DP8156 Line/Hall manifold). 4/22 - Complete fabrication for repair work on the Blue Field South and North Manifolds 2/22 - RFP issued for the repair of corroded saddle points and pipe support structures on P4 (42-inch) and the P1152 (30-in) pipelines located on the south side of Pinder's Point Road. | 2023-03-28 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 13369 | 6819 |  |  | 378225 |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 41174 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
BBH - Pipe support replacement & Pipeline line alignments | Item | Open | MCAP | 8410811M2308 | Maintenance Framework | 2076603 | Wildgoose Thompsona, Tanya | East | 3. Active | Defined | Facility Integrity | 29789 | 25000 |  | 54789.09 | 50000 | 4789 | Yellow | 50000 |  | 50000 | 4789 |  |  | 54636 |  |  | 54636 | Full | 54636 | 29789 | 25000 | 54789 | No | Green | 2023-04-01 | 2023-01-23 | 2023-01-23 | 2023-12-31 | 2023-05-31 | [5 empty] | 29789.09 |  |  | 29789 | Red |  | WorkAhead of Schedule | 15000 | 10000 | [7 empty] | 04/2023 - concrete support sleeper repairs and pipe alignments commence on Inagua Road west (Section A-1). 03/2023 - Delay due to operations initially confirming line availability. | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 54789 |  |  |  |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 45617 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Int - Planned Corr & FI
BBH - Replace Boiler Stack | Item | Open | MCAP | 8410811M2203 | Maintenance Framework | 1916497 | Hernandez, Andres | East | 7. Closed | Defined | Boilers | 13716 |  |  | 13716.07 | 13591 | 125 | Yellow |  |  |  | 13716 |  |  | 817000 |  |  | 817000 | Full | 817000 | 853986 |  | 853986 | No | Green | 2022-03-01 | 2021-12-16 | 2021-12-16 | 2022-12-15 | 2022-10-31 |  |  | 7692.73 | 3117.12 | 2781.07 | 125.15 |  |  | 125 | Red | [11 empty] | 03/28/2023 - Project closed out. 02/01/2023 - Project is ready to be closed. 12/28/2022 - Project marked operational per PM confirmation. 11/4/22 expedited job was realized in October, stack was replaced and we performed complementary jobs while boilers were down. AH 9-30-22 stack will be install in october.. most of the PO will be pay in october.. AH 8-10-22 Stack is fully fabricated, we had delays in shipping in july, stack is boing shipping in August. AH 7-7-22 Stack is programed to be ready at the end of July AH 6-8-22 design was increased to 170mph wind speed, manufacturer has all materials, fabrication process on going. AH 5/4/22 Stack design was approved, stack fabrication to be done by end of July AH 4/4/22 Stack design under Buckeye engineering team review. AH 3/8/22 Project asigned to Warren environment, Stack ETa 16 weeks. AH 2/8/22 working on quotes review, this project will be assigned next month. AH | 2023-03-28 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 13591 | 125 |  |  | 840270 |  | Stine, Carlton | Nash, Tom |  |  | 1 | 41391 |  | Guest, ProSight | Independent | Aqua | 2021-08-12 | Other Programs
BBH - Replace the 4" galvanized water line to utilities. | Item | Open | MCAP | 8410811M2313 | Maintenance Framework | 2085824 | Hernandez, Andres | East | 3. Active | Defined | East | 38074 | 40000 |  | 78074.07 | 90000 | -11926 | Red | 90000 |  | 90000 | -11926 |  |  | 90375 |  |  | 90375 | Phase | 90375 | 38074 | 65000 | 103074 | No | Green | 2023-04-01 | 2023-02-23 | 2023-02-23 | 2023-05-30 | 2023-07-31 | [5 empty] | 38074.07 | 50000 | 50000 | -11926 | Red |  | Forecasting | 20000 | 20000 | [7 empty] | 5/1/23 Materials arrived last week, we are planning to replace section of the lines in may. AH 4-11-23 Pipe will arrive this week to the terminal invoice from material and shipping will be submitted, we will start with pipe installation in may AH 3/1/23, AFE was approved, we are waiting for materials quotes to purchase the pipe. Forecast flipped between April and May. AH 2/1/2023 - AFE to be submitted February. | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 78074 |  |  |  | 25000 | Orischak, Bob | Orischak, Bob |  |  | 1 | 41044 |  | Guest, ProSight | Independent | Aqua | 2021-08-05 | Other Programs
BBH - Splash Zone Repairs | Item | Open | MEXP | 8410811E2303 | Maintenance Framework | 2076592 | McDonald, Carnetta | East | 3. Active | Defined | Facility Integrity |  | 110000 |  | 110000 | 110000 | 0 | Green | 110000 |  | 110000 | 0 |  |  | 110000 |  |  | 110000 | Full | 110000 |  | 110000 | 110000 | No | Green | 2023-06-01 | 2023-01-23 | 2023-01-23 | 2023-12-31 | 2023-07-31 | [13 empty] | 50000 | 60000 | [6 empty] | 04/03/2023- Based on the 2021 Api-570 report, the OLJ and NLJ areas of corrosion was identified and riser clamps on the NLJ need replacement/repairs. This project is forecast to start June 2023, and currently working on SOW. CLM 03/01/2023 - June and July forecast is accurate. The scope of work will be started. The vendor is familiar with the works to be completed and the updated installation quotation will be requested from vendor. 02/07/2023 - AFE Submitted and approved. Forecast schedule for end of Q2, 2023. CLM | 2023-04-06 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 50000 | 60000 |  |  |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 44987 |  | Administrator, System | Independent |  | 2022-08-18 | Int - Planned Corr & FI
BBH - Substation #5 480V Switchgear | Item | Candidate | MCAP |  | Maintenance Framework |  | Wildgoose Thompsona, Tanya | East | 1. Proposed |  | Electrical |  | 425000 |  | 425000 | 425000 | 0 | Green | 425000 |  | 425000 | 0 | [9 empty] | 425000 | 425000 | No | Green | 2023-06-01 |  |  |  | 2023-12-31 | [13 empty] | 100000 | 100000 | 100000 | 75000 | 50000 |  |  |  | 04/03/2023 - Forecast was adjusted for more accurate start given availability. | 2023-04-03 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 100000 | 275000 | 50000 |  |  | Ashley, Robert |  | N/A |  | 1 | 31582 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Other Programs
BBH - Substation 7 Replacement | Item | Open | MCAP |  | Maintenance Framework |  | Wildgoose Thompsona, Tanya | East | 1. Proposed |  | Electrical |  | 165000 |  | 165000 | 165000 | 0 | Green | 165000 |  | 165000 | 0 | [9 empty] | 165000 | 165000 | No | Green | 2023-06-01 |  |  |  | 2023-10-31 | [13 empty] | 45000 | 45000 | 45000 | 30000 |  |  |  |  | 05/09/23 - AFE to be submitted in May. Awaiting revised quotation from vendor on materials and design. Forecasted adjusted to reflect same. 04/3/2023 - AFE to be submitted in April . Forecasted adjusted for pullforward. | 2023-05-09 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 45000 | 120000 |  |  |  | Ashley, Robert |  |  |  | 1 | 45609 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
BBH - Tank 8075 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP |  | Maintenance Framework |  | Campbell, Jamie | East | 1. Proposed |  | Tanks |  | 819325 |  | 819325 | 819325 | 0 | Green | 819325 |  | 819325 | 0 | [9 empty] | 819325 | 819325 | No | Green | 2023-10-01 |  |  |  | 2023-12-31 | [17 empty] | 215775 | 431550 | 172000 |  | This tank is currently schedule for the fourth quarter of 2023. | 2023-03-06 |  |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 0 |  | 819325 |  |  | Stine, Carlton |  |  |  | 1 | 44777 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
BBH - Tank Level Monitoring Upgrades Inland Dock | Item | Open | MCAP | 8410811M2212 | Maintenance Framework | 1954874 | Cooper, Greg | East | 3. Active | Defined | Instrumentation & Controls | 12751 | 28000 |  | 40750.7 | 12379 | 28371 | Red |  |  |  | 40751 |  |  | 143000 |  |  | 143000 | Full | 143000 | 154171 | 28000 | 182171 | Yes | Red | 2022-03-01 | 2022-03-02 | 2022-03-02 | 2022-06-30 | 2023-05-31 |  |  | 789.18 | 664.44 | 3250.81 | 8046.27 | 7675 | 7675 | 371 | Yellow |  |  | 28000 | [8 empty] | 05/03/3023 - Final project costs including those for the purchase of the license key confirmed and forecasted for May. License key has a delivery of 2-3 weeks. Upon receipt of license key and final wrap up in May, project can be closed. 04/04/2023 - Project operational date adjusted to May to account for license key arrival. Final project costs being gathered as a supplemental will be required. 03/02/2023 - Hubs installation scheduled for March. Also identified this week is the need to purchase a license and hardware key. Total cost of license, hardware key and associated shipping being confirmed. Project estimated to be completed end of March. 2/2/2023- Delay in becoming operational due to having to use both Rosemont Raptor Hubs at Bluefield North on tanks 8140, 8141 and 8142. Operational date updated. 12/28/2022 - Operational date updated per PM confirmation due to delays experienced by Hurricane Nicole. 102822 - Radar gauges are on site. Shopwork testing is in progress. 100722 - Radar gauges to be at BBH by 101122 - 092022 - 90% of the electrical infrastructure has been installed. The shipment of the radar gauges has been delayed and will be updated. 070722 - Ordered radar gauges and cabling expected to arrive at BBH by July 31st. In the process of providing an electrical installation PO.060122 - Radar Gauges ordered delivery expected during July 05/04/22 - Purchase requisition for radar gauges is in approval process. | 2023-05-03 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 4704 | 36046 |  |  | 141421 |  | Forsey, Frank | Nash, Tom | N/A |  | 1 | 20420 |  | Guest, ProSight | Independent | Aqua | 2016-08-18 | Other Programs
BBH - Waste Water Treatment Plant (WWTP) FEED Study 2023 | Item | Open | MCAP |  | Maintenance Framework |  | Wildgoose Thompsona, Tanya | East | 1. Proposed |  | Storm Water Management |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 | [9 empty] | 50000 | 50000 | No | Green | 2023-06-01 |  |  |  | 2023-12-31 | [13 empty] | 50000 | [7 empty] | 04/03/2023- Forecast adjusted to reflect contractor availability to be on island. | 2023-04-03 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 50000 |  |  |  |  | Bonenberger, Mark |  |  |  | 1 | 45197 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
BBH - Water Supply Systems to the Jetties | Item | Open | MCAP | 8410811M2205 | Maintenance Framework | 1916295 | Hernandez, Andres | East | 7. Closed | Defined | East | 5876 |  |  | 5876.02 | 5751 | 125 | Yellow |  |  |  | 5876 |  |  | 99000 |  |  | 99000 | Full | 99000 | 105743 |  | 105743 | No | Green | 2022-02-01 | 2021-12-14 | 2021-12-14 | 2022-07-31 | 2022-10-30 |  |  | 198.85 | 2770.95 | 2781.07 | 125.15 |  |  | 125 | Red | [11 empty] | 03/28/2023 - Project closed out. 2/8/23 project ready to close, no expecting more invoices AH 9-30-22 we had to re-class, we had charges from other projects AH 8-10-22, portable eye wash were purchased and installed, we still working on miscellaneous for water filtering AH 7-7-22 Eye was were received, stands and proper signs are being fabricated to install them. 6-8-22 fabrication on going.. AH 5/4/22 Filter were installed on all jetties faucets, portable stainless steel safety showers / eye wash ETA end of July AH 4/1/22 - New analysis for water filtration possibly cheaper solution than previously anticipated. To be updated once installation costs are finalized. Schedule adjusted to accommodate new planning. DC 3/8/22 waiting from final desing AH 2/8/22 working on the preliminary design, project will be assigned next month AH | 2023-03-28 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 5751 | 125 |  |  | 99867 |  | Orischak, Bob | Nash, Tom |  |  | 1 | 41045 |  | Guest, ProSight | Independent | Aqua | 2021-08-05 | Other Programs
BBH 2022 Loading Arm Locking Mechanism Upgrade | Item | Open | MCAP | 8410811M2215 | Maintenance Framework | 2004016 | Herry, Ryan | East | 3. Active | Emergent | East | 26073 | 14093 |  | 40166.18 | 40339 | -173 | Yellow | 43759 |  | 43759 | -3593 |  |  | 105000 |  |  | 105000 | Full | 105000 | 90734 | 14093 | 104827 | No | Green | 2022-09-01 | 2022-07-26 | 2022-07-26 | 2022-12-31 | 2023-06-30 |  |  | 0 | 0 | 0 | 26073.18 | 26246 | 26246 | -173 | Yellow |  |  |  | 14093 | [7 empty] | 05/01/2023 - Mechanical components shipped. Site preparation in progress. 04/03/2023- Safety components completed. Shipments expected upon final payment. 03/03/2023 - Forecast remains good. Components are expected March 20th, 2023 per PM. 2/2/2023 - There is a delay on shipping of the components. Operational date updated. 12.07.22 KB: Pending VAT reclass of $1600 11.07.22 KB: Still pending ($16k) reclass 10/10/22 KB - $16k pending reclass; it was coded to this project by mistake. Should be 8410811M2214 Tank 7401. | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 0 | 40166 |  |  | 64661 |  | Orischak, Bob | Nash, Tom |  |  | 1 | 44164 |  | Meitzler, Antoinette | Independent | Aqua | 2022-07-18 | Other Programs
BBH Boiler #2 Tube Scan 2023 | Item | Open | MEXP | 8410811E2308 | Maintenance Framework | 2095716 | Hernandez, Andres | East | 3. Active | Drawdown | Boilers |  | 85000 |  | 85000 | 85000 | 0 | Green |  | 85000 | 85000 | 0 |  |  | 85000 |  |  | 85000 | Full | 85000 |  | 85000 | 85000 | No | Green | 2023-05-01 | 2023-03-22 | 2023-03-22 | 2023-04-26 | 2023-06-02 | [12 empty] | 85000 | [8 empty] | 5/1/23 Testex, is performing the inspection, project will be ready in may AH Planning to mobilize contractors (Testex- GB insulators) in may, inspection and labor supports will be performed at the same time. AH | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 85000 |  |  |  |  | Stine, Carlton | Nash, Tom | N/A |  | 1 | 46823 |  | Orischak, Bob | JDE Child | Burnt Orange | 2023-03-21
BBH Boiler Unit 2 Tube re-roll 2023 | Item | Open | MEXP | 8410811E2311 | Maintenance Framework | 2120109 | Hernandez, Andres | East | 3. Active | Drawdown | Boilers |  | 66000 |  | 66000 |  | 66000 | Red |  |  |  | 66000 |  |  | 66000 |  |  | 66000 | Full | 66000 |  | 66000 | 66000 | No | Green | 2023-05-01 | 2023-05-04 | 2023-05-04 | 2023-06-10 | 2023-06-10 | [12 empty] | 30000 | 36000 | [7 empty] | 5-6-23 AFE was approved, the intention is to bring Cleaver brooks on may to reroll the tubes, commission the boiler in June. AH | 2023-05-06 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 66000 |  |  |  |  | Stine, Carlton | Nash, Tom | N/A |  | 1 | 47016 |  | Orischak, Bob | JDE Child | Burnt Orange | 2023-05-02
BBH DP8115 Caterpillar Engine Repairs 2023 | Item | Open | MEXP | 8410811E2310 | Maintenance Framework | 2111247 | Herry, Ryan | East | 3. Active | Drawdown | Rotating Equipment |  | 30000 |  | 30000 |  | 30000 | Red |  |  |  | 30000 |  |  | 30000 |  |  | 30000 | Full | 30000 |  | 30000 | 30000 | No | Green | 2023-05-01 | 2023-04-18 | 2023-04-18 | 2023-07-13 | 2023-07-13 | [12 empty] | 30000 | [8 empty] | 05/01/2023 - Caterpillar technicians expected to begin repairs May 3rd. | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 30000 |  |  |  |  | Posipanko, Dan | Nash, Tom | N/A |  | 1 | 46954 |  | Orischak, Bob | JDE Child | Burnt Orange | 2023-04-18
BBH Modify/Upgrade Main Gate Security | Item | Open | MCAP | 8410811M2115 | Exempt | 1837008 | Hernandez, Andres | East | 7. Closed | Defined | East | -1150 |  |  | -1149.55 | 6 | -1155 | Red |  |  |  | -1150 |  |  | 250000 |  |  | 250000 | Full | 250000 | 202068 |  | 202068 | No | Green | 2021-05-01 | 2021-04-14 | 2021-04-14 | 2021-07-31 | 2022-01-31 |  |  | 5.81 |  |  | -1155.36 |  |  | -1155 | Red | [11 empty] | 9/15/22 KB: Closed 4/4/22 Project completed.. 3/8/22Documents on approval process.AH 2/8/22 we submit all documents again waiting from port authority AH 12/6/21 waiting construction approvals from port authority. AH 12/1/2021 Operational date pushed back to end of january 2022 11/1/21waiting construction approvals from port authority. AH 10/6/21 waiting construction approvals from port authority. AH 9/6/21 We received all the drawings from the contractor, drawings were submitted to Port authority, we are waiting for the local authorities to approve the drawings. AH 8/3/21 We had delays on the structures calculations, this is holding the civil and the structures installation, we stared to work on ground slop and gates, foundation and structure drawing should be received this week. AH 7/1/21 We had delays on the structures calculations, this is holding civil and the rest of the project up. I should received final calculation by the end of the day, 7/9/21. AH 6/1/21 - Delay due to pending vendor design. PO for foundation fabrication to submit once designs are confirmed and approved per Andres Hernandez. DC 5/7/21 - Quotes received end of April from vendors. POs to be cut early May for work. DC | 2022-09-15 | Boyd, Kim |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 6 | -1155 |  |  | 9432 |  | Orischak, Bob | Nash, Tom |  |  | 1 | 25211 |  | Administrator, System | Independent | Aqua | 2017-08-23 | Other Programs
BBH Purchase Sparging Air Compressor | Item | Open | MCAP | 8410811M2114 | Exempt | 1820728 | Herry, Ryan | East | 6. Operational | Defined | East | 1621 |  | 1300 | 1620.99 | 1621 | 0 | Green |  |  |  | 1621 |  |  | 106000 |  |  | 106000 | Full | 106000 | 109733 | 1300 | 111033 | No | Green | 2021-05-01 | 2021-03-03 | 2021-03-03 | 2021-08-31 | 2021-07-31 |  |  |  | 1620.99 | [16 empty] | 1300 | 2/1/22 Project is ready to close BL 7/23/21 - Compressor Received and Mobilized on site. Additional Auxiliary Equipment Purchased. [RH] 6/08/21 - Compressor being shipped. 4/7/2021 - Pump expected end of May. 4/7/2021 - Purchase order issued March 9th 2021 | 2022-02-01 | Lienemann, Berend |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 1621 | 0 |  |  |  |  | Orischak, Bob | Nash, Tom |  |  | 1 | 38034 |  | Guest, ProSight | Independent | Aqua | 2020-08-14
BBH Tank 3002 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | 8410811M2219 | Maintenance Framework | 2043731 | Campbell, Jamie | East | 3. Active | Defined | Tanks | 778341 | 270743 | 10720 | 1049083.75 | 994445 | 54638 | Yellow | 928950 |  | 928950 | 120134 |  |  | 125000 | 1111764 |  | 1236764 | Phase | 1236764 | 1009939 | 281463 | 1291402 | No | Green | 2022-12-01 | 2022-11-03 | 2022-11-03 | 2023-02-20 | 2023-07-31 |  |  | 18480.13 | 108961.95 | 343260.27 | 307638.4 | 250000 | 250000 | 57638 | Red |  | WorkAhead of Schedule | 90000 | 80000 | 100743 | [5 empty] | 10720 | 05/01/2023 - Tank Mechanical repairs and hydro-test are completed. Tank coating approximately 90% completed. Tank returned to service 5/1/23. Tank temperature probe outstanding, along with site clean-up and regrade. 04/03/2023 - Large April forecast is due to the speed the project is moving. Tank mechanical repairs are ahead of schedule. The following tank upgrades completed: New EFR center deck, bottom patches, Internal water draw nozzles and sumps, independent radar & temperature poles and pontoons repairs, Stripping suction modification and foam system to be completed. 03/8/2023 - Large forecast in March is result mechanical repairs are expected to be 90% complete and the coating material will be on site. 03/02/2023 - Tank repairs are 50% completed (New water draw nozzle and sumps installed, EFR center deck removed, and new steel plates installed and are being welded). 2/3/2023 Tank 3002 2nd phase AFE is currently being routed for approval. Mechanical proposal have been received, Tampa tank is the lowest bidder, by aprox. $4K. However, there schedule to complete the project is twice QSL. I plan to award project to QSL once AFE is approved. 1/9/2023 Tank 3002 was over the forecasted amount due to VCI being reclassed to the project. Tank cleaning and inspection are completed. Inspection identified extensive EFR repairs and minor bottom repairs along with several other items. 12/2/2022Tank cleaning was delayed due to operational activities at the tank during November. Tank cleaning is currently in progress. HMT will start the inspection on December 12, 2022. | 2023-05-05 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 470702 | 477638 | 100743 |  | 231599 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44774 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
BBH Tank 8051 - OOS API 653 + Seal Insp & Refurb | Item | Open | MEXP | 8410811E2304 | Maintenance Framework |  | Campbell, Jamie | East | 8. Canceled | Defined | Tanks |  |  |  | 0 |  | 0 | Green | 600000 |  | 600000 | -600000 |  |  | 610400 |  |  |  | Full | 610400 |  |  |  | No | Green |  |  |  | 2023-12-31 | 2023-06-30 | [21 empty] | 3/6/23-CES-Forecast removed per 2/13 note. Funding transferred to 8008. 2/13/23 - CES-Per commercial, plan to push this tank to 2025 (updated API 653 compliance date) and transfer funding over to tank 8008. 1/27/23-CES-Per conversation with commercial today, forecast outage for 4Q. 10/5/22-CES-Per commercial, plan to clean and idle for 2023. Reducing budget to $600,000. | 2023-03-06 | Coverley, Colleen |  | East | Pipelines and Terminals | Tank Integrity | Tank Integrity | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 0 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44775 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
BBH Tank 8052 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | 8410811M2302 | Maintenance Framework |  | Campbell, Jamie | East | 8. Canceled | Defined | Tanks |  |  |  | 0 |  | 0 | Green | 600000 |  | 600000 | -600000 |  |  | 654000 |  |  |  | Full | 654000 |  |  |  | No | Green |  |  |  | 2023-12-31 | 2023-09-30 | [21 empty] | 3/6/23-CES-Forecast removed and project cancelled. Plan to push project to 2025 and for completion of 8008 this year. 2/13/23 - CES-Per commercial, plan to push this tank to 2025 (updated API 653 compliance date) and transfer funding over to tank 8008. 1/27/23-CES-Per conversation 10/5/22-CES-Per commercial, plan to clean and idle tank for 2023. Forecast reduced to $600,000. | 2023-03-06 |  |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 0 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44776 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
BBH Tank 8122 - OOS API 653 Insp | Item | Open | MCAP | 8410811M2303 | Maintenance Framework | 2053010 | Campbell, Jamie | East | 3. Active | Defined | Tanks |  | 380000 |  | 380000 | 380000 | 0 | Green | 356473 |  | 356473 | 23527 |  |  | 380000 |  |  | 380000 | Full | 380000 |  | 380000 | 380000 | No | Green | 2023-05-01 | 2022-12-21 | 2022-12-21 | 2023-12-31 | 2023-08-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 50000 | 75000 | 100000 | 155000 | [5 empty] | 05/01/2023 - Due to Operational requirement, BBH Operations would like T-8122 inspection & repairs to start in May 2023. Preparing to take tank out of service. 03/08/23 - Due to Operational requirement, BBH Operations would like T-8122 inspection & repairs to start in May 2023. 03/02/2023 - At this current time, the Q2 forecast stands. 2/3/2023 - Project is scheduled to start 2nd quarter. Currently in communication with Operations on best time to remove from service, since this tank provides fuel to crude & fuel oil pumps. 2/2/2023 - Forecast updated to reflect an EAC on budget. | 2023-05-05 |  |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 125000 | 255000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44778 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
BBH Tank 8006 VCI Installation | Item | Open | MCAP | 8410811M2211 | Maintenance Framework | 1947666 | Campbell, Jamie | East | 6. Operational | Drawdown | Cathodic Protection | 7 |  |  | 6.75 | 7 | 0 | Green |  |  |  | 7 |  |  | 103000 |  |  | 103000 | Full | 103000 | 102865 |  | 102865 | No | Green | 2022-02-01 | 2022-02-23 | 2022-02-23 | 2022-04-30 | 2022-03-31 |  |  |  |  | 6.75 | [18 empty] | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 7 | 0 |  |  | 102858 |  | Geib, Rob | Geib, Robert |  |  | 1 | 42983 |  | Guest, ProSight | Independent | Aqua | 2022-02-16 | Other Programs
BBH Tank 8008 | Item | Open | MEXP | 8410811E2215 | Maintenance Framework | 2014081 | Campbell, Jamie | East | 3. Active | Drawdown | Tanks | 253470 | 439810 |  | 693280 | 750000 | -56720 | Yellow |  | 725000 | 725000 | -31720 |  |  | 339000 | 725000 |  | 1064000 | Full | 1064000 | 624190 | 439810 | 1064000 | No | Green | 2022-09-01 | 2022-08-31 | 2022-08-31 | 2022-08-31 | 2023-06-30 | [5 empty] | 253470 | 200000 | 200000 | 53470 | Red |  | WorkAhead of Schedule | 250000 | 150000 | 39810 | [6 empty] | 05/01/2023 - 4/3/2023 - Large forecast amount reflects the speed the project will be executed. Tank AFE fully approved late March, bids for mechanical repairs received. Tank being awarded to QSL. QSL is waiting on PO to start the upgrades. 3/6/23-CES-Forecast updated to match Phase II (Full) AFE. Funding transferred from tank 8051 and Tank Maintenance drawdown. 03/02/23 - Tank Phase II AFE is currently being routed for appprovals. Tank repairs are schedule to start the second quarter of 2023 03/02/2023 - Tank got recent approval to return to active phase. 2/13/23-CES-Per Commercial, This tank will need to be returned to service. Plan to transfer the budget from tanks 8051 and 8052 for up to $1.2MM. 11/1/22 KB - Reclass completed for the expense project. Any additional work for Tank 8008 will be budgeted for 2023. 10/7/22 KB: Reclass was re-accrued then hit the actuals for Sept. $741k is a double dip. 09/07/22 KB: Accrual submitted for $371k to cover reclassed items. Tank cleaning and inspection is completed. | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Tank Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 653470 | 39810 |  | 370720 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44656 |  | Meitzler, Antoinette | Independent | Aqua | 2022-08-17 | Int - Tanks
BBH Tank 8061 IFR Investigation and Repair | Item | Open | MEXP | 8410811E2305 | Maintenance Framework | 2084481 | Campbell, Jamie | East | 6. Operational | Drawdown | Tanks | 116378 |  |  | 116378 | 108672 | 7706 | Yellow |  |  |  | 116378 |  |  | 97000 |  |  | 97000 | Full | 97000 | 116378 |  | 116378 | No | Green | 2023-02-01 | 2023-02-14 | 2023-02-14 | 2023-03-31 | 2023-04-12 |  |  |  | 17487 | 71185.4 | 27705.6 | 20000 | 20000 | 7706 | Red | [11 empty] | 5/1/2023 - Project cost over run due to addittional engineering requests and tank shell scanning. 4/3/2023 - Tank IFR repairs completed and tank was returned to Operations on March 23, 2023. On April 3, the tank was return to Projects to make a minor modification to the IFR shoe plate, as request by the engineer David Rosenkrantz. Modification will be completed by April 12,2023. 03/8/23 - Commercial is requesting the Tank to be returned to service April 1st to meet client needs, resulting in large spend for March. 03/03/23 - Tank cleaning and internal Inspection is completed. A waiting David Rosentrantz inspection repair. Tampa Tank have mobilized at the tank to start IFR repairs. 03/02/2023 - Approximately additional $60K will be needed to complete repairs. Forecast will be accurately update prior to locking following communication with Carlton. 2/3/2023 Forecast adjusted as per Project Manager. | 2023-05-05 | Coverley, Colleen |  | East | Pipelines and Terminals | Tank Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 88672 | 27706 |  |  |  |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 46561 |  | Stine, Carlton | JDE Child | Burnt Orange | 2023-01-31 | Int - Tanks
BBH Tank 8062 Corrosion Probe Installation | Item | Open | MCAP | 8410811M2217 | Maintenance Framework | 2013058 | Campbell, Jamie | East | 7. Closed | Drawdown | Cathodic Protection | 1564 |  |  | 1563.71 | 1564 | 0 | Green |  |  |  | 1564 |  |  | 10000 |  |  | 10000 | Full | 10000 | 17626 |  | 17626 | No | Green | 2022-09-01 | 2022-08-22 | 2022-08-22 | 2022-09-30 | 2022-09-30 |  |  | 1361.76 | 201.95 | [17 empty] | 03/28/2023 - Project closed out. 03/02/2023 - Project completed and should be cosed. 10/4/2022 Probe installation and concrete pad liner repairs completed by Flawless. Tank probe installation is in progress. Schedule to be completed the end of the month. | 2023-03-28 | Schultz, Amy |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 1564 | 0 |  |  | 16062 |  | Geib, Rob | Geib, Robert |  |  | 1 | 44639 |  | Guest, ProSight | Independent | Aqua | 2022-08-16 | Int - Planned Corr & FI
BBH Vapor Corrosion Inhibitor 2023 Installation and Replenishment | Item | Open | MCAP | 8410811M2305 | Maintenance Framework | 2076678 | Campbell, Jamie | East | 3. Active | Defined | Cathodic Protection | 137684 | 374024 |  | 511708 | 511999 | -291 | Yellow | 480000 |  | 480000 | 31708 |  |  | 512000 |  |  | 512000 | Full | 512000 | 137684 | 374024 | 511708 | No | Green | 2023-03-01 | 2023-01-27 | 2023-01-27 | 2023-12-31 | 2023-11-30 |  |  |  |  | 122240 | 15444 | 15735 | 15735 | -291 | Yellow |  |  | 20439 | 121676 | 15735 | 20439 | 159561 | 15735 | 20439 |  |  | 05/01/2023 - VCI replenishment and probe box modification in progress. 4/3/2023 - Large forecast amount in June is for the second batch of VCI material. Project Accrual for March full forecast. First batch of VCI material arrived at terminal on March 30, 2023. Flawless is preparing to replenish tanks and modify probe boxes. VCI material was ordered. First delivery is scheduled to arrive terminal by 03/27/2023. Resulting in a large forecast for March. | 2023-05-05 |  |  | East | Pipelines and Terminals | Integrity |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 122240 | 157559 | 195735 | 36174 |  |  | Geib, Rob | Stine, Carlton |  |  | 1 | 45346 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
BBH Water Line Connection for corroded pipe | Item | Open | MEXP | 8410811E2209 | Maintenance Framework |  | Herry, Ryan | East | 6. Operational | Drawdown | East | 12 |  |  | 12 | 12 | 0 | Green |  |  |  | 12 |  |  | 35000 |  |  | 35000 | Full | 35000 | 33289 |  | 33289 | No | Green | 2022-02-01 | 2022-02-07 | 2022-02-07 | 2022-03-31 | 2022-03-31 |  |  | 12 | [18 empty] | 3/9/2022 Piping has been installed, making final connection to meter 2-8-22 All permits are currently being obtained [R. Herry] | 2022-03-09 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 12 | 0 |  |  | 33277 |  | Orischak, Bob | Nash, Tom | N/A |  | 1 | 42872 |  | Orischak, Bob | JDE Child | Burnt Orange | 2022-02-07 | Other Programs
BETBO Air to ground coating phase 2 | Item | Open | MCAP | BETBO00M2301 | Maintenance Framework | 2085571 | Norton, Bill | East | 3. Active | Defined | Atmospheric Corrosion |  | 45000 |  | 45000 | 45000 | 0 | Green | 45000 |  | 45000 | 0 |  |  | 43680 |  |  | 43680 | Full | 43680 |  | 45000 | 45000 | No | Green | 2023-10-01 | 2023-02-21 | 2023-02-21 | 2023-11-01 | 2023-11-30 | [17 empty] | 45000 | [5 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Terminals | BETBO - BET BUFFALO TERMINAL |  |  | 0 |  | 45000 |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44345 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
BETQB QB-07 Third Plant Rectifier Replacement | Item | Open | MCAP | BETQB00M2205 | Maintenance Framework | 1971364 | Gable, Rob | East | 7. Closed | Drawdown | Cathodic Protection | 479 |  |  | 479.15 | 479 | 0 | Green |  |  |  | 479 |  |  | 32000 |  |  | 32000 | Full | 32000 | 21756 |  | 21756 | No | Green | 2022-04-01 | 2022-04-15 | 2022-04-15 | 2022-10-30 | 2022-12-30 |  |  | 479.15 | [18 empty] | 2/16/2023 - Closed WO/PO, set OPPM project status to 'Closed'. 2/2/2023 RAG - Ready to Close. No further invoices expected. 1/4/2023 RAG - Work completed for less then expected. 12/2/2022 RAG - Final work to be performed in Dec. 11/3/2022 RAG - Final work to be performed in Dec. 10/4/2022 RAG - Rectifier installed. RMU's to be purchased to complete project. Some funding returned as not needed. 9/6/2022 RAG - Rectifier arrived ahead of schedule. Installation scheduled for next week. 8/2/2022 RAG - Rectifier taking longer than expected to ship. 7/1/2022 RAG - Rectifier to be delivered during last week of July. 5/2/2022 RAG - New project, PO issued for rectifier, no ship date provided. | 2023-02-16 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Baltimore | BETQB - BET BALTIMORE TERMINAL |  | 479 | 0 |  |  | 21277 |  | Geib, Rob | Geib, Robert |  |  | 1 | 43373 |  | Meitzler, Antoinette | Independent | Aqua | 2022-04-07 | Int - Planned Corr & FI
BETRC Air to ground Coating Phase 1 | Item | Open | MCAP | BETRC00M2303 | Maintenance Framework | 2085572 | Norton, Bill | East | 3. Active |  | Atmospheric Corrosion |  | 45000 |  | 45000 | 45000 | 0 | Green | 45000 |  | 45000 | 0 |  |  | 43680 |  |  | 43680 | Full | 43680 |  | 45000 | 45000 | No | Green | 2023-09-01 | 2023-02-21 | 2023-02-21 | 2023-11-01 | 2023-11-30 | [16 empty] | 45000 | [6 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Terminals | BETRC - BET ROCHESTER N TERMINAL AGWAY |  |  | 0 | 45000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44337 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
Booth Butane Relief Repairs Per PSM 2022 | Item | Open | MCAP | BH00000M2304 | Maintenance Framework | 2093301 | Pepe, David | East | 3. Active |  | East | 35971 | 80000 |  | 115970.92 | 150719 | -34748 | Red | 85000 | 65000 | 150000 | -34029 |  |  | 148292 |  |  | 148292 | Full | 148292 | 35971 | 80000 | 115971 | No | Green | 2023-03-01 | 2023-03-01 | 2023-03-01 | 2023-04-30 | 2023-04-30 |  |  |  |  | 718.62 | 35252.3 | 130000 | 130000 | -94748 | Red |  |  | 50000 | 20000 | 10000 | [6 empty] | 5/5/2023-Variance due to Operations needing to start blending earlier and the contractor has to do the construction in stages. Expecting it to be done by end of May. 4/4/2023- -- Variance due to material not yet arriving. Expecting to arrive in wk of 4/10. 2023 03 01 DJP Submitted AFE and had kick off meeting with the local team and PSM to explain the project. 7.19.22 RLO added to 2023 list per Joe Votta as a PSM requirement | 2023-05-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Booth | BH - BOOTH STATION |  | 719 | 105252 | 10000 |  |  |  | Orischak, Bob | Orischak, Bob |  |  | 1 | 44090 |  | Guest, ProSight | Independent | Aqua | 2022-07-07 | Other Programs
Booth Incoming Gasoline Splitter Valve Replacement | Item | Open | MCAP | BH00000M2207 | Maintenance Framework | 2021900 | Keeth, Ed | East | 6. Operational | Defined | Valves | 98814 |  |  | 98814.46 | 56789 | 42025 | Red |  | 140945 | 140945 | -42131 |  |  | 216000 |  |  | 216000 | Full | 216000 | 105077 |  | 105077 | No | Green | 2022-09-01 | 2022-09-06 | 2022-09-06 | 2022-11-30 | 2023-02-28 |  |  | 225.11 | 16406.99 | 40156.92 | 42025.44 |  |  | 42025 | Red | [11 empty] | 4/5/2023-Savings due to not having to replace the actuator on the valve. 3/2/22 Parts are in accured 15k for them. Work will be taking place the week of March 27th. EK5507 2/3/2023-Parts are still not in. Ed Keeth will reach out to vendor. 1/5/23 Have reached out to vendor on status of parts and timing. Misc material ordered by mechanic at Booth. Variance due to parts not coming in Dec. EK5507 12/5/22 Contractor(Allied) has informed that parts are not ready from Cameron. Project will slip into 2023 as installation will not happen in 2022. EK5507 11/3/2022-Ed Keeth will do. Contractor still fabricating parts, they should be ready in Nov. Executing installation in Dec. 10/5/22 Forecast adusted as vendor as was advised by vendor that parts will be ready by the end of Nov and will look to do the rebuild in Dec. EK5507 9/6/22 AFE approved on 9/6/22, Ed Keeth will cut the PO to make the parts and install. . ek5507 8/3/22 Obtained quote for rebuild of valve just waiting on quote for actuator and will have full afe ready for submittal week of aug 8th. ek5507 5/4/22 Currently scoping out and may possibly look to do a rebuild of the valve. The valve is currently welded in and will possibly require a deviation to cut out since this will require the isolation plug/purge to weld in flanges. EK5507 4/16/18 - Deferring this project until first quarter of 2019 as per request from PMO. 3/27/18 AFE will be submitted in April, waiting on one more contractor quote at this time. EK 5507 | 2023-04-05 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Booth | BH - BOOTH STATION |  | 56789 | 42025 |  |  | 6262 |  | Oey, Alex | Oey, Alexander | N/A |  | 1 | 24965 |  | Guest, ProSight | Independent | Aqua | 2017-08-10 | Other Programs
Booth L733 Prover Connections | Item | Open | MCAP | BH00000M2301 | Maintenance Framework | 2073881 | Pepe, David | East | 3. Active | Defined | Measurement & Quality Control | 5822 | 105000 |  | 110822.07 | 110822 | 0 | Green | 115000 |  | 115000 | -4178 |  |  | 8585 |  |  | 8585 | Phase | 8585 | 5822 | 105000 | 110822 | No | Green | 2023-02-01 | 2023-01-01 | 2023-01-01 | 2023-12-31 | 2023-05-31 |  |  |  | 6015.38 | -193.31 | [12 empty] | 105000 |  |  |  | 2023/05/04 - DJP - Looking at a project to install a common small volume prover for the L733 and L734 as the losses on the line provide a favorable IRR and NPV. Looking to discuss with Dave Clark and TJ Zeth during the next week. 2023/03/01 - DJP - Midstream has provided the initial design and have been reviewed withy Booth operations and M&QC. Final AFE will be developed in March along with the project execution schedule. | 2023-05-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Booth | BH - BOOTH STATION |  | 5822 | 0 |  | 105000 |  |  | Hopkins, Christa | Hopkins, Christa | N/A |  | 1 | 24849 |  | Guest, ProSight | Independent | Aqua | 2017-08-07 | Other Programs
Booth Maintenence and Butler Building Painting and Roof Repair | Item | Open | MCAP | BH00000M2206 | Maintenance Framework | 1979712 | Keeth, Ed | East | 7. Closed | Defined | East | 24646 |  |  | 24645.83 | 24543 | 103 | Yellow |  |  |  | 24646 |  |  | 73000 |  |  | 73000 | Full | 73000 | 74988 |  | 74988 | No | Green | 2022-06-01 | 2022-05-04 | 2022-05-04 | 2022-08-31 | 2022-12-31 |  |  | 954.33 | 21310 | 2278.95 | 102.55 |  |  | 103 | Red | [11 empty] | 4/28/2023 - Closed WO/PO (Barr-None $10,900 C1-231127), and set OPPM project status to 'Closed'. MCS. Can close ASAP. 4/4/23 All costs have hit the project. Project can be closed out. EK5507 3/3/22 Accrual made for Barr None, awaiting final invoice. EK5507 2/3/23 - , awaiting 2 invoice. Accrual made for Aspach for concrete work. Accural missed for Barr none. EK5507 12/5/2022-Delayed due to issues with contractor's ISNETWorld (Savoy).11/3/2022-Delayed due to contractor ISN grade, looking for other contractors. Ed Keeth will do. 9/6/22 Barr none to start painting in Sept. ek5507 8/3/2022-On-track for Ed Keeth to finish by the end of the year. 7/6/22 4k variance due to asset team order new windows for the building. ek5507 6/2 22 AFE approved and getting quotes. ek5507 5/4/22 AFE submitted ek5507 4/4/22 Currently working with supply chain to obtain quotes for the roof and painting. One quote for the roof and one quote for the painting have been obtained but will require more 2 more quotes given the dollar amount We are also limited on roofing vendor due to requirements being in isnet and a buckeye approved vendor. ek5507 3/2/2022-Waiting on quotes. 2/3/22 Currently obtaining quotes for painting and roof. ek5507 | 2023-04-28 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Booth | BH - BOOTH STATION |  | 24543 | 103 |  |  | 50342 |  | Orischak, Bob | Tench, David | N/A |  | 1 | 20748 |  | Guest, ProSight | Independent | Aqua | 2016-08-30 | Other Programs
Booth Station (BH) Tank 13 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | BH00000M2302 | Maintenance Framework | 2086163 | Yoder, Michael | East | 3. Active | Defined | Tanks | 367151 | 350000 |  | 717150.96 | 975019 | -257868 | Red | 1183432 |  | 1183432 | -466281 |  |  | 240778 |  |  | 240778 | Phase | 240778 | 367151 | 350000 | 717151 | No | Green | 2023-03-01 | 2023-02-24 | 2023-02-24 | 2023-12-31 | 2023-06-30 |  |  |  |  | 111586.7 | 255564.26 | 250000 | 250000 | 5564 | Yellow |  |  | 120000 | 125000 | 105000 | [6 empty] | 5/1/23 - Sketch sheet replacement and seal replacement in progress. Preparing phase 2 AFE for submission. 4/3/23 - Variance due to cleaning complete in March. Inspection in progress. Reduced April forecast since it appears tank bottom can be saved. Plan to further adjust forecast once final repair scope is determined. 2/9/23 - Updated forecast based on early-March cleaning. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Booth | BH - BOOTH STATION |  | 111587 | 500564 | 105000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44785 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Booth Station (BH) Tank 14 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | BH00000M2303 | Maintenance Framework | 2086164 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 574017 |  | 574017 | 574017 | 0 | Green | 574017 |  | 574017 | 0 |  |  | 240778 |  |  | 240778 | Phase | 240778 |  | 574017 | 574017 | No | Green | 2023-10-01 | 2023-02-24 | 2023-02-24 | 2023-12-31 | 2023-12-31 | [17 empty] | 151004 | 302009 | 121004 |  |  |  | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Booth | BH - BOOTH STATION |  |  | 0 |  | 574017 |  |  | Stine, Carlton |  |  |  | 1 | 44786 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Booth Station (BH) Tank 15 – OOS Corr Insp & Refurb | Item | Open | MCAP | BH00000M2201 | Maintenance Framework | 1937275 | Yoder, Michael | East | 6. Operational | Defined | Tanks | 232711 |  |  | 232710.97 | 223577 | 9134 | Yellow |  |  |  | 232711 |  |  | 394000 | 842000 |  | 1236000 | Full | 1236000 | 1267866 |  | 1267866 | No | Green | 2022-03-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2023-03-31 |  |  | 45000.18 | 147587.28 | 30989.42 | 9134.09 |  |  | 9134 | Red | [11 empty] | 5/2/2023 - April variance due to internal labor. 4/4/2023 - Tank buttoned up and awaiting refill. Small variance due to internal labor. Phase 2 AFE approved. 3/1/2023 - Tank painting complete. Plan to button up mid-March. Variance due to completing painting in February. Phase 2 AFE submitted for approval. 2/1/2023 - Bottom install complete. Seal repairs in progress. Tank painting to start 2/6. Preparing phase 2 AFE for submission. 1/3/2023 - Bottom install in progress. Variance due to additional rim angle work required. Added to January forecast. Preparing phase 2 AFE for submission. 12/1/2022 - Bottom install in progress. Preparing phase 2 AFE for submission. Added 115k to December forecast for outstanding commitments projected to hit before end of year. Added 100k to 2023 Q1 forecast to paint tank. 11/1/2022 - Inspection complete. Bottom needs replacement. Bottom install in progress. Preparing phase 2 AFE for submission. 10/4/2022 - Tank isolated and cleaned. Inspection blast in progress. 9/1/2022 - OOS still planned for around 9/15. 8/1/2022 - OOS still planned for around 9/15. 7/5/2022 - On target for September start. 4/3/22 - March variance due to internal labor. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Booth | BH - BOOTH STATION |  | 223577 | 9134 |  |  | 1035155 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41239 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Booth Station (BH) Tank 16 – OOS Corr Insp & Refurb | Item | Open | MCAP | BH00000M2202 | Maintenance Framework | 1937276 | Yoder, Michael | East | 7. Closed | Defined | Tanks | 217 |  | 0 | 217.03 | 217 | 0 | Green |  |  |  | 217 |  |  | 263000 |  |  | 263000 | Full | 263000 | 280791 | 0 | 280791 | No | Green | 2022-02-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-08-31 |  |  | 217.03 | [17 empty] | 0 | 3/28/2023 - Closed WO/PO, and set OPPM status to 'Closed'. MCS 2/1/23 - Keep open for one more month then close. 1/4/23 - Variance due to seal inspection once roof was re-floated. 12/2/22 - Variance due to internal labor and leg setting charges. 10/4/22 - Variance due to internal labor. 9/1/22 - Tank ready for RTS. 8/1/22 - Temp probe shipped. Plan to button up and RTS by end of month. 7/1/22 - Awaiting install of new temp string prior to RTS. All other work complete. 6/1/22 - Awaiting install of new temp string prior to RTS. All other work complete. 5/3/22 - April variance due to completing tank work early and saving on inspector costs. Tank to be returned to service once new temperature string install. 4/3/22 - March variance due to EAC less than budgeted. Updated forecast. Bottom repairs complete. Liner and EFR coating complete. Strapping and mod inspection week of 4/4. 3/2/22 - Tank cleaned & inspected. Repairs to start week of 3/7. 2/1/22 - Preparing to take tank OOS. | 2023-03-28 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Booth | BH - BOOTH STATION |  | 217 | 0 |  |  | 280574 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41240 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Booth Station Manifold PLC Replacements | Item | Open | MCAP | BH00000M2104 | Exempt | 1845955 | Zimmerman, Steve | East | 3. Active | Defined | Instrumentation & Controls | 10961 | 67000 |  | 77961.22 | 75920 | 2041 | Yellow |  |  |  | 77961 |  |  | 517000 |  |  | 517000 | Full | 517000 | 432337 | 67000 | 499337 | No | Green | 2021-05-01 | 2021-05-05 | 2021-05-05 | 2021-12-31 | 2023-08-31 |  |  | 2083.23 | 4615.05 | 2221.89 | 2041.05 |  |  | 2041 | Red |  |  |  |  | 40000 | 27000 | [5 empty] | 2023-05-03 SRZ: Have scheduled pre-startup site visit for 5/9. Anticipate we will be able to schedule the startup of the remaining PLC after this visit. Startup likely to occur in June/July time frame. 2023-04-04 SRZ: Competing priorities have kept us from scheduling the startup for the Inbound system, but we are anticipating that we should be able to get things in order to complete the startup in the May/June timeframe. 2023-03-02 SRZ: We have now received the bulk of the material we were waiting on. Working on scheduling startup with pipeline/technician/integrator schedules. 2023-02-02 SRZ: Still awaiting delivery of some key material. Startup will be delayed to March at the earliest. 2023-01-03 SRZ: Some critical material is still delayed. Anticipating startup will be moved to late February after final material arrives. 2022-12-01 SRZ: Still waiting on some material, anticipating final startup in January 2023. 2022-11-02 SRZ: Still working on acquiring material for the final startup. At this point will wind up needing to carry some work into January 2023 due to supply chain delays. Have shifted some spend to January as a result. 2022-10-04 SRZ: Startup of the outbound manifold PLC has been completed. During prep work for the upcoming Inbound Manifold PLC replacement it was discovered that we are short several critical PLC modules. Arseal is working on tracking down the missing parts. This may present a problem with scheduling the inbound startup given recent supply chain issues. 2022-09-01 SRZ: Startup of the outbound systems is still on track for the week of 9/12. Once the outbound is complete, will begin scheduling of the inbound manifold. Still anticipate having all work complete prior to the end of 2022. [Most likely operational by Nov 30th, with a few spends in Dec, per SZ] 2022-08-02 SRZ: Startup has been postponed till week of September 12th. The nitrogen purge that we are coordinating with has slipped until that week. 2022-07-05 SRZ: Initial startup has been scheduled for the week of August 22nd. There will be a week long shutdown on the 724 system scheduled for a nitrogen purge and cutout. We will plan to start up the Outbound Manifold PLC that same week to take advantage of the down time. 2022-06-02 SRZ: Startup of remaining portions of the project are still on hold as a result of competing priorities. 2022-05-02 SRZ:Startup of remaining portions of the project have been delayed temporarily as a result of competing priorities. 2022-04-04 SRZ: Conducted startup of meteringin end of March. Working on scheduling the startup for the manifold PLC's, likely in May. Have reduced overall forecast to $450k total based on current expected startup costs. 2022-03-02 SRZ: Some delays in startup scheduling. Hope to begin startup ofthe new systems in late March. 2022-02-02 SRZ: Field work complete. Working on schedulingstartups. 2022-01-04 SRZ: Contractor was able to get most of the material for the field work purchased and invoiced in December. Majority of field construction has been completed. Startup will occur in Q1 2022. 2021-12-02 SRZ: PO cut to electrical contractor. We are seeing some material delays which may stretch construction out longer than originally hoped.2021-11-02 SRZ: Walked down field construction with contractor. Awaiting quote. Material times and soft dig availability are both going to be challenges based on walk down.2021-10-01 SRZ: Working on setting up walk down with contractor to get field construction moving.2021-09-02 SRZ: Final design nearly complete. Scheduling walk down with contractors to get bids for field construction. Lead times on material are starting to become an issue. Most material is already in hand, but are seeing extended lead times on some components needed for the incoming mainline block valves where we will be installing a new remote I/O cabinet.2021-08-02 SRZ: Engineering design continues. Working on setting up a walk down with an electrical contractor for the fiber installation.2021-07-02 SRZ: Engineering design is well underway.2021-06-02 SRZ: PO has been cut to Arseal and they have begun work on the engineering & programming.2021-05-04 SRZ: AFE has been submitted. This project will be combined with the Outbound PLC project to create a new combined project.2021-04-05 SRZ: AFE will besubmitted this week. iAutomation has already begun prepping for the project and is ready to start work as soon as AFE is approvedand PO is cut.2021-03-02 SRZ: Shifted forecast out in anticipation of project PM changing.2021-02-02 SRZ: Working on final AFE prior to submitting.2021-01-05 SRZ:Project status changed to pending AFE. Project is part of2021 MCAP budget. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Booth | BH - BOOTH STATION |  | 8920 | 2041 | 67000 |  | 183015 |  | Forsey, Frank | Forehand, Adam | N/A |  | 1 | 29582 |  | Guest, ProSight | Independent | Aqua | 2018-06-15 | Other Programs
Booth Station Pump PLC Replacement | Item | Open | MCAP | BH00000M2205 | Maintenance Framework | 1971391 | Mohr, David | East | 3. Active | Defined | Instrumentation & Controls | 39773 | 240000 |  | 279773.49 | 250044 | 29729 | Red | 240000 |  | 240000 | 39773 |  |  | 290000 |  |  | 290000 | Full | 290000 | 84071 | 240000 | 324071 | Yes | Red | 2022-06-01 | 2022-04-15 | 2022-04-15 | 2022-12-31 | 2023-08-31 |  |  | 3725.81 | 5802.82 | 515.77 | 29729.09 |  |  | 29729 | Red |  |  |  |  | 100000 | 140000 | [5 empty] | 4/1/2023 Material not anticipated prior to June 2023. DRM 1/3/2023 will be contacting M&M electrical to start making wiring preperations. 12/2/2022- Continuing work on engineering and programming, the install and material will be in 2023. 7/5/2022 Updated forecast to spread across the end of the year.DRM 6/2/2022Moved $240K in forecast to March 2023 due to supply chain issues with material. DRM6/2/2022 Met with Arseal last week. Material may be delayed until 2023. DRM 4/1/2022 DRM Received quote back from Arseal and AFE to follow this week. 3/1/2022 DRM requested quote from Arseal to complete the AFE. | 2023-04-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Booth | BH - BOOTH STATION |  | 10044 | 29729 | 240000 |  | 44297 |  | Forsey, Frank | Tench, David | N/A |  | 1 | 29605 |  | Guest, ProSight | Independent | Aqua | 2018-06-15 | Other Programs
Brewerton Priority 3 API 570 Refurbishments | Item | Open | MCAP |  | Maintenance Framework |  | Pepe, David | East | 1. Proposed |  | Facility Integrity |  | 98000 |  | 98000 | 98000 | 0 | Green | 98000 |  | 98000 | 0 | [9 empty] | 98000 | 98000 | No | Green | 2023-07-01 |  |  |  | 2023-09-30 | [14 empty] | 50000 | 48000 | [9 empty] | East | Pipelines and Terminals | Integrity |  | Auburn Terminals | BETBW - BET BREWERTON TERMINAL |  |  | 0 | 98000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45049 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Brewerton Terminal - Tank Alarm Replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Orischak, Bob | East | 1. Proposed |  | Instrumentation & Controls |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 | [9 empty] | 50000 | 50000 | No | Green | 2023-06-01 |  |  |  | 2023-08-31 | [13 empty] | 10000 | 20000 | 20000 | [9 empty] | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BETBW - BET BREWERTON TERMINAL |  |  | 10000 | 40000 |  |  |  | Forsey, Frank |  |  |  | 1 | 37630 |  | Guest, ProSight | Independent | Aqua | 2020-08-11 | Other Programs
Brewerton Terminal Barge Dock Line Removals | Item | Open | MEXP | BETBW00E2202 | Maintenance Framework | 2022481 | Wing, Hunter | East | 7. Closed | Defined | Facility Integrity | 21966 |  |  | 21966.34 | 21966 | 0 | Green |  |  |  | 21966 |  |  | 160000 |  |  | 160000 | Full | 160000 | 96966 |  | 96966 | No | Green | 2022-12-01 | 2022-09-12 | 2022-09-12 | 2022-12-31 | 2022-12-31 |  |  | 20003.98 | 1962.36 | [17 empty] | 3/14/2023 - Closed WO/PO, and set OPPM status to 'Closed'. MCS 3.02.23-Can close. 2/2/2023-Hold off before closing. 1/5/2023 - HW - Scope of work completed on 12/29/2022, awaiting invoices. 12/6/2022 - HW - Project expected to start the week of 12/12 after the NY Cannel Permit is obtained. Forecast has been updated to match expected spend. 11/8/2022 - HJW - Project reassigned to Hunter. Quotes received from two contractors, and waiting on one more to quote. Envirospec continues with permitting progress. Estimated to start construction between 11/28 - 12/16 and expected to take a week to complete. 10/3/2022 RLO Had 2 companies look at this just waiting for quotes back. 9/1/2022 RLO - Project will need more funding. Working with Marine Program Manager to find additional funds. Will know more next month. 8/3/22 Project will need to be transitioned to another pm. ek5507 7/6/22 Permitting estimate obtained, construction estimated obtained also. Will need to be bid out as estimation came in higher then budgeted amount. Project will need to be transitioned to new PM. ek5507 6/6/22 Permitting Matrix obtained waiting on full quote for permitting along with quote for construction from simpson and brown. ek5507 5/4/22 Plan on meeting with asset team in May along with getting a quote from environmental on permitting required. ek5507 4/16/18 - Project has been deferred until 2019 as per request from PMO. 3/27/18 Will be meeting with Natt Pratt in April to go over what will be needed from a safety perspective given the project will be working and removing pipe over a major waterway. EK5507 | 2023-03-14 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Auburn Terminals | BETBW - BET BREWERTON TERMINAL |  | 21966 | 0 |  |  | 75000 |  | Aiken, Elaine | Aiken, Elaine | N/A |  | 1 | 25004 |  | Guest, ProSight | Independent | Aqua | 2017-08-14 | Int - Planned Corr & FI
BRS 25.3 Colby Rd AC repair | Item | Open | MEXP | RX751BXE2302 | Maintenance Framework | 2085712 | Norton, Bill | East | 3. Active | Defined | Cathodic Protection |  | 25000 |  | 25000 | 25000 | 0 | Green | 25000 |  | 25000 | 0 |  |  | 24750 |  |  | 24750 | Full | 24750 |  | 25000 | 25000 | No | Green | 2023-08-01 | 2023-02-21 | 2023-02-21 | 2023-09-01 | 2023-11-30 | [15 empty] | 25000 | [5 empty] | 5/2/23 Delmar Electric to replace electrical service. waiting on dry conditions. WRN | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Corrosion |  | Auburn Pipeline | RX751BX - ROCHESTER JCT - BATAVIA STATIO |  |  | 0 | 25000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44349 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
BRTQR Air to ground coating Phase 2 | Item | Open | MCAP | BETRQ00M2302 | Maintenance Framework | 2085573 | Norton, Bill | East | 3. Active | Defined | Atmospheric Corrosion |  | 45000 |  | 45000 | 45000 | 0 | Green | 45000 |  | 45000 | 0 |  |  | 43680 |  |  | 43680 | Full | 43680 |  | 45000 | 45000 | No | Green | 2023-09-01 | 2023-02-21 | 2023-02-21 | 2023-11-01 | 2023-11-30 | [16 empty] | 45000 | [6 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Terminals | BETRQ - BET ROCHESTER S TERMINAL XOM |  |  | 0 | 45000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44336 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
Buckeye Bahamas Hub - #4 Electric Pump Replacement | Item | Open | MCAP | 8410811M2106 | Exempt | 1804297 | Herry, Ryan | East | 6. Operational | Defined | Rotating Equipment | 3421 |  |  | 3420.65 | 3421 | 0 | Green |  |  |  | 3421 |  |  | 320000 |  |  | 320000 | Full | 320000 | 369411 |  | 369411 | Yes | Red | 2021-04-01 | 2021-01-27 | 2021-01-27 | 2021-09-30 | 2023-02-10 |  |  | 1688.14 | 1718.72 | 13.79 | [16 empty] | 03/03/2023 - Project is operational. Project will be reviewed for supplemental compliance week of March 10th. 2/2/2023 - Project estimated to be operational pending commissioning 2/10/2023. 12/02/22 KB: Operational date has been moved pending testing by operations team. 09/06/22 - Operational tie-ins will be completed in September 2022. No additional cost anticipated; however, CWIP and Interest may still incurred since this project is not quite operational. KB 07/12/22 - Punch list items in progress, Electrical to be connected. Pump has been installed on the base, and piping is complete. 05/10/22 - Pump is on site, piping modifications being reviewed to accommodate new suction. 03/09/2022 - Awaiting available manpower resources, the team is currently installing DP 3047 Fire Pump. Expected to be installed by the end of March. 01/03/21 - Shipping Delays: Pump picked up from Italy by Unishippers. Expected to reach facility Jan 20th. [R. Herry] 01/03/21 - Site preparation and preliminary pipe work started in anticipation of pump. [R. Herry] 12/9/21 - Receiving materials is delayed. To follow up on expected delivery and reforecast as necessary. DC 10/7/21 - Pump is expected in December. 7/26/21 - Pump Electrical package reviewed and approved - [RH] 7/7/21 - Field office repairs to be completed by July BL 03/03/2021 - Awaiting finalized quote 09/07/2020 - Pump remains on schedule to be ordered in October. 07/06/2020 - Pump to be ordered in October. | 2023-03-03 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 3421 | 0 |  |  | 56296 |  | Posipanko, Dan | Nash, Tom | N/A |  | 1 | 31351 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Other Programs
Buffalo Terminal (BETBO) Tank A-038 - OOS Seal Insp | Item | Open | MEXP | BETBO00E2301 | Maintenance Framework | 2093476 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 25000 |  | 25000 | 133000 | -108000 | Red | 133000 |  | 133000 | -108000 |  |  | 132550 |  |  | 132550 | Phase | 132550 |  | 25000 | 25000 | No | Green | 2023-06-01 | 2023-03-01 | 2023-03-01 | 2023-12-31 | 2023-07-31 | [12 empty] | 0 | 25000 | [7 empty] | 5/1/23 - In-service seal inspection scheduled for 6/15. Reduced forecast assuming there will be little or no required repairs. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Auburn Terminals | BETBO - BET BUFFALO TERMINAL |  |  | 25000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44788 |  | Administrator, System | JDE Child | Burnt Orange | 2022-08-17 | Int - Tanks
Buffalo Transmix Tank Overflow Installation | Item | Open | MEXP | BETBO00E2204 | Maintenance Framework | 1938145 | Yoder, Michael | East | 7. Closed | Defined | Secondary Containment | 544 |  |  | 543.75 | 544 | 0 | Green |  |  |  | 544 |  |  | 100000 |  |  | 100000 | Full | 100000 | 56922 |  | 56922 | No | Green | 2022-05-01 | 2022-01-13 | 2022-01-13 | 2022-12-31 | 2022-06-30 |  |  | 543.75 | [18 empty] | 10/11/2022 - Closed WO/PO, set OPPM status to 'Closed'. MCS 10/5/22-Can Close. 8/2/22 - Processing trailing invoices. 7/1/22 - Work complete. Variance due to change order. Job completed under budget. 6/2/22 - Overflow install in progress. Reduced forecast as expected to come in under budget. 5/3/22 - Pushed forecast back to start in May as scope is being finalized. | 2022-10-11 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Auburn Terminals | BETBO - BET BUFFALO TERMINAL |  | 544 | 0 |  |  | 56379 |  | Spari, Markella | Clark, David |  |  | 1 | 41655 |  | Clark, David | Independent | Aqua | 2021-08-20 | Other Programs
Chesapeake (BETQC) - OWS Submersible Pump Upgrade | Item | Open | MCAP |  | Maintenance Framework |  | Schwindt, Joseph | East | 1. Proposed |  | Storm Water Management |  | 40000 |  | 40000 | 40000 | 0 | Green | 50000 |  | 50000 | -10000 | [9 empty] | 40000 | 40000 | No | Green | 2023-06-01 |  |  |  | 2023-04-30 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 40000 | 0 | [6 empty] | 4/3/2023 - Joe Schwindt to follow up with lead terminal operator regarding pump specs. .2/23/23 - JTS Work has not started. Pushed March and April forecast. | 2023-04-03 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Virginia | BETQC - BET CHESAPEAKE TERMINAL |  |  | 40000 | 0 |  |  |  | Bonenberger, Mark |  |  |  | 1 | 45194 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
Chesapeake Clean and idle #6 oil line | Item | Open | MEXP |  | Maintenance Framework |  | Orischak, Bob | East | 1. Proposed |  | Facility Integrity |  | 0 |  | 0 | 45000 | -45000 | Red | 45000 |  | 45000 | -45000 | [9 empty] | 45000 | 45000 | No | Green | 2024-08-01 |  |  |  | 2023-09-30 | [15 empty] | 0 | 0 |  |  |  |  | 5/1/ 23 RLO Project is being pushed to 2024 Due to funding needed for BBH Boiler 2 system. | 2023-05-02 |  |  | East | Pipelines and Terminals | Station/Terminal |  | Virginia | BETQC - BET CHESAPEAKE TERMINAL |  |  | 0 | 0 |  |  | 45000 | Aiken, Elaine |  |  |  | 1 | 45637 |  | Administrator, System | Independent | Aqua | 2022-08-30 | Int - Planned Corr & FI
Chesapeake Remove diesel dead leg to tanks 5601-5602. | Item | Open | MEXP | BETQC00E2301 | Maintenance Framework | 2084834 | Pepe, David | East | 6. Operational | Defined | Facility Integrity | 30702 | 5000 |  | 35702.25 | 42000 | -6298 | Red | 20000 | 22020 | 42020 | -6318 |  |  | 42020 |  |  | 42020 | Full | 42020 | 30702 | 5000 | 35702 | No | Green | 2023-04-01 | 2023-02-15 | 2023-02-15 | 2023-05-15 | 2023-05-31 | [5 empty] | 30702.25 | 22000 | 22000 | 8702 | Red |  | WorkAhead of Schedule | 5000 | [8 empty] | 5/4/2023 - Completed and waiting for final invoices. 4/20/2023 - Contractor completed the removal of the piping from the main header. Dead leg is free of product and left under 10# nitrogen. 4/4/2023-Delayed due to contractor scheduling issue. Planning to do in April. 2/9/2023 DJP Submitted AFE after receiving quote from contractor. 1/11/2023 DJP Finalizing scope of work and getting with contractor to visit site. | 2023-05-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Virginia | BETQC - BET CHESAPEAKE TERMINAL |  |  | 35702 |  |  |  |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 45636 |  | Administrator, System | Independent | Aqua | 2022-08-30 | Int - Planned Corr & FI
Chesapeake Terminal (BETQC) Tank 5605 – OOS Corr Insp - Flip to MEXP | Item | Open | MEXP | BETQC00E2303 | Maintenance Framework | 1937278 | Yoder, Michael | East | 6. Operational | Defined | Tanks | 751462 |  |  | 751461.77 | 751462 | 0 | Green |  |  |  | 751462 |  |  | 717000 |  |  | 717000 | Full | 717000 | 751462 |  | 751462 | No | Green | 2023-03-01 | 2023-03-15 | 2023-03-15 | 2023-01-31 | 2023-03-31 |  |  |  |  | 751461.77 | [16 empty] | Can close. 4/4/23 - Variance due to flip hitting March business. 3/28/23 - On 3/24, I put in a flip ticket to move the 767K on project BETQC00M2201 to this project. MCS. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Virginia | BETQC - BET CHESAPEAKE TERMINAL |  | 751462 | 0 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46728 |  | Meitzler, Antoinette | Independent | Aqua | 2023-03-08
Chesapeake Terminal (BETQC) Tank 5605 – OOS Corr Insp & Refurb | Item | Open | MCAP | BETQC00M2201 | Maintenance Framework | 1937278 | Yoder, Michael | East | 6. Operational | Defined | Tanks | -680196 |  |  | -680195.64 | -680196 | 0 | Green |  |  |  | -680196 |  |  | 584000 |  |  | 584000 | Phase | 584000 | 2161 |  | 2161 | No | Green | 2022-08-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2023-01-31 |  |  | 33916.57 | 48030.1 | -762142.31 | [16 empty] | Can close. 4/4/23 - Variance due to flip to expense. Project in process of being closed. 3/28/2023 - Flip to expense project has occurred today, and I sclosed WO and closed POs. MCS. 3/28/23 - On 3/24, I put in a flip ticket to move the 767K on this project to Expense Project BETQC00E2303. MCS 3/1/23 - Variance due to additional disposal costs. Preparing phase 2 flip AFE for submission. 2/1/23 - Inspection completed. Tank to remain idle. Variance due to higher than forecast disposal costs. Preparing phase 2 flip AFE for submission. 1/3/2023 - Tank cleaning completed. Inspection to be completed week of 1/9. Updated January forecast. Preparing phase 2 flip AFE for submission. 12/1/22 - Tank cleaning in progress. 11/1/22 - Tank cleaning in progress. 10/4/22 - Preparing to clean tank. Plan to clean, inspect, and leave idle. 9/1/22 - Variance due to early start isolating tank. 8/2/22 - Plan to start cleaning in September. 7/6/2022 - Planned for September start. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | -680196 | 0 |  |  | 682357 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41248 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Chesapeake Terminal Camera Upgrade | Item | Open | MCAP | BETQC00M2204 | Maintenance Framework | 2003931 | Mohr, David | East | 3. Active | Defined | Security & Cameras | 15933 | 2200 |  | 18133.11 | 17118 | 1015 | Yellow |  |  |  | 18133 |  |  | 71000 |  |  | 71000 | Full | 71000 | 66302 | 2200 | 68502 | No | Green | 2022-08-01 | 2022-07-25 | 2022-07-25 | 2022-08-30 | 2023-05-31 |  |  | 14797.84 | 800.11 | 20.12 | 315.04 | 1500 | 1500 | -1185 | Red |  |  | 2200 | [8 empty] | 5/1/2023 CO approved for POE Injector to complete project. 4/1/2023 Vendor onsite this week to complete installation. DRM 2/2/2023 Variance due to licensing issues with the NVR. Project will complete in Feb, within budget. 1/3/2023 Variance due to material not arriving for installation to commence. Expecting installation in January. 12/1/2022 Variance due to material not arriving. Cable and conduit completed. 11/1/2022 Installation in progress. Some material still not received. Variance due to camera vendor and material. 10/1/2022 Cable and conduit install commencing week of 10/3. Camera equipment still not received. DRM 9/1/2022 Material on order from camera vendor. Electrical cable and conduit to start week of 9/12 DRM 8/1/2022 Reduced scope by removing new dock camera. AFE has been approved. PO delivered to Alliance Electrical.. JCI PO to follow. DRM 7/5/2022 Have received all quotes and project AFE amount it $84k. DRM 6/2/2022 Change scope for bids and carved out Electrical portion. I have received only 1 of the 3 Camera bids. DRM 5/2/2022 Had site job walk with vendors and contractors last week. Quotes due by week of 5/9. DRM 4/1/2022 DRM Decided on using Convergint, job walk to follow with Chris Clark. 2/1/2022 Scheduling job walk | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Virginia | BETQC - BET CHESAPEAKE TERMINAL |  | 15618 | 2515 |  |  | 50369 |  | Clark, Chris | Clark, Chris B |  |  | 1 | 37849 |  | Guest, ProSight | Independent | Aqua | 2020-08-13 | Other Programs
chesapeake terminal lighting repair 2023 | Item | Open | MEXP | BETQC00E2302 | Maintenance Framework | 2085407 | Orischak, Bob | East | 3. Active | Drawdown | Electrical | 31998 | 1 |  | 31998.5 | 33001 | -1003 | Yellow |  |  |  | 31999 |  |  | 33000 |  |  | 33000 | Full | 33000 | 31998 | 1 | 31999 | No | Green | 2023-04-01 | 2023-02-21 | 2023-02-21 | 2023-03-25 | 2023-03-25 | [5 empty] | 31997.5 | 33000 | 33000 | -1003 | Yellow | [9 empty] | 1 |  | 5/1/2023 RLO Work is complete and need to accrue the remaining money until billing is complete. 4/3/23 RLO Contractor should be starting work this month. No spends. 2/27/23 RLO, Contractor should finish work in April. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Virginia | BETQC - BET CHESAPEAKE TERMINAL |  |  | 31998 |  | 1 |  |  | Ashley, Robert | Blow, Andrew | N/A |  | 1 | 46620 |  | Orischak, Bob | JDE Child | Burnt Orange | 2023-02-22
Chesapeake Thermal relief lanes 1 & 2 | Item | Open | MCAP | BETQC00M2301 | Maintenance Framework | 2076602 | Pepe, David | East | 6. Operational | Defined | Truck Racks | 23326 | 5000 |  | 28326.24 | 47000 | -18674 | Red | 47000 |  | 47000 | -18674 |  |  | 50743 |  |  | 50743 | Full | 50743 | 23326 | 5000 | 28326 | No | Green | 2023-04-01 | 2023-01-23 | 2023-01-23 | 2023-03-31 | 2023-05-31 | [5 empty] | 23326.24 | 47000 | 47000 | -23674 | Red |  | Savings from AFE Estimate | 5000 | [8 empty] | 5/4/2023 - DJP - completed and waiting on final hours and invoices. April spends were under budget due to finishing earlier than expected 4/13/2023 - project work completed, waiting on the MTRs from the contractor. 4/4/2023-On target for April. 2/9/2023 DJP PO issued and contractor has ordered the materials 1/11/2023 DJP Getting quotes from the contractor and finalized scope of work. Scheduling facility walk in January. | 2023-05-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Virginia | BETQC - BET CHESAPEAKE TERMINAL |  |  | 28326 |  |  |  |  | Younce, Michael | Younce, Michael |  |  | 1 | 45302 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Other Programs
CP System and Potentials Investigation Virginia Terminals | Item | Open | MEXP | BETFF00E2302 | Maintenance Framework | 2096529 | Gable, Rob | East | 3. Active | Drawdown | Cathodic Protection | 4712 | 13000 |  | 17711.7 | 17000 | 712 | Yellow |  |  |  | 17712 |  |  | 17000 |  |  | 17000 | Full | 17000 | 4712 | 13000 | 17712 | No | Green | 2023-04-01 | 2023-03-30 | 2023-03-30 | 2023-12-31 | 2023-12-31 | [5 empty] | 4711.7 |  |  | 4712 | Red |  | WorkAhead of Schedule |  |  |  | 13000 | [5 empty] | 5/2/2023 RAG - Work began early during April. 4/4/2023 RAG - Work to begin in May. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Corrosion |  | Virginia | BETFF - BET FAIRFAX |  |  | 4712 | 13000 |  |  |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 46860 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-03-30
CP System Design and Installation Along JH724JM | Item | Candidate | MCAP |  | Maintenance Framework |  | Gable, Rob | East | 1. Proposed |  | Cathodic Protection |  | 90000 |  | 90000 | 90000 | 0 | Green | 90000 |  | 90000 | 0 | [9 empty] | 90000 | 90000 | No | Green | 2023-07-01 |  |  |  | 2023-09-30 | [14 empty] | 35000 | 40000 | 10000 | 5000 |  |  |  | 5/2/2023 RAG - Planning postponed while investigating other projects in the area during 2023 and 2024. 4/4/2023 RAG - Planning postponed while investigating other projects in the area during 2023 and 2024. 3/2/2023 RAG - Work to begin during Q2. | 2023-05-02 |  |  | East | Pipelines and Terminals | Integrity |  | Mechanicsburg | JH724JM - HGHSPE JCT-MECHBRG JCT |  |  | 0 | 85000 | 5000 |  |  | Geib, Rob |  |  |  | 1 | 45415 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
CY802CA - DIG SHEETS (2) | Item | Open | MCAP | CY802CAM2201 | Maintenance Framework | 2023219 | Keppel, Nicholas | East | 6. Operational | Drawdown | Pipeline Digs | 591 |  |  | 590.55 | 591 | 0 | Green |  |  |  | 591 |  |  | 346000 |  |  | 346000 | Full | 346000 | 152440 |  | 152440 | No | Green | 2022-10-01 | 2022-09-21 | 2022-09-21 | 2022-12-31 | 2022-10-28 |  |  | 590.55 | [18 empty] | 1/5/2023 -The 2 digs were completed in October; variance due to labor costs coming in slightly higher than anticipated | 2023-01-05 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | CY802CA - MARCY TO UTICA |  | 591 | 0 |  |  | 151850 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 45694 |  | Guest, ProSight | Independent | Aqua | 2022-08-29 | Int- Planned Digs
Dewitt Junction CP groundbed replacement | Item | Open | MCAP | DJ00000M2301 | Maintenance Framework | 2094191 | Norton, Bill | East | 3. Active | Defined | Cathodic Protection |  | 45000 |  | 45000 | 45000 | 0 | Green | 45000 |  | 45000 | 0 |  |  | 45003 |  |  | 45003 | Full | 45003 |  | 45000 | 45000 | No | Green | 2023-05-01 | 2023-03-07 | 2023-03-07 | 2023-10-01 | 2023-11-30 | [12 empty] | 17000 |  |  | 28000 | [5 empty] | 4/20/23 materials ordered from Mesa. waiting on quote from Skiles for installation.. | 2023-04-20 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | DJ802ZR - DEWITT JCT TO VERONA |  |  | 17000 | 28000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44350 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
DP701NS Airport Dr. groundbed replacement | Item | Open | MCAP | DP701NSM2101 | Exempt | 1804148 | Norton, Bill | East | 7. Closed | Defined | Atmospheric Corrosion | -150 |  |  | -150 |  | -150 | Red |  |  |  | -150 |  |  | 45000 |  |  | 45000 | Full | 45000 | 41198 |  | 41198 | No | Green | 2021-02-01 | 2021-01-26 | 2021-01-26 | 2021-04-01 | 2021-05-31 | [5 empty] | -150 |  |  | -150 | Red | [11 empty] | 1/26/2022 - WO/POs closed, set OPPM to 'Closed'. 9/30/2021 - Closed WO/PO. MCS 9/2/21-Work completed, ready to close. 8/2/21 final equipment ordered, should arrive this month. 6/1/21 Ground Bed installed, system activated. waiting on rectifier replacement to be installed later. 3/1/21 PO issued -Skiles for groundbed replacement. scheduled for May install Mike Bass to notify property owner of upcoming work. WRB | 2022-01-26 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Macungie Pipe | DP701NS - DUPONT TO NICHOLSON-16IN |  |  | -150 |  |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 37238 |  | Guest, ProSight | Independent | Aqua | 2020-07-23
DP701NSV18A RT 92 block valve recoating | Item | Open | MCAP | DP701NSM2301 | Maintenance Framework | 2083840 | Norton, Bill | East | 3. Active | Defined | Atmospheric Corrosion | 9200 | 15000 |  | 24200 | 25000 | -800 | Yellow | 25000 |  | 25000 | -800 |  |  | 25000 |  |  | 25000 | Full | 25000 | 9200 | 15000 | 24200 | No | Green | 2023-04-01 | 2023-02-01 | 2023-02-01 | 2023-07-01 | 2023-11-30 | [5 empty] | 9200 |  |  | 9200 | Red |  | WorkAhead of Schedule | 6500 |  |  |  |  | 8500 |  |  |  | 4/20/23 first stage work completed. waiting on follow up work to be determined. | 2023-04-20 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Macungie Pipe | DP701NS - DUPONT TO NICHOLSON-16IN |  |  | 15700 |  | 8500 |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44351 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
DP-8053 Pump & Engine Replacement | Item | Open | MCAP | 8410811M2131 | Maintenance Framework | 1901744 | Herry, Ryan | East | 3. Active | Unplanned | Rotating Equipment | 56755 | 719469 |  | 776223.68 | 775775 | 449 | Yellow | 750000 |  | 750000 | 26224 |  |  | 3606000 |  |  | 3606000 | Full | 3606000 | 2901210 | 719469 | 3620679 | No | Green | 2021-11-01 | 2021-11-09 | 2021-11-09 | 2021-12-31 | 2023-08-31 |  |  | 13414.7 | 13962.14 | 14928.84 | 14449 |  |  | 14449 | Red |  | Other | 40000 | 240000 | 200000 | 239469 | [5 empty] | 05/01/2023 - Engineering drawings are being finalized for piping and auxillary systems. Pump and engine shipped with expected arrival May 2023. 04/03/2023 - Final project budget is being reviewed to complete project. Remaining forecasts are good. 03/03/2023 - Full AFE estimated to be submitted March 20th, 2023. Pump shipping has been delayed by two months and forecast pushed to begin spending in May er PM. The pump and engine have been assembled and will be inspected by Buckeye SME Nate Frey on March 6th, 2023. Once inspections are satisfactory, the pump will be shipped and installation to begin.February Cap Int and CWIP Allocations combined total $13.9K. 2/2/2023 - Full AFE will be prepared to reflect total approved budget.January Cap Int and CWIP Allocations combined totalled $13.4K 3.17.22.DLC: Pump being Manufactured, expected late Dec 2022 12/2/21 Operational date moved back to 6/30/23 BL 10/4/2021 - Bid Meeting held, expected bid returned Oct 12th. [R. Herry] Down payment in 2021 with installation in 2022 | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 42306 | 294449 | 439469 |  | 44322 |  | Posipanko, Dan | Nash, Tom |  |  | 1 | 34822 |  | Guest, ProSight | Independent | Aqua | 2019-08-30 | Other Programs
Dupont Relief Valve Replacement | Item | Candidate | MCAP |  | Project Framework |  | Wing, Hunter | East | 1. Proposed |  | Transient/Surge Mitigation |  | 124947 |  | 124947 | 115000 | 9947 | Yellow | 115000 |  | 115000 | 9947 | [9 empty] | 124947 | 124947 | No | Green | 2023-06-01 |  |  |  | 2023-07-31 | [12 empty] | 0 | 100977 | 11598 | 12372 | [5 empty] | 5.1.2023 - HJW - After working with Hydraulics Team, project team needed to update quotes for system to go from 4" (existing) to 6" (Preferred by Hydraulic). Forecast represents estimated cost for project to go to 6" but will be updated with correct numbers once AFE is finalized. Brodie is expected to take 4-6 Week and would push project out to June before completion. 2.2.2023 - HW - Review held with operations on 1.18.23 and project scope was reviewed. Work Plan has been developed, but review with Station SME and Regional Engineer to be held this month. | 2023-05-01 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | DP - DUPONT TERMINAL |  |  | 100977 | 23970 |  |  |  | DiPillo, Evan |  |  |  | 1 | 45259 |  | DiPillo, Evan | Independent | Aqua | 2022-08-25 | Other Programs
East Region Arc Flash | Item | Candidate | MEXP |  | Maintenance Framework |  | Mohr, David | East | 1. Proposed |  | Arc Flash |  | 60000 |  | 60000 | 60000 | 0 | Green | 60000 |  | 60000 | 0 | [9 empty] | 60000 | 60000 | No | Green | 2023-06-01 |  |  |  | 2023-08-31 | [13 empty] | 20000 | 20000 | 20000 | [9 empty] | East | Pipelines and Terminals | Station/Terminal |  | East Region Team | 1182 - EAST DISTRICT WORK TEAM |  |  | 20000 | 40000 |  |  |  | Ashley, Robert |  |  |  | 1 | 45904 |  | Clark, David | Independent | Aqua | 2022-09-25 | Other Programs
East Region Top Loading Fall Prevention | Item | Open | MCAP | 100183M2201 | Maintenance Framework | 1989733 | Schwindt, Joseph | East | 3. Active | Defined | Truck Racks | 36244 | 267444 |  | 303688.3 | 356111 | -52423 | Red | 175000 |  | 175000 | 128688 |  |  | 400000 |  |  | 400000 | Full | 400000 | 80133 | 267444 | 347577 | No | Green | 2022-07-01 | 2022-06-07 | 2022-06-07 | 2022-11-30 | 2023-06-30 |  |  | 5210.19 | 12165.01 | 11291.85 | 7577.25 | 60000 | 60000 | -52423 | Red |  | Contractor/Vendor Issue |  | 163000 |  |  | 104444 |  |  |  |  | 5/1/2023-Variance due to delay in contractor finalizing design. 4/3/2023-Adding change order of 60K in April for Allied. Expecting the work to be all done by June. 2/22/23: JTS Macungie Terminal Now working materials PO. Expecting Material Invoice ($57K) to hit in March. Installation PO to follow with June installation. 1/31/23 RLO Coupa delay due to vendor not being setup. PO has been completed but waiting on invoicing. 1/24/23: Vendor (Bullard) has been reistablished in Coupa/JDE. PO ($57K) for parts issued in January. Single use variance has been issued. PO for installation ($200K) will be issued once approved. PO is for Macungie Terminal only. JTS 1/3/2022-Unable to order parts yet due to Coupa/Vendor reinitiation. 12/1/2022-Project was delayed due to contract selection (IsNetWorld), but realistically wont be done until Feb due to lead time equipment need. 11/2/2022-Have quotes, waiting for Vendor's Coupa/ISNET to cut PO (Bollard). 10/3/2022-AFE will be submitted this week, and have chosen vendor. 8/8/2022 - Out to bid. Looking to award in Aug. 7.20.2022.DLC: Allocated funds to Baltimore boiler re-tube project due to vague scope and new PM starting work in July per local REM - phased project over multiple years | 2023-05-01 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | East Region Team | 1182 - EAST DISTRICT WORK TEAM |  | 28667 | 170577 | 104444 |  | 43889 |  | Younce, Michael |  |  |  | 1 | 41582 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
Evaluate the 1993 Foam Pump Truck in Pt. Reading | Item | Open | MEXP | BPRPR00E2305 | Maintenance Framework | 2111129 | Weirsky, Edward | East | 3. Active | Drawdown | Fire Protection |  | 6001 |  | 6001 |  | 6001 | Red |  |  |  | 6001 |  |  | 6000 |  |  | 6000 | Full | 6000 |  | 6001 | 6001 | No | Green | 2023-07-01 | 2023-04-17 | 2023-04-17 | 2023-12-31 | 2023-12-31 | [14 empty] | 6000 |  |  |  |  | 1 |  |  |  | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 0 | 6000 | 1 |  |  | Jakubowski, Gregory | Jakubowski, Greg | N/A |  | 1 | 46944 |  | Orischak, Bob | JDE Child | Burnt Orange | 2023-04-14
EW913LD - 2022 GEO+MFL ILI | Item | Open | MEXP | EW913RWE2202 | Maintenance Framework | 2012370 | Keppel, Nicholas | East | 6. Operational | Defined | Assessments | 0 |  |  | 0.4 | 0 | 0 | Green |  |  |  | 0 |  |  | 282000 |  |  | 282000 | Full | 282000 | 304584 |  | 304584 | No | Green | 2022-09-01 | 2022-08-15 | 2022-08-15 | 2022-10-31 | 2022-10-19 |  |  | 0 | 0.4 | [17 empty] | 1/5/2023 - Variance due to unanticipated filtration costs that were required to run this ILI tool | 2023-01-05 | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Jet Lines | EW913EN - NEW HAVEN TO EAST HAVEN |  | 0 | 0 |  |  | 304584 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40624 |  | Administrator, System | Independent |  | 2021-07-24 | Int - Assessments
EW913LD DOT & BPL Digs (22 Features) - From 2022 GEO+MFL ILI | Item | Open | MCAP | EW913RWM2302 | Maintenance Framework |  | Keppel, Nicholas | East | 2. Pending AFE |  | Pipeline Digs |  | 1750001 |  | 1750001 |  | 1750001 | Red |  |  |  | 1750001 | [6 empty] | Interim |  |  | 1750001 | 1750001 | No | Green | 2023-05-01 |  |  |  | 2023-12-31 | [12 empty] | 250000 | 250000 | 250000 |  |  | 500000 | 500000 | 1 |  | 5/3/2023 - DOT 60-Day features (4) will be completed in May; DOT 180-Day features (7) will be executed in June and July | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Jet Lines | EW913RW - NEW HAVEN TO MIDDLETOWN JCT |  |  | 500000 | 250000 | 1000001 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46955 |  | Meitzler, Antoinette | Independent | Aqua | 2023-04-18
EW913LD Immediate Digs (Five Features) - From 2022 GEO+MFL ILI | Item | Open | MCAP | EW913RWM2301 | Maintenance Framework | 2093969 | Keppel, Nicholas | East | 3. Active | Emergent | Pipeline Digs | 289189 | 200000 |  | 489189.45 | 780562 | -291373 | Red |  | 1157275 | 1157275 | -668086 |  |  | 1157275 |  |  | 1157275 | Full | 1157275 | 289189 | 200000 | 489189 | No | Green | 2023-03-01 | 2023-04-26 | 2023-04-26 | 2023-05-31 | 2023-05-31 |  |  |  |  | 80562.05 | 208627.4 | 200000 | 200000 | 8627 | Yellow |  |  | 200000 | [8 empty] | 4/7/2023 - Variance due to material purchases and engineering and permitting costs in preparation for April execution | 2023-04-07 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Jet Lines | EW913RW - NEW HAVEN TO MIDDLETOWN JCT |  | 80562 | 408627 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46700 |  | Meitzler, Antoinette | Independent | Aqua | 2023-03-03
Fairfax Ethanol Line Replacement Project 2023 | Item | Candidate | MCAP |  | Maintenance Framework |  | Pepe, David | East | 6. Operational |  | Facility Integrity |  |  |  | 0 |  | 0 | Green | 500000 | -500000 | 0 | 0 | [11 empty] | No | Green |  |  |  |  | 2023-03-31 | [21 empty] | 2/9/2023 - DJP forecast and cost tracking done in "last years" project. will correct at project closeout. 1/3/2023 - PM is currently working w/ engineer. Schedule is dependent on outage planning. | 2023-02-09 |  |  | East | Pipelines and Terminals | Integrity |  | Virginia | BETFF - BET FAIRFAX |  |  | 0 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45777 |  | Orischak, Bob | Independent | Aqua | 2022-09-09 | Int - Planned Corr & FI
Fairfax Multiload Upgrade | Item | Candidate | MCAP |  | Maintenance Framework |  | Pepe, David | East | 5. Deferred |  | Truck Racks |  |  |  | 0 |  | 0 | Green | 360000 |  | 360000 | -360000 | [9 empty] | 910000 | 910000 | No | Green | 2024-03-01 |  |  |  | 2023-10-31 | [21 empty] | 5/4/2023 - Project deferred til 2024. 12/9/2022 DJP EAC much greater than budget. Will have to discuss how to accomplish all this year. 11/17/2022 DJP Getting a quote from Midstream , Triad, and ESDC Integration or the engineering. Toptech for the equipment. Ideally looking at 1 week shutdown per lane. | 2023-05-04 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Virginia | BETFF - BET FAIRFAX |  |  | 0 |  |  |  | 910000 | Younce, Michael |  | N/A |  | 1 | 30151 |  | Guest, ProSight | Independent | Aqua | 2018-07-30 | Other Programs
Fairfax Terminal (BETFF) Tank 3 - OOS API 653, VA DEQ + Seal Insp & Refurb | Item | Open | MEXP | BETFF00E2301 | Maintenance Framework | 2093475 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 290000 |  | 290000 | 290000 | 0 | Green | 290000 |  | 290000 | 0 |  |  | 152350 |  |  | 152350 | Phase | 152350 |  | 290000 | 290000 | No | Green | 2023-08-01 | 2023-03-01 | 2023-03-01 | 2023-12-31 | 2023-10-31 | [15 empty] | 40000 | 150000 | 100000 | [5 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Virginia | BETFF - BET FAIRFAX |  |  | 0 | 190000 | 100000 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44814 |  | Administrator, System | JDE Child | Burnt Orange | 2022-08-17 | Int - Tanks
Fairfax Terminal (BETFF) Tank 5 - OOS API 653, VA DEQ + Seal Insp & Refurb | Item | Open | MCAP | BETFF00M2301 | Maintenance Framework | 2086169 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 313919 |  | 313919 | 313919 | 0 | Green | 313919 |  | 313919 | 0 |  |  | 180013 |  |  | 180013 | Phase | 180013 |  | 313919 | 313919 | No | Green | 2023-09-01 | 2023-02-24 | 2023-02-24 | 2023-12-31 | 2023-11-30 | [16 empty] | 128919 | 100000 | 85000 |  |  | 9/23/22-CES-Anticipating minor repairs, Lowering mechanical repair portion of budget from $215,000 to $100,000. | 2022-09-23 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Virginia | BETFF - BET FAIRFAX |  |  | 0 | 128919 | 185000 |  |  | Stine, Carlton |  |  |  | 1 | 44815 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Fairfax Terminal (BETFF) Tank 5 Tempoary Ethanol Support Project | Item | Open | MEXP |  | Maintenance Framework |  | Yoder, Michael | East | 1. Proposed |  | Tank Outage |  | 80000 |  | 80000 | 80000 | 0 | Green | 80000 |  | 80000 | 0 | [9 empty] | 80000 | 80000 | No | Green | 2023-08-01 |  |  |  | 2023-09-30 | [15 empty] | 40000 | 40000 | [8 empty] | East | Pipelines and Terminals | Tank Integrity |  | Virginia | BETFF - BET FAIRFAX |  |  | 0 | 80000 |  |  |  | Stine, Carlton |  |  |  | 1 | 44755 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Fairfax Terminal Additive Electrical Repair 2023 | Item | Open | MEXP | BETFF00E2303 | Maintenance Framework | 2110411 | Orischak, Bob | East | 3. Active | Drawdown | Electrical |  | 12001 |  | 12001 | 12001 | 0 | Green |  |  |  | 12001 |  |  | 12000 |  |  | 12000 | Full | 12000 |  | 12001 | 12001 | No | Green | 2023-06-01 | 2023-04-10 | 2023-04-10 | 2023-06-25 | 2023-06-25 | [13 empty] | 12000 | [5 empty] | 1 |  | 5/1/2023 RLO Project is not expected to start until June. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Virginia | BETFF - BET FAIRFAX |  |  | 12000 |  | 1 |  |  | Ashley, Robert | Blow, Andrew | N/A |  | 1 | 46917 |  | Orischak, Bob | JDE Child | Burnt Orange | 2023-04-10
Fairfax Terminal Ethanol Line Replacement | Item | Open | MCAP | BETFF00M2106 | Maintenance Framework | 1888595 | Pepe, David | East | 6. Operational | Defined | Facility Integrity | 438143 | 5000 |  | 443143.03 | 398148 | 44995 | Red |  | 500000 | 500000 | -56857 |  |  | 31000 | 491000 |  | 522000 | Full | 522000 | 486846 | 5000 | 491846 | No | Green | 2021-11-01 | 2021-09-23 | 2021-09-23 | 2021-10-31 | 2023-03-31 |  |  | 142588.18 | 102706.79 | 122853.37 | 69994.69 | 30000 | 30000 | 39995 | Red |  | WorkAhead of Schedule | 5000 | [8 empty] | 2023-4-1 - Construction Complete, Commissioning the week of 4/3. Some spends will end up in April for painting and commissioning. 2023-3-1 --DJP-Delay due to permitting, but now on track. Onsite construction has started. Foundation inspection has passed and concrete to be poured week of 2/27/2023. Supports are on site and ready to be installed. Offsite fabrication is complete and passed hydro and NDT.2023-2-3 --DJP-Material is on site, off-site fabrication complete, permit to be issued w/o 2/6. 2023-01-06 DJP - delay in permit and receipt of materials.2022-12-9 DJP performing layout of civil supports and checking concrete. permits should be in hand next week.2022-12-5 Permits submitted, POs cut for material and construction, some shop fab to start this week. most work to be in 2023 1Q.2022-11-10 PO Ready for Materials and Contractor, Permit Set sent to contractor for submittal. djp2022-10-31 - Additional $100k added to 2022 remaining forecast from the Asset Integrity MCAP drawdown.2022-09-12 - Cost of project will be more than budgeted. Will attempt to begin work in 2022, dependent on permitting approvals by City and Fire. New project entered for 2023 to cover the additional cost of the project.8/3/22 -Quote was way above budget (300K vs budget of 200K) will need to be transitioned to another pm. ek55077/6/22 Construction estimate obtained and came in considerably higher then expected. Spoke to Elaine Aiken that a decision will need to be made for path forward as project should be transitioned to a new pm. ek 55075/2/22 No change for accrual. Have several calls into Fairfax code enforcement to see where we are in the process. ek55074/4/22 Accural made for mid stream eng. Print have been submitted to Fairfax code enforcement. ek55073/2/22 Accrual made for Mid stream. Project will be turned over to Dave Pepe for full AFE submittal and execution. Print will be submitted to Farifax code enforment for review next month. ek550710/5/2021 - Drawings are being reviewed.9/3/21 Eng design in process hoping to have final prints completed and ready by end of Sept, then have tosubmit to Fire Marshall down there for permit. EK55078/4/2021-Currently working on AFE and Engrg design to run new line. 7/6/2021 plan to scope in July.. ek5507 | 2023-04-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Virginia | BETFF - BET FAIRFAX |  | 368148 | 74995 |  |  | 19657 |  | Aiken, Elaine | Blow, Andrew |  |  | 1 | 37537 |  | Guest, ProSight | Independent | Aqua | 2020-08-07 | Int - Planned Corr & FI
Fairfax Terminal HVAC Replacement 2023 | Item | Open | MCAP | BETFF00M2302 | Maintenance Framework | 2095140 | Orischak, Bob | East | 3. Active | Drawdown | East |  | 69900 |  | 69900 | 69900 | 0 | Green |  | 69900 | 69900 | 0 |  |  | 69900 |  |  | 69900 | Full | 69900 |  | 69900 | 69900 | No | Green | 2023-07-01 | 2023-03-16 | 2023-03-16 | 2023-05-30 | 2023-12-31 | [14 empty] | 69900 | [6 empty] | 5/1/23 RLO Project not expected to start till july. 4/3/23 RLO Still waiting on materials 3/20/23 RLO Project Approved. Materials are 15wk leadtime | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Virginia | BETFF - BET FAIRFAX |  |  | 0 | 69900 |  |  |  | Orischak, Bob | Blow, Andrew |  |  | 1 | 46770 |  | Orischak, Bob | Independent | Aqua | 2023-03-14
Fairfax Terminal Rectifier RMU & Explosion Proof Junction Box Install | Item | Open | MCAP | BETFF00M2201 | Maintenance Framework | 1938830 | Gable, Rob | East | 3. Active | Defined | Cathodic Protection | 9219 | 36000 |  | 45218.72 | 44867 | 352 | Yellow |  |  |  | 45219 |  |  | 43000 |  |  | 43000 | Full | 43000 | 11626 | 36000 | 47626 | Yes | Red | 2022-05-01 | 2022-01-20 | 2022-01-20 | 2022-07-15 | 2023-08-31 |  |  |  | 2246.99 | 6620.21 | 351.52 |  |  | 352 | Red |  |  |  |  | 13000 | 23000 | [5 empty] | 5/2/2023 RAG - Planning a site visit with electrical contractor in the next month. 4/4/2023 RAG - Additional supplies purchased ahead of schedule. 3/2/2023 RAG - Supplies purchased ahead of schedule. Work to begin during Q2. 2/2/2023 RAG - Work has already been planned for 2023. 1/4/2023 RAG - Work has already been planned for 2023. 12/2/2022 RAG - Project forecasted in 2023. 11/3/2022 RAG - Project forecasted in 2023. 10/4/2022 RAG - Project forecasted for 2023. No work to be performed during 2022. 6/2/2022 RAG - Have forecasted all $41K into 2023 to fund BETQC00M2202 & BNTUE00M2207. 5/11/2023 RAG - Forecasting all remaining $43K in funds into 2023 to free up funds for 2 other projects (QC-03 Replacement & BNTUE 3 Main Rectifiers Replacement) once unlocked. 5/2/2022 RAG - Diverted contractor to project of higher time priority. 4/4/2022 RAG - Preparing work to begin as forecasted. 2/2/2022 RAG - AFE has been approved and WOR created. 1/12/2022 RAG - AFE submitted on 1/12/2022. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Virginia | BETFF - BET FAIRFAX |  | 8867 | 352 | 36000 |  | 2407 |  | Geib, Rob | Geib, Robert |  |  | 1 | 41085 |  | Guest, ProSight | Independent | Aqua | 2021-08-06 | Int - Accel Corr & FI
Fairfax VRU Release Prevention | Item | Open | MCAP |  | Maintenance Framework |  | Pepe, David | East | 8. Canceled |  | Vapor Management |  | 0 |  | 0 | 26000 | -26000 | Red | 61000 |  | 61000 | -61000 | [9 empty] | 0 | 0 | No | Green |  |  |  |  | 2023-07-31 | [19 empty] | 0 |  | 3/21/2023 - mrk - removed $35k in funds for overforecast on Jax and N Charleston projects. 1/26/2023 - DJP - the project will be cancelled and switched to another VRU since the Fairfax Unit will be completed as part of the installation of a new VRU. 12/9/22 DJP Getting quotes for material. Will complete in the 1Q2023. | 2023-03-21 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Virginia | BETFF - BET FAIRFAX |  |  | 0 |  | 0 |  |  | Karl, Marissa |  |  |  | 1 | 44947 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Other Programs
Fullerton Prover Connections | Item | Open | MCAP | FE00000M2201 | Maintenance Framework | 1981513 | Mohr, David | East | 7. Closed | Drawdown | East | 2742 |  |  | 2741.94 | 2742 | 0 | Green |  |  |  | 2742 |  |  | 33000 |  | 7656 | 33000 | Full | 40656 | 40774 |  | 40774 | No | Green | 2022-07-01 | 2022-05-24 | 2022-05-24 | 2022-07-31 | 2022-12-31 |  |  | 2623.87 | 118.07 | [17 empty] | 3/14/2023 - Closed WO/PO, and set OPPM project status to 'Closed'. MCS 2/2/2023-Leave open for another month.12/2/2022 Project is completed. 11/1/2022 Variance due to contractor redesign. Expected by mid Dec. 10/3/2022 Redesign required. Met with contractor. Estimate completion by months end. Electrical installation completed. DRM 8/182022 Met with contractor and approved the design. Fabrication has statrted. DRM 6/2/2022 Issued PO's last week for prover connections. Prover may be scrapped to offset cost from C&W. DRM | 2023-04-24 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | FE - FULLERTON TERMINAL |  | 2742 | 0 |  |  | 38033 |  | Orischak, Bob | Orischak, Bob |  |  | 1 | 43815 |  | Meitzler, Antoinette | Independent | Aqua | 2022-05-20 | Other Programs
Groton - Approach Structure - Substructure repairs | Item | Open | MCAP |  | Project Framework |  | Wojton, Brian | East | 4. On-Hold |  | Marine |  | 1 |  | 1 | 1 | 0 | Green | 500000 |  | 500000 | -499999 | [9 empty] | 1 | 1 | No | Green | 2023-10-01 |  |  |  | 2023-10-31 | [15 empty] | 0 | 0 | 1 |  |  |  | 2.14.23.DLC: Removed forecast and put project on hold per program manager | 2023-02-14 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Jet Lines | BETQG - BET GROTON TERMINAL |  |  | 0 | 0 | 1 |  |  | Spari, Markella |  |  |  | 1 | 41937 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Marine
Groton Clean and idle OOS Piping Phase II | Item | Candidate | MEXP |  | Maintenance Framework |  | Wojton, Brian | East | 1. Proposed |  | Facility Integrity |  | 75000 |  | 75000 | 75000 | 0 | Green | 75000 |  | 75000 | 0 | [9 empty] | 75000 | 75000 | No | Green | 2023-07-01 |  |  |  | 2023-05-31 | [12 empty] | 0 |  | 25000 | 50000 | [5 empty] | 05/06/2023 - Spoke with Ops/Gary and preparing scope for priority drain downs and removals. | 2023-05-08 |  |  | East | Pipelines and Terminals | Station/Terminal |  | Jet Lines | BETQG - BET GROTON TERMINAL |  |  | 0 | 75000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 34281 |  | DeSocio, David | Independent | Aqua | 2019-08-21 | Int - Planned Corr & FI
GROTON PAINT PIPING UNDER GRATING | Item | Candidate | MCAP |  | Maintenance Framework |  | Wing, Hunter | East | 1. Proposed |  | Facility Painting |  | 75000 |  | 75000 | 75000 | 0 | Green | 75000 |  | 75000 | 0 | [9 empty] | 75000 | 75000 | No | Green | 2023-07-01 |  |  |  | 2023-06-30 | [12 empty] | 0 | 0 | 50000 | 25000 | [5 empty] | 5/1/2023 - HJW - Quote to demo old pipe and install into existing system came back $21K overbudget. Going to obtain quotes through supply chain for coating the pipe vs removing. Some areas are very bad on corrosion, and some are tight for a roller or brush. Will consult Corrosion Specialist for this facility to see what their opinion is on project. Forecast pushed until summer when weather is better and until SOW is determined. 2.27.23 - HW - Walking down with operations and contractor to see what best options are for this SOW. Piping is in tight area and not easy to paint. | 2023-05-01 |  |  | East | Pipelines and Terminals | Integrity |  | Jet Lines | BETQG - BET GROTON TERMINAL |  |  | 0 | 75000 |  |  |  | Geib, Rob |  | N/A |  | 1 | 19959 |  | Guest, ProSight | Independent | Aqua | 2016-08-04 | Int - Planned Corr & FI
Groton Terminal API 570 Inspection | Item | Open | MEXP | BETQG00E2202 | Maintenance Framework | 1981505 | Keeth, Ed | East | 7. Closed | Defined | Facility Integrity | -3062 |  |  | -3062.1 | -3062 | 0 | Green |  |  |  | -3062 |  |  | 56000 |  |  | 56000 | Full | 56000 | 41593 |  | 41593 | No | Green | 2022-11-01 | 2022-05-24 | 2022-05-24 | 2022-08-31 | 2022-12-31 |  |  | -3062.1 | [18 empty] | 3/14/2023 - Closed WO/PO and set OPPM project status to 'Closed'. 2/3/2023-Work completed, wait a month before closing. 1/5/23 Work is completed. Accrual made for 25k for Lake Superior Consulting. EK5507 2022-11-03 -Ed Keeth is doing. Project pushed to mid-November/December due to shifting our inspector to other inspections that were more urgent because of USCG deadlines. Ed Keeth will do. 9/6/2022-On track to start in October, Ed Keeth will do. 6/2/22 AFE approved trying to confirm sch with contractor. ek5507 | 2023-03-14 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Jet Lines | BETQG - BET GROTON TERMINAL |  | -3062 | 0 |  |  | 44655 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 41193 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Accel Corr & FI
Groton Terminal Atmospheric Refurbishment | Item | Open | MCAP | BETQG00M2201 | Maintenance Framework | 1939591 | Occhi, Edward | East | 7. Closed | Defined | Atmospheric Corrosion | 108 |  |  | 107.87 | 108 | 0 | Green |  |  |  | 108 |  |  | 40000 |  | 5525 | 40000 | Full | 45525 | 45488 |  | 45488 | No | Green | 2022-10-01 | 2022-01-27 | 2022-01-27 | 2022-12-31 | 2022-11-30 |  |  | 144.89 | -37.02 | [17 empty] | 02/22/2023 CWIP charges pushed over budget... requested additional amount added to OPPM to avoid supplemen trigger. 01/27/2023 - CWIP charges triggering supplement. Request submitted to supplement $1,600 to offset and remove trigger. | 2023-03-01 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Jet Lines | BETQG - BET GROTON TERMINAL |  | 108 | 0 |  |  | 45381 |  | Geib, Rob | Geib, Robert |  |  | 1 | 41088 |  | Guest, ProSight | Independent | Aqua | 2021-08-06 | Int - Accel Corr & FI
Guthsville Junction (GZ) North Block Valve Replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Keppel, Nicholas | East | 5. Deferred | Defined | Valves |  |  |  | 0 |  | 0 | Green | 240000 |  | 240000 | -240000 | [11 empty] | No | Green |  |  |  |  | 2023-09-30 | [21 empty] | 5/1/2023 - Project deferred on 2/14/2023 by REM; Planned for 2024. 11/3/2022- This project will executed in 2023. 4/25/2022 - This project will be deferred in order to utilize monies for other projects; as previously noted, due to the magnitude of this project's scope, this project will need a budget between $250 and $350K. | 2023-05-03 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | GZ - GUTHSVILLE JCT |  |  | 0 |  |  |  |  | Oey, Alex |  |  |  | 1 | 41489 |  | Guest, ProSight | Independent | Aqua | 2021-08-18 | Other Programs
Hamden Terminal Dike Erosion Phase 1 | Item | Open | MCAP | BNTNH00M2102 | Maintenance Framework | 1877582 | DeSocio, David | East | 3. Active | Defined | Secondary Containment | 29242 | 325000 |  | 354241.82 | 354418 | -176 | Yellow | 350000 |  | 350000 | 4242 |  |  | 41000 |  |  | 41000 | Phase | 41000 | 117634 | 325000 | 442634 | No | Green | 2021-08-01 | 2021-08-09 | 2021-08-09 | 2021-12-31 | 2023-03-31 |  |  | 995.16 | 3255 | 167.56 | 24824.1 | 25000 | 25000 | -176 | Yellow |  |  | 25000 | 150000 | 100000 | 50000 | [5 empty] | 6/9/22- Delays with design and permitting. 3/24/23 - $262,000.00 of this project is being used to fund the emergency work being executed by Brian Wojton. | 2023-03-24 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNH - New Haven Hamden Terminal |  | 4418 | 199824 | 150000 |  | 47267 |  | Clark, Dave | Buchalski, Edwin |  |  | 1 | 40828 |  | Meitzler, Antoinette | Independent | Aqua | 2021-07-29 | Other Programs
Hamden Terminal Roof Replacement 2023 | Item | Open | MCAP | BNTNH00M2303 | Maintenance Framework | 2119885 | Orischak, Bob | East | 3. Active | Drawdown | East |  | 28000 |  | 28000 |  | 28000 | Red |  | 28080 | 28080 | -80 |  |  | 28080 |  |  | 28080 | Full | 28080 |  | 28000 | 28000 | No | Green | 2023-05-01 | 2023-05-02 | 2023-05-02 | 2023-05-31 | 2023-05-30 | [12 empty] | 28000 | [10 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNH - New Haven Hamden Terminal |  |  | 28000 |  |  |  |  | Orischak, Bob | Wing, Stephen W. |  |  | 1 | 47002 |  | Orischak, Bob | Independent | Aqua | 2023-04-29
Hartwell Road Valve Actuator and Pressure Transmitter Installation | Item | Open | MCAP | AB00000M2304 | Maintenance Framework | 2094183 | Mohr, David | East | 3. Active | Defined | Valves | 1592 | 190000 |  | 191592.37 | 190000 | 1592 | Yellow | 190000 |  | 190000 | 1592 |  |  | 190143 |  |  | 190143 | Full | 190143 | 1592 | 190000 | 191592 | No | Green | 2023-04-01 | 2023-03-07 | 2023-03-07 | 2023-08-31 | 2023-08-31 | [5 empty] | 1592.37 |  |  | 1592 | Red |  |  |  | 30000 | 80000 | 80000 | [5 empty] | 5/1/2023 Received Pressure transmitters, Engineering progressing, ROW completed and check delivired to utility to schedule pole and line work. 4/1/2023 met at the valve site and electrical contractor to provide quote. Actuator is on order. 3/1/2023 Received quotes for material and engineering. Submitted AFE. DRM 2/2/2023 Solicitated quotes from Engineering, Electrical, Actuator. Initial discussion with ROW for increase easement, | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Pipeline | AB - AUBURN STATION |  |  | 31592 | 160000 |  |  |  | Oey, Alex | Tracey, Steve |  |  | 1 | 45903 |  | Clark, David | Independent | Aqua | 2022-09-25 | Other Programs
Inwood Replace storage trailer unit | Item | Open | MCAP | IW00000M2301 | Maintenance Framework | 2083816 | DeSocio, David | East | 6. Operational | Defined | East | 25187 |  |  | 25186.63 | 18500 | 6687 | Red | 18500 |  | 18500 | 6687 |  |  | 18500 |  |  | 18500 | Full | 18500 | 25187 |  | 25187 | Yes | Red | 2023-04-01 | 2023-02-01 | 2023-02-01 | 2023-10-01 | 2023-04-30 | [5 empty] | 25186.63 | 18500 | 18500 | 6687 | Red |  | WorkAhead of Schedule | [11 empty] | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Long Island | IW - INWOOD |  |  | 25187 |  |  |  |  | Orischak, Bob | Klumpp, Eugene |  |  | 1 | 41788 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Jet Line System CP Surveys | Item | Open | MEXP | BETWE00E2202 | Maintenance Framework | 1946979 | Occhi, Edward | East | 7. Closed | Defined | Atmospheric Corrosion | 759 |  |  | 758.79 | 759 | 0 | Green |  |  |  | 759 |  |  | 28000 |  |  | 28000 | Full | 28000 | 30047 |  | 30047 | No | Green | 2022-03-01 | 2022-02-15 | 2022-02-15 | 2022-12-31 | 2022-11-30 |  |  | 758.79 | [18 empty] | 01/06/2023 reclass submitted to move $9,313.96 to BPTPC00M2202. 12/8/2022 Reclass submitted for $9,313.96 of payroll from LN607NWM2201. 7/1/2022 Networkers not used in July. 6/2/2022 - vendor to submit invoice. Vendor has not submitted invoice yet | 2023-01-06 | Walker, Carol |  | East | Pipelines and Terminals | Corrosion |  | Jet Lines | ED - EAST HARTFORD STATION |  | 759 | 0 |  |  | 29288 |  | Geib, Rob | Geib, Robert |  |  | 1 | 40911 |  | Guest, ProSight | Independent | Aqua | 2021-08-03 | Int - Planned Corr & FI
Jet Lines CP Upgrades | Item | Open | MCAP | BETWE00M2201 | Maintenance Framework | 1946434 | Occhi, Edward | East | 7. Closed | Defined | Cathodic Protection | 2171 |  |  | 2171.25 | 2171 | 0 | Green |  |  |  | 2171 |  |  | 40000 |  |  | 40000 | Full | 40000 | 42953 |  | 42953 | No | Green | 2022-06-01 | 2022-02-10 | 2022-02-10 | 2022-12-31 | 2022-11-30 |  |  | 2192.74 | -21.49 | [17 empty] | 4/4/2022 - Contractor no longer doing construction projects. New construction work contractor to be retained. | 2022-04-04 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Jet Lines | BETWE - BET WETHERSFIELD TERMINAL |  | 2171 | 0 |  |  | 40782 |  | Geib, Rob | Geib, Robert |  |  | 1 | 40905 |  | Guest, ProSight | Independent | Aqua | 2021-08-03 | Other Programs
Jet Lines Test Station Repair / Replacement | Item | Open | MEXP | BETWE00E2203 | Maintenance Framework | 1946425 | Occhi, Edward | East | 7. Closed | Defined | Cathodic Protection | 2809 |  |  | 2809 | 2809 | 0 | Green |  |  |  | 2809 |  |  | 40000 |  |  | 40000 | Full | 40000 | 43992 |  | 43992 | No | Green | 2022-03-01 | 2022-02-10 | 2022-02-10 | 2022-12-31 | 2022-11-30 |  |  | 2809 | [18 empty] | 2/2/2023 reclass submitted $155 to BETWE00E2204. 2/2/2023 - CT SELF ASSES FEE TRIGGER SUPPLEMENT. | 2023-02-02 | Walker, Carol |  | East | Pipelines and Terminals | Corrosion |  | Jet Lines | BETWE - BET WETHERSFIELD TERMINAL |  | 2809 | 0 |  |  | 41183 |  | Geib, Rob | Geib, Robert |  |  | 1 | 40609 |  | Guest, ProSight | Independent | Aqua | 2021-07-23 | Int - Planned Corr & FI
JFK 601/602 West Boundary Valve Upgrade and Relocation | Item | Open | MCAP | JK00000M1701 | Exempt | 1280833 | DeSocio, David | East | 3. Active | Unplanned | Valves | 24112 | 345000 |  | 369112.38 | 358703 | 10409 | Yellow | 265000 |  | 265000 | 104112 |  |  | 266000 |  |  | 266000 | Phase | 266000 | 633968 | 2845000 | 3478968 | No | Green | 2020-01-01 | 2016-12-25 | 2016-12-25 | 2017-12-31 | 2024-09-27 |  |  | 2816.28 | 2990.67 | 7896.12 | 10409.31 | 0 | 0 | 10409 | Red |  | WorkAhead of Schedule | 5000 | 15000 | 40000 | 80000 | 80000 | 55000 | 70000 |  |  | 8-10-20 Project under review by PANYNJ 10/18/2018 - Multi phase project continuing into 2019 03/01/2018 project has been updated to Phase status. Supplemental alert to be disregarded. | 2020-08-10 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Long Island | NL601JK - NEW LOTS-JFK AIRPORT-FUEL |  | 13703 | 30409 | 200000 | 125000 | 1375 | 2000000 | Oey, Alex | Klumpp, Eugene |  |  | 1 | 12894 |  | Guest, ProSight | Independent | Aqua | 2014-09-08 | Other Programs
L724 Lab Analysis | Item | Open | MEXP | BH724SNE2201 | Maintenance Framework | 2051851 | Bartal, Nick | East | 3. Active | Drawdown | Pipeline Digs | 29600 |  |  | 29600 | 29600 | 0 | Green |  |  |  | 29600 |  |  | 39600 |  |  | 39600 | Full | 39600 | 39600 |  | 39600 | No | Green | 2022-12-01 | 2022-12-09 | 2022-12-09 | 2023-02-28 | 2023-01-31 |  |  | 0 | 19800 | 9800 | [16 empty] | 3.2.23 - Accrual $29,800 (AS) 2/7/23 - lab work still in process - forecast moved to Feb. 1/9/23 - Work began and accrued in Dec | 2023-03-02 | Schultz, Amy |  | East | Pipelines and Terminals | Pipeline Integrity |  | Booth | BH724SN - BOOTH TO SINKING SPRING |  | 29600 | 0 |  |  | 10000 |  | Bartal, Nick | Shook, Mark B. | N/A |  | 1 | 46344 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-12-09 | Int- Planned Digs
Leak Detection - Johnson Rd & Doughty Blvd Install | Item | Open | MCAP | LY00000M2102 | Exempt | 1903051 | DeSocio, David | East | 7. Closed | Defined | Leak Detection | 2465 |  |  | 2465.47 | 2465 | 0 | Green |  |  |  | 2465 |  |  | 180000 |  |  | 180000 | Full | 180000 | 211211 |  | 211211 | No | Green | 2021-11-01 | 2021-10-26 | 2021-10-26 | 2021-12-31 | 2022-09-30 |  |  | 2359.3 | 106.17 | [17 empty] | 4/5/22 Program owner will be adding $50k for additional funding needed to upgrade OMNI's. 10/5/21 - Waiting on final bids from vendors to finalize AFE amount. 2/8/21 - Projects has been put on hold until further evaluation by Program Owner. 5/31/18 - working to test if line can be pressurized from existing sump. May provide a temporary work-around until funds are available for preferable solution 4/16/2018 IW999A2M1801 was issued in 2018 currently tagged closed in JDE 04/13/2018 - PMO - Per discussion with Rick Bishop, it was decided this project would get deferred to 2019 to support overall MCAP Portfolio reductions for remainder of 2018. PMO copied forecasts from 2018 into 2019 to ensure this project is included in 2019 Budget Planning. Removed Operational Date to be updated for 2019 planning. 02/26/2018 AFE in workflow pending approvals. Since this is a new program, Prog Owner to visit site and review work to be done. Trip re-scheduled to May 2nd. | 2022-04-05 | Colletti, Daniella |  | East | Pipelines and Terminals | Integrity |  | Long Island | LY - LONG ISLAND CITY TERMINAL |  | 2465 | 0 |  |  | 148242 |  | Guenther, Steve | DeSocio, David | N/A |  | 1 | 25473 |  | Guest, ProSight | Independent | Aqua | 2017-09-01 | Leak Detection
Leak Detection - Long Island City to Kinder Morgan Gas | Item | Open | MCAP | LY999C1M2101 | Exempt | 1903041 | DeSocio, David | East | 7. Closed | Defined | Leak Detection | 58693 |  |  | 58692.63 | 57493 | 1200 | Yellow |  |  |  | 58693 |  |  | 150000 |  |  | 150000 | Phase | 150000 | 385205 |  | 385205 | No | Green | 2021-12-01 | 2021-10-26 | 2021-10-26 | 2021-10-01 | 2022-12-15 |  |  | 64804.31 | 2689.29 | -10000.97 | 1200 |  |  | 1200 | Red | [11 empty] | 3/2/23 - Hydrotest on idle line needed to be completed prior to completing install and checkout. 12/5/2022 scheduled allowed more work to be completed. 11/3/2022 work completed ahead of schedule. 10/10/22 - DD - Idle line will now be activated for a new customer- will need to install an additional meter, valve, control cabinet and transmitter. | 2023-03-02 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Long Island | LY999C1 - LIC TO APOLLO JCT (FUEL) |  | 57493 | 1200 |  |  | 256790 |  | Guenther, Steve | Bishop, Rick | N/A |  | 1 | 30150 |  | Guest, ProSight | Independent | Aqua | 2018-07-30 | Leak Detection
Leak Detection - Long Island City to Metro Gas & Fuel | Item | Open | MCAP | LY999A3M2103 | Exempt | 1903039 | DeSocio, David | East | 7. Closed | Defined | Leak Detection | 366 |  |  | 366.13 | 366 | 0 | Green |  |  |  | 366 |  |  | 220000 |  | 75000 | 220000 | Full | 295000 | 321287 |  | 321287 | No | Green | 2021-10-01 | 2021-10-26 | 2021-10-26 | 2021-08-01 | 2022-10-21 |  |  | 366.13 | [18 empty] | 10/11/22 B Clark to handle supple. issue due to reclass oversight from 2021 CATSI payment. 10/10/22 -DD - Will need a supplemental AFE due to additional work needed for piping modifications and electrical work. 4/19/2022 - Reclass to be submitted by B Clark team for $41,925.20; CATSI purchase order/payment error. | 2022-12-06 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Long Island | LY999A3 - LIC TO METRO (GAS) |  | 366 | 0 |  |  | 173773 |  | Guenther, Steve | Bishop, Rick | N/A |  | 1 | 30147 |  | Guest, ProSight | Independent | Aqua | 2018-07-30 | Leak Detection
Leak Detection - Long Island City to Zenith Gas | Item | Open | MCAP | LY999A1M2001 | Exempt | 1744153 | DeSocio, David | East | 3. Active | Defined | Leak Detection | 9730 | 150000 |  | 159730.25 | 155302 | 4429 | Yellow | 120000 |  | 120000 | 39730 |  |  | 71000 | 90000 |  | 161000 | Phase | 161000 | 104699 | 150000 | 254699 | No | Green | 2020-10-01 | 2020-08-11 | 2020-08-11 | 2020-11-15 | 2023-08-01 |  |  | 1012.29 | 722.43 | 3566.8 | 4428.73 | 0 | 0 | 4429 | Red |  |  | 0 | 0 | 20000 | 40000 | 70000 | 20000 |  |  |  | 12/5/2022 Still waiting on agreement with Zenith. 9/8/22 - Waiting on agreement with Zenith | 2022-12-05 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Long Island | LY999A1 - LIC TO MOTIVA (GAS) |  | 5302 | 4429 | 130000 | 20000 | 36074 |  | Guenther, Steve | Bishop, Rick |  |  | 1 | 36401 |  | Kabaria, Erika | Independent | Aqua | 2020-03-24 | Leak Detection
Leak Detection - PR999A1 | Item | Candidate | MCAP |  | Maintenance Framework |  | Yezik, James | East | 4. On-Hold |  | Leak Detection |  | 10000 |  | 10000 | 10000 | 0 | Green | 100000 |  | 100000 | -90000 | [9 empty] | 10000 | 10000 | No | Green | 2023-10-01 |  |  |  | 2023-04-30 | [12 empty] | 0 | 0 |  |  |  | 10000 | [7 empty] | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 0 |  | 10000 |  |  | Guenther, Steve |  |  |  | 1 | 45103 |  | Clark, David | Independent | Aqua | 2022-08-19 | Leak Detection
Linden 20" Gate Valve Replacement | Item | Open | MCAP | LN00000M2211 | Maintenance Framework | 1946358 | DeSocio, David | East | 7. Closed | Drawdown | East | 13237 |  |  | 13237.43 | 13237 | 0 | Green |  |  |  | 13237 |  |  | 40000 |  |  | 40000 | Full | 40000 | 45263 |  | 45263 | No | Green | 2022-11-01 | 2022-02-09 | 2022-02-09 | 2022-03-01 | 2022-03-01 |  |  | 12667.4 | 570.03 | [17 empty] | 12/5/2022 Work completed sooner than expected. | 2022-12-05 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  | 13237 | 0 |  |  | 32026 |  | Orischak, Bob | Klumpp, Eugene |  |  | 1 | 42868 |  | Meitzler, Antoinette | Independent | Aqua | 2022-02-04 | Other Programs
Linden 400 AMP Main Circuit Breaker for Booster pumps | Item | Open | MCAP | LN00000M2203 | Maintenance Framework | 1937266 | DeSocio, David | East | 7. Closed | Defined | Electrical | 15267 |  |  | 15266.67 | 14538 | 729 | Yellow |  |  |  | 15267 |  |  | 44000 |  |  | 44000 | Full | 44000 | 55649 |  | 55649 | No | Green | 2022-05-01 | 2022-01-05 | 2022-01-05 | 2022-07-01 | 2022-07-01 |  |  |  | 6580 | 7957.78 | 728.89 |  |  | 729 | Red | [13 empty] | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  | 14538 | 729 |  |  | 40383 |  | Ashley, Robert | Klumpp, Eugene |  |  | 1 | 37407 |  | Guest, ProSight | Independent | Aqua | 2020-07-31 | Other Programs
Linden 5KV Motor Feed Cable Replacement 2022 | Item | Open | MCAP | LN00000M2215 | Maintenance Framework | 2043849 | Orischak, Bob | East | 7. Closed | Drawdown | Electrical | 3572 |  |  | 3571.8 | 3572 | 0 | Green |  |  |  | 3572 |  |  | 32000 |  | 5053 | 37053 | Full | 37053 | 40138 |  | 40138 | No | Green | 2022-12-01 | 2022-11-04 | 2022-11-04 | 2022-12-15 | 2023-02-28 |  |  | 486.9 | 2952.06 | 132.84 | [16 empty] | 3/6/2023 - Closed WO/PO and set OPPM status to 'Closed' MCS. 2/22/2023 RLO Ready to Close. 1/31/2023 RLO Supplemental needed for this work. Project ready to close at end of February 01/03/2023 - RLO This can be accrued. Work has been completed. Supplemental may be needed due to extra work being done. 12/1/2022 RLO Contractor delay. This will be completed in Dec. Can accrue. 11/2/2022 - RLO This project was just approved on 11.1.22. Expect the work to be completed in November | 2023-03-06 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  | 3572 | 0 |  |  | 36566 |  | Ashley, Robert | Klug, Wayne |  |  | 1 | 46146 |  | Orischak, Bob | Independent | Aqua | 2022-10-31 | Other Programs
LINDEN 601 DOOR OLIVER REMOVAL | Item | Open | MEXP | LN00000E2309 | Maintenance Framework | 2094267 | DeSocio, David | East | 3. Active | Defined | Facility Integrity | 10000 | 190000 |  | 200000 | 200000 | 0 | Green |  |  |  | 200000 |  |  | 196900 |  |  | 196900 | Full | 196900 | 10000 | 190000 | 200000 | No | Green | 2023-04-01 | 2023-03-08 | 2023-03-08 | 2023-08-01 | 2023-07-07 | [5 empty] | 10000 | 10000 | 10000 | 0 | Green |  |  | 10000 | 10000 | 100000 | 40000 | 30000 |  |  |  |  | 2022-09-12 - This project has a high likelihood of pushing to 2023 due to lack of PM resources. Region is reviewing feasibility of completing in 2022. | 2022-09-12 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Linden | LN - LINDEN STATION |  |  | 30000 | 170000 |  |  | 0 | Aiken, Elaine | Klumpp, Eugene | N/A |  | 1 | 19813 |  | Guest, ProSight | Independent | Aqua | 2016-07-29 | Int - Planned Corr & FI
Linden 601 Sump Repairs | Item | Open | MEXP | LN00000E2209 | Maintenance Framework | 1980184 | Wojton, Brian | East | 6. Operational | Defined | Facility Integrity | 6971 | 20000 |  | 26971.37 | 6971 | 20000 | Red |  | 60000 | 60000 | -33029 |  |  | 35000 |  | 60000 | 95000 | Supplemental | 95000 | 75556 | 20000 | 95556 | No | Green | 2022-11-01 | 2022-05-10 | 2022-05-10 | 2022-08-30 | 2022-12-31 |  |  | 6470.46 | 14.92 | 485.99 | [7 empty] | 5000 | 15000 | [7 empty] | 04/20/2023 - canopies ordered via CC by Ops. Installation in June. 1/10/2023 Supplement request to be submitted. 12/01/2022 - 601 separator and sump cleaned and inspected. 601 separator patched and lined. 602 separator was cleaned, inspected and lined. 9/22/2022 - work pushed to Nov. by Ops to help with thermal relief concerns into the sump. 8/8/2022 - work scheduled to start in late Aug. | 2023-05-08 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Linden | LN - LINDEN STATION |  | 6971 | 20000 |  |  | 68584 |  | Aiken, Elaine | Klumpp, Eugene |  |  | 1 | 38430 |  | Administrator, System | Independent | Aqua | 2020-08-31 | Int - Planned Corr & FI
Linden 603 Gas Driver Refurbishment | Item | Open | MCAP | LN00000M2204 | Maintenance Framework | 1937982 | DeSocio, David | East | 7. Closed | Defined | Rotating Equipment | -25880 |  |  | -25880.07 | -25880 | 0 | Green |  |  |  | -25880 |  |  | 286000 |  |  | 286000 | Full | 286000 | 256516 |  | 256516 | No | Green | 2022-01-01 | 2022-01-11 | 2022-01-11 | 2022-11-01 | 2022-11-30 |  |  | 11654.22 | -4269.01 | -33265.28 | [16 empty] | 3/28/2023 Reclass submitted to move $34,243 off project and onto Opex account 62865. 3/2/23 - Costs came in less than expedted. 1/18/2023 reclass submitted : $1,031 from cancelled BPNQP projects, M2204 and M2205. 01/04/2023 overaccrual for November. | 2023-03-28 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  | -25880 | 0 |  |  | 282396 |  | Posipanko, Dan | Klumpp, Eugene | N/A |  | 1 | 21057 |  | Guest, ProSight | Independent | Aqua | 2016-09-06 | Other Programs
Linden 607 Booster 1&2 Upgrade | Item | Open | MCAP | LN00000M2304 | Maintenance Framework | 2075100 | DeSocio, David | East | 3. Active | Defined | Rotating Equipment | 34452 | 110000 |  | 144452.28 | 145000 | -548 | Yellow | 145000 |  | 145000 | -548 |  |  | 145475 |  |  | 145475 | Full | 145475 | 34452 | 110000 | 144452 | No | Green | 2023-04-01 | 2023-01-13 | 2023-01-13 | 2023-07-01 | 2023-06-30 | [5 empty] | 34452.28 | 35000 | 35000 | -548 | Yellow |  |  | 0 | 20000 | 40000 | 50000 | [5 empty] | One booster at a time will be taken out of service, upgraded, then put back into service to maintain line uptime. <NQF> | 2022-09-14 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  |  | 54452 | 90000 |  |  |  | Posipanko, Dan |  |  |  | 1 | 45256 |  | Guest, ProSight | Independent | Aqua | 2022-08-24 | Other Programs
Linden Aerial Switch Repair | Item | Open | MCAP | LN00000M2218 | Maintenance Framework | 2045861 | DeSocio, David | East | 7. Closed | Defined | Electrical | 21667 |  |  | 21666.51 | 20776 | 891 | Yellow | 20000 |  | 20000 | 1667 |  |  | 20000 |  |  | 20000 | Full | 20000 | 21667 |  | 21667 | No | Green | 2023-02-01 | 2022-11-25 | 2022-11-25 | 2022-12-20 | 2022-12-02 |  |  |  | 978.58 | 19797.06 | 890.87 |  |  | 891 | Red | [13 empty] | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  | 20776 | 891 |  |  |  |  | Ashley, Robert | Klug, Wayne |  |  | 1 | 44413 |  | Guest, ProSight | Independent | Aqua | 2022-08-04 | Other Programs
Linden Atmospheric Refurbishment | Item | Open | MCAP | LN00000M2314 | Maintenance Framework | 2095937 | Occhi, Edward | East | 3. Active | Defined | Atmospheric Corrosion |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 |  |  | 100190 |  |  | 100190 | Full | 100190 |  | 100000 | 100000 | No | Green | 2023-08-01 | 2023-03-23 | 2023-03-23 | 2023-10-31 | 2023-06-30 | [13 empty] | 0 | 0 | 30000 | 40000 | 30000 | [5 empty] | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Linden | LN - LINDEN STATION |  |  | 0 | 70000 | 30000 |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45081 |  | Guest, ProSight | Independent | Aqua | 2022-08-18 | Int - Planned Corr & FI
Linden B3 Pump and Motor Overhaul | Item | Open | MCAP | LN00000M2306 | Maintenance Framework | 2076554 | DeSocio, David | East | 3. Active | Defined | Rotating Equipment | 91800 | 50000 |  | 141800 | 140000 | 1800 | Yellow | 140000 |  | 140000 | 1800 |  |  | 139150 |  |  | 139150 | Full | 139150 | 91800 | 50000 | 141800 | No | Green | 2023-03-01 | 2023-01-23 | 2023-01-23 | 2023-07-01 | 2023-05-31 |  |  |  |  | 40000 | 51800 | 50000 | 50000 | 1800 | Yellow |  |  | 25000 | 25000 | [9 empty] | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  | 40000 | 101800 |  |  |  |  | Posipanko, Dan | Klumpp, Eugene |  |  | 1 | 37580 |  | Guest, ProSight | Independent | Aqua | 2020-08-10 | Other Programs
Linden Catwalk Installation | Item | Open | MCAP | LN00000M2305 | Maintenance Framework | 2074858 | DeSocio, David | East | 6. Operational | Defined | East | 49400 | 0 |  | 49400 | 50000 | -600 | Yellow | 50000 |  | 50000 | -600 |  |  | 50095 |  |  | 50095 | Full | 50095 | 49400 | 0 | 49400 | No | Green | 2023-04-01 | 2023-01-10 | 2023-01-10 | 2023-06-01 | 2023-03-31 | [5 empty] | 49400 | 30000 | 30000 | 19400 | Red |  | WorkAhead of Schedule | 0 | 0 |  | 0 | [7 empty] | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  |  | 49400 | 0 |  |  |  | Orischak, Bob | Klumpp, Eugene |  |  | 1 | 45232 |  | Guest, ProSight | Independent | Aqua | 2022-08-23 | Other Programs
Linden Citgo Communications | Item | Open | MCAP | LN00000M2303 | Maintenance Framework | 2074139 | DeSocio, David | East | 6. Operational | Emergent | Leak Detection | 20000 |  |  | 20000 | 20000 | 0 | Green |  |  |  | 20000 |  |  | 20240 |  |  | 20240 | Full | 20240 | 20000 |  | 20000 | No | Green | 2023-04-01 | 2023-01-05 | 2023-01-05 | 2022-05-01 | 2023-05-01 | [5 empty] | 20000 | 20000 | 20000 | 0 | Green | [13 empty] | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Linden | LN - LINDEN STATION |  |  | 20000 |  |  |  |  | Guenther, Steve | Klumpp, Eugene |  |  | 1 | 46400 |  | Meitzler, Antoinette | Independent | Aqua | 2022-12-22
Linden Communications Room Air Conditioning Replacement | Item | Open | MCAP | LN00000M2301 | Maintenance Framework | 2051750 | DeSocio, David | East | 7. Closed | Defined | East | 24305 | -3000 |  | 21304.93 | 21305 | 0 | Green | 20000 |  | 20000 | 1305 |  |  | 20000 |  |  | 20000 | Full | 20000 | 31100 | -3000 | 28100 | No | Green | 2022-12-01 | 2022-12-07 | 2022-12-07 | 2023-04-01 | 2023-02-01 |  |  | 15468.49 | 8455.92 | 380.52 | [14 empty] | -3000 |  |  |  | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  | 24305 | 0 |  | -3000 | 6795 |  | Orischak, Bob | Klumpp, Eugene |  |  | 1 | 45255 |  | Guest, ProSight | Independent | Aqua | 2022-08-24 | Other Programs
Linden L601 Booster 3 PLC Programming | Item | Open | MEXP | LN00000E2301 | Exempt | 2051756 | DeSocio, David | East | 3. Active | Defined | East | 6668 |  |  | 6667.5 | 25560 | -18893 | Red | 25000 |  | 25000 | -18333 |  |  | 25000 |  |  | 25000 | Full | 25000 | 6668 |  | 6668 | No | Green | 2023-02-01 | 2022-12-07 | 2022-12-07 | 2023-03-01 | 2023-03-31 |  |  |  | 25000 | 560 | -18892.5 |  |  | -18893 | Red |  | Buckeye/Customer Schedule | [9 empty] | 3/2/23 - Vendor needed more time to complete programming and receive parts needed. 5/5/23 - Delay due to Operations Schedule | 2023-05-05 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Linden | LN - LINDEN STATION |  | 25560 | -18893 |  |  |  |  | Orischak, Bob | Klumpp, Eugene |  |  | 1 | 44415 |  | Guest, ProSight | Independent | Aqua | 2022-08-04 | IT
Linden L601 Surge Protection Installation | Item | Open | MCAP | LN00000M2313 | Project Framework | 2094887 | DeSocio, David | East | 3. Active | Defined | Transient/Surge Mitigation |  | 235000 |  | 235000 | 235000 | 0 | Green | 235000 |  | 235000 | 0 |  |  | 235460 |  |  | 235460 | Full | 235460 |  | 235000 | 235000 | No | Green | 2023-05-01 | 2023-03-10 | 2023-03-10 | 2023-08-01 | 2023-06-09 | [12 empty] | 10000 | 10000 | 90000 | 95000 | 30000 |  |  |  |  | 12/5/2022 - Work will take place in 2023. | 2022-12-05 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  |  | 20000 | 215000 |  |  |  | DiPillo, Evan | Klumpp, Eugene |  |  | 1 | 40541 |  | Guest, ProSight | Independent |  | 2021-07-17 | Other Programs
Linden L603 Install 16" Check Valve for Surge Mitigation | Item | Open | MCAP | LN00000M2312 | Project Framework | 2094888 | DeSocio, David | East | 3. Active | Defined | Transient/Surge Mitigation |  | 130000 |  | 130000 | 130000 | 0 | Green |  |  |  | 130000 |  |  | 129930 |  |  | 129930 | Full | 129930 |  | 130000 | 130000 | No | Green | 2023-05-01 | 2023-03-10 | 2023-03-10 | 2023-08-01 | 2023-09-30 | [12 empty] | 10000 | 0 |  | 0 | 0 |  | 60000 | 60000 |  | 4/26/23 - project on hold until 4th qtr of 2023 11/2/2022 project on hold until next year. 10/4/2022 project to be done next year. 8.1.22.DLC: Moved funds from deferred L601 surge mitigation project | 2023-04-26 | Schultz, Amy |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  |  | 10000 | 0 | 120000 |  | 0 | DiPillo, Evan | Klumpp, Eugene |  |  | 1 | 41657 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Linden L604 Rahway River Valve Relocation | Item | Open | MCAP | LN00000M2101 | Exempt | 1801017 | Garcia, Francisco | East | 5. Deferred | Unplanned | Valves |  | 1 |  | 1 | 1 | 0 | Green |  |  |  | 1 |  |  | 140000 |  |  | 140000 | Phase | 140000 | 120829 | 1 | 120830 | No | Green | 2021-02-01 | 2021-01-01 | 2021-01-01 | 2021-08-01 | 2021-08-01 | [19 empty] | 1 |  | 10/7/21 - Lower priority. 3/8/21 - Working on permitting. | 2021-10-07 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  |  | 0 |  | 1 | 6757 |  | Oey, Alex | Bassani, Joel D. | N/A |  | 1 | 31751 |  | Samilo, Gregory | Independent | Aqua | 2018-09-21 | Other Programs
Linden L620 Delaware River Mainline Actuator Replacement | Item | Open | MCAP | LN00000M2309 | Maintenance Framework | 2077053 | DeSocio, David | East | 3. Active | Defined | Valves | 69166 | 100000 |  | 169165.74 | 150000 | 19166 | Red | 150000 |  | 150000 | 19166 |  |  | 150385 |  |  | 150385 |  | 150385 | 69166 | 100000 | 169166 | Yes | Red | 2023-04-01 | 2023-01-30 | 2023-01-30 | 2023-10-01 | 2023-06-30 | [5 empty] | 69165.74 | 50000 | 50000 | 19166 | Red |  |  | 0 | 20000 | 40000 | 40000 | [7 empty] | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | FZ620XX - FLEM VALVE SITE TO PA S/L-20IN |  |  | 89166 | 80000 |  |  |  | Oey, Alex | Klug, Wayne |  |  | 1 | 44331 |  | Guest, ProSight | Independent | Aqua | 2022-07-29 | Other Programs
Linden L620 Flemington Mainline Actuator Replacement | Item | Open | MCAP | LN00000M2310 | Maintenance Framework | 2077052 | DeSocio, David | East | 3. Active | Defined | Valves | 49600 | 100000 |  | 149599.84 | 150000 | -400 | Yellow | 150000 |  | 150000 | -400 |  |  | 150285 |  |  | 150285 | Full | 150285 | 49600 | 100000 | 149600 | No | Green | 2023-04-01 | 2023-01-30 | 2023-01-30 | 2023-10-01 | 2023-06-30 | [5 empty] | 49599.84 | 50000 | 50000 | -400 | Yellow |  |  | 0 | 20000 |  | 40000 | 40000 | [6 empty] | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | FZ - FLEMINGTON VALVE SITE |  |  | 69600 | 80000 |  |  |  | Oey, Alex | Klumpp, Eugene |  |  | 1 | 44430 |  | Guest, ProSight | Independent | Aqua | 2022-08-04 | Other Programs
Linden Paving Phase 3 - Slip Trip Falls | Item | Open | MCAP | LN00000M2217 | Maintenance Framework | 2045635 | DeSocio, David | East | 7. Closed | Defined | East | 52478 |  |  | 52478.05 | 52478 | 0 | Green | 50000 |  | 50000 | 2478 |  |  | 51000 |  |  | 51000 | Full | 51000 | 55758 |  | 55758 | No | Green | 2022-12-01 | 2022-11-18 | 2022-11-18 | 2022-12-20 | 2022-12-07 |  |  | 50121.1 | 2255.45 | 101.5 | [18 empty] | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  | 52478 | 0 |  |  | 3280 |  | Orischak, Bob | Klug, Wayne |  |  | 1 | 44260 |  | Guest, ProSight | Independent | Aqua | 2022-07-26 | Other Programs
Linden Phase 2 Dikes and Swales | Item | Open | MCAP | LN00000M2308 | Maintenance Framework | 2077584 | Wojton, Brian | East | 3. Active | Defined | East | 28688 | 25000 |  | 53687.74 | 47997 | 5691 | Red | 50000 |  | 50000 | 3688 |  |  | 50095 |  |  | 50095 | Phase | 50095 | 28688 | 25000 | 53688 | No | Green | 2023-03-01 | 2023-01-31 | 2023-01-31 | 2023-06-15 | 2023-05-31 |  |  |  |  | 7996.88 | 20690.86 | 15000 | 15000 | 5691 | Red |  |  | 25000 | [8 empty] | 05/08/2023 - south tank field work is complete and north field IP. 04/21/23 - project is in progress and is awarded to Furino. | 2023-05-08 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  | 7997 | 45691 |  |  |  |  | Orischak, Bob | Klumpp, Eugene |  |  | 1 | 45413 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Other Programs
Linden Pressure Transmitter ReRange Initiative | Item | Open | MCAP | LN00000M2315 | Maintenance Framework | 2095648 | DeSocio, David | East | 6. Operational | Drawdown | Instrumentation & Controls | 65097 | 0 |  | 65096.76 | 68000 | -2903 | Yellow |  | 68320 | 68320 | -3223 |  |  | 68320 |  |  | 68320 | Full | 68320 | 65097 | 0 | 65097 | No | Green | 2023-04-01 | 2023-03-20 | 2023-03-20 | 2023-12-01 | 2023-05-31 | [5 empty] | 65096.76 | 20000 | 20000 | 45097 | Red |  | WorkAhead of Schedule | 0 | 0 |  | 0 | [7 empty] | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  |  | 65097 | 0 |  |  |  | Forsey, Frank | Klumpp, Eugene |  |  | 1 | 44281 |  | Guest, ProSight | Independent | Aqua | 2022-07-27 | Other Programs
Linden Racoon Damage | Item | Open | MEXP | LN00000E2307 | Maintenance Framework | 2076587 | Orischak, Bob | East | 3. Active | Defined | East | 27536 |  |  | 27536.43 |  | 27536 | Red | 30000 |  | 30000 | -2464 |  |  | 30240 |  |  | 30240 | Full | 30240 | 27536 |  | 27536 | No | Green | 2023-04-01 | 2023-01-25 | 2023-01-25 | 2023-05-25 | 2023-03-31 | [5 empty] | 27536.43 |  |  | 27536 | Red |  | WorkAhead of Schedule | [9 empty] | 5/1/23 RLO Project is complete. Hold open for one month to confirm invoices are all in and paid 4/3/23 RLO Contractor estimates are coming back above money available. I have asked operations to see about reducing the scope of work to fit budget. They are going back to contractor. This project prob won't occur till May. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Linden | LN - LINDEN STATION |  |  | 27536 |  |  |  |  | Orischak, Bob |  |  |  | 1 | 44261 |  | Guest, ProSight | Independent | Aqua | 2022-07-26 | Other Programs
Linden Station (LN) Tank 109 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | LN00000E2304 | Maintenance Framework | 2074850 | Marrocco, Alex | East | 6. Operational | Defined | Tanks | 10000 | 20000 |  | 30000 | 10000 | 20000 | Red | 10000 |  | 10000 | 20000 |  |  | 11000 |  |  | 11000 | Full | 11000 | 10000 | 20000 | 30000 | Yes | Red | 2023-04-01 | 2023-01-09 | 2023-01-09 | 2023-01-31 | 2023-05-01 | [5 empty] | 10000 | 10000 | 10000 | 0 | Green |  |  | 20000 | [10 empty] | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | Linden | LN - LINDEN STATION |  |  | 30000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44832 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Linden Station (LN) Tank 116 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | LN00000E2305 | Maintenance Framework | 2074851 | Marrocco, Alex | East | 7. Closed | Defined | Tanks | 5920 |  |  | 5920 | 5920 | 0 | Green | 10000 |  | 10000 | -4080 |  |  | 11000 |  |  | 11000 | Full | 11000 | 5920 |  | 5920 | No | Green | 2023-02-01 | 2023-01-09 | 2023-01-09 | 2023-01-31 | 2023-01-31 |  |  |  | 5920 | [17 empty] | 2/3/2023 late invoicing. | 2023-02-03 | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | Linden | LN - LINDEN STATION |  | 5920 | 0 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44833 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Linden Station (LN) Tank 91 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | LN00000E2303 | Maintenance Framework | 2074848 | Marrocco, Alex | East | 3. Active | Defined | Tanks | 10000 |  |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 |  |  | 11000 |  |  | 11000 | Full | 11000 | 10000 |  | 10000 | No | Green | 2023-04-01 | 2023-01-09 | 2023-01-09 | 2023-01-31 | 2023-12-31 | [5 empty] | 10000 | 10000 | 10000 | 0 | Green | [13 empty] | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | Linden | LN - LINDEN STATION |  |  | 10000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44831 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Linden T156 Foam Line Repair | Item | Open | MEXP | LN00000E2302 | Maintenance Framework | 2053662 | Wojton, Brian | East | 3. Active | Defined | Fire Protection |  | 40000 |  | 40000 | 50000 | -10000 | Red | 50000 |  | 50000 | -10000 |  |  | 50000 |  |  | 50000 | Full | 50000 |  | 40000 | 40000 | No | Green | 2023-05-01 | 2022-12-27 | 2022-12-27 | 2023-03-01 | 2023-05-31 | [6 empty] | 10000 | 10000 | -10000 | Red |  |  | 20000 | 20000 | [7 empty] | 05/02/2023 - work delayed due to weather. Will start in May. 04/21/2023 - project is in progress and is awarded to Furino. | 2023-05-08 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Linden | LN - LINDEN STATION |  |  | 40000 |  |  |  |  | Jakubowski, Gregory |  |  |  | 1 | 44417 |  | Guest, ProSight | Independent | Aqua | 2022-08-04 | Other Programs
Linden Tank 105 and 106 Lighting System Repair | Item | Open | MEXP | LN00000E2213 | Maintenance Framework | 2051842 | Orischak, Bob | East | 7. Closed | Drawdown | East | -2639 |  |  | -2639.49 | -2639 | 0 | Green |  |  |  | -2639 |  |  | 16000 |  |  | 16000 | Full | 16000 | 13361 |  | 13361 | No | Green | 2022-12-01 | 2022-12-08 | 2022-12-08 | 2022-12-16 | 2022-12-16 |  |  | 10665.51 | -13305 | [17 empty] | 3/7/2023 - Closed WO/PO, and set OPPM status to 'Closed' MCS. 3/1/2023 RLO ready to close. 2/22/2023 RLO checking with ops 1/31/23 RLO Still waiting on contractor invoices. Need to re-accrue 1/3/2023 - Project operational, awaiting invoice. | 2023-03-07 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Linden | LN - LINDEN STATION |  | -2639 | 0 |  |  | 16000 |  | Orischak, Bob | Klumpp, Eugene | N/A |  | 1 | 46334 |  | Orischak, Bob | JDE Child | Burnt Orange | 2022-12-08 | Other Programs
LINDEN Tank 115/16 and 98/99 Dike Rebuild and Regrading | Item | Open | MEXP | LN00000E2308 | Maintenance Framework | 2077117 | DeSocio, David | East | 3. Active | Defined | Secondary Containment | 30198 | 30000 |  | 60198.46 | 60000 | 198 | Yellow | 60000 |  | 60000 | 198 |  |  | 59400 |  |  | 59400 | Full | 59400 | 30198 | 30000 | 60198 | No | Green | 2023-04-01 | 2023-01-31 | 2023-01-31 | 2023-08-01 | 2023-03-31 | [5 empty] | 30198.46 | 30000 | 30000 | 198 | Yellow |  |  | 30000 | [10 empty] | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Linden | LN - LINDEN STATION |  |  | 60198 |  |  |  |  | Spari, Markella | Klumpp, Eugene | N/A |  | 1 | 24780 |  | Guest, ProSight | Independent | Aqua | 2017-08-02 | Other Programs
Linden Tank 118 Booster Pump Repair 2022 | Item | Open | MCAP | LN00000M2214 | Maintenance Framework | 1989778 | Orischak, Bob | East | 7. Closed | Drawdown | East | -46 |  |  | -45.89 | -46 | 0 | Green |  |  |  | -46 |  |  | 89000 |  |  | 89000 | Full | 89000 | 100193 |  | 100193 | No | Green | 2022-07-01 | 2022-07-12 | 2022-07-12 | 2022-09-01 | 2022-11-30 |  |  | -45.89 | [18 empty] | 1/9/2022 - Closed WO/PO, set OPPM project status to 'Closed'. MCS. 12/1/2022 RLO READY TO CLOSE at end of Dec 11/2/2022 RLO Waiting on Operations to update me on the status. 10/3/2022 RLO Pump came in, waiting for vac truck service. . 9/1/2022 - RLO I will work with local ops to determine the repair time. Actual charges were for shipping. | 2023-01-09 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  | -46 | 0 |  |  | 100238 |  | Orischak, Bob | Klumpp, Eugene |  |  | 1 | 44082 |  | Meitzler, Antoinette | Independent | Aqua | 2022-07-07 | Other Programs
LINDEN Tank 126 Berm Refurbishment | Item | Open | MCAP | LN00000M2311 | Maintenance Framework | 2083800 | DeSocio, David | East | 3. Active | Defined | Secondary Containment |  | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 |  |  | 30240 |  |  | 30240 | Full | 30240 |  | 30000 | 30000 | No | Green | 2023-07-01 | 2023-02-01 | 2023-02-01 | 2023-10-01 | 2023-08-31 | [14 empty] | 30000 | 0 | [7 empty] | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  |  | 0 | 30000 |  |  |  | Clark, Dave | Klug, Wayne | N/A |  | 1 | 24781 |  | Guest, ProSight | Independent | Aqua | 2017-08-02 | Other Programs
Linden Tank 152 607 Suction Valve | Item | Open | MCAP | LN00000M2307 | Maintenance Framework | 2077034 | DeSocio, David | East | 7. Closed | Drawdown | East | 47068 | 1 |  | 47069.46 | 42777 | 4293 | Red |  | 39848 | 39848 | 7221 |  |  | 39848 |  |  | 39848 | Full | 39848 | 47068 | 1 | 47069 | No | Green | 2023-02-01 | 2023-01-30 | 2023-01-30 | 2023-04-01 | 2023-04-01 |  |  |  | 4731.43 | 11544.31 | 30792.72 | 26500 | 26500 | 4293 | Red | [9 empty] | 1 |  |  |  | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  | 16276 | 30793 |  | 1 |  |  | Orischak, Bob | Klug, Wayne |  |  | 1 | 46552 |  | Meitzler, Antoinette | Independent | Aqua | 2023-01-26 | Other Programs
Linden Tank Surge Protection Phase III | Item | Open | MCAP | LN00000M2302 | Maintenance Framework | 2051755 | DeSocio, David | East | 3. Active | Defined | Instrumentation & Controls | 22695 | 7000 |  | 29694.99 | 32608 | -2913 | Yellow | 30000 |  | 30000 | -305 |  |  | 30000 |  |  | 30000 | Full | 30000 | 22695 | 7000 | 29695 | No | Green | 2023-01-01 | 2022-12-07 | 2022-12-07 | 2023-03-01 | 2023-05-01 |  |  | 10000 | 450 | 2157.8 | 10087.19 | 10000 | 10000 | 87 | Yellow |  |  | 7000 | [8 empty] | 3/2/23 - Material delivery delay. Expected delivery 3/12/23 | 2023-03-02 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  | 12608 | 17087 |  |  |  |  | Forsey, Frank | Klumpp, Eugene |  |  | 1 | 44253 |  | Guest, ProSight | Independent | Aqua | 2022-07-26 | Other Programs
Linden VFD Building HVAC Coil Repair 2023 | Item | Open | MEXP | LN00000E2306 | Maintenance Framework | 2075752 | Orischak, Bob | East | 3. Active | Drawdown | East |  | 45000 |  | 45000 | 45000 | 0 | Green |  |  |  | 45000 |  |  | 45000 |  |  | 45000 | Full | 45000 |  | 45000 | 45000 | No | Green | 2023-07-01 | 2023-01-18 | 2023-01-18 | 2023-03-25 | 2023-03-25 | [6 empty] | 0 | 0 | 0 | Green |  |  |  |  | 45000 | [6 empty] | 5/1/23 RLO Materials did not arrive and are on Back order till July. 4/3/23 RLO Materials should be arriving at HVAC contractor this month and should be scheduled to install next month. 2/22/23 RLO Project just approved and parts are 8 weeks out. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Linden | LN - LINDEN STATION |  |  | 0 | 45000 |  |  |  | Orischak, Bob | Klumpp, Eugene | N/A |  | 1 | 46491 |  | Orischak, Bob | JDE Child | Burnt Orange | 2023-01-18 | Other Programs
LIPL Inwood Removal of Door Oliver Filters | Item | Candidate | MEXP |  | Maintenance Framework |  | Bodner, Jordan | East | 1. Proposed |  | Facility Integrity |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 | [9 empty] | 100000 | 100000 | No | Green | 2023-09-01 |  |  |  | 2023-09-30 | [16 empty] | 100000 | [8 empty] | East | Pipelines and Terminals | Station/Terminal |  | Long Island | IW - INWOOD |  |  | 0 | 100000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 33663 |  | DeSocio, David | Independent | Aqua | 2019-07-05 | Int - Planned Corr & FI
LN607NW - 2021 GEO+AMFL ILI | Item | Open | MEXP | LN607NWE2101 | Exempt | 1804313 | Keppel, Nicholas | East | 6. Operational | Defined | Assessments | -5375 |  |  | -5375 | 0 | -5375 | Red |  |  |  | -5375 |  |  | 280500 | 14500 |  | 295000 | Full | 295000 | 249188 |  | 249188 | No | Green | 2021-07-01 | 2021-01-26 | 2021-01-26 | 2021-12-31 | 2022-05-19 |  |  | 0 | -5375 | 5375 | -5375 |  |  | -5375 | Red | [11 empty] | 1/5/2023 - Project completed in May 2022. | 2023-01-05 | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Linden | LN607NW - LINDEN TO NEWARK AIRPORT |  | 0 | -5375 |  |  | 24968 |  | Bartal, Nick | Bassani, Joel D. |  |  | 1 | 37037 |  | Administrator, System | JDE Child | Burnt Orange | 2020-07-13 | Int - Assessments
LOng Island City 602L Prover Repair 2023 | Item | Open | MEXP | LZ602XXE2301 | Maintenance Framework | 2109973 | Orischak, Bob | East | 2. Pending AFE | Drawdown | East |  | 20001 |  | 20001 |  | 20001 | Red |  | 20000 | 20000 | 1 |  |  | 20000 |  |  | 20000 | Full | 20000 |  | 20001 | 20001 | No | Green | 2023-07-01 | 2023-04-17 | 2023-04-17 | 2023-12-31 | 2023-12-31 | [14 empty] | 20000 |  |  |  |  | 1 |  |  |  | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Long Island | LZ602XX - LINDEN TO NY S/L (GAS) LIPL |  |  | 0 | 20000 | 1 |  |  | Orischak, Bob | Klumpp, Eugene | N/A |  | 1 | 46952 |  | Orischak, Bob | JDE Child | Burnt Orange | 2023-04-17
Long Island Test Station Repair / Replacement | Item | Open | MEXP | JK00000E2202 | Maintenance Framework | 1939601 | Occhi, Edward | East | 7. Closed | Defined | Cathodic Protection | 210 |  |  | 210.05 | 210 | 0 | Green |  |  |  | 210 |  |  | 60000 |  |  | 60000 | Full | 60000 | 60472 |  | 60472 | No | Green | 2022-06-01 | 2022-01-27 | 2022-01-27 | 2022-12-31 | 2022-11-30 |  |  | 210.05 | [20 empty] | Walker, Carol |  | East | Pipelines and Terminals | Corrosion |  | Long Island | LY - LONG ISLAND CITY TERMINAL |  | 210 | 0 |  |  | 60262 |  | Geib, Rob | Geib, Robert |  |  | 1 | 40610 |  | Guest, ProSight | Independent | Aqua | 2021-07-23 | Int - Planned Corr & FI
Long Island Valve 17B Access Stairs Replacement | Item | Open | MCAP | JK00000M2301 | Maintenance Framework | 2074859 | DeSocio, David | East | 3. Active | Defined | East |  | 70000 |  | 70000 | 70000 | 0 | Green | 70000 |  | 70000 | 0 |  |  | 69900 |  |  | 69900 | Full | 69900 |  | 70000 | 70000 | No | Green | 2023-06-01 | 2023-01-10 | 2023-01-10 | 2023-06-01 | 2023-04-30 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 30000 | 40000 | [8 empty] | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Long Island | JK - JFK TERMINAL |  |  | 30000 | 40000 |  |  |  | Orischak, Bob | Klumpp, Eugene |  |  | 1 | 45228 |  | Guest, ProSight | Independent | Aqua | 2022-08-23 | Other Programs
LP806BW Digs – From 2021 GEO+MFL ILI | Item | Open | MCAP | LP806BWM2201 | Maintenance Framework | 1990668 | Keppel, Nicholas | East | 6. Operational | Drawdown | Pipeline Digs | 849672 |  |  | 849672.36 | 827216 | 22457 | Yellow |  |  |  | 849672 |  |  | 789000 |  |  | 789000 | Full | 789000 | 895719 |  | 895719 | Yes | Red | 2022-09-01 | 2022-06-16 | 2022-06-16 | 2022-11-30 | 2023-03-10 |  |  | 18409.82 | 394608.72 | 414196.99 | 22456.83 |  |  | 22457 | Red | [11 empty] | 5/1/2023-Will be submitting a supplemental. Any additional spend on this project will be negligible. 4/7/2023 - Variance due to extremely poor site conditions requiring longer execution time, as well as longer setup time due to laying of timber access mats | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | LP806BW - LIVERPOOL TO BREWERTON |  | 827216 | 22457 |  |  | 46047 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 42760 |  | Guest, ProSight | Independent | Aqua | 2022-01-14 | Int- Planned Digs
Ludlow Video System | Item | Open | MCAP | LD00000M2301 | Maintenance Framework | 2112058 | Mohr, David | East | 3. Active | Defined | Security & Cameras |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 |  |  | 40158 |  |  | 40158 | Full | 40158 |  | 40000 | 40000 | No | Green | 2023-08-01 | 2023-04-21 | 2023-04-21 | 2023-08-31 | 2023-06-30 | [15 empty] | 40000 | [5 empty] | 5/1/2023 UTI selected as vendor. Waiting for electrical quote to start project. 3/1/2023 Conference call scheduled with vendors to discuss scope for proposal. DRM 2/2/2023 Project overview held with Chris Clark. Contractors to be contacted for job/site walk. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Jet Lines | LD - LUDLOW STATION |  |  | 0 | 40000 |  |  |  | Clark, Chris | Clark, Chris B | N/A |  | 1 | 30825 |  | DeSocio, David | Independent | Aqua | 2018-08-23 | Other Programs
Macungie (BETZM) - Secondary containment improvements | Item | Open | MEXP | BETZM00E2301 | Maintenance Framework |  | Pepe, David | East | 3. Active | Defined | Secondary Containment | 11948 | 114000 |  | 125947.5 | 174018 | -48070 | Red | 174000 |  | 174000 | -48053 |  |  | 79200 |  |  | 79200 | Phase | 79200 | 11948 | 114000 | 125948 | No | Green | 2023-03-01 | 2023-02-21 | 2023-02-21 | 2024-12-31 | 2023-09-30 |  |  |  |  | 30017.5 | -18070 | 30000 | 30000 | -48070 | Red |  | Forecasting | 39000 |  | 50000 | 20000 | 5000 |  |  |  |  | 2023/5/4 - Engineering is now complete and ready for bid. Construction expected in July, completed in August. 2023/4/4-Engineering underway, waiting for drawings. 2023/03/02 - Engineering Mar/Apr, and then bidding May/June, construction July/Aug.12/09/2022 DJP waiting on the recommendations from engineering firm. | 2023-05-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Macungie Terminal | BETZG - BET MACUNGIE TERMINAL |  | 30018 | 20930 | 75000 |  |  |  | Spari, Markella | Mengel, Jason L. |  |  | 1 | 45171 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
Macungie 69kV Engineering Survey | Item | Open | MCAP | ZG00000M2203 | Maintenance Framework | 1938273 | Mohr, David | East | 3. Active | Defined | Electrical | 512 |  |  | 511.79 | 5519 | -5007 | Red |  |  |  | 512 |  |  | 24000 |  |  | 24000 | Full | 24000 | 19482 |  | 19482 | No | Green | 2022-03-01 | 2022-01-14 | 2022-01-14 | 2022-08-31 | 2023-04-30 |  |  | 5143.85 | -4815.55 | 90.94 | 92.55 | 5100 | 5100 | -5007 | Red | [11 empty] | 4/1/2023 variance due to 69kv switch not received. DRM 2/2/2023 - Re-opening this project due to wanting to show accrual for material not having been received. (Outstanding material is a 5.1K. 69KV switch). 12/22/2022 - Closed WO/PO, set OPPM status to 'Closed'. 10/5/2022-Can close. 7/5/2022-Savings. /2/2022 Received InfraRed report and recommended repair report. Awaiting quote to included in 2023 projects. DRM 5/2/2022 Work scheduled for 5/3. DRM 4/1/2022 DRM requested date from PPL and tentatively scheduled for 5/4 3/9/2022 - PO cut for $17.5K to Diefenderfer. MCS. 3/1/2022 DRM Met with Diefenderfer yesterday for updated quote and requested quote from Longo. 2/2/2022 - Had a quote from contractor last year - have reached out for updated quote. | 2023-04-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | ZG - MACUNGIE STATION |  | 419 | 93 |  |  | 18970 |  | Ashley, Robert | Hoover, Bret |  |  | 1 | 41037 |  | Guest, ProSight | Independent | Aqua | 2021-08-05 | Other Programs
Macungie Asset Atmospheric Corrosion Remediation 2023 | Item | Open | MCAP | ZG00000M2305 | Maintenance Framework | 2086661 | Gable, Rob | East | 3. Active | Defined | Atmospheric Corrosion |  | 20000 |  | 20000 | 20000 | 0 | Green | 20000 |  | 20000 | 0 |  |  | 20150 |  |  | 20150 | Full | 20150 |  | 20000 | 20000 | No | Green | 2023-07-01 | 2023-02-27 | 2023-02-27 | 2023-10-01 | 2023-07-31 | [14 empty] | 10000 | 5000 | 5000 |  |  |  |  | 5/2/2023 RAG - Work to begin during Q3. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 0 | 20000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45391 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Macungie Backup CC - new cameras | Item | Open | MCAP | 1348816M2302 | Maintenance Framework | 2110638 | Pepe, David | East | 3. Active | Defined | Security & Cameras |  | 60000 |  | 60000 | 60000 | 0 | Green | 50000 |  | 50000 | 10000 |  |  | 63835 |  |  | 63835 | Full | 63835 |  | 60000 | 60000 | No | Green | 2023-06-01 | 2023-04-13 | 2023-04-13 | 2023-06-30 | 2023-02-28 | [13 empty] | 25000 | 35000 | [6 empty] | 2023 05 01 - DJP - AFE approved, equipment ordered. Need to get a confirmation from the equipment vendor on the delivery. 2023 04 05 - DJP - AFE Submitted 2023 03 01 - Changes PM to DJP. Proposal meeting with the equipment vendors due by March 17. I don't expect any spend until June. Need to update the financial forecast notes. | 2023-05-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Corporate | Corporate |  |  | 25000 | 35000 |  |  |  | Clark, Chris | Clark, Chris B | N/A |  | 1 | 26287 |  | Clark, Chris B. | Independent | Aqua | 2017-09-16 | Other Programs
Macungie Backup CC - UPS and Generator Replacement | Item | Open | MCAP | 1348816M2301 | Maintenance Framework | 2110639 | Pepe, David | East | 3. Active | Defined | Electrical | 11133 | 240000 |  | 251132.82 | 240000 | 11133 | Yellow | 265000 |  | 265000 | -13867 |  |  | 660835 |  |  | 660835 | Full | 660835 | 11133 | 580000 | 591133 | No | Green | 2023-04-01 | 2023-04-13 | 2023-04-13 | 2024-04-01 | 2023-08-31 | [5 empty] | 11132.82 |  |  | 11133 | Red |  | Other | 0 | 0 | 20000 | 80000 | 140000 |  |  |  |  | 5/4/2023-Variance due to unexpected need for a 25% downpayment. 4/4/2023 DJP AFE submitted for approval. Bids received for major equipment. 3/1/2023 DJP Putting together the AFE. Received the quotes for the UPS and generator. Adjusted the forecast for the procurement of the equipment in April 2023 installation of the UPS in August and Generator in 2024. | 2023-05-04 | Sautter, Maureen |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Operating Infrastructure |  | East Region Team |  |  |  | 11133 | 240000 |  |  | 340000 | Ashley, Robert | Orischak, Bob |  |  | 1 | 44437 |  | Guest, ProSight | Independent | Aqua | 2022-08-05 | Other Programs
Macungie Demo Old Sun Bldg. and Old Sample building | Item | Open | MEXP |  | Maintenance Framework |  | Wing, Hunter | East | 8. Canceled |  | East |  | 0 |  | 0 | 0 | 0 | Green | 40001 |  | 40001 | -40001 | [9 empty] | 0 | 0 | No | Green |  |  |  |  | 2023-12-31 | [14 empty] | 0 |  |  |  |  | 0 |  | 2.2.23 - HW - Walkdown completed on 1.18.23 and it was determined that this building has already been demoed. Project will be returned to Region's Drawdown. | 2023-02-02 |  |  | East | Pipelines and Terminals | Station/Terminal |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 0 | 0 | 0 |  |  | Orischak, Bob |  |  |  | 1 | 24532 |  | Administrator, System | Independent | Aqua | 2017-07-27 | Other Programs
Macungie Leighton Gravitometer Installation 2023 | Item | Candidate | MCAP |  | Maintenance Framework |  | Mohr, David | East | 1. Proposed |  | East |  | 100000 |  | 100000 | 200000 | -100000 | Red | 200000 |  | 200000 | -100000 | [9 empty] | 100000 | 100000 | No | Green | 2023-09-01 |  |  |  | 2023-09-30 | [15 empty] | 0 | 100000 |  |  |  |  | 5/1/2023 Meeting to discuss options of Lehighton or Bald Mountain for gravitometer location. Clint G. to provide estimate to bring piping above grade. 4/1/2023 Meeting to discuss location of gravitometer. Whether continue forward with Lehighton or reinstall above ground at Bald Mountain. Meeting schedule week of 4/10. 3/1/2023 Site visit scheduled for 3/1- with electrical and mechanical contractor. DRM | 2023-05-02 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | LE701DP - LEHIGHTON TO DUPONT-16IN |  |  | 0 | 100000 |  |  |  | Orischak, Bob | Orischak, Bob |  |  | 1 | 45368 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Other Programs
Macungie North Terminal 1 Tank 96 Rack Pump Replacement | Item | Open | MCAP | BETZM00M2302 | Maintenance Framework | 2052235 | Pepe, David | East | 3. Active | Defined | Rotating Equipment | 11513 | 90000 |  | 101513.48 | 102000 | -487 | Yellow | 90000 |  | 90000 | 11513 |  |  | 115116 |  |  | 115116 | Full | 115116 | 11513 | 90000 | 101513 | No | Green | 2023-04-01 | 2023-01-03 | 2023-01-03 | 2023-07-01 | 2023-08-31 | [5 empty] | 11513.48 | 12000 | 12000 | -487 | Yellow |  |  |  | 15000 | 75000 | [6 empty] | 5/4/2023 - Still waiting on equipment, expecting it in June. Construction in July. 4/4/2023-Expecting pump on-site in April 3/1/2023 - DJP - Checking on the VFD delivery from manufacturer distributor. 2/3/2023 - Pump doesn't arrive until April 2023, the VFD will come in June, expecting construction in July. 12/19/2022 DJP Interim Approved and long lead pump and VFD requisitioned. | 2023-05-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Terminal | BETZM - BET MACUNGIE #1 & 2 |  |  | 26513 | 75000 |  |  |  | Posipanko, Dan | Posipanko, Daniel A. | N/A |  | 1 | 25114 |  | Guest, ProSight | Independent | Aqua | 2017-08-22 | Other Programs
Macungie Pipeline 2000HP Motor Refurbishment 2023 | Item | Open | MCAP | ZG00000M2311 | Maintenance Framework | 2096511 | Orischak, Bob | East | 3. Active | Drawdown | Rotating Equipment |  | 95000 |  | 95000 | 95000 | 0 | Green |  | 99025 | 99025 | -4025 |  |  | 99025 |  |  | 99025 | Full | 99025 |  | 95000 | 95000 | No | Green | 2023-06-01 | 2023-03-30 | 2023-03-30 | 2023-05-20 | 2023-05-03 | [12 empty] | 0 | 90000 | 5000 | [6 empty] | 5/1/23 RLO Vendor is just getting started on the motor this month and should be billed in July. {MCS 5/5/2023 -- 3 WOs 2001999, 2002677, 2093547 which were created before the AFE was granted will be flipped in May, as of today there is about $25.5K total on them). 4/3/23 - RLO Purchase Order just sent to vendor for repair. | 2023-05-05 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 90000 | 5000 |  |  |  | Posipanko, Dan | Orischak, Bob |  |  | 1 | 46845 |  | Orischak, Bob | Independent | Aqua | 2023-03-27
Macungie Pipeline Asset Air-to-Ground Transition Recoats 2023 | Item | Open | MCAP | ZG00000M2304 | Maintenance Framework | 2085588 | Gable, Rob | East | 3. Active | Defined | Atmospheric Corrosion |  | 35000 |  | 35000 | 35000 | 0 | Green | 35000 |  | 35000 | 0 |  |  | 33671 |  |  | 33671 | Full | 33671 |  | 35000 | 35000 | No | Green | 2023-07-01 | 2023-02-21 | 2023-02-21 | 2023-10-01 | 2023-08-31 | [14 empty] | 20000 | 15000 | [5 empty] | 5/2/2023 RAG - Work to begin during Q3. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 0 | 35000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45392 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Macungie Propane and Butane Hazgas LEL Detectors | Item | Open | MCAP | ZG00000M2207 | Maintenance Framework | 2073856 | Mohr, David | East | 6. Operational | Defined | Instrumentation & Controls | 1060 |  |  | 1060.29 | 2060 | -1000 | Red | 17000 |  | 17000 | -15940 |  |  | 77000 |  |  | 77000 | Full | 77000 | 76370 |  | 76370 | No | Green | 2022-06-01 | 2022-03-22 | 2022-03-22 | 2022-06-30 | 2023-04-30 |  |  | 346.62 | 353.66 | 360.01 |  | 1000 | 1000 | -1000 | Red | [11 empty] | 5/1/2023 Programing completed by Texan and system is operational. 4/1/2023 Waiting on technicians to t/s system. DRM 2/2/2023 - Project will complete in Feb, just needs a few hours for technicians. Program updated and installed. Requires technician to verify correct operation 1/3/2023 Texon required to program PLC and test. Schedule for week of 1/9 12/1/2022 Propane side installed and butane waiting on Texon to program PLC. estimated week of 12/5. Variance due to PLC Programming engineer not being required. 11/1/2022 Commissioning schedule Mid-November10/3/2022 Electrical install completed. Scheduling of commissioning with MidStream Engineering scheduled at month's end due to butane blending season. . 9/1/2022 Issues with getting the soft dig company to site. Scheduled for week of 9/5 DRM 8/3/2022-Budget is on Target -will not need a Supplemental. 8/1/2022 Soft digging to start 8/15. Hazgas detectors have been shipped.DRM 7/5/2022 Soft dig and cable and conduit will be installed this month. Material has been ordered. It has a 20 week leadtime. Move material and installton next year. DRM 6/2/2022 Installation commenced week of 5/30. DRM 4/1/2022 DRM Walked the job with electrical contractor and asset team. PO issued to Diefenderfer. 3/1/2022 DRM Met with Diefenderfer to develop scope with asset team and requested quote to complete the AFE. 2/1/2022 Job walked and quoted last year. Will revisit to update quote with contractor and AFE to follow . | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | ZG - MACUNGIE STATION |  | 1060 | 0 |  |  | 75310 |  | Forsey, Frank | Forehand, Adam |  |  | 1 | 40484 |  | Guest, ProSight | Independent | Aqua | 2021-07-07 | Other Programs
Macungie Station - Replace L701 Manifold Fuel Division Valve | Item | Open | MCAP | ZG00000M2110 | Exempt | 1846940 | Keppel, Nicholas | East | 3. Active | Defined | Valves |  | 37000 |  | 37000 | 37000 | 0 | Green |  |  |  | 37000 |  |  | 40000 |  |  | 40000 | Full | 40000 | 361 | 37000 | 37361 | No | Green | 2021-09-01 | 2021-05-17 | 2021-05-17 | 2021-08-31 | 2023-01-31 | [13 empty] | 37000 | [7 empty] | 3/3/2023 - Work has been pushed to Q2 2023 due to supply shortage for necessary components. | 2023-03-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 37000 |  |  |  |  | Oey, Alex | Oey, Alexander |  |  | 1 | 36827 |  | Guest, ProSight | Independent | Aqua | 2020-06-03 | Other Programs
Macungie Station (ZG) - South Pond Improvements | Item | Open | MCAP | ZG00000M1912 | Exempt | 1659480 | Gebert, Clint | East | 7. Closed | Defined | Storm Water Management | -43592 |  |  | -43592.01 | -43592 | 0 | Green |  |  |  | -43592 |  |  | 22000 | 141000 |  | 163000 | Full | 163000 | 158787 |  | 158787 | No | Green | 2020-01-01 | 2019-12-16 | 2019-12-16 | 2020-12-31 | 2022-12-31 |  |  | 1431.99 | -45024 | [17 empty] | 3/7/2023 - Closed WO/PO and set OPPM status to 'Closed'. MCS Can close. 2/3/2023-Forecasting a 45K flip out of South Pond into the Fire project. 12/5/22-CGG- this project (when considered with the fire system project) is complete and on budget. 10/3/22- Actively working.9/6/2022- Contractor is on-site. 8/3/22-CGG-Does not need supplemental (this is a phased project). Project awarded to DPH Excavating. Mobilization is set for end of August.7/6/22-CGG- Received one bid waiting on a second. Hoping to combine fire system project and this one due to proximity and type of work. 5/19/2022 - slid out Operational date from last year to this summer. MCS. 5/4/2022 - Re-activated this to "Active"; it was set to "Deferred" last summer. Permits have just been received by Clint Gebert,and got 1 bid, will go after another. 8/2/21-CGG- review letter received from LCSC and at this point construction will most likely not occur in 2021. Project construction will be forecast in 2022. 7/6/2021-Waiting on Lehigh County permit. 6/3/2020 - Report received, but deferring this year's project funds to next year because what was allocated this year is not enough to complete construction. 5/20/20 - Slid out operational date based on forecast $ and note below. MCS 4/3/2020 - Kiely is in the permitting process. 1/6/20 - Permit process has begun. 12/2/19-CGG- AFE will be submitted this week.1-25-19-CGG- Walked site with Contractor this week and Consultant Engineer to discuss project approach and scope of work. Research is needed to determine implications of pond volume being for Fire Suppression and pond also serving as spill volume for southern most tank dikes. Permit investigation will begin. Phased approach may be required for this project. | 2023-03-07 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | ZG - MACUNGIE STATION |  | -43592 | 0 |  |  | 168561 |  | Bonenberger, Mark | Hoover, Bret | N/A |  | 1 | 29874 |  | Guest, ProSight | Independent | Aqua | 2018-07-12 | Other Programs
Macungie Station (ZG) Replace Deteriorating Utility Poles in North and South Tank Farms - 2022 | Item | Open | MCAP | ZG00000M2301 | Maintenance Framework | 2083834 | Mohr, David | East | 3. Active | Defined | Electrical |  | 85000 |  | 85000 | 85000 | 0 | Green | 85000 |  | 85000 | 0 |  |  | 85476 |  |  | 85476 | Full | 85476 |  | 85000 | 85000 | No | Green | 2023-08-01 | 2023-02-03 | 2023-02-03 | 2023-08-31 | 2023-08-31 | [15 empty] | 85000 | [5 empty] | 5/1/2023 Diefenderfer to determine the worst of the worst to replace first and schedule. 4/1/2023 PO issued to Diefenderfer. 3/1/2023 AFE approved and Contractor to deliver list of current poles to replace. DRM 2/2/2023 Contacted electrical contractor to start planning pole selection for replacement. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 0 | 85000 |  |  |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 37236 |  | Guest, ProSight | Independent | Aqua | 2020-07-23 | Other Programs
Macungie Station (ZG) Tank 206 - OOS Seal Insp | Item | Open | MEXP | ZG00000E2301 | Maintenance Framework | 2093479 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 30000 |  | 30000 | 30000 | 0 | Green | 125000 |  | 125000 | -95000 |  |  | 24750 |  |  | 24750 | Phase | 24750 |  | 30000 | 30000 | No | Green | 2023-10-01 | 2023-03-01 | 2023-03-01 | 2023-12-31 | 2023-12-31 | [17 empty] | 25000 | 5000 |  |  | 2/9/23 - Updated forecast based on assumption that seal inspection to be completed in-service with no required repairs. | 2023-02-09 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 0 |  | 30000 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44838 |  | Administrator, System | JDE Child | Burnt Orange | 2022-08-17 | Int - Tanks
Macungie Station (ZG) Tank 214 - OOS Seal Insp | Item | Open | MEXP | ZG00000E2302 | Maintenance Framework | 2093478 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 30000 |  | 30000 | 30000 | 0 | Green | 145000 |  | 145000 | -115000 |  |  | 24750 |  |  | 24750 | Phase | 24750 |  | 30000 | 30000 | No | Green | 2023-10-01 | 2023-03-01 | 2023-03-01 | 2023-12-31 | 2023-12-31 | [17 empty] | 25000 | 5000 | 0 |  | 2/9/23 - Updated forecast assuming seal inspection will be performed in-service with no required repairs. | 2023-02-09 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 0 |  | 30000 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44839 |  | Administrator, System | JDE Child | Burnt Orange | 2022-08-17 | Int - Tanks
Macungie Station (ZG) Tank 228 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | ZG00000M2302 | Maintenance Framework | 2086168 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 465707 |  | 465707 | 465707 | 0 | Green | 465707 |  | 465707 | 0 |  |  | 181178 |  |  | 181178 | Phase | 181178 |  | 465707 | 465707 | No | Green | 2023-09-01 | 2023-02-24 | 2023-02-24 | 2023-12-31 | 2023-12-31 | [16 empty] | 89707 | 100000 | 200000 | 76000 |  |  |  | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 0 | 89707 | 376000 |  |  | Stine, Carlton |  |  |  | 1 | 44840 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Macungie Station (ZG) Tank 211 - OOS Jet Tank Cleaning Inspection | Item | Open | MEXP | ZG00000E2201 | Maintenance Framework | 1937919 | Yoder, Michael | East | 6. Operational | Defined | Tanks | 18713 |  |  | 18713.17 | 18713 | 0 | Green |  |  |  | 18713 |  |  | 252000 |  |  | 252000 | Full | 252000 | 182155 |  | 182155 | No | Green | 2022-10-01 | 2022-01-05 | 2022-01-05 | 2022-12-31 | 2023-01-31 |  |  | 10200.32 | 3202.13 | 5310.72 | [16 empty] | Plan to close in June. 4/4/23 - Variance due to trailing disposal invoice. 3/1/23 - Variance due to PCard Material purchases. 2/1/23 - Tank returned to service. Variance due to sales tax and stone work. 1/3/23 - Tank repairs complete. Plan to button up mid-January. 12/1/22 - Tank lining in progress. Variance due to projected costs less than budgeted. 11/1/22 - Tank cleaning in progress. 10/4/22 - Scheduled to start mid-October. 9/1/22 - Planned October start. 7/6/2022 - Planned for September. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Macungie Pipe | ZG - MACUNGIE STATION |  | 18713 | 0 |  |  | 163441 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41284 |  | Administrator, System | JDE Child | Burnt Orange | 2021-08-09 | Int - Tanks
Macungie Station 603 Scraper Trap Valve Replacement | Item | Open | MCAP | ZG00000M2210 | Maintenance Framework | 1972073 | Keppel, Nicholas | East | 6. Operational | Defined | Valves | 1923 |  |  | 1923.09 | 1923 | 0 | Green |  |  |  | 1923 |  |  | 140000 |  |  |  | Full | 140000 | 142962 |  | 142962 | No | Green | 2022-05-01 |  |  | 2022-10-31 | 2023-01-19 |  |  | 1658.36 | 264.73 | [17 empty] | 1/5/2022 - Majority of work finalized in December 2022; minor activities to be completed in January 2023 | 2023-01-05 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | ZG - MACUNGIE STATION |  | 1923 | 0 |  |  | 141038 |  | Oey, Alex | Oey, Alexander |  |  | 1 | 24592 |  | Administrator, System | Independent | Aqua | 2017-07-27 | Other Programs
Macungie Station Fire Protection Upgrade - 2022 | Item | Open | MCAP | ZG00000M2211 | Maintenance Framework | 1980882 | Gebert, Clint | East | 7. Closed | Defined | Fire Protection | 2050 |  |  | 2050.08 | 2050 | 0 | Green |  |  |  | 2050 |  |  | 242000 |  |  | 242000 | Full | 242000 | 216959 |  | 216959 | No | Green | 2022-05-01 | 2022-07-26 | 2022-07-26 | 2022-12-31 | 2022-11-30 |  |  | -45000 | 45024 | 2026.08 | [16 empty] | 3/7/2023 - Closed WO/PO, and set OPPM status to 'Closed'. MCS Can close. 2/3/2023-Forecasting 45K in Feb for a flip from the South Pond project. 12/5/2022-Project complete, waiting on final invoices. 10/3/22 actively working.9/6/2022-Contractor is mobilized, on site. 8/3/22-CGG- Project is showing needs supplemental, but is solely due to the 2023 forecast. Project awarded to DPH Excavating. Mobilization is scheduled for end of August. HDPE pipe lead time is 10 weeks. 7/6/22-CGG- Have received 2 bids and am currently comparing bids. Scope will most likely need to be scaled back to stay within budget. | 2023-03-07 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | ZG - MACUNGIE STATION |  | 2050 | 0 |  |  | 214908 |  | Jakubowski, Gregory | Jakubowski, Greg |  |  | 1 | 40849 |  | Guest, ProSight | Independent | Aqua | 2021-07-29 | Other Programs
Macungie Station Fire Protection Upgrade - 2023 | Item | Open | MCAP | ZG00000M2313 | Maintenance Framework |  | Gebert, Clint | East | 2. Pending AFE |  | Fire Protection |  | 325000 |  | 325000 | 325000 | 0 | Green | 325000 |  | 325000 | 0 | [6 empty] | Interim |  |  | 325000 | 325000 | No | Green | 2023-08-01 |  |  |  | 2023-11-30 | [15 empty] | 25000 | 100000 | 100000 | 100000 | [6 empty] | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 0 | 125000 | 200000 |  |  | Jakubowski, Gregory | Jakubowski, Greg |  |  | 1 | 45699 |  | Clark, David | Independent | Aqua | 2022-08-29 | Other Programs
Macungie Station L701 Scraper Trap Block Valve Installation | Item | Candidate | MCAP |  | Maintenance Framework |  | Keppel, Nicholas | East | 1. Proposed |  | Valves |  | 120000 |  | 120000 | 120000 | 0 | Green | 120000 |  | 120000 | 0 | [9 empty] | 120000 | 120000 | No | Green | 2023-07-01 |  |  |  | 2023-09-30 | [14 empty] | 20000 | 50000 | 50000 | [8 empty] | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 0 | 120000 |  |  |  | Oey, Alex |  | N/A |  | 1 | 24971 |  | Guest, ProSight | Independent | Aqua | 2017-08-10 | Other Programs
Macungie Station- Remove electric from deep well buildings | Item | Open | MCAP | ZG00000M2312 | Maintenance Framework | 2110677 | Wing, Hunter | East | 2. Pending AFE |  | East |  | 97965 |  | 97965 | 80000 | 17965 | Red | 80000 |  | 80000 | 17965 | [6 empty] | Interim |  |  | 97965 | 97965 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 77728 | 20237 | [5 empty] | 5/1/2023 - Project Forecast Updated. Electrical SOW has come in under budget. Installing new roof puts project $18000 over budget. Quote from electrical contractor to bring electrical outside the building will be provided the week of 5/1. Forecast has been updated to show what project cost with new roof will be. Notes will be updated once final SOW is updated. Contractor has been approved to purchase outdoor rated equipment with long lead times. 4/3/2023 - Have gotten quotes. | 2023-05-01 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 0 | 97965 |  |  |  | Orischak, Bob |  |  |  | 1 | 44313 |  | Guest, ProSight | Independent | Aqua | 2022-07-28 | Other Programs
Macungie Station ZG - 603 to 714 Direct Valve - Power and Control Wiring Upgrade | Item | Open | MCAP | ZG00000M2308 | Maintenance Framework | 2094187 | Mohr, David | East | 3. Active | Defined | Valves |  | 80000 |  | 80000 | 80000 | 0 | Green | 80000 |  | 80000 | 0 |  |  | 85680 |  |  | 85680 | Full | 85680 |  | 80000 | 80000 | No | Green | 2023-10-01 | 2023-03-07 | 2023-03-07 | 2023-10-31 | 2023-10-31 | [17 empty] | 80000 |  |  |  | 5/1/2023 Soft dig, conduit and back fill completed. 4/1/2023 Actuator and valve ordered. Electrical contractor onsite laying C&C. 3/1/ Received quotes for material and engineering. AFE submitted. DRM | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 0 |  | 80000 |  |  | Oey, Alex | Oey, Alexander | N/A |  | 1 | 20695 |  | Guest, ProSight | Independent | Aqua | 2016-08-29 | Other Programs
Macungie Station ZG - 620 to 714 Direct Valve - Power and Control Wiring Upgrade | Item | Open | MCAP | ZG00000M2307 | Maintenance Framework | 2094188 | Mohr, David | East | 3. Active | Defined | Valves |  | 92000 |  | 92000 | 92000 | 0 | Green | 92000 |  | 92000 | 0 |  |  | 90340 |  |  | 90340 | Full | 90340 |  | 92000 | 92000 | No | Green | 2023-07-01 | 2023-03-07 | 2023-03-07 | 2023-10-31 | 2023-05-31 | [12 empty] | 0 |  | 92000 | [6 empty] | 5/1/2023 Soft dig, conduit and back fill completed. 4/1/2023 Actuator and valve ordered. Electrical contractor onsite laying C&C. 3/1/ Received quotes for material and engineering. AFE submitted. DRM | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 0 | 92000 |  |  |  | Oey, Alex | Oey, Alexander | N/A |  | 1 | 20697 |  | Guest, ProSight | Independent | Aqua | 2016-08-29 | Other Programs
Macungie T2 Insulated Pipe Priority 2 Repairs | Item | Open | MEXP | BETZG00E2304 | Maintenance Framework | 2093303 | Wing, Hunter | East | 3. Active | Defined | Facility Integrity | 6500 |  | 10000 | 6500 | 10000 | -3500 | Red | 20000 |  | 20000 | -13500 |  |  | 20000 |  |  | 20000 | Full | 20000 | 6500 | 10000 | 16500 | No | Green | 2023-04-01 | 2023-03-01 | 2023-03-01 | 2023-03-17 | 2023-05-31 | [5 empty] | 6500 | 10000 | 10000 | -3500 | Red |  | Savings from AFE Estimate | [8 empty] | 10000 | 5/1/2023 - HJW - Initial Project scope is complete. If integrity has any more insulation repair projects at Macungie T2, they can be completed under this budget. If not, project will move towards closeout. 4/4/2023-Waiting for Elaine Aiken to get clarification on the other priority items. 2.22.23 - HW - Scope determined to be just an HDPE liner repair needed for two supports. $10K has been added to contingency just in case supports determined to be in bad shape than expected. 2.2.23 - HW - Site Walk completed with operations on 1.18.23. More information was collected on where the repairs are needed. It has been determined that the HDPE liner needs to be cut back more in order to inspect/UT the supports. If UT is good, new liner will be installed. If UT is bad then new supports will be installed and liner will be repaired. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Macungie Terminal | BETZG - BET MACUNGIE TERMINAL |  |  | 6500 |  |  |  |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 45069 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Macungie Terminal (BETZG) Tank 101 (001A) - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | BETZG00E2302 | Maintenance Framework | 2093480 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 |  |  | 11000 |  |  | 11000 | Phase | 11000 |  | 10000 | 10000 | No | Green | 2023-07-01 | 2023-03-01 | 2023-03-01 | 2023-12-31 | 2023-12-31 | [14 empty] | 10000 | [10 empty] | East | Pipelines and Terminals | Tank Integrity |  | Macungie Terminal | BETZG - BET MACUNGIE TERMINAL |  |  | 0 | 10000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44841 |  | Administrator, System | JDE Child | Burnt Orange | 2022-08-17 | Int - Tanks
Macungie Terminal (BETZG) Tank 201 (003A) - OOS API 653, PADEP + Seal Insp & Refurb | Item | Open | MCAP | BETZG00M2301 | Maintenance Framework | 2082835 | Yoder, Michael | East | 3. Active | Defined | Tanks | 261054 | 40000 |  | 301054.46 | 291638 | 9416 | Yellow | 302617 |  | 302617 | -1563 |  |  | 141897 |  |  | 141897 | Phase | 141897 | 261054 | 40000 | 301054 | No | Green | 2023-02-01 | 2023-01-31 | 2023-01-31 | 2023-05-30 | 2023-05-30 |  |  |  | 39539.94 | 122098.5 | 99416.02 | 90000 | 90000 | 9416 | Yellow |  |  | 40000 | [8 empty] | 5/1/23 - Internal and external coating complete. Plan to install jet nozzle piping and button up tank 5/10. 4/4/23 - Mechanical repairs complete. Liner install in progress. Preparing phase 2 AFE for submission. 3/1/23 - Tank cleaning in progress. 2/1/23 - Tank legs set. Preparing to take tank OOS. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Macungie Terminal | BETZG - BET MACUNGIE TERMINAL |  | 161638 | 139416 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44842 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Macungie Terminal (BETZG) Tank 224 OOS Corrosion Inspection and Refurb | Item | Open | MEXP | BETZG00E2303 | Maintenance Framework | 2093473 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 320000 |  | 320000 | 320000 | 0 | Green | 320000 |  | 320000 | 0 |  |  | 169400 |  |  | 169400 | Phase | 169400 |  | 320000 | 320000 | No | Green | 2023-07-01 | 2023-03-01 | 2023-03-01 | 2023-12-31 | 2023-08-31 | [14 empty] | 100000 | 220000 | [5 empty] | 5/1/23 - Moved forecast back to July. Looking at potentially deferring this tank to Jan 2024 start. 1/9/23 - Move forecast to start in June as tank 201 will need to be completed prior to starting tank 224 OOS. | 2023-05-01 |  |  | East | Pipelines and Terminals | Tank Integrity |  | Macungie Terminal | BETZG - BET MACUNGIE TERMINAL |  |  | 0 | 320000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 45741 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-09-01 | Int - Tanks
Macungie Terminal (ZG) - Site survey to validate SPCC plan calculations and review. | Item | Open | MEXP | ZG00000E2203 | Maintenance Framework | 1989402 | Gebert, Clint | East | 7. Closed | Defined | Secondary Containment | 4078 |  |  | 4078 | 4078 | 0 | Green |  |  |  | 4078 |  |  | 32000 |  |  | 32000 | Full | 32000 | 29024 |  | 29024 | No | Green | 2022-08-01 | 2022-06-03 | 2022-06-03 | 2022-08-01 | 2022-09-30 |  |  | 4078 | [18 empty] | 2/14/2023 - Closed WO/PO, set OPPM project status to 'Closed'. MCS can close. 12/5/2022-Survey complete, project operational. 11/7/2022-Changed status to 'Operational' per Clint Gebert. 9/6/2022-Survey completed, awaiting final plans. 8/3/2022- Believe still on track for August. 7/6/2022 - Vendor selected, on track for August. | 2023-02-14 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Macungie Terminal | BETZG - BET MACUNGIE TERMINAL |  | 4078 | 0 |  |  | 24946 |  | Spari, Markella | Clark, David |  |  | 1 | 41559 |  | Administrator, System | Independent | Aqua | 2021-08-19 | Other Programs
Macungie Terminal 1 Replace Rectifier BESZG-01 | Item | Open | MCAP | BESZG00M2302 | Maintenance Framework | 2085714 | Gable, Rob | East | 3. Active | Defined | Cathodic Protection |  | 32000 |  | 32000 | 32000 | 0 | Green | 32000 |  | 32000 | 0 |  |  | 32078 |  |  | 32078 | Full | 32078 |  | 32000 | 32000 | No | Green | 2023-05-01 | 2023-02-22 | 2023-02-22 | 2023-09-30 | 2023-07-31 | [12 empty] | 5000 | 17000 | 5000 |  | 5000 |  |  |  |  | 5/2/2023 RAG - Rectifier scheduled to be delivered during May. 4/4/2023 RAG - PO's have been issued. Rectifier scheduled to be delivered during May. 3/2/2023 RAG - Awaiting quotes from Diefenderfer and JA Electronics. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Macungie Terminal | BESZG - BES MACUNGIE #1 TERM FH 1&2 |  |  | 22000 | 10000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45423 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Macungie Terminal 2 Ethanol Motor Replacement | Item | Open | MCAP | BESZM00M2202 | Maintenance Framework | 2043606 | Orischak, Bob | East | 7. Closed | Drawdown | Rotating Equipment | 1523 |  |  | 1523.28 | 53 | 1470 | Red |  |  |  | 1523 |  |  | 29000 |  |  | 29000 | Full | 29000 | 13244 |  | 13244 | No | Green | 2022-11-01 | 2022-10-27 | 2022-10-27 | 2022-12-31 | 2022-12-31 |  |  | 53.08 |  |  | 1470.2 |  |  | 1470 | Red | [11 empty] | 2/7/2023 - Closed/ WO/PO, set OPPM project status to 'Closed'. MCS. 1/31/2023 RLO Project can be closed. 01/03/2023 RLO Waiting on Operations to update me on the status of this project 12/1/2022 RLO Operational, waiting for Labor to hit project 11/2/2022 RLO Project was just approved on 11/1/22. Expect that the terminal purchased and installed and the costs MAY need to be reclassed. | 2023-02-07 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Terminal | BESZM - BES MACUNGIE #2 TERM FH 3 |  | 53 | 1470 |  |  | 11720 |  | Posipanko, Dan |  |  |  | 1 | 46103 |  | Orischak, Bob | Independent | Aqua | 2022-10-20 | Other Programs
Macungie Terminal 2 Propane Fire Eye Replacement | Item | Open | MCAP |  | Maintenance Framework |  | Mohr, David | East | 2. Pending AFE | Defined | Instrumentation & Controls |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 |  |  | 69569 |  |  |  | Full | 69569 |  | 100000 | 100000 | No | Green | 2023-08-01 |  |  | 2023-10-31 | 2023-09-30 | [14 empty] | 0 | 60000 | 40000 |  |  |  |  | 5/1/2023 Discussion are ongoing to make this project a 2 phose project due to higher than expected estimates. AFE to be submitted this week. 4/1/2023 Waiting for quote from electrical contractor to submit AFE | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Terminal | BETZM - BET MACUNGIE #1 & 2 |  |  | 0 | 100000 |  |  |  | Forsey, Frank |  | N/A |  | 1 | 25023 |  | Guest, ProSight | Independent | Aqua | 2017-08-16 | Other Programs
Macungie Terminal 3 pipe metal to metal contact mitigation. | Item | Candidate | MCAP |  | Maintenance Framework |  | Gable, Rob | East | 1. Proposed |  | Atmospheric Corrosion |  | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 | [9 empty] | 30000 | 30000 | No | Green | 2023-11-01 |  |  |  | 2023-11-30 | [18 empty] | 30000 |  |  | 5/2/2023 RAG - Work to begin during Q4. | 2023-05-02 |  |  | East | Pipelines and Terminals | Integrity |  | Macungie Terminal | BETZG - BET MACUNGIE TERMINAL |  |  | 0 |  | 30000 |  |  | Geib, Rob |  |  |  | 1 | 44302 |  | Guest, ProSight | Independent | Aqua | 2022-07-28 | Int - Planned Corr & FI
Macungie Terminal Door replacement | Item | Open | MCAP | BETZG00M2302 | Maintenance Framework | 2086016 | Wing, Hunter | East | 3. Active | Defined | East | 15840 | 30150 |  | 45990 | 47518 | -1528 | Yellow | 42000 |  | 42000 | 3990 |  |  | 45990 |  |  | 45990 | Full | 45990 | 15840 | 30150 | 45990 | No | Green | 2023-04-01 | 2023-04-12 | 2023-04-12 | 2023-06-30 | 2023-05-31 | [5 empty] | 15840 |  |  | 15840 | Red |  | WorkAhead of Schedule | 30150 | 0 | [7 empty] | 5/1/2023 - HJW - Project is underway and expected to be completed the week of 5/22. Garage Doors will be completed week of 5/1 and the man doors later in May. Forecast has been updated to show corrected forecast. 4.3.23 - HW - Door Installation expected week of 4.22 and the man doors 5/22. 2.27.23 - HW - Project Awarded to AllMark Doors. Electrical still TBD. 2.2.23 - HW - Two out of the Three Bids have been received, with the last bid expected the week of 2.6. Bids will be reviewed with operations to ensure scope is correct, then AFE and Work Plan to be submitted soon after. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Terminal | BETZG - BET MACUNGIE TERMINAL |  |  | 45990 |  |  |  |  | Orischak, Bob | Orischak, Bob |  |  | 1 | 44301 |  | Guest, ProSight | Independent | Aqua | 2022-07-28 | Other Programs
Macungie Terminal Propane Bullets Catwalk Access | Item | Open | MCAP | BETZM00M2301 | Maintenance Framework | 2051757 | Pepe, David | East | 3. Active | Defined | East | 56786 | 25000 |  | 81785.83 | 95843 | -14057 | Red | 80000 |  | 80000 | 1786 |  |  | 137000 |  |  | 137000 | Full | 137000 | 56786 | 25000 | 81786 | No | Green | 2023-01-01 | 2022-12-07 | 2022-12-07 | 2023-04-30 | 2023-06-30 |  |  | 5997 | 9347.87 | 492.76 | 40948.2 | 60000 | 60000 | -19052 | Red |  | Buckeye/Customer Schedule | 12500 | 12500 | [7 empty] | 5/4/2023 - DJP - Equipment has been received. Trying to coordinate the contractor to complete in May or Junbe. 4/1/2023 - DJP - After receiving quotes for the fabrication of the access platform. I am reviewing other options and pushing out the construction until April and May after receiving multiple construction quotes. 3/1/2023 - DJP - Engineering complete, out to bid. Bidding is taking longer than expected. Looking for foundations in March and construction in April. 2/3/2023-Engineering almost complete, installation expected March or so. 11/23/22 Walked down the project with operations and engineering company. Received the quote from SafeRack and Carbis. Received Quote from Midstream Engineering. DJP | 2023-05-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Terminal | BETZM - BET MACUNGIE #1 & 2 |  | 15838 | 65948 |  |  |  |  | Orischak, Bob |  |  |  | 1 | 44298 |  | Guest, ProSight | Independent | Aqua | 2022-07-28 | Other Programs
Macungie Terminals Air-to-Ground Transition Recoats 2021 | Item | Candidate | MCAP |  | Maintenance Framework |  | Gable, Rob | East | 1. Proposed |  | Atmospheric Corrosion |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 | [9 empty] | 40000 | 40000 | No | Green | 2023-08-01 |  |  |  | 2023-09-30 | [15 empty] | 20000 | 20000 |  |  |  |  | 5/2/2023 RAG - Work to begin during Q3. | 2023-05-02 |  |  | East | Pipelines and Terminals | Integrity |  | Macungie Terminal | BESZG - BES MACUNGIE #1 TERM FH 1&2 |  |  | 0 | 40000 |  |  |  | Geib, Rob |  |  |  | 1 | 37093 |  | Guest, ProSight | Independent | Aqua | 2020-07-15 | Int - Planned Corr & FI
Macungie ZG Butane Relief Repairs Per PSM 2022 | Item | Open | MEXP | BESZG00E2301 | Maintenance Framework | 2112619 | Pepe, David | East | 3. Active | Defined | East |  | 150000 |  | 150000 | 100000 | 50000 | Red | 100000 | 49883 | 149883 | 117 |  |  | 149881 |  |  | 149881 | Full | 149881 |  | 150000 | 150000 | No | Green | 2023-06-01 | 2023-04-25 | 2023-04-25 | 2023-06-30 | 2023-06-30 | [13 empty] | 75000 | 75000 | [6 empty] | 5/4/2023-Out for bid. 4/20/2023 DJP AFE submitted for the propane system. Getting bids from contractors. The butane system will be submitted in 2024. 12/14/22 DJP This project Includes the Butane and Propane systems at Macungie. | 2023-05-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 75000 | 75000 |  |  |  | Orischak, Bob | Orischak, Bob |  |  | 1 | 44188 |  | Guest, ProSight | Independent |  | 2022-07-22 | Other Programs
Maine Asset Atmospheric Corrosion Remediation 2022 | Item | Candidate | MCAP |  | Maintenance Framework |  | Gable, Rob | East | 1. Proposed |  | Atmospheric Corrosion |  | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 | [9 empty] | 30000 | 30000 | No | Green | 2023-08-01 |  |  |  | 2023-09-30 | [15 empty] | 10000 | 20000 |  |  |  |  | 5/2/2023 RAG - Work to begin during Q3. | 2023-05-02 |  |  | East | Pipelines and Terminals | Integrity |  | Maine | HW - HALLOWELL STATION |  |  | 0 | 30000 |  |  |  | Geib, Rob |  |  |  | 1 | 40895 |  | Guest, ProSight | Independent | Aqua | 2021-08-02 | Int - Planned Corr & FI
Maine Asset Atmospheric Corrosion Remediation 2023 | Item | Open | MCAP | HW00000M2301 | Maintenance Framework | 2086630 | Gable, Rob | East | 3. Active | Defined | Atmospheric Corrosion |  | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 |  |  | 30137 |  |  | 30137 | Full | 30137 |  | 30000 | 30000 | No | Green | 2023-07-01 | 2023-02-27 | 2023-02-27 | 2023-10-01 | 2023-08-31 | [14 empty] | 10000 | 20000 | [5 empty] | 5/2/2023 RAG - Work to begin during Q3. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Maine | HW - HALLOWELL STATION |  |  | 0 | 30000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45397 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Maine Asset CP Troubleshooting 2022 | Item | Open | MEXP | HW755BME2202 | Maintenance Framework | 1938851 | Gable, Rob | East | 7. Closed | Defined | Cathodic Protection | 209 |  |  | 208.72 | 209 | 0 | Green |  |  |  | 209 |  |  | 40000 |  |  | 40000 | Full | 40000 | 14243 |  | 14243 | No | Green | 2022-09-01 | 2022-01-20 | 2022-01-20 | 2022-11-15 | 2022-12-31 |  |  | 208.72 | [18 empty] | 1/10/2023 - Closed WO/PO and set OPPM project status to 'Closed'. MCS. 1/4/2023 RAG - Ready to close, no other invoices expected. 12/2/2022 RAG - Junction Box and RMU will arrive in December. 11/3/2022 RAG - Remaining bond work delayed until Dec. 10/4/2022 RAG - Remaining bond work delayed until Dec. 9/6/2022 RAG - Delay due to scheduling conflict and awaiting annual CP survey to review. 8/2/2022 RAG - Work to be performed after 2022 CP survey is completed and reviewed. 5/2/2022 RAG - Preparing work to begin as forecasted. 4/4/2022 RAG - Preparing work to begin as forecasted. 2/2/2022 RAG - AFE has been approved and WOR created. 1/13/2022 RAG - AFE submitted on 1/13/2022. | 2023-01-10 | Sautter, Maureen |  | East | Pipelines and Terminals | Corrosion |  | Maine | HW755BM - HALLOWELL - BANGOR TERM |  | 209 | 0 |  |  | 14034 |  | Geib, Rob | Geib, Robert |  |  | 1 | 40884 |  | Guest, ProSight | Independent | Aqua | 2021-07-30 | Int - Planned Corr & FI
Maine Asset CP Troubleshooting 2023 | Item | Open | MEXP | HW755BME2302 | Maintenance Framework | 2085418 | Gable, Rob | East | 3. Active | Defined | Cathodic Protection |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 |  |  | 39305 |  |  | 39305 | Full | 39305 |  | 40000 | 40000 | No | Green | 2023-07-01 | 2023-02-21 | 2023-02-21 | 2023-11-15 | 2023-10-31 | [14 empty] | 5000 | 15000 | 10000 | 10000 |  |  |  | 5/2/2023 RAG - Work to begin during Q3. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Corrosion |  | Maine | HW755BM - HALLOWELL - BANGOR TERM |  |  | 0 | 30000 | 10000 |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45398 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Malvern & Booth Assets Atmospheric Corrosion Remediation 2022 | Item | Open | MCAP | MX00000M2202 | Maintenance Framework | 1938836 | Gable, Rob | East | 7. Closed | Defined | Atmospheric Corrosion | 608 |  |  | 608.07 | 608 | 0 | Green |  |  |  | 608 |  |  | 27000 |  | 8127 | 35127 | Full | 35127 | 33372 |  | 33372 | No | Green | 2022-09-01 | 2022-01-20 | 2022-01-20 | 2022-09-15 | 2022-12-31 |  |  | 2363.07 | -1755 | [17 empty] | 3/14/2023 - Closed WO/PO, and set OPPM project status to 'Closed'. MCS 3/2/2023 RAG - Ready to Close. Accrual not needed. No more invoices expected. 2/2/2023 RAG - Awaiting final invoices. 1/4/2023 RAG - Work completed.12/2/2022 RAG - Work being performed during week of 12/5. 11/3/2022 RAG - JSR preparing to start work. 10/4/2022 RAG - PO's issued and materials purchased, Installation scheduled for Oct/Nov. 9/6/2022 RAG - PO being applied for. 8/2/2022 RAG - JSR providing quote and schedule. 7/1/2022 RAG - Currently developing repair program. 4/4/2022 RAG - Preparing work to begin as forecasted. 2/2/2022 RAG - AFE has been approved and WOR created. 1/12/2022 RAG - AFE submitted on 1/12/2022. | 2023-03-14 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Malvern | MX - MALVERN STATION TERMINAL |  | 608 | 0 |  |  | 32764 |  | Geib, Rob | Tench, David |  |  | 1 | 40892 |  | Guest, ProSight | Independent | Aqua | 2021-08-02 | Int - Planned Corr & FI
Malvern (BETMX) - Secondary containment upgrades and drainage improvements | Item | Open | MCAP |  | Maintenance Framework |  | Wing, Hunter | East | 1. Proposed |  | Secondary Containment |  | 98000 |  | 98000 | 98000 | 0 | Green | 98000 |  | 98000 | 0 | [9 empty] | 98000 | 98000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 98000 | [6 empty] | 5/1/2023 - Project scope has been developed. Project will be bid out with Dave Pepe's Malvern Projects within the next few weeks. Forecast will be updated once bids are received. | 2023-05-01 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Malvern | BETMX - BET MALVERN TERMINAL |  |  | 0 | 98000 |  |  |  | Clark, Dave |  |  |  | 1 | 45163 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
Malvern Asset Air-to-Ground Transition Recoats 2022 | Item | Open | MCAP | MX00000M2201 | Maintenance Framework | 1938805 | Gable, Rob | East | 8. Canceled | Defined | Atmospheric Corrosion | -425 |  |  | -424.8 | -425 | 0 | Green |  |  |  | -425 |  |  | 20000 |  |  | 20000 | Full | 20000 | 0 |  | 0 | No | Green | 2022-06-01 | 2022-01-20 | 2022-01-20 | 2022-07-01 | 2022-10-31 |  |  | -424.8 | [18 empty] | 1/23/2023 - Submitted a flip ticket today to move this $425 to local budget. Project is cancelled. -MCS. 10/4/2022 RAG - Site visits have revealed that no further locations remain. Project to be canceled as not needed. 9/6/2022 RAG - PO being applied for. 8/2/2022 RAG - contractor delay - JSR providing quote and schedule. 7/1/2022 RAG - Awaiting quote from JSR. 6/2/2022 RAG - Setting up JSR to perform recoats. 5/2/2022 RAG - Preparing work to begin as forecasted. 4/4/2022 RAG - Preparing work to begin as forecasted. 2/2/2022 RAG - AFE has been approved and WOR created. 1/12/2022 RAG - AFE submitted on 1/11/2022. | 2023-01-23 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Malvern | MX - MALVERN STATION TERMINAL |  | -425 | 0 |  |  | 425 |  | Geib, Rob | Geib, Robert |  |  | 1 | 40878 |  | Guest, ProSight | Independent | Aqua | 2021-07-30 | Int - Planned Corr & FI
Malvern Asset Air-to-Ground Transition Recoats 2023 | Item | Open | MCAP | MX00000M2301 | Maintenance Framework | 2085569 | Gable, Rob | East | 3. Active | Defined | Atmospheric Corrosion |  | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 |  |  | 28816 |  |  | 28816 | Full | 28816 |  | 30000 | 30000 | No | Green | 2023-06-01 | 2023-02-21 | 2023-02-21 | 2023-09-01 | 2023-06-30 | [13 empty] | 15000 |  | 15000 | [5 empty] | 5/2/2023 RAG - Work to begin during Q3. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Malvern | MX - MALVERN STATION TERMINAL |  |  | 15000 | 15000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45396 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Malvern Fire-Water Line Replacement - Phase II - 2022 | Item | Open | MCAP | BETMX00M2203 | Maintenance Framework | 1989401 | Mohr, David | East | 3. Active | Defined | Fire Protection | 18309 | 73000 |  | 91309.19 | 90084 | 1225 | Yellow |  |  |  | 91309 |  |  | 90000 |  |  | 90000 | Full | 90000 | 18309 | 73000 | 91309 | No | Green | 2023-01-01 | 2022-06-03 | 2022-06-03 | 2022-12-31 | 2023-05-31 |  |  | 48.28 |  | 15035.83 | 3225.08 | 75000 | 75000 | -71775 | Red |  |  | 73000 | [8 empty] | 5/1/2023 Contractor has one lane left to complete. Variance due to conservation activities with bird nest and young birds in nest holding up project. Should be completed this month, 4/1/2023 Contractor did not complete installation in March as anticipated. Contractor onsite to finish installation. 3/1/2023 All material received and installation scheduled for week of 3/20. DRM 2/2/2023 Working to schedule installation. 1/2/2023 Material still has not arrived. 12/1/2022 Variance due to material delay with no estimate of arrival. 11/1/2022 Variance due to material delay with no estimate of arrival. 10/5/2022-Delay in Material, unknown delivery date. Forecasting $ in October but may not happen. 9/1/2022 Waiting for material. DRM 7/5/2022 Have issued PO to Oliver for the installation of the sensors an Fire pre-panel. DRM 6/2/2022 Received quotes back from Kistler and Obrien. AFE submitted but was rejected due to additional fun\ding determination. DRM 5/2/2022 Meeting Kistler-Obrien this week for second quote. AFE to follow. DRM 4/1/2022 DRM Meeting with Bob Orischak and Clint Gebert to review the project. Received initial quote and need to collect a second. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Malvern | BETMX - BET MALVERN TERMINAL |  | 15084 | 76225 |  |  |  |  | Jakubowski, Gregory | Tench, David |  |  | 1 | 37242 |  | Guest, ProSight | Independent | Aqua | 2020-07-23 | Other Programs
Malvern Generic Additive Tote | Item | Open | MCAP | BETMX00M2201 | Maintenance Framework | 1955658 | Keeth, Ed | East | 8. Canceled | Drawdown | East |  |  |  | 0 |  | 0 | Green | [6 empty] | 36000 |  |  | 36000 | Full | 36000 | 3985 |  | 3985 | No | Green | 2022-04-01 | 2022-03-10 | 2022-03-10 | 2022-05-31 | 2022-12-31 | [21 empty] | 4/5/2023 - Cancelling the project -- take off Ed Keeth's plate (confirm with Bob Orischak). 2/3/2023-no change. Hunter Wing? 12/5/2022-Project delayed due to lack of PM resources. Once a PM assigned they can talk to Tench about it. 9/6/2022-Project needs to be transitioned away from Ed Keeth. 5/4/22 3k variance due to asset team getting misc materials for project. ek5507 4/4/22 lead time on tote around 8 weeks. Will sch construction once tote comes in. ek5507 | 2023-04-05 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Malvern | BETMX - BET MALVERN TERMINAL |  |  | 0 |  |  | 3985 |  | Orischak, Bob | Tench, David |  |  | 1 | 43138 |  | Meitzler, Antoinette | Independent | Aqua | 2022-03-09 | Other Programs
Malvern Priority 3 API 570 Refurbishments | Item | Open | MCAP |  | Maintenance Framework |  | Pepe, David | East | 1. Proposed |  | Facility Integrity |  | 230000 |  | 230000 | 230000 | 0 | Green | 230000 |  | 230000 | 0 | [9 empty] | 230000 | 230000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [13 empty] | 0 | 100000 | 100000 | 30000 | [8 empty] | East | Pipelines and Terminals | Integrity |  | Malvern | BETMX - BET MALVERN TERMINAL |  |  | 0 | 230000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45054 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Malvern Switchgear PM | Item | Open | MEXP | MX00000E2202 | Maintenance Framework | 1938634 | Mohr, David | East | 3. Active | Defined | Electrical | 0 | 30000 |  | 30000 | 30000 | 0 | Green |  |  |  | 30000 |  |  | 30000 |  |  | 30000 | Full | 30000 | 166 | 30000 | 30166 | No | Green | 2022-08-01 | 2022-01-18 | 2022-01-18 | 2022-10-31 | 2023-05-31 | [5 empty] | 0 | 30000 | 30000 | -30000 | Red |  | Buckeye/Customer Schedule | 30000 | [8 empty] | 5/1/2023 PM and Repair schedule for 5/24-25 with shutdown. Variance due to scheduling the shutdown with contractor. 4/1/2023 Shutdown to be scheduled for month of april. DRM 2/2/2023 Working with contractor to schedule what can be done in lieu of PPL shuitdown. 1/3/2023 PPL not responding to requests 12/1/2022 Still having issues with PPL to schedule shutdown 11/1/2022 Variance due getting PPL to schedule date for shutdown. 10/3/2022 Scheduling shutdown with PPL for shutdown. 8/1/2022 Requested quote from longo for substation PM Service DRM | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Malvern | MX - MALVERN STATION TERMINAL |  |  | 30000 |  |  | 166 |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 33990 |  | Guest, ProSight | Independent | Aqua | 2019-08-13 | Other Programs
Marcy (CY) Tank 1 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | CY00000E2301 | Maintenance Framework | 2093483 | Yoder, Michael | East | 6. Operational | Defined | Tanks | 5723 |  |  | 5722.54 | 10000 | -4277 | Red | 10000 |  | 10000 | -4277 |  |  | 11000 |  |  | 11000 | Phase | 11000 | 5723 |  | 5723 | No | Green | 2023-04-01 | 2023-03-01 | 2023-03-01 | 2023-12-31 | 2023-04-30 | [5 empty] | 5722.54 | 10000 | 10000 | -4277 | Red | [11 empty] | Plan to close in June. 5/1/23 - Seal inspection complete. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Auburn Pipeline | CY - MARCY TERMINAL |  |  | 5723 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44844 |  | Administrator, System | JDE Child | Burnt Orange | 2022-08-17 | Int - Tanks
Marcy CY - Replace Prover 4-Way Valve | Item | Open | MCAP | CY00000M2301 | Maintenance Framework | 2076598 | Mohr, David | East | 3. Active | Defined | Measurement & Quality Control | 59268 | 94000 |  | 153267.8 | 150898 | 2369 | Yellow | 150000 |  | 150000 | 3268 |  |  | 149978 |  |  | 149978 | Full | 149978 | 59268 | 94000 | 153268 | No | Green | 2023-02-01 | 2023-01-24 | 2023-01-24 | 2023-07-30 | 2023-09-30 |  |  |  | 333.35 | 47565.13 | 11369.32 |  |  | 11369 | Red | [5 empty] | 13000 | 81000 |  |  |  |  | 5/1/2023 Received the 4way valve actuator. Issuing PO to fabricator. Variance du to receing actuator ahead of schedule4/1/2023 4-way valve received. 3/1/2023 4way and actuator on order. 4-way has shipped, will be received in March. Actuator estimated arrival for July. DRM .2/2/2023 Received all quotes and PO's to follow. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Pipeline | CY - MARCY TERMINAL |  | 47898 | 11369 | 94000 |  |  |  | Hopkins, Christa | Tracey, Steve |  |  | 1 | 40496 |  | Guest, ProSight | Independent | Aqua | 2021-07-09 | Other Programs
Marcy Pipeline Terminal Transmix Pump | Item | Open | MCAP | BETCY00M2202 | Maintenance Framework | 2044565 | Pepe, David | East | 3. Active | Defined | Rotating Equipment | 22026 | 165000 | 0 | 187025.73 | 186126 | 900 | Yellow | 60000 |  | 60000 | 127026 |  |  | 213000 |  |  | 213000 | Full | 213000 | 39962 | 165000 | 204962 | No | Green | 2022-11-01 | 2022-11-11 | 2022-11-11 | 2023-06-01 | 2023-09-30 | 189 | Red | 110.35 | 1015.38 | 20000 | 900 | 0 | 0 | 900 | Red | [5 empty] | 80000 | 85000 |  |  |  | 0 | 5/4/2023-Pump expected Aug/Sep. 4/1/2023-Pump expected Aug/Sept, the piping has been shop-vaced. . 2/3/2023-shop fabrication is underway, installation planned for summer. 1/11/2023-Pump Ordered on 11/18/2023 due 8/1/2023 working with contractor to install new piping at site. 1/4/2023-Delay due to waiting for piping changes, which are now re-finalized, planning to schedule Jan/Feb. 2022/12/05 DJP - operations has some changes to the piping, will hold off on the installation. 12/1/2022 DJP Shop Fabrication of the Piping completed, site installation expected 12/7/22. Working with Local Ops to drain up pipe for installation. Getting pump on order for mid 2023 delivery. 9/1/2022 RLO Looking to give this to Dave Pepe. Will be purchasing the pump in 2022 but 20+week lead time says install will happen in 23' 8/1/2022 RLO Still expecting to spend in Sept. Handing project off to Joe Schwindt 4/26/22 Had call regarding pump with asset team and Nate Frey. He is in the process of spec out a pump. Once we know the pump I will obtain cut sheet and bid out since it will involve piping modifications. ek5507 4/4/22 Plan on Scoping in late April. ek5507 | 2023-05-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BETCY - BET MARCY TERMINAL |  | 21126 | 900 | 165000 |  | 17936 |  | Posipanko, Dan | Orischak, Bob |  |  | 1 | 24605 |  | Administrator, System | Independent | Aqua | 2017-07-27 | Other Programs
Marcy Terminal - Replace Marlow Cast Iron PUL Pump | Item | Open | MCAP | BETCY00M2301 | Maintenance Framework | 2052880 | Pepe, David | East | 3. Active | Defined | Rotating Equipment | 362 | 120000 |  | 120362.48 | 120000 | 362 | Yellow | 130000 |  | 130000 | -9638 |  |  | 119053 |  |  | 119053 | Full | 119053 | 362 | 120000 | 120362 | No | Green | 2023-04-01 | 2023-01-03 | 2023-01-03 | 2023-07-01 | 2023-06-30 | [5 empty] | 362.48 | 15000 | 15000 | -14638 | Red |  | Supply Chain | 15000 | 16000 | 89000 | [6 empty] | 5/4/2023-Pump has just shipped. 4/1/2023-Expecting pump on site in April 2/3/2023 - Pump doesn't arrive until April 2023, the VFD will come in June, expecting construction in July. 12/19/2022 DJP Interim Approved and long lead pump and VFD requisitioned. 12/9/2022 DJP submitted interim AFE for order of pump and new drive before the end of the year to obtain favorable pricing and delivery. | 2023-05-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BETCY - BET MARCY TERMINAL |  |  | 31362 | 89000 |  |  |  | Posipanko, Dan | Posipanko, Daniel A. |  |  | 1 | 44122 |  | Guest, ProSight | Independent | Aqua | 2022-07-13 | Other Programs
Marcy Terminal BETCY - Replace Marlow Cast Iron ULSD Pump/Motor | Item | Open | MCAP | BETCY00M2302 | Maintenance Framework | 2052231 | Pepe, David | East | 3. Active | Defined | Rotating Equipment |  | 77000 |  | 77000 | 77000 | 0 | Green | 130000 |  | 130000 | -53000 |  |  | 79702 |  |  | 79702 | Full | 79702 |  | 77000 | 77000 | No | Green | 2023-05-01 | 2023-01-03 | 2023-01-03 | 2023-07-01 | 2023-06-30 | [6 empty] | 12000 | 12000 | -12000 | Red |  | Supply Chain | 12000 |  | 65000 | [6 empty] | 5/4/2023-Pump has just shipped. 4/1/2023-Expecting pump on site in April 2/3/2023 - Pump doesn't arrive until April 2023, the VFD will come in June, expecting construction in July. 12/19/2022 DJP Interim Approved and long lead pump requisitioned. 12/9/2022 DJP submitted interim AFE for order of pump and new drive before the end of the year to obtain favorable pricing and delivery. | 2023-05-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BETCY - BET MARCY TERMINAL |  |  | 12000 | 65000 |  |  |  | Posipanko, Dan | Posipanko, Daniel A. |  |  | 1 | 44121 |  | Guest, ProSight | Independent | Aqua | 2022-07-13 | Other Programs
Marcy VAC Pump Rebuilt | Item | Open | MEXP | BETCY00E2201 | Maintenance Framework | 1957025 (new: 2075815) | Orischak, Bob | East | 6. Operational | Drawdown | East | 67632 |  |  | 67631.52 | 54783 | 12849 | Red |  |  |  | 67632 |  |  | 42000 |  |  | 42000 | Full | 42000 | 89262 |  | 89262 | No | Green | 2022-04-01 | 2022-03-28 | 2022-03-28 | 2022-04-30 | 2023-08-09 |  |  | 44782.5 |  |  | 22849.02 | 10000 | 10000 | 12849 | Red | [11 empty] | 5/1/2023 RLO Waiting for final scope and costs to be identified. It will need a supplemental. 4/3/23 RLO - The pump has failed a 4th time. Must keep project open to determine costs. 3/1/2023 RLO Addtional costs coming on this project due to new pump that has now failed. 2/1/2023-Variance due to missed accrual. Increased scope of work due to second failed vac pump.1/23/2023 - Reset OPPM status to 'Operational', had been set to 'Closed' in OPPM prematurely. Zink invoice came in. 9/8/2022 - Closed WO/PO (cancelled the 42K Zink OP-227504). Set OPPM status to 'Closed'. MCS 9/1/2022 RLO Close Project 8/1/2022 RLO still waiting on ZEECO to complete. . 7/1/2022 - Accrue to Zeeco. Most of project looks paid- I reached out to ops to see if they have any more invoices RLO 6/2/2022-RLO-waiting to hear from Vapor Team. 5/6/2022-Believe work will be done in May, but subject to contractor availability. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Auburn Terminals | BETCY - BET MARCY TERMINAL |  | 44783 | 22849 |  |  | 21630 |  | Orischak, Bob | Campion, Tom | N/A |  | 1 | 43283 |  | Meitzler, Antoinette | JDE Child | Burnt Orange | 2022-03-29 | Other Programs
Mechanicsburg Asset CP Troubleshooting 2023 | Item | Open | MEXP | SN724SKE2301 | Maintenance Framework | 2085629 | Gable, Rob | East | 3. Active | Defined | Cathodic Protection | 10940 | 25000 |  | 35940.13 | 30108 | 5832 | Red | 30001 |  | 30001 | 5939 |  |  | 29520 |  |  | 29520 | Full | 29520 | 10940 | 25000 | 35940 | Yes | Red | 2023-03-01 | 2023-02-21 | 2023-02-21 | 2023-11-15 | 2023-11-15 |  |  |  |  | 4178.33 | 6761.8 | 5930 | 5930 | 832 | Red |  | Contractor/Vendor Issue |  | 5000 |  |  | 10000 | 10000 |  |  |  | 5/2/2023 RAG - Delay in spending due to sudden loss of main CP contractor. 4/2/2023 RAG - Flips will be made from asset charges. 3/2/2023 RAG - Work to begin during Q2. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Corrosion |  | Mechanicsburg | SN724SK - SINKING SPRING -SCHAEFFERSTOWN |  | 4178 | 11762 | 10000 | 10000 |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45412 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Mechanicsburg East Control Valve Replacement | Item | Open | MCAP | MG00000M2102 | Maintenance Framework | 1869251 | Gebert, Clint | East | 7. Closed | Defined | Valves | 5482 |  |  | 5481.89 |  | 5482 | Red |  |  |  | 5482 |  |  | 165000 |  |  | 165000 | Full | 165000 | 130628 |  | 130628 | No | Green | 2021-07-01 | 2021-08-23 | 2021-08-23 | 2021-12-31 | 2022-08-31 | [5 empty] | 5481.89 |  |  | 5482 | Red | [11 empty] | 4/13/2023 - Setting RTC back to 'No' to (potentially) accommodate Barr-None painting invoice 10546 $5,141 which just came in today. 12/28/2022 - Closed WO/PO, set OPPM project status to 'Closed'. 12/5/2022-Can close.10/3/22- work complete. spend not forecasted due to purge impacts on asset team in MP. Control valve was completed when time allowed and was not planned the preceeding month.8/29/22-CGG- Job Completed, CV was installed week of 8/22 at request of Asset team. Project Complete. 8/3/2022-Project pushed to Dec due to asset team involvement in second 724 purge. 7/6/22-CGG- Project was scheduled for June/July but had to be pushed off due to required Asset Team involvement in corporate purge project on the 724. 6/2/22-CGG- Piping and valve hydrotested. Waiting on electrical and comms portion to be finished. Targeting install toward end of June. 5/4/2022-Valve came in, now we are fabricating piping. 4/5/22-CGG-CV and actuator were just delivered to MP. 3/3/22-CGG- CV is in North America. Currently having operator installed. Install will be scheduled after CV is delivered. 2/3/22 - (same) ie control valve won't come until April 12/3/21-CGG- Control valve is estimated to arrive in April 2022. Install will be planned when it arrives.11/1/21-Waiting on materials. 10/4/21-CGG-PO issued for Masoneilan Control Valve. Long lead time. 9/3/2021-Exploring valve combinations/options to stay within budget. .8/2/21-CGG- currently modeling both a CCI and Masoneilan control valve. | 2023-04-13 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Mechanicsburg | MG - MECHANICSBURG EAST |  |  | 5482 |  |  | 120401 |  | Oey, Alex | Oey, Alexander | N/A |  | 1 | 25865 |  | Guest, ProSight | Independent | Aqua | 2017-09-13 | Other Programs
Mechanicsburg East Sump Tank Alarm Replacement | Item | Open | MCAP | MG00000M2202 | Maintenance Framework | 1970917 | Mohr, David | East | 7. Closed | Defined | Instrumentation & Controls | -6500 |  |  | -6500 | -6500 | 0 | Green |  |  |  | -6500 |  | Other | 64000 |  |  | 64000 | Full | 64000 | 56963 |  | 56963 | No | Green | 2022-06-01 | 2022-04-11 | 2022-04-11 | 2022-06-30 | 2022-08-31 |  |  | -6500 | [18 empty] | 4/25/2023 - Closed WO/PO, and set OPPM project status to 'Closed'. MCS Can close. 2/2/2023 Variance is due to no more to invoice on the project. 10/5/2022-Project completed, waiting for invoice from Arseal. Oct FC is reclass of M2201 (shared invoicing) 9/1/2022 Project is operational. DRM 7/5/2022 Cable and Conduit install. Waiting for fuel cycle and for other work to be completed. DRM 6/2/2022 Conduit and Cable Installation progressing DRM 5/3/2022 Installation scheduled for the 3rd week in May. DRM 2/1/2022 Reached out to asset team to discuss. 3/1/2022 DRM Met at Mechanicsburg East last week to discuss and scope project. Developed basic drawings for conduit runs to sample shed and Sump tanks.AFE will be developed once quotes are received for probes, electrical and programming. 4/1/2022 DRM Reviewed scope and completed job walk with Diefenderfer. Received quote for soft dig and electrical work. AFE this week. | 2023-04-25 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Mechanicsburg | MG - MECHANICSBURG EAST |  | -6500 | 0 |  |  | 63463 |  | Forsey, Frank | Orischak, Bob | N/A |  | 1 | 31522 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Other Programs
Mechanicsburg Retrofit Breakers | Item | Open | MCAP | MP00000M2302 | Maintenance Framework | 2083824 | Mohr, David | East | 3. Active | Defined | Electrical |  | 275000 |  | 275000 | 275000 | 0 | Green | 275000 |  | 275000 | 0 |  |  | 274924 |  |  | 274924 | Full | 274924 |  | 275000 | 275000 | No | Green | 2023-08-01 | 2023-02-03 | 2023-02-03 | 2023-08-31 | 2023-08-31 | [15 empty] | 275000 | [5 empty] | 5/1/2023 Wrapping up Coupa bid event and selecting contractor/vendor. 4/1/2023 Coupa bid event is underway. 3/1/2023 Submitted for bid event through COUPA. 2/2/2023 Received quote from Longo Electric for breakers and installation service | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Mechanicsburg | MP - MECHANICSBURG STATION |  |  | 0 | 275000 |  |  |  | Ashley, Robert | Orischak, Bob |  |  | 1 | 41406 |  | Guest, ProSight | Independent | Aqua | 2021-08-13 | Other Programs
Mechanicsburg Station PLC Replacement | Item | Open | MCAP | MP00000M2203 | Maintenance Framework | 1957347 | Mohr, David | East | 3. Active | Defined | Instrumentation & Controls | 6568 | 90000 |  | 96568.24 | 94839 | 1729 | Yellow | 90000 |  | 90000 | 6568 |  | Other | 141000 |  |  | 141000 | Full | 141000 | 50121 | 90000 | 140121 | No | Green | 2022-05-01 | 2022-03-28 | 2022-03-28 | 2022-10-31 | 2023-07-31 |  |  | 554.59 | 864.03 | 3420.71 | 1728.91 |  |  | 1729 | Red |  |  |  |  | 90000 | [6 empty] | 4/1/2023 Remaining material not scheduled to arrive prior to June 2023. 1\3\2023 Will be contacting Deifenderfer Electrical to start making wiring preparations prior to shutdown. 12/2/2022 - Engineering is done, doing nothing else until next year. 8/2/2022-On-track for engineering being done this year. 6/9/2022 Moved $90K in forecast to April 2023 due to supply chain issues with material. DRM 6/2/2022 Met with Arseal last week. May be shipping delay of the material to late this year. DRM 4/1/2022 DRM PO Issued to Arseal. The work will occur in 4Q due to long lead for material delivery. 3/1/2022 DRM requested quote from Arseal to complete the AFE. | 2023-04-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Mechanicsburg | MP - MECHANICSBURG STATION |  | 4839 | 1729 | 90000 |  | 43553 |  | Forsey, Frank | Orischak, Bob |  |  | 1 | 34758 |  | Guest, ProSight | Independent | Aqua | 2019-08-29 | Other Programs
Mechanicsburg Station Unit 1 Piping Replacement | Item | Open | MCAP | MP00000M2301 | Maintenance Framework | 2074854 | Gebert, Clint | East | 3. Active | Defined | Facility Integrity | 57748 | 394000 |  | 451748.09 | 450309 | 1439 | Yellow | 450000 |  | 450000 | 1748 |  |  | 469903 |  |  | 469903 | Full | 469903 | 57748 | 394000 | 451748 | No | Green | 2023-01-01 | 2023-04-13 | 2023-04-13 | 2023-12-31 | 2023-10-31 |  |  | 29033 | 1273.49 | 26002.43 | 1439.17 |  |  | 1439 | Red | [6 empty] | 200000 | 194000 |  |  |  | 5/3/2023-Work won't happen until there are 2 units funtional in Mechanicsburg. 3/3/2022-Materials came in in Feb. 2/3/2022-Variance due to a material order which was needed ASAP after AFE was created. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Mechanicsburg | MP - MECHANICSBURG STATION |  | 56309 | 1439 | 200000 | 194000 |  |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 40731 |  | Clark, David | Independent | Aqua | 2021-07-23 | Int - Planned Corr & FI
Mechanicsburg Station Unit 2 Piping Replacement | Item | Open | MCAP | MP00000M2204 | Maintenance Framework | 2046226 | Gebert, Clint | East | 3. Active | Defined | Facility Integrity | 60497 | 379125 |  | 439621.69 | 466282 | -26660 | Yellow | 190000 | 195000 | 385000 | 54622 |  |  | 438000 |  |  | 438000 | Full | 438000 | 60497 | 379125 | 439622 | No | Green | 2023-01-01 | 2022-12-06 | 2022-12-06 | 2023-04-30 | 2023-06-30 |  |  | 30785.55 | 1964.85 | 26281.55 | 1464.74 | 89125 | 89125 | -87660 | Red |  | Other |  | 89000 | 210125 | 60000 | 20000 |  |  |  |  | 5/3/23-CGG- variance due to Unit coming back from hydro east and needing to go back for repairs. 3/3/2023-Variance caused by delay in materials which are expected shortly. 2/3/2023-Variance due to ordering half of what was planned, 1/5/23-CGG- variance due to material order not able to be placed in December. Material costs should hit January.12/5/2022-Hoping to order materials in Dec. 11/28/22-CGG- AFE submitted. 2022-09-12 - Part of the forecast was pushed to 2023. Resource issues with no available PMs. Region reviewing options for starting project still in Q4 2022. 9.12.22.DLC: Moved forecast into 2023 per PM 7/6/22-CGG- No time to work on this at the moment. Hoping to fit project in later in the year. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity | Integrity | Mechanicsburg | MP - MECHANICSBURG STATION |  | 59032 | 90465 | 290125 |  |  |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 40515 |  | Guest, ProSight | Independent | Aqua | 2021-07-12 | Int - Planned Corr & FI
Mechanicsburg Unit 2 Pump Repair | Item | Open | MEXP | MG00000E2301 | Maintenance Framework | 2084869 | Orischak, Bob | East | 6. Operational | Drawdown | Rotating Equipment | 72828 | 25001 |  | 97828.93 | 86792 | 11037 | Red |  |  |  | 97829 |  |  | 65000 |  |  | 65000 | Full | 65000 | 72828 | 25001 | 97829 | No | Green | 2023-03-01 | 2023-02-15 | 2023-02-15 | 2023-03-15 | 2023-03-31 |  |  |  |  | 56790.56 | 16037.37 | 30000 | 30000 | -13963 | Red |  | Contractor/Vendor Issue | 25000 | [6 empty] | 1 |  | 5/1/23 RLO the pump that was delivered had an issue with the rotor. rebuild company is blaming Buckeye. This is going to be an extra 25k hitting this project. 04/3/23 RLO - All money from this project is currently hitting OPEX. This will be reclassed to this project upon complete. Expected to be complete by 4/8/23 [MCS 4/3/2023-accruing 35K for HydroEast, and will do residual flip from local for April business]. 3/28/2023 - I put in flip ticket to move the 35K on WO 2051620 local budget onto this project. MCS. 3/9/2023 - Will put 35K flip ticket in (for March business) for payroll and small purchases already incurred on local budget. POs were proactively flipped 3/2. Changed the forecast from 65K all in April to 35K in March, 30K in April. MCS 3/1/2023 RLO Project just approved. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Mechanicsburg | MG - MECHANICSBURG EAST |  | 56791 | 41037 |  | 1 |  |  | Posipanko, Dan | Posipanko, Daniel A. | N/A |  | 1 | 46603 |  | Orischak, Bob | JDE Child | Burnt Orange | 2023-02-15 | Other Programs
Mechanicsburg West Pipeline Control Valve Replacement | Item | Open | MCAP | MT00000M2301 | Maintenance Framework | 2111211 | Gebert, Clint | East | 2. Pending AFE |  | Valves | 915 | 100000 |  | 100914.93 | 100000 | 915 | Yellow | 100000 |  | 100000 | 915 | [6 empty] | Interim |  | 915 | 100000 | 100915 | No | Green | 2023-04-01 |  |  |  | 2023-09-30 | [5 empty] | 914.93 |  |  | 915 | Red | [6 empty] | 100000 | [6 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Mechanicsburg | MT - MECHANICSBURG WEST |  |  | 915 | 100000 |  |  |  | Oey, Alex | Oey, Alexander |  |  | 1 | 34118 |  | Guest, ProSight | Independent | Aqua | 2019-08-19 | Other Programs
MP720DT - Digs from 2021 GEO+XYZ ILI | Item | Open | MCAP | MP720KTM2201 | Exempt | 1945854 | Gebert, Clint | East | 7. Closed | Defined | Pipeline Digs | 497 |  |  | 496.58 | 497 | 0 | Green |  |  |  | 497 |  |  | 931000 |  |  | 931000 | Full | 931000 | 627278 |  | 627278 | No | Green | 2022-02-01 | 2022-03-26 | 2022-03-26 | 2022-12-31 | 2022-08-31 |  |  | 496.58 | [18 empty] | 1/12/2023 - Closed WO/PO, set OPPM Project status to 'Closed'. MCS 12/5/2022-Can close. 9/6/22-CGG- Project is complete. Awaiting final invoices. Project will be completed under budget due to ability to open multiple sites and minimize amount of time Welders and NDT crew were required to be on site. Forecast reduced to reflect expected savings. 8/3/2022- Permits obtained, crew is mobilized on-site. 7/6/2022-Still waiting on permits. Variance due to DEP comments to Kiely. 5/4/2022-Still waiting on permits. 4/5/22-CGG- Permits submitted. Work will be scheduled after permits are received. Forecast is a estimated timeframe at this point. 3/14/22-CGG-AFE submitted. Cannot update forecast due to OPPM locked. Emailed Program owner and D.Clark total amount of $938,000 with monthly forecast. Environmental permitting has begun. Permit issuance and conditions will dictate when spends occur. Right now June, July, and August is the assumed timeline. 3/4/2022 -" Started permitting. Money can be [is] shown in August and September for now". -Clint Gebert. 3/3/22 - Project moved to Clint Gebert (per Ed Keeth). 3/3/22 This is Clint Geberts project and should be moved to his oppm. EK5507 | 2023-01-12 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Mechanicsburg | MP720KT - MECHANICSBURG-NEW KINGSTON |  | 497 | 0 |  |  | 626782 |  | Bartal, Nick | Guenther, Steve |  |  | 1 | 41007 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
MX750LX - Install CP System Along MX750LX | Item | Open | MCAP | MX750LXM2101 | Exempt | 1803601 | Gable, Rob | East | 3. Active | Defined | Cathodic Protection | 354 | 105500 |  | 105853.89 | 105763 | 90 | Yellow |  |  |  | 105854 |  |  | 117000 |  |  | 117000 | Full | 117000 | 19049 | 105500 | 124549 | No | Green | 2021-01-01 | 2021-01-20 | 2021-01-20 | 2021-11-15 | 2023-05-31 |  |  | 86.24 | 87.79 | 89.37 | 90.49 |  |  | 90 | Red |  |  | 24000 |  | 45000 | 36500 | [5 empty] | 5/2/2023 RAG - Will work on property rights during Q2. 3/2/2023 RAG - Work to begin during Q2. 2/2/2023 RAG - Work had previously been deferred into 2023. 1/4/2023 RAG - Work had previously been deferred into 2023. 12/2/2022 RAG - Work had previously been deferred into 2023. 11/3/2022 RAG - Work had previously been deferred into 2023. 9/30/2022 RAG - ROW Specialist is still finalizing the ROW rights for the groundbed and pole. Funds forecasted into 2023. 9/6/2022 RAG - Spoke to ROW Specialist. He has sent letters. He will contact farm owner in person during 1st 2 weeks of September. 8/2/2022 RAG - Waiting for property rights assistance from ROW Specialist. 7/1/2022 RAG - Waiting for property rights assistance from ROW Specialist. 6/2/2022 RAG - Waiting for property rights assistance from ROW Specialist. 5/2/2022 RAG - Requests sent to Regional ROW Agent for property rights assistance. 4/4/2022 RAG - Reviewing final design adjustments. 3/2/2022 RAG - Preparing work to begin as forecasted. 2/2/2022 RAG - Coordinating with ROW Agent to purchase property rights during Q1. 1/4/2022 RAG - Work will continue during 2022. 12/2/2021 RAG - Work deferred to 2022 per Rob Geib. 9/16/2021 RAG - As per discussion with Rob Geib, remaining $109,000 forecasted for 2021 will be forecasted to 2022 and now moved to project EP00000M2101. 9/2/2021 RAG - Design received. 8/3/2021 RAG - Design work performed during July. 7/6/2021 RAG Design being performed the week of 7/12. 6/2/2021 RAG - Location has been determined. Testing and design will start in June. 4/2/2021 RAG - Location search and design to be performed in Q2. 3/2/2021 RAG - AFE approved. 1/8/2021 RAG - AFE Submitted. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Malvern | MX750LX - MALVERN TO LANCASTER JCT |  | 263 | 24090 | 81500 |  | 7604 |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 25713 |  | Guest, ProSight | Independent | Aqua | 2017-09-08 | Other Programs
New Haven - Waterfront - Fuel loading platform engineering assessment | Item | Candidate | MCAP |  | Project Framework |  | Wojton, Brian | East | 1. Proposed |  | Marine |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 | [9 empty] | 600000 | 600000 | No | Green | 2023-09-01 |  |  |  | 2023-09-30 | [16 empty] | 100000 |  |  |  |  | 05/08/2023 - discussions with Ops regarding scope of the fuel loading platform assessment IP. | 2023-05-08 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  |  | 0 | 100000 |  |  | 500000 | Spari, Markella |  |  |  | 1 | 45118 |  | Spari, Markella | Independent | Aqua | 2022-08-19 | Marine
New Haven - Waterfront Dock repairs | Item | Candidate | MEXP |  | Project Framework |  | Wojton, Brian | East | 1. Proposed |  | Marine |  | 120000 |  | 120000 | 120000 | 0 | Green | 120000 |  | 120000 | 0 | [9 empty] | 120000 | 120000 | No | Green | 2023-09-01 |  |  |  | 2023-09-30 | [16 empty] | 120000 |  |  |  |  | 05/08/2023 - visit to be scheduled in June to prepare scope of work. | 2023-05-08 |  |  | East | Pipelines and Terminals | Station/Terminal |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  |  | 0 | 120000 |  |  |  | Spari, Markella |  |  |  | 1 | 45802 |  | Clark, David | Independent | Aqua | 2022-09-10 | Marine
New Haven 85 East - Bulkhead Replacement | Item | Open | MCAP | BNTNX00M2205 | Project Framework | 2053733 | Wojton, Brian | East | 3. Active | Defined | Marine | 98227 | 95000 |  | 193227.35 | 210670 | -17443 | Yellow | 250000 |  | 250000 | -56773 |  |  | 250000 |  |  | 250000 | Phase | 250000 | 142457 | 95000 | 237457 | No | Green | 2022-12-01 | 2022-12-28 | 2022-12-28 | 2023-08-30 | 2023-08-31 |  |  | 15809.35 | 48606.36 | 21254.5 | 12557.14 | 15000 | 15000 | -2443 | Red |  |  | 15000 | 30000 | 50000 | [6 empty] | 05/08/2023 - meeting set 5/10 to review parameters for conceptual bulkhead design. 4/21/23 - Bowman is evaluating the data and providing options to Buckeye on best repair. 3/3/2023 - additional costs occurred due to down time caused by Operations activities. 11/23/2022 - moved 50k into Dec. for Geotech work pulled forward. | 2023-05-08 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNX - New Haven 85 East Terminal |  | 85670 | 57557 | 50000 |  | 44230 |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 45880 |  | Clark, David | Independent | Aqua | 2022-09-20 | Other Programs
New Haven 85 East - OWS Recondition | Item | Open | MCAP | BNTNX00M2304 | Maintenance Framework | 2119758 | Schwindt, Joseph | East | 3. Active | Defined | Storm Water Management |  | 200000 |  | 200000 | 200000 | 0 | Green | 200000 | 22300 | 222300 | -22300 |  |  | 223000 |  |  | 223000 | Full | 223000 |  | 200000 | 200000 | No | Green | 2023-06-01 | 2023-05-01 | 2023-05-01 | 2023-09-30 | 2023-09-30 | [6 empty] | 0 | 0 | 0 | Green |  |  |  | 60000 |  |  | 140000 |  |  |  |  | 5/1/2023 - Getting quotes. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNX - New Haven 85 East Terminal |  |  | 60000 | 140000 |  |  |  | Bonenberger, Mark | Orischak, Bob |  |  | 1 | 44451 |  | Guest, ProSight | Independent | Aqua | 2022-08-08 | Other Programs
New Haven 85 East (BNTNX) - Loading Rack Containment Improvements | Item | Candidate | MCAP |  | Maintenance Framework |  | Schwindt, Joseph | East | 1. Proposed |  | Secondary Containment |  | 65000 |  | 65000 | 65000 | 0 | Green | 65000 |  | 65000 | 0 | [9 empty] | 65000 | 65000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 65000 | [10 empty] | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNX - New Haven 85 East Terminal |  |  | 0 | 65000 |  |  |  | Clark, Dave |  |  |  | 1 | 45792 |  | Clark, David | Independent | Aqua | 2022-09-10 | Other Programs
New Haven 85 East Dredging | Item | Open | MCAP | BNTNX00M2202 | Project Framework | 1954939 | Wojton, Brian | East | 3. Active | Defined | Marine | 97805 | 175000 |  | 272805.47 | 267518 | 5288 | Yellow |  |  |  | 272805 |  |  | 84000 | 244000 |  | 328000 | Phase | 328000 | 187420 | 175000 | 362420 | No | Green | 2022-03-01 | 2022-03-03 | 2022-03-03 | 2022-10-30 | 2023-07-31 |  |  | 60252.48 | 18059.16 | 14206.19 | 5287.64 | 0 | 0 | 5288 | Red |  |  | 0 | 0 | 35000 |  | 140000 |  |  |  |  | 04/05/23: MKS Due to uncertainties with this project and permitting considerations this project may not be completed this year. Reallocating 470K to fund project OPPM ID 46566 Perth Amboy Biodiesel LA Refurbishment. 1.30.23 SDB: Laboratory can now proceed with secondary phase of Tier III Biological testing. Scheduling sediment coring in February. 1.3.23 SDB: Received laboratory analytical for the first phase of testing. Phase II of the Tier III testing still needs to be completed once clam species needed is available. 1.3.2023 TN - Delay due to needed materials for testing by contractor. 1.25.22 SDB: Bioaccumulation test will be completed next year. The sheet wall will need to be replaced before dredging can be completed. 10.31.22 TN - Triton unable to do sediment testing at the moment, will go into next year. 10.31.22 SDB: Coring contractor completed coring work and samples are in the lab for elutriate testing. 10.18.22 SDB: Coring contractor scheduled for 10/24. Can only complete elutriate testing as the required clam species needed for bioacculmulation test are not available. Delay of approximately 3 months. 10.5.22 SDB: Received final SAP plan from ACOE. TCC is scheduling the coring contractor. 9.7.22:MKS 2023 forecast adjusted to 750K. 9.2.22 SDB: TCC received PO for Tier III testing. 8.25.22 SDB: Proposal accepted and an AFE to cover these costs is being approved. A new PO for these additional services will be issued to TCC. 8.15.22 SDB: TCC to provide us with a proposal for the elutriate testing required. 8.1.22 SDB: TCC received suitability determination from ACOE. TCC reviewed the reply in order to determine path forward as a Full Tier III will be the most likely at the moment. 7.8.22 SDB: Triton Coastal Consultants is waiting on ACOE reply on the suitability determination which is under review. Dredging may be delayed as the failed bulkhead will need to be repaired prior to dredging. 6.9.22.DLC: Added back in $100k for engineering for 2023 effort. 6.6.22 KDB: Projected Budget $950K; $860K has yet to be forecasted. 5.31.22 SDB: TCC presently waiting for the reply regarding the suitability determination from the ACOE. Once received we can then submitthe application to the CT DEEP/ACOE. 5.2.22 SDB: TCC continues working on submittal documentation and looking at alternate dredgingand disposal scenarios. 3.31.22 SDB: Data was submitted to ACOE/ CT DEEP on first week of March. Waiting for the ACOE suitability determination in 3-6 months. 3.7.22 SDB: Soil samples results received. Discussing path forward with TCC and options. 3.1.22 SDB: Requested Phase 1 AFE and is routed for Approval. 2.18.22.DLC: Getting sample results in Feb and wall inspected to finalize scope. | 2023-04-05 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNX - New Haven 85 East Terminal |  | 92518 | 5288 | 175000 |  | 89614 |  | Spari, Markella | Spari, Markella |  |  | 1 | 42162 |  | Clark, David | Independent | Aqua | 2021-09-16 | Marine
New Haven 85 East Rack Fall Protection | Item | Candidate | MCAP |  | Maintenance Framework |  | Schwindt, Joseph | East | 1. Proposed |  | East |  | 155000 |  | 155000 | 155000 | 0 | Green | 155000 |  | 155000 | 0 | [9 empty] | 155000 | 155000 | No | Green | 2023-06-01 |  |  |  | 2023-11-30 | [13 empty] | 80000 |  |  |  |  | 75000 |  |  | 4/3/2023 - Joe Schmidt will contact vendor (Bullard) to get an estimate. | 2023-04-03 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNX - New Haven 85 East Terminal |  |  | 80000 |  | 75000 |  |  | Orischak, Bob |  |  |  | 1 | 44530 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Other Programs
New Haven 85 East Terminal (BNTNX) Tank 15A - OOS API 653 Insp | Item | Open | MCAP | BNTNX00M2302 | Maintenance Framework | 2086562 | Marrocco, Alex | East | 3. Active | Defined | Tanks | 47652 | 900000 |  | 947652.09 | 270000 | 677652 | Red | 989914 |  | 989914 | -42262 |  |  | 127770 |  |  | 127770 | Phase | 127770 | 47652 | 900000 | 947652 | No | Green | 2023-04-01 | 2023-02-27 | 2023-02-27 | 2023-07-31 | 2023-07-31 | [5 empty] | 47652.09 | 20000 | 20000 | 27652 | Red |  |  | 100000 | 300000 | 300000 | 200000 | [5 empty] | 4/5/2023 Tank cleaning was late in starting and has since been completed. Inspection is underway. 3/3/2023 Work is behind schedule due to contractor availability. Expect to resume project this month. | 2023-05-08 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | New Haven Harbor | BNTNX - New Haven 85 East Terminal |  |  | 447652 | 500000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44853 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
New Haven 85 East Terminal (BNTNX) Tank 8A - OOS API 653 Insp | Item | Open | MCAP | BNTNX00M2303 | Maintenance Framework | 2086548 | Marrocco, Alex | East | 3. Active | Defined | Tanks | 128470 | 267000 |  | 395470.11 | 282774 | 112696 | Red | 395222 |  | 395222 | 248 |  |  | 225095 |  |  | 225095 | Phase | 225095 | 128470 | 267000 | 395470 | No | Green | 2023-03-01 | 2023-02-27 | 2023-02-27 | 2023-06-30 | 2023-05-31 |  |  |  |  | 12773.93 | 115696.18 | 70000 | 70000 | 45696 | Red |  |  | 100000 | 100000 | 67000 | [6 empty] | 4/5/2023 Tank was late in coming out-of-service. Tank is now out-of-service and being cleaned. | 2023-04-05 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | New Haven Harbor | BNTNX - New Haven 85 East Terminal |  | 12774 | 315696 | 67000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44855 |  | Administrator, System | Independent | Aqua | 2022-08-18 | Int - Tanks
New Haven 85 East Terminal (BNTNX) Tank 17A Inspection and Repair | Item | Open | MEXP | BNTNX00E2302 | Maintenance Framework | 2110060 | Marrocco, Alex | East | 3. Active | Drawdown | Tanks | 140000 | 10000 |  | 150000 | 150000 | 0 | Green |  |  |  | 150000 |  |  | 150000 |  |  | 150000 | Full | 150000 | 140000 | 10000 | 150000 | No | Green | 2023-04-01 | 2023-04-07 | 2023-04-07 | 2023-08-31 | 2023-08-31 | [5 empty] | 140000 | 50000 | 50000 | 90000 | Red |  |  | 10000 | [10 empty] | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | New Haven Harbor | BNTNX - New Haven 85 East Terminal |  |  | 150000 |  |  |  |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 46906 |  | Stine, Carlton | JDE Child | Burnt Orange | 2023-04-07
New Haven Booster #1 (AA) - Arc Flash Study | Item | Open | MEXP | HV00000E2301 | Maintenance Framework | 2077118 | DeSocio, David | East | 3. Active | Defined | Arc Flash |  | 13000 |  | 13000 | 13000 | 0 | Green | 13000 |  | 13000 | 0 |  |  | 12100 |  |  | 12100 | Full | 12100 |  | 13000 | 13000 | No | Green | 2023-08-01 | 2023-01-31 | 2023-01-31 | 2023-11-01 | 2023-08-31 | [15 empty] | 13000 | [7 empty] | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Jet Lines | HV - NEW HAVEN TERMINAL |  |  | 0 | 13000 |  |  |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 41613 |  | Ashley, Robert | Independent | Aqua | 2021-08-19 | Other Programs
New Haven booster #2 (BA) - Arc Flash Study | Item | Open | MEXP | HV00000E2302 | Maintenance Framework | 2077116 | DeSocio, David | East | 3. Active | Defined | Arc Flash |  | 13000 |  | 13000 | 13000 | 0 | Green | 13000 |  | 13000 | 0 |  |  | 12100 |  |  | 12100 | Full | 12100 |  | 13000 | 13000 | No | Green | 2023-08-01 | 2023-01-31 | 2023-01-31 | 2023-11-01 | 2023-08-31 | [15 empty] | 13000 | [7 empty] | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Jet Lines | HV - NEW HAVEN TERMINAL |  |  | 0 | 13000 |  |  |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 41615 |  | Ashley, Robert | Independent | Aqua | 2021-08-19 | Other Programs
New Haven CP Upgrade | Item | Open | MCAP | HV00000M2301 | Maintenance Framework | 2095654 | Occhi, Edward | East | 3. Active | Defined | Marine | 2880 | 25000 |  | 27879.5 | 35000 | -7121 | Red | 35000 |  | 35000 | -7121 |  |  | 34950 |  |  | 34950 | Full | 34950 | 2880 | 25000 | 27880 | No | Green | 2023-04-01 | 2023-03-20 | 2023-03-20 | 2023-12-20 | 2023-04-30 | [5 empty] | 2879.5 | 0 | 0 | 2880 | Red |  |  | 0 | 0 | 25000 | [8 empty] | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Jet Lines | HV - NEW HAVEN TERMINAL |  |  | 2880 | 25000 |  |  |  | Spari, Markella | Spari, Markella |  |  | 1 | 45085 |  | Guest, ProSight | Independent | Aqua | 2022-08-18 | Marine
New Haven Dock Line API-570 Repairs | Item | Open | MEXP | BNTNV00E2206 | Maintenance Framework | 2052954 | Wojton, Brian | East | 3. Active | Unplanned | Facility Integrity | -4071 | 30000 |  | 25928.74 | 29929 | -4000 | Red |  |  |  | 25929 |  |  | 43000 |  |  | 43000 | Phase | 43000 | 22929 | 30000 | 52929 | No | Green | 2022-12-01 | 2022-12-20 | 2022-12-20 | 2023-08-30 | 2023-05-31 |  |  | -71.26 | 0 | 0 | -4000 | 0 | 0 | -4000 | Red |  |  | 10000 | 20000 | [7 empty] | 1/05/2023 - less work completed due to weather. 2/20/2023 - moved resumed spending to April for better weather conditions. | 2023-02-20 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  | -71 | 26000 |  |  | 27000 |  | Aiken, Elaine |  |  |  | 1 | 46271 |  | Aiken, Elaine | Independent | Aqua | 2022-11-29 | Int - Planned Corr & FI
New Haven Forbes (BNTNF) Tank 30M IFR Inspection & Refurb | Item | Open | MEXP | BNTNF00E2301 | Maintenance Framework | 2052993 | Marrocco, Alex | East | 3. Active | Drawdown | Tanks | 15366 | 60000 |  | 75366.08 | 75366 | 0 | Green |  |  |  | 75366 |  |  | 60000 |  |  | 60000 | Full | 60000 | 15366 | 60000 | 75366 | No | Green | 2023-01-01 | 2022-12-21 | 2022-12-21 | 2023-02-28 | 2023-06-30 |  |  | 13800 | -62.5 | 1628.58 |  | 60000 | 60000 | -60000 | Red |  | Buckeye/Customer Schedule | 60000 | [8 empty] | 5/3/2023 Contractor unavailable to do work; scheduled for mid May 2023. 4/5/2023 Tank Cleaning is complete; IFR has been inspected; waiting on fabrication and installation of components. 3/3/2023 work is behind schedule due to operational constraints. | 2023-05-03 | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | New Haven Harbor | BNTNF - New Haven Forbes Termina |  | 15366 | 60000 |  |  |  |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 46395 |  | Stine, Carlton | JDE Child | Burnt Orange | 2022-12-21 | Int - Tanks
New Haven Forbes (BNTNF) Tank 32M IFR Inspection & Refurb | Item | Open | MEXP | BNTNF00E2302 | Maintenance Framework | 2053000 | Marrocco, Alex | East | 3. Active | Drawdown | Tanks | 15366 | 60000 |  | 75366.08 | 75366 | 0 | Green |  |  |  | 75366 |  |  | 60000 |  |  | 60000 | Full | 60000 | 15366 | 60000 | 75366 | No | Green | 2023-01-01 | 2022-12-21 | 2022-12-21 | 2023-02-28 | 2023-06-30 |  |  | 13800 | -62.5 | 1628.58 |  | 0 | 0 | 0 | Green |  |  | 0 | 60000 | [7 empty] | 3/3/2023 Work is behind schedule due to operational constraints. | 2023-03-03 | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | New Haven Harbor | BNTNF - New Haven Forbes Termina |  | 15366 | 60000 |  |  |  |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 46396 |  | Stine, Carlton | JDE Child | Burnt Orange | 2022-12-21 | Int - Tanks
New Haven Forbes Dead Leg Removal 2023 | Item | Open | MEXP | BNTNF00E2206 | Maintenance Framework | 2046375 | Wojton, Brian | East | 6. Operational | Defined | Facility Integrity | 156343 | 0 |  | 156342.67 | 156343 | 0 | Green | 290400 |  | 290400 | -134057 |  |  | 290000 |  |  | 290000 | Phase | 290000 | 299948 | 0 | 299948 | No | Green | 2022-11-01 | 2022-11-30 | 2022-11-30 | 2023-12-31 | 2023-05-01 |  |  | 70275.55 |  | 86067.12 | [8 empty] | 0 | [7 empty] | 4/5/2023 - More work in done in March to take advantage of tanks being out-of-service. 2/3/2023 - more work completed than expected. Ops gave approval to complete ethanol dead leg work. 01/05/2023 - completed more dead leg work in 2022 than expected. 12/09/2023 - Approval to advance some funds from the 2023 budget into December 2022 while contractors are already working at the site on dead leg remediation. | 2023-04-05 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | New Haven Harbor | BNTNF - New Haven Forbes Termina |  | 156343 | 0 |  |  | 143606 |  | Aiken, Elaine |  |  |  | 1 | 45404 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
New Haven Forbes Dead Leg Removal Phase 1 | Item | Open | MEXP | BNTNF00E2202 | Maintenance Framework | 1946836 | Wojton, Brian | East | 7. Closed | Defined | Facility Integrity | 1118 |  |  | 1117.88 | 1118 | 0 | Green |  |  |  | 1118 |  |  | 116000 | 100000 |  | 216000 | Phase | 216000 | 260755 |  | 260755 | No | Green | 2022-02-01 | 2022-04-14 | 2022-04-14 | 2022-10-30 | 2022-11-30 |  |  | 1117.88 | [18 empty] | 01/05/2023 more work completed than expected for project close out. 10/5/2022 Delay due to Waterfront Release Repair. 9/22/2022 - Phoenix to work on Forbes dead leg release instead of contracted work. Work to resume late Sept./Oct. 8/8/2022 - majority of work pushed to Sept./Oct. due to Contractor avail. 6/1/2022 - supplemental for 100k routed and added 100k to forecast. 5/30/2022 - based on bids, another 100k needed to complete 2022 scope. 4/1/2022 - out to bid for dead leg scope. | 2023-01-05 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | New Haven Harbor | BNTNF - New Haven Forbes Termina |  | 1118 | 0 |  |  | 259638 |  | Aiken, Elaine | Buchalski, Edwin |  |  | 1 | 37119 |  | DeSocio, David | Independent | Aqua | 2020-07-16 | Int - Planned Corr & FI
New Haven Forbes Release Repairs | Item | Open | MEXP | BNTNF00E2205 | Maintenance Framework | 2013355 | Wojton, Brian | East | 7. Closed | Drawdown | Facility Integrity | 5098 |  |  | 5097.92 | 5098 | 0 | Green |  |  |  | 5098 |  |  | 50000 |  |  | 50000 | Full | 50000 | 67297 |  | 67297 | No | Green | 2022-09-01 | 2022-08-25 | 2022-08-25 | 2022-10-31 | 2022-11-30 |  |  | 891.8 | 3056.74 | 1149.38 | [16 empty] | 2/8/2023 a couple of soil borings from GES still pending from PO...project can be closed when these are finished. 1/3/2023 - additional costs during project closeout. 10/5/2022 Contractor used for Forbes release repair. 9/1/2022 - work scheduled for Sept. (funding from Integrity draw down.) | 2023-03-08 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | New Haven Harbor | BNTNF - New Haven Forbes Termina |  | 5098 | 0 |  |  | 62199 |  | Aiken, Elaine | Aiken, Elaine | N/A |  | 1 | 45240 |  | Aiken, Elaine | JDE Child | Burnt Orange | 2022-08-24 | Int - Planned Corr & FI
New Haven Forbes Stormwater Systems Upgrades | Item | Open | MCAP | BNTNF00M2205 | Maintenance Framework | 1980911 | Wojton, Brian | East | 6. Operational | Defined | Storm Water Management | 9643 |  |  | 9643.34 | 9643 | 0 | Green |  |  |  | 9643 |  |  | 50000 |  |  | 50000 | Full | 50000 | 49282 |  | 49282 | No | Green | 2022-08-01 | 2022-05-18 | 2022-05-18 | 2022-08-30 | 2022-12-31 |  |  | 6040.35 | 3379.29 | 223.7 | [16 empty] | 9/15/2022 - sampling scheduled for Sept. 8/8/2022 - work scheduled to start late Aug. | 2022-09-26 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNF - New Haven Forbes Termina |  | 9643 | 0 |  |  | 39638 |  | Bonenberger, Mark |  |  |  | 1 | 40903 |  | Guest, ProSight | Independent | Aqua | 2021-08-03 | Other Programs
New Haven Forbes Terminal (BNTNF) Tank 21M - OOS Corr + Seal Insp & Refurb | Item | Open | MCAP | BNTNF00M2201 | Maintenance Framework | 1937221 | Marrocco, Alex | East | 3. Active | Defined | Tanks | 281727 | 15000 |  | 296727.17 | 262095 | 34633 | Red | 75000 |  | 75000 | 221727 |  |  | 364000 |  |  | 364000 | Phase | 364000 | 284397 | 15000 | 299397 | No | Green | 2022-10-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2023-05-31 |  |  | 49251.91 | 124527.6 | 73315.16 | 34632.5 | 15000 | 15000 | 19633 | Red |  |  | 15000 | [8 empty] | 4/5/2023 Cost of IFR seals repairs came in less than expected. 3/3/2023 Work behind schedule due to contactor availability (Allentech). 2/3/2023 scope of work less than anticipated. 1/5/2023 project is behind schedule. 12/5/2022 Cleaning costs to be assumed by Forbes stripping tanks AFE. 11/3/2022 charges for isolation, stripping and cleaning are being covered by BNTNF00B2201. 9/2/22-CES-New Haven tanks will start in October due to CCI exit strategy and timing needed for commercial. Updating forecast accordingly and moving some funds into 2023. | 2023-04-05 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | New Haven Harbor | BNTNF - New Haven Forbes Termina |  | 247095 | 49633 |  |  | 2670 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41296 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
New Haven Forbes Terminal (BNTNF) Tank 29M - OOS Corr Insp & Refurb | Item | Open | MCAP | BNTNF00M2202 | Maintenance Framework | 1937223 | Marrocco, Alex | East | 3. Active | Defined | Tanks | 230333 | 15000 |  | 245333.41 | 233428 | 11905 | Yellow | 50000 |  | 50000 | 195333 |  |  | 164000 |  |  | 164000 | Phase | 164000 | 231317 | 15000 | 246317 | No | Green | 2022-10-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2023-05-31 |  |  | 38098.55 | 68852.85 | 86476.78 | 36905.23 | 40000 | 40000 | -3095 | Yellow |  | Contractor/Vendor Issue | 15000 | [8 empty] | 4/5/2023 Allentech completed work ahead of schedule and invoice at $51K was paid. 3/3/2023 Work behind schedule due to contactor availability (Allentech). 1/5/2023 Tank had to return to service temporarily to meet customer demands. 12/5/2022 Cleaning costs to be assumed by Forbes stripping tanks AFE. 11/3/2022 charges for isolation, stripping and cleaning are being covered by BNTNF00B2201. 9/2/22-CES-New Haven tanks will start in October due to CCI exit strategy and timing needed for commercial. Updating forecast accordingly and moving some funds into 2023. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | New Haven Harbor | BNTNF - New Haven Forbes Termina |  | 193428 | 51905 |  |  | 984 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41297 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
New Haven Forbes Terminal (BNTNF) Tank 31M - OOS Corr + Seal Insp & Refurb) | Item | Open | MCAP | BNTNF00M2203 | Maintenance Framework | 1937224 | Marrocco, Alex | East | 3. Active | Defined | Tanks | 383223 | 40000 |  | 423223.34 | 392836 | 30388 | Yellow | 25000 |  | 25000 | 398223 |  |  | 199000 |  |  | 199000 | Phase | 199000 | 456151 | 40000 | 496151 | No | Green | 2022-10-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2023-05-31 |  |  | 220324.93 | 115927.48 | 41583.2 | 5387.73 | 15000 | 15000 | -9612 | Red |  |  | 40000 | [8 empty] | 1/5/2023 Project is behind schedule. 12/5/2022 Cleaning costs to be assumed by Forbes stripping tanks AFE. 11/3/2022 charges for isolation, stripping and cleaning are being covered by BNTNF00B2201. 9/2/22-CES-New Haven tanks will start in October due to CCI exit strategy and timing needed for commercial. Updating forecast accordingly and moving some funds into 2023. | 2023-01-05 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | New Haven Harbor | BNTNF - New Haven Forbes Termina |  | 377836 | 45388 |  |  | 72928 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41298 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
New Haven Hamden Containment Wall Emergency Refurbish | Item | Open | MCAP | BNTNH00M2301 | Maintenance Framework | 2086172 | Wojton, Brian | East | 6. Operational | Emergent | Secondary Containment | 163245 | 48000 |  | 211244.68 | 182700 | 28545 | Red |  |  |  | 211245 |  |  | 261700 |  |  | 261700 | Full | 261700 | 163245 | 48000 | 211245 | No | Green | 2023-03-01 | 2023-02-27 | 2023-02-27 | 2023-05-30 | 2023-05-01 |  |  |  |  | 82700 | 80544.68 | 50000 | 50000 | 30545 | Red |  | WorkAhead of Schedule | 48000 | [8 empty] | 05/02/2023 S&B completed work ahead of schedule. 4/21/23 Project is nearly complete and handled as an emergent project. | 2023-05-02 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNH - New Haven Hamden Terminal |  | 82700 | 128545 |  |  |  |  | Clark, Dave | Gardner, Dale |  |  | 1 | 46570 |  | Wojton, Brian | Independent | Aqua | 2023-02-01 | Other Programs
New Haven Hamden Electrical Repairs Phase I | Item | Open | MCAP | BNTNH00M2302 | Maintenance Framework | 2110420 | DeSocio, David | East | 3. Active | Defined | Electrical |  | 0 |  | 0 |  | 0 | Green | 13000 |  | 13000 | -13000 |  |  | 27378 |  |  | 27378 | Full | 27378 |  | 27000 | 27000 | No | Green | 2024-02-01 | 2023-04-10 | 2023-04-10 | 2023-11-03 | 2024-11-30 | [15 empty] | 0 | [5 empty] | 4/14/23 - Additional MCAP funding of $6,500 will be coming from East Region Drawdown. DD | 2023-04-14 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNH - New Haven Hamden Terminal |  |  | 0 | 0 |  |  | 27000 | Ashley, Robert | Stanisich, Carla D. |  |  | 1 | 44577 |  | Guest, ProSight | Independent | Aqua | 2022-08-12 | Other Programs
New Haven Lane 6 Ethanol Piping Repair | Item | Open | MEXP | BNTNX00E2205 | Maintenance Framework | 1990035 | Orischak, Bob | East | 7. Closed | Drawdown | East | 1 |  |  | 0.9 | 1 | 0 | Green |  |  |  | 1 |  |  | 16500 |  |  | 16500 | Full | 16500 | 17181 |  | 17181 | No | Green | 2022-10-01 | 2022-06-10 | 2022-06-10 | 2022-07-20 | 2022-10-31 |  |  | 0.9 | [18 empty] | 1/9/2023 - Closed WO/PO, set OPPM project status to 'Closed'. MCS. 1/3/2022-Can close. 11/2/2022 RLO-Work Completed, awaiting invoice.. 10/3/2022 RLO Waiting for Steve Wing to schedule contractor to be onsite. 8/1/2022 RLO waiting on Contractor to come onsite after biodiesels 7/1/2022 - Added the forecast to July for this work to be completed. Waiting to hear from Ops and contractor to see if they are available to fix this in July RLO | 2023-01-09 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | New Haven Harbor | BNTNX - New Haven 85 East Terminal |  | 1 | 0 |  |  | 17180 |  | Orischak, Bob | Wing, Stephen W. | N/A |  | 1 | 43948 |  | Orischak, Bob | JDE Child | Burnt Orange | 2022-06-09 | Other Programs
New Haven ML PLC Replacement 2023 | Item | Open | MCAP | EW00000M2301 | Maintenance Framework | 2076600 | Orischak, Bob | East | 3. Active | Drawdown | Instrumentation & Controls | 13293 | 52000 |  | 65293.12 | 52000 | 13293 | Red |  |  |  | 65293 |  |  | 23300 |  | 28700 | 52000 | Supplemental | 52000 | 13293 | 74000 | 87293 | Yes | Red | 2023-04-01 | 2023-01-23 | 2023-01-23 | 2023-12-15 | 2023-12-29 | [5 empty] | 13293.12 | 0 | 0 | 13293 | Red | [8 empty] | 52000 |  |  | 5/1/23- April spend was for the down-payment on the material. 2/1/2023-PO has been cut, waiting on delivery. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Jet Lines | EW - NEW HAVEN STATION |  |  | 13293 |  | 52000 |  |  | Forsey, Frank | Wing, Stephen W. |  |  | 1 | 46489 |  | Orischak, Bob | Independent | Aqua | 2023-01-17 | Other Programs
New Haven Waterfront - Tank 213 Dike field drainage | Item | Open | MCAP | BNTNV00M2203 | Maintenance Framework | 1970216 | Wojton, Brian | East | 7. Closed | Defined | Secondary Containment | 17910 |  |  | 17910.17 | 17910 | 0 | Green |  |  |  | 17910 |  |  | 78000 |  | 55000 | 133000 | Supplemental | 133000 | 134816 |  | 134816 | No | Green | 2022-06-01 | 2022-04-01 | 2022-04-01 | 2022-11-30 | 2023-03-07 |  |  | 2832.23 | 13493.98 | 1583.96 | [16 empty] | 3/3/2023 S&B completed sooner than expected. 01/05/2023 Contractors completed work ahead of schedule due to Corporate. 11/3/2022 work delayed by Operations, due to customer exit. 9/15/2022 - engineering plan reviewed by Ops. Getting prices for re-grading work. Work to start in Oct.. 8/8/2022 - engineering IP. Work scheduled to start in Sept. | 2023-03-03 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  | 17910 | 0 |  |  | 116906 |  | Clark, Dave | Spari, Markella |  |  | 1 | 40897 |  | Guest, ProSight | Independent | Aqua | 2021-08-02 | Other Programs
New Haven Waterfront (BNTNX) - Loading Rack Containment Improvements | Item | Candidate | MCAP |  | Maintenance Framework |  | Schwindt, Joseph | East | 1. Proposed |  | Secondary Containment |  | 65000 |  | 65000 | 65000 | 0 | Green | 65000 |  | 65000 | 0 | [9 empty] | 65000 | 65000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 65000 | [6 empty] | 4/3/2023 - Getting quotes, and determining an approach. | 2023-04-03 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  |  | 0 | 65000 |  |  |  | Clark, Dave |  |  |  | 1 | 45793 |  | Clark, David | Independent | Aqua | 2022-09-10 | Other Programs
New Haven Waterfront Containment Valve replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Schwindt, Joseph | East | 1. Proposed |  | Secondary Containment |  | 98000 |  | 98000 | 98000 | 0 | Green | 98000 |  | 98000 | 0 | [9 empty] | 98000 | 98000 | No | Green | 2023-06-01 |  |  |  | 2023-06-30 | [13 empty] | 98000 | [7 empty] | 4/3/2023 - Getting quotes, Joe Schwint to contact Mike Baffano about specifics on valves. | 2023-04-03 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  |  | 98000 |  |  |  |  | Clark, Dave |  |  |  | 1 | 44528 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Other Programs
New Haven Waterfront Tank 209 Staircase installation | Item | Candidate | MCAP |  | Maintenance Framework |  | Marrocco, Alex | East | 1. Proposed |  | Tanks |  | 94500 |  | 94500 | 94500 | 0 | Green | 94500 |  | 94500 | 0 | [9 empty] | 94500 | 94500 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [12 empty] | 0 |  | 44500 | 50000 | [9 empty] | East | Pipelines and Terminals | Integrity |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  |  | 0 | 94500 |  |  |  | Stine, Carlton |  |  |  | 1 | 44453 |  | Guest, ProSight | Independent | Aqua | 2022-08-08 | Int - Tanks
New Haven Waterfront Tank 216 Bottom Coating Replacement | Item | Open | MCAP | BNTNV00M2301 | Maintenance Framework | 2074810 | Marrocco, Alex | East | 6. Operational | Drawdown | Tanks | 112815 |  |  | 112815.02 | 112014 | 801 | Yellow |  |  |  | 112815 |  |  | 103153 |  |  | 103153 | Full | 103153 | 112815 |  | 112815 | No | Green | 2023-01-01 | 2023-01-09 | 2023-01-09 | 2023-02-01 | 2023-03-31 |  |  | 90097.16 | 16676.77 | 5239.74 | 801.35 |  |  | 801 | Red | [13 empty] | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  | 112014 | 801 |  |  |  |  | Stine, Carlton | Shook, Mark B. |  |  | 1 | 46440 |  | Meitzler, Antoinette | Independent | Aqua | 2023-01-09 | Int - Tanks
New Haven Waterfront Terminal (BNTNV) Tank 201 - OOS Seal Insp | Item | Open | MEXP | BNTNV00E2302 | Maintenance Framework | 2095935 | Marrocco, Alex | East | 3. Active | Defined | Tanks |  | 32000 |  | 32000 | 130000 | -98000 | Red | 130000 |  | 130000 | -98000 |  |  | 26188 |  |  | 26188 | Phase | 26188 |  | 32000 | 32000 | No | Green | 2023-09-01 | 2023-03-23 | 2023-03-23 | 2023-09-30 | 2023-11-30 | [16 empty] | 32000 |  |  |  |  | 4.14.23.DLC: Reduced overall forecast to match in-service inspection needs.. | 2023-04-14 | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  |  | 0 | 32000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44856 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
New Haven Waterfront Terminal (BNTNV) Tank 206 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | BNTNV00M2304 | Maintenance Framework | 2086482 | Marrocco, Alex | East | 3. Active | Defined | Tanks | 474 | 307000 |  | 307473.93 | 230474 | 77000 | Red | 306912 |  | 306912 | 562 |  |  | 127770 |  |  | 127770 | Phase | 127770 | 474 | 307000 | 307474 | No | Green | 2023-03-01 | 2023-02-27 | 2023-02-27 | 2023-06-30 | 2023-08-31 |  |  |  |  | 473.93 |  | 60000 | 60000 | -60000 | Red |  | Buckeye/Customer Schedule | 40000 | 150000 | 117000 | [6 empty] | 5/3/2023 Tank is still in service; scheduled to come out of service later this month. 4/5/2023 Tank was late in coming out-of-service. 9/23/22-CES-Taking 10% for budget calibration. 50/50 on MCAP/MEXP. Ethanol tank liner & seals. | 2023-05-03 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  | 474 | 190000 | 117000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44857 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
New Jersey Terminals CP Surveys | Item | Open | MEXP | BPRPR00E2205 | Maintenance Framework | 1946982 | Occhi, Edward | East | 7. Closed | Defined | Atmospheric Corrosion | 39 |  |  | 38.61 | 39 | 0 | Green |  |  |  | 39 |  |  | 28000 |  |  | 28000 | Full | 28000 | 29006 |  | 29006 | No | Green | 2022-05-01 | 2022-02-15 | 2022-02-15 | 2022-12-31 | 2022-11-30 |  |  | 38.61 | [20 empty] | Walker, Carol |  | East | Pipelines and Terminals | Corrosion |  | Linden | LNNON - LINDEN |  | 39 | 0 |  |  | 28967 |  | Geib, Rob | Geib, Robert |  |  | 1 | 40912 |  | Guest, ProSight | Independent | Aqua | 2021-08-03 | Int - Planned Corr & FI
New Kingston terminal MP720LS MP107 Removal of dead leg on old delivery line | Item | Open | MEXP | MP720KTE2301 | Maintenance Framework |  | Pepe, David | East | 8. Canceled | Defined | Facility Integrity |  | 0 |  | 0 | 0 | 0 | Green | 300000 |  | 300000 | -300000 |  |  | 301987 |  |  |  | Full | 301987 |  | 0 | 0 | No | Green |  |  |  | 2023-05-01 | 2023-07-31 | [12 empty] | 0 | 0 | [7 empty] | 3/1/2023 DJP AFE Rejected, forecast removed. 1/13/2023 DJP AFE submitted. 12/07/2022 DJP reached out for Kiely to provide a quote for engineering, purge plan, and support to complete this cutout. | 2023-02-24 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Mechanicsburg | MP720KT - MECHANICSBURG-NEW KINGSTON |  |  | 0 |  |  |  |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 37468 |  | Guest, ProSight | Independent | Aqua | 2020-08-05 | Int - Planned Corr & FI
Newark Relief System Review | Item | Candidate | MEXP |  | Maintenance Framework |  | Wojton, Brian | East | 1. Proposed |  | East |  | 25000 |  | 25000 | 25000 | 0 | Green | 25000 |  | 25000 | 0 | [9 empty] | 25000 | 25000 | No | Green | 2023-07-01 |  |  |  | 2023-02-28 | [12 empty] | 0 |  | 25000 | [10 empty] | East | Pipelines and Terminals | Station/Terminal |  | Harbor North Terminals | BETQN - BET NEWARK TERMINAL |  |  | 0 | 25000 |  |  |  | Orischak, Bob |  |  |  | 1 | 45782 |  | Clark, David | Independent | Aqua | 2022-09-09 | Other Programs
Paulsboro Station Arc Flash Study Review | Item | Open | MEXP | PY00000E2301 | Maintenance Framework | 2084744 | Mohr, David | East | 6. Operational | Defined | Arc Flash | 12000 | 0 |  | 12000 | 16000 | -4000 | Red | 20000 |  | 20000 | -8000 |  |  | 16060 |  |  | 16060 | Full | 16060 | 12000 | 0 | 12000 | No | Green | 2023-04-01 | 2023-02-16 | 2023-02-16 | 2023-04-30 | 2023-04-30 | [5 empty] | 12000 | 16000 | 16000 | -4000 | Red |  |  | 0 | [8 empty] | 5/1/2023 Arc Flash study completed and documentation loaded to Buckeye Hare Point Site 4/1/2023 Scheduled for week of 4/10. 3/1/2023 Received quote from contractor. Can pull into this qtr if needed. DRM 2/2/2022 Requested quote from contractor. 2022-Oct-4 -- reassigning to Dave Mohr per Zimmerman -- this is a 2023 project. 2020-07-01 SRZ: Funds shifted to 2021. 2020 funding will be used to do site that has not had any study at all yet. 2020-06-01 SRZ: Will file AFE this week and begin preliminary engineering on sites where accurate single lines exist. 2020-05-04 SRZ: Preparing AFE, will start minor preliminary engineering, but final site data gathering will be delayed until COVID impacts all travel again. 2020-04-01 SRZ: This project will be canceled and the funds will be used to conduct the work at other sites in the East District that have not yet had a study completed. When AFE has been approved, will adjust forecast to other sites. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Malvern | PY - PAULSBORO REFINERY |  |  | 12000 |  |  |  |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 33986 |  | Guest, ProSight | Independent | Aqua | 2019-08-13 | Other Programs
Paulsboro VFD Air Conditioner Replacement - 2023 | Item | Open | MCAP |  | Maintenance Framework |  | Mohr, David | East | 2. Pending AFE | Defined | East |  | 16000 |  | 16000 | 16000 | 0 | Green |  |  |  | 16000 |  |  | 16060 |  |  | 16060 | Full | 16060 |  | 16000 | 16000 | No | Green | 2023-08-01 | 2023-02-16 | 2023-02-16 | 2023-04-30 | 2023-08-31 | [15 empty] | 16000 | [5 empty] | 5/1/2023 Meeting on 5/4 at PY to determine the best way to replace the AC in the crowded piping environment 4/1/2023 Scheduling another meeting with contractor. 3/1/2023 Meeting contractor 3/10 at PY. DRM 2/2/2023 Requested contractor info to request a quote. | 2023-05-02 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Malvern | PY - PAULSBORO REFINERY |  |  | 0 | 16000 |  |  |  | Orischak, Bob | Tench, David | N/A |  | 1 | 20666 |  | Orischak, Bob | Independent | Aqua | 2016-08-29 | Other Programs
Pennsauken 12" #6 Oil Line Replacement | Item | Open | MCAP | BPNQP00M2101 | Exempt | 1801536 | DeSocio, David | East | 3. Active | Defined | Facility Integrity | 126 | 25001 |  | 25127.21 | 1 | 25126 | Red |  |  |  | 25127 |  |  | 75000 |  |  | 75000 | Full | 75000 | 52883 | 25001 | 77884 | No | Green | 2021-02-01 | 2021-01-05 | 2021-01-05 | 2021-08-21 | 2023-09-22 | [5 empty] | 126.21 |  |  | 126 | Red |  |  |  | 0 | 25000 |  |  |  |  | 1 |  | 3/27/2023 status changed to "on-hold," per FG. 3/8/21 - Preliminary Eng/drawing review. | 2023-03-27 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Pennsauken | BPNQP - BPN PENNSAUKEN TERMINAL |  |  | 126 | 25000 | 1 | 341 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 37326 |  | Guest, ProSight | Independent | Aqua | 2020-07-28 | Int - Planned Corr & FI
Pennsauken Ethanol Line Modifications | Item | Candidate | MCAP |  | Maintenance Framework |  | Wojton, Brian | East | 4. On-Hold | Defined | Secondary Containment |  |  |  | 0 |  | 0 | Green | [15 empty] | No | Green |  |  |  |  | 2022-04-30 | [21 empty] | 4.21.22.DLC: Removed forecast for Port Reading 2022 XOM project | 2022-04-21 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Pennsauken | BPNQP - BPN PENNSAUKEN TERMINAL |  |  | 0 |  |  |  |  | Clark, Dave |  | N/A |  | 1 | 30704 |  | DeSocio, David | Independent | Aqua | 2018-08-20 | Other Programs
Pennsauken Fire System Upgrade | Item | Open | MCAP | BPNQP00M2205 | Maintenance Framework | 1937303 | DeSocio, David | East | 8. Canceled | Defined | Fire Protection | -1016 |  |  | -1015.78 | -1016 | 0 | Green |  |  |  | -1016 |  |  | 25000 |  |  | 25000 | Full | 25000 | 0 |  | 0 | No | Green | 2022-09-01 | 2022-01-05 | 2022-01-05 | 2022-06-01 | 2023-12-31 |  |  | -1015.78 | [18 empty] | 1/18/2023 - Reclass submitted to move actuals off cancelled project and onto LN00000M2204. 6.1.22.DLC: Removed forecast. | 2023-01-18 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Pennsauken | BPNQP - BPN PENNSAUKEN TERMINAL |  | -1016 | 0 |  |  | 1016 |  | Jakubowski, Gregory | Jakubowski, Greg |  |  | 1 | 40378 |  | Guest, ProSight | Independent | Aqua | 2021-06-29 | Other Programs
Pennsauken Install Pumpoff Piping at Lane 11 Rack | Item | Candidate | MCAP |  | Maintenance Framework |  | Wojton, Brian | East | 4. On-Hold | Defined | Secondary Containment |  | 1 |  | 1 | 1 | 0 | Green |  |  |  | 1 | [9 empty] | 1 | 1 | No | Green | 2023-12-01 |  |  |  | 2022-12-31 | [19 empty] | 1 |  | 4.21.22.DLC: Removed forecast for Port Reading 2022 XOM project | 2022-04-21 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Pennsauken | BPNQP - BPN PENNSAUKEN TERMINAL |  |  | 0 |  | 1 |  |  | Clark, Dave |  | N/A |  | 1 | 19860 |  | Guest, ProSight | Independent | Aqua | 2016-08-02 | Other Programs
Pennsauken Loading Rack Containment Upgrades | Item | Open | MCAP | BPNQP00M2303 | Maintenance Framework | 2119752 | Wojton, Brian | East | 3. Active | Defined | Truck Racks |  | 11000 |  | 11000 | 11000 | 0 | Green | 11000 |  | 11000 | 0 |  |  | 12870 |  |  | 12870 | Full | 12870 |  | 11000 | 11000 | No | Green | 2023-06-01 | 2023-04-29 | 2023-04-29 | 2023-06-30 | 2023-07-15 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 11000 | [7 empty] | 3/15/2023 - project currently on hold. | 2023-03-30 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Pennsauken | BPNQP - BPN PENNSAUKEN TERMINAL |  |  | 11000 |  |  |  |  | Younce, Michael | Younce, Michael |  |  | 1 | 42241 |  | Guest, ProSight | Independent | Aqua | 2021-10-01 | Other Programs
Pennsauken MCC and Boiler Room Roof Replacements | Item | Candidate | MCAP |  | Maintenance Framework |  | Wojton, Brian | East | 1. Proposed |  | East |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 | [9 empty] | 40000 | 40000 | No | Green | 2023-07-01 |  |  |  | 2023-06-30 | [13 empty] | 0 | 40000 | [10 empty] | East | Pipelines and Terminals | Operating Infrastructure |  | Pennsauken | JY - PENNSAUKEN DELIVERY LOCATION |  |  | 0 | 40000 |  |  |  | Orischak, Bob |  |  |  | 1 | 42243 |  | Guest, ProSight | Independent | Aqua | 2021-10-01 | Other Programs
PENNSAUKEN RECOAT UNDERWATER LINES | Item | Open | MCAP | BPNQP00M2204 | Maintenance Framework | 1938629 | DeSocio, David | East | 8. Canceled | Defined | Facility Painting | -15 |  |  | -15.13 | -15 | 0 | Green |  |  |  | -15 |  |  | 30000 |  |  | 30000 | Full | 30000 | 0 |  | 0 | No | Green | 2022-09-01 | 2022-01-18 | 2022-01-18 | 2022-10-01 | 2023-09-30 |  |  | -15.13 | [18 empty] | 1/18/2023 - Reclass submitted to move actuals off cancelled project and onto LN00000M2204. 6/2/22 - RLO This project has been placed on hold | 2023-01-18 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Pennsauken | BPNQP - BPN PENNSAUKEN TERMINAL |  | -15 | 0 |  |  | 15 |  | Geib, Rob |  | N/A |  | 1 | 24902 |  | Guest, ProSight | Independent | Aqua | 2017-08-09 | Int - Planned Corr & FI
PENNSAUKEN REMOVE CAST IRON VALVES PHASE I | Item | Open | MCAP | BPNQP00M2302 | Maintenance Framework | 2109806 | Bodner, Jordan | East | 3. Active | Defined | Facility Integrity | 550 | 40000 |  | 40549.79 | 40000 | 550 | Yellow | 40000 |  | 40000 | 550 |  |  | 52943 |  |  | 52943 | Full | 52943 | 550 | 40000 | 40550 | No | Green | 2023-04-01 | 2023-04-04 | 2023-04-04 | 2023-05-03 | 2023-05-31 | [5 empty] | 549.79 |  |  | 550 | Red |  |  | 40000 | [10 empty] | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Pennsauken | BPNQP - BPN PENNSAUKEN TERMINAL |  |  | 40550 |  |  |  |  | Aiken, Elaine | Oey, Alexander | N/A |  | 1 | 24897 |  | Guest, ProSight | Independent | Aqua | 2017-08-09 | Int - Planned Corr & FI
Pennsauken Replace Terminal Building A-C Unit | Item | Candidate | MCAP |  | Maintenance Framework |  | Wojton, Brian | East | 1. Proposed |  | East |  | 20000 |  | 20000 | 20000 | 0 | Green | 20000 |  | 20000 | 0 | [9 empty] | 20000 | 20000 | No | Green | 2023-07-01 |  |  |  | 2023-06-30 | [13 empty] | 0 | 20000 | [10 empty] | East | Pipelines and Terminals | Operating Infrastructure |  | Pennsauken | BPNQP - BPN PENNSAUKEN TERMINAL |  |  | 0 | 20000 |  |  |  | Orischak, Bob |  |  |  | 1 | 44275 |  | Guest, ProSight | Independent | Aqua | 2022-07-27 | Other Programs
Pennsauken River Road Terminal (BPNQP) Tank 2016 - OOS API 653 Insp | Item | Open | MCAP | BPNQP00M2301 | Maintenance Framework | 2109739 | Marrocco, Alex | East | 3. Active | Defined | Tanks |  | 168000 |  | 168000 | 168000 | 0 | Green | 168014 |  | 168014 | -14 |  |  | 86785 |  |  | 86785 | Phase | 86785 |  | 168000 | 168000 | No | Green | 2023-05-01 | 2023-04-03 | 2023-04-03 | 2023-08-31 | 2023-06-30 | [12 empty] | 50000 | 100000 | 18000 | [8 empty] | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Pennsauken | BPNQP - BPN PENNSAUKEN TERMINAL |  |  | 150000 | 18000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44859 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Pennsauken River Road Terminal (BPNQP) Tank 2018 – OOS Corr Insp & Refurb | Item | Open | MCAP | BPNQP00M2203 | Maintenance Framework | 1937269 | Marrocco, Alex | East | 7. Closed | Defined | Tanks | 13467 |  |  | 13467.05 | 13467 | 0 | Green |  |  |  | 13467 |  |  | 287000 |  |  | 287000 | Phase | 287000 | 260508 |  | 260508 | No | Green | 2022-09-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-01-31 |  |  | 11834.66 | 1632.39 | [17 empty] | 1/5/2023 costs came in lower than expected. 9/2/22-CES-Per Alex, tank is sitting on low legs. Tank will be cleaned on low, jacked, and inspected. Plan to clean in September, jack and inspect in October. Plan is to likely leave tank idle so updating forecasting accordingly. | 2023-01-05 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Pennsauken | BPNQP - BPN PENNSAUKEN TERMINAL |  | 13467 | 0 |  |  | 247041 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41307 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
PERTH AMBOY - 767TK Foam Piping Modification | Item | Open | MCAP | BPTPC00M2220 | Maintenance Framework | 2051167 | Marrocco, Alex | East | 6. Operational | Defined | Fire Protection | -21100 | 16000 |  | -5100 | -5100 | 0 | Green |  |  |  | -5100 |  |  | 77000 |  |  | 77000 | Phase | 77000 | 21860 | 16000 | 37860 | No | Green | 2022-11-01 | 2022-12-02 | 2022-12-02 | 2022-12-15 | 2022-12-08 |  |  | 0 | -21100 |  |  | 0 | 0 | 0 | Green |  |  | 16000 | [8 empty] | 3/3/2023 Work will resume upon approval of Phase 2 AFE. 1/5/2023 unable to complete work in December. 12/10/2022 - Work is moving forward faster than expected | 2023-03-03 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | -21100 | 16000 |  |  | 42960 |  | Jakubowski, Gregory | Stine, Carlton |  |  | 1 | 38101 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
PERTH AMBOY - 768TK Foam Piping Modification | Item | Open | MCAP | BPTPC00M2213 | Maintenance Framework | 2011421 | Marrocco, Alex | East | 3. Active | Defined | Fire Protection | 2894 | 100000 |  | 102894.35 | 32219 | 70676 | Red |  |  |  | 102894 |  |  | 250000 |  |  | 250000 | Full | 250000 | 142227 | 100000 | 242227 | No | Green | 2022-08-01 | 2022-08-05 | 2022-08-05 | 2022-11-30 | 2023-06-30 |  |  | 896.78 | 654.65 | 667.29 | 675.63 | 0 | 0 | 676 | Red |  |  | 50000 | 50000 | [7 empty] | 3/3/2023 Work has not resumed due to Operations constraints. 1/5/2023 forecast error due to accrual mixup 12/5/2022 Working with vendor to provide more timely billing. 11/3/2022 Fabricated piping been delayed to vendor availability. 9/2/22 - AFE approved. Work has started. Piping modifications expected to begin week of 9/26, with completion 10/31.8/3/22 - AFE has been submitted and awaiting approval. Once approved, expect to begin work immediately. 7/12/22 GJ - will be executed by AM this year; 5/5/2022 EC- No change. 4/7/2022 EC- No change. May- June. /2/7/22 EC: Forecasts updated. Delayed to May-June. | 2023-03-03 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 2219 | 100676 |  |  | 139333 |  | Jakubowski, Gregory | Bassani, Joel D. |  |  | 1 | 38096 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
PERTH AMBOY - 769TK Foam Piping Relocation | Item | Candidate | MCAP |  | Maintenance Framework |  | Marrocco, Alex | East | 1. Proposed | Defined | Fire Protection |  | 250000 |  | 250000 | 250000 | 0 | Green | 250000 |  | 250000 | 0 | [9 empty] | 250000 | 250000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [12 empty] | 0 | 0 | 200000 | 50000 | [5 empty] | 7/12/22 GJ - will need additional budget and defer to 2023 - reallocate funding to other emergent fire projects - Fairfax, Rochester North, New Haven Forbes: 5/5/2022 EC- No change. 4/7/2022 EC- No change. May-June. 2/7/22 EC: Forecasts updated. Delayed to May-June. | 2022-07-12 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 0 | 250000 |  |  |  | Jakubowski, Gregory |  |  |  | 1 | 38090 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
Perth Amboy - Asphalt Cargo Hose Heating | Item | Candidate | MCAP |  | Project Framework |  | Wojton, Brian | East | 2. Pending AFE |  | Marine |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 | [9 empty] | 50000 | 50000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 50000 | [6 empty] | 9/22/2022 - project being considered for 2023. | 2022-09-26 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 0 | 50000 |  |  |  | Spari, Markella |  |  |  | 1 | 44249 |  | Guest, ProSight | Independent | Aqua | 2022-07-26 | Marine
Perth Amboy - ETP Mechanical Completion, Commissioning and Start-Up | Item | Open | MCAP | BPTPC00M2102 | Exempt | 1804034 | Wojton, Brian | East | 3. Active | Defined | Storm Water Management | 12359 | 35000 |  | 47359.24 | 45960 | 1399 | Yellow | 35000 |  | 35000 | 12359 |  |  | 301000 |  |  | 301000 | Full | 301000 | 294552 | 35000 | 329552 | No | Green | 2021-01-01 | 2021-01-25 | 2021-01-25 | 2021-06-30 | 2023-06-30 |  |  | 7868.84 | 1710.04 | 1381.12 | 1399.24 | 0 | 0 | 1399 | Red |  |  | 0 |  | 35000 | [6 empty] | 4/21/23 Brian to setup a meeting with stakeholders and have a path forward developed by them. Otherwise this project will be closed due to lack of direction from Corp. 9/18/2022 - start-up of new system waiting on CAMU waste stream determination. Start up may slip into 2023. Move remaining 4Q22 forecast to 2Q23. 8/8/2022 - testing and separator start up scheduled for late Aug. 12/15/2021 - Start up and commissioning push to spring of 2022 due to prolonged cleaning of storm lines leading to the new separators. 3/31/2021 - By-pass piping is complete. System checkout started. New pumps in service. 1/24/2021 - AFE approved. Piping by-pass work awarded to Sylvan on GMT MSA. 1/4/2021 - AFE routed for approval. | 2023-04-21 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 10960 | 1399 | 35000 |  | 35588 |  | Bonenberger, Mark | DeSocio, David |  |  | 1 | 37253 |  | Guest, ProSight | Independent | Aqua | 2020-07-23 | Other Programs
Perth Amboy - Overfill Containment at Truck Track Additive Tanks | Item | Open | MCAP | BPTPC00M2209 | Maintenance Framework | 1990488 | Wojton, Brian | East | 7. Closed | Defined | Secondary Containment | 101 |  |  | 101.38 | 101 | 0 | Green |  |  |  | 101 |  |  | 54000 |  |  | 54000 | Full | 54000 | 56074 |  | 56074 | No | Green | 2022-10-01 | 2022-06-14 | 2022-06-14 | 2022-07-05 | 2022-11-30 |  |  | 101.38 | [18 empty] | 11/3/2022 more work done ahead of schedule. 9/5/2022 - project pushed to Sept./Oct. due to changes in design / scope related to new XOM additive tank install. Will install curbing concurrently with the XOM project. 8/8/2022 - project start pushed to Aug. | 2022-11-03 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 101 | 0 |  |  | 55973 |  | Clark, Dave | Buchalski, Edwin |  |  | 1 | 41656 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Perth Amboy - Rehabilitate Main Dock Trestle / Approach | Item | Open | MCAP | BPTPC00M2307 | Project Framework | 2119869 | Wojton, Brian | East | 3. Active | Emergent | Marine |  | 750000 |  | 750000 | 750000 | 0 | Green |  | 751425 | 751425 | -1425 |  |  | 157275 |  |  | 157275 | Phase | 157275 |  | 750000 | 750000 | No | Green | 2023-05-01 | 2023-05-02 | 2023-05-02 | 2023-12-30 | 2023-12-29 | [6 empty] | 0 | 0 | 0 | Green |  |  | 25000 | 50000 | 25000 | 25000 | 25000 | 200000 | 200000 | 200000 |  | 4/1/2022 - project created to address priority upgrades needed to the main dock accessway trestle as identified by 2022 dock inspection. Will be funded by 2023 Perth main dock platform upgrades which will be pushed to 2024. | 2023-04-05 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 75000 | 75000 | 600000 |  |  | Spari, Markella | Spari, Markella |  |  | 1 | 46865 |  | Wojton, Brian | Independent | Aqua | 2023-03-31
Perth Amboy - Remove Old OOS Pipe Phase III | Item | Candidate | MEXP |  | Maintenance Framework |  | Wojton, Brian | East | 1. Proposed |  | Facility Integrity |  | 1 |  | 1 | 100000 | -99999 | Red | 100000 |  | 100000 | -99999 | [9 empty] | 500001 | 500001 | No | Green | 2023-12-01 |  |  |  | 2023-09-30 | [19 empty] | 1 | [5 empty] | East | Pipelines and Terminals | Station/Terminal |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 0 |  | 1 |  | 100000 | Aiken, Elaine |  |  |  | 1 | 37386 |  | Guest, ProSight | Independent | Aqua | 2020-07-30 | Int - Planned Corr & FI
Perth Amboy - South Dock - Reinforcement of loading platform and introduction of mooring point | Item | Candidate | MCAP |  | Project Framework |  | Wojton, Brian | East | 1. Proposed |  | Marine |  | 0 |  | 0 | 0 | 0 | Green | 750000 |  | 750000 | -750000 | [9 empty] | 750000 | 750000 | No | Green | 2024-05-01 |  |  |  | 2023-09-30 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4/4/2023 - funding for this project moved to 2024. Approved funding for 2023 will be used to fund the Perth accessway trestle upgrades. | 2023-04-04 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 0 | 0 | 0 |  | 750000 | Spari, Markella |  |  |  | 1 | 45108 |  | Spari, Markella | Independent | Aqua | 2022-08-19 | Marine
Perth Amboy - TBA Warehouse Removal | Item | Candidate | MEXP |  | Maintenance Framework |  | Wojton, Brian | East | 1. Proposed |  | East |  | 1 |  | 1 | 200001 | -200000 | Red | 200001 |  | 200001 | -200000 | [9 empty] | 250001 | 250001 | No | Green | 2023-12-01 |  |  |  | 2023-12-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | [6 empty] | 1 |  | Placeholder number RLO | 2022-09-06 |  |  | East | Pipelines and Terminals | Station/Terminal |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 0 |  | 1 |  | 250000 | Orischak, Bob |  |  |  | 1 | 37376 |  | Guest, ProSight | Independent | Aqua | 2020-07-30 | Other Programs
Perth Amboy - Walkway support sleeve repairs | Item | Open | MEXP | BPTPC00E2220 | Project Framework | 2046276 | Wojton, Brian | East | 3. Active | Emergent | Marine | 50239 | 100000 |  | 150239.11 | 156363 | -6124 | Yellow |  |  |  | 150239 |  |  | 160000 |  |  | 160000 | Full | 160000 | 147649 | 100000 | 247649 | Yes | Red | 2022-11-01 | 2022-11-29 | 2022-11-29 | 2023-01-30 | 2023-06-02 |  |  | 9277.5 | 25818.39 | 21267.22 | -6124 |  |  | -6124 | Red |  |  | 0 | 50000 | 50000 | [6 empty] | 5/2/2023 - Additional severe corrosion identified above the original repair location. Funding approved to correct the additional repair area. Supplement to be submitted in May. 3/15/2023 - original pipe repair scope is complete. Fiction clamps installed. During this work, additional corrosion was identified. Current obtaining an estimate to repair. 12/2/2022 reclass pending for $23K from 1348250E2218 for Marine Solutions invoice. 11/23/2022 - Reduced spend in Dec. to 100k based on results of bids. | 2023-05-02 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 56363 | 43876 | 50000 |  | 97410 |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 46117 |  | Spari, Markella | Independent | Aqua | 2022-10-25 | Other Programs
Perth Amboy (BPTPC) Tank 328 Walkway Upgrade | Item | Open | MCAP | BPTPC00M2306 | Maintenance Framework | 2110551 | Bodner, Jordan | East | 3. Active | Defined | East |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 |  |  | 67790 |  |  | 67790 | Full | 67790 |  | 50000 | 50000 | No | Green | 2023-06-01 | 2023-04-12 | 2023-04-12 | 2023-05-29 | 2023-06-30 | [13 empty] | 50000 | [9 empty] | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 50000 |  |  |  |  | Orischak, Bob | Samuel, Michael |  |  | 1 | 43351 |  | Stine, Carlton | Independent | Aqua | 2022-04-06 | Other Programs
Perth Amboy Admin Building Renovation Engineering | Item | Open | MEXP | BPTPC00E2219 | Maintenance Framework | 2037301 | DeSocio, David | East | 7. Closed | Drawdown | East | -969 |  |  | -969 | -969 | 0 | Green |  |  |  | -969 |  |  | 14000 |  |  | 14000 | Full | 14000 | 12231 |  | 12231 | No | Green | 2022-11-01 | 2022-10-18 | 2022-10-18 | 2022-12-14 | 2022-12-14 |  |  | -969 | [20 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | -969 | 0 |  |  | 13200 |  | Orischak, Bob | Orischak, Bob | N/A |  | 1 | 46076 |  | Orischak, Bob | JDE Child | Burnt Orange | 2022-10-18 | Other Programs
Perth Amboy Atmospheric Refurbishment | Item | Open | MCAP | BPTPC00M2203 | Maintenance Framework | 2012051 | Occhi, Edward | East | 7. Closed | Defined | Atmospheric Corrosion | 257 |  |  | 256.54 | 257 | 0 | Green |  |  |  | 257 |  |  | 26000 |  |  | 26000 | Full | 26000 | 27898 |  | 27898 | No | Green | 2022-10-01 | 2022-01-27 | 2022-01-27 | 2022-12-31 | 2022-11-30 |  |  | 256.54 | [20 empty] | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 257 | 0 |  |  | 27641 |  | Geib, Rob | Geib, Robert |  |  | 1 | 41090 |  | Guest, ProSight | JDE Child | Burnt Orange | 2021-08-06 | Int - Planned Corr & FI
Perth Amboy Berth 2 Bollard 2023 | Item | Open | MCAP | BPTPC00M2308 | Project Framework |  | Smith, Rachele | East | 2. Pending AFE | Emergent | Marine |  | 185518 |  | 185518 |  | 185518 | Red |  |  |  | 185518 |  |  | 203067 |  |  |  | Phase | 203067 |  | 185518 | 185518 | No | Green | 2023-05-01 |  |  | 2023-12-29 | 2023-12-29 | [12 empty] | 67125 | 38754 | 38574 | 38574 | 2491 | [6 empty] | Boyd, Kim |  | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 105879 | 79639 |  |  |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 47024 |  | Boyd, Kimberly | Independent | Aqua | 2023-05-03
Perth Amboy Catwalk Improvements Phase II | Item | Open | MCAP | BPTPC00M2204 | Maintenance Framework | 1954839 | Wojton, Brian | East | 7. Closed | Defined | East | 443 |  |  | 443.23 | 443 | 0 | Green |  |  |  | 443 |  |  | 110000 |  |  | 110000 | Phase | 110000 | 124770 |  | 124770 | No | Green | 2022-06-01 | 2022-03-01 | 2022-03-01 | 2022-08-30 | 2022-11-30 |  |  | 443.23 | [18 empty] | 8/8/2022 - installation IP. Completing in stages. 7/28/2022 - catwalk fabrication and galv. complete. | 2022-08-08 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 443 | 0 |  |  | 124326 |  | Orischak, Bob | Buchalski, Edwin | N/A |  | 1 | 25659 |  | Guest, ProSight | Independent | Aqua | 2017-09-08 | Other Programs
Perth Amboy CP Upgrade for Piping | Item | Open | MCAP | BPTPC00M2202 | Maintenance Framework | 1939590 | Occhi, Edward | East | 7. Closed | Defined | Cathodic Protection | 8507 |  |  | 8507.49 | 8507 | 0 | Green |  |  |  | 8507 |  |  | 35000 |  |  | 35000 | Full | 35000 | 43694 |  | 43694 | No | Green | 2022-10-01 | 2022-01-27 | 2022-01-27 | 2021-12-31 | 2022-11-30 |  |  | 6618.69 | 1888.8 | [17 empty] | 1/27/2023 - Reclass submitted for $2,700 from JK00000M2201. 1/6/2023 - (-8,000) forecast entered to offset overaccrual in December of $14K. Only needed to accrue $6000. 1/6/2023 Reclass submitted for $9,313.96 from BETWE00E2202. | 2023-01-27 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 8507 | 0 |  |  | 35186 |  | Geib, Rob | Geib, Robert |  |  | 1 | 40735 |  | Guest, ProSight | Independent | Aqua | 2021-07-26 | Other Programs
Perth Amboy Emergency Generator Repair 2022 | Item | Candidate | MEXP |  | Maintenance Framework |  | Wojton, Brian | East | 1. Proposed | Drawdown | East |  | 59000 |  | 59000 | 59000 | 0 | Green |  |  |  | 59000 | [9 empty] | 118000 | 118000 | No | Green | 2023-09-01 |  |  | 2023-01-06 | 2023-01-06 | [13 empty] | 0 |  |  | 59000 | [8 empty] | East | Pipelines and Terminals | Station/Terminal |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 0 | 59000 |  |  | 59000 | Orischak, Bob | Samuel, Michael | N/A |  | 1 | 46414 |  | Orischak, Bob | Independent | Aqua | 2023-01-04 | Other Programs
Perth Amboy ETP Sediment Management 2020 | Item | Open | MEXP | BPTPC00E2001 | Exempt | 1671859 | Wojton, Brian | East | 3. Active | Defined | East | 33629 | 200000 |  | 233629.17 | 219275 | 14355 | Yellow |  |  |  | 233629 |  |  | 3424000 |  |  | 3424000 | Phase | 3424000 | 3808048 | 200000 | 4008048 | No | Green | 2020-05-01 | 2019-08-12 | 2019-08-12 | 2020-12-31 | 2023-12-31 |  |  | 8738.29 | -242.72 | 10779.04 | 14354.56 | 0 | 0 | 14355 | Red |  | Forecasting | 0 | 0 | 200000 | [6 empty] | 5/2/2023 unexpected waste disposal invoice hit. 4/21/23 See notes from other ETP above. Meeting to be held and direction given from Corporate 12/2/2022 More waste disposed of than anticipated. 11/3/2022 much more waste disposal hit in October than expected. 10/5/2022 more waste disposal than anticipated. 9/22/2022 - cleaning of EQ tank may not happen in 2022 due to delays on commissioning the new ETP separators. Moved 200k into 2Q23. 9/5/2022 - more waste was generated and transported than expected in Aug. (ahead of sch.). 8/8/2022 - Completed the Clarifier tank cleaning ahead of schedule. 7/6/2022 more than expected waste and disposal costs. 5/4/2022 Less waste disposed than expected. 4/5/2022 more waste disposed of than expected. 3/3/2022 Waste disposed ahead of schedule. 12/24/2021 - Storm line cleaning suspended until spring. 8/15/2021 - storm sewer cleaning IP. 7/15/2021 - Bio-disc cleaning IP. Waste disposal to follow. 1/15/2020 - Waste disposal from Tank 327 IP. 10/1/2020 - Work for Tank 765 and 327 awarded to Auchter. Handex will process. 5//30/20 - Project approved to start 3/25/2020 - Project is ON HOLD until confirmation that current forecast is approved by Man. 2/10/2020 - Scope of this project will be prepared in Feb. and spend will be coordinated with ETP MCAP | 2023-05-02 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Perth Amboy | BPTPC - BPT PERTH AMBOY | BPTPC00E1900 | 19275 | 14355 | 200000 |  | 1364441 |  | Orischak, Bob | McGuire, David |  |  | 1 | 33330 |  | Kabaria, Erika | Child (Major Project) | Olive | 2019-05-17 | Other Programs
Perth Amboy Hot Oil Heater Furnace Maintenance 2023 | Item | Candidate | MEXP |  | Maintenance Framework |  | Wojton, Brian | East | 1. Proposed |  | Boilers |  | 95000 |  | 95000 | 95000 | 0 | Green |  |  |  | 95000 | [9 empty] | 95000 | 95000 | No | Green | 2023-07-01 |  |  |  | 2023-06-30 | [13 empty] | 0 | 95000 | [10 empty] | East | Pipelines and Terminals | Station/Terminal |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 0 | 95000 |  |  |  | Stine, Carlton |  |  |  | 1 | 44392 |  | Guest, ProSight | Independent | Aqua | 2022-08-03 | Other Programs
PERTH AMBOY INSTALL NEW PUMP AND CATCH BASIN N TANK 12 CONTAINMENT AREA | Item | Open | MCAP | BPTPC00M2210 | Maintenance Framework | 1990490 | Wojton, Brian | East | 7. Closed | Defined | Secondary Containment | 17703 |  |  | 17703.15 | 17703 | 0 | Green |  |  |  | 17703 |  |  | 126000 |  | 76000 | 202000 | Supplemental | 202000 | 221522 |  | 221522 | No | Green | 2022-08-01 | 2022-06-14 | 2022-06-14 | 2022-09-30 | 2022-12-30 |  |  | 17055.06 | 648.09 | [17 empty] | 11/23/2022 - added additional funding (70K) needed and approved to complete this work in 2022 based on bids. 9/22/2022 - engineering review in progress. Work scheduled to start in Oct. 8/8/2022 - Allied working on engineering / options. | 2022-11-23 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 17703 | 0 |  |  | 203819 |  | Clark, Dave |  | N/A |  | 1 | 24441 |  | DeSocio, David | Independent | Aqua | 2017-07-25 | Other Programs
Perth Amboy Insulated Pipe Phase 2 Inspection | Item | Open | MEXP |  | Maintenance Framework |  | Wojton, Brian | East | 1. Proposed |  | Facility Integrity |  | 110000 |  | 110000 | 110000 | 0 | Green | 110000 |  | 110000 | 0 | [9 empty] | 110000 | 110000 | No | Green | 2023-09-01 |  |  |  | 2023-07-31 | [16 empty] | 50000 | 60000 | [7 empty] | East | Pipelines and Terminals | Station/Terminal |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 0 | 50000 | 60000 |  |  | Aiken, Elaine |  |  |  | 1 | 45066 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Perth Amboy Office Build Out | Item | Open | MCAP | BPRPR00M2301 | Maintenance Framework | 2075918 | DeSocio, David | East | 3. Active | Defined | East | 26480 | 395000 |  | 421479.53 | 420000 | 1480 | Yellow | 400000 |  | 400000 | 21480 |  |  | 401925 |  |  | 401925 | Full | 401925 | 26480 | 395000 | 421480 | No | Green | 2023-04-01 | 2023-01-19 | 2023-01-19 | 2023-09-01 | 2023-09-30 | [5 empty] | 26479.53 | 25000 | 25000 | 1480 | Yellow |  |  | 0 | 0 | 0 | 20000 | 100000 | 175000 | 100000 |  |  |  |  | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 26480 | 120000 | 275000 |  |  | Orischak, Bob | Votta, Joseph T. |  |  | 1 | 45856 |  | Orischak, Bob | Independent | Aqua | 2022-09-16 | Other Programs
Perth Amboy Priority 3 API 570 Repairs | Item | Open | MEXP |  | Maintenance Framework |  | Wojton, Brian | East | 1. Proposed |  | Facility Integrity |  | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 | [9 empty] | 30000 | 30000 | No | Green | 2023-08-01 |  |  |  | 2023-08-31 | [15 empty] | 30000 | [9 empty] | East | Pipelines and Terminals | Station/Terminal |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 0 | 30000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45055 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Perth Amboy Tank 777 Mechanical Repairs | Item | Open | MEXP | BPTPC00E2217 | Maintenance Framework | 2023243 | Marrocco, Alex | East | 7. Closed | Drawdown | Tanks | -10000 |  |  | -10000 | -10000 | 0 | Green |  |  |  | -10000 |  |  | 35000 |  |  | 35000 | Full | 35000 | 15326 |  | 15326 | No | Green | 2022-10-01 | 2022-09-21 | 2022-09-21 | 2022-09-16 | 2022-09-30 |  |  | -10000 | [18 empty] | 2/3/2023 project closed 1/5/2023 accrual error; project complete. 11/7/2022 accrual adjustment for October. 11/7/2022 reclass posted. 11/3/2022 waiting on reclass 10/10/2022 $22,529 RECLASS SUBMITTED FROM BPTPC00E2216. | 2023-02-03 | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | -10000 | 0 |  |  | 25326 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 45813 |  | Meitzler, Antoinette | Independent | Aqua | 2022-09-12 | Int - Tanks
PERTH AMBOY TANK 777 REPAIRS | Item | Open | MEXP | BPTPC00E2303 | Maintenance Framework | 2111165 | Marrocco, Alex | East | 6. Operational | Drawdown | Tanks | 30000 | 0 |  | 30000 |  | 30000 | Red |  |  |  | 30000 |  |  | 35000 |  |  | 35000 | Full | 35000 | 30000 | 0 | 30000 | No | Green | 2023-04-01 | 2023-04-17 | 2023-04-17 | 2023-05-31 | 2023-05-31 | [5 empty] | 30000 |  |  | 30000 | Red |  |  | 0 | [10 empty] | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 30000 |  |  |  |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 46953 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-04-17
Perth Amboy Tank 778 IFR Repairs | Item | Open | MEXP | BPTPC00E2222 | Maintenance Framework | 2046274 | Marrocco, Alex | East | 7. Closed | Emergent | Tanks | 3495 |  |  | 3495.42 | 3495 | 0 | Green |  |  |  | 3495 |  |  | 156000 |  |  | 156000 | Full | 156000 | 116948 |  | 116948 | No | Green | 2022-12-01 | 2022-11-29 | 2022-11-29 | 2022-12-31 | 2022-12-31 |  |  | 3495.42 | [18 empty] | 1/5/2023 project complete. costs came in less than anticipated. 12/9/22-CES-Identified pull forward project. | 2023-01-05 | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 3495 | 0 |  |  | 113452 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46262 |  | Meitzler, Antoinette | Independent | Aqua | 2022-11-23 | Int - Tanks
Perth Amboy Tank Basin Regrading | Item | Open | MEXP | BPTPC00E1813 | Exempt | 1494650 | Wojton, Brian | East | 3. Active | Defined | East |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 |  |  | 50000 |  |  | 50000 | Full | 50000 |  | 100000 | 100000 | Yes | Red | 2023-08-01 | 2018-08-28 | 2018-08-28 | 2018-09-30 | 2023-08-31 | [15 empty] | 50000 | [5 empty] | 5/2/2023 - New phased AFE to be submitted. Added 50k in budget for 2024. | 2023-05-02 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 0 | 50000 |  |  | 50000 | Orischak, Bob | Mattsson, Michael J | N/A |  | 1 | 24452 |  | DeSocio, David | Independent | Aqua | 2017-07-25 | Other Programs
Perth Amboy Terminal - Permeability Testing | Item | Open | MEXP | BPTPC00E2301 | Maintenance Framework | 2076589 | Wojton, Brian | East | 3. Active | Defined | Secondary Containment |  | 35000 |  | 35000 | 45000 | -10000 | Red | 45000 |  | 45000 | -10000 |  |  | 44550 |  |  | 44550 | Full | 44550 |  | 35000 | 35000 | No | Green | 2023-05-01 | 2023-01-24 | 2023-01-24 | 2023-06-15 | 2023-07-15 | [6 empty] | 10000 | 10000 | -10000 | Red |  | Weather | 10000 | 15000 | 10000 | [6 empty] | 05/2/2023 - permeability testing delayed due to wet weather. 4/21/23 Contractor onsite. Envirospec is performing this work. | 2023-05-02 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 25000 | 10000 |  |  |  | Spari, Markella | Orischak, Bob |  |  | 1 | 44386 |  | Guest, ProSight | Independent | Aqua | 2022-08-03 | Other Programs
Perth Amboy Terminal (BPTPC) Tank 12 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | BPTPC00M2301 | Maintenance Framework | 2074856 | Marrocco, Alex | East | 6. Operational | Defined | Tanks | 311389 | 10000 |  | 321388.53 | 306983 | 14405 | Yellow | 501125 |  | 501125 | -179736 |  |  | 207555 | 115540 |  | 323095 | Phase | 323095 | 311389 | 10000 | 321389 | No | Green | 2023-02-01 | 2023-01-10 | 2023-01-10 | 2023-05-31 | 2023-05-01 |  |  |  | 140465.66 | 66517.83 | 104405.04 | 90000 | 90000 | 14405 | Red |  |  | 10000 | [8 empty] | 4/5/2023 Contractor waiting on repairs to IFR and seals; contractor is behind schedule. 3/9/2023 More work than anticipated. Tank to be finished end of May. 2/3/2023 late start on project due to customer requirements. | 2023-04-05 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 206983 | 114405 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44860 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Perth Amboy Terminal (BPTPC) Tank 23 - OOS Seal Insp | Item | Open | MEXP | BPTPC00E2302 | Maintenance Framework | 2095932 | Marrocco, Alex | East | 3. Active | Defined | Tanks |  | 20000 |  | 20000 | 160000 | -140000 | Red | 160000 |  | 160000 | -140000 |  |  | 27288 |  |  | 27288 | Phase | 27288 |  | 20000 | 20000 | No | Green | 2023-05-01 | 2023-03-23 | 2023-03-23 | 2023-04-30 | 2023-07-31 | [12 empty] | 20000 | [8 empty] | 4.14.23.DLC: Reduced overall forecast to match in-service inspection needs.. | 2023-04-14 | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 20000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44862 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Perth Amboy Terminal (BPTPC) Tank 27 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP |  | Maintenance Framework |  | Marrocco, Alex | East | 1. Proposed |  | Tanks |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 | [9 empty] | 10000 | 10000 | No | Green | 2023-09-01 |  |  |  | 2023-12-31 | [16 empty] | 10000 | [8 empty] | East | Pipelines and Terminals | Tank Integrity |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 0 | 10000 |  |  |  | Stine, Carlton |  |  |  | 1 | 44863 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Perth Amboy Terminal (BPTPC) Tank 758 - OOS API 653 Insp - PHMSA 10 Year | Item | Open | MCAP | BPTPC00M2305 | Maintenance Framework | 2096524 | Marrocco, Alex | East | 3. Active | Defined | Tanks |  | 368111 |  | 368111 | 368111 | 0 | Green | 368111 |  | 368111 | 0 |  |  | 198888 |  |  | 198888 | Phase | 198888 |  | 368111 | 368111 | No | Green | 2023-06-01 | 2023-03-30 | 2023-03-30 | 2023-10-01 | 2023-08-31 | [13 empty] | 68111 | 150000 | 150000 | [7 empty] | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 68111 | 300000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44864 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Perth Amboy Terminal (BPTPC) Tank 780 - OOS API 653 Insp | Item | Open | MCAP | BPTPC00M2303 | Maintenance Framework | 2095936 | Marrocco, Alex | East | 3. Active | Defined | Tanks | 976 | 380000 |  | 380976.31 | 265000 | 115976 | Red | 380645 |  | 380645 | 331 |  |  | 198970 |  |  | 198970 | Phase | 198970 | 976 | 380000 | 380976 | No | Green | 2023-04-01 | 2023-03-23 | 2023-03-23 | 2023-07-01 | 2023-07-31 | [5 empty] | 976.31 | 40000 | 40000 | -39024 | Red |  | Contractor/Vendor Issue | 100000 | 150000 | 130000 | [6 empty] | 5/3/2023 Contractor has been back logged; work is scheduled to begin June 2023. | 2023-05-03 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 250976 | 130000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44867 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Perth Amboy Terminal (BPTPC) Tank 723 – OOS Corr Insp & Refurb | Item | Open | MEXP | BPTPC00E2202 | Maintenance Framework | 1937902 | Marrocco, Alex | East | 7. Closed | Defined | Tanks | 448 |  |  | 447.83 | 448 | 0 | Green |  |  |  | 448 |  |  | 60000 |  |  | 60000 | Phase | 60000 | 63258 |  | 63258 | No | Green | 2022-07-01 | 2022-01-05 | 2022-01-05 | 2022-12-31 | 2022-12-31 |  |  | 447.83 | [18 empty] | 9/2/22 - Mechanical work complete. Awaiting liner repairs. 8/3/22 - Tank cleaned, inspection in progress. | 2022-09-02 | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 448 | 0 |  |  | 62810 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41308 |  | Administrator, System | JDE Child | Burnt Orange | 2021-08-09 | Int - Tanks
Perth Amboy Transformer Maintenance | Item | Candidate | MEXP |  | Maintenance Framework |  | Wojton, Brian | East | 1. Proposed |  | Electrical |  | 25000 |  | 25000 | 25000 | 0 | Green | 25000 |  | 25000 | 0 | [9 empty] | 25000 | 25000 | No | Green | 2023-10-01 |  |  |  | 2023-10-31 | [17 empty] | 25000 | [7 empty] | East | Pipelines and Terminals | Station/Terminal |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 0 |  | 25000 |  |  | Ashley, Robert |  | N/A |  | 1 | 30736 |  | Guest, ProSight | Independent | Aqua | 2018-08-20 | Other Programs
Port Reading - Cast Iron Pump Removal Phase 3 | Item | Open | MCAP | BPRPR00M2207 | Maintenance Framework | 1940004 | Wojton, Brian | East | 7. Closed | Defined | Rotating Equipment | 10305 |  | 138000 | 10304.55 | 10305 | 0 | Green |  |  |  | 10305 |  |  | 238000 |  |  | 238000 | Full | 238000 | 117566 | 138000 | 255566 | No | Green | 2022-02-01 | 2022-02-01 | 2022-02-01 | 2022-12-31 | 2022-09-30 |  |  | 3000 | 6990 | 314.55 | [15 empty] | 138000 | 6/1/2022 - Reclass submitted for $12,500 to MEXP dead leg project BPRPR00E2214. 4/5/2022 Reclass effected and Engineering ahead of schedule. 3/3/2022 - Equipment received from prior month and reclassed to this AFE. | 2022-06-07 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 10305 | 0 |  |  | 107261 |  | Posipanko, Dan | Orischak, Bob |  |  | 1 | 41601 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
Port Reading - Dock cathodic protection upgrades | Item | Candidate | MCAP |  | Project Framework |  | Occhi, Edward | East | 1. Proposed |  | Marine |  | 80000 |  | 80000 | 80000 | 0 | Green | 80000 |  | 80000 | 0 | [9 empty] | 80000 | 80000 | No | Green | 2023-05-01 |  |  |  | 2023-06-30 | 8 | Yellow | [10 empty] | 40000 | 40000 | [11 empty] | East | Pipelines and Terminals | Operating Infrastructure | Operating Infrastructure | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 80000 |  |  |  |  | Spari, Markella |  |  |  | 1 | 45836 |  | Clark, David | Independent | Aqua | 2022-09-13 | Marine
Port Reading - MVRU direct drive phase 2 | Item | Open | MCAP | BPRPR00M2215 | Maintenance Framework | 1981493 | Wojton, Brian | East | 7. Closed | Defined | Vapor Management | -1219 |  |  | -1218.75 | -1219 | 0 | Green |  |  |  | -1219 |  |  | 90000 |  |  | 90000 | Full | 90000 | 98390 |  | 98390 | No | Green | 2022-05-01 | 2022-05-24 | 2022-05-24 | 2022-12-31 | 2022-11-30 |  |  | -1218.75 | [18 empty] | 1/20/2023 - Reclass submitted for $1,218.75 to BPRPR00E2209. 9/22/2022 - waiting for MVRU downtime to finish work. 9/6/2022 - work completed ahead of schedule. 8/8/2022 - MVRU supply pumps upgraded. Piping mods. IP. 4/19/22 - Forecasted pushed out to Q4. | 2023-01-24 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | -1219 | 0 |  |  | 99608 |  | Karl, Marissa | Buchalski, Edwin |  |  | 1 | 41600 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
Port Reading 2022 XOM Tank RTS | Item | Open | MEXP | BPRPR00E2209 | Maintenance Framework | 1971712 | Wojton, Brian | East | 7. Closed | Drawdown | Tanks | -4420 |  | 0 | -4420.25 | -4420 | 0 | Green |  |  |  | -4420 |  |  | 991000 |  |  | 991000 | Full | 991000 | 1049452 | 0 | 1049452 | No | Green | 2022-04-01 | 2022-04-18 | 2022-04-18 |  | 2022-10-01 |  |  | -4466.25 | 46 | [16 empty] | 0 | 01/05/2023 Additional costs during project closeout. 11/14/2022 8 Varec gauges put into inventory for BPRPR. ($20,296) 11/3/2022 - side gauge material arrived ahead of schedule. 9/22/2022 - work is complete. Punch List IP. 9/8/2022 work completed ahead of schedule 8/8/2022 - work completed ahead of schedule. 7/6/2022 Completed more IFR repairs and valve work than expected. Needed to move up RTS dates for XOM tanks. 6/5/22 - 99k variance due to more IFR and tank work completed in May than anticipated. 5/11/22 - Project ahead of schedule DC | 2023-01-05 | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | -4420 | 0 |  |  | 1053872 |  | Stine, Carlton | Buchalski, Edwin |  |  | 1 | 43346 |  | Clark, David | Independent | Aqua | 2022-04-05 | Int - Tanks
Port Reading 2022 XOM Valve Replacements | Item | Open | MCAP | BPRPR00M2212 | Maintenance Framework | 1971695 | Wojton, Brian | East | 7. Closed | Defined | Valves | 5434 |  |  | 5434.27 | 5434 | 0 | Green |  |  |  | 5434 |  |  | 750000 |  |  | 750000 | Full | 750000 | 822369 |  | 822369 | No | Green | 2022-04-01 | 2022-04-18 | 2022-04-18 | 2022-07-30 | 2022-10-01 |  |  | 5200.26 | 234.01 | [17 empty] | 9/22/2022 - punch list work IP. 8/8/2022 - work completed ahead of schedule. 7/6/22 - Valve extensions arrived ahead of schedule. 6/5/22 - exceeded forecast in May by 140k because valves were delivered ahead of schedule. 4.21.22.DLC: Re-forecasted all to May.. Variance due to initial incorrect forecast | 2022-09-26 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 5434 | 0 |  |  | 816934 |  | Oey, Alex | Buchalski, Edwin |  |  | 1 | 43347 |  | Clark, David | Independent | Aqua | 2022-04-05 | Other Programs
Port Reading 2022 XOM Vessel Gauging Upgrades | Item | Open | MCAP | BPRPR00M2216 | Maintenance Framework | 1981508 | Wojton, Brian | East | 6. Operational | Drawdown | Instrumentation & Controls | 1953 |  |  | 1953.46 | 1953 | 0 | Green |  |  |  | 1953 |  |  | 52000 |  |  | 52000 | Phase | 52000 | 47079 |  | 47079 | No | Green | 2022-05-01 | 2022-05-24 | 2022-05-24 | 2022-12-31 | 2022-10-31 |  |  | 976.73 |  | 976.73 | [16 empty] | 9/22/2023 - work complete. Validation flow test remains. 8/8/2022 - PD gauge upgrades IP. | 2022-09-26 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 1953 | 0 |  |  | 45126 |  | Forsey, Frank |  |  |  | 1 | 43349 |  | Clark, David | Independent | Aqua | 2022-04-05 | Other Programs
Port Reading API 570 Refurbishments | Item | Candidate | MCAP |  | Maintenance Framework |  | Wojton, Brian | East | 1. Proposed |  | Facility Integrity |  | 336000 |  | 336000 | 336000 | 0 | Green | 336000 |  | 336000 | 0 | [9 empty] | 336000 | 336000 | No | Green | 2023-06-01 |  |  |  | 2023-07-31 | [13 empty] | 56000 | 280000 | [10 empty] | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 56000 | 280000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45319 |  | Aiken, Elaine | Independent | Aqua | 2022-08-25 | Int - Planned Corr & FI
Port Reading Atmospheric Refurbishment | Item | Open | MCAP | BPRPR00M2303 | Maintenance Framework | 2095136 | Occhi, Edward | East | 3. Active | Defined | Atmospheric Corrosion | 3299 | 85000 |  | 88299.19 | 93157 | -4858 | Yellow | 90000 |  | 90000 | -1701 |  |  | 90288 |  |  | 90288 | Full | 90288 | 3299 | 85000 | 88299 | No | Green | 2023-03-01 | 2023-03-15 | 2023-03-15 | 2023-10-31 | 2023-07-31 |  |  |  |  | 3157.12 | 142.07 | 5000 | 5000 | -4858 | Red |  |  | 0 | 30000 | 20000 | 20000 | 15000 | [6 empty] | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 3157 | 30142 | 55000 |  |  |  | Geib, Rob | Samuel, Michael |  |  | 1 | 41086 |  | Guest, ProSight | Independent | Aqua | 2021-08-06 | Int - Planned Corr & FI
Port Reading Butane Line CP Installation | Item | Open | MCAP | BPRPR00M2306 | Maintenance Framework | 2111953 | Occhi, Edward | East | 3. Active | Defined | Cathodic Protection |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 |  |  | 100448 |  |  | 100448 | Full | 100448 |  | 100000 | 100000 | No | Green | 2023-06-01 | 2023-04-20 | 2023-04-20 | 2023-12-20 | 2023-07-31 | [13 empty] | 25000 | 25000 | 25000 | 15000 | 10000 | [5 empty] | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 25000 | 65000 | 10000 |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 42187 |  | Clark, David | Independent | Aqua | 2021-09-17 | Int - Planned Corr & FI
Port Reading Butane Offload Pump System Improvements | Item | Open | MCAP | BPRPR00M2208 | Maintenance Framework | 1945821 | Wojton, Brian | East | 3. Active | Defined | Instrumentation & Controls | 22688 | 75000 |  | 97687.85 | 69596 | 28092 | Red | 60000 |  | 60000 | 37688 |  |  | 191000 |  |  | 191000 | Full | 191000 | 148918 | 75000 | 223918 | Yes | Red | 2022-07-01 | 2022-02-03 | 2022-02-03 | 2022-12-31 | 2023-06-30 |  |  | 1715.09 | 620.57 | 7260.4 | 13091.79 |  |  | 13092 | Red |  |  | 15000 | 0 | 60000 | [6 empty] | 11/3/2022 more work completed ahead of schedule. 10/5/2022 more work completed than anticipated. 9/8/2022 - troubleshooting and testing waiting for rail downtime. 8/8/2022 - engineering IP. Moved 60k to 2023. | 2022-11-03 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 9596 | 28092 | 60000 |  | 126230 |  | Forsey, Frank | Leehan, Brendan |  |  | 1 | 42186 |  | Clark, David | Independent | Aqua | 2021-09-17 | Other Programs
Port Reading Butane Reliefs Phase 1 | Item | Open | MCAP | BPRPR00M2206 | Maintenance Framework | 1945613 | Wojton, Brian | East | 6. Operational | Defined | Facility Integrity | 20742 | 0 |  | 20741.89 | 20234 | 508 | Yellow |  |  |  | 20742 |  |  | 302000 |  |  | 302000 | Phase | 302000 | 503696 | 0 | 503696 | No | Green | 2022-03-01 | 2022-02-01 | 2022-02-01 | 2022-12-31 | 410257 |  |  | 7167.47 | 8989.84 | 4076.61 | 507.97 |  |  | 508 | Red |  |  | 0 | 0 | 0 | 0 | [5 empty] | 12/2/2022 - more work completed due to Ops. schedule. 11/3/2022 - more work completed than anticipated. 11/1/2022 - Increased forecast for 2022 and added $300,000 in 2023 for butane thermal relief upgrades. 9/22/2022 - work put on hold due to an incident. Sylvan will assume mech. work. Work to resume last Oct. 9/6/2022 - work completed ahead of schedule. 8/8/2022 - relief upgrades IP. 6/3/2022 Work commencement postponed to June 2022. 4/5/2022 - additional Engineering completed; more than anticipated. | 2023-03-26 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 20234 | 508 | 0 |  | 482954 |  | Aiken, Elaine | Lee, David |  |  | 1 | 42184 |  | Clark, David | Independent | Aqua | 2021-09-17 | Int - Planned Corr & FI
Port Reading Butane Thermal Relief Upgrades | Item | Candidate | MCAP |  | Maintenance Framework |  | Wojton, Brian | East | 1. Proposed |  | Facility Integrity |  | 1 |  | 1 | 1 | 0 | Green |  |  |  | 1 | [9 empty] | 400001 | 400001 | No | Green | 2023-09-01 |  |  |  | 2023-12-29 | [12 empty] | 0 | 0 | 0 | 0 | 1 | [8 empty] | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 0 | 1 |  |  | 400000 | Aiken, Elaine |  |  |  | 1 | 46189 |  | Guest, ProSight | Independent | Aqua | 2022-11-07 | Int - Planned Corr & FI
Port Reading D and K Line Replacement at Dike Wall | Item | Open | MCAP | BPRPR00M2302 | Maintenance Framework | 2093995 | Wojton, Brian | East | 3. Active | Drawdown | Facility Integrity | 108211 | 60000 |  | 168210.67 | 169739 | -1528 | Yellow |  | 150000 | 150000 | 18211 |  |  | 159055 |  |  | 159055 | Full | 159055 | 108211 | 60000 | 168211 | No | Green | 2023-03-01 | 2023-03-06 | 2023-03-06 | 2023-06-15 | 2023-12-31 |  |  |  |  | 69739.15 | 38471.52 | 40000 | 40000 | -1528 | Yellow |  |  | 30000 | 30000 | [7 empty] | 5/8/2023 - K-Line is complete. D-Line delayed due to Ops activity. Moved 30k to June for D-Line. 3/16/2023 - Reclass from BPRPR00E2222 submitted for $69,574. 2/20/2023 - AFE routed for approval as approved by Elaine. | 2023-05-08 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 69739 | 98472 |  |  |  |  | Aiken, Elaine | Samuel, Michael |  |  | 1 | 46602 |  | Aiken, Elaine | Independent | Aqua | 2023-02-15
Port Reading Deluge System Installation 2023 | Item | Candidate | MCAP |  | Maintenance Framework |  | Wojton, Brian | East | 1. Proposed |  | Fire Protection |  | 150000 |  | 150000 | 150000 | 0 | Green | 150000 |  | 150000 | 0 | [9 empty] | 150000 | 150000 | No | Green | 2023-06-01 |  |  |  | 2023-07-31 | [12 empty] | 0 | 20000 | 80000 | 50000 | [9 empty] | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 20000 | 130000 |  |  |  | Jakubowski, Gregory |  |  |  | 1 | 44091 |  | Guest, ProSight | Independent | Aqua | 2022-07-07 | Other Programs
Port Reading Dockline Asbestos Abatement | Item | Open | MCAP | BPRPR00M2110 | Maintenance Framework | 1856111 | Keppel, Nicholas | East | 7. Closed | Defined | Marine | -194106 |  |  | -194105.91 | -194106 | 0 | Green |  |  |  | -194106 |  |  | 209000 |  |  | 209000 | Full | 209000 | 0 |  | 0 | No | Green | 2021-07-01 | 2021-06-10 | 2021-06-10 | 2021-07-31 | 2021-08-31 |  |  | -194105.91 | [18 empty] | 1/27/2023 -Put in flip ticket yesterday to move these $194K to a newly created flip Expense project (BPRPR00E2301). Reason: Per Sarah Loveless (Property Accounting), this project is not considered Capital (asbestos abatement without the installation of a new asset does not meet the criteria of a capital project). -MCS 1/19/2022 - Closed WO/PO, set OPPM status to 'Closed'. Can close. 9/2/2021 - Project completed in August 2021 | 2023-02-13 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | -194106 | 0 |  |  |  |  | Spari, Markella | Buchalski, Edwin |  |  | 1 | 37223 |  | Guest, ProSight | Independent | Aqua | 2020-07-22 | Other Programs
Port Reading Electrical Evaluation Upgrades - Phase 2 | Item | Open | MEXP | BPRPR00E2202 | Maintenance Framework | 1937488 | DeSocio, David | East | 7. Closed | Defined | Electrical | -7448 |  |  | -7447.75 | -7448 | 0 | Green |  |  |  | -7448 |  |  | 75000 |  |  | 75000 | Full | 75000 | 30266 |  | 30266 | No | Green | 2022-10-01 | 2022-01-06 | 2022-01-06 | 2022-07-01 | 2022-11-04 |  |  | -7447.75 | [18 empty] | 1/4/2023 Delay due to contractor schedule. 7/26/2022 - OPPM duplicates issue - Alex Marrocco tanks 7943/7944 currently shares same Project ID. Any of Alex Marrocco's $ on this project will get flipped (August biz?) to a new project number. MCS. | 2023-01-04 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | -7448 | 0 |  |  | 37713 |  | Ashley, Robert | Buchalski, Edwin |  |  | 1 | 37834 |  | DeSocio, David | Independent | Aqua | 2020-08-13 | Other Programs
Port Reading Firewater Supply Study | Item | Open | MEXP | BPRPR00E2225 | Maintenance Framework | 2023906 | Weirsky, Edward | East | 3. Active | Defined | Fire Protection | 20115 | 15799 |  | 35914 | 35914 | 0 | Green |  |  |  | 35914 |  |  | 47000 |  |  | 47000 | Full | 47000 | 31201 | 15799 | 47000 | No | Green | 2022-11-01 | 2022-09-29 | 2022-09-29 | 2022-11-30 | 2023-06-30 |  |  |  | 9172 | 6394 | 4549 |  |  | 4549 | Red |  |  | 5000 | 10799 | [7 empty] | 3/2/23 - TN/EW - Until the water line is resolved, contractor cannot complete study 12/1/22 - TN - ESDC work cannot be done due to site conditions 10/28/22 TN - ESDC pushed work | 2023-03-02 | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 15566 | 20348 |  |  | 11086 |  | Jakubowski, Gregory | Jakubowski, Greg |  |  | 1 | 45765 |  | Clark, David | Independent | Aqua | 2022-09-08 | Other Programs
Port Reading Insulated Pipe Priority 2 Repairs | Item | Open | MEXP |  | Maintenance Framework |  | Wojton, Brian | East | 1. Proposed |  | Facility Integrity |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 | [9 empty] | 40000 | 40000 | No | Green | 2023-11-01 |  |  |  | 2023-12-31 | [18 empty] | 20000 | 20000 | [5 empty] | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 0 |  | 40000 |  |  | Aiken, Elaine |  |  |  | 1 | 45070 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Port Reading Line Painting Phase 2 | Item | Open | MCAP | BPRPR00M2217 | Maintenance Framework |  | Keppel, Nicholas | East | 6. Operational | Defined | Facility Painting | 88326 |  |  | 88325.95 | 84300 | 4026 | Yellow |  |  |  | 88326 |  |  | 112000 |  |  | 112000 | Full | 112000 | 94762 |  | 94762 | No | Green | 2022-09-01 | 2022-08-17 | 2022-08-17 | 2022-11-30 | 2023-04-30 |  |  |  |  | 84300 | 4025.95 |  |  | 4026 | Red | [11 empty] | 4/7/2023 - Variance due to contractor becoming available ahead of schedule and work was able to be pulled in March 2023 | 2023-04-07 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 84300 | 4026 |  |  | 6436 |  | Geib, Rob | Geib, Robert |  |  | 1 | 37258 |  | Guest, ProSight | Independent | Aqua | 2020-07-23 | Int - Planned Corr & FI
Port Reading LPG Security Fence Installation | Item | Open | MCAP | BPRPR00M2116 | Maintenance Framework | 1900927 | Wojton, Brian | East | 4. On-Hold | Defined | East |  | 1 |  | 1 | 1 | 0 | Green |  |  |  | 1 |  |  | 180000 |  | 205000 | 385000 | Supplemental | 385000 | 124525 | 1 | 124526 | No | Green | 2021-11-01 | 2021-10-10 | 2021-10-10 | 2021-12-31 | 2022-12-30 | [19 empty] | 1 |  | 7/13/22 - Project placed On Hold per DLC pending reclasses for cancellation. DC 2/26/2022 - Supplemental submitted for 385k total project cost / Chris Clark. Forecast revised to reflect spend. 12/7/2021 - fencing material received. Project placed on hold by CC. 11/15/21 - Fencing material ordered for Dec. start 10/25/2021 - Bidding IP via CS. | 2022-08-08 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 0 |  | 1 | 32777 |  | Orischak, Bob | Leehan, Brendan |  |  | 1 | 40611 |  | Guest, ProSight | Independent | Aqua | 2021-07-23 | Other Programs
Port Reading paint/coat bare piping for Dock Lines on North Dock | Item | Open | MEXP | BPRPR00E2307 | Maintenance Framework | 2112798 | Bodner, Jordan | East | 3. Active | Defined | Facility Integrity |  | 20000 |  | 20000 | 20000 | 0 | Green | 20000 |  | 20000 | 0 |  |  | 22000 |  |  | 22000 | Full | 22000 |  | 20000 | 20000 | No | Green | 2023-10-01 | 2023-04-27 | 2023-04-27 | 2023-06-16 | 2023-10-31 | [17 empty] | 20000 | [5 empty] | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 0 |  | 20000 |  |  | Aiken, Elaine |  |  |  | 1 | 45683 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Int - Planned Corr & FI
Port Reading Piping Evaluation and Repair | Item | Open | MEXP | BPRPR00E2222 | Maintenance Framework | 2014074 | Wojton, Brian | East | 6. Operational | Drawdown | Facility Integrity | -34675 |  |  | -34674.8 | -34675 | 0 | Green |  |  |  | -34675 |  |  | 40000 |  |  | 40000 | Full | 40000 | 86518 |  | 86518 | No | Green | 2022-09-01 | 2022-08-31 | 2022-08-31 | 2022-10-31 | 2023-03-31 |  |  | 1825.2 | 29 | -36529 |  | 0 | 0 | 0 | Green | [11 empty] | 3/16/2023 Reclass submitted for $69,574- FM Sylvan - to BPRPR00M2302. 3/3/2023 Work was delayed due to tank 1202 incident. 2/20/2023 - work delayed in Feb. due to Tank 1202 incident. A separate AFE was submitted for the replacement for D Line and K Line on 2/20/2023 (Port Reading D and K Line Replacement at Dike Wall). 2/3/2023 scope expanded and was waiting for funding approval from facility integrity. 11/22/2022 - added 65k in Dec. to complete excavation and repair of D Line. 9/22/2022 - excavation complete and repair plan IP. | 2023-03-16 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | -34675 | 0 |  |  | 121193 |  | Aiken, Elaine | Shook, Mark B. | N/A |  | 1 | 45735 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-08-31 | Int - Planned Corr & FI
Port Reading Reconfigure 7945 Butane Line with Backpressure Valve | Item | Open | MCAP | BPRPR00M2209 | Maintenance Framework | 1946405 | Wojton, Brian | East | 7. Closed | Defined | East | 350 |  |  | 349.6 | 350 | 0 | Green |  |  |  | 350 |  |  | 191000 |  |  | 191000 | Full | 191000 | 10497 |  | 10497 | No | Green | 2022-04-01 | 2022-02-10 | 2022-02-10 | 2022-12-31 | 2022-10-01 |  |  | 349.6 | [18 empty] | 4.21.22.DLC: Moved forecast to 2022 XOM valve project... to be cancelled | 2022-04-21 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 350 | 0 |  |  | 10148 |  | Orischak, Bob | Leehan, Brendan |  |  | 1 | 42188 |  | Clark, David | Independent | Aqua | 2021-09-17 | Other Programs
Port Reading remove dead legs in Dock lines | Item | Open | MCAP |  | Maintenance Framework |  | Bodner, Jordan | East | 1. Proposed |  | Facility Integrity |  | 35000 |  | 35000 | 35000 | 0 | Green | 35000 |  | 35000 | 0 | [9 empty] | 35000 | 35000 | No | Green | 2023-09-01 |  |  |  | 2023-09-30 | [16 empty] | 35000 | [8 empty] | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 0 | 35000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45685 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Int - Planned Corr & FI
Port Reading Tank 1233 Phase 2 - Bottom and Seal Upgrades | Item | Open | MCAP | BPRPR00M2219 | Maintenance Framework | 2051664 | Marrocco, Alex | East | 6. Operational | Emergent | Tanks | 237362 | 20000 |  | 257361.83 | 249865 | 7497 | Yellow |  |  |  | 257362 |  |  | 388000 |  |  | 388000 | Full | 388000 | 308812 | 20000 | 328812 | No | Green | 2022-12-01 | 2022-12-06 | 2022-12-06 | 2022-12-31 | 2023-03-31 |  |  | 115511.66 | 97800.65 | 26552.74 | -2503.22 |  |  | -2503 | Red |  |  | 20000 | [8 empty] | 5/2/2023 reclass submitted for $6,203.66 from BPTPC00M2219...Invoice coded to wrong project. 2/3/2023 Work is behind schedule due to weather. 1/5/2023 additional work required (coating blast). | 2023-05-02 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 239865 | 17497 |  |  | 71450 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46266 |  | Perry, Betty | Independent | Aqua | 2022-11-28 | Int - Tanks
Port Reading Tank IFR Upgrades for NGSR | Item | Open | MEXP | BPRPR00E2216 | Maintenance Framework | 2003298 | Wojton, Brian | East | 7. Closed | Drawdown | Tanks | 26 |  |  | 25.62 | 26 | 0 | Green |  |  |  | 26 |  |  | 144000 |  |  | 144000 | Full | 144000 | 143370 |  | 143370 | No | Green | 2022-07-01 | 2022-07-18 | 2022-07-18 | 2022-08-15 | 2022-09-30 |  |  | 25.62 | [18 empty] | 9/22/2022 - project close out IP. 9/6/2022 - tank work completed ahead of schedule. 8/8/2022 - work completed ahead of schedule. | 2022-09-26 | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 26 | 0 |  |  | 143344 |  | Stine, Carlton | Dobias, Arthur P. |  |  | 1 | 44129 |  | Clark, David | Independent | Aqua | 2022-07-13 | Int - Tanks
Port Reading Terminal (BPRPR) Tank 1233 - OOS API 653 Insp | Item | Open | MCAP | BPRPR00M2218 | Maintenance Framework | 2023244 | Marrocco, Alex | East | 6. Operational | Emergent | Tanks | -87296 |  |  | -87296.17 | -87296 | 0 | Green | 330000 |  | 330000 | -417296 |  |  | 24000 |  |  | 24000 | Phase | 24000 | 22359 |  | 22359 | No | Green | 2022-09-01 | 2022-09-21 | 2022-09-21 | 2022-09-30 | 2022-12-31 |  |  | -87296.17 | [18 empty] | 1/10/2023 negative forecast entered to adjust incorrect accrual entry. 1/3/2023 Tank is requiring more repairs and it was pulled forward from 2023 project list.11/3/2022 Tank inspection was pulled-in from 2023, since the tank is currently out-of-service. | 2023-01-10 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | -87296 | 0 |  |  | 109655 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44868 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Port Reading Terminal (BPRPR) Tank 7940 - OOS API 653 Insp | Item | Open | MCAP | BPRPR00M2304 | Maintenance Framework | 2095804 | Marrocco, Alex | East | 3. Active | Defined | Tanks | 58464 | 712000 |  | 770464.46 | 700000 | 70464 | Red | 712278 |  | 712278 | 58186 |  |  | 225095 |  |  | 225095 | Phase | 225095 | 58464 | 712000 | 770464 | No | Green | 2023-04-01 | 2023-03-23 | 2023-03-23 | 2023-07-31 | 2023-10-31 | [5 empty] | 58464.46 | 100000 | 100000 | -41536 | Red |  | Other | 100000 | 300000 | 300000 | 12000 | 0 | 0 |  |  |  | 5/3/2023 overforecasted for month. | 2023-05-03 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 458464 | 312000 | 0 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44869 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Port Reading Terminal (BPRPR) Tank 1202– OOS Corr Insp & Refurb | Item | Open | MCAP | BPRPR00M2118 | Maintenance Framework | 1910235 | Wojton, Brian | East | 7. Closed | Defined | Tanks | 214 |  |  | 214.36 | 214 | 0 | Green |  |  |  | 214 |  | Carryover/Emergent/Drawdown/Reclass | 190000 | 1452000 | 211000 | 1853000 | Supplemental | 1853000 | 1954096 |  | 1954096 | No | Green | 2021-12-01 | 2021-11-22 | 2021-11-22 | 2022-05-30 | 2022-08-30 |  |  | 214.36 | [18 empty] | 9/22/2022 - project close out IP. 9/6/2022 - work completed ahead of schedule. 8/8/2022 - work completed ahead of schedule. 7/6/2022 - Bottom lining ahead of sch. in June. 5/11/22 - Work completed ahead of schedule. DC 4/7/22 - JJ White added additional manpower in March thus they completed more work than forecasted 3/3/22 - Costs came in less than expected. 2/8/22 - New bottom installation IP. 2/1/22-CES-Tank needs a need bottom and major repairs. 12/8/21-CES-DJA scanning tank now. Indication of major repairs needed on the tank bottom. | 2022-09-26 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 214 | 0 |  |  | 1349047 |  | Stine, Carlton | Buchalski, Edwin |  |  | 1 | 41312 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Port Reading Terminal (BPRPR) Tank 1210 Out of Service AIFR Repair | Item | Open | MEXP | BPRPR00E2302 | Maintenance Framework | 2095099 | Marrocco, Alex | East | 3. Active | Drawdown | Tanks |  | 85000 |  | 85000 | 85000 | 0 | Green |  |  |  | 85000 |  |  | 85000 |  |  | 85000 | Full | 85000 |  | 85000 | 85000 | No | Green | 2023-05-01 | 2023-03-16 | 2023-03-16 | 2023-06-30 | 2023-06-30 | [6 empty] | 65000 | 65000 | -65000 | Red |  | Buckeye/Customer Schedule | 40000 | 45000 | [7 empty] | 5/3/2023 Tank is still in service; scheduled to come out of service later this month. 3/20/23-CES-Project created to address a tear in the aluminum sheeting associated with tank 1210's floating roof. | 2023-05-03 | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 85000 |  |  |  |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 46767 |  | Stine, Carlton | JDE Child | Burnt Orange | 2023-03-14
Port Reading Terminal (BPRPR) Tank 1215 - OOS Corr Insp & Refurb | Item | Open | MCAP | BPRPR00M2101 | Exempt | 1810011 | Wojton, Brian | East | 7. Closed | Unplanned | Tanks | 186 |  |  | 186.2 | 186 | 0 | Green |  |  |  | 186 |  | Carryover/Emergent/Drawdown/Reclass | 660000 |  |  | 660000 | Phase | 660000 | 435349 |  | 435349 | No | Green | 2021-10-01 | 2021-01-11 | 2021-01-11 | 2021-12-31 | 2022-05-31 |  |  | 186.2 | [18 empty] | 9/22/2022 - project close out IP. 4/5/2022 pulled some work ahead to get tank ready for customer. 1/8/2022 - repairs IP. 1/15/2022 - roof and rafters deemed repairable for 10 year inspection interval by HMT. 12/8//21-CES-tank bottom is savable. Evaluation of the cone roof ongoing. Tank may need new roof. 10/25/2021 - tank is clean and IFR raising IP. 10/7/21-CES-API 653 inspection due in November. Tank to be removed from service soon. Needs to be scheduled with Ops. 1/28/2021 Expect to take tank out of service October 2, 2021. | 2022-09-26 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 186 | 0 |  |  | 221424 |  | Stine, Carlton | Bassani, Joel D. | N/A |  | 1 | 30397 |  | Guest, ProSight | Independent | Aqua | 2018-08-07 | Int - Tanks
Port Reading Terminal (BPRPR) Tank 7934 IFR Leg Repair | Item | Open | MEXP | BPRPR00E2303 | Maintenance Framework | 2110042 | Marrocco, Alex | East | 3. Active | Drawdown | Tanks | 69300 | 20000 |  | 89300 | 85000 | 4300 | Yellow |  |  |  | 89300 |  |  | 85000 |  |  | 85000 | Full | 85000 | 69300 | 20000 | 89300 | No | Green | 2023-04-01 | 2023-04-07 | 2023-04-07 |  | 2023-05-31 | [5 empty] | 69300 | 60000 | 60000 | 9300 | Red |  |  | 20000 | [10 empty] | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 89300 |  |  |  |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 46868 |  | Stine, Carlton | JDE Child | Burnt Orange | 2023-04-05
Port Reading Terminal (BPRPR) Tank 7935 - OOS Corr Insp & Refurb | Item | Open | MCAP | BPRPR00M2102 | Exempt | 1810012 | Wojton, Brian | East | 7. Closed | Unplanned | Tanks | 212 |  |  | 212.42 | 212 | 0 | Green |  |  |  | 212 |  |  | 438000 |  |  | 438000 | Phase | 438000 | 438629 |  | 438629 | No | Green | 2021-05-01 | 2021-02-01 | 2021-02-01 | 2021-12-31 | 2022-08-27 |  |  | 212.42 | [18 empty] | 9/22/2022 - tank RTS and project close out IP. 8/8/2022 - work completed ahead of schedule. 3/31/2022 - approved to begin bottom repair and tank work by BPL Leadership (XOM tank). Work to start in April. Forecast adjusted as needed. 7/2/2021 Tank inspection is complete. Moderate patching tank bottom required, along with IFR seal repairs. 6/15/2021 Tank has been taken out of service, isolated, and cleaned; tank inspection scheduled to start Wednesday, 6/16. 5/18/2021 Tank is expected to come out of service June 1, 2021. 1/28/2021 Expect to take tank out of service April 1, 2021. | 2022-09-26 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 212 | 0 |  |  | 371722 |  | Stine, Carlton | Bassani, Joel D. | N/A |  | 1 | 30396 |  | Guest, ProSight | Independent | Aqua | 2018-08-07 | Int - Tanks
Port Reading Terminal Air-to-Ground Coating | Item | Open | MCAP | BPRPR00M2205 | Maintenance Framework | 1939603 | Occhi, Edward | East | 7. Closed | Defined | Atmospheric Corrosion | 4152 |  |  | 4152 | 4152 | 0 | Green |  |  |  | 4152 |  |  | 100000 |  |  | 100000 | Full | 100000 | 108979 |  | 108979 | No | Green | 2022-09-01 | 2022-01-27 | 2022-01-27 | 2022-12-31 | 2022-11-30 |  |  | 4000 | 152 | [19 empty] | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 4152 | 0 |  |  | 104827 |  | Geib, Rob | Geib, Robert |  |  | 1 | 37413 |  | Guest, ProSight | Independent | Aqua | 2020-08-03 | Int - Planned Corr & FI
Port Reading Terminal Refined Product Relief Study 2023 | Item | Open | MEXP | BPRPR00E2308 | Maintenance Framework |  | Orischak, Bob | East | 2. Pending AFE | Defined | Facility Integrity |  | 135000 |  | 135000 | 135000 | 0 | Green | 135000 |  | 135000 | 0 |  |  | 139750 |  |  |  | Full | 139750 |  | 135000 | 135000 | No | Green | 2023-08-01 |  |  | 2023-10-25 | 2023-08-31 | [15 empty] | 135000 | [7 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 0 | 135000 |  |  |  | Aiken, Elaine | Orischak, Bob |  |  | 1 | 44089 |  | Guest, ProSight | Independent | Aqua | 2022-07-07 | Int - Planned Corr & FI
Port Wilmington (BNTUE) Tank 15 – OOS Corr Insp & Refurb | Item | Open | MCAP | BNTUE00M2201 | Maintenance Framework | 1937280 | Yoder, Michael | East | 6. Operational | Defined | Tanks | 66274 | 11228 |  | 77501.78 | 75373 | 2129 | Yellow |  |  |  | 77502 |  |  | 206000 | 90000 |  | 296000 | Full | 296000 | 291022 | 11228 | 302250 | No | Green | 2022-07-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-10-31 |  |  | 973.63 | 33124.8 | 13490.62 | 18684.73 | 16556 | 16556 | 2129 | Red |  |  | 11228 | [8 empty] | 5/2/23 - Electrical complete. 4/4/23 - Phase 2 AFE approved. Tank gauging in progress. 3/1/23 - Variance due to materials received ahead of schedule. Reduced March forecast. Preparing phase 2 AFE for submission. 2/1/23 - Variance due to disposal invoice. Preparing phase 2 AFE for submission. 1/4/23 - Variance due to disposal costs higher than estimated. Preparing phase 2 AFE for submission. 12/2/22 - Preparing phase 2 AFE for submission. 11/1/22 - Repairs completed. Tank returned to service. Moved 45k to Q1 2023 due to long lead time item (tank gauging). 10/4/22 - Tank cleaning in progress. 9/1/22 - Plan to clean late September. 7/6/2022 - Planned for September. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Port Wilmington | BNTUE - WIlmington(DE) Terminal |  | 47589 | 29913 |  |  | 224748 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41314 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Port Wilmington (BNTUE) Tank 15 Support Project | Item | Open | MCAP | BNTUE00M2104 | Maintenance Framework | 2011056 | Yoder, Michael | East | 7. Closed | Defined | Tank Outage | 863 |  |  | 863.17 | 863 | 0 | Green |  |  |  | 863 |  |  | 250000 |  |  | 250000 | Full | 250000 | 184202 |  | 184202 | No | Green | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-02-01 | 2022-11-30 |  |  | 525.46 |  | 337.71 | [16 empty] | 3/14/2023 - Closed WO/PO, and set OPPM status to 'Closed'. MCS 2/1/23 - Keep open for one more month then close. 1/4/23 - Variance due to additional mechanical work. Project still came in under budget. 12/5/22-Keep open 1 more month.12/1/22 - T16 cleaned and ready for normal ULSD service. Variance due to costs less than budgeted. 11/1/22 - T15 returned to service. Emptying T16 and cleaning to start 11/14. 10/4/22 - Piping mods completed. Moved some spend to December for tank 16 cleaning after tank 15 returns to normal service. 9/2/2022 - Variance due to early start. Adjusted forecast to offset. 8/1/2022 - Revised AFE out for approval. Plan to start construction in September. 5/4/2022 - Planning to submit AFE this month | 2023-03-14 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Port Wilmington | BNTUE - WIlmington(DE) Terminal |  | 863 | 0 |  |  | 183339 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41315 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Port Wilmington (BNTUE) Tank 2 – OOS Corr Insp & Refurb | Item | Open | MCAP | BNTUE00M2202 | Maintenance Framework | 1937281 | Yoder, Michael | East | 6. Operational | Defined | Tanks | 8892 |  |  | 8892.2 | 8344 | 549 | Yellow |  |  |  | 8892 |  |  | 435000 | 356000 |  | 791000 | Full | 791000 | 798636 |  | 798636 | No | Green | 2022-05-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-09-30 |  |  | 0 | 240 | 1849.57 | 6802.63 | 6254 | 6254 | 549 | Yellow | [11 empty] | 5/2/23 - Electrical complete. 4/4/23 - Tank gauging in progress. 3/1/23 - Awaiting electrical invoices. 2/1/23 - Tank gauging in progress. 1/4/23 - Tank gauging in progress. Moved 6k to March forecast for commissioning gauging equipment. 12/2/22 - Tank gauging install in progress. 11/1/22 - Tank gauging work in progress. Preparing phase 2 AFE for submission. 10/4/22 - Tank returned to service. Updated Q4 forecast for tank gauging. Preparing phase 2 AFE for approval. 9/2/22 - Tank repairs complete. Liner repairs in progress. Preparing phase 2 AFE for approval. 8/2/22 - Tank repairs in progress. Updated forecast for planned liner repairs. 7/13/2022-Tank 2 inspection is in progress and there will be significant repairs. Scope is not yet determined yet so forecast is best I have' -Yoder.7/1/22 - Tank cleaned. Variance due to completing tank cleaning ahead of schedule. Reduced June forecast since repair scope until inspection completed around 7/11. 6/2/22 - Tank stripped and isolated. Variance due to early start. 2/1/2022 - Pushed back forecast to April in order to get tank 3 returned to service prior to taking tank 2 OOS. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Port Wilmington | BNTUE - WIlmington(DE) Terminal |  | 2090 | 6803 |  |  | 789744 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41316 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Port Wilmington Diesel Prover Pump Back Crossover | Item | Open | MCAP | BNTUE00M2302 | Maintenance Framework | 2095135 | Wing, Hunter | East | 3. Active | Defined | East |  | 24944 |  | 24944 | 25000 | -56 | Yellow | 25000 |  | 25000 | -56 |  |  | 24944 |  |  | 24944 | Full | 24944 |  | 24944 | 24944 | No | Green | 2023-06-01 | 2023-03-15 | 2023-03-15 | 2023-07-07 | 2023-09-30 | [13 empty] | 24944 | [7 empty] | 5/1/2023 - HJW - PO issued to MDavis has been awarded the scope and expected to have the handle extensions by mid to end of may. will install in June. 4/4/2023-Have gotten bids. 3/14/23 - HW - AFE submitted 3/14. Quotes obtained from JZ and MDavis. Work expected to be completed with VCU project in June/July. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Port Wilmington | BNTUE - WIlmington(DE) Terminal |  |  | 24944 |  |  |  |  | Orischak, Bob | Orischak, Bob |  |  | 1 | 38650 |  | Guest, ProSight | Independent | Aqua | 2020-09-24 | Other Programs
Port Wilmington System Atmospheric Corrosion Remediation | Item | Open | MCAP | BNTUE00M2206 | Maintenance Framework | 1938852 | Gable, Rob | East | 3. Active | Defined | Atmospheric Corrosion |  | 25000 |  | 25000 | 25000 | 0 | Green |  |  |  | 25000 |  |  | 25000 |  |  | 25000 | Full | 25000 |  | 25000 | 25000 | No | Green | 2023-08-01 | 2022-01-20 | 2022-01-20 | 2022-09-15 | 2023-06-30 | [15 empty] | 15000 | 10000 |  |  |  |  | 5/2/2023 RAG - Work to begin during Q3. 2/2/2023 RAG - Work had previously been deferred into 2023. 1/4/2023 RAG - Work had previously been deferred into 2023. 12/2/2022 RAG - Work had previously been deferred until 2023. 11/3/2022 RAG - Work had previously been deferred until 2023. 9/29/2022 RAG - Deferring spending to 2023 due to contractor availability and scheduling. 9/6/2022 RAG - Working with JSR. 8/2/2022 RAG - Currently developing repair program. 4/4/2022 RAG - Preparing work to begin as forecasted. 2/2/2022 RAG - AFE has been approved and WOR created. 1/12/2022 RAG - AFE submitted on 1/12/2022.11/3/2022 RAG - Work had previously been deferred until 2023. 9/29/2022 RAG - Deferring spending to 2023 due to contractor availability and scheduling. 9/6/2022 RAG - Working with JSR. 8/2/2022 RAG - Currently developing repair program. 4/4/2022 RAG - Preparing work to begin as forecasted. 2/2/2022 RAG - AFE has been approved and WOR created. 1/12/2022 RAG - AFE submitted on 1/12/2022. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Port Wilmington | BNTUE - WIlmington(DE) Terminal |  |  | 0 | 25000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 40891 |  | Guest, ProSight | Independent | Aqua | 2021-08-02 | Int - Accel Corr & FI
Port Wilmington VCU Burner and Air Duct Upgrade | Item | Open | MCAP | BNTUE00M2301 | Maintenance Framework | 2095138 | Wing, Hunter | East | 3. Active | Defined | Vapor Management | 32257 | 138461 |  | 170717.98 | 170000 | 718 | Yellow | 160000 |  | 160000 | 10718 |  |  | 170641 |  |  | 170641 | Full | 170641 | 32257 | 138461 | 170718 | No | Green | 2023-04-01 | 2023-03-16 | 2023-03-16 | 2023-07-07 | 2023-07-31 | [5 empty] | 32256.98 | 60000 | 60000 | -27743 | Red |  | Savings from AFE Estimate | 0 | 116867 | 21594 | 0 | [5 empty] | 5/1/2023 - HJW - PO Issued to JZ and MDavis for SOW. Planned execution to start mid June. Expected to take 1 week to complete. Forecast updated to represent actual forecast. April misforecast was a cost savings from JZ due to added scope that was not needed. 4/4/2023-PO issued to Zink, have gotten bids for mechanical labor..Up-front engineering started recently. 3/14/23 - HW - AFE submitted 3/14. Quotes obtained from JZ and MDavis. JZ requires 40% of materials to be paid upfront and will hit in April. Remainder to hit in June / July | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Port Wilmington | BNTUE - WIlmington(DE) Terminal |  |  | 149124 | 21594 |  |  |  | Karl, Marissa | Orischak, Bob |  |  | 1 | 44943 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Other Programs
Pt Reading Fire Pump Repair 2022 | Item | Open | MEXP | BPRPR00E2227 | Maintenance Framework | 2037846 | Orischak, Bob | East | 7. Closed | Drawdown | Fire Protection | 25948 |  |  | 25948 | 25948 | 0 | Green |  |  |  | 25948 |  |  | 27000 |  |  | 27000 | Full | 27000 | 25948 |  | 25948 | No | Green | 2023-01-01 | 2022-12-20 | 2022-12-20 | 2022-12-31 | 2023-02-01 |  |  | 25948 | [18 empty] | 2/7/2023 - Closed WO/PO, set OPPM project status to 'Closed'. (PO already closed, and sclosed WO 2027846,)which was never mapped to the project and therefore the labor got assigned to local BPRPR).. MCS 1/31/2023 - RLO Work has been completed. Can Close 01/03/23 RLO - Project was just approved last week of December. Spends to occur in January. | 2023-02-07 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 25948 | 0 |  |  |  |  | Jakubowski, Gregory | Jakubowski, Greg | N/A |  | 1 | 46368 |  | Orischak, Bob | JDE Child | Burnt Orange | 2022-12-15 | Other Programs
Pt. Reading Butane Relief Engineering 2023 | Item | Open | MEXP | BPRPR00E2304 | Maintenance Framework | 2110627 | Wojton, Brian | East | 3. Active | Drawdown | East |  | 85001 |  | 85001 |  | 85001 | Red |  | 85000 | 85000 | 1 |  |  | 85000 |  |  | 85000 | Full | 85000 |  | 85001 | 85001 | No | Green | 2023-05-01 | 2023-04-13 | 2023-04-13 | 2023-07-31 | 2023-07-31 | [12 empty] | 25000 | 60000 | [5 empty] | 1 |  | 4/21/23 ESDC is performing an engineering analysis and a path forward. Expected to be complete by end of June. | 2023-04-21 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 85000 |  | 1 |  |  | Orischak, Bob | Orischak, Bob | N/A |  | 1 | 46941 |  | Orischak, Bob | JDE Child | Burnt Orange | 2023-04-13
PY740XX - DIG SHEETS (4) | Item | Open | MCAP | PY740XXM2201 | Maintenance Framework | 2037800 | Gebert, Clint | East | 6. Operational | Drawdown | Pipeline Digs | 13195 |  |  | 13194.5 | 13195 | 0 | Green |  |  |  | 13195 |  |  | 358000 |  |  | 358000 | Full | 358000 | 322618 |  | 322618 | No | Green | 2022-10-01 | 2022-12-01 | 2022-12-01 | 2022-12-31 | 2023-04-28 |  |  | 3530.08 | 9248.25 | 416.17 | 0 |  |  | 0 | Green | [11 empty] | 5/3/2023-The I-476 features cannot be dug and will be the subject of a 2024 purge and cut-out project. handled by ECS. 2/3/2023-One more dig to do, just surveyed it this wk, not sure will be able to do because it is under the Blue Route. 1/5/2023-The 2 DOT sites are completed, determining feasibility of last BPL site. 12/5/2022-Less scope than originally anticipated (1 site is left out of the AFE due to complexity). 11/28/22-CGG- Both DOT digs are complete. The BPL site requires more investigation as to whether it can be accomplished. Possibly Located beneath the I-476N on ramp from I-95S. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Malvern | PY740XX - PAULSBORO TO PA S/L(MALVERN) |  | 13195 | 0 |  |  | 309423 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46102 |  | Guest, ProSight | Independent | Aqua | 2022-10-20 | Int- Planned Digs
Raritan Bay Asbestos Abatement | Item | Open | MEXP | BFRQF00E2203 | Maintenance Framework | 1954870 | Wojton, Brian | East | 7. Closed | Defined | East | 2375 |  |  | 2374.68 | 2375 | 0 | Green |  |  |  | 2375 |  |  | 125000 |  |  | 125000 | Full | 125000 | 82177 |  | 82177 | No | Green | 2022-05-01 | 2022-03-02 | 2022-03-02 | 2022-08-30 | 2022-11-18 |  |  | 2355 | 19.68 | [17 empty] | 9/22/2022 - working with Ops to define remaining scope. 8/8/2022 - working with Ops to define remaining scope. 3/25/2022 - Bids received and work issued to Furino. Abatement to start 4/22022. | 2022-09-26 | Walker, Carol |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BFRQF - BFR RARITAN BAY TERMINAL |  | 2375 | 0 |  |  | 79803 |  | Orischak, Bob | Buchalski, Edwin |  |  | 1 | 34086 |  | Guest, ProSight | Independent | Aqua | 2019-08-16 | Other Programs
Raritan Bay Atmospheric Refurbishment | Item | Open | MCAP | BFRQF00M2204 | Maintenance Framework | 1939594 | Occhi, Edward | East | 7. Closed | Defined | Atmospheric Corrosion |  | 60000 |  | 60000 | 60000 | 0 | Green |  |  |  | 60000 |  |  | 100000 |  |  | 100000 | Full | 100000 |  | 60000 | 60000 | No | Green | 2023-05-01 | 2022-01-27 | 2022-01-27 | 2022-12-31 | 2022-12-09 | [12 empty] | 15000 | 30000 | 15000 | [8 empty] | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BFRQF - BFR RARITAN BAY TERMINAL |  |  | 45000 | 15000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 41087 |  | Guest, ProSight | Independent | Aqua | 2021-08-06 | Int - Planned Corr & FI
Raritan Bay Fire Pump Replacement | Item | Open | MCAP | BFRQF00M2206 | Maintenance Framework | 1979442 | DeSocio, David | East | 7. Closed | Drawdown | Fire Protection | 300 | 45000 |  | 45300.29 | 45300 | 0 | Green |  |  |  | 45300 |  |  | 177000 |  |  | 177000 | Full | 177000 | 147007 | 45000 | 192007 | No | Green | 2022-07-01 | 2022-05-02 | 2022-05-02 | 2022-09-01 | 2022-11-17 |  |  | 222.16 | 78.13 | [15 empty] | 45000 |  | 1 30 23 - Looking now to reuse potentially at Rensselaer 12 2 22 - Pump may now be used at Port Reading. Waiting on Management to confirm location. | 2023-01-31 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BFRQF - BFR RARITAN BAY TERMINAL |  | 300 | 0 |  | 45000 | 146706 |  | Jakubowski, Gregory | Buchalski, Edwin |  |  | 1 | 43561 |  | Meitzler, Antoinette | Independent | Aqua | 2022-04-28 | Other Programs
Raritan Bay New Fire Pump | Item | Open | MCAP | BFRQF00M2202 | Maintenance Framework | 1938286 | DeSocio, David | East | 4. On-Hold | Emergent | Fire Protection | 2936 | 73000 |  | 75935.74 | 75936 | 0 | Green |  |  |  | 75936 |  |  | 77000 |  |  | 77000 | Supplemental | 77000 | 2936 | 73000 | 75936 | No | Green | 2023-02-01 | 2022-01-14 | 2022-01-14 | 2022-03-01 | 2022-06-30 |  |  |  | 1957.16 | 978.58 | [8 empty] | 0 | 73000 | [8 empty] | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 2936 | 0 | 73000 |  |  |  | Jakubowski, Gregory | Buchalski, Edwin |  |  | 1 | 42030 |  | Clark, David | Independent | Aqua | 2021-09-01
Raritan Bay Terminal (BFRQF) Tank 0245 - OOS API 653 Insp | Item | Open | MCAP | BFRQF00M2301 | Maintenance Framework |  | Marrocco, Alex | East | 8. Canceled | Defined | Tanks |  | 0 |  | 0 | 0 | 0 | Green | 1156216 |  | 1156216 | -1156216 |  |  | 109685 |  |  |  | Phase | 109685 |  | 0 | 0 | No | Green |  |  |  | 2023-06-30 | 2023-07-31 | [12 empty] | 0 | [8 empty] | 4/24/23 Canceled due to idle of the facility. RLO 3/9/23-CES-Removing forecast. Tank will be cleaned and idled. AFE is being routed against MEXP program. 2/27/23-CES-Per commercial, plan to clean, inspect, and leave this tank idle. Reducing forecast to match phase 1 AFE amount of $293,000. 9/13/22-CES-Forecasting a scenario where full spend for RTS is anticipated. Consider commercial needs upon inspection. | 2023-04-24 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BFRQF - BFR RARITAN BAY TERMINAL |  |  | 0 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44873 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Raritan Bay Terminal (BFRQF) Tank 0245 Cleaning and Idle | Item | Open | MEXP | BFRQF00E2301 | Maintenance Framework | 2095692 | Marrocco, Alex | East | 6. Operational | Drawdown | Tanks | 40553 | 15000 |  | 55552.92 | 115000 | -59447 | Red |  | 105388 | 105388 | -49835 |  |  | 105388 |  |  | 105388 | Full | 105388 | 40553 | 15000 | 55553 | No | Green | 2023-04-01 | 2023-03-21 | 2023-03-21 | 2023-04-30 | 2023-04-30 | [5 empty] | 40552.92 | 50000 | 50000 | -9447 | Red |  |  | 15000 | [8 empty] | 3/20/23-CES-Tank was budgeted as MCAP. Plan will be to clean and idle so project was funded via drawdown. | 2023-03-20 | Walker, Carol |  | East | Pipelines and Terminals | Tank Integrity |  | Harbor South Terminals | BFRQF - BFR RARITAN BAY TERMINAL |  |  | 55553 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46752 |  | Meitzler, Antoinette | Independent | Aqua | 2023-03-10
Raritan Bay Terminal (BFRQF) Tank 0244 – OOS Corr Insp & Refurb | Item | Open | MCAP | BFRQF00M2201 | Maintenance Framework | 1937271 | Marrocco, Alex | East | 7. Closed | Defined | Tanks | 1554 |  |  | 1553.88 | 1554 | 0 | Green |  |  |  | 1554 |  |  | 464000 |  |  | 464000 | Phase | 464000 | 126877 |  | 126877 | No | Green | 2022-06-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-12-31 |  |  | 1553.88 | [18 empty] | 9/11/22/-CES-Negative variance represents work being delayed. Cost to return tank to service is not justified given current commercial needs. 9/2/22 - Work deferred until further notice. Updated forecast. 8/3/22 - Tank inspection in progress. | 2022-09-11 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BFRQF - BFR RARITAN BAY TERMINAL |  | 1554 | 0 |  |  | 125323 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41320 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
RC999A2 Shipper Line Removal | Item | Open | MEXP |  | Maintenance Framework |  | Pepe, David | East | 8. Canceled |  | Facility Integrity |  | 0 |  | 0 | 0 | 0 | Green | 45000 |  | 45000 | -45000 | [9 empty] | 0 | 0 | No | Green |  |  |  |  | 2023-10-31 | [17 empty] | 0 |  |  |  | 3.02.2023 - Advised by Operations that cutout not required (Current owner does not require). 12/07/22 DJP Reached out to Kiely to discuss the planning for the cutout. | 2023-03-02 |  |  | East | Pipelines and Terminals | Station/Terminal |  | Auburn Pipeline | RC999A2 - ROCHESTER TO GULF |  |  | 0 |  | 0 |  |  | Aiken, Elaine |  |  |  | 1 | 24559 |  | Administrator, System | Independent | Aqua | 2017-07-27 | Int - Planned Corr & FI
RC999A5 buried IJ repair | Item | Open | MEXP | RC999A5E2301 | Maintenance Framework | 2085711 | Norton, Bill | East | 3. Active | Defined | Cathodic Protection |  | 35000 |  | 35000 | 35000 | 0 | Green | 35000 |  | 35000 | 0 |  |  | 33620 |  |  | 33620 | Full | 33620 |  | 35000 | 35000 | No | Green | 2023-06-01 | 2023-02-21 | 2023-02-21 | 2023-10-01 | 2023-11-30 | [13 empty] | 35000 | [9 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Corrosion |  | Auburn Pipeline | RC999A5 - ROCHESTER TO HESS |  |  | 35000 |  |  |  |  | Geib, Rob |  |  |  | 1 | 44353 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
Rectifier RH-01 Replacement BETRH | Item | Open | MCAP | BETRH00M2204 | Maintenance Framework | 2037203 | Gable, Rob | East | 6. Operational | Drawdown | Cathodic Protection | 20409 |  |  | 20409.15 | 20213 | 196 | Yellow |  |  |  | 20409 |  |  | 49000 |  |  | 49000 | Full | 49000 | 51617 |  | 51617 | No | Green | 2022-11-01 | 2022-10-16 | 2022-10-16 | 2022-12-20 | 2022-12-31 |  |  | 6318.06 | 9545.31 | 4350.03 | 195.75 |  |  | 196 | Red | [11 empty] | 5/2/2023 RAG - Awaiting final invoices form Old Dominion. 4/4/2023 RAG - Awaiting final invoices form Old Dominion. 3/2/2023 RAG - Awaiting invoices. Replacement rectifier required. 2/28/2023 RAG - Job Book complete and sent to Joan for review. 2/2/2023 RAG - Extra $6K required to replace rectifier that was received damaged. 1/4/2023 RAG - Work completed for less than expected. 12/2/2022 RAG - Work performed by Old Dominion. PO issued for rectifier. 11/3/2022 RAG - New project. Scheduled for Nov/Dec installation by Old Dominion. PO has been issued. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Virginia | BETRH - BET RICHMOND |  | 20213 | 196 |  |  | 31207 |  | Geib, Rob | Geib, Robert |  |  | 1 | 46061 |  | Perry, Betty | Independent | Aqua | 2022-10-12 | Int - Planned Corr & FI
Rensselaer - Loading Platform and Breasting Dolphins substructure repairs. | Item | Open | MCAP | BETQE00M2205 | Maintenance Framework | 1938784 | Wojton, Brian | East | 3. Active | Defined | Marine | 67 | 665000 |  | 665066.97 | 680000 | -14933 | Yellow | 680000 |  | 680000 | -14933 |  |  | 30000 |  |  | 30000 | Phase | 30000 | 28060 | 665000 | 693060 | No | Green | 2022-03-01 | 2022-01-20 | 2022-01-20 | 2022-12-31 | 2023-08-31 | [5 empty] | 66.97 |  |  | 67 | Red |  |  | 10000 | 50000 | 200000 | 200000 | 80000 | 125000 |  |  |  | 11.25.22 SDB: Anchor Consultants completed inspection and will issue a report. 11.9.22 TN - Forecast for December removed 10.31.22 SDB: Anchor consultants dive inspection rescheduled for 11/16-17. 9.17.22 SDB: Anchor consultants scheduled inspection for 10/26-27. Work plans approved by Ops/Safety/Scheduling. 9.7.22 MKS: Repair scope is not defined yet. 2023 forecast (500K) is based on 2022 bid pricing. 185K likely to be moved within portfolio. 9.2.22 SDB: Revised proposal received from Anchor Consultants. Presently under review. 8.22.22 SDB: Upper management agreed and a new detailed inspection and revised repair method will be requested from a different engineering firm. Work is deferred until this process is completed. 8.15.22 SDB: Dive inspections completed and revised repair procedures and proposal expected from KT Marine this week. 8.1.22 SDB: Dive inspection by KT Marine to start this week. 7.25.22 SDB: Dive inspection by KT Marine scheduled for first week of August. 7.8.22 SDB: KT Marine presented proposal for an additional dive inspection in order to confirm or revise repair procedures. PO was issued. Job and Dive Plans have been reviewed and approved. Inspection tentatively scheduled for the week of 07/25. 6.10.22 SDB: LOI was sent and accepted by the winning contractor KT Marine. 5.31.22 SDB: Bid process was extended and additional contractors were invited. Bid process was closed on 05/25 and we are presently reviewing proposals with short listed contractors in order to award the work. 5.2.22 SDB: Received proposals from bidding contractors. Will review proposals and schedules to determine award and issue PO. 4.11.22 SDB: This project is presently being bid out by supply chain. Bids due 3rd week of April. 3.31.22 Supply chain scheduled to hold a bid process in the first half of April. 2.18.22.DLC Bidding out with supply chain. | 2022-11-25 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | Roseton and Rensselaer | BETQE - BET RENSSELAER TERMINAL |  |  | 60067 | 480000 | 125000 | 27993 |  | Spari, Markella | Martin, David N. |  |  | 1 | 41938 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Marine
Rensselaer - Timber Cribwall | Item | Open | MCAP | BETQE00M2204 | Maintenance Framework | 1954937 | Wojton, Brian | East | 4. On-Hold | Defined | Marine |  | 1 |  | 1 | 1 | 0 | Green |  |  |  | 1 |  |  | 59000 |  |  | 59000 | Phase | 59000 | 34302 | 1 | 34303 | No | Green | 2022-03-01 | 2022-03-03 | 2022-03-03 | 2022-10-30 | 2023-11-30 | [17 empty] | 0 | 1 |  |  | 2.14.23.DLC: Removed forecast and put project on hold per program manager11.25.22 SDB: Anchor Consultants completed the inspection and will issue the report. 9.18.22 SDB: Inspection by Anchor consultants scheduled for 10/26 and 27. 9.7.22 MKS Repair scope not defined 2023 carryover adjusted to 500K based on 2022 bid pricing. 9.2.22 SDB: Proposal received from Anchor Consultants. Presently under review. 8.25.22 SDB: Requested proposal from engineering firm to conduct an inspection, evaluation and to provide alternate repair methods with estimated costs for the deteriorating timber wall. 8.1.22 SDB: Project is deferred until 2023. 6.10.22 SDB: The SOW for this project was removed from the Rensselaer work. Additional Inspections and a new repair method will be evaluated and project may be executed at a later date. 5.31.22 SDB: Bid process was extended and additional contractors were invited. Bid process was closed on 05/25 and we are presently reviewing proposals with short listed contractors in order to award the work. 5.2.22 SDB: Received proposals from bidding contractors. Will review proposals and schedules to determine award and issue PO. 4.11.22 SDB: This project is presently being bid out by supply chain. Bids du on 3rd week of April. 3.31.22 SDB: Supply chain scheduled to hold a bid process in the first alp of April. 2.18.22.DLC Bidding out with supply chain | 2023-02-14 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | Roseton and Rensselaer | BETQE - BET RENSSELAER TERMINAL |  |  | 0 |  | 1 | 34302 |  | Spari, Markella | Spari, Markella |  |  | 1 | 41939 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Marine
Rensselaer Air to ground coating phase 2 | Item | Open | MCAP | BETQE00M2301 | Maintenance Framework | 2085653 | Norton, Bill | East | 3. Active | Defined | Atmospheric Corrosion |  | 45000 |  | 45000 | 45000 | 0 | Green | 45000 |  | 45000 | 0 |  |  | 45435 |  |  | 45435 | Full | 45435 |  | 45000 | 45000 | No | Green | 2023-09-01 | 2023-02-21 | 2023-02-21 | 2023-11-01 | 2023-11-30 | [16 empty] | 45000 | [6 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Roseton and Rensselaer | BETQE - BET RENSSELAER TERMINAL |  |  | 0 | 45000 |  |  |  | Geib, Rob | Gee, Ryan |  |  | 1 | 44338 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
Rensselaer API 570 Priority 2 Repairs | Item | Open | MEXP |  | Maintenance Framework |  | Wing, Hunter | East | 1. Proposed |  | Facility Integrity |  | 50000 |  | 50000 | 50000 | 0 | Green | 55000 |  | 55000 | -5000 | [9 empty] | 50000 | 50000 | No | Green | 2023-05-01 |  |  |  | 2023-08-31 | 8 | Yellow |  |  |  |  | 10000 | 10000 | -10000 | Red |  | Contractor/Vendor Issue | 15000 | 35000 | 0 | 0 | [5 empty] | 5/1/2023 - HW - Mechanical portion expected to be completed by end of May. Project will be completed during Daylight and Asphalt Projects. FPI has provided quote for Mechanical SOW and is pending integrity approval to continue. Painting contractor soon to be determined within the next week through Supply Chain who will coordinate a small bid event for painting contractors. Project has also found that some items listed on the 570 Punchlist are significant projects and will need need additional funding identified by integrity. Integrity to determine what items on the 570 list need to be completed on this project. Forecast has been updated based on understanding of current SOW. 4/10/2023 - AFE to be submitted after detailed walkdown with contractor and then review with integrity. 4/4/2023 - Planning to do during downtime in April or May | 2023-05-02 |  |  | East | Pipelines and Terminals | Station/Terminal |  | Roseton and Rensselaer | BETQE - BET RENSSELAER TERMINAL |  |  | 50000 | 0 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45058 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Rensselaer CP troubleshooting and repair | Item | Open | MEXP | BETQE00E2301 | Maintenance Framework | 2085675 | Norton, Bill | East | 3. Active | Defined | Cathodic Protection |  | 35000 |  | 35000 | 35000 | 0 | Green | 35000 |  | 35000 | 0 |  |  | 34650 |  |  | 34650 | Full | 34650 |  | 35000 | 35000 | No | Green | 2023-09-01 | 2023-02-21 | 2023-02-21 | 2023-10-01 | 2023-11-30 | [16 empty] | 35000 |  |  |  |  | 5/2/23 Lake Superior to perform troubleshooting to determine where repairs are needed. WRN | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Corrosion |  | Roseton and Rensselaer | BETQE - BET RENSSELAER TERMINAL |  |  | 0 | 35000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44346 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
Rensselaer Office Building Refurbishments | Item | Candidate | MCAP |  | Maintenance Framework |  | Orischak, Bob | East | 8. Canceled |  | East |  | 0 |  | 0 | 50000 | -50000 | Red | 50000 |  | 50000 | -50000 | [9 empty] | 0 | 0 | No | Green |  |  |  |  | 2023-06-30 | [12 empty] | 0 | 0 | [7 empty] | 5/1/23 - Project is being canceled and funding moved to Baltimore Electrical. RLO | 2023-05-01 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Roseton and Rensselaer | BETQE - BET RENSSELAER TERMINAL |  |  | 0 |  |  |  |  | Orischak, Bob |  |  |  | 1 | 37254 |  | Guest, ProSight | Independent | Aqua | 2020-07-23 | Other Programs
Rensselaer Oil-Stop Valve Installation | Item | Open | MCAP | BETQE00M2206 | Maintenance Framework | 2003619 | Mohr, David | East | 3. Active | Defined | Storm Water Management | 5267 | 50000 |  | 55266.97 | 54762 | 505 | Yellow |  |  |  | 55267 |  |  | 147000 |  |  | 147000 | Full | 147000 | 106298 | 50000 | 156298 | No | Green | 2022-07-01 | 2022-09-21 | 2022-09-21 | 2022-12-31 | 2023-05-31 |  |  | 562.87 | 2873.65 | 1325.79 | 504.66 | 50000 | 50000 | -49495 | Red |  | Weather | 50000 | [8 empty] | 5/1/2023Varience dues to weather (rain). Installation is progressing but slow due to rain. Inlet valve received. 4/1/2023 Issued PO's for construction. Installation to be completed this month. 3/1/2023 Met with contractors to request updated quotes and scope discussions. DRM 2/2/2023 Variance due to not receiving the permit to install/operate 1/3/2023 Have not received permit from NYS to allow installation/operation 12/1/2022 Received Oil-stop valve tank. variance due to not having permit to install from NYDEC. 11/1/2022 - Expecting valve this month but, have not received NYDEC permit10/5/22-Expecting the valve in October. 9/1/2022 Stop valve on order from MErcer, DRM 8/3/2022 - Will be submitting for a full AFE. 8/1/2022 Waiting for permit, AFE has been approved and PO or valve cut for valve/box construction. Electrical and civil PO to follow. DRM 7/5/2022 Waiting to here back from State of NY for permit. DRM 6/2/2022 Steve Tracy is providing quotes for elec/mech contractor. We have quote for Valve. Permitting request is being worked by Envirospec. DRM 5/2/2022 Working with Gianna of Envirospec to get the NYDEP permitting completed. Requested quote from Mac Son. DRM 2/2/2022 Had conversations with Clint G. Further discussion is required. 3/2/18 - This project has been mis-marked as a 5. The NYDEC may not even give us permission to install the valve and therefore should be a 4. This project is being deferred until 2019 to offset some other project overages in the East District.BSK. 3/1/2022 DRM Determined there in not a NYDEC approval letter for a change to the SPDES permit. Working with Nate Pratt and Steve Tracey to determine what is needed before AFE can be developed. 4/1/2022 DRM Met with Mark Bonenberger and Nate Pratt. Determined there is not a permit in place to allow for us to install the valve. Further investigation for permit submittal required. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Roseton and Rensselaer | BETQE - BET RENSSELAER TERMINAL |  | 4762 | 50505 |  |  | 101031 |  | Bonenberger, Mark | Tracey, Steve | N/A |  | 1 | 25098 |  | Guest, ProSight | Independent | Aqua | 2017-08-21 | Other Programs
Rensselaer Terminal (BETQE) Tank 1510 - OOS Corr + Seal Insp & Refurb | Item | Open | MCAP | BETQE00M2201 | Maintenance Framework | 1937283 | Marrocco, Alex | East | 6. Operational | Defined | Tanks | 381244 |  |  | 381243.52 | 371727 | 9517 | Yellow | 50000 |  | 50000 | 331244 |  |  | 188000 |  |  | 188000 | Phase | 188000 | 460779 |  | 460779 | No | Green | 2022-10-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2023-03-31 |  |  | 238158.62 | 125848.22 | 7719.79 | 9516.89 |  |  | 9517 | Red | [11 empty] | 3/9/2023 Completed ahead of schedule; phase 2 afe to be submitted. 1/5/2023 contractor availability issue. | 2023-03-09 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Roseton and Rensselaer | BETQE - BET RENSSELAER TERMINAL |  | 371727 | 9517 |  |  | 79535 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41322 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Rensselaer Terminal Piping Daylight 2023 | Item | Open | MCAP | BETQE00M2302 | Maintenance Framework | 2095004 | Wing, Hunter | East | 3. Active | Defined | Facility Integrity | 174850 | 241000 |  | 415849.88 | 426733 | -10883 | Yellow | 238000 |  | 238000 | 177850 |  |  | 426733 |  |  | 426733 | Full | 426733 | 174850 | 241000 | 415850 | No | Green | 2023-04-01 | 2023-04-19 | 2023-04-19 | 2023-05-22 | 2023-07-31 | [5 empty] | 174849.88 | 220000 | 220000 | -45150 | Red |  | Contractor/Vendor Issue | 156000 | 85000 | 0 | [6 empty] | 5/1/2023 - HJW - Project is underway. 60%-70% of SOW is completed. Expected to be completed by end of May. Missed forecast due to delay with steel supports, materials, weather, and contractor production. Forecast has been updated to represent corrected forecast. 4/3/2023-PO imminent. Planning to start week of 4/10. 2.2.2023 - HW - Site Walkdown completed with operations on 1.30.23. Execution Plan is being developed and a bid event is expected to start before the end of the month. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Roseton and Rensselaer | BETQE - BET RENSSELAER TERMINAL |  |  | 415850 | 0 |  |  |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 45883 |  | Clark, David | Independent | Aqua | 2022-09-21 | Int - Planned Corr & FI
Replace AC Power and AC Disconnects to BH Rectifiers | Item | Open | MEXP | BH00000E2203 | Maintenance Framework | 2014070 | Gable, Rob | East | 7. Closed | Drawdown | Cathodic Protection | 4296 |  |  | 4296.12 | 4296 | 0 | Green |  |  |  | 4296 |  |  | 37000 |  |  | 37000 | Full | 37000 | 36021 |  | 36021 | No | Green | 2022-10-01 | 2022-08-31 | 2022-08-31 | 2022-11-30 | 2022-12-31 |  |  | 4296.12 | [18 empty] | 1/10/2023 - Closed WO/PO and set OPPM project status to 'Closed'. MCS 1/4/2023 RAG - Ready to close, no other invoices expected. 12/2/2022 RAG - Work performed by M&M Electrical. 11/3/2022 RAG - M&M scheduled to start work in Nov. 10/4/2022 RAG - PO's Issued, awaiting schedule form M&M Electrical. Ordering materials which will receive in Oct, labor in Nov. 9/6/2022 RAG - Scheduling M&M Electrical. | 2023-02-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Corrosion |  | Booth | BH - BOOTH STATION |  | 4296 | 0 |  |  | 31725 |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 45734 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-08-31 | Int - Planned Corr & FI
Replace Rectifier E-12B Macungie Station South Yard | Item | Open | MCAP | ZG00000M2303 | Maintenance Framework | 2085645 | Gable, Rob | East | 3. Active | Defined | Cathodic Protection | 8528 | 26500 |  | 35027.84 | 35000 | 28 | Yellow | 35000 |  | 35000 | 28 |  |  | 35019 |  |  | 35019 | Full | 35019 | 8528 | 26500 | 35028 | No | Green | 2023-04-01 | 2023-02-21 | 2023-02-21 | 2023-09-30 | 2023-07-31 | [5 empty] | 8527.84 | 5000 | 5000 | 3528 | Red |  | WorkAhead of Schedule |  | 16500 | 5000 |  | 5000 |  |  |  |  | 5/2/2023 RAG - Materials purchased ahead of schedule. 4/4/2023 RAG - PO's have been issued. Rectifier scheduled to be delivered during May. 3/2/2023 RAG - Awaiting quotes from Diefenderfer and JA Electronics. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 25028 | 10000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45418 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
RG714SN US 422 Relocation | Item | Open | MCAP | RG714SNM2201 | Maintenance Framework | 2046374 | Taylor, Ryan | East | 3. Active | Defined | Pipeline Digs | 84007 | 3515000 |  | 3599006.93 | 3610004 | -10997 | Yellow |  |  |  | 3599007 |  |  | 138635 |  |  | 138635 | Phase | 138635 | 92757 | 3515000 | 3607757 | No | Green | 2022-12-01 | 2023-03-10 | 2023-03-10 | 2023-08-01 | 2023-10-01 |  |  | 9082.5 | 15196.68 | 30724.85 | 29002.9 | 40000 | 40000 | -10997 | Red |  |  | 15000 |  |  | 1750000 | 1750000 |  |  |  |  | 20230309 - RJT - Updated project start. 2/28/2023 - RJT Forecast updated. | 2023-04-11 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Macungie Pipe | RG714SN - TUCKERTON-SINKING SPRING |  | 55004 | 44003 | 3500000 |  | 8750 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46249 |  | Guest, ProSight | Independent | Aqua | 2022-11-18 | Int- Planned Digs
Richmond North (BSEVA) Tank 55 OOS Corrosion Inspection and Refurb | Item | Open | MCAP | BSEVA00M2202 | Maintenance Framework | 2013349 | Yoder, Michael | East | 6. Operational | Defined | Tanks | 75905 |  |  | 75905.37 | 75905 | 0 | Yellow |  | 64000 | 64000 | 11905 |  |  | 250000 | 64000 |  | 314000 | Phase | 314000 | 311160 |  | 311160 | No | Green | 2022-10-01 | 2022-08-25 | 2022-08-25 | 2022-12-31 | 2023-01-31 |  |  | 38413.44 | 2167.22 | 29.75 | 35294.96 | 35295 | 35295 | 0 | Yellow | [11 empty] | Plan to close in June. 5/2/23 - Phase 2 AFE approved. Final disposal invoice paid. 4/4/23 - Awaiting final disposal invoice. May need phase 2 AFE. 3/1/23 - Waste Management still working on finding a disposal facility for the ethanol load. Will likely need phase 2 AFE to cover costs. 2/1/23 - Tank returned to service. 1/3/2023 - Tank repairs complete. Plan to button up and return to service mid-January. Variance due to holidays. 12/2/2022 - Tank cleaned and inspected. Repairs in progress. 11/1/2022 - Piping in progress. Tank cleaning mid-November. 10/4/2022 - Plan to start piping mods late-October. 9/2/2022 - Phase 1 AFE approved. Plan to start in October. 8/1/2022 - Plan to submit phase 1 AFE in August. 6/9/22 - Pushed forecast to September. Extension granted from state to push OOS due date to 11/30. 6-1-22 - Pushed forecast to start in July. Plan to finalize OOS date once acquisition is complete. 5.10.22.DLC: Initial Forecast | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Virginia | BSEVA - RICHMOND TERMINAL |  | 40610 | 35295 |  |  | 235254 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 43535 |  | Stine, Carlton | Independent | Aqua | 2022-04-25 | Int - Tanks
Richmond South Fire Line Pipe Replacement 2023 | Item | Open | MCAP | BETRH00M2304 | Maintenance Framework | 2112820 | Weirsky, Edward | East | 3. Active | Drawdown | Fire Protection |  | 150000 |  | 150000 |  | 150000 | Red |  | 157950 | 157950 | -7950 |  |  | 157950 |  |  | 157950 | Full | 157950 |  | 150000 | 150000 | No | Green | 2023-05-01 | 2023-04-27 | 2023-04-27 | 2023-05-05 | 2023-06-30 | [12 empty] | 100000 | 50000 | [7 empty] | 5/1/23 RLO Project Transferred to Ed Weirsky | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Virginia | BETRH - BET RICHMOND |  |  | 150000 |  |  |  |  | Jakubowski, Gregory | Blow, Andrew |  |  | 1 | 46982 |  | Orischak, Bob | Independent | Aqua | 2023-04-25
Richmond Terminal (BETRH) Tank 2 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | BETRH00M2302 | Maintenance Framework | 2086167 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 396163 |  | 396163 | 396163 | 0 | Green | 396163 |  | 396163 | 0 |  |  | 182343 |  |  | 182343 | Phase | 182343 |  | 396163 | 396163 | No | Green | 2023-10-01 | 2023-02-24 | 2023-02-24 | 2023-12-31 | 2023-12-31 | [17 empty] | 96163 | 150000 | 150000 |  |  |  | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Virginia | BETRH - BET RICHMOND |  |  | 0 |  | 396163 |  |  | Stine, Carlton |  |  |  | 1 | 44874 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Richmond Terminal (BETRH) Tank 24 - OOS API 653 + Seal Insp & Refurb | Item | Open | MEXP | BETRH00E2301 | Maintenance Framework | 2084408 | Yoder, Michael | East | 6. Operational | Defined | Tanks | 173921 | 12000 |  | 185920.6 | 282000 | -96080 | Red | 282000 |  | 282000 | -96079 |  |  | 154880 |  |  | 154880 | Phase | 154880 | 173921 | 12000 | 185921 | No | Green | 2023-03-01 | 2023-02-02 | 2023-02-02 | 2023-06-30 | 2023-04-30 |  |  |  |  | 90000.18 | 83920.42 | 126000 | 126000 | -42080 | Red |  | WorkAhead of Schedule | 12000 | [8 empty] | 5/2/23 - Tank returned to service. April variance due to completing ahead of schedule and repair costs less than estimated. Reduced May forecast and EAC. Preparing phase 2 AFE for submission. 4/4/23 - Tank cleaned and inspected. Tank repairs to start 4/17. Plan to submit phase 2 AFE once quotes received from repair contractor. 3/3/2023-Cleaning to start 3/6. 2/1/23 - Plan to take OOS late-February / early-March. 9/23/22-CES-Bottom in good condition at last inspection and seals replaced. Anticipating minor repairs. removing $47,000 in forecast. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Virginia | BETRH - BET RICHMOND |  | 90000 | 95920 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44875 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Richmond Terminal (BETRH) Tank 26 - OOS Corr + Seal Insp & Refurb | Item | Open | MEXP | BETRH00E2202 | Maintenance Framework | 1937924 | Yoder, Michael | East | 6. Operational | Defined | Tanks | 21205 |  |  | 21204.75 | 21205 | 0 | Green |  |  |  | 21205 |  |  | 170000 | 142000 |  | 312000 | Phase | 312000 | 307948 |  | 307948 | No | Green | 2022-08-01 | 2022-01-05 | 2022-01-05 | 2022-12-31 | 2022-12-31 |  |  | 20321.75 | 883 | [17 empty] | 4/4/23 - Phase 2 AFE approved. 3/1/23 - Moved 4k to March for Magnetrol install. They had to be sent back to factory to fit the correct flange. Preparing phase 2 AFE for submission. 2/1/23 - Variance due to additional piping costs. Preparing phase 2 AFE for submission. 1/4/23 - Tank returned to service. Preparing phase 2 AFE for submission. Added 10k to February forecast for new Magnetrol receipt and install. 12/2/22 - Tank repairs complete. Plan to button up and RTS mid-December. 11/1/22 - Tank repairs in progress. Liner needs significant repairs. Updated forecast. Preparing phase 2 AFE for submission. 10/4/22 - Tank isolated and cleaned. Inspection in progress. 9/2/22 - Plan to set legs and start cleaning late-September. Variance for prep work. 7/6/2022 - Planned for September start. | 2023-04-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Virginia | BETRH - BET RICHMOND |  | 21205 | 0 |  |  | 286743 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41325 |  | Administrator, System | JDE Child | Burnt Orange | 2021-08-09 | Int - Tanks
Richmond VRU Release Prevention | Item | Open | MCAP | BETRH00M2301 | Maintenance Framework | 2076605 | Pepe, David | East | 3. Active | Defined | Vapor Management | 26704 | 25000 |  | 51703.77 | 50348 | 1356 | Yellow | 50000 |  | 50000 | 1704 |  |  | 50533 |  |  | 50533 | Full | 50533 | 26704 | 25000 | 51704 | No | Green | 2023-03-01 | 2023-01-23 | 2023-01-23 | 2023-04-01 | 2023-08-31 |  |  |  |  | 10348 | 16355.77 | 40000 | 40000 | -23644 | Red |  | Buckeye/Customer Schedule | 25000 | [8 empty] | 5/1/2023 - DJP - Material arrived on site in late March and the mechanical contractor has taken measurements to shop fabricate the spool. the electrical contractor has installed the conduuit. Shcheduled downtime for the rack on May 17th. 3/1/2023 - AFE approved, equipment on order, copntractor proposal received. Ontrack for April completion. 2/3/2023 - Met with contractor, material will be ordered shortly. 1/12/2023 DJP AFE submitted 1/11/2023 DJP updated forecast, based on material delivery, 12/9/2022 DJP will complete in 1Q2023. getting material quotes. | 2023-05-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Virginia | BETRH - BET RICHMOND |  | 10348 | 41356 |  |  |  |  | Karl, Marissa | Orischak, Bob |  |  | 1 | 44948 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Other Programs
Ridley Park Turbine Meter Repair | Item | Open | MEXP | RJ00000E2301 | Maintenance Framework | 2083618 | Wing, Hunter | East | 6. Operational | Drawdown | Electrical | 12398 | 2001 |  | 14399.33 | 22399 | -8000 | Red |  |  |  | 14399 |  |  | 30000 |  |  | 30000 | Full | 30000 | 12398 | 2001 | 14399 | No | Green | 2023-03-01 | 2023-02-21 | 2023-02-21 | 2023-03-13 | 2023-03-10 |  |  |  |  | 12398.33 |  | 10000 | 10000 | -10000 | Red |  | Forecasting | 2000 | [6 empty] | 1 |  | 5/1/2023 - HJW - Assigned PM working to finish JB with information provided to the PM from the execution PM. No updated on any additional charges to hit the project. Will allow one more cycle before moving to close. 4/4/2023 - Project is completed (on 3/10/2023), forecasting 10K in possible trailing spend. . 2/22/23 RLO Project Just approved. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Malvern | RJ - RIDLEY PARK - BPLT |  | 12398 | 2000 |  | 1 |  |  | Ashley, Robert | Tench, David | N/A |  | 1 | 46612 |  | Orischak, Bob | JDE Child | Burnt Orange | 2023-02-17
RJ740MX Sinkhole Evaluation | Item | Open | MEXP | XX740MXE2201 | Maintenance Framework | 2003601 | Karl, Marissa | East | 7. Closed | Drawdown | Exposed Pipe Evaluation & Remediation | -147 |  |  | -146.9 | -147 | 0 | Green |  |  |  | -147 |  |  | 10000 |  |  |  | Full | 10000 | 16314 |  | 16314 | No | Green | 2022-10-01 |  |  | 2022-08-31 | 2022-09-30 |  |  | -146.9 | [18 empty] | 111/2/2022 - mrk -project is complete, waiting on $2,100 invoice from vendor. 10/27/2022 - Per Marissa Karl today 'This should be marked operational at this time, waiting on one invoice.'. Changed project status to 'Operational'. - M. Sautter. 10/10/222 - 26k was a missed accrual. Added to October forecast as we expect invoice to come in october. Field inspection completed August, Report expected to be received October. 9/12/22 - $16,900 added to September from MEXP Drawdown - Pipeline per request from Shook and Karl (AS) 9/6/2022-Likely to not complete this year due to PM workload. 8/2/22 Didn't realize I was going to manage this project. | 2022-11-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Pipeline Integrity |  | Malvern | XX740MX - NJ S/L TO MALVERN |  | -147 | 0 |  |  | 16461 |  | Hurley, Brian | Shook, Mark B. | N/A |  | 1 | 44204 |  | Hurley, Brian | JDE Child | Burnt Orange | 2022-07-22 | Int - Exposure Evals
Roanoke I (BSEVR) Tank 20-7 - OOS API 653 + Seal Insp & Refurb | Item | Open | MEXP | BSEVR00E2301 | Maintenance Framework | 2093472 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 270000 |  | 270000 | 270000 | 0 | Green | 270000 |  | 270000 | 0 |  |  | 169950 |  |  | 169950 | Phase | 169950 |  | 270000 | 270000 | No | Green | 2023-05-01 | 2023-03-01 | 2023-03-01 | 2023-12-31 | 2023-12-31 | [12 empty] | 75000 | 145000 | 50000 | [6 empty] | 5/2/23 - Set IFR cables to high position. Preparing to MT, isolate and clean tank around 5/15. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Virginia | BSEVR - ROANOKE TERMINAL |  |  | 220000 | 50000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44876 |  | Administrator, System | JDE Child | Burnt Orange | 2022-08-17 | Int - Tanks
Roanoke I (BSEVR) Tank 40-2 - OOS API 653 + Seal Insp & Refurb | Item | Open | MEXP | BSEVR00E2302 | Maintenance Framework | 2093474 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 295000 |  | 295000 | 295000 | 0 | Green | 295000 |  | 295000 | 0 |  |  | 164450 |  |  | 164450 | Phase | 164450 |  | 295000 | 295000 | No | Green | 2023-09-01 | 2023-03-01 | 2023-03-01 | 2023-12-31 | 2023-12-31 | [16 empty] | 95000 | 125000 | 75000 |  |  | 9/23/22-CES-Reducing mechanical repair budget to reflect anticipated minor repairs. | 2022-09-23 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Virginia | BSEVR - ROANOKE TERMINAL |  |  | 0 | 95000 | 200000 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44877 |  | Administrator, System | JDE Child | Burnt Orange | 2022-08-17 | Int - Tanks
Roanoke Terminal (BSEUH) Out of Service Support Project | Item | Open | MEXP |  | Maintenance Framework |  | Yoder, Michael | East | 1. Proposed |  | Tank Outage |  | 0 |  | 0 | 0 | 0 | Green | 100000 |  | 100000 | -100000 | [9 empty] | 0 | 0 | No | Green |  |  |  |  | 2023-06-30 | [12 empty] | 0 | 0 | [7 empty] | 4/4/23 - Zeroed out forecast since it was determined that no piping mods are required for tank change of service. | 2023-04-04 |  |  | East | Pipelines and Terminals | Tank Integrity |  | Virginia | BSEVR - ROANOKE TERMINAL |  |  | 0 |  |  |  |  | Stine, Carlton |  |  |  | 1 | 44756 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Rochester air to ground coating replacement | Item | Open | MCAP | RQ00000M2301 | Maintenance Framework | 2086686 | Norton, Bill | East | 3. Active | Defined | Atmospheric Corrosion |  | 25000 |  | 25000 | 25000 | 0 | Green | 25000 |  | 25000 | 0 |  |  | 25048 |  |  | 25048 | Full | 25048 |  | 25000 | 25000 | No | Green | 2023-07-01 | 2023-02-27 | 2023-02-27 | 2023-10-01 | 2023-11-30 | [14 empty] | 25000 | [8 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | RQ - ROCHESTER TERMINAL |  |  | 0 | 25000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44354 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
Rochester North - Replace Cast Iron Pump P4 | Item | Open | MCAP | BETRC00M2301 | Maintenance Framework | 2052233 | Pepe, David | East | 3. Active | Defined | Rotating Equipment |  | 87000 |  | 87000 | 87000 | 0 | Green | 95000 |  | 95000 | -8000 |  |  | 79702 |  |  | 79702 | Interim | 79702 |  | 87000 | 87000 | No | Green | 2023-05-01 | 2023-01-09 | 2023-01-09 | 2023-07-01 | 2023-07-31 | [6 empty] | 12000 | 12000 | -12000 | Red |  | Supply Chain | 12000 | 75000 | [7 empty] | 5/4/2023-Pump now shipped. 4/1/2023-Expecting pump on site in April 1/4/2023 - Pump doesn't arrive until April 2023, the VFD will come in June, expecting construction in July. 12/19/2022 DJP Interim Approved and long lead pump requisitioned. 12/9/2022 DJP submitted interim AFE for order of pump and new drive before the end of the year to obtain favorable pricing and delivery. | 2023-05-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BETRC - BET ROCHESTER N TERMINAL AGWAY |  |  | 87000 |  |  |  |  | Posipanko, Dan | Posipanko, Daniel A. |  |  | 1 | 44123 |  | Guest, ProSight | Independent | Aqua | 2022-07-13 | Other Programs
Rochester North - Replace Cast Iron Pump P8 | Item | Open | MCAP | BETRC00M2302 | Maintenance Framework | 2052876 | Pepe, David | East | 3. Active | Defined | Rotating Equipment | 1015 | 82000 |  | 83015.38 | 83015 | 0 | Green | 95000 |  | 95000 | -11985 |  |  | 79702 |  |  | 79702 | Full | 79702 | 1015 | 82000 | 83015 | No | Green | 2023-02-01 | 2023-02-15 | 2023-02-15 | 2023-07-01 | 2023-05-31 |  |  |  | 1015.38 |  |  | 12000 | 12000 | -12000 | Red |  | Supply Chain | 12000 | 70000 | [7 empty] | 5/4/2023-Pump now shipped. 4/1/2023-Expecting pump on site in April 1/4/2023 - Pump doesn't arrive until April 2023, the VFD will come in June, expecting construction in July. 12/19/2022 DJP Interim Approved and long lead pump requisitioned. 12/9/2022 DJP submitted interim AFE for order of pump and new drive before the end of the year to obtain favorable pricing and delivery. | 2023-05-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BETRC - BET ROCHESTER N TERMINAL AGWAY |  | 1015 | 82000 |  |  |  |  | Posipanko, Dan | Posipanko, Daniel A. |  |  | 1 | 44124 |  | Guest, ProSight | Independent | Aqua | 2022-07-13 | Other Programs
Rochester North (BETRC) - Secondary containment upgrades for double wall tank and additive tank | Item | Open | MCAP |  | Maintenance Framework |  | Wing, Hunter | East | 1. Proposed |  | Secondary Containment |  | 55000 |  | 55000 | 55000 | 0 | Green | 55000 |  | 55000 | 0 | [9 empty] | 55000 | 55000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 55000 | [6 empty] | 5/1/2023 - HJW Pending final SOW. Expected to be only a spill kit needed for SOW. AFE may be significantly smaller than originally proposed. Once Environmental and Program owner have approved the plan, AFE will be submitted. 3.14.23 - HW - Working with HSSE to determine what is needed for this project. 2.2.23 - Walkdown completed with operations of 1.31.23 of additive area. Work Plan to be developed this month with the work expected to start this summer when Diesel sales are slower. | 2023-05-01 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BETRC - BET ROCHESTER N TERMINAL AGWAY |  |  | 0 | 55000 |  |  |  | Clark, Dave |  |  |  | 1 | 45165 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
Rochester RC Rotork Valve Operator Upgrades | Item | Open | MCAP | RC00000M2201 | Maintenance Framework | 1946280 | Mohr, David | East | 3. Active | Defined | Valves | 5923 | 12000 |  | 17923.38 | 17635 | 288 | Yellow | 62000 |  | 62000 | -44077 |  |  | 68000 |  |  | 68000 | Full | 68000 | 60717 | 12000 | 72717 | No | Green | 2022-02-01 | 2022-02-08 | 2022-02-08 | 2022-07-31 | 2023-05-31 |  |  | 4208.97 | 435.22 | 990.75 | 288.44 | 12000 | 12000 | -11712 | Red |  | Buckeye/Customer Schedule | 12000 | [8 empty] | 5/1/2023 Variance due to techs schedule and other project loading. 4/1/2023 Installation progressing. 3/1/2023 There was a bug in the actuator firmware and Rotork is onsite this week to correct. Installation to follow. DRM 1/3/2023-Technicians to schedule installation of valves when weather improves. 12/1/2022 Variance due to receiving material early.9/2/2022 - Valve actuators have been ordered, and money forecasted for 2023 for that material and installation. 8/3//2022 Valve actuators have been ordered, but not expected this year due to supply chain issue. Moved balance to 4/2023. DRM 4/2/2022 - Actuators expected in 8 weeks. 3/1/2022 DRM Actuators have been ordered and have 12 week lead time. 2/2/2022 Received updated quote from vendor AFE to follow. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Pipeline | RC - ROCHESTER TERMINAL |  | 5635 | 12288 |  |  | 54794 |  | Oey, Alex | Campion, Tom |  |  | 1 | 34133 |  | Guest, ProSight | Independent | Aqua | 2019-08-19 | Other Programs
Rochester South Terminal - Tank Alarm Replacement | Item | Open | MCAP | BETRQ00M2301 | Maintenance Framework | 2084754 | Mohr, David | East | 3. Active | Defined | Instrumentation & Controls |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 |  |  | 50336 |  |  | 50336 | Full | 50336 |  | 50000 | 50000 | No | Green | 2023-07-01 | 2023-02-16 | 2023-02-16 | 2023-07-31 | 2023-09-30 | [14 empty] | 20000 | 20000 | 10000 |  |  |  |  | 5/1/2023-Material is on order. 4/1/2023 Issue with PO to vendor. Corrected and now on order. 3/1/2023 Material on order with vendor. DRM 2/2/2023 Reached out to asset team for update and assistance | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BETRQ - BET ROCHESTER S TERMINAL XOM |  |  | 0 | 50000 |  |  |  | Forsey, Frank | Tracey, Steve |  |  | 1 | 37631 |  | Guest, ProSight | Independent | Aqua | 2020-08-11 | Other Programs
Rochester South Terminal (BETRQ) Tank 31 – OOS Seal Inspection | Item | Open | MCAP | BETRQ00M2201 | Maintenance Framework | 1937284 | Yoder, Michael | East | 6. Operational | Defined | Tanks | 14135 |  |  | 14135.45 | 13758 | 377 | Yellow |  |  |  | 14135 |  |  | 186000 | 212000 |  | 186000 | Full | 398000 | 380688 |  | 380688 | No | Green | 2022-07-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-11-30 |  |  | 4883.63 | 490.36 | 8384.17 | 377.29 |  |  | 377 | Red | [11 empty] | 4/4/23 - Phase 2 AFE approved. Variance due to not receiving invoice from cleaning contractor. Plan to update forecast once issue is resolved. 3/1/23 - Variance due to still working with vendor on final invoice amount. Moved 25k to March. Preparing Phase 2 AFE for submission. 2/1/23 - Variance due to internal labor. Added 25k to Feb forecast for estimated vendor payment. Preparing phase 2 AFE for submission. 1/4/23 - Variance due to additional piping mods. Preparing phase 2 AFE for submission. 12/2/22 - Preparing to return tank to service. Variance due to work ahead of schedule. Preparing phase 2 AFE for submission. 11/1/22 - Tank repairs in progress. Repair scope less than budgeted. Reduced forecast. 10/4/22 - Tank cleaning in progress. 9/2/22 - Plan to take OSS late-September. 8/2/2022 - July variance for coating work. 7/6/2022 - Planned for September start. | 2023-04-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Terminals | BETRQ - BET ROCHESTER S TERMINAL XOM |  | 13758 | 377 |  |  | 366552 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41326 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Rochester South Terminal (BETRQ) Tank 38 Flip to MEXP | Item | Open | MEXP | BETRQ00E2103 | Exempt | 1909779 | Yoder, Michael | East | 7. Closed | Emergent | Tanks | 14 |  |  | 13.86 | 14 | 0 | Green |  |  |  | 14 |  |  | 39000 |  |  | 39000 | Full | 39000 | 33161 |  | 33161 | No | Green | 2021-11-01 | 2021-11-16 | 2021-11-16 | 2021-12-31 | 2021-12-31 |  |  | 13.86 | [18 empty] | 3/29/2022 - Closed WO/PO, set OPPM status to 'Closed'. MCS can close. 1/4/2022 - Variance due to flip to expense hitting November business. No further spend. Changed status to operational. 12/2/2021 - Flip to expense submitted but has not yet hit project. | 2022-03-29 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Auburn Terminals | BETRQ - BET ROCHESTER S TERMINAL XOM |  | 14 | 0 |  |  | 14 |  | Stine, Carlton |  |  |  | 1 | 42422 |  | Meitzler, Antoinette | Independent | Aqua | 2021-11-11 | Int - Tanks
Rochester Station (RC) Tank A-001 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | RC00000E2301 | Maintenance Framework | 2093482 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 |  |  | 11000 |  |  | 11000 | Phase | 11000 |  | 10000 | 10000 | No | Green | 2023-06-01 | 2023-03-01 | 2023-03-01 | 2023-12-31 | 2023-12-31 | [13 empty] | 10000 | [9 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Auburn Pipeline | RC - ROCHESTER TERMINAL |  |  | 10000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44878 |  | Administrator, System | JDE Child | Burnt Orange | 2022-08-17 | Int - Tanks
Rochester terminal painting | Item | Open | MCAP | RC00000M2301 | Maintenance Framework | 2083814 | Norton, Bill | East | 3. Active | Defined | Atmospheric Corrosion |  | 25000 |  | 25000 | 25000 | 0 | Green | 25000 |  | 25000 | 0 |  |  | 25000 |  |  | 25000 | Full | 25000 |  | 25000 | 25000 | No | Green | 2023-08-01 | 2023-02-02 | 2023-02-02 | 2023-10-01 | 2023-11-30 | [12 empty] | 0 |  |  | 25000 | [5 empty] | 5/2/2023-Contractor is currently an F is Isnetworld (wrongly, something in the automated system) - Work may occur in either May or June. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | RC - ROCHESTER TERMINAL |  |  | 0 | 25000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44352 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
Rochester West Priority 3 API 570 Refurbishments | Item | Open | MCAP |  | Maintenance Framework |  | Keppel, Nicholas | East | 1. Proposed |  | Facility Integrity |  | 109000 |  | 109000 | 109000 | 0 | Green | 109000 |  | 109000 | 0 | [9 empty] | 109000 | 109000 | No | Green | 2023-08-01 |  |  |  | 2023-09-30 | [15 empty] | 75000 | 34000 | [8 empty] | East | Pipelines and Terminals | Integrity |  | Auburn Terminals | BRTQR - BRT ROCHESTER WEST TERMINAL |  |  | 0 | 109000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45053 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Rochester West Pump Rebuild 2023 | Item | Open | MEXP | BRTQR00E2301 | Maintenance Framework | 2119783 | Orischak, Bob | East | 3. Active | Drawdown | Rotating Equipment |  | 30001 |  | 30001 |  | 30001 | Red |  | 30000 | 30000 | 1 |  |  | 31000 |  |  | 31000 | Full | 31000 |  | 30001 | 30001 | No | Green | 2023-06-01 | 2023-05-01 | 2023-05-01 | 2023-05-24 | 2023-05-24 | [13 empty] | 30000 | [5 empty] | 1 | [5 empty] | East | Pipelines and Terminals | Station/Terminal |  | Auburn Terminals | BRTQR - BRT ROCHESTER WEST TERMINAL |  |  | 30000 |  | 1 |  |  | Posipanko, Dan | Tracey, Steve | N/A |  | 1 | 47006 |  | Orischak, Bob | JDE Child | Burnt Orange | 2023-05-01
Roseton Air to ground coating phase 2 | Item | Open | MCAP | BETQO00M2301 | Maintenance Framework | 2085654 | Norton, Bill | East | 3. Active | Defined | Atmospheric Corrosion |  | 45000 |  | 45000 | 45000 | 0 | Green | 45000 |  | 45000 | 0 |  |  | 45435 |  |  | 45435 | Full | 45435 |  | 45000 | 45000 | No | Green | 2023-09-01 | 2023-02-21 | 2023-02-21 | 2023-11-01 | 2023-11-30 | [16 empty] | 45000 | [6 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Roseton and Rensselaer | BETQO - BET ROSETON TERMINAL |  |  | 0 | 45000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44347 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
Roseton and Rensselaer terminals atmospheric inspection | Item | Open | MEXP | 1348250E2311 | Maintenance Framework |  | Norton, Bill | East | 8. Canceled |  | Atmospheric Corrosion |  | 25000 |  | 25000 | 25000 | 0 | Green | 25000 |  | 25000 | 0 | [9 empty] | 25000 | 25000 | No | Green | 2023-10-01 |  |  |  | 2023-11-30 | [17 empty] | 25000 |  |  |  | 3/2/2023 - Project is cancelled due to being funded through Local Operations Budget. | 2023-03-02 |  |  | East | Pipelines and Terminals | Corrosion |  | Roseton and Rensselaer | BETQE - BET RENSSELAER TERMINAL |  |  | 0 |  | 25000 |  |  | Geib, Rob |  |  |  | 1 | 44348 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
Roseton Driveway Rebuild at Gate | Item | Candidate | MCAP |  | Maintenance Framework |  | Schwindt, Joseph | East | 1. Proposed |  | East |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 | [9 empty] | 40000 | 40000 | No | Green | 2023-06-01 |  |  |  | 2023-06-30 | [13 empty] | 40000 | [7 empty] | 5/3/23 - Quotes recieved significantly greater than budget. Will revisit scope and look to lower cost closer to budget. 4/3/2023 - Trying to get quotes. | 2023-05-03 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Roseton and Rensselaer | BETQO - BET ROSETON TERMINAL |  |  | 40000 |  |  |  |  | Orischak, Bob |  | N/A |  | 1 | 25096 |  | Guest, ProSight | Independent | Aqua | 2017-08-21 | Other Programs
Roseton Garage Bathroom Refurbishment | Item | Candidate | MCAP |  | Maintenance Framework |  | Schwindt, Joseph | East | 8. Canceled |  | East |  |  |  | 0 | 0 | 0 | Green | 30000 |  | 30000 | -30000 | [11 empty] | No | Green |  |  |  |  | 2023-04-30 | [6 empty] | 0 | 0 | 0 | Green | [11 empty] | 3/29/23: Project can be cancelled. Per Steve Tracey the septic system associated with this bathroom has been taken out of service (filled with concrete). | 2023-03-29 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Roseton and Rensselaer | BETQO - BET ROSETON TERMINAL |  |  | 0 |  |  |  |  | Orischak, Bob |  |  |  | 1 | 37122 |  | Guest, ProSight | Independent | Aqua | 2020-07-16 | Other Programs
Roseton Pile Wraps | Item | Open | MCAP | BETQO00M2105 | Maintenance Framework | 1876289 | Wojton, Brian | East | 3. Active | Defined | Marine | 3513 | 666200 |  | 669712.85 | 666262 | 3451 | Yellow | 700000 |  | 700000 | -30287 |  |  | 199000 |  |  | 199000 | Phase | 199000 | 126500 | 666200 | 792700 | No | Green | 2022-02-01 | 2021-08-02 | 2021-08-02 | 2021-12-31 | 2023-09-30 |  |  | -42862.5 | 23458.97 | 19465.56 | 3450.82 |  |  | 3451 | Red |  |  | 25000 | 25000 | 100000 | 200000 | 300000 | 16200 |  |  |  | 4/25/2023 - awarded PO to Bowman to begin scope and detail preparation for priorities identified on dock recent dock inspection report. 3/3/2023 Project reassigned to Brian; cleaning up old invoices. 2/3/2023 invoices didn't hit project yet. 01.13.23 SDB: Proposal for RFP documentation and repair procedures received. 01.05.23 SDB: Inspection report received and under initial review. 01.03.23 SDB: Draft inspection report received and under review. 11.25.22 SDB: Anchor Consultants completed the inspection and will be sending their report. 11.10.22 SDB: Anchor Consultants dive inspection rescheduled for 11/14-15.10.17.22 SDB: Anchor consultants scheduled the dive inspection for 10/24 and 25. Plans approved by Ops/Safety/Scheduling.10.5.22 SDB: Anchor consultants is scheduling their inspection for Roseton.9.30.22 TN - 700k is forecasted for 2023 9.27.22 SDB: Anchor Consultants received their PO for Inspection work.9.21.22 SDB: Full AFE was submitted in 7/14/21 for $199k. These funds will be used to complete the inspections, repair procedures and bid documents for the project in order to go through the bid process. Work is scheduled in 2023. 9.16.22 SDB: Anchor Consultants to receive a PO for the routine inspection of the marine structures.9.9.22: 2023 carryover 700K9.2.22 SDB: Proposal received from Anchor Consultants. Presently under review.8.22.22 SDB: Upper management agreed and a new detailed inspection and revised repair method will be requested from a different engineering firm. Work is deferred until this process is completed.8.15.22 SDB: Dive inspections completed and expecting repair procedures and proposal this week from KT marine this week.8.1.22 SDB: Dive inspection by KT Marine to start this week.7.25.22 SDB: Dive inspection by KT scheduled first week of August.7.8.22 SDB: KT presented proposal for an additional dive inspection in order to confirm or revise the repair procedures. PO was issued. Job and dive plans have been reviewed and approved. Inspection tentatively scheduled for the week of 07/25.6.10.22 SDB: LOI was sent and accepted by the winning contractor KT Marine.5.31.22 SDB: Bid process was extended and additional contractors were invited. Bid process was closed on 05/25 and weare presently reviewing proposals in order to award the work.5.2.22 SDB: Received proposals from bidding contractors. Will review proposals and schedules to determine award and issue PO.4/11/22 SDB: This projectis presently being bid out by supply chain. Bids due 3rd week of April.3.31.22 SDB: Supply chain scheduled to hold a bid process in the first half of April.2.18.22.DLC Bidding out with supply chain 1/3/22 Will look to have 3rd party pm do project as 2022 due to project work load. ek55076/2/21 Plan on scoping inmid to late June. ek55072/2/20 Will plan on scoping in May/June time frame. EK5507 | 2023-05-08 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | Roseton and Rensselaer | BETQO - BET ROSETON TERMINAL |  | 62 | 53451 | 600000 | 16200 | 122987 |  | Spari, Markella | Martin, David N. |  |  | 1 | 38026 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Marine
Roseton Priority 3 API 570 Refurbishments | Item | Open | MCAP |  | Maintenance Framework |  | Keppel, Nicholas | East | 1. Proposed |  | Facility Integrity |  | 82000 |  | 82000 | 82000 | 0 | Green | 82000 |  | 82000 | 0 | [9 empty] | 82000 | 82000 | No | Green | 2023-08-01 |  |  |  | 2023-09-30 | [15 empty] | 40000 | 42000 | [8 empty] | East | Pipelines and Terminals | Integrity |  | Roseton and Rensselaer | BETQO - BET ROSETON TERMINAL |  |  | 0 | 82000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45051 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Roseton replace Red Dye Tank | Item | Candidate | MCAP |  | Maintenance Framework |  | Yoder, Michael | East | 1. Proposed |  | Tanks |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 | [9 empty] | 50000 | 50000 | No | Green | 2023-07-01 |  |  |  | 2023-01-31 | [14 empty] | 50000 | [6 empty] | 5/1/23 - Preparing AFE for submission. 1/9/23 - Moved forecast to July since work to be performed outside of heating oil season. | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Roseton and Rensselaer | BETQO - BET ROSETON TERMINAL |  |  | 0 | 50000 |  |  |  | Stine, Carlton |  |  |  | 1 | 44646 |  | Guest, ProSight | Independent | Aqua | 2022-08-17 | Int - Tanks
Roseton Valve Pit and Pipeline Refurbishment FEED | Item | Open | MCAP | BETQO00M2104 | Maintenance Framework | 1867140 | Gebert, Clint | East | 5. Deferred | Defined | Facility Integrity |  | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 | [6 empty] | Interim |  | 732 | 30000 | 30732 | No | Green | 2021-07-01 |  |  |  | 2023-07-31 | [14 empty] | 30000 | [6 empty] | 5/3/2023-Working on planning the package for the railroad. 12/5/2022-Pulled in 2022, and relisted as a 2023 project. The current 2023 forecast of 30K is just to do a plan. 8/4/2021- Trying to figure out scope. 7/6/2021 - Scoping project out on Monday with asset team. 8/2/21-CGG- project was scoped with Asset Team. Project intent is pipe corrosion not necessarily concrete vault work. Further discussions are needed as to constructability and cost implications for this project. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Roseton and Rensselaer | BETQO - BET ROSETON TERMINAL |  |  | 0 | 30000 |  |  |  | Aiken, Elaine | Tracey, Steve | N/A |  | 1 | 25090 |  | Guest, ProSight | Independent | Aqua | 2017-08-21 | Int - Planned Corr & FI
RX751BO - DIG SHEETS (26) DOT-180 + (8) BPL-Other - Due 06-06-22 | Item | Open | MCAP | RX751BXM2201 | Maintenance Framework | 1946224 | Gebert, Clint | East | 6. Operational | Drawdown | Pipeline Digs | 23000 |  |  | 23000.04 | 23000 | 0 | Green |  |  |  | 23000 |  |  | 3844000 |  | 1343000 | 5187000 | Supplemental | 5187000 | 5004267 |  | 5004267 | No | Green | 2022-02-01 | 2022-04-01 | 2022-04-01 | 2022-06-06 | 2022-08-31 |  |  | 17600 | 5167.5 | 232.54 | [16 empty] | 3/7/2023 - Closed all PO's. However, was unable to close all the WO's ... 5 wouldn't let me due to 'Additional Data" -- WOs 1947210, 212, 213,219,239 3/3/23-Close PO's and anything to prevent charges to project.2/28/23-CGG-SUpplemental submitted. 2/3/2023-Variance due to trailing landscaping invoice. 12/52022-Supplemental will be submitted by Clint while he is on vacation. 9/6/2022-Project is complete now. Variance calculation looks wrong due to late-n-month forecast lowering by PMO? Actuals 232K, FC 96K, variance negative 117K. 8/3/22-CGG- Planning to put in a supplemental. Crew is on last site and should be complete next week Sept forecast is for moving mats, etc.. 7/6/2022 - Pipe condition and secondary features, will be requiring 11 crew-weeks of work. Gebert will discuss increase with Bartal. 6/2/22-CGG- DOT sites complete. Working on proximities over 40% CO. at sites with env. permits and long matted access. 5/4/2022-Project is ongoing. Due to condition onf line, difficult to forecast number of days per site. 4/5/22-CGG- Otis started earlier due to weather. I reviewed potential permit sites due to Kiely being inundated with Corporate reports for exposures. Several sites will not require permits as desk top review originally showed. 2 crews started in March in attempt to complete DOT sites by June Due date. 3/3/2022-Project scheduled to start April 1st.Desktop review currently being done for permitting. 2/3/2022 - Clint Gebert says the major spend will not start until March depending on weather in upstate NY. Possibility of small spend in Feb for Materials. | 2023-03-07 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | RX751BX - ROCHESTER JCT - BATAVIA STATIO |  | 23000 | 0 |  |  | 4981267 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 42642 |  | Guest, ProSight | Independent | Aqua | 2021-12-21 | Int- Planned Digs
RX751BO - Digs from 2022 GEO+MFL ILI | Item | Candidate | MCAP |  | Maintenance Framework |  | Gebert, Clint | East | 8. Canceled |  | Pipeline Digs |  | 0 |  | 0 | 0 | 0 | Green | 617000 |  | 617000 | -617000 | [9 empty] | 0 | 0 | No | Green |  |  |  |  | 2023-08-31 | [15 empty] | 0 | [5 empty] | 3/3/23 - removed forecast and marked as canceled. Work is being completed under other projects. | 2023-03-03 |  |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | RX751BX - ROCHESTER JCT - BATAVIA STATIO |  |  | 0 | 0 |  |  |  | Bartal, Nick |  |  |  | 1 | 42227 |  | Guest, ProSight | Independent | Aqua | 2021-09-28 | Int - Planned Cutouts
RX751BO 2022 Onstream Final Report Digs | Item | Open | MCAP | RX751BXM2301 | Maintenance Framework | 2075036 | Gebert, Clint | East | 3. Active | Drawdown | Pipeline Digs | 2389847 | 1530001 |  | 3919848.34 | 3749881 | 169967 | Yellow |  |  |  | 3919848 |  |  | 3981477 |  |  | 3981477 | Full | 3981477 | 2389847 | 1530001 | 3919848 | No | Green | 2023-01-01 | 2023-03-20 | 2023-03-20 | 2023-07-31 | 2023-12-31 |  |  | 121977.36 | 592632.42 | 955270.38 | 719967.18 | 550000 | 550000 | 169967 | Red |  |  | 550000 | 550000 | 430000 |  |  |  |  | 1 |  | 5/3/2023-Must finish in July. 4/10/23 - repairing additional features at dig sites. 3/3/23-CGG- Variance due to decision to not complete DOT dig in Oatka Creek. Scope change. This potentially eliminates around $637,000 in dig cost from the project. It is suspected that 2 other issued sites may have already been cut out on last year's purge. Future cost savings may result if confirmed. 2/3/2022- Variance is due to 2 weeks of work performed in January (Gebert wasn't able to put FC in because project did not appear on his forecast needed the 1$ FC) | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | RX751BX - ROCHESTER JCT - BATAVIA STATIO |  | 1669880 | 1819967 | 430000 | 1 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46451 |  | Meitzler, Antoinette | Independent | Aqua | 2023-01-11 | Int- Planned Digs
RX751BO Onstream DOT Immediate Digs | Item | Open | MCAP | RX751BXM2204 | Maintenance Framework | 2022744 | Gebert, Clint | East | 6. Operational | Drawdown | Pipeline Digs | 203091 |  |  | 203090.92 | 203091 | 0 | Green |  |  |  | 203091 |  |  | 1867000 |  |  | 1867000 | Full | 1867000 | 1211794 |  | 1211794 | No | Green | 2022-09-01 | 2022-12-11 | 2022-12-11 | 2022-12-31 | 2022-12-31 |  |  | 187268.78 | 15140.8 | 681.34 | [16 empty] | 3/7/2023 - Closed POs, but was unable to close 1 WO (need more data on APPURTEN for WO 2023095 -- F-0109613 ), I sclosed the others. MCS 3/2/2023-Can close. 2/3/2023-All sites complete, very little additional spend anticipated. Variance due to trailing costs, incl matting. 1/5/23-CGG- Permit not received for last site near a RR. Weather also was very wet. Work delayed until January 2023. Forecast also reduced.12/12/22-CGG- December forecast needs to be reduced to $300K. 12/5/2022-Variance due to severe snowstorm in upstate NY before T-giving. so lost 2 weeks worth of work. 10/10/22 - Variance due to project being identified after Sept forecast loc 10/24/22-CGG-Forecast updated to reflect a 2 crew approach. | 2023-03-07 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | RX751BX - ROCHESTER JCT - BATAVIA STATIO |  | 203091 | 0 |  |  | 1008703 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 45854 |  | Perry, Betty | Independent | Aqua | 2022-09-16 | Int- Planned Digs
RX751BO Purge and Multiple Cut Out Sites | Item | Open | MCAP | RX751BXM2202 | Project Framework | 1946223 | Gebert, Clint | East | 6. Operational | Defined | Pipeline Digs | 22018 |  |  | 22017.9 | 10615 | 11403 | Red |  |  |  | 22018 |  |  | 3090000 |  | 200000 | 3290000 | Supplemental | 3290000 | 3275935 |  | 3275935 | No | Green | 2022-02-01 | 2022-08-12 | 2022-08-12 | 2022-12-31 | 2022-11-30 |  |  | 7742.22 | 2748.98 | 123.7 | 11403 |  |  | 11403 | Red |  | Supply Chain | [9 empty] | 5/3/2023-Variance due to Rotork actuator ordered last year that just came in. 3/3/2023 -Supplemental submitted. Closed all POs except the untapped Tech Components OP-237728 $10,579 Rotork (requisitioner Marc Talomie) that was made on Jan 5. (ask Clint?). 2/3/2023-can close, project is complete and invoiced. 1/5/2023 - Trailing invoices for matting and rental invoices (trench boxes, etc). 12/5/2022-Project is operational, awaiting final invoices. 9/6/2022-All sites are prepped, and will be hydrotested next next week. 8/3/2022-Scope change-more pipe required than originally estimated. 7/23/22-CGG- Forecast updated for an 11 site cutout plan, duration of downtime may affect this assumption. ILI run was just completed on RX751BO and it is expected that digs will be issued. Purge will most likely be pushed back into October due to digs. 7/6/2022 - On track for Aug/Sep. Readiness review and TRC are done, so full AFE will be submitted. 6/2/2022 - Getting estimates. 5/4/2022-Mechanical Materials has arrived sooner than expected. Note: the summer forecast is a placeholder, and is expected to increase. 4/5/22-CGG- at this point this is a place holder from the 2021 project scope. This dollar amount and project should be viewed as a place holder and it is expected to have a increased scope of work based on upcoming tool results and the current policy changes regarding B sleeves. If this project moves forward it is anticipated to have a substantial increase in scope and cost. I will be prepping cut out sites utilizing crews currently performing digs on the same line section. 3/10/2022 - MCS - $61K PO cut to Raritan for seamless pipe,etc. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | RX751BX - ROCHESTER JCT - BATAVIA STATIO |  | 10615 | 11403 |  |  | 3253917 |  | Bartal, Nick | Tracey, Steve |  |  | 1 | 41810 |  | Bartal, Nick | Independent | Aqua | 2021-08-20 | Int - Planned Cutouts
RX751BXEP233913 Exposure Remediation | Item | Open | MCAP | RX751BXM2203 | Project Framework | 1989742 | Gebert, Clint | East | 2. Pending AFE | Defined | Exposure Remediation | 104 | 750000 |  | 750104.12 | 750035 | 70 | Yellow |  |  |  | 750104 | [6 empty] | Interim |  | 14639 | 750000 | 764639 | No | Green | 2022-11-01 |  |  |  | 2023-04-30 |  |  |  |  | 34.5 | 69.62 |  |  | 70 | Red | [5 empty] | 375000 | 375000 |  |  |  |  | 5/3/2023-Will start and end late summer/early fall. 2/3/2023-Purge and cutout is required. 12/2/22-CGG- Had stakeholder meeting with NYDEC agencies after their review letter was received. Path forward with permitting has been defined. Based on restrictions this may be possible for construction in August/September2023 depending on permit issuance. Scope of work change forecasted for 2023, guessing at 350K, but could be higher. 9/6/2022-Still waiting on permit. 8/3/22-CGG- Permit submitted to access from West bank and do an instream repair. 7/6/2022 - Still pursuing permits, vendor is being overloaded with corporate work. 6/2/22-CGG- Interim AFE was submitted. 4/5/2022 - Started permit process and permit timing will determining construction timing. July at the earliest or may have prohibitive cost. 3/3/2022 - Permit submission currently being drafted. Timelines will be determined based on permit requirements. The soonest will be summer or fall. 8/24/21 - To be cutout during RX751 purge instead of in stream repair. Reassigned to Clint Gebert. | 2023-05-03 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | RX751BX - ROCHESTER JCT - BATAVIA STATIO |  | 35 | 70 | 750000 |  | 14535 |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 41164 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Accel Exposures
Sinking Spring Gate Installation Controls | Item | Open | MCAP |  | Maintenance Framework |  | Pepe, David | East | 1. Proposed |  | East |  | 25000 |  | 25000 | 25000 | 0 | Green | 25000 |  | 25000 | 0 | [9 empty] | 25000 | 25000 | No | Green | 2023-09-01 |  |  |  | 2023-05-31 | [16 empty] | 25000 |  |  |  |  | 4/21/2023 DJP - requested information from security team. | 2023-04-21 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Mechanicsburg | SN - SINKING SPRING TERMINAL |  |  | 0 | 25000 |  |  |  | Orischak, Bob |  |  |  | 1 | 24580 |  | Administrator, System | Independent | Aqua | 2017-07-27 | Other Programs
Sinking Spring PD Meter Replacement | Item | Open | MCAP | SN00000M2002 | Exempt | 1743980 | Pepe, David | East | 5. Deferred | Defined | Measurement & Quality Control | 28213 |  |  | 28213.47 | 22713 | 5501 | Red |  |  |  | 28213 |  |  | 131000 | 323000 |  | 454000 | Phase | 2048789 | 758398 | 1350000 | 2108398 | No | Green | 2020-08-01 | 2020-08-10 | 2020-08-10 | 2021-12-30 | 2023-08-31 |  |  | 12349.34 | 5124.72 | 5238.84 | 5500.57 |  |  | 5501 | Red | [11 empty] | 3/1/2023 DJP - Project Delayed until later in the year or next year and AFE will have to be reinitiated. Forecast for 2023 removed and only minor spends remain to be invoiced. All forecast moved to 2024. 2/3/2023-Delayed because AFE is not fully approved (it is in process). 1/27/2023 DJP - Submitted Full AFE / Phase 3 for construction and all previous costs1/4/2023-Valves came in 1 month sooner than vendor had promised last month. Working on phase III AFE for construction. 2022/12/05 DJP valves have been delayed until January, Construction final bidding due this week, need to submit the final AFE for construction.10/11/22 RLO Dave to evaluate getting civil done this year and bidding out mech and electrical in October. 9/6/22 23K variance due to expecting material to arrive sooner than it will. EK55078/3/22 Project transitioned to Dave Pepe. 200K FC for Aug is good (materials). All project information has been turned over to him. Will need to bid out mechanical and electricla and submit final AFE for construction. ek55077/6/22-MCS: 24K underage because partial invoice accrued for 190K came in at 145K. 7/6/22 Project should be transitioned to new/contract pm. Scope of work along with mechical/electrical scopes will need to be completed for final afe submission. ek55075/4/22 Currently working on scope of work to bid out contraction and working of final AFE. Will be transition to Dave Pepe come July. ek5507 4/4/22 Variance due to mis forecast as vendor was able to up delivery of the prover and required the 50% payment. 3/3/22 Working on Phase II AFE, and have adjusted forecast. Prover to be delivered in April 300k moved to that month. EK55071/3/22 Plan on costing out piping, and control valve Jan/Feb time frame. Hoping to have project bid out May/June time frame with construction in August. EK550712/3/2021-Prover went out to bid and will be awarding contract to FMD. 10/5/21 Still no approval on prints from corporate. PO issued for prover ek 55079/3/21 No change waiting for corporate eng on approval of design. ek55078/4/21 Eng prints submitted to ENG and Design for review and approval. Will input po for small volume prover this month. EK55077/6/2021 - Phase II AFE in approval routing. 12/3/2020 Accrual made for Kiely and Meterordered. Will be ordering other material this month. EK55079/2/2020 - In 2020 we will be purchasing turbine meter and doing design. In2021 will purchase SVP and control valve. In 2022, will do construction. Due to budget constraints.3/4/2020 Plan is to scope out for the sonic in March. Will be meeting with MP guys and eng design firm to develop material list and plan. EK55072/4/2020 The new PD meters that were spec'd out and would have the same take out as the existing will no longer be made. Vendor has offered a different model but has a 8" longer take outand will require modification to the piping. Bill Serra advised to scope out and budget for sonic meter. Will put together an AFE for total budget with 2020's budgeted amount to be spent on equipment and 2021 installation. Currently working with Steve Zimmerman to gather numbers for AFE submittal. EK5507 | 2023-02-24 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Mechanicsburg | SN - SINKING SPRING TERMINAL |  | 22713 | 5501 |  |  | 630914 | 1350000 | Hopkins, Christa | Hopkins, Christa | N/A |  | 1 | 21001 |  | Guest, ProSight | Independent | Aqua | 2016-09-05 | Other Programs
South Portland Vacuum Breaker Rebuild 2022 | Item | Open | MEXP | PM755HWE2206 | Maintenance Framework | 2022161 | Orischak, Bob | East | 7. Closed | Drawdown | East | -1250 |  |  | -1250 | -1250 | 0 | Green |  |  |  | -1250 |  |  | 22500 |  |  | 22500 | Full | 22500 | 21250 |  | 21250 | No | Green | 2022-12-01 | 2022-09-27 | 2022-09-27 | 2022-12-31 | 2022-12-31 |  |  | 0 | -1250 | [17 empty] | 3/7/2023 - Closed WO/PO (closed the WO which was mapped to the project, which was 2023760). Set OPPM status to 'Closed'. MCS 2/22/23 RLO Ready to close. 01/03/2023 RLO Can be accrued. Work has been completed. 12/1/22 RLO to be spent this month 11/2/2022 RLO Should be ready in December 10/3/22 RLO Proj was not approved due to issue with JV confusion. Hoping to have this done by EOY. 9/12/2022 - RLO Project just approved. Will need to be sent out to rebuild 6wks. | 2023-03-07 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Maine | PM755HW - S PORTLAND TERM - HALLOWELL |  | -1250 | 0 |  |  | 22500 |  | Orischak, Bob | Wing, Stephen W. | N/A |  | 1 | 45776 |  | Orischak, Bob | Independent | Aqua | 2022-09-09 | Other Programs
Springfield Terminal Air Compressor Replacement | Item | Open | MCAP | BETXS00M2201 | Maintenance Framework | 2052898 | Orischak, Bob | East | 3. Active | Drawdown | East | 31529 |  |  | 31528.82 | 30034 | 1495 | Yellow |  |  |  | 31529 |  |  | 32000 |  |  | 32000 | Full | 32000 | 31529 |  | 31529 | No | Green | 2023-03-01 | 2022-12-16 | 2022-12-16 | 2023-01-31 | 2023-04-12 |  |  |  |  | 30033.77 | 1495.05 |  |  | 1495 | Red | [11 empty] | 4/25/2023 - Wanting to close, but will hold up because invoice IN000066829 OP-237451 has been snagged for a month due to $350 receipting challenges.MS 4/3/23 RLO - Project is complete and ready to close. 1/31/2023 RLO - Air compressor has been delayed and may not come in for 45 more days. 1/3/2023 RLO - Project just approved at end of December. Work expected to be complete by end of January | 2023-05-01 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Jet Lines | BETXS - BET SPRINGFIELD TERMINAL |  | 30034 | 1495 |  |  |  |  | Orischak, Bob | Wing, Stephen W. |  |  | 1 | 46343 |  | Orischak, Bob | Independent | Aqua | 2022-12-09 | Other Programs
St Lucia (BSLQL) Tank 1030 Substitution Project | Item | Open | MCAP | BSLQL00M2304 | Maintenance Framework | 2096479 | Campbell, Jamie | East | 6. Operational | Defined | Tanks | 17000 | 0 |  | 16999.98 | 17775 | -775 | Yellow | 15000 |  | 15000 | 2000 |  |  | 17775 |  |  | 17775 | Full | 17775 | 17000 | 0 | 17000 | No | Green | 2023-04-01 | 2023-03-29 | 2023-03-29 | 2023-04-30 | 2023-04-19 | [5 empty] | 16999.98 | 17775 | 17775 | -775 | Yellow |  |  | 0 | [8 empty] | 05/01/2023 - Project ready to close. 4/3/2023 - Tank and piping modification are currently in progress to transfer product out of tank 1030. | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  |  | 17000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44304 |  | Stine, Carlton | Independent | Aqua | 2022-07-28 | Int - Tanks
St Lucia - Dry Cargo Dock - Concrete structural repairs | Item | Open | MCAP | BSLQL00M2202 | Maintenance Framework | 1915386 | Hernandez, Andres | East | 7. Closed | Defined | Marine | 2541 |  |  | 2540.84 | 2541 | 0 | Green |  |  |  | 2541 |  |  | 607000 |  |  | 607000 | Phase | 607000 | 633687 |  | 633687 | No | Green | 2022-02-01 | 2021-12-02 | 2021-12-02 | 2022-09-28 | 2022-12-22 |  |  | 2431.43 | 109.41 | [17 empty] | 03/28/2023 - Project closed out. 03/03/2023 - This project is ready to close. 26/11/22: Work commenced on the South side pier structure. Completion set for December. 10/10/22 KB: Forecast updated per O. Wildgoose. 09-10-22: Delays continue as berthing activities have increased. One side of the pier is now operational. finishing touches still aim to be completed end of December 2022. 7-7-22 The project is rescheduled to continue in September due to dock operations AH 6-8-22 Project ongoing, fabrication depends from dock availability. AH 5/4/22 - Favorable scheduling allowed more work than previously expected. 4/12/22 - Weather and tide delayed work, pushed into Q2. DC | 2023-03-28 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  | 2541 | 0 |  |  | 631146 |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 41942 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Marine
St Lucia (BSLQL) Tank 1013 OOS Corrosion Inspection and Refurb | Item | Open | MCAP | BSLQL00M2206 | Maintenance Framework | 1915763 | Campbell, Jamie | East | 3. Active | Defined | Tanks | 525552 | 14039 |  | 539590.82 | 524356 | 15235 | Yellow |  |  |  | 539591 |  |  | 319000 | 882000 |  | 1201000 | Full | 1201000 | 1301195 | 14039 | 1315234 | Yes | Red | 2022-04-01 | 2021-12-08 | 2021-12-08 | 2022-06-30 | 2023-06-15 |  |  | 127268.97 | 133718.49 | 208733.64 | 55830.72 | 54635 | 54635 | 1196 | Yellow |  |  | 14039 | [8 empty] | 5/1/2023 -Tank pontoons repairs are completed, Tank gauge pole expected on island May 12, 2023. 4/4/2023 Tank EFR pontoon repairs are 90% completed after the arrival of steel plates mid-March. still waiting the arrival of the radar gauge pole for installation. 3/8/23 Large forecast amounts are a result of the progression if the tank repairs. 03/02/2023 - Tank bottom repairs in completed, EFR repairs are 50% completed. Tank coating ordered and scheduled delivery to site end of March 2023. Project is slightly ahead of schedule in February 2023. 2/3/2023 - Tampa Tank delivered all material to terminal January 28, 2023. Crew arrived Feb 1, 2023, Bottom repairs are in progress. Acrrual for Tampa Tank completed in amount of $120k due to invoice arriving late. Materials arrived early. 1/9/2023 - Materials for the repairs have been fabricated and schedule to arrive terminal 1/20/2023. Crew is schedule to arrive onsite the week of 1/23/2023. 12/4/2022 AFE approvals completed and tank mechanical repairs awarded to Tampa Tank. Mechanical repairs are schedule to begin January 3, 2023. Tampa is currently procuring material for delivery. 10/4/2022 Contractor's bids received, waiting on Management and Commercial is deciding to proceed or defer the tank. 10/4/2022 Tank bottom inspection is completed, scope of work developed and RFP send to contractors. Tank EFR and Bottom requires extensive patching, along with several other repairs required of the EFR. 9/11/22-CES-Variance appears to be missed forecast of Island Freight and Sandblast grit from Sherwin Williams. Tank is progressing as planned but had a one month delay to removal of existing tank internal liner. 9/5/2022 Tank bottom inspection blast is completed. Tank inspectors are currently inside the tank scanning the bottom. 8/1/2022 Tank bottom coating removal is 65% completed. Process is slow due shipment of abrasive material arriving late. 7/4/2022 The tank bottom coating is in progress of being removed by the local coating team. The process is slow due the small crewonsite and the extreme weather that the island had experience during June. Variance due to additional purchase of material based on condition of tank bottom. 6/9/2022 HMT start the OOS inspection but advise that the tank bottom coating need tobe removed to complete scanning. Blasting crew is mobilizing at the tank on 6/10/2022. HMT also highlighted serious issues with Tank pontoons. 6/01/2022 - Tank cleaning is 90% completed. HMT is scheduleto began OOS API 653Inspections on June 8, 2022. 4/30/22 - Tank cleaning is currently in progress. The forecast spend was under in April, due to tank having to be prep before the tank cleaning could begin. 4/1/2022 - Tank will be removedfrom service on March 6, for cleaning 2/1/2022 - Operational date moved to September 2022 BL | 2023-05-05 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  | 469721 | 69870 |  |  | 775643 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41334 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
St Lucia 2020 Jet Rodder Sewer Cleaning Pump | Item | Open | MCAP | BSLQL00M2210 | Maintenance Framework | 2045710 | Wildgoose, Oneil | East | 7. Closed | Defined | East |  |  |  | 0 |  | 0 | Green | 55000 |  | 55000 | -55000 |  |  | 64000 |  |  | 64000 | Full | 64000 | 69223 |  | 69223 | No | Green | 2022-11-01 | 2022-11-22 | 2022-11-22 | 2022-12-31 | 2022-12-31 | [21 empty] | 04/03/2023 - Jet Rodder has been shipped expected to be on island first week in April. 03/03/2023 - Delivery of the Jet Rodder expected April/May of 2023. 2/10/2023 - Still awaiting Jed rodder delivery 2/3/2023 - All project cost are in and project is operational. 12/07/22- Jett Roder has been purchased from the manufacture. | 2023-04-03 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  |  | 0 |  |  | 69223 |  | Orischak, Bob | Orischak, Bob |  |  | 1 | 34700 |  | Guest, ProSight | Independent | Aqua | 2019-08-29 | Other Programs
ST LUCIA 2022 PURCHASE OF A SIDE BY SIDE VEHICLE | Item | Open | MCAP | BSLQL00M2209 | Maintenance Framework | 2045712 | Wildgoose, Oneil | East | 7. Closed | Defined | East |  |  |  | 0 |  | 0 | Green | 30000 |  | 30000 | -30000 |  |  | 36000 |  |  | 36000 | Full | 36000 | 36409 |  | 36409 | No | Green | 2022-11-01 | 2022-11-22 | 2022-11-22 | 2022-12-31 | 2022-12-31 | [21 empty] | 02/10/2023 - Sid by side received by the terminal 12/29/22 KDB: Removed $30k forecasted in Jan '23. There is no additional spend. | 2023-02-10 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  |  | 0 |  |  | 36409 |  | Orischak, Bob | Orischak, Bob |  |  | 1 | 41627 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
St Lucia 2023 Environmental Cleaning Bay | Item | Open | MCAP | BSLQL00M2303 | Maintenance Framework | 2083844 | Wildgoose, Oneil | East | 3. Active | Defined | East | 113751 | 10460 |  | 124211.37 | 122075 | 2136 | Yellow | 110000 | 10460 | 120460 | 3751 |  |  | 120460 |  |  | 120460 | Full | 120460 | 113751 | 10460 | 124211 | No | Green | 2023-02-01 | 2023-02-03 | 2023-02-03 | 2023-05-30 | 2023-06-30 |  |  |  | 35638.81 | 41476.41 | 36636.15 | 34500 | 34500 | 2136 | Yellow |  |  | 10460 | [8 empty] | 05/02/2023 - Project is on schedule. Currently in construction mode. 04/03/2023 - Accrual for $39K captured for March Project is on schedule. 03/03/2023 -Work is ongoing and the project is on schedule. 2/10/2023 - AFE approved, initial drawings and layout in progress. 2/3/2023 - AFE being routed for approval. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  | 77115 | 47096 |  |  |  |  | Orischak, Bob | Votta, Joseph T. |  |  | 1 | 44294 |  | Guest, ProSight | Independent | Aqua | 2022-07-27 | Other Programs
St Lucia 2023 Fire Water Refurbishment Project | Item | Open | MCAP | BSLQL00M2301 | Maintenance Framework | 2082831 | Wildgoose, Oneil | East | 3. Active | Defined | Fire Protection | 112928 | 126722 |  | 239649.53 | 238178 | 1472 | Yellow | 204000 | 30580 | 234580 | 5070 |  |  | 234580 |  |  | 234580 | Full | 234580 | 112928 | 126722 | 239650 | No | Green | 2023-02-01 | 2023-01-31 | 2023-01-31 | 2023-12-31 | 2023-12-31 |  |  |  | 74216.09 | 22068.66 | 16642.78 | 17000 | 17000 | -357 | Yellow |  |  | 18829 | 17000 | 17000 | 17000 | 17000 | 17000 | 17000 | 5893 |  | 05/02/2023 - Project is on schedule for completion. $4,107 accrual captured for April. 04/03/2023 - Project is ongoing and progressing according to plan. All material has been purchased and installation of new foam risers are ongoing. 03/03/2023 - Project is ongoing, on schedule and on budget. 2/10/2023 - Forecast for February utilized for material purchases and labor. Material has been ordered and onsight work commencing 2/3/2023 - Forecasted adjusted per PM. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  | 96285 | 52472 | 51000 | 39893 |  |  | Jakubowski, Gregory | Votta, Joseph T. |  |  | 1 | 44295 |  | Guest, ProSight | Independent | Aqua | 2022-07-27 | Other Programs
St Lucia 2023 Marine Crane tower repairs and crane install | Item | Open | MEXP | BSLQL00E2303 | Project Framework | 2112704 | Hernandez, Andres | East | 3. Active | Defined | Marine |  | 228000 |  | 228000 | 431275 | -203275 | Red | 431275 |  | 431275 | -203275 |  |  | 223000 |  |  | 223000 | Full | 223000 |  | 228000 | 228000 | No | Green | 2023-06-01 | 2023-04-26 | 2023-04-26 | 2023-11-30 | 2023-08-31 | [13 empty] | 35000 | 50000 | 57500 | 40000 | 33000 | 12500 |  |  | 5-1-23, AFE was approved, we will cut the PO to Bowman engineering, to perform the structural design AH 4.14.23.DLC: reduced by $200k as part of 3+9 MEXP reduction for East Region4-11-23, AFE will be submit this month to get money approve AH 03/1/2023 - Continue to await structural analysis to submit AFE. As a result, April forecast adjusted to October. 2/8/23. Waiting for structural analysis to submit AFE. | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  |  | 35000 | 147500 | 45500 |  |  | Spari, Markella | Spari, Markella |  |  | 1 | 44426 |  | Guest, ProSight | Independent | Aqua | 2022-08-04 | Marine
St Lucia 2023 Rebuilt of Generator Engines | Item | Open | MEXP | BSLQL00E2302 | Maintenance Framework | 2084409 | Wildgoose, Oneil | East | 3. Active | Defined | East | 43866 | 75000 | 10000 | 118866.25 | 120000 | -1134 | Yellow | 110000 |  | 110000 | 8866 |  |  | 120000 |  |  | 120000 | Full | 120000 | 43866 | 85000 | 128866 | No | Green | 2023-04-01 | 2023-02-03 | 2023-02-03 | 2023-05-09 | 2023-08-31 | [5 empty] | 43866.25 | 45000 | 45000 | -1134 | Yellow |  |  | 25000 |  | 25000 | 25000 |  |  |  |  | 10000 | 05/02/2023 - Parts have been ordered as approved. Forecast being adjusted for actual timing of long lead items before lock. 04/03/2023 - Project is commencing with material purchase in April. Actual rebult will aim to start in June. 03/03/2023 - Project remains good at this time. 2/3/2023- AFE being routed for approval. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  |  | 68866 | 50000 |  |  |  | Orischak, Bob | Votta, Joseph T. |  |  | 1 | 44293 |  | Guest, ProSight | Independent | Aqua | 2022-07-27 | Other Programs
St Lucia Apparatus Repair and Testing | Item | Open | MEXP | BSLQL00E2112 | Maintenance Framework | 1915855 | Wildgoose, Oneil | East | 7. Closed | Drawdown | Fire Protection | 19963 |  |  | 19962.97 | 19963 | 0 | Green |  |  |  | 19963 |  |  | 20000 |  |  | 20000 | Full | 20000 | 19963 |  | 19963 | No | Green | 2023-02-01 | 2021-12-09 | 2021-12-09 | 2022-01-31 | 2023-03-01 |  |  |  | 19962.97 | 0 | 0 |  |  | 0 | Green | [11 empty] | 05/02/2023 - Working to have final invoices submitted to close project. 03/03/2023 - Foam Apparatus tested and commissioned by Foam Technology, awaiting the final invoices. 2/2/2023 Testing for foam system is scheduled for February 13th-16th 2023.09/10/22: Still awaiting date for Haines to visit site for pumper repair. Aiming for October 2022. Emergent repair of only plant foam pumper to allow it to use plant foam from totes 09/03/2022 - Team has not found the necessary part as yet. Hoping that part can be identified in September and payment processed in October. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  | 19963 | 0 |  |  |  |  | Jakubowski, Gregory | Jakubowski, Greg | N/A |  | 1 | 42606 |  | Meitzler, Antoinette | JDE Child | Burnt Orange | 2021-12-09 | Other Programs
St Lucia Limited (BSLQL) Tank 1030 - OOS API 653 Insp | Item | Open | MCAP | BSLQL00M2302 | Maintenance Framework | 2053009 | Campbell, Jamie | East | 3. Active | Defined | Tanks | 90733 | 285000 |  | 375733.46 | 378000 | -2267 | Yellow | 360000 |  | 360000 | 15733 |  |  | 378000 |  |  | 378000 | Full | 378000 | 90733 | 285000 | 375733 | No | Green | 2023-04-01 | 2022-12-21 | 2022-12-21 | 2023-12-31 | 2023-07-15 | [5 empty] | 90733.46 | 93000 | 93000 | -2267 | Yellow |  |  | 48000 | 67000 | 70000 | 100000 | [5 empty] | 5/1/2023 - Tank - bottom repairs are completed. Tank roof repairs in progress. Tank bottom coating to be completed by end of month. 04/04/2023 - Large spend in April is for material. Tank was removed from service April 3, 2023. Tank cleaning, inspection and procurement of some material will happen in April. 03/08/23 - There is a large spend projected in May for tank material cost. 03/02/2023 - Forecast is being brought forward due to Commercial request. Spending projected to begin April. Tank is schedule to be removed from service in2nd quarter, as per last communication with Terminal and Commercial. | 2023-05-05 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  |  | 205733 | 170000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44883 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
St Lucia Limited (BSLQL) Tank 1033 – OOS Corr Insp & Refurb | Item | Open | MCAP | BSLQL00M2205 | Maintenance Framework | 1915706 | Campbell, Jamie | East | 6. Operational | Defined | Tanks | -28285 |  |  | -28285.37 | -28873 | 588 | Yellow |  |  |  | -28285 |  |  | 185000 |  |  | 185000 | Phase | 185000 | 219126 |  | 219126 | No | Green | 2022-02-01 | 2021-12-06 | 2021-12-06 | 2022-06-30 | 2022-07-31 |  |  | -41938 |  | 13064.7 | 587.93 |  |  | 588 | Red | [11 empty] | 2/3/2022 -Dropping $41.9K accruals per Bob Orischak to close project. 6/1/2022 Tank have been returned to service waiting on final invoices to close project. 4/30/22 - Tank project is waiting on final invoice to close project. 4/6/22 - Work addressed earlier than scheduled DC 4/1/2022 Tank repairs and bottom coating completed ahead of schedule, Tank is waiting the replacement Radar gauge. Tank will be returned to service on March 14, 2022. 3/2/22 Tank is not available until March, delaying February forecast 3/1/22 Tank is being cleaned for HMT inspectors arrival on March 7, 2022. 2/1/22 Project start delayed by one month, tank preparation will be underway BL | 2023-02-12 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  | -28873 | 588 |  |  | 247412 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41340 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
St Lucia Terminal Atmospheric Corrosion Inspections 2022 | Item | Open | MEXP | BSLQL00E2203 | Maintenance Framework | 1938856 | Gable, Rob | East | 7. Closed | Defined | Cathodic Protection | 305 |  |  | 304.8 | 305 | 0 | Green |  |  |  | 305 |  |  | 32000 |  | 8346 | 40346 | Full | 40346 | 27492 |  | 27492 | No | Green | 2022-06-01 | 2022-01-20 | 2022-01-20 | 2022-10-15 | 2022-12-31 |  |  | 13158.65 | -13017.33 | 163.48 | [16 empty] | 3/14/2023 - Closed WO/PO and set OPPM project status to 'Closed'. MCS 3/2/2023 - All invoices received, project ready to close. 2/2/2023 RAG - Awaiting final invoices. 1/4/2023 RAG - Completed for less than planned. 12/2/2022 RAG - Setting up LSC to perform inspections during Dec. 11/3/2022 RAG - LSC has confirmed they will perform work during Dec. 10/4/2022 RAG - Scheduling LSC. Progress delayed because original contractor stopped the travel process. 7/1/2022 RAG - Site visit performed. Now work can be scheduled for Q3. 6/2/2022 RAG - Work will be performed after site visit during June. Site visit delayed due to scheduling issues. 5/2/2022 RAG - Preparing work to begin as forecasted. 4/4/2022 RAG - Planning site visit with in next 6 weeks. 3/2/2022 RAG - Preparing work to begin as forecasted. 2/2/2022 RAG - AFE has been approved and WOR created. 1/13/2022 RAG - AFE submitted on 1/13/2022. | 2023-03-14 | Sautter, Maureen |  | East | Pipelines and Terminals | Corrosion |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  | 305 | 0 |  |  | 27187 |  | Geib, Rob | Geib, Robert |  |  | 1 | 42620 |  | Guest, ProSight | Independent | Aqua | 2021-12-15 | Int - Accel Corr & FI
St. Lucia Green Firefighting Foam Pilot Project | Item | Open | MCAP | BSLQL00M2109 | Exempt | 183849 | Edward, Faustinus | East | 7. Closed | Unplanned | Fire Protection | 9867 |  |  | 9867.47 | 7749 | 2118 | Red |  |  |  | 9867 |  |  | 273000 |  |  | 273000 | Full | 273000 | 336527 |  | 336527 | No | Green | 2021-09-01 | 2021-04-28 | 2021-04-28 | 2021-12-15 | 2022-04-28 |  |  |  |  | 7749.2 | 2118.27 |  |  | 2118 | Red | [11 empty] | 10/25/21 - FireDOS, foam tank, and foam concentrate all arrived at facility in October. Additional InBAL valve needed $27k. System drawing/engineering done. Site to install (GJ) 9/8/21 - Items are expecting to arrive in September.6/9/2021 - Drawings completed for the additional piping and pending the purchases which have been submitted. 4/11/21 Project 1 for this will be St. Lucia. In design now, PM to be Faustinus Edward anticipated spend $250-300k for St Lucia beginning May 2021 through October. St. Lucia ordering materials as of May 27. SS pricing increase on tank approx. $10k, site will try and hold budget. Project 2 will be Cleveland Terminal. PM to be Nick Keppel, will spend remainder of this 3Q-4Q (GJ) | 2021-11-30 | Boyd, Kim |  | East | Pipelines and Terminals | Operating Infrastructure |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  | 7749 | 2118 |  |  | 21721 |  | Jakubowski, Gregory | Bissaillon, Paul |  |  | 1 | 37124 |  | Guest, ProSight | Independent | Aqua | 2020-07-16 | Other Programs
St. Lucia Limited (BSLQL) 2022 Rebuilding of Generator #2 | Item | Open | MEXP | BSLQL00E2205 | Maintenance Framework | 1956010 | Wildgoose, Oneil | East | 7. Closed | Defined | Electrical | 11133 |  |  | 11132.63 | 11133 | 0 | Green |  |  |  | 11133 |  |  | 121000 |  |  | 121000 | Full | 121000 | 148290 |  | 148290 | No | Green | 2022-05-01 | 2022-03-14 | 2022-03-14 | 2022-06-30 | 2022-12-27 |  |  | 2665.52 |  | 8467.11 | [16 empty] | 12/07/22: Project is completed awaiting final invoices from contractor. 10/12/22 KB: Reclass pending to change object account to reflect additional $34K of actuals. 09/10/22: Current delay of tools to complete the rebuilt of the engine. Technicians are still scheduled to arrive on island in October. 09/07/22 KB: Sept forecast includes $34k reclass of zofix outside services that are currently not showing. July 1st 2022: Parts have been shipped from the Bahamas to st. lucia. As soon as parts arrive in St Lucia, Technician will travel and commence rebuilding. May 9th 2022: Rebuilt parts have been ordered and are awaiting delivery to st Lucia. PO has been created for rebuilt labor and also awaiting parts to arrived on island. This work may not commence until mid June. 09/03/22- Actuals are incorrect so forecast cannot happen until corrected. | 2022-12-07 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  | 11133 | 0 |  |  | 137157 |  | Ashley, Robert | Davalos, Glenda |  |  | 1 | 41616 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
Syracuse Terminal JV Flash Tester Purchase 2023 | Item | Open | MCAP | BJVQS00M2301 | Maintenance Framework | 2111160 | Orischak, Bob | East | 3. Active | Defined | East |  | 20000 |  | 20000 | 20000 | 0 | Green | 20000 |  | 20000 | 0 |  |  | 20240 |  |  | 20240 | Full | 20240 |  | 20000 | 20000 | No | Green | 2023-08-01 | 2023-04-17 | 2023-04-17 | 2023-08-25 | 2023-05-31 | [12 empty] | 0 |  |  | 20000 | [7 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BJVQS - BJV SYRACUSE JV TERMINAL |  |  | 0 | 20000 |  |  |  | Orischak, Bob | Tracey, Steve |  |  | 1 | 44326 |  | Guest, ProSight | Independent | Aqua | 2022-07-29 | Other Programs
Syracuse Terminal JV PLC upgrades 2023 | Item | Candidate | MCAP |  | Maintenance Framework |  | Orischak, Bob | East | 1. Proposed |  | East |  | 115000 |  | 115000 | 115000 | 0 | Green | 115000 |  | 115000 | 0 | [9 empty] | 115000 | 115000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 115000 | [10 empty] | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BJVQS - BJV SYRACUSE JV TERMINAL |  |  | 0 | 115000 |  |  |  | Orischak, Bob |  |  |  | 1 | 44320 |  | Guest, ProSight | Independent | Aqua | 2022-07-29 | Other Programs
Syracuse Terminal JV Remove and dispose of AFFF Foam 2023 | Item | Candidate | MEXP |  | Maintenance Framework |  | Orischak, Bob | East | 1. Proposed |  | East |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 | [9 empty] | 50000 | 50000 | No | Green | 2023-08-01 |  |  |  | 2023-08-31 | [15 empty] | 50000 | [9 empty] | East | Pipelines and Terminals | Station/Terminal |  | Auburn Terminals | BJVQS - BJV SYRACUSE JV TERMINAL |  |  | 0 | 50000 |  |  |  | Orischak, Bob |  |  |  | 1 | 44322 |  | Guest, ProSight | Independent | Aqua | 2022-07-29 | Other Programs
Syracuse Terminal JV VRU and VCU PLC Upgrade 2023 | Item | Candidate | MCAP |  | Maintenance Framework |  | Orischak, Bob | East | 1. Proposed |  | East |  | 80000 |  | 80000 | 80000 | 0 | Green | 80000 |  | 80000 | 0 | [9 empty] | 80000 | 80000 | No | Green | 2023-10-01 |  |  |  | 2023-10-31 | [17 empty] | 80000 | [7 empty] | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BJVQS - BJV SYRACUSE JV TERMINAL |  |  | 0 |  | 80000 |  |  | Orischak, Bob |  |  |  | 1 | 44324 |  | Guest, ProSight | Independent | Aqua | 2022-07-29 | Other Programs
TAA - OT Lab System | Item | Open | MCAP |  | Exempt |  | Garcia, Francisco | East | 5. Deferred |  | OT & IT Field Ops |  |  |  | 0 |  | 0 | Green | [15 empty] | No | Green |  |  |  |  | 2023-10-31 | [21 empty] | ?-10/31/22 - Deferred to 2024 per ELT cost reduction request.//bo | 2022-10-31 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 |  |  |  |  | Gingras, Stephan |  |  |  | 1 | 45491 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
Tank 8062 Concrete slab Coating | Item | Open | MCAP | 8410811M2132 | Maintenance Framework | 1902523 | Hernandez, Andres | East | 7. Closed | Unplanned | Secondary Containment | 10 |  |  | 9.92 | 10 | 0 | Green |  |  |  | 10 |  |  | 241000 |  |  | 241000 | Full | 241000 | 220892 |  | 220892 | No | Green | 2021-12-01 | 2021-10-19 | 2021-10-19 | 2021-12-31 | 2022-03-31 |  |  |  |  | 9.92 | [16 empty] | 4/7/22 Project completed. ready to close AH 3/8/22 project will be ready at the end of the month. we dont speck more charges on it AH 2/8/22 we had to buy extra materials after the inspection.. not as much as we were expecting, project will be completed at the end of the month. AH 01/10/22 we had to do extra work on the slab to meet proper CSP, CSP is important to ensure coating adheres properly on the concrete.. AH 12/6/21We are waiting the coating materials to start the process, materials are going to arrive middle of Dec on freeport. AH 12/1/2021 Estimated operational date moved back to march 2022 BL | 2022-09-15 | Boyd, Kim |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 10 | 0 |  |  | 25841 |  | Clark, Dave | Nash, Tom |  |  | 1 | 42256 |  | Perry, Betty | Independent | Aqua | 2021-10-06 | Other Programs
Trenton Terminal 1 (BETHK) Tank 3 - OOS API 653 Insp | Item | Open | MCAP | BETHK00M2301 | Maintenance Framework | 2096558 | Marrocco, Alex | East | 3. Active | Defined | Tanks |  | 232000 |  | 232000 | 245000 | -13000 | Yellow | 232381 |  | 232381 | -381 |  |  | 121135 |  |  | 121135 | Phase | 121135 |  | 232000 | 232000 | No | Green | 2023-05-01 | 2023-03-30 | 2023-03-30 | 2023-08-31 | 2023-06-30 | [6 empty] | 0 | 0 | 0 | Green |  |  | 45000 | 100000 | 87000 | [8 empty] | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Pennsauken | BETHK - BET Trenton Terminal (formerly Duck Island I) |  |  | 145000 | 87000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44890 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
TS and Anode Install at Reading RR Casings 734L and 740L | Item | Open | MCAP | JD734BHM2201 | Maintenance Framework | 1939348 | Gable, Rob | East | 6. Operational | Defined | Cathodic Protection | 199817 |  |  | 199817 | 199817 | 0 | Green | 48000 |  | 48000 | 151817 |  |  | 230000 |  |  | 230000 | Full | 230000 | 260093 |  | 260093 | Yes | Red | 2022-08-01 | 2022-01-21 | 2022-01-21 | 2022-10-15 | 2023-03-31 |  |  | 78146.36 | 209486.49 | -87815.85 | [16 empty] | 5/2/2023 RAG - Ready to close. No more invoices expected. 4/4/2023-Project complete, no more invoices expected. Can close. March Variance is due to over-accruing for Kiely in February. Overall the project came in close to budget at 251K, only 20K over. 3/2/2023RAG - Majority of work complete. CO being processed. Likely will need a small supplemental due to field conditions (deeper than we thought, muddier soil) 2/2/2023 RAG - Work began in January and continues. 1/4/2023 RAG - Work to begin during Jan 2023. 12/2/2022 RAG - Work to start by Kiely on 1/3/2023. Forecasts have been adjusted with R Geib. Dec funds are for materials. 11/3/2022 RAG - Preparing with Kiely to start project. 10/4/2022 RAG - Kiely verified we are on schedule to start mid Nov. 9/6/2022 RAG - Kiely proceeding with permitting, job WILL get done in Nov-Jan timeframe.. 6/2/2022 RAG - Kiely received PO for permit work. 5/2/2022 RAG - Informed by Kiely that permits only allow work to be performed from November 16, 2022 to March 14, 2023. PO issued to Kiely to secure wetland permit extensions and RR permits now for the Nov/March timeframe. A portion of the funding is now forecasted into Q1 2023. 4/4/2022 RAG - Preparing work to begin as forecasted. 2/2/2022 RAG - AFE has been approved and WOR created. 1/13/2022 RAG - AFE submitted on 1/13/2022. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Booth | JD734BH - DELAWARE RIVER JCT TO BOOTH |  | 199817 | 0 |  |  | 60276 |  | Geib, Rob | Geib, Robert |  |  | 1 | 42619 |  | Guest, ProSight | Independent | Aqua | 2021-12-15 | Int - Planned Corr & FI
Tuckerton (BETRG) - Secondary containment upgrades | Item | Open | MCAP |  | Maintenance Framework |  | Pepe, David | East | 1. Proposed |  | Secondary Containment |  | 60000 |  | 60000 | 60000 | 0 | Green | 60000 |  | 60000 | 0 | [9 empty] | 60000 | 60000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 30000 | 30000 | [5 empty] | 4/21/2023 DJP - Need to install a concrete housekeeping pad around the BIO tank, getting quotes. 3/1/2023 DJP - reviewed with SPCC team for requriements. | 2023-04-21 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | RG - TUCKERTON TERMINAL |  |  | 0 | 60000 |  |  |  | Clark, Dave |  |  |  | 1 | 45164 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
Tuckerton Tank Dike Access Steps | Item | Open | MCAP | BETRG00M2301 | Maintenance Framework |  | Pepe, David | East | 2. Pending AFE | Defined | Secondary Containment |  | 75000 |  | 75000 | 75000 | 0 | Green | 75000 |  | 75000 | 0 | [6 empty] | Interim |  |  | 75000 | 75000 | No | Green | 2023-07-01 |  |  | 2023-12-31 | 2023-07-31 | [14 empty] | 50000 | 25000 | [5 empty] | 4/21/2023 DJP - reviewed stair design and getting revised prints. Forecast moved to Q3. 1/13/2023 DJP engaged Midstream to provide quote on developing the accessway design and permit drawings (if required) | 2023-04-21 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Terminal | BETRG - BET TUCKERTON |  |  | 0 | 75000 |  |  |  | Clark, Dave |  |  |  | 1 | 44297 |  | Guest, ProSight | Independent | Aqua | 2022-07-28 | Other Programs
Tuckerton Terminal Pumpback Pump Replacement | Item | Open | MCAP |  | Maintenance Framework |  | Orischak, Bob | East | 1. Proposed |  | Rotating Equipment |  | 39000 |  | 39000 | 39000 | 0 | Green | 39000 |  | 39000 | 0 | [9 empty] | 39000 | 39000 | No | Green | 2023-06-01 |  |  |  | 2023-06-30 | [13 empty] | 39000 | [11 empty] | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Terminal | BETRG - BET TUCKERTON |  |  | 39000 |  |  |  |  | Posipanko, Dan |  |  |  | 1 | 24584 |  | Administrator, System | Independent | Aqua | 2017-07-27 | Other Programs
UF999AU Valve 4 AC Mitigation Monitor Installation | Item | Open | MCAP | UF999AUM2301 | Maintenance Framework |  | Gable, Rob | East | 2. Pending AFE | Drawdown | Cathodic Protection |  | 11600 |  | 11600 |  | 11600 | Red |  | 11587 | 11587 | 13 |  |  | 11587 |  |  |  | Full | 11587 |  | 11600 | 11600 | No | Green | 2023-06-01 |  |  | 2023-08-01 | 2023-08-01 | [13 empty] | 3000 |  | 7600 | 1000 |  |  |  |  | 5/2/2023 RAG - Awaiting AFE approval. 4/7/2023 RAG - Submitted AFE Request into OPPM and Asset Funding Request for $11,600 on 4/7/2023. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Port Wilmington | BNTUE - WIlmington(DE) Terminal |  |  | 3000 | 8600 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 46927 |  | Meitzler, Antoinette | Independent | Aqua | 2023-04-12
Utica Terminal - Replace Louvers and Actuators on VCU | Item | Open | MCAP |  | Maintenance Framework |  | Mohr, David | East | 2. Pending AFE |  | Vapor Management |  | 22000 |  | 22000 | 22000 | 0 | Green | 22000 |  | 22000 | 0 | [9 empty] | 22000 | 22000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 22000 | [6 empty] | 5/1/2023 Waiting for additional labor costs on estimate. 4/1/2023 Received quote and requested more information from vendor/contractor with regards to installation 3/1/2023 Requested quote from vendor/contractor. DRM | 2023-05-02 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BETCA - BET UTICA TERMINAL |  |  | 0 | 22000 |  |  |  | Karl, Marissa |  |  |  | 1 | 44330 |  | Guest, ProSight | Independent | Aqua | 2022-07-29 | Other Programs
Utica Terminal (BETCA) Tank A-37 – OOS Corr + Seal Insp & Refurb | Item | Open | MCAP | BETCA00M2201 | Maintenance Framework | 1937285 | Yoder, Michael | East | 6. Operational | Defined | Tanks | 7472 |  |  | 7471.97 | 3386 | 4085 | Red |  |  |  | 7472 |  |  | 176000 | 163000 |  | 339000 | Full | 339000 | 359360 |  | 359360 | No | Green | 2022-05-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-10-31 |  |  | 3262.5 | 123.98 |  | 4085.49 |  |  | 4085 | Red | [11 empty] | 5/2/23 - April variance due to trailing electrical equipment invoice. 3/15/2023-Holding up on closing due to untapped PO from Sept 2022 Mike is checking on ($3K OP-234577 ). Can close. 2/1/23 - Variance due to trailing disposal invoice. May proceed with closing project. Can close. 12/2/22 - Variance due to trailing inspection services invoice. 11/1/22 - Tank returned to service. Variance due to additional product transfer and disposal costs. Preparing phase 2 AFE to submission. 10/4/22 - Preparing to return to service. Preparing phase 2 AFE for submission. 9/2/22 - Tank and coating repairs complete. IFR upgrades in progress. Preparing phase 2 AFE for submission. 8/2/22 - Tank repairs in progress. Updated forecast. Plan to submit phase 2 AFE once coating repair scope is finalized. 7/1/22 - Tank cleaned and inspected. Reduced July forecast since repairs anticipated to start late-July. Plan to submit phase 2 AFE once scope of finalized. 6/2/22 - Tank stripped. Plan to isolate and clean early-June. Variance due to ahead of schedule. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Terminals | BETCA - BET UTICA TERMINAL |  | 3386 | 4085 |  |  | 351888 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41348 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Utica Terminal Boiler Replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Wing, Hunter | East | 1. Proposed |  | East |  | 40000 |  | 40000 | 40000 | 0 | Green | 36000 |  | 36000 | 4000 | [9 empty] | 40000 | 40000 | No | Green | 2023-06-01 |  |  |  | 2023-06-30 | [13 empty] | 40000 | [7 empty] | 5/1/2023 - HJW - Rewalking SOW with operations to look at new idea to install NG as a cleaner alternative to the Fuel Oil we currently have. At this time, SOW is higher than budget with fuel oil. Will update SOW once path forward is determined. 4/3/2023-Obtained quote, but it was 10K over budget, Supply Chain is helping with vendor selection.3.02.23- Getting quote. 2.2.23 - Site Walkdown with operations was completed on 1.31.23. Operations was going to reach out to their HVAC contractor to get an updated quote. Expected to submit AFE and Work Plan in February | 2023-05-01 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BETCA - BET UTICA TERMINAL |  |  | 40000 |  |  |  |  | Orischak, Bob |  |  |  | 1 | 37333 |  | Guest, ProSight | Independent | Aqua | 2020-07-29 | Other Programs
Vestal (BETZL) - Secondary containment improvements | Item | Open | MEXP | BETZL00E2301 | Maintenance Framework |  | Pepe, David | East | 2. Pending AFE | Defined | Secondary Containment |  | 72000 |  | 72000 | 72000 | 0 | Green | 72000 |  | 72000 | 0 |  |  | 72450 |  |  |  | Full | 72450 |  | 72000 | 72000 | No | Green | 2023-08-01 |  |  | 2023-08-31 | 2023-10-31 | [15 empty] | 22000 | 25000 | 25000 |  |  |  | 5/4/2023 DJP - met with contractor on site to get quote on the installation of the berm around the additive and BIO tanks and the repair of the overfill path. AFE Submitted 5/4/2023 | 2023-05-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Auburn Terminals | BETZL - BET VESTAL TERMINAL |  |  | 0 | 47000 | 25000 |  |  | Spari, Markella | Spari, Markella |  |  | 1 | 45173 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
Vestal (ZL) Tank 1 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | ZL00000M2302 | Maintenance Framework | 2086170 | Yoder, Michael | East | 3. Active | Defined | Tanks |  | 123013 |  | 123013 | 123013 | 0 | Green | 123013 |  | 123013 | 0 |  |  | 109928 |  |  | 109928 | Phase | 109928 |  | 123013 | 123013 | No | Green | 2023-09-01 | 2023-02-24 | 2023-02-24 | 2023-12-31 | 2023-09-30 | [16 empty] | 123013 | [6 empty] | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | ZL - VESTAL TERMINAL |  |  | 0 | 123013 |  |  |  | Stine, Carlton |  |  |  | 1 | 44891 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Vestal Priority 3 API 570 Refurbishments | Item | Open | MCAP |  | Maintenance Framework |  | Mohr, David | East | 1. Proposed |  | Facility Integrity |  | 160000 |  | 160000 | 160000 | 0 | Green | 160000 |  | 160000 | 0 | [9 empty] | 160000 | 160000 | No | Green | 2023-07-01 |  |  |  | 2023-09-30 | [14 empty] | 75000 | 75000 | 10000 |  |  |  |  | 5/1/2023 Meetings held with contractors to collect estimates. 2/2/2023 Received inspection and tank information from the integrity group. | 2023-05-02 |  |  | East | Pipelines and Terminals | Integrity |  | Auburn Terminals | BETZL - BET VESTAL TERMINAL |  |  | 0 | 160000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45052 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Vestal Rotork Operator Replacements | Item | Open | MCAP | ZL00000M2301 | Maintenance Framework | 2077114 | Mohr, David | East | 3. Active | Defined | Valves |  | 75000 |  | 75000 | 75000 | 0 | Green | 75000 |  | 75000 | 0 |  |  | 77259 |  |  | 77259 | Full | 77259 |  | 75000 | 75000 | No | Green | 2023-07-01 | 2023-01-31 | 2023-01-31 | 2023-10-13 | 2023-04-30 | [6 empty] | 0 | 0 | 0 | Green |  |  |  |  | 75000 | [6 empty] | 2/2/2023 - PO issued, 26 week lead time. | 2023-02-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Pipeline | ZL - VESTAL TERMINAL |  |  | 0 | 75000 |  |  |  | Oey, Alex | Tracey, Steve |  |  | 1 | 44286 |  | Guest, ProSight | Independent | Aqua | 2022-07-27 | Other Programs
Vestal Tank 17 Concrete Pad and Tank Replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Bodner, Jordan | East | 2. Pending AFE | Defined | Tanks |  | 145000 |  | 145000 | 145000 | 0 | Green | 145000 |  | 145000 | 0 | [9 empty] | 145000 | 145000 | No | Green | 2023-08-01 |  |  |  | 2023-08-31 | [15 empty] | 145000 | [5 empty] | 2/1/2023-Spending expected to occur 3rd quarter. 7/27/22 - This is significantly underfunded for 2022. Deferring this project to 2023 RLO 4/2/21 - This is not an approved project for 2021.11/4/19 - Project is being deferred until 2021. Will get a better scope and estimate in 2020 and request again in 2021. Will use this years money for an emergent project at Rochester South that needs to get done before winter sets in. 10/3/19 - Local Ops still working with Highland Tank on new proposal. 9/3/19 - Still figuring out what to do. Quote for original SOW came out higher than what was budgeted and do not feel it is worth the price. Looking at purchasing a new tank with ladder, so may carryover into 2020. 4/1/19 - Moved from 2nd qtr. into 4th qtr. as per request from PMO. | 2023-03-09 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Auburn Terminals | BETZL - BET VESTAL TERMINAL |  |  | 0 | 145000 |  |  |  | Stine, Carlton |  | N/A |  | 1 | 25472 |  | Guest, ProSight | Independent | Aqua | 2017-09-01 | Int - Tanks
VESTAL TANK 25726 ROOF DRAIN REPAIR | Item | Open | MEXP | BETZL00E2203 | Maintenance Framework | 2043799 | Yoder, Michael | East | 6. Operational | Emergent | Tanks | 5413 | 4000 |  | 9412.75 | 9413 | 0 | Green |  |  |  | 9413 |  |  | 90000 |  |  | 90000 | Full | 90000 | 91926 | 4000 | 95926 | No | Green | 2022-11-01 | 2022-11-04 | 2022-11-04 | 2022-12-31 | 2022-12-31 |  |  | 5412.75 | [9 empty] | 4000 | [8 empty] | 4/5/2023-Added 4K to May FC for leg setting. 2/1/23 - Variance for disposal invoice. Tank may sit empty until RVP season so keep project open for leg setting. 1/4/23 - Repairs complete. Tank returned to service. 12/2/22 - Tank cleaning in progress. Roof drain repairs starting 12/7. 11/1/22 - Emergent AFE submitted. Baselined forecast. Cleaning to start 11/14. | 2023-04-05 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Auburn Terminals | BETZL - BET VESTAL TERMINAL |  | 5413 | 4000 |  |  | 86513 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46129 |  | Perry, Betty | Independent | Aqua | 2022-10-27 | Int - Tanks
Vestal Terminal (BETZL) Tank A-003 – OOS Seal Inspection | Item | Open | MEXP | BETZL00E2201 | Maintenance Framework | 1937927 | Yoder, Michael | East | 7. Closed | Defined | Tanks | 1239 |  |  | 1238.51 | 1239 | 0 | Green |  |  |  | 1239 |  |  | 191000 | 145000 |  | 336000 | Full | 336000 | 347446 |  | 347446 | No | Green | 2022-05-01 | 2022-01-05 | 2022-01-05 | 2022-12-31 | 2022-10-31 |  |  |  | 1238.51 | [17 empty] | 4/19/2023 - Closed WO/PO, and set OPPM status to 'Closed'. MCS can close. 3/1/23 - Variance due to PCard Material Purchases. 12/2/22 - Phase 2 approved. Variance due to additional drain up costs. 11/1/22 - Tank returned to service. Added 15k to November forecast for gauge repair. Preparing phase 2 AFE for submission. 10/4/22 - Preparing to return tank to service, jet nozzle piping and button-up in October. . Preparing phase 2 AFE for submission. 9/2/22 - Tank repairs in progress. Added 50k for added scope. Preparing phase 2 AFE for submission. 8/2/22 - Tank repairs in progress. 7/1/22 - Tank cleaned. Inspection in progress. Reduced July forecast since repairs anticipated to start late-July. 6/2/22 - Tank cleaning in progress. 5/4/2022 - Planning to take OOS at end of May. | 2023-04-19 | Sautter, Maureen |  | East | Pipelines and Terminals | Tank Integrity |  | Auburn Terminals | BETZL - BET VESTAL TERMINAL |  | 1239 | 0 |  |  | 346208 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41349 |  | Administrator, System | JDE Child | Burnt Orange | 2021-08-09 | Int - Tanks
Wethersfield Atmospheric Refurbishment | Item | Open | MCAP | BETWE00M2202 | Maintenance Framework | 1939600 | Occhi, Edward | East | 7. Closed | Defined | Atmospheric Corrosion | 388 |  |  | 388.08 | 388 | 0 | Green |  |  |  | 388 |  |  | 60000 |  |  | 60000 | Full | 60000 | 65546 |  | 65546 | No | Green | 2022-10-01 | 2022-01-27 | 2022-01-27 | 2022-12-31 | 2022-11-30 |  |  | 388.08 | [18 empty] | 2/2/2023 reclass submitted for ct self assess $3,730.63 to BETWE00E2204. 2/2/2023 ct self assess fee triggered supplement | 2023-02-02 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Jet Lines | BETWE - BET WETHERSFIELD TERMINAL |  | 388 | 0 |  |  | 65158 |  | Geib, Rob | Geib, Robert |  |  | 1 | 41082 |  | Guest, ProSight | Independent | Aqua | 2021-08-06 | Int - Accel Corr & FI
Wethersfield Terminal (BETWE) Tank 4501 - OOS Seal Insp | Item | Open | MEXP |  | Maintenance Framework |  | Marrocco, Alex | East | 1. Proposed |  | Tanks |  | 158000 |  | 158000 | 96000 | 62000 | Red | 96000 |  | 96000 | 62000 | [9 empty] | 158000 | 158000 | No | Green | 2023-09-01 |  |  |  | 2023-11-30 | [16 empty] | 16000 | 80000 | 62000 | [6 empty] | East | Pipelines and Terminals | Tank Integrity |  | Jet Lines | WE - WETHERSFIELD |  |  | 0 | 16000 | 142000 |  |  | Stine, Carlton |  |  |  | 1 | 44894 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Wethersfield Triennial Atmospheric Terminal Surveys | Item | Open | MEXP | BETWE00E2204 | Maintenance Framework | 1939593 | Occhi, Edward | East | 7. Closed | Defined | Atmospheric Corrosion | 4246 |  |  | 4246.01 | 4246 | 0 | Green |  |  |  | 4246 |  |  | 20000 |  |  | 20000 | Full | 20000 | 16618 |  | 16618 | No | Green | 2022-04-01 | 2022-01-27 | 2022-01-27 | 2022-12-31 | 2022-11-30 |  |  | 3885.63 | 360.38 | [17 empty] | 2/2/2024 Reclasses submitted for $3,730 and $155 from BETWE00M2202 AND BETWE00E2203. | 2023-02-02 | Walker, Carol |  | East | Pipelines and Terminals | Corrosion |  | Jet Lines | BETWE - BET WETHERSFIELD TERMINAL |  | 4246 | 0 |  |  | 12372 |  | Geib, Rob | Geib, Robert |  |  | 1 | 40910 |  | Guest, ProSight | Independent | Aqua | 2021-08-03 | Int - Planned Corr & FI
Williamsport BES Terminal (BETAM) Tank 453 (001A) - OOS API 653, PADEP + Seal Insp & Refurb | Item | Open | MCAP | BETAM00M2301 | Maintenance Framework | 2086171 | Yoder, Michael | East | 3. Active | Defined | Tanks | 846 | 246492 |  | 247338.43 | 246492 | 846 | Yellow | 246492 |  | 246492 | 846 |  |  | 175353 |  |  | 175353 | Phase | 175353 | 846 | 246492 | 247338 | No | Green | 2023-04-01 | 2023-02-24 | 2023-02-24 | 2023-12-31 | 2023-10-31 | [5 empty] | 846.43 |  |  | 846 | Red |  |  |  | 61623 | 123246 | 61623 | [5 empty] | 5/2/23 - Moved spend up to June for planned early start on tank OOS. | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Macungie Terminal | BETAM - BET SOUTH WILLIAMSPORT |  |  | 62469 | 184869 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44895 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Yabacoa Terminal 2023 Annual Survey | Item | Open | MEXP | BCTYA00E2305 | Maintenance Framework |  | Norton, Bill | East | 8. Canceled | Defined | Cathodic Protection | 0 | 50001 |  | 50001 | 50001 | 0 | Green | 50001 |  | 50001 | 0 |  |  | 49500 |  |  | 49500 | Full | 49500 | 0 | 50001 | 50001 | No | Green | 2023-09-01 | 2023-02-21 | 2023-02-21 | 2023-09-01 | 2023-11-30 | [5 empty] | 0 |  |  | 0 | Green | [6 empty] | 50000 |  |  | 1 |  | 3/2/2023 - Project is cancelled due to being funded through Local Operations Budget. 9/2/2022 - Forecasted $ in Summer 2023. | 2023-03-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Corrosion |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 0 | 50000 | 1 |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44341 |  | Guest, ProSight | Independent |  | 2022-08-05 | Int - Planned Corr & FI
Yabucoa - Dredging Permiting and Planning MCAP | Item | Open | MCAP | BCTYA00M2219 | Project Framework | 2052928 | White, Stephen | East | 3. Active | Defined | Marine | 148453 | 688457 |  | 836909.53 | 839091 | -2182 | Yellow |  | 960000 | 960000 | -123090 |  |  | 476000 |  |  | 476000 | Phase | 476000 | 261509 | 688457 | 949966 | No | Green | 2022-12-01 | 2023-01-06 | 2023-01-06 | 2023-05-30 | 2023-12-15 |  |  | 4557.47 | 51298.66 | 56778.22 | 35818.18 | 38000 | 38000 | -2182 | Yellow |  |  | 30000 | 68457 | 115000 | 115000 | 120000 | 80000 | 80000 | 80000 |  | 05/02/2023 - Accruals of $23K being captured for April. Forecast adjusted for May to reflect anticipated progress. Apr. 13, 2023 SGW - Teams Meeting with Colleen Coverley, Chris Kauffman and myself to discuss particulars for a Phase 2 AFE. April 12, 2023 SGW - weekly update with Gov't Relations team. Nothing new to report. April 5, 2023 SGW - Weekly update with Gov't Relations team. Executive Summary re: Yabucoa was delivered to Congresswoman's office this past Friday, March 31. April 4, 2023 SGW - Monthly review with Markella Spari and Angela Mirandi. Mar. 30, 2023 SGW - Meeting with U.S. Army Corps of Engineers in Jacksonville has been arranged for April 24. This is a pre-application meeting. March 29, 2023 SGW - Weekly call with Buckeye Gov't Relations Team. Need to submit an "Executive Summary" for dredging the Yabucoa Channel by this coming Friday to the Congresswoman from Puerto Rico. Tom Nash is pulling this together with Buckeye Commercial. March 15, 2023 - weekly call with Buckeye Gov't Relations team. Buckeye needs to develop an "Executive Summary" discussing the benefits of the Corps of Engineers taking over the dredging of the Yabucoa Channel. Tom Nash will take this on. 03/09/2023 CC - Remaining forecast remains at $780K, but updated per PM. March 3, 2023 SGW - sent my PowerPoint presentation to the Buckeye Gov't Relations team as background information. 03/02/2023 CC - Entered 600K in forecast pulled from "Yabucoa Dredging" project previously forecasted for $600K in 2023. Also added to the forecast was $180K that was forecasted on BCTYA00E2211. 03/01/2023 -A reclass totaling $50,435.05 was posted in February to move the remaining actuals on BCTYA00E2211 to BCTYA00M2219. The forecast for BCTYA00E2211 will need to be zeroed and incorporated in BCTYA00M2219 to reflect the MEXP to MCAP flip. 02.02.23 SDB: Received the revised proposal for the MPRSA 103 EPA sampling portion of the work. A third PO will need to be provided to MCJ to continue work without incurring delays. 01.31.23 SDB: Held initial meeting with the USFWS andNMFS to inform them of the upcoming project and receive comments from both agencies. Held meeting with the mayor of the Yabucoa municipality in order to request a letter of endorsement from them. 01.03.23 SDB: Costs will be reclasssed from the MEXP project. Additional funding is required for 2023. | 2023-05-02 | Coverley, Colleen | Clark, David | East | Pipelines and Terminals | Operating Infrastructure |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | 112634 | 134275 | 350000 | 240000 | 113056 |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 46390 |  | Meitzler, Antoinette | Independent | Aqua | 2022-12-20 | Other Programs
Yabucoa - Panalarm Replacement | Item | Open | MCAP | BCTYA00M2204 | Maintenance Framework | 1938138 | DeSocio, David | East | 7. Closed | Defined | Instrumentation & Controls | 0 |  |  | 0 |  | 0 | Green |  |  |  | 0 |  |  | 25000 |  |  | 25000 | Full | 25000 | 19304 |  | 19304 | No | Green | 2022-04-01 | 2022-01-13 | 2022-01-13 | 2022-06-01 | 2022-11-01 | [5 empty] | 0 |  |  | 0 | Green | [11 empty] | 1/3/2023 - Late billing from contractor 10/18/22 - Funds for 2022 will only cover Engineering and Design. Additional funds will be needed for 2023. 11/7/22 - Project will be completed in 2022 by local Team. | 2023-01-10 | Walker, Carol |  | East | Pipelines and Terminals | Operating Infrastructure |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 0 |  |  | 19304 |  | Forsey, Frank | Nash, Tom |  |  | 1 | 34813 |  | Guest, ProSight | Independent | Aqua | 2019-08-29 | Other Programs
Yabucoa - Upgrade 115KV Oil Circuit Breaker | Item | Open | MCAP | BCTYA00M2215 | Maintenance Framework | 1955482 | McPhee, Jaylon | East | 3. Active | Defined | Electrical | 49824 | 80000 |  | 129824 | 99824 | 30000 | Red |  |  |  | 129824 |  |  | 125000 |  |  | 125000 | Full | 125000 | 101923 | 80000 | 181923 | Yes | Red | 2022-07-01 | 2022-03-03 | 2022-03-03 | 2022-12-31 | 2023-08-31 |  |  | 48000 | 1824 | 0 | 0 |  |  | 0 | Green |  |  |  |  | 20000 | 40000 | 20000 |  |  |  |  | 05/022023 - Breaker is ready to be shipped. Civil work, crane and scaffolding to be be erected. Forecast adjusted to reflect timiing of installation and true project need. 04/04/2023 - Drawings have been approved . Fiield installation is projected to be $52K (additional $25K). A supplemental will be required for the installation of the transformer. Working on getting addtional quotes and supplemental will be submitted once numbers are determined. 3/1/2023 - Breaker remains on schedule to meet June forecast of $25K. An electrical team in the Yabucoa is currently conducting an assement of the full details that will be required to install the breaker. At this time the $25K is questioned to not be sufficient for the install, but once quotations are received the final and confirmed ETC will be known and potential for supplemental. 2/1/2023- Due to the lead time of the 115KV breaker, the estimated operational date has been updated to refllect August 2023. Forecast has also been updated. 12.09.22 - Expectation now to install CB is 5/23. KDB 08/22/22 - installation forecasted in Dec. 22 instead of Jan 23. Duplicate forecast in January was removed. with this project we have already ordered the 115kv Breaker. However, the lead time on the delivery of the breaker is 8 - 10 months and the breaker was ordered in April 2022, which will give a delivery date around December, 2022 to January, 2023. I don't forecast any work being done with installation until this breaker is delivered to the facility at Yabucoa. However, we can begin the rigging and removal of existing redundant electrical material to prepare for the installation of the new 115kv breaker. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | 49824 | 0 | 80000 |  | 52099 |  | Ashley, Robert | Davalos, Glenda |  |  | 1 | 40917 |  | Guest, ProSight | Independent | Aqua | 2021-08-04 | Other Programs
Yabucoa API 570 Inspection | Item | Open | MEXP | BCTYA00E2208 | Maintenance Framework | 1972376 | McDonald, Carnetta | East | 7. Closed | Defined | Facility Integrity | -9957 |  |  | -9957.2 | -17204 | 7247 | Red |  |  |  | -9957 |  |  | 50000 |  |  | 50000 | Full | 50000 | 52874 |  | 52874 | No | Green | 2022-05-01 | 2022-04-22 | 2022-04-22 | 2022-11-30 | 2022-12-31 |  |  | -9957.2 | 2361.17 | -2361.17 |  | -7247 | -7247 | 7247 | Red | [11 empty] | 04/18/2023 - Reclass of $2,361.17 was posted crediting the project in March instead of April as originally estimated. Scaffolding costs for January remain on project reducing the total reclass. Project closed per PM approval. 03/29/2023 - Reclass for scaffolding services to be posted in April 2023. Scaffolding posted to project after being reversed and reposted. 12/01/2022 -This inspection is 85% completed with an estimated completion date of December 30th, 2022. 10/10/22 KB - Postponed to October. 10/01/2022 - Api-570 Inspection has begun and slated for end of December completion. CLM 09/01/2022 - This project is still set to start in September 2022 but the Contractor, Project Specialist is currently having issues with ISN on obtaining a A or B grade in the system. They are currently working with Procurement/ISN to resolve this issue ASAP. CLM 08/01/2022 - Project on schedule to start September 2022, Gasoline lines at East Pipe track to TK-003-W1. CLM 05/01/2022 - This API-570 inspection is schedule for September, 2022. CLM | 2023-04-18 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | -9957 | 0 |  |  | 62831 |  | Aiken, Elaine | Orischak, Bob |  |  | 1 | 41188 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
Yabucoa Asbestos Abatement 2023 | Item | Open | MEXP | BCTYA00E2301 | Maintenance Framework | 2052955 | McPhee, Jaylon | East | 3. Active | Defined | Facility Integrity | 31012 | 70000 |  | 101011.74 | 103457 | -2445 | Yellow | 100000 |  | 100000 | 1012 |  |  | 101000 |  |  | 101000 | Full | 101000 | 31012 | 70000 | 101012 | No | Green | 2023-02-01 | 2022-12-20 | 2022-12-20 | 2023-12-31 | 2023-09-30 |  |  |  | 3456.74 | 15000 | 12555 | 25000 | 25000 | -12445 | Red |  | Contractor/Vendor Issue | 20000 | 20000 | 20000 | 10000 | [5 empty] | 05/02/2023 - Operational delays as contractor was awaiting the delivery of sand blasting equipment parts. Insulation was removed on pipes TK-14, TK-32, and TK-31. 4/4/23 - Project is progressing. waiting on JR Insulation to provide invoices. Continue to accrue 15k. 3/1/2023 - Delay in spending due to timing to confirm vendors were ISN certified, and quotes were requested to be resubmitted to ensure prices remained the same. Quotes are expected to be received within the next two weeks and project will resume scheduled spending. Forecast adjusted to begin spending April. 02/01/2023 - Project in the bid process to select contractor. Project forecast currently projecting accurate beginning of spend. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | 18457 | 52555 | 30000 |  |  |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 44494 |  | Guest, ProSight | Independent | Aqua | 2022-08-09 | Int - Planned Corr & FI
Yabucoa Facility Piping Upgrades - 2022 | Item | Open | MCAP | BCTYA00M2216 | Maintenance Framework | 1971892 | McDonald, Carnetta | East | 7. Closed | Defined | Facility Integrity | 113 |  |  | 112.78 | 113 | 0 | Green |  |  |  | 113 |  |  | 150000 |  |  | 150000 | Full | 150000 | 162537 |  | 162537 | No | Green | 2022-06-01 | 2022-04-20 | 2022-04-20 | 2022-10-31 | 2022-11-30 |  |  | 112.78 | [18 empty] | 12/01/2022 - Project completed within budget and on schedule. CLM 10/01/2022 - Another delay occurred due to Hurricane Fiona; two weeks. Gasoline Pipeline 8" support repairs were completed. Gasoline through TK-88 earth dike, a patch was installed on current clamp. Pipe supports at Gasoline pipeline pipe track from TK-40-41-42-43 completed. Project is now on schedule for end of December 2022 completion. CLM 09/01/2022 - This project is ongoing with a completion date of December 2022. Forecast not met due to minor operational delays. Remaining forecast from August has been pushed to September 2022. CLM 08/01/2022 - 1000FT OF 14" ULSD Line was replaced, 20% of welds were tested with X/rays and passed. Project is still on schedule for end of September 2022 completion. CLM 07/01/2022 - This project is experiencing operational delay. The work will resume this month, July 2022. CLM 06/01/2022 - This project is on schedule to start in June, 2022. A site visit was conducted once again in order to identified areas that will be impacted. The area for this work, pipe-rack south of TK-17 and TK-18. CLM 05/01/2022 -Forecast shifted from April to June 2022 due to availability of contractors for this work, therefore the work has been pushed back. CLM | 2022-12-06 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | 113 | 0 |  |  | 162424 |  | Aiken, Elaine | Orischak, Bob |  |  | 1 | 42660 |  | Clark, David | Independent | Aqua | 2022-01-03 | Int - Accel Corr & FI
Yabucoa Fire Water and Foam Headers Refurbishments Phase1 | Item | Open | MEXP | BCTYA00E2209 | Maintenance Framework | 1990352 | McPhee, Jaylon | East | 7. Closed | Defined | Fire Protection | -1 |  |  | -1.44 | 0 | -1 | Red |  |  |  | -1 |  |  | 30000 |  |  | 30000 | Full | 30000 | 29999 |  | 29999 | No | Green | 2022-08-01 | 2022-06-13 | 2022-06-13 | 2022-12-31 | 2023-01-31 |  |  | -1627.2 | 0 | 0 | 1625.76 | 1627 | 1627 | -1 | Yellow | [11 empty] | 05/02/2023 - Project ready to be close per PM. Project has been closed. 4/4/2023 - Project final forecast will be spent in April and project will be ready to close end of April 2023. 3/1/2023 - Project final forecast will be spent in March and project will be ready to close end of March 2023. 02/1/2023 - Project is operational. Final hydrant operational as of January 31st, 2023. Operational date updated to reflect same. | 2023-05-02 | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | -1627 | 1626 |  |  | 30000 |  | Jakubowski, Gregory | Nash, Tom |  |  | 1 | 41795 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Yabucoa Main Dock Loading Arms Repainting | Item | Open | MEXP | BCTYA00E2302 | Maintenance Framework | 2052958 | McPhee, Jaylon | East | 3. Active | Defined | Facility Integrity | 0 | 125500 | 12500 | 125500 | 125500 | 0 | Green | 125000 |  | 125000 | 500 |  |  | 138000 |  |  | 138000 | Full | 138000 | 0 | 138000 | 138000 | No | Green | 2023-05-01 | 2022-12-20 | 2022-12-20 | 2023-12-31 | 2023-08-31 | [5 empty] | 0 |  |  | 0 | Green |  |  | 62750 | 62750 | [6 empty] | 12500 | 04/04/2023 - Ship schedule did not allow window for painting in March. Project reforecasted for May/June completion. 3/1/2023 - The contractors had to be confrrmed to be in good standing with ISN. Additionally, new quotes were requested to ensure that prices would remain the same. Project forecasts are confirmed good per PM. 02/1/2023 - Project is in the bid process of selecting the contractor. At this time the forecast stands. | 2023-04-04 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 125500 |  |  |  |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 44977 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Yabucoa Main Dock Wharf Line Repairs | Item | Open | MEXP |  | Maintenance Framework |  | Wildgoose Thompsona, Tanya | East | 1. Proposed |  | Facility Integrity | 0 | 150000 |  | 150000 | 150000 | 0 | Green | 150000 |  | 150000 | 0 | [8 empty] | 0 | 150000 | 150000 | No | Green | 2023-08-01 |  |  |  | 2023-09-30 | [5 empty] | 0 |  |  | 0 | Green | [5 empty] | 75000 | 75000 | [8 empty] | East | Pipelines and Terminals | Station/Terminal |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 0 | 150000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 44978 |  | Administrator, System | Independent |  | 2022-08-18 | Int - Planned Corr & FI
Yabucoa Main Dock Wharf Lines API-570 Repairs | Item | Open | MEXP | BCTYA00E2203 | Maintenance Framework | 1947022 | McDonald, Carnetta | East | 7. Closed | Defined | Facility Integrity | 940 |  |  | 940.33 | 940 | 0 | Green |  |  |  | 940 |  |  | 114000 |  |  | 114000 | Full | 114000 | 122052 |  | 122052 | No | Green | 2022-03-01 | 2022-02-16 | 2022-02-16 | 2022-12-31 | 2022-11-30 |  |  | 599.33 | 341 | [17 empty] | 03/28/2023 - Project closed out. 03/01/2023 - Project is ready to be closed. 12/01/2022 - Project completed on time and within budget. CLM 10/01/2022 - Vessel delay at the dock prevented installation of patch and spools. All fabrication is completed pending installation at this time. Overall completion of this project is still on track for end of October 2022. CLM 09/01/2022 - Project on schedule, with a completion date, end of this month September 2022. CLM 08/01/2022 - Repairs started on the 24" F.O. line. Line emptied and filled with water in preparation. Three (3) scaffolds were removed and five (5) pending for installation in August 2022. The 20" gasoline line is now completed and hydrotest passed. This project is on schedule with minor delays and due for completion, end of September 2022. CLM 07/01/2022 - Contractor started preparation on the 20" gasoline regular line for weld repairs. Line was drained, and blinds installed. Line is being flushed with water. CLM 06/01/2022 - The work is ongoing with an overall completion of 75%. The welding repairs to ULSD completed and pipeline passed hydrotest. Welding repairs to the Premium Gasoline has begun. Once completed, hydrotest will commence for final completion. CLM 05/01/2022 - Continuing with coating and surface prep on the accessible piping from the platform at Main Dock. Scaffolding in progress for pipes with no platform facilities. Work is about 40% completed overall. Piping that requires welding will take place in June 2022, when hydrotest activities starts. CLM 04/01/2022 - Project forecast has been shifted from August to April 2022. Project is on schedule with no current delays. CLM 02/01/2022 - Submitting AFE this month, February 2022. CLM | 2023-03-28 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | 940 | 0 |  |  | 121112 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 41203 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
Yabucoa New Back Up FCU - 2460 (Tank Master) to sustain New TLR2 Protocol | Item | Candidate | MCAP |  | Maintenance Framework |  | Silva, Carmelo | East | 8. Canceled |  | Instrumentation & Controls | 0 |  |  | 0 |  | 0 | Green | 30000 |  | 30000 | -30000 | [8 empty] | 0 |  | 0 | No | Green |  |  |  |  | 2023-05-31 | [5 empty] | 0 |  |  | 0 | Green | [11 empty] | 04/04/2023 - Thought process is that project will be cancelled. Per PM project forecast has been zeroed. Pending scope is minimal and will be executed on Opex. 03/02/2023 - PM updated that AFE will be updated for March. Forecast would require no changes. 2/1/2023 - AFE to be submitted mid February. | 2023-04-04 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 0 |  |  |  |  | Forsey, Frank |  |  |  | 1 | 41776 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Yabucoa Pipe Support Upgrades 2022 | Item | Open | MCAP | BCTYA00M2217 | Maintenance Framework | 1991181 | McPhee, Jaylon | East | 7. Closed | Defined | Facility Integrity | 10570 |  |  | 10570.27 | 10570 | 0 | Green |  |  |  | 10570 |  |  | 115000 |  |  | 115000 | Full | 115000 | 118689 |  | 118689 | No | Green | 2022-08-01 | 2022-06-20 | 2022-06-20 | 2022-12-31 | 2022-12-31 |  |  | 10183.3 | 3386.97 | -3000 | [16 empty] | 03/29/2023 - Project closed out. 3/1/2023 - Project is ready to be closed. $3,000 actuals in February will be reclassed in March. 2/1/2023 - Project is complete. Project status updated to operational. PM confirming all works have been completed. 10-12-22 Project reforecasted to October due to delays in material receipts. DC | 2023-03-29 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | 10570 | 0 |  |  | 108119 |  | Aiken, Elaine | Davalos, Glenda |  |  | 1 | 41173 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
Yabucoa Pipe Support Upgrades 2023 | Item | Open | MCAP | BCTYA00M2301 | Maintenance Framework | 2084756 | Wildgoose Thompsona, Tanya | East | 3. Active | Defined | Facility Integrity | 50214 | 50000 |  | 100214.13 | 97686 | 2529 | Yellow | 85000 | 14425 | 99425 | 789 |  |  | 99425 |  |  | 99425 | Full | 99425 | 50214 | 50000 | 100214 | No | Green | 2023-03-01 | 2023-02-16 | 2023-02-16 | 2023-08-31 | 2023-08-31 |  |  |  |  | 22685.63 | 27528.5 | 25000 | 25000 | 2529 | Yellow |  |  | 20000 | 25000 | 5000 | [6 empty] | 2023-04-01 -Cleaning and painting of piping at support area on pipe rack south of TK-18 /17. Continue replacing corroded pipe support beam with galvanized steel beams and I-Rods at pipe-rack south of TK-18 /17. | 2023-05-03 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | 22686 | 72529 | 5000 |  |  |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 44975 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Yabucoa Piping API-570 Repairs 2023 | Item | Open | MEXP | BCTYA00E2306 | Maintenance Framework | 2085829 | Wildgoose Thompsona, Tanya | East | 3. Active | Defined | Facility Integrity | 81287 | 193794 |  | 275081.25 | 275000 | 82 | Yellow | 275000 |  | 275000 | 81 |  |  | 275000 |  |  | 275000 | Full | 275000 | 81287 | 193794 | 275081 | No | Green | 2023-03-01 | 2023-02-24 | 2023-02-24 | 2023-12-15 | 2023-12-31 |  |  |  |  | 11205.58 | 70081.67 | 50000 | 50000 | 20082 | Red |  | WorkAhead of Schedule | 30000 | 25000 | 50000 | 30000 | 30000 | 20000 | 5000 | 3794 |  | 2023-03-05 - replaced sections of pipes along the 14” Premium Gasoline Line. 25 weld saddle patches also installed. The Line sections were precoated for installation. This pre-work contributed to April overspend as compared to forecast. Man power and extra hours were worked to meet schedule provided by client. 2023-03-28 - Terminal received the client approval to take the line out of service for the repairs. -Line in process to be emptied for blinding and LOTO -2” RV’s discharge gasoline line was installed and placed in service. -14” Premium Gasoline Line -Patches continues to be fabricated at maintenance shop 2023-03-01 - Operations Delays: Line not available to work on waiting for client decision. | 2023-05-03 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | 11206 | 125082 | 110000 | 28794 |  |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 44976 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Yabucoa Piping Repairs 2022 | Item | Open | MEXP | BCTYA00E2206 | Maintenance Framework | 1956660 | McDonald, Carnetta | East | 7. Closed | Defined | Facility Integrity | 9240 |  |  | 9240 | 9240 | 0 | Green |  |  |  | 9240 |  |  | 275000 |  |  | 275000 | Full | 275000 | 289553 |  | 289553 | No | Green | 2022-03-01 | 2022-03-20 | 2022-03-20 | 2022-09-30 | 2022-12-31 |  |  |  |  | 9240 | [16 empty] | 12/01/2022 - Project slated to be completed December 15th, 2022. CLM 10/01/2022 - Delay due to awaiting pipeline availability from operations for repair patches. CLM 09/01/2022 - The work on this project was expediated, therefore the new completion date is end of this month, September 2022. Project on schedule, with no weather or operational delays. CLM 08/01/2022 - This project had some delays this month, due to the same contractor company working on this project, relocating to assist with the Yabucoa Piping Repairs project, to accommodate a client's cargo. Otherwise, this project is ongoing and schedule for an end of year completion. CLM 07/01/2022 - Replacement of 14" ULSD line tentative to start July 18th pending clients approval, operations. Upon completion of this work, all field welds will be painted, weather permitting. CLM 06/01/2022 - Additional piping material was ordered, 420 feet for the 14" dia. pipe. Schedule is now in progress for the crane to install pipes in the pipe track, as part of the preparation work. Materials for the 18" & 20" dia. pipes, are now on site. CLM 5.11.22.DLC: Reduced May per PM email 05/01/2022 -Sections of the 14" was blasted and prime at the warehouse yard. PO issued for materials 18" and 20" pipe sections, that will be delivered May 17th, 2022. Had issues with the abrasive blasting material (black beauty) availability on the island, resulted a two week delay. CLM 04/01/2022 - Project on schedule with no current delays. CLM 02/01/2022 - Submitting AFE this month, February 2022. CLM | 2023-04-03 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | 9240 | 0 |  |  | 280313 |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 41204 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
Yabucoa Power Transformer replacement at Power Center #6 | Item | Open | MCAP | BCTYA00M2212 | Maintenance Framework | 1946985 | Campbell, Jamie | East | 6. Operational | Defined | Electrical | -5322 |  |  | -5321.69 | -5322 | 0 | Green |  |  |  | -5322 |  |  | 100000 |  |  | 100000 | Full | 100000 | 102039 |  | 102039 | No | Green | 2022-03-01 | 2022-02-15 | 2022-02-15 | 2022-12-31 | 2022-12-31 |  |  | 1098.31 | -6420 | [17 empty] | 3/2/23 - Stair Electric invoice can be cancel, as the project is completed and there are no outstanding invoices. Project ready to close. 2/2/2023 - Star Electric invoice outstanding and required before project can be closed. 12/04/2022 - Transformer installed and commissioned. 10/7/22 KB - Transformer arrived in Sept; anticipated to arrive in Oct. 9/5/2022 Waiting delivery of transformer. 8/1/2022 - Transformer purchase and is schedule to arrive Yabucoa terminal in October. | 2023-03-06 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | -5322 | 0 |  |  | 107361 |  | Ashley, Robert | Davalos, Glenda |  |  | 1 | 41614 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
Yabucoa Small Dock API-570 Repairs | Item | Open | MEXP | BCTYA00E2303 | Maintenance Framework | 2052959 | McPhee, Jaylon | East | 3. Active | Defined | Facility Integrity | 67703 | 10000 |  | 77703.02 | 75379 | 2324 | Yellow | 75000 |  | 75000 | 2703 |  |  | 77000 |  |  | 77000 | Full | 77000 | 67703 | 10000 | 77703 | No | Green | 2023-02-01 | 2022-12-20 | 2022-12-20 | 2023-12-31 | 2023-06-30 |  |  |  | 3600 | 42309.87 | 21793.15 | 10760 | 10760 | 11033 | Red |  | Forecasting | 10000 | [8 empty] | 05/02/2023 - Reclass for $9,240.00 crediting project was posted. Mechanical repairs completed to the No 6 Fuel Oil Line. Hydrotest completed and line completely painted. Piping support continues and piping support repairs began. Scaffolding for various locations installed. 04/04/2023 - Reclass of $9,240 OFF of this project to happen in April. Incorrect project posting. Project is ongoing. 3/1/2023 - Contractor began working on project in February. Forecast moved up one month to account for the work that has began. 02/01/20203 - Project is active. Inspection company is expected to be selected in February. At this time the forecast stands. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | 45910 | 31793 |  |  |  |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 44979 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Yabucoa Terminal (BCTYA) Tank Outage Substitution Project | Item | Candidate | MEXP |  | Maintenance Framework |  | Campbell, Jamie | East | 1. Proposed |  | Tank Outage | 0 | 15000 |  | 15000 | 15000 | 0 | Green | 15000 |  | 15000 | 0 | [8 empty] | 0 | 15000 | 15000 | No | Green | 2023-06-01 |  |  |  | 2023-06-30 | [5 empty] | 0 |  |  | 0 | Green |  |  |  | 15000 | [11 empty] | East | Pipelines and Terminals | Tank Integrity |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 15000 |  |  |  |  | Stine, Carlton |  |  |  | 1 | 44305 |  | Stine, Carlton | Independent | Aqua | 2022-07-28 | Int - Tanks
Yabucoa Terminal (BCTYA) Tank TK-003-33 - OOS API 653 Insp | Item | Open | MCAP | BCTYA00M2303 | Maintenance Framework | 2093541 | Campbell, Jamie | East | 3. Active | Defined | Tanks | 37720 | 448000 |  | 485719.6 | 488000 | -2280 | Yellow | 488000 |  | 488000 | -2280 |  |  | 488000 |  |  | 488000 | Full | 488000 | 37720 | 448000 | 485720 | No | Green | 2023-04-01 | 2023-03-03 | 2023-03-03 | 2023-06-01 | 2023-10-31 | [5 empty] | 37719.6 | 40000 | 40000 | -2280 | Yellow |  |  | 20000 | 75000 | 90000 | 155000 | 108000 |  |  |  |  | 5/1/2023 - Tank cleaning scheduled to be completed May 11,2023. Inspection company schedule to start internal inspections immediately after tank cleaning. 04/04/2023 - Tank recently removed service for cleaning, inspections, and repairs. Long lead items (wind girder material and stair treads) have been ordered to assist in expediting tanks repairs. | 2023-05-05 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 132720 | 353000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44898 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Yabucoa Terminal (BCTYA) Tank TK-003-36 - OOS API 653 Insp | Item | Open | MCAP | BCTYA00M2218 | Maintenance Framework | 2043846 | Campbell, Jamie | East | 6. Operational | Defined | Tanks | 114411 |  |  | 114410.94 | 471409 | -356998 | Red | 488000 |  | 488000 | -373589 |  |  | 109000 |  |  | 109000 | Phase | 109000 | 131002 |  | 131002 | No | Green | 2022-11-01 | 2022-11-04 | 2022-11-04 | 2023-02-20 | 2023-04-15 |  |  | 9238.04 | 30463.63 | 61568.17 | 13141.1 | 25000 | 25000 | -11859 | Red |  | WorkAhead of Schedule | [9 empty] | 5/1/2023 - Tank project completed and ready for close. 4/17/23-CES-Per conversation with PM, reducing forecast by $330,000 and transferring over to tank 22 for installation of liner. 4/4/2023 - Tank mechanical repairs are completed. Tank coating in progress. 03/02/2023 - Tank stair treads and wind girder replacement are in progress. This tank is projecting to come in under budget, due to the minor repair scope. Tank mechanical repairs are schedule to wrap-up the first week of April. Coating of bottom and roof to follow. Tank is schedule to be under budget. 2/2/2023 - Tank bottom patches completed. Tank roof repairs in progress. Awaiting material delivery for stair treads and windgirder. 1/9/2023 - Tank inspection on going. Scope of work to follow once inspecting completed. Mechanical repairs to start in February. 12/4/2022 - Tank cleaning completed and Inspection is schedule for December 13, 2022. Tank Integrity decided to pull in Tank, for cleaning and inspection in 2022. | 2023-05-05 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | 101270 | 13141 |  |  | 16591 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44899 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Yabucoa Terminal (BCTYA) Tank TK-003-40 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP |  | Maintenance Framework |  | Campbell, Jamie | East | 1. Proposed |  | Tanks | 0 | 484000 |  | 484000 | 484000 | 0 | Green | 488000 |  | 488000 | -4000 | [8 empty] | 0 | 484000 | 484000 | No | Green | 2023-06-01 |  |  |  | 2023-06-30 | [5 empty] | 0 |  |  | 0 | Green |  |  |  | 20000 | 164000 | 100000 | 200000 | [8 empty] | East | Pipelines and Terminals | Integrity |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 20000 | 464000 |  |  |  | Stine, Carlton |  |  |  | 1 | 44900 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Yabucoa Terminal (BCTYA) Tank TK-003-41 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | BCTYA00M2302 | Maintenance Framework | 2093572 | Campbell, Jamie | East | 3. Active | Defined | Tanks | 0 | 565666 |  | 565666 | 565666 | 0 | Green | 488000 |  | 488000 | 77666 |  |  | 565666 |  |  | 565666 | Full | 565666 | 0 | 565666 | 565666 | No | Green | 2023-07-01 | 2023-03-03 | 2023-03-03 | 2023-08-01 | 2023-11-30 | [5 empty] | 0 |  |  | 0 | Green |  |  |  |  | 20000 | 50000 | 100000 | 200000 | 118000 | 77666 |  | 05/01/2023 - Risk based inspection completed.. | 2023-05-01 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 0 | 170000 | 395666 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44901 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Yabucoa Terminal (BCTYA) Tank TK-003-42 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP |  | Maintenance Framework |  | Campbell, Jamie | East | 1. Proposed |  | Tanks | 0 | 488000 |  | 488000 | 488000 | 0 | Green | 488000 |  | 488000 | 0 | [8 empty] | 0 | 488000 | 488000 | No | Green | 2023-08-01 |  |  |  | 2023-06-30 | [5 empty] | 0 |  |  | 0 | Green | [5 empty] | 20000 | 160000 | 108000 | 200000 | [6 empty] | East | Pipelines and Terminals | Integrity |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 0 | 180000 | 308000 |  |  | Stine, Carlton |  |  |  | 1 | 44902 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Yabucoa Terminal (BCTYA) Tank TK-003-43 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP |  | Maintenance Framework |  | Campbell, Jamie | East | 1. Proposed |  | Tanks | 0 | 488000 |  | 488000 | 488000 | 0 | Green | 488000 |  | 488000 | 0 | [8 empty] | 0 | 488000 | 488000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [5 empty] | 0 |  |  | 0 | Green |  |  |  |  | 20000 | 120000 | 150000 | 198000 | [7 empty] | East | Pipelines and Terminals | Integrity |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 0 | 290000 | 198000 |  |  | Stine, Carlton |  |  |  | 1 | 44903 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Yabucoa Terminal (BCTYA) Tank TK-003-22 – OOS Corr Insp & Refurb | Item | Open | MCAP | BCTYA00M2201 | Maintenance Framework | 1915795 | Campbell, Jamie | East | 3. Active | Defined | Tanks | 452848 | 346302 |  | 799150.03 | 458194 | 340957 | Red | 104600 | 385000 | 489600 | 309550 |  |  | 307000 | 664000 |  | 1356000 | Full | 1356000 | 965654 | 346302 | 1311956 | No | Green | 2022-03-01 | 2021-12-08 | 2021-12-08 | 2022-06-30 | 2023-05-31 |  |  | -6229.83 | 142469.4 | 162186.95 | 154421.51 | 142167 | 142167 | 12255 | Yellow |  | Other | 116000 | 166000 | 64302 | [6 empty] | 5/1/2023 - Tank mechanical repairs are completed, Door sheet x-rayed, no flaws founded. Post inspection completed by Project Specialist. Tank internal coating are in progress. 4/17/23-CES-Transferring $330,000 over to tank 22 from Yabucoa tank 36 for installation of a liner. 4/4/2023 Large April spend is projected for bottom repairs completion. Tank mechanical repairs are 80%completed. Waiting on Supply Chain with internal coating bids. 3/8/23 - Large forecast amounts due the tank repairs projected speed. 3/2/2023 - Tampa progress well in February, resulting in a variance by being ahead of schedule. The tank bottom repairs are 60% completed. Bottom repairs are projected to be completed the first week of April. 2/3/2023 - Project was delayed to accommodate Commerical request to return Tank 003-91 earlier. Tank repairs are in progress. Hand rails, sample hatch and roof repairs completed. Bottom plate repairs in progress. 1/9/2023 Tampa tank started work on Tank 22 1/10/2023. 12/4/2022 Tank material arrived at the terminal and is onsite to start repairs January 2, 2023. Terminal requested Tampa to start Tank 91 first, due to a Commercial deal for that tank. 11/4/2022 Tampa Tank has procured all the material and is scheduled to arrive the first week of December. 10/4/2022 Tank delayed due to the pasting of Hurricane Fiona by about three weeks. Tampa Tank is gearing up to be onsite by within two weeks. Tanks has extensive bottom patches to be completed. 9/1/2022 Tank inspection and scope of work developed. Tampa Tank is schedule to mobilize on September 20,2022.8/1/2022 Tank cleaning finally finished, and bottom & Interior inspection in progress. 7/5/2022 Tank cleaning was delayed by one week due to extreme weather. Tank inspectors are schedule to start July 12, 20226/01/2022 Tank cleaning is 60% completed, It is schedule to be completed the end of June. The tank was left with more heavier material in the center. The external inspection is completed, Internal inspection schedule to start immediately after cleaning.4/30/22 - Tank is currenting being clean by Aqua Vac. 4/1/2022 - Tank is LOTO, and turned over to the cleaning contractor (Aquavac)12/2/2021 - Phase 1 AFE Submitted | 2023-05-03 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | 298427 | 436422 | 64302 |  | 512806 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41353 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Yabucoa Terminal (BCTYA) Tank TK-003-32 – OOS Corr Insp & Refurb | Item | Open | MCAP | BCTYA00M2202 | Maintenance Framework | 1915707 | Campbell, Jamie | East | 3. Active | Defined | Tanks | 164088 | 168401 |  | 332489.29 | 332698 | -209 | Yellow | 127572 |  | 127572 | 204917 |  |  | 191000 | 170000 |  | 361000 | Full | 361000 | 195378 | 168401 | 363779 | No | Green | 2022-04-01 | 2022-03-14 | 2022-03-14 | 2022-06-30 | 2023-05-15 |  |  | 24683.8 | 19965.05 | 22322.33 | 97117.11 | 80000 | 80000 | 17117 | Red |  | Other | 77914 | 75000 | 15487 | [6 empty] | 05/01/2023 - Tank Mechanical repairs are in progress by Tampa Tank. 4/4/2023 - Large April spend is for projected material delivery and bottom and repairs expected to be completed by end of month. Tampa Tank was awarded the project, and have started bottom repairs. Tank wind girder and stair tread material have to be shipped from Tampa and other material is available in Puerto Rico. 03/02/2023 Inspection report is recently received, Scope of work being developed to submit into COUPA. Mechanical repairs to being last week of March. 2/3/2023 - Tank internal inspection in progress. 1/9/2023 - Tank cleaning in final stage. inspection is schedule to follow the on Jan 23, 2023. 12/4/2022 - Tank was emptied moving product with vac-truck, Tank cleaning to start December 14, 2022. Internal inspection to follow immediately afterwards. 11/4/2022 Tank pump down delayed, due to pump failures. Terminal had to locate a replacement pump to continue stripping product out of the tank. 10/4/2022 Tank is delayed being taken of service due to the passing of Hurricane Fiona. Tank is currently being prep to be removed from service and start the pumping down of the remainder of the product that is left inside. 9/1/2022 Waiting the tank to be removed from service 8/1/2022 Operations and Commercial team is waiting on a sale for the product inside tank to release it for OOS API inspections and upgrades. 7/5/2022 Yabucoa Operations can not afford to remove the tank out of service until October. 6/1/2022 Project schedule to start July 2022. 4/30/22 - Tank is schedule to be remove from service in July 2022. 12/2/2021 - Phase 1 AFE submitted | 2023-05-05 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | 66971 | 250031 | 15487 |  | 31290 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41354 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Yabucoa Terminal (BCTYA) Tank TK-003-91 – OOS Corr + Seal Insp & Refurb | Item | Open | MCAP | BCTYA00M2203 | Maintenance Framework | 1915764 | Campbell, Jamie | East | 6. Operational | Defined | Tanks | 666002 |  |  | 666001.64 | 644261 | 21741 | Yellow |  |  |  | 666002 |  |  | 307000 | 782000 |  | 1089000 | Full | 1089000 | 1207258 |  | 1207258 | Yes | Red | 2022-08-01 | 2021-12-08 | 2021-12-08 | 2022-06-30 | 2023-02-28 |  |  | 221587.31 | 139134.7 | 273538.91 | 31740.72 | 10000 | 10000 | 21741 | Red |  | Other | [9 empty] | 4/4/2023 - Large variance due to commercial requesting tank earlier for client needs. Tank repairs completed, waiting on final invoices to close the project. 3/2/2023 Tank coating is in process. Tank is in service. 2/3/2023 Tank mechanical repairs are completed. Tank bottom coating is in progress. Will meet Commercial delay for client. 1/9/2023 Tank 003-91 is over forecasted, due to Commercial requesting the Tank earlier the anticipated. Tampa Tank executed 90% of the repairs during before the New Year. Roof (cone/IFR) patches, bottom plate repairs, Stair treads and handrail replacement are completed. The tank foam dam and seal are the only outstanding items. Tampa tank place to complete all mechanical repairs by Jan 17, 2023. After, which the coating team will enter the tank to coat the bottom. 12/4/2022 Tampa Tank has started the repairs to tank 91. 50% of the material is onsite for the mechanical repairs. 11/4/2022Tank cleaning and external inspection completed. Internal inspection is in progress. 10/4/2022 Tank cleaning delayed due to the pasting of Fiona. Tank cleaning is in progress and is schedule to be completed by the end of the month. 9/5/2022 Tank was removed from service on 9/1/22. Tank LOTO and remainder of product removed with Vac-truck are completed. Turbine blowers installed to force ventilation to allow entry for cleaning. 8/1/2022 Tank on track to be release in September for OOS API Inspections. Yabucoa team schedule to place roof on high legs position the mid of August to facilitate removing tank from service. 6/6/2022 Tank schedule to be release in September, due to operational needs 6/01/2022 Project schedule to start july 2022. 4/30/22 - Tank is schedule to be removed from service in July 2022. 4/5/22 - Forecast pushed to due to material availability. DC 12/2/2022 - Phase 1 AFE submitted | 2023-04-09 | Coverley, Colleen |  | East | Pipelines and Terminals | Integrity |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | 634261 | 31741 |  |  | 541256 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41355 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Yabucoa Terminal Gasoline Line (East Side) API-570 Repairs | Item | Open | MEXP | BCTYA00E2307 | Maintenance Framework | 2112686 | McPhee, Jaylon | East | 3. Active | Defined | Facility Integrity | 0 | 72000 | 7500 | 72000 | 75000 | -3000 | Yellow | 75000 |  | 75000 | -3000 |  |  | 82500 |  |  | 82500 | Full | 82500 | 0 | 79500 | 79500 | No | Green | 2023-05-01 | 2023-04-26 | 2023-04-26 | 2023-08-31 | 2023-08-31 | [5 empty] | 0 |  |  | 0 | Green |  |  | 12000 | 20000 | 20000 | 20000 |  |  |  |  | 7500 | 05/02/2023- AFE has been approved. Finalizing contractor selection to begin work. Forecast pulled forward to begin spending in May, 04/04/2023 - Meeting and AFE prep scheduled for 2nd week of April. 3/1/2023 - AFEs remain pending at this time, but estimated to be submitted ed of March. At this time forecast stand. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 32000 | 40000 |  |  |  | Aiken, Elaine | Orischak, Bob |  |  | 1 | 44980 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Yabucoa Terminal Gasoline Line (West Side) API-570 Inspection | Item | Open | MEXP | BCTYA00E2308 | Maintenance Framework | 2119753 | McPhee, Jaylon | East | 3. Active | Defined | Facility Integrity | 0 | 30000 | 3000 | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 |  |  | 33000 |  |  | 33000 | Phase | 33000 | 0 | 33000 | 33000 | No | Green | 2023-07-01 | 2023-04-29 | 2023-04-29 | 2023-10-31 | 2023-06-30 | [5 empty] | 0 |  |  | 0 | Green |  |  |  |  | 30000 | [5 empty] | 3000 | 05/02/2023- AFE has been approved. Finalizing contractor selection to begin work. Forecast pushed to July based on inspector availability. Contractors currently working on tanks. 04/04/2023 Meeting and AFE prep scheduled for 2nd week of April. 3/1/2023 - AFE is estimated to be submitted end of March. At this time the forecast stands. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 0 | 30000 |  |  |  | Aiken, Elaine | Nash, Tom |  |  | 1 | 44981 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
ZA 19.7 Lehigh River CP system design | Item | Open | MEXP | GZ701LEE2301 | Maintenance Framework | 2086010 | Norton, Bill | East | 3. Active | Defined | Cathodic Protection | 0 | 15000 |  | 15000 | 15000 | 0 | Green | 15000 |  | 15000 | 0 |  |  | 14850 |  |  | 14850 | Full | 14850 | 0 | 15000 | 15000 | No | Green | 2023-07-01 | 2023-02-21 | 2023-02-21 | 2023-10-01 | 2023-11-30 | [5 empty] | 0 |  |  | 0 | Green |  |  |  |  | 15000 | [6 empty] | 5/2/23 Lake Superior to perform testing and design work. WRN | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Corrosion |  | Macungie Pipe | GZ701LE - GUTHSVILLE TO LEHIGHTON-16 |  |  | 0 | 15000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44356 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
ZG Macungie Station- Manifold piping paint | Item | Open | MCAP | ZG00000M2306 | Maintenance Framework | 2086587 | Mohr, David | East | 3. Active | Defined | Atmospheric Corrosion | 0 | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 |  |  | 39672 |  |  | 39672 | Full | 39672 | 0 | 40000 | 40000 | No | Green | 2023-06-01 | 2023-02-27 | 2023-02-27 | 2023-05-31 | 2023-06-30 | [5 empty] | 0 | 40000 | 40000 | -40000 | Red |  | Contractor/Vendor Issue |  | 40000 | [7 empty] | 5/1/2023 Variance due to contractor schedule and weather. 4/4/2023 Issuing PO to Barr-None. 3/1/2023 Reach out to Barr-None to schedule | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 40000 |  |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44314 |  | Guest, ProSight | Independent | Aqua | 2022-07-28 | Int - Planned Corr & FI
ZG Macungie Station Sump Pump Replacement | Item | Open | MCAP | ZG00000M2310 | Maintenance Framework | 2096638 | Pepe, David | East | 3. Active | Defined | Rotating Equipment | 0 | 89000 |  | 89000 | 89000 | 0 | Green | 79000 |  | 79000 | 10000 |  |  | 90685 |  |  | 90685 | Full | 90685 | 0 | 89000 | 89000 | No | Green | 2023-05-01 | 2023-03-30 | 2023-03-30 | 2023-11-30 | 2023-04-30 | [5 empty] | 0 | 0 | 0 | 0 | Green |  |  | 7500 | 11500 |  | 13000 |  | 57000 |  |  |  | 4/1/2023 - Equipment and Installation quotes have been received. AFE to be submitted. | 2023-03-23 | Sautter, Maureen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Pipe | ZG - MACUNGIE STATION |  |  | 19000 | 13000 | 57000 |  |  | Posipanko, Dan | Posipanko, Daniel A. |  |  | 1 | 44309 |  | Guest, ProSight | Independent | Aqua | 2022-07-28 | Other Programs
2020 Buckeye Criteria Digs for line WV190ES | Item | Open | MCAP | WV190HOM2001 | Exempt | 1781980 | Kosior, Albert | ECS Pipeline Integrity | 7. Closed | Drawdown | Pipeline Digs | -4139 |  |  | -4138.96 | -4139 | 0 | Green |  |  |  | -4139 |  |  | 103000 |  | 12000 | 115000 | Supplemental | 115000 | 0 |  | 0 | No | Green | 2020-12-01 | 2020-12-03 | 2020-12-03 | 2020-12-31 | 2020-12-31 |  |  |  |  | -4138.96 | [16 empty] | 1-8-21 Dig was completed in December, site was found to be contaminated and had to dispose of spoils. 12-7-2020 AFE is pending approval, work to be completed in December. 11/25/2020- AFE submitted today for $103k 10/6/20 - Conducting kickoff mtg with InterCon this month and will get AFE submitted by end of month. Looking to perform dig after completion of the 163 digs in late November. 9/8/20 - Project will go to Intercon, need to have kick off meeting, working details 5/8/20 - Digs scheduled for 3rd quarter. | 2021-01-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | St. Louis | WV190HO - WOOD RIVER TO HORSESHOE LAKE |  | -4139 | 0 |  |  |  |  | Bartal, Nick | Bassani, Joel D. |  |  | 1 | 36304 |  | Kabaria, Erika | Independent | Aqua | 2020-03-13
2020 Line 761 Pipeline Repair MEXP Flips | Item | Open | MEXP | XX761NBE2001 | Exempt | 1688987 | Kosior, Albert | ECS Pipeline Integrity | 7. Closed | Drawdown | Pipeline Digs | 3267 |  |  | 3267.46 | 3267 | 0 | Green |  |  |  | 3267 |  |  | 70000 |  |  | 70000 | Full | 70000 | 100846 |  | 100846 | No | Green | 2020-02-01 | 2020-03-03 | 2020-03-03 |  | 2020-12-31 |  |  |  |  | 3267.46 | [16 empty] | 12-7-2020 Confirming the flip was complete and that the project can be closed out. 11/9/20 - AFE approved for capital to expense flips. Need to confirm in Nov that we can close this out. | 2020-12-07 | Hill, Elizabeth | Kosior, Al | West | Pipelines and Terminals | Pipeline Integrity |  | Sugar Creek | XX761NB - MO S/L TO COUNCIL BLUFFS |  | 3267 | 0 |  |  |  |  | Bartal, Nick | Bassani, Joel D. | N/A |  | 1 | 36217 |  | Bassani, Joel | JDE Child |  | 2020-03-07
2022 - EN913EW - Pressure Test and Go/No-Go ILI | Item | Open | MEXP | EN913EWE2201 | Maintenance Framework | 1957360 | Garcia, Francisco | ECS Pipeline Integrity | 7. Closed | Defined | Assessments | 1745 |  |  | 1744.96 | 1745 | 0 | Green |  |  |  | 1745 |  |  | 136000 |  |  | 136000 | Full | 136000 | 82457 |  | 82457 | No | Green | 2022-09-01 | 2022-03-28 | 2022-03-28 | 2022-11-30 | 2022-02-01 |  |  | 1744.96 | [18 empty] | 10/4/2022 - Buckeye emergency delayed project. 09-12-22 Will conduct pressure test but not the Go no go portion of the project | 2022-10-04 | Walker, Carol |  | East | Pipelines and Terminals | Pipeline Integrity |  | Jet Lines | EW913RW - NEW HAVEN TO MIDDLETOWN JCT |  | 1745 | 0 |  |  | 80712 |  | Bartal, Nick |  |  |  | 1 | 40623 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Assessments
2022 - PN160AG - Pressure Test | Item | Open | MEXP | PN160AGE2202 | Maintenance Framework | 2012527 | Kosior, Albert | ECS Pipeline Integrity | 6. Operational | Defined | Assessments | 1314 |  |  | 1314.48 | 180 | 1134 | Red |  |  |  | 1314 |  | Other | 859000 |  |  | 859000 | Full | 859000 | 815530 |  | 815530 | No | Green | 2022-08-01 | 2022-08-29 | 2022-08-29 | 2022-12-31 | 2022-12-08 |  |  | 90 | 0 | 90.43 | 1134.05 |  |  | 1134 | Red | [11 empty] | 12-8-22 Finished grading tank dike floor for Argo Tank #14, working closeout and final invoicing. 11-6-22 Working closeout, have some minor restoration to complete in the dike at tank 14. 10-10-22 Working project closeout. Waiting on final WM invoices for PCW and spoils. Need to perform grading work in tank 14 dike due to ruts from water filtration. Final cost is estimated to come in at or just below AFE. 9-12-22 The hydrotest was successfully completed on 9/1/22. The test went longer than planned due to the need to temper the water longer. Additional costs were also incurred due to a release of hydrotest water at Peotone that requires cleanup. 8-9-22 The work is scheduled for the last week of August and the first week of September. The AFE to be submitted directly. 7-12-22 Working plan, schedule looking to be the laws week in august, first of September. 6/9/22 - Working on plan with OM. Have requested tankage at Argo for the month of August. 5-9-22 Developing plan. 4-7-22 Developing plan. 3-7-22 Working on gather information on requested pipeline cutouts to be completed when the line is purged. There are 2 stopple fittings identified for removal. | 2022-12-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Argo | PN160AG - PEOTONE TO ARGO |  | 180 | 1134 |  |  | 814216 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40706 |  | Administrator, System | Independent | Aqua | 2021-07-24 | Int - Assessments
2022 - PR609OB - ILI | Item | Open | MEXP | PR609OBE2201 | Maintenance Framework | 2023162 | Garcia, Francisco | ECS Pipeline Integrity | 7. Closed | Defined | Assessments | -24449 |  |  | -24449.48 | -24449 | 0 | Green |  |  |  | -24449 |  |  | 110000 |  |  | 110000 | Full | 110000 | 51472 |  | 51472 | No | Green | 2022-10-01 | 2022-09-20 | 2022-09-20 | 2022-12-31 | 2022-11-29 |  |  | -24449.48 | [18 empty] | 2/2/2023 cost came in less than Dec. accrual for Enduro. 12/2/2022 savings due to using Buckeye internal labor. | 2023-02-02 | Walker, Carol |  | East | Pipelines and Terminals | Pipeline Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | -24449 | 0 |  |  | 75921 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40634 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Assessments
2022 - PR999A1 Short Line Pressure Test | Item | Open | MEXP | BPRPR00E2224 | Maintenance Framework | 2023167 | Garcia, Francisco | ECS Pipeline Integrity | 7. Closed | Defined | Assessments | 977 |  |  | 976.88 | 977 | 0 | Green |  |  |  | 977 |  |  | 75000 |  |  | 75000 | Full | 75000 | 77798 |  | 77798 | No | Green | 2022-10-01 | 2022-11-04 | 2022-11-04 | 2022-12-31 | 2022-10-30 |  |  | 976.88 | [18 empty] | 01/04/2022 Spool fabrication and PSEG backup. 11/2/2022 savings from use of in-house labor; full afe submitted; approval pending. 10/4/2022 project to start next week. | 2023-01-04 | Walker, Carol |  | East | Pipelines and Terminals | Pipeline Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 977 | 0 |  |  | 76821 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40635 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Assessments
2023 Annual Criteria Digs - LA401CB-1 | Item | Open | MCAP | LA401ELM2301 | Maintenance Framework | 2094150 | Melcer, Paul | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Digs | 10162 | 130000 |  | 140161.55 | 172698 | -32537 | Red | 170000 |  | 170000 | -29838 |  |  | 198050 |  |  | 198050 | Full | 198050 | 10162 | 130000 | 140162 | No | Green | 2023-03-01 | 2023-03-07 | 2023-03-07 | 2023-12-31 | 2023-08-31 |  |  |  |  | 2698.4 | 7463.15 |  |  | 7463 | Red |  |  |  | 70000 | 60000 | [8 empty] | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Lima Pipelines | LA401EL - LIMA TO ELLIOTT |  | 2698 | 77463 | 60000 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44921 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int- Planned Digs
2023 Annual Criteria Digs - LA410-411-414DS-1 | Item | Open | MCAP | LA410FJM2301 | Maintenance Framework | 2094889 | Melcer, Paul | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Digs | 21906 | 140000 |  | 161905.68 | 172094 | -10189 | Yellow | 170000 |  | 170000 | -8094 |  |  | 198050 |  |  | 198050 | Full | 198050 | 21906 | 140000 | 161906 | No | Green | 2023-03-01 | 2023-03-12 | 2023-03-12 | 2023-12-31 | 2023-09-30 |  |  |  |  | 2094.24 | 19811.44 |  |  | 19811 | Red |  |  | 15000 | 125000 | [9 empty] | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Lima Pipelines | LA410FJ - LIMA-FINDLAY JCT#9&#11-12IN |  | 2094 | 159811 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44924 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int- Planned Digs
2023 Annual Criteria Digs - RD401IL | Item | Open | MCAP | RD401CBM2301 | Maintenance Framework | 2095188 | Melcer, Paul | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Digs | 13465 | 610000 |  | 623465.03 | 610000 | 13465 | Yellow | 610000 |  | 610000 | 13465 |  |  | 683200 |  |  | 683200 | Phase | 683200 | 13465 | 610000 | 623465 | No | Green | 2023-04-01 | 2023-03-09 | 2023-03-09 | 2023-12-31 | 2023-07-31 | [5 empty] | 13465.03 |  |  | 13465 | Red |  |  |  | 300000 | 310000 | [8 empty] | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Lima Pipelines | RD401CB - HILLIARDS TO COLUMBUS |  |  | 313465 | 310000 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44922 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int- Planned Digs
2023 Annual Criteria Digs - UG761NB | Item | Open | MCAP | XX761NBM2301 | Maintenance Framework | 2095606 | Melcer, Paul | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Digs | 116038 | 140000 |  | 256037.95 | 446052 | -190014 | Red | 440000 |  | 440000 | -183962 |  |  | 512600 |  |  | 512600 | Full | 512600 | 116038 | 140000 | 256038 | No | Green | 2023-03-01 | 2023-03-19 | 2023-03-19 | 2023-08-31 | 2023-08-31 |  |  |  |  | 6052.09 | 109985.86 | 200000 | 200000 | -90014 | Red |  |  | 140000 | 0 | [9 empty] | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | XX761NB - MO S/L TO COUNCIL BLUFFS |  | 6052 | 249986 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44927 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int- Planned Digs
2023 Annual Criteria Digs - WF208WB | Item | Open | MCAP | WF208WBM2301 | Maintenance Framework | 2093971 | Melcer, Paul | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Digs | 24485 | 350000 |  | 374485.12 | 333783 | 40702 | Red | 330000 | 76953 | 406953 | -32468 |  |  | 406953 |  |  | 406953 | Full | 406953 | 24485 | 350000 | 374485 | No | Green | 2023-03-01 | 2023-04-14 | 2023-04-14 | 2023-12-31 | 2023-09-30 |  |  |  |  | 3782.8 | 20702.32 |  |  | 20702 | Red |  |  | 350000 | [10 empty] | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | WF208WB - FLINT TO BAY CITY |  | 3783 | 370702 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44918 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int- Planned Digs
2023 Annual Criteria Digs - WO165ZI | Item | Open | MCAP | WO165EFM2301 | Maintenance Framework | 2095604 | Melcer, Paul | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Digs | 25391 | 235000 |  | 260391.43 | 375524 | -115132 | Red | 375000 |  | 375000 | -114609 |  |  | 420000 |  |  | 420000 | Full | 420000 | 25391 | 235000 | 260391 | No | Green | 2023-03-01 | 2023-03-18 | 2023-03-18 | 2023-12-31 | 2023-09-30 |  |  |  |  | 523.56 | 24867.87 |  |  | 24868 | Red |  |  | 235000 | [8 empty] | 2-13-23 Dig have been issued. Developing project now. 1-10-23 Digs have not been issued yet | 2023-02-13 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | St. Louis | WO165EF - WOOD RIVER TO EFFINGHAM |  | 524 | 259868 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44916 |  | Administrator, System | Independent | Aqua | 2022-08-18 | Int- Planned Digs
2023 UI999A1 - Pressure Test | Item | Open | MEXP | UI999A1E2301 | Maintenance Framework |  | Melcer, Paul | ECS Pipeline Integrity | 2. Pending AFE | Defined | Assessments |  | 88000 |  | 88000 | 88000 | 0 | Green | 90000 |  | 90000 | -2000 |  |  | 88000 |  |  |  | Full | 88000 |  | 88000 | 88000 | No | Green | 2023-10-01 |  |  | 2023-12-31 | 2023-06-30 | [17 empty] | 88000 |  |  |  | 5/5/23 - Test planning on hold while regulatory determination is reviewed. Not yet canceled | 2023-05-05 | Williams, Nikole |  | South | Pipelines and Terminals | Pipeline Integrity |  | Tennessee | BSEUI - KNOXVILLE I TERMINAL |  |  | 0 |  | 88000 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44705 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 UK999A1 - Pressure Test | Item | Open | MEXP | UK999A1E2301 | Maintenance Framework |  | Melcer, Paul | ECS Pipeline Integrity | 2. Pending AFE | Defined | Assessments |  | 50000 |  | 50000 | 50000 | 0 | Green | 90000 |  | 90000 | -40000 |  |  | 88000 |  |  |  | Full | 88000 |  | 50000 | 50000 | No | Green | 2023-10-01 |  |  | 2023-12-31 | 2023-05-31 | [17 empty] | 50000 |  |  |  | 5/5/23 - Test planning on hold while regulatory determination is reviewed. Not yet canceled | 2023-05-05 | Williams, Nikole |  | South | Pipelines and Terminals | Pipeline Integrity |  | Tennessee | BSEUK - KNOXVILLE II TERMINAL |  |  | 0 |  | 50000 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44706 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 VD999A1 - Pressure Test | Item | Open | MEXP | VD999A1E2301 | Maintenance Framework |  | Melcer, Paul | ECS Pipeline Integrity | 2. Pending AFE | Defined | Assessments |  | 50000 |  | 50000 | 50000 | 0 | Green | 90000 |  | 90000 | -40000 |  |  | 88000 |  |  |  | Phase | 88000 |  | 50000 | 50000 | No | Green | 2023-10-01 |  |  |  | 2023-05-31 | [17 empty] | 50000 |  |  |  | 5/5/23 - Test planning on hold while regulatory determination is reviewed. Not yet canceled | 2023-05-05 | Williams, Nikole |  | South | Pipelines and Terminals | Pipeline Integrity |  | North Carolina | BSEVD - CHARLOTTE II TERMINAL |  |  | 0 |  | 50000 |  |  | Bartal, Nick | Baldwin, T. Andy |  |  | 1 | 44717 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 VD999A2 - Pressure Test | Item | Open | MEXP | VD999A2E2301 | Maintenance Framework |  | Melcer, Paul | ECS Pipeline Integrity | 2. Pending AFE | Defined | Assessments |  | 88000 |  | 88000 | 88000 | 0 | Green | 90000 |  | 90000 | -2000 |  |  | 88000 |  |  |  | Phase | 88000 |  | 88000 | 88000 | No | Green | 2023-10-01 |  |  | 2023-12-31 | 2023-06-30 | [17 empty] | 88000 |  |  |  | 5/5/23 - Test planning on hold while regulatory determination is reviewed. Not yet canceled | 2023-05-05 | Williams, Nikole |  | South | Pipelines and Terminals | Pipeline Integrity |  | North Carolina | BSEVD - CHARLOTTE II TERMINAL |  |  | 0 |  | 88000 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44718 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 VE999A1 - Pressure Test | Item | Open | MEXP |  | Maintenance Framework |  | Melcer, Paul | ECS Pipeline Integrity | 2. Pending AFE | Defined | Assessments |  | 88000 |  | 88000 | 88000 | 0 | Green | 90000 |  | 90000 | -2000 | [6 empty] | Phase |  |  | 88000 | 88000 | No | Green | 2023-10-01 |  |  |  | 2023-06-30 | [17 empty] | 88000 |  |  |  | 5/5/23 - Test planning on hold while regulatory determination is reviewed. Not yet canceled | 2023-05-05 | Williams, Nikole |  | South | Pipelines and Terminals | Pipeline Integrity |  | Alabama | BSEVE - BIRMINGHAM SOUTH TERMINAL |  |  | 0 |  | 88000 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44719 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 VF999A1 - Pressure Test | Item | Open | MEXP | VF999A1E2301 | Maintenance Framework |  | Melcer, Paul | ECS Pipeline Integrity | 2. Pending AFE | Defined | Assessments |  | 88000 |  | 88000 | 88000 | 0 | Green | 90000 |  | 90000 | -2000 |  |  | 88000 |  |  |  | Phase | 88000 |  | 88000 | 88000 | No | Green | 2023-10-01 |  |  | 2023-12-31 | 2023-07-31 | [17 empty] | 88000 |  |  |  | 5/5/23 - Test planning on hold while regulatory determination is reviewed. Not yet canceled | 2023-05-05 | Williams, Nikole |  | South | Pipelines and Terminals | Pipeline Integrity |  | Tennessee | BSEVF - CHATTANOOGA II TERMINAL |  |  | 0 |  | 88000 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44720 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 VH999A1 - Pressure Test | Item | Open | MEXP | VH999A1E2301 | Maintenance Framework |  | Melcer, Paul | ECS Pipeline Integrity | 2. Pending AFE | Defined | Assessments |  | 88000 |  | 88000 | 88000 | 0 | Green | 90000 |  | 90000 | -2000 |  |  | 88000 |  |  |  | Phase | 88000 |  | 88000 | 88000 | No | Green | 2023-10-01 |  |  | 2023-12-31 | 2023-07-31 | [17 empty] | 88000 |  |  |  | 5/5/23 - Test planning on hold while regulatory determination is reviewed. Not yet canceled | 2023-05-05 | Williams, Nikole |  | South | Pipelines and Terminals | Pipeline Integrity |  | Georgia | BSEVH - DORAVILLE I TERMINAL |  |  | 0 |  | 88000 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44721 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 VH999A2 - Pressure Test | Item | Open | MEXP | VH999A2E2301 | Maintenance Framework |  | Melcer, Paul | ECS Pipeline Integrity | 2. Pending AFE | Defined | Assessments |  | 88000 |  | 88000 | 88000 | 0 | Green | 90000 |  | 90000 | -2000 |  |  | 88000 |  |  |  | Phase | 88000 |  | 88000 | 88000 | No | Green | 2023-10-01 |  |  | 2023-12-31 | 2023-08-31 | [17 empty] | 88000 |  |  |  | 5/5/23 - Test planning on hold while regulatory determination is reviewed. Not yet canceled | 2023-05-05 | Williams, Nikole |  | South | Pipelines and Terminals | Pipeline Integrity |  | Georgia | BSEVH - DORAVILLE I TERMINAL |  |  | 0 |  | 88000 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44722 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 VK999A1 - Pressure Test | Item | Open | MEXP |  | Maintenance Framework |  | Melcer, Paul | ECS Pipeline Integrity | 2. Pending AFE | Defined | Assessments |  | 88000 |  | 88000 | 88000 | 0 | Green | 90000 |  | 90000 | -2000 | [6 empty] | Phase |  |  | 88000 | 88000 | No | Green | 2023-10-01 |  |  |  | 2023-08-31 | [17 empty] | 88000 |  |  |  | 5/5/23 - Test planning on hold while regulatory determination is reviewed. Not yet canceled | 2023-05-05 | Williams, Nikole |  | South | Pipelines and Terminals | Pipeline Integrity |  | Georgia | BSEVK - DORAVILLE II TERMINAL |  |  | 0 |  | 88000 |  |  | Bartal, Nick | Baldwin, T. Andy |  |  | 1 | 44723 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 VP999A1 - Pressure Test | Item | Open | MEXP | VP999A1E2301 | Maintenance Framework |  | Melcer, Paul | ECS Pipeline Integrity | 2. Pending AFE | Defined | Assessments |  | 88000 |  | 88000 | 88000 | 0 | Green | 90000 |  | 90000 | -2000 |  |  | 88000 |  |  |  | Phase | 88000 |  | 88000 | 88000 | No | Green | 2023-10-01 |  |  | 2023-12-31 | 2023-09-30 | [17 empty] | 88000 |  |  |  | 5/5/23 - Test planning on hold while regulatory determination is reviewed. Not yet canceled | 2023-05-05 | Williams, Nikole |  | South | Pipelines and Terminals | Pipeline Integrity |  | North Carolina | BSEVP - GREENSBORO I TERMINAL |  |  | 0 |  | 88000 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44724 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 VP999A2 - Pressure Test | Item | Open | MEXP | VP999A2E2301 | Maintenance Framework |  | Melcer, Paul | ECS Pipeline Integrity | 2. Pending AFE | Defined | Assessments |  | 88000 |  | 88000 | 88000 | 0 | Green | 90000 |  | 90000 | -2000 |  |  | 88000 |  |  |  | Phase | 88000 |  | 88000 | 88000 | No | Green | 2023-10-01 |  |  | 2023-12-31 | 2023-09-30 | [17 empty] | 88000 |  |  |  | 5/5/23 - Test planning on hold while regulatory determination is reviewed. Not yet canceled | 2023-05-05 | Williams, Nikole |  | South | Pipelines and Terminals | Pipeline Integrity |  | North Carolina | BSEVP - GREENSBORO I TERMINAL |  |  | 0 |  | 88000 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44725 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 VV999A1 - Pressure Test | Item | Open | MEXP | VV999A1E2301 | Maintenance Framework |  | Melcer, Paul | ECS Pipeline Integrity | 2. Pending AFE | Defined | Assessments |  | 50000 |  | 50000 | 50000 | 0 | Green | 90000 |  | 90000 | -40000 |  |  | 88000 |  |  |  | Full | 88000 |  | 50000 | 50000 | No | Green | 2023-10-01 |  |  | 2023-12-31 | 2023-05-31 | [17 empty] | 50000 |  |  |  | 5/5/23 - Test planning on hold while regulatory determination is reviewed. Not yet canceled | 2023-05-05 | Williams, Nikole |  | South | Pipelines and Terminals | Pipeline Integrity |  | North Carolina | BSEVV - GREENSBORO II TERMINAL |  |  | 0 |  | 50000 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44728 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 VV999A2 - Pressure Test | Item | Open | MEXP | VV999A2E2301 | Maintenance Framework |  | Melcer, Paul | ECS Pipeline Integrity | 2. Pending AFE | Defined | Assessments |  | 88000 |  | 88000 | 88000 | 0 | Green | 90000 |  | 90000 | -2000 |  |  | 88000 |  |  |  | Full | 88000 |  | 88000 | 88000 | No | Green | 2023-10-01 |  |  | 2023-12-31 | 2023-06-30 | [17 empty] | 88000 |  |  |  | 5/5/23 - Test planning on hold while regulatory determination is reviewed. Not yet canceled | 2023-05-05 | Williams, Nikole |  | South | Pipelines and Terminals | Pipeline Integrity |  | North Carolina | BSEVV - GREENSBORO II TERMINAL |  |  | 0 |  | 88000 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44729 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2024 - PY740MX - Purge and Multiple Cutouts | Item | Candidate | MCAP |  | Project Framework |  | Garcia, Francisco | ECS Pipeline Integrity | 1. Proposed |  | Pipeline Digs |  | 100000 |  | 100000 | 100000 | 0 | Green |  |  |  | 100000 | [9 empty] | 3000000 | 3000000 | No | Green | 2023-10-01 |  |  |  | 2024-12-31 | [17 empty] | 100000 | [7 empty] | East | Pipelines and Terminals | Integrity |  | Malvern | PY740XX - PAULSBORO TO PA S/L(MALVERN) |  |  | 0 |  | 100000 |  | 2900000 | Bartal, Nick |  |  |  | 1 | 46732 |  | Bartal, Nick | Independent | Aqua | 2023-03-09
AG160DN Immediate Digs 2022 | Item | Open | MCAP | AG160DNM2201 | Maintenance Framework | 2022711 | Kosior, Albert | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | -26062 |  |  | -26062.22 | -26062 | 0 | Green |  |  |  | -26062 |  | Other | 234000 |  |  | 234000 | Full | 234000 | 230495 |  | 230495 | No | Green | 2022-09-01 | 2022-10-18 | 2022-10-18 | 2022-09-23 | 2022-11-07 |  |  | -26062.22 | [18 empty] | 1/10/22 - Inspection charges from 160 cut outs charged to this project reclass submitted 11-6-22 Working closeout, managing waste spoils disposal. 10-10-22 Dig was completed last month, working restoration work and spoils disposal. Dig was more complicated due to it being located under the concrete curb of a gas station along Rte. 83. There was also a large storm water pipe over the pipeline that had to be removed to access the anomaly feature. | 2023-01-10 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Argo | AG160DN - ARGO TO DES PLAINES |  | -26062 | 0 |  |  | 256558 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 45833 |  | Schultz, Amy | Independent | Aqua | 2022-09-13 | Int- Planned Digs
AR760HH Relocation at I-380 Crossing | Item | Open | MCAP | AR760HHM2201 | Project Framework | 2011814 | Segraves, Scott | ECS Pipeline Integrity | 3. Active | Emergent | Pipeline Replacements | 126191 | 1435000 |  | 1561191.42 | 1526881 | 34310 | Yellow | 1500000 |  | 1500000 | 61191 |  |  | 194000 |  |  | 194000 | Phase | 194000 | 172314 | 1435000 | 1607314 | No | Green | 2022-09-01 | 2022-08-25 | 2022-08-25 | 2023-05-30 | 2023-09-30 |  |  | 25226.49 | 25409.67 | 26244.8 | 49310.46 | 15000 | 15000 | 34310 | Red |  |  | 15000 | 750000 | 640000 | 25000 | 5000 |  |  |  |  | 5/3/2023 - SAS - Overspend for April 2023 caused by engineering costs all hitting in a single month. 3/2/2023 - SAS - Slight overspend for February 2023 caused by slightly higher invoicing from engineering provider. 2/2/2023 - SAS - Slight overspend for January 2023 caused by slightly higher invoicing from engineering provider. 1/5/2023 - SAS - Slight overspend for December 2022 caused by slightly higher invoicing from engineering provider. 12/5/2022 - Full engineering and permitting started. | 2023-05-03 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Eastern Iowa | AR760HH - CEDER RAPIDS TO HARPER STA |  | 76881 | 814310 | 670000 |  | 46123 |  | Oldham, David | Boone, David G. |  |  | 1 | 44465 |  | Meitzler, Antoinette | Independent | Aqua | 2022-08-09 | Other Programs
AR760HH_1119_1124 Shallow Pipe | Item | Open | MCAP | AR760HHM2301 | Project Framework | 2075766 | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Defined | Shallow Pipe Remediation | 146175 | 1760000 |  | 1906175.06 | 1898954 | 7221 | Yellow |  |  |  | 1906175 |  |  | 218900 |  |  | 218900 | Phase | 218900 | 146175 | 1760000 | 1906175 | No | Green | 2023-01-01 | 2023-01-18 | 2023-01-18 |  | 2023-05-31 |  |  | 46307.21 | 36381.06 | 46266.21 | 17220.58 | 10000 | 10000 | 7221 | Red |  |  | 10000 | 800000 | 950000 | [6 empty] | 3/8/23 NV- Engineering ahead of schedule | 2023-03-08 | Williams, Nikole |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | AR - CEDAR RAPIDS TERMINAL |  | 128954 | 827221 | 950000 |  |  |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 44580 |  | Guest, ProSight | Independent | Aqua | 2022-08-12 | Int - Planned Exposures
BH724MP - Cutouts | Item | Open | MCAP | JH724JMM2201 | Project Framework | 1945861 | Segraves, Scott | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | 15675 |  | 0 | 15674.5 | 15675 | 0 | Green |  |  |  | 15675 |  |  | 57000 | 2924000 | 1529105 | 4510105 | Supplemental | 4510105 | 4509337 | 0 | 4509337 | No | Green | 2022-03-01 | 2022-02-04 | 2022-02-04 | 2022-07-01 | 2022-07-31 |  |  | 329.24 | 14014.77 | 1330.49 | [15 empty] | 0 | 3/2/2023 - Overspend for February 2023 caused by unexpected invoice for punch-list fence repair. 12/5/2022 - Underspend for November 2022 caused by $200K reduction in final invoicing for Over & Under negotiated by Supply Chain. 11/3/2022 - Overspend for October 2022 caused by contractor costs higher than expected. 10/4/2022 - Minor underspend for September 2022 caused by slightly lower than expected Over and Under charges. 9/6/2022 - Minor underspend for August 2022 due to lower than expected contractor costs. 7/6/2022 - Overspend for June 2022 caused by large amount of rock encountered on the cutout digs. 6/3/2022 - Construction is underway and on track for completion in July 2022. 5/4/2022 - Overspend for April 2022 caused by confusion in PM change and added scope to install 4" valve at Mechanicsburg trap to be used during cutout purge. 3/4/2022 - The scope of this working is being evaluated to include any B Sleeve cutouts that may be in the purge sections. | 2023-03-02 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Mechanicsburg | JH724JM - HGHSPE JCT-MECHBRG JCT |  | 15675 | 0 |  |  | 4493663 |  | Bartal, Nick | Guenther, Steve | N/A |  | 1 | 21128 |  | Guest, ProSight | Independent | Aqua | 2016-09-08 | Int - Accel Cutouts
BH724SN - P-0155829 Cutout | Item | Open | MCAP | BH724SNM2201 | Project Framework | 1945864 | Segraves, Scott | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | 165201 | 26479 | 147295 | 191679.74 | 192236 | -556 | Yellow | 50000 |  | 50000 | 141680 |  | Scope Increase | 47000 | 3243000 |  | 3290000 | Full | 3290000 | 2986059 | 173774 | 3159833 | No | Green | 2022-03-01 | 2022-02-04 | 2022-02-04 | 2022-07-01 | 2022-09-16 |  |  | 132186.03 | 5155.43 | -4105.92 | 31965.2 | 59000 | 59000 | -27035 | Red |  |  | 26479 | [7 empty] | 147295 | 5/3/2023 - Underspend in April 2023 caused by delayed delivery of a gravitometer. 12/5/2022 - Final contractor invoices were less than expected resulting in an underspend for November 2022. 10/4/2022 - Project is operational, working on site clean-up. Forecast on target for September 2022. 8/3/2022 - ROW payments hit all at once leading to minor overage in July 2022. 7/6/2022 - Gearing up to begin work in early August. 3/10/22 - Delay pending information on historical B sleeves. DC 3/4/2022 - The scope of this project is being evaluated to include any B Sleeve that need to be cutout in the purge section. | 2023-05-03 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Booth | BH724SN - BOOTH TO SINKING SPRING |  | 133236 | 58444 |  |  | 2820858 |  | Bartal, Nick | Guenther, Steve |  |  | 1 | 40769 |  | Bartal, Nick | Independent | Aqua | 2021-07-28 | Int - Accel Cutouts
BH724SNEP149610 Exposure Remediation | Item | Open | MCAP | BH724SNM2202 | Project Framework | 1954849 | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Defined | Exposure Remediation | 5718 | 150000 |  | 155718.16 | 152343 | 3375 | Yellow |  |  |  | 155718 |  |  | 76000 |  |  | 76000 | Phase | 76000 | 61015 | 150000 | 211015 | No | Green | 2022-03-01 | 2022-03-01 | 2022-03-01 | 2022-10-01 | 2023-12-31 |  |  | 208 | 1863.31 | 271.73 | 3375.12 |  |  | 3375 | Red | [6 empty] | 150000 |  |  |  |  | 3/8/23 NV- Permitting process underway, work to be started around Q3. 11/9/2022 NV- Over accrued dollars in September, resulting in variance in October. 7/12/22- Bergmann Engineering & permitting ahead of schedule NV | 2023-03-08 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Booth | BH724SN - BOOTH TO SINKING SPRING |  | 2343 | 3375 | 150000 |  | 55296 |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 41159 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Accel Exposures
CN165ZI B-Sleeve Cutouts 2022 | Item | Open | MCAP | CN165ZIM2202 | Project Framework | 1970327 | Oldham, David | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | 58318 |  | 160000 | 58318.1 | 58132 | 186 | Yellow |  |  |  | 58318 |  |  | 3048000 |  |  | 3048000 | Full | 3048000 | 2277268 | 160000 | 2437268 | No | Green | 2022-04-01 | 2022-09-06 | 2022-09-06 | 2022-10-08 | 2022-10-30 |  |  | 19894.92 | 34102.49 | 4134.61 | 186.08 |  |  | 186 | Red | [10 empty] | 160000 | 3/7/2023 - dwo: Contractor lost track of matting costs and technical issue delayed $25k matting invoice. 2/2/2023 - dwo: variance from late waste and cleanup costs. 1/10/2023 - dwo: Closeout and site restoration completion costs lower than forecasted. 12/5/2022: dwo - Variance associated with matting costs and internal site restoration/project closeout work. 11/8/2022: dwo - 95% of Site restoration complete. A few cleanup requirements remain for November 10/10/2022: dwo - cutouts executed week of 10/3. Sept variance associated with weighted forecast not distributing heavier burn seen during the week of 10/3. 9/6/2022: dwo - construction activities and staging started last week of August. 8/18/2022: dwo - updated forecast to reflect additional cutouts identified and planned to be included during the October outage. 6/9/2022: dwo - Transferred $500k to SG162DUM2201, OPPM ID: 43716. 6/9/2022 - Rescheduling to Q3/4 due to commercial scheduling. DC. 6.6.22.dwo: Removed $1.46 million from forecast and re-distributed to OPPM ID 43339 (165 cutouts downstream of Zionsville). 5.25.22.DLC: Added in funds from other OPPM record and cancelled other record5.3.2022 - dwo: Project to be funded from the B-sleeve budget allocation. Site Preparation for cutouts will begin in June. Cutouts tentatively planned for July to correspond with Al Kosior's "Ronald Reagan" reimbursed relocation. | 2023-03-07 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Indianapolis | CN165ZI - CARBON TO ZIONSVILLE |  | 58132 | 186 |  |  | 2218950 |  | Bartal, Nick | Guenther, Steve |  |  | 1 | 43339 |  | Meitzler, Antoinette | Independent | Aqua | 2022-04-05 | Int - Accel Cutouts
Coraopolis 718 Meter Upgrade | Item | Open | MCAP | CP00000M2103 | Exempt | 1916444 | Segraves, Scott | ECS Pipeline Integrity | 6. Operational | Emergent | Leak Detection | 24108 |  | 0 | 24107.95 | 22244 | 1864 | Yellow |  |  |  | 24108 |  |  | 963000 |  |  | 963000 | Full | 963000 | 1007747 | 0 | 1007747 | No | Green | 2022-01-01 | 2021-12-15 | 2021-12-15 | 2022-06-24 | 2022-12-02 |  |  | 20121.24 | -1294.54 | 3417.48 | 1863.77 |  |  | 1864 | Red | [10 empty] | 0 | 12/5/2022 - Underspend for November 2022 caused by reclass from PG718COR1701 not entered in time to post for month. Reclass will be posted in December. 11/3/2022 - Project is nearly operational. Overspend for October 2022 caused by confusion allocating spends between multiple project numbers at a single site. 10/4/2022 - Minor overspend for September 2022 caused by higher than expected invoices from Arseal and McCutcheon. 8/3/2022 - Arseal accrual higher than actual invoice lead to a minor underspend for July 2022. 6/9/2022 - Push to Q3 due to delay in PLC design. DC 3/3/2022 - Receiving materials and beginning prefab work. | 2023-01-06 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Coraopolis | CP - CORAOPOLIS TERMINAL BPL |  | 22244 | 1864 |  |  | 983640 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 42523 |  | Meitzler, Antoinette | Independent | Aqua | 2021-11-30 | Leak Detection
Coraopolis 718 Relief Upgrade | Item | Open | MCAP | CP00000M2104 | Exempt | 1915902 | Segraves, Scott | ECS Pipeline Integrity | 6. Operational | Emergent | Leak Detection | 24506 |  |  | 24505.52 | 24506 | 0 | Green |  |  |  | 24506 |  |  | 953000 |  |  | 953000 | Full | 953000 | 996218 |  | 996218 | No | Green | 2021-12-01 | 2021-12-10 | 2021-12-10 |  | 2022-12-02 |  |  | 7181.71 | 15136.22 | 2187.59 | [18 empty] | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Coraopolis | CP - CORAOPOLIS TERMINAL BPL |  | 24506 | 0 |  |  | 71706 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 42524 |  | Meitzler, Antoinette | Independent | Aqua | 2021-11-30 | Leak Detection
CP700PA-2 - Cutouts | Item | Open | MCAP | TT700PAM2201 | Maintenance Framework | 1945806 | Segraves, Scott | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | 213952 | 9000 | 49818 | 222951.97 | 206884 | 16068 | Yellow |  |  |  | 222952 |  |  | 44000 | 507000 |  | 551000 | Full | 551000 | 458326 | 58818 | 517144 | No | Green | 2022-03-01 | 2022-02-03 | 2022-02-03 | 2022-07-01 | 2022-12-31 |  |  | 50648.51 | 101210.81 | 40024.9 | 22067.75 | 10000 | 10000 | 12068 | Red |  |  | 7000 | 2000 | [6 empty] | 49818 | 3/2/2023 - SAS - Overspend for February 2023 caused by missed forecast for trap modifications at Beaver Grade Road. 2/3/2023 - SAS - Contractor invoicing for rental equipment and expenses billed in January 2023 resulted in a slight overage. 1/5/2023 - SAS - Contractor invoicing was much lower than their estimate. Full project scope was completed in December 2022 and all invoicing has been submitted. This resulted in an underspend for December. 12/5/2022 SAS - ROW issues did not allow construction to begin in November 2022 resulting in an underspend for that month. 11/2/2022 NAV- Right of Way delays due to lack of access to the site, project has not started but should be complete by year end. 9/9/2022 NAV- Redhorse started work early, accrued dollars for work compete causing the variance. Permitting issues caused project to be pushed to october, forecast adjusted accordingly. 8/5/2022 NV- Work to be completed in July delayed due to permitting. NV 7/12/2022- In planning stage, outage planned for August. NV 3/4/2022 - The scope of this project is being evaluated to include any B Sleeves that may need to be cutout in the purge section. | 2023-04-05 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Coraopolis | TT700PA - TIOGA TANKS TO PITTS AIRPORT |  | 191884 | 31068 |  |  | 244374 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40719 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Accel Cutouts
CS165XXEP753902 Exposure Remediation | Item | Open | MCAP | CS165XXM2201 | Project Framework | 1955007 | Bevevino, Jared | ECS Pipeline Integrity | 6. Operational | Defined | Exposure Remediation | 110 |  |  | 110.35 | 110 | 0 | Green |  |  |  | 110 |  |  | 65000 | 203000 |  | 268000 | Full | 268000 | 199358 |  | 199358 | No | Green | 2022-03-01 | 2022-03-03 | 2022-03-03 | 2022-10-01 | 2022-12-31 |  |  | 110.35 | [18 empty] | 8/9/22 NAV- Forecast adjusted as start date for August. 06-08-2022 Construction forecast moved back to September based on Permitting timeframe. | 2022-08-09 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | St. Louis | CS - CASEY STATION |  | 110 | 0 |  |  | 199248 |  | Hurley, Brian | Hoekstra, Matt |  |  | 1 | 41168 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Accel Exposures
CS165XXEP758064 Exposure Remediation | Item | Open | MCAP | CS165XXM2202 | Project Framework | 1954856 | Bevevino, Jared | ECS Pipeline Integrity | 6. Operational | Defined | Exposure Remediation | 199 |  |  | 199.12 | 199 | 0 | Green |  |  |  | 199 |  |  | 60000 | 131000 |  | 191000 | Full | 191000 | 133564 |  | 133564 | No | Green | 2022-03-01 | 2022-03-02 | 2022-03-02 | 2022-10-01 | 2022-12-31 |  |  | 199.12 | [18 empty] | 09-08-2022- Project completed in August. Was originall y scheduled for September. 8/9/22 NAV- forecast adjusted based on schedule change to start in August. 07-19-2022- Moved forecast from L701 Dresserville Creek Exposure project to this project. | 2022-09-08 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | St. Louis | CS - CASEY STATION |  | 199 | 0 |  |  | 133365 |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 41167 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Accel Exposures
CSX EW913RW Relocation | Item | Open | MCAP | EW913RWM2303 | Project Framework | 2111937 | Segraves, Scott | ECS Pipeline Integrity | 2. Pending AFE | Drawdown | Pipeline Replacements |  | 54001 |  | 54001 |  | 54001 | Red |  |  |  | 54001 | [6 empty] | Interim |  |  | 54001 | 54001 | No | Green | 2023-05-01 |  |  |  | 1900-12-31 | [12 empty] | 20000 | 20000 | 10000 | 4000 |  |  |  | 1 |  |  |  | Williams, Nikole |  | East | Pipelines and Terminals | Integrity | [5 empty] | 40000 | 14000 | 1 |  |  | Oldham, David | Boone, David G. |  |  | 1 | 46962 |  | Meitzler, Antoinette | Independent | Aqua | 2023-04-19
Detroit Station 300# Upgrades 2022 | Item | Open | MCAP | WD00000M2201 | Project Framework | 1946828 | Oldham, David | ECS Pipeline Integrity | 6. Operational | Defined | Transient/Surge Mitigation | 59643 |  |  | 59642.8 | 55303 | 4340 | Yellow |  |  |  | 59643 |  |  | 425000 | 1714000 |  | 2139000 | Full | 2139000 | 1836607 |  | 1836607 | No | Green | 2022-02-01 | 2022-02-13 | 2022-02-13 | 2021-12-31 | 2022-10-27 |  |  | 22092.68 | 5292.11 | 20418.09 | 11839.92 | 7500 | 7500 | 4340 | Red | [11 empty] | 4/10/23 - dwo: Variance from close out engineering, PM, and disposal costs. 1/10/23 - dwo: Variance caused by $32k reclass from WD999A2M1701. 12/5/22: dwo - November burn lower due to managing construction additional scope with scope reductions. Requires $15k of charges to be reclass'd from WD999A2M1701. 11/8/2022: dwo - October burn was lower due to coordination with Marathon maintenance personnel to handle mechanical isolation with refinery. 9/6/2022: dwo - Variance caused from fabrication start date adjustment. 7/29/22: dwo - $183k in valves arrived early causing positive variance in July. small volume prover ($106k) also arrived. 7/1/22: dwo - small volume prover did not ship ($106k). Scheduled to ship in July 6/9/2022 - Materials arriving earlier than expected. Costs pulled forward from Q3. DC 6/6/22: dwo - Bid event scheduled for June. Valve PO issued with partial delivery in June. 5/9/22: dwo - Construction bid event planned for May to finalize pricing. 4/13/22 - Sourcing of materials higher than expected initially. Final bid costs and full AFE expected in May. DC 4/4/2022: dwo - Forecast associated with long lead item purchase. Delayed bid event resulted in associated progress payment to be made in April vs. Mar. EAC updated based on preliminary materials pricing and design review final scope of work. Full AFE to be submitted following construction bid event in May. | 2023-04-10 | Williams, Nikole |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Pipeline | WD - DETROIT STATION |  | 47803 | 11840 |  |  | 1776964 |  | DiPillo, Evan | Guenther, Steve |  |  | 1 | 42023 |  | Clark, David | Independent | Aqua | 2021-08-31 | Other Programs
DJ316LREP6149 Exposure Remediation | Item | Open | MCAP | LR316BDM2301 | Project Framework | 2075767 | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Defined | Exposure Remediation | 15000 | 220000 |  | 235000 | 225000 | 10000 | Yellow | 250000 |  | 250000 | -15000 |  |  | 119875 |  |  | 119875 | Phase | 119875 | 15000 | 220000 | 235000 | No | Green | 2023-04-01 | 2023-01-18 | 2023-01-18 | 2023-09-01 | 2023-12-31 | [5 empty] | 15000 | 10000 | 10000 | 5000 | Red |  |  | 10000 | 5000 | 205000 |  |  |  |  | 0 |  |  |  | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Mantua | LR316BD - LORAIN CO TO BRADLEY RD. |  |  | 30000 | 205000 | 0 |  |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 44562 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Int - Planned Exposures
DJ802ZR Spans-Exposures Capital Upgrades Engineering | Item | Open | MCAP | DJ802ZRM2201 | Project Framework | 1946865, 1946866 | Taylor, Ryan | ECS Pipeline Integrity | 6. Operational | Emergent | Exposure Remediation | 319 |  |  | 319.35 | 319 | 0 | Green |  |  |  | 319 |  |  | 143000 |  |  | 143000 | Full | 143000 | 9473 |  | 9473 | No | Green | 2022-02-01 | 2022-02-15 | 2022-02-15 | 2022-04-01 | 2022-12-31 |  |  | 319.35 | [18 empty] | 1/10/23 NV- Final assessment charges hit | 2023-01-10 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | DJ802ZR - DEWITT JCT TO VERONA |  | 319 | 0 |  |  | 9154 |  | Hurley, Brian | Guenther, Steve |  |  | 1 | 42925 |  | Meitzler, Antoinette | Independent | Aqua | 2022-02-11 | Int - Accel Exposures
DN999A1 - 2021 Pressure Test and Go-No Go ILI | Item | Open | MEXP | DN999A1E2101 | Exempt | 1784260 | Kosior, Albert | ECS Pipeline Integrity | 6. Operational | Defined | Assessments | 12 |  |  | 11.67 | 12 | 0 | Green |  |  |  | 12 |  |  | 96000 |  |  | 96000 | Full | 96000 | 59743 |  | 59743 | No | Green | 2021-10-01 | 2020-12-29 | 2020-12-29 | 2021-12-31 | 2021-11-01 |  |  |  | 11.67 | [17 empty] | 1-4-22 Working closeout. 12-2-21 Working closeout 11-1-21 The hydrotest and ILI tool run was completed in October. 10-4-21 Planning meetings are being held with stakeholders and we will be able to run the Go/No Go tool. Working to schedule outage for week of 10/25. 9-2-21 Working on plan development. 8-2-21 Planning 7-1-21 In planning phase 6-1-21 In planning phase 5-6-21 In planning phase 4-5-21 In planning phase 3-3-21 In planning phase 2-5-21 Project in development. 1-8-21 Developing project. | 2022-01-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Argo | DN - DES PLAINES TERMINAL |  | 12 | 0 |  |  | 3964 |  | Bartal, Nick | Bassani, Joel D. |  |  | 1 | 37009 |  | Administrator, System | JDE Child | Burnt Orange | 2020-07-13 | Int - Assessments
DN999A2 - 2021 Pressure Test and Go-No Go ILI | Item | Open | MEXP | DN999A2E2101 | Exempt | 1784261 | Kosior, Albert | ECS Pipeline Integrity | 6. Operational | Defined | Assessments | 12 |  |  | 11.67 | 12 | 0 | Green |  |  |  | 12 |  |  | 96000 |  |  | 96000 | Full | 96000 | 55457 |  | 55457 | No | Green | 2021-11-01 | 2020-12-29 | 2020-12-29 | 2021-12-31 | 2021-12-01 |  |  |  | 11.67 | [17 empty] | 1-4-22 Working closeout. 12-2-21 Hydrotest was performed the first part of the month along with the tool run. All completed successfully. 11-1-21 Work is schedule for the first part of November. 10-4-21 Working with team to develop plan, will be able to run the Go/No Go tool. Requesting outage for week of 11/1. 9-2-21 Working on plan development. 8-2-21 Planning 7-1-21 In planning phase 6-1-21 In planning phase 5-6-21 In planning phase 4-5-21 In planning phase 3-3-21 In planning phase 2-5-21 Project in development. 1-8-21 Developing project | 2022-01-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Argo | DN - DES PLAINES TERMINAL |  | 12 | 0 |  |  | -3000 |  | Bartal, Nick | Bassani, Joel D. |  |  | 1 | 37010 |  | Administrator, System | JDE Child | Burnt Orange | 2020-07-13 | Int - Assessments
Engineering Leak Detection 2021 | Item | Open | MCAP | 1348262M2101 | Exempt | 1847210 | Yezik, James | ECS Pipeline Integrity | 3. Active | Defined | Leak Detection | 399689 | 100000 |  | 499688.9 | 486807 | 12882 | Yellow | 500000 |  | 500000 | -311 |  |  | 1683000 |  | 802000 | 2485000 | Supplemental | 2485000 | 2187699 | 100000 | 2287699 | No | Green | 2021-06-01 | 2021-05-21 | 2021-05-21 | 2024-10-01 | 2024-10-01 |  |  | 128990.99 | 109516.23 | 48299.96 | 112881.72 | 100000 | 100000 | 12882 | Red |  |  | 50000 | 50000 | [7 empty] | 5/2/23 JY - Allied invoicing still needing to be accrued. 4/12/23 JY - Allied invoicing still lagging. $53k invoiced start of April. 3/3/23 JY - Invoicing from Allied not fully resolved. Received email from Allied about putting money in specific line items. 2/8/23 JY - Allied billing issues appear to be resolved after discussing with their AP group. Invoices have not yet caught up with work performed. Only billed through mid-December. 1/6/23 JY - Created Allied CO on 12/13. Was not signed and returned until 1/6/23. Have not received an Allied invoice since 10/31. 12/8/22 JY - Waiting on Allied to issue CO to create supplemental for 2023 spends. 11/3/22 NV- Engineering timing for both Allied & DNV has resulted in variance. 10/25/22 JY - no updates to spends. Tracking accurately based on engineering work being performed for program by different vendors. 10/4/22 JY - money accrued in September due to not being billed. Will see spends in October as a result. 9/1/22 JY - money hit July instead of August. Shifted money from September to October/November expecting spends on PPA and clamp on metering Phase 1 AFEs. 8/5/22 JY - engineering has slowed down for Allied, moving money into September. 7/1/22 JY - New Allied schedule showing more activity in August September, moved $75k from July to Sept. 5/6/22 JY - moved $90k from October to May forecast for meter invoice and burn rate update. 4/7/22 JY - moved $40k from April to October based on Allied estimate. 4/4/22 JY - Adding funding for Wayne, Marcy, Vestal, and Long Island/Inwood per PM requests. Total removed was $625k. 3.11.22.DLC: Reallocated project funds into Aug-Nov for 6 CCX Projects unlikely to complete in 2022...3/10/22 - Vendor delays causing variance. Forecast to be updated once evaluation complete. DC Forecast removed for 2021 Leak detection regulation requires installations completed by 2024. The overall program is being re-evaluated and now emergent type work is expected in 2021. | 2023-05-02 | Williams, Nikole |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Integrity |  | Corporate | Corporate |  | 286807 | 212882 |  |  | 1479290 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 38460 |  | Kabaria, Erika | Independent | Aqua | 2020-09-02 | Leak Detection
EU163KK - Digs from 2022 GEO+MFL ILI | Item | Open | MCAP | EU163JUM2201 | Maintenance Framework | 2044485 | Kosior, Albert | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Digs | 1068521 | -409 |  | 1068111.69 | 989472 | 78640 | Yellow |  |  |  | 1068112 |  | Scheduling | 1452410 |  |  | 1452410 | Interim | 1452410 | 1513262 | -409 | 1512853 | No | Green | 2022-11-01 | 2023-02-06 | 2023-02-06 | 2023-06-30 | 2023-06-30 |  |  | 362364.26 | 289513.32 | 137594.32 | 279048.79 | 200000 | 200000 | 79049 | Red |  | Forecasting | -409 | [8 empty] | 5.8.23 - $-409 forecast in May due to MEXP Flip to EU163JUE2301 (AS) 4-7-23 Completed all of the DOT immediate digs. Integrity asked that the three remaining DOT 180-day digs not identified for completion in the Phase 1 be completed before demobing crew. The forecasted cost reflects this additional work in April. 4.6.23 - Reduced March by $91,690 due to MEXP Flip EU163JUE2301 (AS) 3-8-23 Work was not able to begin on the last immediate dig in the NSRR due to not being able to schedule flaggers through the railroad. Dig is looking to go in March. 2-13-23 Work is looking to end the end of February with the completion of the 5 immediate digs and three additional dig sites. 1-10-22 Completed one DOT immediate dig and 1 BPL other, working RR dig in Feb permits have been procured 12-8-22 Work started on the 7 immediate dig features on 11/28 and one crew is working the digs. 11-8-22 75 features were issued at the end of October, 5 of them being immediate digs. One of the immediates digs is in a railroad row. 9-29-22 The tool was trapped on 8/24/22 and any possible immediate digs would come in 30-60 days with the balance to fall into 2023. Estimating possibility of 3 digs being issued this year with and the rest falling into next 2023. 9-12-22 No change 8-9-22 No change 6/9/22 - No change 5/12-22 Tool needs to be rerun, preliminary report targeted for arrival end of September. Final report November 5-10-22 No digs issued yet 4-7-22 No digs issued yet. 3/9/22 - No change; digs not yet issued. | 2023-05-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Michiana | EU163JU - E CHICAGO B/G TO HAMMOND J B/G |  | 789472 | 278640 |  |  | 444741 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 41009 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
EU163KK - Like and Similar (Due 05-17-22) | Item | Open | MCAP | XX163KKM2201 | Maintenance Framework | 1917268 | Kizzire, Jerrod | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | -6285 |  |  | -6284.86 | -6285 | 0 | Green |  |  |  | -6285 |  |  | 210000 |  | 318000 | 528000 | Supplemental | 528000 | 392180 |  | 392180 | No | Green | 2022-05-01 | 2022-05-03 | 2022-05-03 | 2022-05-31 | 2022-05-31 |  |  |  | -6284.86 | [17 empty] | 7/12/22 - Additional composite wrap and tie in work not previously included in estimate. DC 6/8/22 - dig work wrapping up in June. 3/4/2022 - This project is grouped with another dig project in the area and the schedule has pushed back. | 2022-07-12 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Michiana | EU163JU - E CHICAGO B/G TO HAMMOND J B/G |  | -6285 | 0 |  |  | 398465 |  | Bartal, Nick | Guenther, Steve |  |  | 1 | 42486 |  | Guest, ProSight | Independent | Aqua | 2021-11-22 | Int - Accel Digs
EW913LD - Digs from 2021 UCD ILI | Item | Open | MCAP | EW913RWM2202 | Exempt | 1979771 | Garcia, Francisco | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Digs | 3610 | 140000 |  | 143609.67 | 140869 | 2740 | Yellow |  |  |  | 143610 |  |  | 200000 |  |  | 200000 | Full | 200000 | 65332 | 140000 | 205332 | No | Green | 2022-05-01 | 2022-05-06 | 2022-05-06 | 2022-12-31 | 2023-06-30 |  |  | 284.32 | 289.85 | 295.06 | 2740.44 | 0 | 0 | 2740 | Red |  |  |  | 140000 | [7 empty] | 05/01/2023 - Dig has not started yet. Due to begin in June 2023. 12/2/2022 RR permitting delay. 11-2-2022 RR permitting delay. 9-12-22 ROW speaking with RR to obtain permit 6/2/2022 - Reclassed $53K from BB913WM2201 (Henkel) 5/10/22 - Digs issued, released excess forecast. 4/11/22 - No change; digs not yet issued. | 2023-05-01 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Jet Lines | EW913RW - NEW HAVEN TO MIDDLETOWN JCT |  | 869 | 142740 |  |  | 61723 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 41019 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
GC415GK Shallow Pipe Remediation | Item | Open | MCAP | GC415GKM1801 | Exempt | 1493813 | Bevevino, Jared | ECS Pipeline Integrity | 6. Operational | Defined | Shallow Pipe Remediation | 228 |  |  | 227.62 | 58 | 170 | Red |  |  |  | 228 |  |  | 163000 | 149000 |  | 312000 | Full | 312000 | 211766 |  | 211766 | No | Green | 2022-02-01 | 2018-08-22 | 2018-08-22 | 2019-11-29 | 2022-11-18 |  |  | -4518.08 | 795.6 | 3780 | 170.1 |  |  | 170 | Red | [11 empty] | 1/10/23 NV- Golder ahead of schedule. 8/9/22 NAV- forecast adjustment for contractor schedule updates. 06/08/2022-Forecast reduced by 200k based on estimated construction costs. Still waiting on quotes. 03-09-2022 Work has resumed as of 03/01/2022. Construction expected to be completedWork expected to q3 resume January 2020 as long as the project is approved in the MCAP budgeting cycle. Placed on hold because the project was not approved to move forward with construction during the MCAP budgeting cycle in October. The only work that was completed was preliminary engineering. This work will still be usable once the project resumes. | 2023-01-10 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity | Integrity | Mantua | GC415GK - WAKEMAN - BRECKSVILLE-#1-E |  | 58 | 170 |  |  | 189371 |  | Hurley, Brian | Bassani, Joel D. |  |  | 1 | 30504 |  | Kabaria, Erika | Independent | Aqua | 2018-08-13 | Int - Planned Exposures
HD150SB - Digs from 2021 GEO+MFL ILI | Item | Open | MCAP | HD150WHM2201 | Maintenance Framework | 1946282 | Kosior, Albert | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | -291701 |  |  | -291701.24 | -291701 | 0 | Green |  |  |  | -291701 |  |  | 725000 |  |  | 725000 | Phase | 725000 | 539017 |  | 539017 | No | Green | 2022-02-01 | 2022-02-08 | 2022-02-08 | 2022-04-30 | 2022-06-28 |  |  |  |  | -291701.24 | [16 empty] | 4.6.23 - Added -$179,433 to March forecast due to MEXP Flip HD150WHE2201 (AS) 3.7.23 - March forecast -$112,269 due to MEXP flip to HD150WHE2201 (AS) 7/12/22 - June variance was flip forecast erroneously being put in July instead of June. 6/28/22 - Moved project to operational (AK) 6/7/22 - Negative $276,000 forecast in June to offset L150 2022 MEXP Flips HD150WHE2201 forecast for $276,000 in June (AS) 5-9-22 Working on finding resources to complete the two additional digs in June. The April variance id due to the additional work required on the north end of the casing after it was investigated. 4-7-22 Finished the 4 dent digs in March. An ECO was submitted for the 4 additional digs. I have been requested to perform two more risk ranked sigs before the line is idled in June. 3-7-22 Finishing the last of the initial 7 digs the first part of March. 4 additional dent digs were issued and an ECO was submitted. The 4 additional digs are estimated to cost $300k. The February variance was due to due to work starting the second week of the month and working only three weeks. 2-2-22 A stage 1 AFE for $725,000 was submitted to perform 7 of the worst mloss digs. Work to begin on 2/7/2022 with two crews. | 2023-04-06 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Michiana | HD150WH - HARTSDALE TO WHEELER |  | -291701 | 0 |  |  | 830718 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 41003 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
HD156KG155HD - DIG SHEETS (7) DOT-180 + (20) BPL-Other - Due 05-11-22 | Item | Open | MCAP | HD156KGM2201 | Maintenance Framework |  | Kosior, Albert | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | -23994 |  |  | -23994.03 | -24176 | 182 | Yellow |  |  |  | -23994 |  | Other | 1869000 |  |  | 1869000 | Full | 1869000 | 1573162 |  | 1573162 | No | Green | 2022-03-01 | 2022-04-06 | 2022-04-06 | 2022-06-15 | 2022-09-12 |  |  | 11540.6 | -39763.33 | 4046.6 | 182.1 |  |  | 182 | Red | [11 empty] | 4.6.23 - Added -$6,381 to March forecast due to MEXP Flip HD156KGE2201 (AS) 3.7.23 - March forecast -$2,334 due to MEXP Flip to HD156KGE2201 (AS) 3.2.23 - Added -$42536 to February due to flip to HD156KGE2201 (AS) 1/6/23 - Added $17,367 to December negative forecast due to Flip to HD156KGE2201 (AS) 12/7/22 - Just received a $75k invoice from CSX for the flip dig for flagging and monitoring services. Determining best way to process the charge. 12/2/22 - December Forecast -$1,421,798 due to Flip to HD156KGE2201 (AS) 10-10-22 Awaiting final invoicing for ground water disposal. Forecast is $19,450 - $3,512 = $15,938 10/7/22 - negative $3,512 in Oct due to reclass to HD156KGE2201 (AS) 912-22 - The digs were completed the later part of August. The main drivers for the overage was the significant cost of contaminated ground water disposal at the ECWMD property digs and the issues encountered at the CSX dig which required two redesigns of engineered shoring, the need to use pointed dewatering and the cost of CSX watch and protect services. A supplemental AFE is being developed. 9/12/22 - additional costs associated with CSX site constraints. 8-9-22 Working CSX dig and are on the third engineering shoring design. Have had delays with the redesign work and CSX approval timelines. 7/12/22 - Three digs remain, one in CSXRR, one in NSRR, and one in roadway. Additional costs due to issues at the CSX dig site and substantial charges to dispose of PCW ground water at the East Chicago Waterway Managements property digs. 7/12/22 - Additional costs due to railroad permitting and 999 line cutout work. DC 6/9/22 - Three digs remain to be assessed and will be completed by the end of July. We have gone to one crew. Crew is currently working the HM999A4 dig. 6/8/22 - Digs in process. 5/11/22 - Per Nick Bartal, digs pushed to June/July. DC 5-9-22 The 7 DOT 180-day digs have been completed and working on balance of digs. 4-7-22Work began on 4/4 and will run through the middle of June. Starting on the DOT 180-Day digs first. April variance due to delays bringing on the second crew. 3-7-22 An interim AFE was submitted for the permitting and fees for the four R/R dig sites. Looking to start the work in April. February variance dueto permitting delays. 2-2-22 Working four railroad permitting issues now, will be submitting a stage 1 AFE for permitting costs directly. 1-4-22 Digs are being staked currently. There are a number of them that are within R/RROW and will require O/S for permitting. | 2023-04-06 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | KG155HD - LAKE GEORGE TO HARTSDALE |  | -24176 | 182 |  |  | 1597156 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 42452 |  | Guest, ProSight | Independent | Aqua | 2021-11-16 | Int- Planned Digs
HD164-162EU Historic Upgrade Cutouts 2022 | Item | Open | MCAP | SG162DUM2201 | Project Framework | 1980984 | Oldham, David | ECS Pipeline Integrity | 6. Operational | Drawdown | Pipeline Digs | -7194 |  |  | -7194.42 | -7299 | 104 | Yellow |  |  |  | -7194 |  |  | 91000 | 580000 |  | 671000 | Full | 671000 | 550972 |  | 550972 | No | Green | 2022-05-01 | 2022-05-19 | 2022-05-19 | 2022-09-15 | 2022-09-15 |  |  | -5373.92 | -4243.98 | 2319.12 | 104.36 |  |  | 104 | Red | [11 empty] | 12/5/2022: dwo - Work completed sooner than expected and cost savings experienced by coordinating crews between 165 cutout work. 10/11/2022: dwo - Construction started in September and outage/cutouts scheduled for the week of 10/10. 7/11/22: dwo - Permits submitted. Anticipate August approval and Sept construction. 6/9/2022: Built forecast. Transferred $500k from CN165ZIM2202, OPPM ID: 43339 | 2022-12-05 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | St. Louis | SG162DU - SAUGET (ESL) TO DUPO |  | -7299 | 104 |  |  | 558166 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 43716 |  | Meitzler, Antoinette | Independent | Aqua | 2022-05-11 | Int - Accel Cutouts
IM760UG Spans-Exposures Capital Upgrade Engineering | Item | Open | MCAP | IM760UGM2201 | Project Framework | 1946905, 1946906, 1946907, 1946908, 1946909, 1946910, 1946911, 1946912 | Taylor, Ryan | ECS Pipeline Integrity | 6. Operational | Emergent | Exposure Remediation | 40620 | -85000 |  | -44379.88 | 620 | -45000 | Red |  |  |  | -44380 |  |  | 997000 |  |  | 997000 | Full | 997000 | 157966 | -85000 | 72966 | No | Green | 2022-02-01 | 2022-02-15 | 2022-02-15 | 2022-04-01 | 2022-12-31 |  |  | 620.12 |  |  | 40000 |  |  | 40000 | Red |  | Other | -85000 | [8 empty] | 20230509 NV- Invoice hit prior to reclass being complete. Reclass to be complete in May. 3.8.22.DLC: Work completed ahead of schedule | 2023-05-09 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | IM760UG - MILAN STA TO SUGAR CREEK TERM |  | 620 | -45000 |  |  | 117346 |  | Hurley, Brian | Guenther, Steve |  |  | 1 | 42934 |  | Meitzler, Antoinette | Independent | Aqua | 2022-02-11 | Int - Accel Exposures
IM760UG_1487_1489 Shallow Pipe | Item | Candidate | MCAP |  | Project Framework |  | Bevevino, Jared | ECS Pipeline Integrity | 2. Pending AFE |  | Shallow Pipe Remediation |  |  |  | 0 |  | 0 | Green | 1500000 |  | 1500000 | -1500000 | [11 empty] | No | Green |  |  |  |  | 2023-05-31 | [21 empty] | 1/2/23 - Removed 2023 forecast and moved to AR760HH BMH. | 2023-01-03 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Sugar Creek | IM760UG - MILAN STA TO SUGAR CREEK TERM |  |  | 0 |  |  |  |  | Hurley, Brian |  |  |  | 1 | 44581 |  | Guest, ProSight | Independent | Aqua | 2022-08-12 | Int - Planned Exposures
IM760UGEP24A Exposure Remediation | Item | Candidate | MCAP |  | Project Framework |  | Bevevino, Jared | ECS Pipeline Integrity | 2. Pending AFE |  | Exposure Remediation |  |  |  | 0 |  | 0 | Green | 250000 |  | 250000 | -250000 | [11 empty] | No | Green |  |  |  |  | 2023-08-31 | [21 empty] | 2/2/23 - MCAP project cancelled and moved to MEXP Exposure Remediation | 2023-02-02 |  |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | IM760UG - MILAN STA TO SUGAR CREEK TERM |  |  | 0 |  |  |  |  | Hurley, Brian |  |  |  | 1 | 44538 |  | Guest, ProSight | Independent |  | 2022-08-13 | Int - Planned Exposures
IM760UGEP37 Exposure Remediation | Item | Open | MCAP | IM760UGM2308 | Project Framework | 2095207 | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Defined | Exposure Remediation | 21250 | 1160000 |  | 1181249.9 | 1185000 | -3750 | Yellow | 1100000 |  | 1100000 | 81250 |  |  | 123200 |  |  | 123200 | Phase | 123200 | 21250 | 1160000 | 1181250 | No | Green | 2023-04-01 | 2023-03-17 | 2023-03-17 | 2023-10-15 | 2023-05-31 | [5 empty] | 21249.9 | 25000 | 25000 | -3750 | Red |  |  | 20000 | 10000 | 10000 | 10000 | 10000 | 1100000 | [5 empty] | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | IM760UG - MILAN STA TO SUGAR CREEK TERM |  |  | 51250 | 30000 | 1100000 |  |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 44539 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Int - Planned Exposures
IM760UGEP39 Exposure Remediation | Item | Open | MCAP | IM760UGM2301 | Project Framework | 2075808 | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Defined | Exposure Remediation | 18256 | 220000 |  | 238255.5 | 228031 | 10225 | Yellow | 250000 |  | 250000 | -11745 |  |  | 96575 |  |  | 96575 | Phase | 96575 | 18256 | 220000 | 238256 | No | Green | 2023-01-01 | 2023-01-19 | 2023-01-19 | 2023-10-01 | 2023-08-31 |  |  | 2900 | 130.5 | 5000 | 10225 | 10000 | 10000 | 225 | Yellow |  |  | 10000 | 5000 | 5000 | 200000 | [7 empty] | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | IM760UG - MILAN STA TO SUGAR CREEK TERM |  | 8031 | 25225 | 205000 |  |  |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 44540 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Int - Planned Exposures
IM760UGEP65A Exposure Remediation | Item | Open | MCAP | IM760UGM2302 | Project Framework | 2083846 | Bevevino, Jared | ECS Pipeline Integrity | 2. Pending AFE | Defined | Exposure Remediation | 15225 | 230000 |  | 245225 | 245000 | 225 | Yellow | 250000 |  | 250000 | -4775 |  |  | 96575 |  |  | 96575 | Phase | 96575 | 15225 | 230000 | 245225 | No | Green | 2023-03-01 | 2023-02-02 | 2023-02-02 | 2023-10-01 | 2023-08-31 |  |  |  |  | 5000 | 10225 | 10000 | 10000 | 225 | Yellow |  |  | 15000 | 15000 |  | 200000 | [7 empty] | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | IM760UG - MILAN STA TO SUGAR CREEK TERM |  | 5000 | 40225 | 200000 |  |  |  | Hurley, Brian | Shepherd, Duane E. |  |  | 1 | 44541 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Int - Planned Exposures
IM760UGEP68A Exposure Remediation | Item | Open | MCAP | IM760UGM2306 | Project Framework | 2096364 | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Defined | Exposure Remediation | 20360 | 225000 |  | 245360 | 238000 | 7360 | Yellow | 250000 |  | 250000 | -4640 |  |  | 116500 |  |  | 116500 | Phase | 116500 | 20360 | 225000 | 245360 | No | Green | 2023-03-01 | 2023-03-30 | 2023-03-30 | 2023-10-15 | 2023-08-31 |  |  |  |  | 8000 | 12360 | 10000 | 10000 | 2360 | Red |  |  | 10000 | 10000 | 5000 | 200000 | [7 empty] | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | IM760UG - MILAN STA TO SUGAR CREEK TERM |  | 8000 | 32360 | 205000 |  |  |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 44542 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Int - Planned Exposures
IM760UGEP74 Exposure Remediation | Item | Open | MCAP | IM760UGM2305 | Project Framework | 2094897 | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Defined | Exposure Remediation | 25000 | 1160000 |  | 1185000 | 1175000 | 10000 | Yellow | 1100000 |  | 1100000 | 85000 |  |  | 227175 |  |  | 227175 | Phase | 227175 | 25000 | 1160000 | 1185000 | No | Green | 2023-04-01 | 2023-03-12 | 2023-03-12 | 2023-10-15 | 2023-05-31 | [5 empty] | 25000 | 25000 | 25000 | 0 | Green |  |  | 10000 | 15000 | 15000 | 10000 | 1110000 | [6 empty] | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | IM760UG - MILAN STA TO SUGAR CREEK TERM |  |  | 50000 | 1135000 |  |  |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 44543 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Int - Planned Exposures
IM760UGEP94 Exposure Remediation | Item | Open | MCAP | IM760UGM2304 | Project Framework | 2094902 | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Defined | Exposure Remediation | 31617 | 1900000 |  | 1931617 | 1915000 | 16617 | Yellow | 1550000 |  | 1550000 | 381617 |  |  | 233000 |  |  | 233000 | Phase | 233000 | 31617 | 1900000 | 1931617 | No | Green | 2023-04-01 | 2023-03-12 | 2023-03-12 | 2023-10-15 | 2023-05-31 | [5 empty] | 31617 | 25000 | 25000 | 6617 | Red |  |  | 20000 | 20000 | 20000 | 15000 | 10000 | 1815000 |  |  |  | 2/2/23 - BMH forecast updated to account for additional length of relocation | 2023-02-02 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | IM760UG - MILAN STA TO SUGAR CREEK TERM |  |  | 71617 | 45000 | 1815000 |  |  | Hurley, Brian |  |  |  | 1 | 44544 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Int - Planned Exposures
IM760UGEP97C Exposure Remediation | Item | Open | MCAP | IM760UGM2307 | Project Framework | 2095182 | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Defined | Exposure Remediation | 45000 | 1868000 |  | 1913000 | 1905000 | 8000 | Yellow | 1100000 |  | 1100000 | 813000 |  |  | 291250 |  |  | 291250 | Phase | 291250 | 45000 | 1868000 | 1913000 | No | Green | 2023-04-01 | 2023-03-17 | 2023-03-17 | 2023-10-15 | 2023-05-31 | [5 empty] | 45000 | 25000 | 25000 | 20000 | Red |  | WorkAhead of Schedule | 10000 | 14000 | 14000 | 15000 | 5000 | 1810000 |  |  |  | 5/8/23 NV- Engineering ahead of schedule. 2/2/23 - BMH forecast updated to account for additional length of relocation | 2023-05-08 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | IM760UG - MILAN STA TO SUGAR CREEK TERM |  |  | 69000 | 34000 | 1810000 |  |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 44545 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Int - Planned Exposures
JC701ZNEP96747 Exposure Remediation | Item | Open | MCAP | JC701ZNM2301 | Project Framework | 2077045 | Taylor, Ryan | ECS Pipeline Integrity | 3. Active |  | Exposure Remediation | 64394 | 600000 |  | 664394.42 | 656763 | 7631 | Yellow |  | 56264 | 56264 | 608130 |  |  | 56264 |  |  | 56264 | Phase | 56264 | 64394 | 600000 | 664394 | No | Green | 2023-03-01 | 2023-03-16 | 2023-03-16 | 2023-07-01 | 2023-07-01 |  |  |  |  | 26763.49 | 37630.93 | 30000 | 30000 | 7631 | Red |  |  | 200000 | 300000 | 100000 | [6 empty] | 20230411 - RJT - Updated major spend start and decreased forecast by $400K 20230405 - RJT - Variance due to material arriving early. 20230309 - RJT - updated project start spend. | 2023-04-11 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | JC701ZN - JOHNSON CITY-MAINE 14 & 16 INCH |  | 26763 | 537631 | 100000 |  |  |  | Hurley, Brian | Guenther, Steve |  |  | 1 | 46533 |  | Hurley, Brian | Independent | Aqua | 2023-01-24 | Int - Planned Exposures
KG999B1 Pipeline Relocation | Item | Open | MCAP | KG999B1M2202 | Project Framework | 2044228 | Oldham, David | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Replacements | 264323 | 1421500 |  | 1685823.37 | 1701642 | -15819 | Yellow | 800000 | 1067000 | 1867000 | -181177 |  |  | 57000 | 1810000 |  | 1867000 | Full | 1867000 | 279368 | 1421500 | 1700868 | No | Green | 2022-12-01 | 2022-11-07 | 2022-11-07 | 2023-06-01 | 2023-04-30 |  |  | 70795.24 | 24775.37 | 46071.42 | 122681.34 | 95000 | 95000 | 27681 | Red |  | WorkAhead of Schedule | 1220000 | 150000 | 50000 | 1500 | [5 empty] | 5/8/2023: dwo - Contractor able to complete some qualifications early before mobilization on 5/1 4/10/2023: dwo - Variance associated with schedule shift due to shorter anticipated shorter construction schedule. 3/7/2023: dwo - Forecast accounted for procurement of items that will not be delivered to site until Mar/April. 11/8/2022: dwo - Phase I AFE opened for FEED study and purge planning. Construction to target Q1 or Q2 CY23 based on permitting requirements identified in FEED. | 2023-05-08 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | KG999B1 - CLARK JCT TO BP WHITING |  | 141642 | 1492681 | 51500 |  | 15045 |  | Oldham, David | Boone, David G. |  |  | 1 | 45922 |  | Clark, David | Independent | Aqua | 2022-09-27 | Other Programs
KZ001-002XB - Digs from 2021 UCD ILI | Item | Open | MCAP | KZ001LKM2202 | Exempt | 1971355 | Kosior, Albert | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | -26000 |  |  | -26000.18 | -26000 | 0 | Green |  |  |  | -26000 |  | Scheduling | 4643000 |  |  | 4643000 | Full | 4643000 | 4623638 |  | 4623638 | No | Green | 2022-04-01 | 2022-06-27 | 2022-06-27 | 2022-11-30 | 2022-11-30 |  |  | 2155.42 | 1965.1 | -30120.7 | [16 empty] | 3.7.23 - March forecast of -$34,151 due to MEXP Flip to KZ001LKE2301 (AS) 11-6-22 Digs completed, working closeout. 10-10-22 Last dig to complete the first part of October. 9-12-22 Digs in progress, looking at later part of October to complete. 8-9-22 Digs are underway. July variance due to additional costs related to a historical spill site and having to manage contaminated soils and water. 7-12-22 - Scheduling due to slightly delayed start date from approximation in AFE. DC 7-12-22 Digs are in-process, running with two crews. 6-9-22 AFE was submitted and the digs are scheduled to start on Monday, 6/13/22, and are scheduled to take 19 weeks to complete. May variance is due to delay in sleeve delivery. 5-9-22 Digs have been staked and are currently being reviewed by ROW for permitting and access. Two of the digs are in wet areas. 600 feet of sleeve have ben ordered. Working to get two crews from InterCon to start on the digs the first part of June. 4/8/22 - NEB, digs just issued; left total forecast the same 4-7-22 Digs have not been issued yet. 3/6/22 - Digs not yet issued, pushed forecast out. 2-9-22 No digs issued yet, pushed forecast out one month. 1-10-22 Not digs issued yet, pushed forecast out. | 2023-03-07 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Michiana | KZ001LK - KOUTS TO LAKETON |  | -26000 | 0 |  |  | 4649638 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 41020 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
KZ001-002XB Dig Sheets (1) BPL-Other (Sleeves) - Due 2-19-22 MEXP | Item | Open | MEXP | KZ001LKE2103 | Exempt | 1901925 | Oldham, David | ECS Pipeline Integrity | 6. Operational | Unplanned | Pipeline Digs | 163 |  |  | 162.9 | 163 | 0 | Green |  |  |  | 163 |  |  | 174000 |  |  | 174000 | Full | 174000 | 185028 |  | 185028 | No | Green | 2021-10-01 | 2022-01-03 | 2022-01-03 | 2022-02-28 | 2021-11-30 |  |  | 162.9 | [22 empty] | West | Pipelines and Terminals | Pipeline Integrity |  | Michiana | KZ001LK - KOUTS TO LAKETON |  | 163 | 0 |  |  | 37694 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 42297 |  | Meitzler, Antoinette | Independent | Aqua | 2021-10-12 | Int- Planned Digs
L001-002 Cutouts 2023 | Item | Open | MCAP |  | Project Framework |  | Oldham, David | ECS Pipeline Integrity | 2. Pending AFE |  | Pipeline Digs |  | 0 |  | 0 | 550000 | -550000 | Red | 550000 |  | 550000 | -550000 | [9 empty] | 0 | 0 | No | Green |  |  |  |  | 2023-06-30 | [15 empty] | 0 | 0 |  |  |  |  | 5/8/2023 - dwo: Duplicate project to OPPM ID 46942. Forecast set to $0. | 2023-05-08 |  |  | West | Pipelines and Terminals | Integrity |  | Corporate | Corporate |  |  | 0 | 0 |  |  |  | Bartal, Nick |  |  |  | 1 | 44932 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Cutouts
L163 Cutouts 2023 | Item | Open | MCAP |  | Project Framework |  | Kosior, Albert | ECS Pipeline Integrity | 2. Pending AFE |  | Pipeline Digs |  | 400000 |  | 400000 | 400000 | 0 | Green | 400000 |  | 400000 | 0 | [9 empty] | 400000 | 400000 | No | Green | 2023-12-01 |  |  |  | 2023-10-31 | [19 empty] | 400000 |  | 2-13-23 Cutout have not been determined at this point. Business review of the line to be completed upon completion of the Phase 1 Immediate digs project completion the end of February. 1-10-23 Cut outs have not been determined at this point. Waiting to complete the current metal loss program | 2023-02-13 |  |  | West | Pipelines and Terminals | Integrity |  | Michiana | JU163XX - HAMMOND JCT B/G TO IL S/L |  |  | 0 |  | 400000 |  |  | Bartal, Nick |  |  |  | 1 | 44931 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Cutouts
L165 Interim Repair Cutout 2023 | Item | Open | MCAP | XX165CNM2301 | Project Framework | 2120219 | Oldham, David | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Digs |  | 440000 |  | 440000 | 400000 | 40000 | Yellow | 400000 |  | 400000 | 40000 |  |  | 56755 |  |  | 56755 | Phase | 56755 |  | 440000 | 440000 | No | Green | 2023-05-01 | 2023-05-05 | 2023-05-05 | 2023-12-31 | 2023-08-31 | [12 empty] | 110000 | 275000 | 55000 | [8 empty] | Carter, Paige |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Integrity |  | Indianapolis | XX165CN - IL S/L TO CARBON |  |  | 385000 | 55000 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 45945 |  | Clark, David | Independent | Aqua | 2022-10-01 | Int- Planned Digs
L190 2021 MEXP FLIPS | Item | Open | MEXP | WV190HOE2101 | Exempt | 1823903 | Kosior, Albert | ECS Pipeline Integrity | 7. Closed | Drawdown | Navigable Waterway Inspection | 4139 |  |  | 4138.96 | 4139 | 0 | Green |  |  |  | 4139 |  |  | 99548 |  |  | 99548 | Full | 99548 | 103687 |  | 103687 | No | Green | 2021-03-01 | 2021-03-31 | 2021-03-31 | 2021-04-30 | 2021-04-30 |  |  |  |  | 4138.96 | [16 empty] | 5-6-21 Accounting flip 4-5-21 Accounting flip | 2021-05-06 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | St. Louis | WV190HO - WOOD RIVER TO HORSESHOE LAKE |  | 4139 | 0 |  |  |  |  | Bassani, Joel | Bartal, Nick | N/A |  | 1 | 39653 |  | Schultz, Amy | JDE Child | Burnt Orange | 2021-03-31
L415 B-sleeve cutouts | Item | Open | MCAP | GC415GKM2301 | Project Framework | 2112642 | Segraves, Scott | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Digs |  | 2000000 |  | 2000000 | 2000000 | 0 | Green | 1000000 |  | 1000000 | 1000000 |  |  | 81450 |  |  | 81450 | Phase | 81450 |  | 2000000 | 2000000 | No | Green | 2023-05-01 | 2023-04-25 | 2023-04-25 | 2023-08-04 | 2023-10-20 | [12 empty] | 5000 | 15000 | 1000000 | 915000 | 50000 | 10000 | 5000 |  |  | 8.5.22.DLC: Removed funds for UB760AR Shallow Pipe Remediation Cascade Township 16820+04 | 2022-08-05 | Carter, Paige |  | West | Pipelines and Terminals | Integrity |  | Mantua | GC415GK - WAKEMAN - BRECKSVILLE-#1-E |  |  | 20000 | 1965000 | 15000 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 43945 |  | Clark, David | Independent | Aqua | 2022-06-08 | Int - Accel Cutouts
L760 - B-sleeve cutouts 2023 | Item | Candidate | MCAP |  | Project Framework |  | Kosior, Albert | ECS Pipeline Integrity | 2. Pending AFE |  | Pipeline Digs |  | 500000 |  | 500000 | 500000 | 0 | Green | 500000 |  | 500000 | 0 | [9 empty] | 500000 | 500000 | No | Green | 2023-06-01 |  |  |  | 2023-07-31 | [13 empty] | 50000 | 250000 |  |  | 100000 | 100000 |  |  | 5/8/23 Compiling cut out list. Working with exposures group to finalize purge to set schedule for cut outs. 2-13-23 Developing cutouts project. 1-10-23 Working to identify cut outs 11-5-22 Removed remaining forecast for 2022. 10-10-22 Reduced forecasts 9-12-22 Will submit stage 1 AFE before the end of the month. | 2023-05-08 |  |  | West | Pipelines and Terminals | Integrity |  | Eastern Iowa | UB760AR - DUBUQUE VLV - CEDER RAPIDS TER |  |  | 50000 | 250000 | 200000 |  |  | Bartal, Nick |  |  |  | 1 | 45148 |  | Guest, ProSight | Independent | Aqua | 2022-08-22 | Int - Planned Cutouts
Leak Detection - BB999A1-A4, Booster 1 to 2, BS999A1, GW999A4, LD913SR | Item | Open | MCAP | EW00000M2001 | Maintenance Framework | 1777300 | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Defined | Leak Detection | 512388 | 625000 |  | 1137388.03 | 1121662 | 15726 | Yellow | 2500000 |  | 2500000 | -1362612 |  |  | 474000 | 3038000 |  | 3512000 | Full | 3512000 | 2798309 | 625000 | 3423309 | No | Green | 2020-12-01 | 2020-11-28 | 2020-11-28 | 2021-07-31 | 2023-09-30 |  |  | 203193.88 | 205461.11 | 38007.27 | 65725.77 | 50000 | 50000 | 15726 | Red |  | Other | 60000 | 225000 | 150000 | 100000 | 90000 |  |  |  |  | 5/8/23 NV- Unforecasted interest charge. 4/11/23 NV- Unforecasted labor, CWIP & Interest. Forecast adjusted due to project delay start until May. 3/8/23 NV- Change order coming in for more than expected. Forecast adjusted to reflect trailing electric & integration costs. 1/10/23 NV- Safety Standown caused variance. 12/9/22 NV- More work completed than expected. 11/9/2022 NV- Could not get downtime as needed. 10/5/2022 NAV- Mobilization pushed back until 10/10. 09-08-2022- More materials arrived than expected in August. 2022 Forecast adjusted 400k down due to two lines dropping off list because they will be idled or abandoned. 8/9/22 NAV- contractor prefabbing materials initially forecasted in August wont be on site until September. 07-19-2022. Per discussion with Ben Clark, forecast adjusted to reflect the expected spends through the rest of year. TRC to be scheduled. 7/12/22 PLC components arrived earlier than expected. NV 06-08-2022-Preliminary electrical work to start in August with mechanical to follow in months after. 05/09/2022- unexpected invoicing of materials not due until late summer. 03-09-2022 March spends inlcude delivery of valve and PLC comoponents. Hoping to start construction mid late q2 01/11 December spends include up front payment of PLC panels. 11/9 Project design is underway which is being charged to the Short Line Engineering Leak Detection Project. Costs to hit this project later in this year will include reclassing purchasing of meters to this project number. Project in process of preliminary assessment | 2023-05-08 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Jet Lines | EW - NEW HAVEN STATION |  | 446662 | 350726 | 340000 |  | 1988769 |  | Guenther, Steve | Bishop, Rick | N/A |  | 1 | 30149 |  | Guest, ProSight | Independent | Aqua | 2018-07-30 | Leak Detection
Leak Detection - CY802CA, CY999A1, CY999A2 - Marcy to Utica | Item | Open | MCAP | CY802CAM2301 | Maintenance Framework | 2075642 | Yezik, James | ECS Pipeline Integrity | 3. Active | Defined | Leak Detection | 217099 | 250000 |  | 467099.24 | 473655 | -6555 | Yellow | 190000 | 245000 | 435000 | 32099 |  |  | 447105 |  |  | 447105 | Full | 447105 | 217099 | 250000 | 467099 | No | Green | 2023-01-01 | 2023-01-17 | 2023-01-17 | 2023-08-01 | 2023-11-30 |  |  | 38975.38 | 63311.33 | 21367.85 | 93444.68 | 100000 | 100000 | -6555 | Yellow |  | Buckeye/Customer Schedule | 150000 | 50000 | 50000 | [6 empty] | 5/2/23 JY - Accruing Kruse work. Haven't been invoiced yet. 4/4/23 JY - Vestal work/weather delays caused work to slide back ~two weeks. April spends will balance March underspend. 3/3/23 JY - Work ahead of schedule and invoices already being received. 2/8/23 JY - valves purchased for work and arrived earlier than expected. Work will still begin after Vestal completes. Early April target. 1/9/23 JY - Preparing for work to start after Vestal work finishes. 9/6/22 JY - Pushed to 2023. 3/29/22 JY - IFR being created. Scheduled to have IFC by May. Will need PPA at Marcy and Coriolis at Utica. Also installing back pressure valve at Utica to hold pressure on line for integrity. Funds shifted from leak detection engineering. | 2023-05-02 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | CY802CA - MARCY TO UTICA |  | 123655 | 293445 | 50000 |  |  |  | Guenther, Steve | Guenther, Steve | N/A |  | 1 | 30159 |  | Guest, ProSight | Independent | Aqua | 2018-07-30 | Leak Detection
Leak Detection - RC999A6 - Rochester to BET | Item | Open | MCAP | RC999A6M1901 | Exempt | 1653800 | Yezik, James | ECS Pipeline Integrity | 6. Operational | Defined | Leak Detection | 30841 | 50000 |  | 80841.36 | 70683 | 10158 | Red | 50000 |  | 50000 | 30841 |  |  | 102000 | 1771000 |  | 1873000 | Phase | 1873000 | 3290051 | 50000 | 3340051 | No | Green | 2020-01-01 | 2019-11-26 | 2019-11-26 | 2020-12-31 | 2023-08-31 |  |  | -92097.45 | 100932.02 | 11848.65 | 10158.14 | 50000 | 50000 | -39842 | Red |  | Contractor/Vendor Issue |  |  |  |  | 50000 |  |  |  |  | 4/19/23 JY - PLC components still missing and incorrect MOXA models ordered for integration. Equipment is ordered, but lead times are 8 weeks. 4/12/23 JY - Working with Arseal to finalize PLC panels that were shipped incomplete. 3/3/23 JY - Strike invoicing offset January forecast data. Invoicing should be complete from Strike. 2/16/23 JY - Strike finally invoiced final charges on 2/15/23. February spends will offset January spends. 2/8/23 JY - Strike requested CO for $20k and then another for $63k because their invoicing had gotten impacted due to personnel issues. 1/6/23 JY - Strike needs to issue CO and has not. Have reminded them several times. 11/3/2022 NV- Variance due to Strike invoice/PO issue 11/3/22 JY - Original Strike PO had to be cancelled, causing 285k credit. New PO created to account for remaining invoice dollars of $650k 10/25/22 JY - electrical done 10/14. final walkthrough with Ops to take place.Integration after with SCADA. 10/4/22 JY - electrical delays and shifting of crews in September. work expected to be completed week of 10/10. 9-2-22 JY: Electrical has slid into September. Completion week of 9/12 or 9/19. 8-5-22 JY: increased spends forecasted for August due to overall project cost increase. 7/22/2022 NV: Missed accrual $288,212 forecasted into July 2022-working with accounting to get added to scorecard review. 2022-06-01 JY: Project shop work has started. Site work will start week of 6/6, projected electrical completion 8/18. Spends adjusted based on schedule. 2022-04-06 JY: Adjusting forecast based on timing of final site visit and construction to follow. Received cost estimate for more accuracy in spends. 2022-03-02 JY: Prior PO configuration caused billing to take place in February prior to receipt of materials. Acuator that did arrive, arrived early per original schedule. These two things caused February variance. 2022-01-25 JY: Yezik hastaken over project as PM. Will perform site walk with Zimmeran and Bolt construction 01/26 and adjust budget as needed. 2022-01-04 SRZ: SteveGuenther is planning to provide a PM to assist in getting the field construction moving.This should hopefully help get the project back on track for completion. 2021-12-02 SRZ: Working to getsite visit with Bolt set up before end of year. Intention to start construction in January. Looking at possibility of contract PM to help get timeline back on track. 2021-11-02 SRZ: MSA has been signed for Bolt construction for leak detection work. We will use them for the project as a result. Working on setting up walk down with Bolt, as well as Right of Way negotiations with shippers. 2021-10-04 SRZ: Long lead material has begun to arrive. Working on prep for bid walk downs. 2021-09-02 SRZ: Actuators and meters are on order. Prepping for ROW conversations with shippers and field construction bid meetings. 2021-08-02 SRZ: Valves on order. Quote received for actuators. PO for meters & actuators should go out this week. 2021-07-02 SRZ: Some delays in ordering material will result in money shifting to wards the end of 2021. Working on getting PO's cut now. 2021-06-02 SRZ: All design complete. Working on ordering material and working with ROW to evaluate if any modification is necessary to our agreements at the shipper endpoints to accommodate our work. 2021-05-04 SRZ: Civil and Mechanical design packages submitted to engineering for review. Should have electrical package to submit shortly.Ordering material and starting to work with RW on shipper contacts. 2021-04-05 SRZ: Final design completed. Working on ordering long lead material andright of way/permitting. 2021-03-02 SRZ: Shifted funds for material further out due to delays. Those spends will realistically hit later than originally planned. 2021-02-02 SRZ: Delays in material arriving will result in some spends pushing further out. Preliminary engineering is nearly complete. 2021-01-05 SRZ: Cutting purchase orders for long lead material.Final design 50% complete. 2020-12-01 SRZ: AFE approved. Continuing design work and preparing to order long lead material such as valves and meters. 2020-11-01 SRZ: Final design underway. TRC meeting scheduled for 11/4. 2020-10-05 SRZ: AFE estimate complete. Preparing to submit. 2020-09-02 SRZ: Finalizing AFE for submittal. Full engineering design will proceed immediately with AFE approval. 2020-08-03 SRZ: Adjusted forecast to match AFE to be submitted by end of week. 2020-07-01 SRZ: AFE will be sent out for review shortly. 2020-06-01 SRZ: AFE will be filed shortly and project will proceed for 3rd & 4th quarter execution. 2020-05-04 SRZ: Meeting held to make final project determination. For 2020 project will install valves at all 7 endpoints, and meters at 3 endpoints. Will do testing on leak detection capabilities with meters installed. Will not install pressurization system. 2020-04-01 SRZ: Due to COVID-19 crisis, a final determination has not yet been made by the leak detection team regarding Buckeye's companywide approach to this issue. 2020-03-02 SRZ:Stakeholder meeting held, awaiting final determination by Leak Detection Team to resolve scope. 2020-02-03 SRZ: Preliminary design complete. Currently working on AFE quality estimate, after which AFEwill be ready to submit. Prior to AFE submission will conduct stakeholder review of project to ensure funding is available from drawdown and that the project as estimated will meet our requirements. 2020-01-02SRZ: Site visit with operations and Allied Engineering conducted. Working on preliminary AFE quality estimatefor full AFE. We were notified that the funding will likely be available to do all of the Rochester lines rather than just one, so projectedcosts for the final AFE may be substantially more than originally budgeted for a single line. Additional would be paid for out of the Leak Detection Drawdown. 2019-12-02 SRZ: Continuing work on preliminary engineering in preparation for full Phase 2 construction AFE. 2019-11-01 SRZ: Meeting with Allied to get proposal for engineering. Plan is to do AFE quality estimate with 2019 dollars, then continue the detailed design in 2020. 2019-10-03SRZ: Will schedule kickoff meeting next week to review some key concepts before proceeding. Recent DOT ruling also has potential to effect project. 2019-09-03 SRZ: Finalizing estimate for next years budget. Putting together list of challenges/options for stakeholders meeting. 2019-08-02 SRZ: Continue to work to refine actual scope of project with stakeholders. 2019-07-02 SRZ: Still working to define final project scope and goals before beginning preliminary engineering. Meeting with M&QC has identified significant issues with attempting to do a pump back system on the jet lines. 2019-06-04 SRZ: Working with M&QC on quality concerns related to potential pump back system for leak detection. Initial work with Scada/Leakwarn SME's has indicated that pump back system would be better suitedfor this application than any attempt at shipper side metering. | 2023-04-19 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | RC999A6 - ROCHESTER TO MOBIL |  | 20683 | 10158 | 50000 |  | 2623715 |  | Guenther, Steve | Bishop, Rick | N/A |  | 1 | 30146 |  | Guest, ProSight | Independent | Aqua | 2018-07-30 | Leak Detection
Leak Detection - Vestal | Item | Open | MCAP | ZL00000M2201 | Maintenance Framework | 2036171 | Yezik, James | ECS Pipeline Integrity | 3. Active | Emergent | Leak Detection | 444508 | 250000 |  | 694508.18 | 664912 | 29596 | Yellow | 1000000 |  | 1000000 | -305492 |  |  | 1132000 |  |  | 1132000 | Full | 1132000 | 640146 | 250000 | 890146 | No | Green | 2022-10-01 | 2022-10-06 | 2022-10-06 | 2022-12-31 | 2023-09-30 |  |  | -92514.91 | 98209.84 | 209217.24 | 229596.01 | 200000 | 200000 | 29596 | Red |  | Engineering or Scope Change | 100000 | 100000 | 50000 | [6 empty] | 5/2/23 JY - Mechanical complete - waiting on final invoices due to piping anomalies found when excavating piping. Electrical 75% - waiting on invoices, havent received any. 4/4/23 JY - Mechanical almost complete. Electrical started 4/3. Later than expected. April spends will balance March underspend. 3/3/23 JY - Work began 2/21 for mechanical. Electrical scheduled to begin mid-March. 2/8/23 JY - Change of mechanical contractor caused delay in start of work. New contractor has been chosen with work expected to start week of 2/20. New quote for electrical work still needed from Bolt. 1/6/23 - Piping fabrication work has begun, but delays on Jet Lines project have pushed back start date onsite. 12/8/22 JY - Site walk with Strike to procur piping prior to EOY with local fabrication shop performing work. Construction to follow in 2023. 11/3/2022 NV- Variance due to delay of work from Strike personnel issues. 10/25/22 JY - Delays at Jet Lines sites impacting work. Will determine what can be done before EOY with Strike. 10/4/22 JY - Work delayed due to Strike personnel issues. 9.7.22.DLC: Shifted in funds from Marcy Short Line Project 9-2-22 JY: Waiting on Strike quote before issuing AFE. Site visit has taken place and will start work week of 9/26. 3/29/22 JY - Project added based on Allied Engineering progress. IFC expected in May. Clamp on metering, piping modification, PLC panels, and SCADA tie-in. Funds added from leak detection engineering. | 2023-05-02 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Auburn Terminals | BETZL - BET VESTAL TERMINAL |  | 214912 | 429596 | 50000 |  | 195638 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 43286 |  | Yezik, James | Independent | Aqua | 2022-03-29 | Leak Detection
Leak Detection Pennsauken -JY770QQ | Item | Open | MCAP | JY770QQM2301 | Maintenance Framework | 2096509 | Lyle, Trevor | ECS Pipeline Integrity | 2. Pending AFE | Defined | Leak Detection | 9100 | 39300 |  | 48400 | 52400 | -4000 | Yellow | 100000 |  | 100000 | -51600 | [6 empty] | Interim |  | 9100 | 39300 | 48400 | No | Green | 2023-04-01 |  |  |  | 2023-11-30 | [5 empty] | 9100 | 13100 | 13100 | -4000 | Red |  |  |  | 20500 | 13100 |  |  | 5700 |  |  |  | 03--09-2023 TJL - Material to be ordered is on 20 weeks lead time (to be confirmed) - installation will be delayed 07-20-22 Project not likely to be ready for 2022. Will go in 2023 | 2023-03-09 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Pennsauken | JY770QQ - PENN DELIV LOC TO PEN TERMINAL |  |  | 29600 | 13100 | 5700 |  |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 41422 |  | Administrator, System | Independent | Aqua | 2021-08-13 | Leak Detection
Leak Detection Port Reading - PR608XP | Item | Open | MCAP | PR608XPM2301 | Maintenance Framework | 2109729 | Lyle, Trevor | ECS Pipeline Integrity | 2. Pending AFE | Defined | Leak Detection | 9100 | 39300 |  | 48400 | 52400 | -4000 | Yellow | 100000 |  | 100000 | -51600 | [6 empty] | Interim |  | 9100 | 39300 | 48400 | No | Green | 2023-04-01 |  |  |  | 2023-11-30 | [5 empty] | 9100 | 13100 | 13100 | -4000 | Red |  |  |  | 20500 | 13100 |  |  | 5700 |  |  |  | 03--09-2023 TJL - Material to be ordered is on 20 weeks lead time (to be confirmed) - installation will be delayed 07-20-2022 Project not likely to be ready for 2022. Will go in 2023 | 2023-03-09 |  |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 29600 | 13100 | 5700 |  |  | Guenther, Steve |  |  |  | 1 | 41435 |  | Administrator, System | Independent | Aqua | 2021-08-13 | Leak Detection
Leak Detection Tuckerton - RG999A1 | Item | Open | MCAP | RG999A1M2301 | Maintenance Framework | 2096447 | Lyle, Trevor | ECS Pipeline Integrity | 2. Pending AFE | Defined | Leak Detection | 9100 | 39300 |  | 48400 | 52400 | -4000 | Yellow | 100000 |  | 100000 | -51600 | [6 empty] | Interim |  | 9100 | 39300 | 48400 | No | Green | 2023-04-01 |  |  |  | 2023-11-30 | [5 empty] | 9100 | 13100 | 13100 | -4000 | Red |  |  |  | 20500 | 13100 |  |  | 5700 |  |  |  | 03--09-2023 TJL - Material to be ordered is on 20 weeks lead time (to be confirmed) - installation will be delayed 07-22-22- Project not likely to move forward in 2022. WIll fall into 2023. 04/11/22 JY - added funds to August to cover engineering and construction costs. 02-08-2022 Project not likely to be ready for 2022. Will go in 2023 | 2023-03-09 |  |  | East | Pipelines and Terminals | Integrity |  | Macungie Pipe | RG999A1 - TUCKERTON TO FARM & HOME |  |  | 29600 | 13100 | 5700 |  |  | Guenther, Steve |  |  |  | 1 | 41437 |  | Administrator, System | Independent | Aqua | 2021-08-13 | Leak Detection
Leak Detection-LN999A1 | Item | Open | MCAP |  | Maintenance Framework |  | Yezik, James | ECS Pipeline Integrity | 2. Pending AFE | Defined | Leak Detection |  | 50000 |  | 50000 | 100000 | -50000 | Red | 100000 |  | 100000 | -50000 | [9 empty] | 50000 | 50000 | No | Green | 2023-10-01 |  |  |  | 2023-10-31 | [12 empty] | 0 |  |  |  |  | 50000 |  |  |  | 07-22-2022 Project not likely to be ready for 2022. Will go in 2023 | 2022-07-20 |  |  | East | Pipelines and Terminals | Integrity |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 0 |  | 50000 |  |  | Guenther, Steve |  |  |  | 1 | 41423 |  | Administrator, System | Independent | Aqua | 2021-08-13 | Leak Detection
Leak Detection-PY999A2 | Item | Open | MCAP |  | Maintenance Framework |  | Yezik, James | ECS Pipeline Integrity | 2. Pending AFE | Defined | Leak Detection |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 | [9 empty] | 100000 | 100000 | No | Green | 2023-10-01 |  |  |  | 2023-08-31 | [12 empty] | 0 |  |  |  |  | 100000 |  |  |  | 07-22-2022 Project not likely to be ready for 2022. Will go in 2023 | 2022-07-20 |  |  | East | Pipelines and Terminals | Integrity |  | Booth | BH - BOOTH STATION |  |  | 0 |  | 100000 |  |  | Guenther, Steve |  |  |  | 1 | 41436 |  | Administrator, System | Independent | Aqua | 2021-08-13 | Leak Detection
Linden Incoming Shipper PLC Replacement | Item | Open | MCAP | LN00000M2106 | Exempt | 1821359 | Bevevino, Jared | ECS Pipeline Integrity | 6. Operational | Defined | Instrumentation & Controls | -3348 |  |  | -3348.34 | -3348 | 0 | Green |  |  |  | -3348 |  |  | 69000 | 178000 |  | 247000 | Full | 247000 | 172182 |  | 172182 | No | Green | 2021-03-01 | 2021-03-08 | 2021-03-08 | 2021-07-31 | 2022-12-31 |  |  | 1826.3 | 0 | -5174.64 | [16 empty] | 1/10/23 NV- Electrical & programming cost less than expected. 12/9/22 NV- Electrical work less than expected. 09-08-2022 All materials have arrived. Still looking to complete in 2022. 8-8-2022 - Added 2023 Rollover Forecast of $1 to indicate addition consideration during budgeting should hardware/labor delays be observed in September. FF 06-08-2022-Material arrival time now September 04/11/2022 Still waiting on materials. 01/11/2022 Work pushed back 2 months due to the arrival of materials. 12-8-21 Work forecasted in December complete in November. 11/9 only work to be completed this year is the Omni upgrade with the PLC upgrade to happen in 2022 due to long lead time of materials. Phase 2 AFE submitted to purchase controls materials. Materials are backlogged and construction will look to commence in October/November/December. Phase 1 AFE submitted 03/01. Expected to begin engineering in late March Construction to begin in August/September | 2023-01-10 | Williams, Nikole |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  | -3348 | 0 |  |  | 68812 |  | Forsey, Frank | Ashley, Robert |  |  | 1 | 37621 |  | DeSocio, David | Independent | Aqua | 2020-08-11 | Other Programs
Linden North Tank Farm PLC Replacement | Item | Open | MCAP | LN00000M2216 | Maintenance Framework | 2045666 | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Defined | Instrumentation & Controls | -19606 | 65000 |  | 45393.74 | 45394 | 0 | Green | 100000 |  | 100000 | -54606 |  |  | 95000 |  |  | 95000 | Phase | 95000 | 1077 | 65000 | 66077 | No | Green | 2022-11-01 | 2022-11-18 | 2022-11-18 | 2023-12-31 | 2023-05-31 |  |  | 93.67 | 97.13 | -19797.06 |  | 0 | 0 | 0 | Green |  |  | 20000 | 30000 | 15000 | [6 empty] | 4/11/23 NV- Unforecasted reclass hit. 07-20-2022 Will only be able to accomplish engineering thie year due to material lead times. 03-09-2022 Site visit scheduled for the end of July. | 2023-04-11 | Williams, Nikole |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  | -19606 | 50000 | 15000 |  | 20683 |  | Forsey, Frank | Forehand, Adam |  |  | 1 | 37623 |  | DeSocio, David | Independent | Aqua | 2020-08-11 | Other Programs
Linden South Tank Farm PLC Replacement | Item | Open | MCAP | LN00000M2107 | Exempt | 1822128 | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Defined | Instrumentation & Controls | 48501 | 300000 |  | 348500.59 | 347057 | 1444 | Yellow | 300000 |  | 300000 | 48501 |  |  | 109000 | 446000 |  | 555000 | Full | 555000 | 231659 | 300000 | 531659 | No | Green | 2021-03-01 | 2021-03-11 | 2021-03-11 | 2022-06-01 | 2023-12-31 |  |  | 1188.46 | 1713.86 | 19154.38 | 26443.89 | 25000 | 25000 | 1444 | Yellow |  |  | 75000 |  | 75000 | 75000 |  | 75000 |  |  |  | 3/8/23 NV- Forecast adjusted due to lack of downtime on the line to do the work. Site walk happening 3/9 & more information to come. 12/9/22 NV- Materials arrived sooner than expected. 07-20-22 Forecast pushed back until 2023 due to expected arrival of materials 06-08-2022 Material arrive time now Septemner. Construction October at the earliest 03-09-2022 Work pushed back further due to further delay of material arrival dates. 01/011/2022 Work pushed back to Q2 due to arrival of materials. 12-8-21 Still plan on procuring materials with all work to take place in 2022. 11/9 Plan is to procure some of the material this year will all work to take place in 2022. Received all quotes for necessary job components. Most likely will have to shift project into 2022 because total project cost is 5-600k Still waiting on quotes from the panel shop and electrical contractors Phase 1 AFE submitted 03/01. Engineering slated for late March Construction early 3rd quarter | 2023-03-08 | Williams, Nikole |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  | 22057 | 101444 | 150000 | 75000 | 60496 |  | Forsey, Frank | Ashley, Robert |  |  | 1 | 37624 |  | DeSocio, David | Independent | Aqua | 2020-08-11 | Other Programs
LN603FZEP90199 Brentwood/Oakwood Drive Exposure Evaluation | Item | Open | MEXP | LN603FZE2301 | Maintenance Framework | 2110057 | Taylor, Ryan | ECS Pipeline Integrity | 3. Active | Drawdown | Exposed Pipe Evaluation & Remediation |  | 5000 |  | 5000 | 5000 | 0 | Green |  |  |  | 5000 |  |  | 5000 |  |  | 5000 | Full | 5000 |  | 5000 | 5000 | No | Green | 2023-05-01 | 2023-04-07 | 2023-04-07 | 2023-05-31 | 2023-05-31 | [6 empty] | 5000 | 5000 | -5000 | Red |  | Forecasting | 5000 | [10 empty] | Williams, Nikole |  | East | Pipelines and Terminals | Pipeline Integrity |  | Linden | LN603FZ - LINDEN TO FLEM VALVE -16IN |  |  | 5000 |  |  |  |  | Hurley, Brian | Bartal, Nick | N/A |  | 1 | 46881 |  | Hurley, Brian | JDE Child | Burnt Orange | 2023-04-05
LN603ZG - Like and Similar (Due 05-17-22) | Item | Open | MCAP | LN603FZM2201 | Maintenance Framework | 1945782 | Garcia, Francisco | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Digs | 158120 | 1000000 |  | 1158120.44 | 1159241 | -1121 | Yellow |  |  |  | 1158120 |  |  | 32000 | 1070000 |  | 1102000 | Full | 1102000 | 197676 | 1000000 | 1197676 | No | Green | 2022-05-01 | 2022-02-03 | 2022-02-03 | 2022-07-01 | 2023-07-01 |  |  | 54326.9 | 2356.91 | 557.26 | 100879.37 | 0 | 0 | 100879 | Red |  | WorkAhead of Schedule | 150000 | 370000 | 300000 | 180000 | [5 empty] | 5/5/2023 Partial May forecast pushed back to August... work just started. 5/2/2023 Work ahead of schedule; maintaining environmental controls. 1/03/2023 - project recently added to scorecard.. Kiely accrual didn't payout from previous PM entry. 12/9/2022 - Work rescheduled to Feb 23 due to transition of PMs. DC 11/2/2022 NAV- Work delayed due to permitting. 5/6/22 - $10k permitting support estimated for May 22 KB 3/4/2022 - This project has been pushed back later in the year due to environmental permitting. | 2023-05-05 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Linden | LN603FZ - LINDEN TO FLEM VALVE -16IN |  | 57241 | 620879 | 480000 |  | 39555 |  | Bartal, Nick | Guenther, Steve |  |  | 1 | 42482 |  | Guest, ProSight | Independent | Aqua | 2021-11-22 | Int - Accel Digs
LN604PC Additional Digs | Item | Open | MCAP | LN604PCM2102 | Exempt | 1869262 | Garcia, Francisco | ECS Pipeline Integrity | 7. Closed | Unplanned | Pipeline Digs | 8572 |  |  | 8572.4 | 8572 | 0 | Green |  |  |  | 8572 |  |  | 271000 |  | 163000 | 434000 | Supplemental | 434000 | 442443 |  | 442443 | No | Green | 2021-08-01 | 2021-09-01 | 2021-09-01 | 2021-12-31 | 2021-11-23 |  |  | 8203.25 | 369.15 | [17 empty] | 12/2/2022 supplement request to be submitted. 11/2/2022 supplement request will be submitted this week. 5/3/2022 supplement request will be submitted. | 2022-12-02 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Linden | LN - LINDEN STATION |  | 8572 | 0 |  |  | 11924 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40601 |  | Meitzler, Antoinette | Independent | Aqua | 2021-07-22 | Int- Planned Digs
LZ601JK - 2022 GEO+UWM ILI Digs | Item | Open | MCAP | LZ601XXM2201 | Exempt | 1972579 | Garcia, Francisco | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | 2226472 | 0 |  | 2226472.19 | 2168441 | 58031 | Yellow |  |  |  | 2226472 |  |  | 1064000 |  | 2863000 | 1064000 | Full | 3927000 | 4180504 | 0 | 4180504 | Yes | Red | 2022-05-01 | 2022-06-09 | 2022-06-09 | 2022-12-31 | 2023-05-01 |  |  | 162925.36 | 961438.7 | 964076.86 | 138031.27 | 30000 | 30000 | 108031 | Red |  | Other | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 05/02/2023 supplement request and engineering change order to be submitted. 05/02/2023 extra work completed by Hallen and additional invoicing resulted. 04/06/2023 Supplement request to be submitted with ECO. 04/04/2023 reclass expected -$30K from LZ602 03/09/2023 Project work ahead of schedule DC 02/02/2023 More work completed than expected. 01/04/2023 Overaccrual in November. 12/2/2022 Suppplemental AFE to be submitted. ECO was approved. 10/10/22 - Worked ahead on other digs while awaiting JFK site. 09-12-2022: Still waiting on permission from PANYNJ to conduct work. Also waiting for DEP permit for NJ digs 6/7/2022 Costs incurred from work planning, etc., ahead of schedule. 4/8/22 - NEB updated forecast for issued swamp digs | 2023-05-02 | Sautter, Maureen |  | East | Pipelines and Terminals | Integrity |  | Long Island | LZ601XX - LINDEN TO NY S/L (FUEL) LIPL |  | 2088441 | 138031 | 0 |  | 1954032 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 41012 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
LZ601JK Cutouts | Item | Open | MCAP | NL601JKM2301 | Project Framework | 2074862 | Garcia, Francisco | ECS Pipeline Integrity | 6. Operational |  | Pipeline Digs | 1347107 |  |  | 1347107.21 | 1190189 | 156919 | Red | 550000 |  | 550000 | 797107 |  |  | 1089000 |  |  | 1089000 | Full | 1089000 | 1347107 |  | 1347107 | Yes | Red | 2023-01-01 | 2023-01-10 | 2023-01-10 | 2023-06-30 | 2023-04-30 |  |  | 100000 | 310097.3 | 441091.22 | 495918.69 | 339000 | 339000 | 156919 | Red | [11 empty] | 05/02/2023 Supplement request and engineering change order to be submitted. 04/06/2023 Supplement request to be submitted with ECO. 3/2/2023 - waiting on invoices from Contractor; forecast was not missed; reaccrual. 2/9/23 - Project just approved invoiced for mobilization and start work | 2023-05-02 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Long Island | NL601JK - NEW LOTS-JFK AIRPORT-FUEL |  | 851189 | 495919 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 43946 |  | Guest, ProSight | Independent | Aqua | 2022-06-08 | Int - Accel Cutouts
LZ602IW - Digs from 2021 GEO+UWM ILI | Item | Open | MCAP | LZ602XXM2103 | Maintenance Framework | 1910733 | Garcia, Francisco | ECS Pipeline Integrity | 7. Closed | Defined | Pipeline Digs | 8569 |  |  | 8568.94 | 3697 | 4872 | Red |  |  |  | 8569 |  |  | 1163000 |  | 1616000 | 2779000 | Supplemental | 2779000 | 2857086 |  | 2857086 | No | Green | 2021-12-01 | 2022-01-20 | 2022-01-20 | 2022-12-31 | 2022-12-31 |  |  | 16655.07 | 14021.02 | -26978.87 | 4871.72 |  |  | 4872 | Red | [11 empty] | 04/04/2023 Reclass $30K to LZ601 submitted. 01/04/2023 Hallen costs more than anticipated due to work conducted in swamp. 9/12/2022 - Work ahead of schedule reallocated resources from 601 line pending JFK permitting. DC 7/5/2022 Material ordered and services contracted and paid for ahead of final AFE approved. 5/3/2022 Additional invoices from Napp and Janx; covered by supplement request, which has been submitted. 4/8/22 - NEB updated forecast for final issued digs outside of swamp area. 4/5/2022 - Costs came in less than expected; supplement still required. 3/9/22 - NEB Updated future forecast in anticipation of final ILI analysis digs (not yet discovered). 3/2/2022 Additional costs due to swamp and weather conditions. | 2023-04-04 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Linden | LNNON - LINDEN |  | 3697 | 4872 |  |  | 2509939 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 41008 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
LZ602XX Relocation | Item | Open | MCAP | LZ602XXM2201 | Maintenance Framework | 1938173 | Oldham, David | ECS Pipeline Integrity | 3. Active | Unplanned | Pipeline Digs | 75431 | 6070000 | 26000 | 6145431.1 | 6136061 | 9370 | Yellow | 4000000 |  | 4000000 | 2145431 |  |  | 316000 |  |  | 316000 | Phase | 316000 | 179441 | 7796000 | 7975441 | No | Green | 2022-01-01 | 2022-03-16 | 2022-03-16 | 2023-01-21 | 2023-07-31 |  |  | 26437.4 | 7161.25 | 7462.83 | 34369.62 | 25000 | 25000 | 9370 | Red |  |  | 25000 | 35000 | 5000 | 5000 | 500000 | 1500000 | 2000000 | 2000000 | 26000 | 3/7/2023 - dwo: Landowner delay. 2/2/2023 - dwo: Landowner challenge delayed Conrail permit/engineering effort. 1/10/23 - dwo: Project is moving forward with detailed engineering and Conrail permit submission. 9/6/2022: dwo - Title search complete and assessing alternate route through env. conservation easement. 7/11/22 - dwo: Continue to be delayed from landowner engagement. 6/6/22 - dwo: Landowner meeting in June should allow detailed engineering and permitting to proceed. 5/3/22 - dwo: Detailed engineering and permit submission on hold waiting for ROW easement negotiation. 4/11/22: forecast updated to reflect only engineering and permitting services. should permit timelines support 2022 construction, forecast will be updated accordingly. 2/22/22: Initiated engineering and permitting effort to complete pipeline relocations. Proceeding in first quarter to complete relocations in 2022 construction contingent on ROW negotiations and anticipated lengthy permitting process. | 2023-04-10 |  |  | East | Pipelines and Terminals | Integrity |  | Long Island | LZ602XX - LINDEN TO NY S/L (GAS) LIPL |  | 41061 | 94370 | 510000 | 5500000 | 104010 | 1700000 | Bartal, Nick | Guenther, Steve |  |  | 1 | 42750 |  | Guest, ProSight | Independent | Aqua | 2022-01-12 | Int - Advanced Strategy
PM755HW Richmond Road Exposure Repair-Mats | Item | Open | MCAP | PM755HWM2101 | Exempt | 1804077 | Bevevino, Jared | ECS Pipeline Integrity | 6. Operational | Defined | Exposure Remediation | 20371 |  |  | 20371.41 | 20609 | -238 | Yellow |  |  |  | 20371 |  |  | 45000 | 179000 |  | 224000 | Full | 224000 | 215537 |  | 215537 | No | Green | 2021-02-01 | 2021-01-25 | 2021-01-25 | 2021-10-15 | 2022-08-31 |  |  | 800 | 16200 | 3609 | -237.59 |  |  | -238 | Red | [11 empty] | 3/8/23 NV- Environmental costs came in higher than expected. 11/16 Received permit. Conditions of permit is that construction has to take place between July and September so this has been pushed back to July 2022. 11/9 Delay in permitting could push project back to 2022. All construction now forecast in 2022 due to the unknown timeline of permits Engineering and Permitting expected from March to June with 4th quarter contruction | 2023-03-08 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Maine | PM755HW - S PORTLAND TERM - HALLOWELL |  | 20609 | -238 |  |  | 159926 |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 37607 |  | Administrator, System | Independent | Aqua | 2020-08-11 | Int - Accel Exposures
PM755HW Spans-Exposures Captial Upgrade Engineering | Item | Open | MCAP | PM755HWM2202 | Project Framework | 1970610 | Taylor, Ryan | ECS Pipeline Integrity | 6. Operational | Defined | Exposure Remediation | 1471 |  |  | 1471.25 | 1471 | 0 | Green |  |  |  | 1471 |  |  | 498000 |  |  | 498000 | Phase | 498000 | 40188 |  | 40188 | No | Green | 2022-12-01 | 2022-04-07 | 2022-04-07 | 2022-04-01 | 2022-04-01 |  |  | 1471.25 | [18 empty] | 1/10/23 NV- Final assessment charges hit | 2023-01-10 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Maine | PM755HW - S PORTLAND TERM - HALLOWELL |  | 1471 | 0 |  |  | 38717 |  | Hurley, Brian | Guenther, Steve |  |  | 1 | 43140 |  | Meitzler, Antoinette | Independent | Aqua | 2022-03-09 | Int - Accel Exposures
Port Reading Dock PLC Upgrades | Item | Open | MCAP | BPRPR00M2107 | Exempt | 1838492 | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Defined | Instrumentation & Controls | 2991 |  |  | 2990.53 | 2226 | 765 | Red |  |  |  | 2991 |  |  | 89000 |  |  | 89000 | Phase | 89000 | 160972 |  | 160972 | No | Green | 2021-05-01 | 2021-04-28 | 2021-04-28 | 2021-07-31 | 2023-08-31 |  |  | 728.73 | 741.89 | 755.23 | 764.68 |  |  | 765 | Red | [11 empty] | 03-09-2022 All future forecasts removed as this project will go forward as part of a larger RCAP project with Exxon. 03-09-2022 Overspend in February attributed to two valves wrongly being charged to to this project. Working on fixing this. 02/10/2022 Fabircated PLC panels to arrive in February. Holding off work until to atleast March to coincide with possible RCAP projects 01/11/2022 Materials to arrive in February. Should be able to commence work then. Phase 2 AFE to be submitted shortly. 12-8-21 Still waiting on costs on all proposals to submit Phase II AFE. Should be submitted by end of year with all construction to take place in 2022. 11/9 Project slated for construction in 2022 with preliminary electrical and automation work to be done q4 2021 | 2022-03-10 | Williams, Nikole |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 2226 | 765 |  |  | 46564 |  | Forsey, Frank | Forehand, Adam |  |  | 1 | 37072 |  | DeSocio, David | Independent | Aqua | 2020-07-14 | Other Programs
PP8660HF Validation Digs 2023 | Item | Open | MCAP | PP860HFM2301 | Maintenance Framework | 2096277 | Melcer, Paul | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Digs | 3665 | 20000 |  | 23664.92 | 100000 | -76335 | Red |  |  |  | 23665 |  |  | 116500 |  |  | 116500 | Full | 116500 | 3665 | 20000 | 23665 | No | Green | 2023-04-01 | 2023-03-26 | 2023-03-26 | 2023-08-31 | 2023-06-01 | [5 empty] | 3664.92 |  |  | 3665 | Red |  |  | 20000 | [10 empty] | Williams, Nikole |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 23665 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46706 |  | Melcer, Paul | Independent | Aqua | 2023-03-06
PR608XP 2018 Port Reading to Port Reading Junction PRESSURE TEST | Item | Open | MCAP | PR608XPM1901 | Exempt | 1613563 | Garcia, Francisco | ECS Pipeline Integrity | 7. Closed | Unplanned | Pipeline Digs | 14614 |  |  | 14613.72 | 14614 | 0 | Green |  |  |  | 14614 |  |  | 350000 |  |  | 350000 | Full | 350000 | 390941 |  | 390941 | No | Green | 2020-01-01 | 2019-07-29 | 2019-07-29 | 2019-11-20 | 2021-12-01 |  |  | 13984.42 | 629.3 | [17 empty] | 2/2/2023 late invoice 01/04/2023 supplement or reclass to be submitted once final costs come in. Project complete. 01/03/2023 reclass applied for $78K, and other Brayco costs came in lower than expected. 12/2/2022 Work delayed due to contractor availability. Reclass submitted for $78K to BPRPR00E2226. 11/28/2022 reclass still pending.. new afe created and pending approval... reclass will be to BPRPR00E2226. 11/2/2022 - reclass $78,485 Simpson & Brown charges from 2021, which were applied by Operations; PM unaware of charges in 2021....reclass now pending to another project. 7/8/2019 AFE has been rejected and resubmitted due to update to work description. No changes to cost. | 2023-02-02 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 14614 | 0 |  |  | -8544 |  | Bartal, Nick | Buchalski, Edwin | N/A |  | 1 | 31158 |  | Guest, ProSight | Independent | Aqua | 2018-08-28 | Int - Assessments
River Rouge Terminal 300# Flange Upgrades 2022 | Item | Open | MCAP | BETHY00M2202 | Project Framework | 1946984 | Oldham, David | ECS Pipeline Integrity | 6. Operational | Defined | Transient/Surge Mitigation | 293657 | 100000 |  | 393656.91 | 393819 | -162 | Yellow | 10000 | 325000 | 335000 | 58657 |  |  | 119000 | 772000 |  | 891000 | Full | 891000 | 832570 | 100000 | 932570 | No | Green | 2022-03-01 | 2022-02-15 | 2022-02-15 | 2022-07-31 | 2023-03-16 |  |  | 7255.11 | 18111.93 | 263451.95 | 4837.92 | 65000 | 65000 | -60162 | Red |  | Weather | 23000 | 35000 | 42000 | [6 empty] | 5/8/2023: dwo - punchlist items delayed for more favorable weather. 4/10/2023: dwo - Variance due to weather not supporting complete closeout of work (painting, roof install, etc.) 1/10/2023: dwo - Variance caused by the delivery of equipment that had been pushed to 2023. All equipment is now in and outage targets the first week in March to coordinate work through scheduling and manage weather risk. 11/8/2022: dwo - Project continues to be delayed due to electrical components not shipping (original ship date in July). Anticipate remaining construction to push to CY23 unless breakers arrive before the end of November. 9/6/22: dwo - Variance due to electrical and mechanical contractors completing some work in advance to limit cold weather construction activities. Outage target pushed to November due to continued delay of electrical components. budget added to 2023 to reflect likely closeout project and as-built costs. 7/29/22: dwo - electrical components delivery further delayed to August. Construction outage pushed to September to mitigate further schedule risk. 7/5/2022: dwo - VFD and Electrical enclosure delivery delayed to July (~$36k). 6/6/22: dwo - Actuals - Forecast is <$10k. 5/9/2022: dwo - Contractor awarded for work. Anticipate materials being delivered in May and June and pre-fab construction work beginning in June. 4/4/2022: dwo - EAC updated to reflect final scope determined from design review and cost estimates from material bid events. Full AFE to be submitted in April. | 2023-05-08 | Williams, Nikole |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  | 288819 | 62838 | 42000 |  | 538913 |  | DiPillo, Evan | Guenther, Steve |  |  | 1 | 42024 |  | Clark, David | Independent | Aqua | 2021-08-31 | Other Programs
SA604LN - Cutouts | Item | Open | MCAP | LN604XPM2201 | Project Framework | 1945780 | Garcia, Francisco | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Digs | 3214 | 823000 |  | 826214.1 | 823472 | 2742 | Yellow |  |  |  | 826214 |  |  | 32000 | 791000 |  | 823000 | Phase | 823000 | 36749 | 823000 | 859749 | No | Green | 2022-05-01 | 2022-02-03 | 2022-02-03 | 2022-07-01 | 2023-06-30 |  |  | 153.98 | 157.48 | 160.31 | 2742.33 | 0 | 0 | 2742 | Red |  |  | 150000 | 523000 | 150000 | [6 empty] | 5/5/2023 Contractor will start in two weeks due to availability. May forecast reduced to $150K. 11/2/2022 NAV- Permitting delay, Kiely has not started work 7/12/22: Permitting delay NV 6/9/22 KDB: Permitting delayed until June the PO has been executed. 5/6/22 - $10k permitting support estimated for May 22 KB 3/4/2022 - This project has been pushed back in the year due to environment permitting. | 2023-05-05 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Linden | SA204PR - SEWAREN TO PT READING |  | 472 | 675742 | 150000 |  | 33535 |  | Bartal, Nick | Guenther, Steve |  |  | 1 | 40725 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Accel Cutouts
SA999A1 Piping Modification | Item | Open | MCAP | SA00000M1901 | Exempt | 1632746 | Garcia, Francisco | ECS Pipeline Integrity | 3. Active | Unplanned | ILI Modifications | 2306 | 30000 | 15000 | 32305.69 | 31716 | 590 | Yellow |  |  |  | 32306 |  |  | 157000 |  |  | 157000 | Full | 157000 | 124109 | 45000 | 169109 | No | Green | 2020-02-01 | 2019-09-27 | 2019-09-27 | 2019-12-31 | 2023-06-30 |  |  | 561.85 | 572 | 582.28 | 589.56 | 0 | 0 | 590 | Red |  |  |  | 30000 | [6 empty] | 15000 | 5/3/2022 Supplement request to be submitted. 4/8/22 - NEB added $15k contingency from overall program variance. | 2022-05-03 | Walker, Carol |  | East | Pipelines and Terminals | Integrity |  | Linden | SA - SEWAREN |  | 1716 | 30590 |  |  | 5406 |  | Bartal, Nick | Bassani, Joel D. | N/A |  | 1 | 29175 |  | Kudla, Megan | Independent | Aqua | 2018-06-05 | Other Programs
SA999A1 Shell Sewaren PRESSURE TEST | Item | Open | MEXP | SA00000E2001 | Exempt | 1768475 | Garcia, Francisco | ECS Pipeline Integrity | 3. Active | Unplanned | Assessments |  | 70000 |  | 70000 | 70000 | 0 | Green |  |  |  | 70000 |  |  | 70000 |  |  | 70000 | Full | 70000 | 49 | 70000 | 70049 | No | Green | 2021-04-01 | 2020-10-16 | 2020-10-16 | 2020-11-15 | 2023-06-30 | [6 empty] | 0 | 0 | 0 | Green |  |  |  | 70000 | [7 empty] | 4/12/2023 - LZ601 cutouts project took predominance in April so forecast was pushed back to June. No additional delays are expected. .9/27/22 - Assessment moved to 2023 3/2/2022 Forecast pushed back to April. | 2023-04-12 | Walker, Carol |  | East | Pipelines and Terminals | Pipeline Integrity |  | Linden | SA - SEWAREN |  |  | 70000 |  |  |  |  | Bartal, Nick | Bartal, Nick | N/A |  | 1 | 31157 |  | Guest, ProSight | Independent | Aqua | 2018-08-28 | Int - Assessments
Tinicum Island Road | Item | Open | MEXP | JD734BHE2201 | Maintenance Framework | 2051657 | Segraves, Scott | ECS Pipeline Integrity | 3. Active | Emergent | East | 9270 | 679249 |  | 688519.14 | 691427 | -2908 | Yellow | 800000 |  | 800000 | -111481 |  |  | 897000 |  |  | 897000 | Full | 897000 | 94152 | 679249 | 773401 | No | Green | 2022-12-01 | 2022-12-06 | 2022-12-06 | 2023-03-17 | 2023-03-17 |  |  | 18.14 | 8639.5 | 520 | 92.5 | 3000 | 3000 | -2908 | Red |  |  | 3000 | 676249 | [7 empty] | 2/2/2023 - SAS - Waiting on PHL Airport to send reimbursement agreement. | 2023-02-02 | Williams, Nikole |  | East | Pipelines and Terminals | Station/Terminal |  | Booth | JD734BH - DELAWARE RIVER JCT TO BOOTH |  | 9178 | 679342 |  |  | 84882 |  | Orischak, Bob | Votta, Joseph T. |  |  | 1 | 45965 |  | Clark, David | Independent | Aqua | 2022-10-04 | Other Programs
UB760AR Shallow Pipe Remediation Cascade Township 16820+04 | Item | Open | MCAP | UB760ARM2201 | Project Framework | 1956781 | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Drawdown | Shallow Pipe Remediation | 30014 | 500000 |  | 530014.18 | 518957 | 11058 | Yellow | 2200000 |  | 2200000 | -1669986 |  |  | 147000 | 2549000 |  | 2696000 | Full | 2696000 | 1313454 | 500000 | 1813454 | No | Green | 2022-03-01 | 2022-03-22 | 2022-03-22 | 2022-10-01 | 2023-06-30 |  |  | 35242.24 | -17571.84 | 1286.19 | 11057.59 |  |  | 11058 | Red |  |  |  | 200000 | 300000 | [6 empty] | 3/8/23 NV- NDT costs came in lower than expected. 1/10/23 NV- Missed forecasting CWIP & Interest. 12/5/22 NAV- Project moved forward with guidance from executive team after forecasts were locked. 08/23/2022-Forecast pushed back to 2023. 8/9/22 NAV- Updated forecast for project expected spends. 8.5.22.DLC: Moved $2.063MM from L415 deferral... 07-20-2022 Forecast adjusted to include construction in 2022 -2022 Work expected to commence in March. Waiting on AFE submission. | 2023-03-08 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity | Integrity | Eastern Iowa | UB760AR - DUBUQUE VLV - CEDER RAPIDS TER |  | 18957 | 211058 | 300000 |  | 1283440 |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 42899 |  | Guest, ProSight | Independent | Aqua | 2022-02-09 | Int - Accel Exposures
UB760AREP250A 2022 Exposure Repair | Item | Open | MCAP | UB760ARM2103 | Project Framework | 1909915 | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Defined | Exposure Remediation | 96353 | 400000 |  | 496352.6 | 488949 | 7404 | Yellow | 1550000 |  | 1550000 | -1053647 |  |  | 150000 | 1984000 |  | 2134000 | Full | 2134000 | 1419359 | 400000 | 1819359 | No | Green | 2021-12-01 | 2022-03-04 | 2022-03-04 | 2021-12-31 | 2023-04-30 |  |  | 71411.48 | -2447.84 | 19985.04 | 7403.92 |  |  | 7404 | Red |  |  |  | 200000 | 200000 | [6 empty] | 4/11/23 NV- Under accrued $10K previous month. 1/10/23 NV- Change order larger than expected due to issues to HDD. 12/5/22 NAV- Project moved forward with guidance from executive team after forecasts were locked. 08-22-2022 Forecast moved back to 2023 8/9/22 NAV- Forecast adjusted for project expected spends. 8.5.22.DLC: Added $1.037MM from 3 project reductions (ZG714ZN; ZG701JC, L761 sleeves) 07-20-22 Adjusting forecast to include construction costs 7/12/22 Golder ahead of schedule NV 05/09/2022. Project forecast as construction will be completed. Final decision yet to be made. 12-08-21 Preliminary Site Visit and Report to be submitted in December | 2023-04-11 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Eastern Iowa | UB760AR - DUBUQUE VLV - CEDER RAPIDS TER |  | 88949 | 207404 | 200000 |  | 1315006 |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 42448 |  | Meitzler, Antoinette | Independent | Aqua | 2021-11-15 | Int - Accel Exposures
UB760AREP284_UB760AREP284B Exposure Remediation | Item | Open | MCAP | UB760ARM2301 | Project Framework | 2075608 | Taylor, Ryan | ECS Pipeline Integrity | 3. Active | Defined | Exposure Remediation | 35093 | 1340000 |  | 1375092.51 | 1448131 | -73038 | Yellow |  | 280272 | 280272 | 1094821 |  |  |  | 12568 |  |  | Phase | 12568 | 35093 | 1340000 | 1375093 | No | Green | 2023-01-01 |  |  | 2023-10-01 | 2023-11-30 |  |  | 10000 | 50690 | 7440.91 | -33038.4 | 40000 | 40000 | -73038 | Red |  | Forecasting | 20000 | 100000 | 820000 | 400000 | [5 empty] | 20230509 NV - Reclass forecasted but not complete, to be complete in May. 20230411 - RJT - Adjust major spend start. 20230309 - RJT - Adjusted Project spend start | 2023-05-09 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Eastern Iowa | UB760AR - DUBUQUE VLV - CEDER RAPIDS TER |  | 68131 | 86962 | 1220000 |  |  |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 46432 |  | Guest, ProSight | Independent | Aqua | 2023-01-05 | Int - Planned Exposures
UC762OI MP 52 Exposure Remediation | Item | Open | MCAP | UC762OIM2204 | Project Framework | 1955384 | Bevevino, Jared | ECS Pipeline Integrity | 6. Operational | Defined | Exposure Remediation | 19556 |  |  | 19555.56 | 17184 | 2372 | Red |  |  |  | 19556 |  |  | 1785000 |  |  | 1785000 | Full | 1785000 | 1511843 |  | 1511843 | No | Green | 2022-09-01 | 2022-09-06 | 2022-09-06 | 2022-10-15 | 2022-10-15 |  |  | -3926.09 | 15157.55 | 5952.11 | 2371.99 |  |  | 2372 | Red | [11 empty] | 3/8/23 NV- Invoice coding error, will be corrected going forward. 1/10/23 NV- Change order for drilling issues more than expected.12/9/22 NV- Change order more than expected. 11/3/202 NV- Variance due to change order higher than expected. 10/10/2022 NAV- Additional drilling costs 9/12/2022- Accruals from 43103 will hit this project in September. 09-08-2022-Forecasts moved from 43103 | 2023-03-08 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | UC762OI - CRESTION STA TO DES MOINES TER |  | 17184 | 2372 |  |  | 1492287 |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 45224 |  | Meitzler, Antoinette | Independent | Aqua | 2022-08-23 | Int - Accel Cutouts
UC762OI Spans-Exposures Captial Upgrade | Item | Open | MCAP | UC762OIM2203 | Project Framework |  | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Defined | Exposure Remediation | 16621 |  |  | 16620.93 | 20371 | -3750 | Red |  |  |  | 16621 |  |  | 648000 | 1137000 |  | 648000 | Full | 1785000 | 288545 |  | 288545 | No | Green | 2022-03-01 | 2022-04-12 | 2022-04-12 | 2022-04-01 | 2023-12-31 |  |  | -18046.39 | 28839.29 | 9577.92 | -3749.89 |  |  | -3750 | Red | [11 empty] | 3/8/23 NV- Inspector costs hit, missed forecast. 1/10/23 NV- Inspector costs higher than expected. 11/2/2022 NV- Inspector PO needs to be reclassed, waiting until fully billed out to reclass. 10/12/22 - Negative variance reflecting reclass to new project DC 10/11/22 NAV- Negative forecast should have been entered for October. 9/12/2022 NAV- Accruals will shift to 45224 negative variance expected to hit for September ~$200K. Variance due to unexpected ROW fees. 09-02-2022-New project number created. Forecasts moved to that OPPM entry. 8/9/22 NAV- forecast adjusted to updated schedule starting in late august. 07-12-2022- Golder Engineering and permitting sped up in June. Will have final construction numbers on 07-20 05/09/2022.Moving forward with full design,permitting, and construction on one of the exposure assessment done under this project number-WO-1955384 | 2023-03-08 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | UC762OI - CRESTION STA TO DES MOINES TER |  | 20371 | -3750 |  |  | 271924 |  | Hurley, Brian | Guenther, Steve |  |  | 1 | 43103 |  | Meitzler, Antoinette | Independent | Aqua | 2022-03-04 | Int - Accel Exposures
UC762OIEP75C/76A Exposure Remediation | Item | Open | MCAP | UC762OIM2201 | Project Framework | 1947077 | Bevevino, Jared | ECS Pipeline Integrity | 6. Operational | Defined | Exposure Remediation | 1285 |  |  | 1284.75 | 5388 | -4103 | Red |  |  |  | 1285 |  |  | 182000 | 1096000 |  | 1278000 | Full | 1278000 | 843899 |  | 843899 | No | Green | 2022-02-01 | 2022-02-25 | 2022-02-25 | 2022-10-01 | 2022-12-31 |  |  | 3936.89 | -4523.4 | 5974.05 | -4102.79 |  |  | -4103 | Red | [11 empty] | 11/9/22 NV- Purge assistance cost less than expected. 10/11/2022 NAV- Work ahead of schedule. 8/9/2022- Forecasted adjusted due to receiving the schedule from the contractors and expected start date is mid-September. 7/12/22 Golder ahead of schedule. NV 05/09/2022-More money spent on engineering this month than expected. 03-09-2022- Spends flipped from OPPM ID 42447 as interim to this project. | 2022-11-09 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | UC762OI - CRESTION STA TO DES MOINES TER |  | 5388 | -4103 |  |  | 842614 |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 41163 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Accel Exposures
UC762OIEP90C Exposure Remediation | Item | Open | MCAP | UC762OIM2202 | Project Framework | 1947078 | Bevevino, Jared | ECS Pipeline Integrity | 6. Operational | Defined | Exposure Remediation | -15725 |  |  | -15724.71 | -13223 | -2502 | Red |  |  |  | -15725 |  |  | 152000 | 1057000 |  | 1209000 | Full | 1209000 | 804380 |  | 804380 | No | Green | 2022-02-01 | 2022-03-04 | 2022-03-04 | 2022-10-01 | 2022-11-10 |  |  | -12444.08 | 30033.21 | -30811.84 | -2502 |  |  | -2502 | Red | [11 empty] | 4/11/23 NV- Invoice error caused for over accrual. 3/8/23 NV- Invoice coding error, will be corrected going forward. 1/10/23 NV- Additional costs put in geocell. 11/9/2022 NV- Less N2 needed than expected for purge. 10/4/2022 NAV- Contractor ahead of schedule. 9/12/22 NAV- Variance due to inspector costs hitting project due to the way PO was cut. Inspector working at various sites but PO cut to this project. 8/9/22 NAV- forecast adjusted given contractors updated schedule not starting project until late September. 07-12-2022- Golder Engineering and permitting sped up in June. Will have final construction numbers on 07-20 | 2023-04-11 |  |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | UC762OI - CRESTION STA TO DES MOINES TER |  | -13223 | -2502 |  |  | 820105 |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 42710 |  | Clark, David | Independent | Aqua | 2022-01-06 | Int - Accel Exposures
UD761UR Spans-Exposures Capital Upgrade Engineering | Item | Open | MCAP | UD761URM2201 | Project Framework | 1946921,1946922,1946923,1946924,1946925,1946926, 1946927, 1946928 | Taylor, Ryan | ECS Pipeline Integrity | 6. Operational | Emergent | Exposure Remediation | 283 |  |  | 283.25 | 283 | 0 | Green |  |  |  | 283 |  |  | 783000 |  |  | 783000 | Full | 783000 | 66892 |  | 66892 | No | Green | 2022-03-01 | 2022-02-15 | 2022-02-15 | 2022-04-01 | 2022-04-01 |  |  | 283.25 | [18 empty] | 4.7.22.NAW-Determined assessment report not needed at several sites | 2022-04-07 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | UD761UR - MUDDY CREEK TO BURLINGTION JCT |  | 283 | 0 |  |  | 66608 |  | Hurley, Brian | Guenther, Steve |  |  | 1 | 42911 |  | Meitzler, Antoinette | Independent | Aqua | 2022-02-11 | Int - Accel Exposures
UDE761UREP71A Exposure Remediation | Item | Candidate | MCAP |  | Project Framework |  | Bevevino, Jared | ECS Pipeline Integrity | 2. Pending AFE |  | Exposure Remediation |  |  |  | 0 |  | 0 | Green | 1100000 |  | 1100000 | -1100000 | [11 empty] | No | Green |  |  |  |  | 2023-06-30 | [21 empty] | 2/2/23 - BMH Project deferred $1100000 reallocated to other exposures | 2023-02-02 |  |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | UD761UR - MUDDY CREEK TO BURLINGTION JCT |  |  | 0 |  |  |  |  | Hurley, Brian |  |  |  | 1 | 44551 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Int - Planned Exposures
UG761UD Spans-Exposures Capital Upgrade Engineering | Item | Open | MCAP | UG761UDM2201 | Project Framework | 1946955, 1946956, 1946957, 1946958, 1946959, 1946960 | Bevevino, Jared | ECS Pipeline Integrity | 6. Operational | Emergent | Exposure Remediation | 553 |  |  | 553.28 | 553 | 0 | Green |  |  |  | 553 |  |  | 427000 |  |  | 427000 | Full | 427000 | 311206 |  | 311206 | No | Green | 2022-05-01 | 2022-02-15 | 2022-02-15 | 2022-04-01 | 2022-04-01 |  |  | 553.28 | [18 empty] | 1/10/23 NV- Final assessment costs hit, missed forecast. 12/9/22 NV- Previously accrued dollars moved to different project. 8/9/22 NAV- Dollars should have been accrued for Kiely at beginning of project in March, thus the variance in July. Missed in the process of transitioning projects from PM to PM. Forecast adjusted to match contractor schedule. 07-12-2022 Exposures UG761UDEP31 and UG761UDEP20A moving forward under this work project number 7.22.NAW-Determined assessment report not needed at several sites | 2023-01-10 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | UG761UD - SUGAR CREEK TERM - MUDDY CREEK |  | 553 | 0 |  |  | 310653 |  | Hurley, Brian | Guenther, Steve |  |  | 1 | 42914 |  | Meitzler, Antoinette | Independent | Aqua | 2022-02-11 | Int - Accel Exposures
UG761UDEP28 Exposure Remediation | Item | Open | MCAP | UG761UDM2301 | Project Framework | 2109913 | Bevevino, Jared | ECS Pipeline Integrity | 3. Active | Defined | Exposure Remediation | 8000 | 30001 |  | 38001 | 35001 | 3000 | Yellow |  |  |  | 38001 |  |  | 96695 |  |  | 96695 | Phase | 96695 | 8000 | 30001 | 38001 | No | Green | 2023-04-01 | 2023-04-04 | 2023-04-04 | 2023-10-15 | 2023-09-01 | [5 empty] | 8000 | 5000 | 5000 | 3000 | Red |  |  | 10000 | 10000 | 10000 |  |  |  |  | 1 |  |  |  | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | UD761UR - MUDDY CREEK TO BURLINGTION JCT |  |  | 28000 | 10000 | 1 |  |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 46596 |  | Bevevino, Jared | Independent | Aqua | 2023-02-14
UR762XX Spans-Exposures Captial Upgrade Engineering | Item | Open | MCAP | UR762XXM2201 | Project Framework | 1971062 | Taylor, Ryan | ECS Pipeline Integrity | 6. Operational | Defined | Exposure Remediation | 525 |  |  | 524.93 | 525 | 0 | Green |  |  |  | 525 |  |  | 214000 |  |  | 214000 | Phase | 214000 | 14339 |  | 14339 | No | Green | 2022-12-01 | 2022-04-12 | 2022-04-12 | 2022-04-01 | 2022-04-01 |  |  | 524.93 | [18 empty] | 1/10/23 NV- Final assessment charges hit | 2023-01-10 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | UR762XX - BURLINGTION JCT TO IA S/L |  | 525 | 0 |  |  | 13814 |  | Hurley, Brian | Guenther, Steve |  |  | 1 | 43104 |  | Meitzler, Antoinette | Independent | Aqua | 2022-03-04 | Int - Accel Exposures
Waterloo Station DRA Skid Containment | Item | Open | MCAP | WA00000M2003 | Exempt | 1744251 | Bevevino, Jared | ECS Pipeline Integrity | 6. Operational | Unplanned | Secondary Containment | 2285 |  |  | 2285 | 2285 | 0 | Green |  |  |  | 2285 |  |  | 23000 | 211000 |  | 234000 | Full | 234000 | 224912 |  | 224912 | No | Green | 2020-09-01 | 2020-08-13 | 2020-08-13 | 2020-11-01 | 2021-08-31 |  |  |  | 539.3 | 1745.7 | [16 empty] | 12-08-21 Waste expected to be disposed of in December 11/9 Project is complete as of 09/30. some waste disposal costs to hit and as-built engineering. Plan is still to replace with new PLUS skid Preliminary engineering just completed by Diamond Z Drawings have been sent out to same contractors as Penn Forest but I have not received quotes yet Estimated completion will be late October Update as of 09/10 Project will be pushed off to 2021 due to current year budget concerns. | 2021-12-08 | Williams, Nikole |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Pipeline | WA - WATERLOO STATION |  | 2285 | 0 |  |  | 3422 |  | Clark, Dave | Loy, Brian J. |  |  | 1 | 34036 |  | Guest, ProSight | Independent | Aqua | 2019-08-15 | Other Programs
WO160AS Luke Hahn B Sleeve cutouts | Item | Open | MCAP | WO160BNM2203 | Exempt | 2012362 | Taylor, Ryan | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | 84956 | 28000 |  | 112955.62 | 111190 | 1766 | Yellow |  |  |  | 112956 |  |  | 930000 |  | 401000 | 930000 | Supplemental | 1331000 | 1274306 | 28000 | 1302306 | No | Green | 2022-08-01 | 2022-10-02 | 2022-10-02 | 2022-10-07 | 2022-12-31 |  |  | 28711.23 | 47962.96 | 6515.63 | 1765.8 |  |  | 1766 | Red |  |  | 28000 | [8 empty] | 1/10/23 NV- Delays across the board added to higher spend. 10/7/2022 NAV- Scope change and purge time changed resulting in variance. 9/9/2022 NAV- Project start up delayed to September. Purge delayed to October, updated forecast accordingly. 8/9/2022 NAV- Project schedule pushed out, updated forecast accordingly. 6.8.22.DLC: - moved $250k from other L160 OPPM record | 2023-01-10 | Williams, Nikole | Guenther, Stephen | West | Pipelines and Terminals | Integrity |  | St. Louis | WO160BN - WOOD RIVER TO BARNETT |  | 83190 | 29766 |  |  | 1189350 |  | Bartal, Nick | Guenther, Steve |  |  | 1 | 43872 |  | Clark, David | Independent | Aqua | 2022-06-02 | Int - Accel Cutouts
WO160BN Spans-Exposures Capital Upgrade Engineering | Item | Open | MCAP | WO160BNM2201 | Project Framework | 1946893, 1946894, 1946895, 1946896, 1946897, 1946898 | Taylor, Ryan | ECS Pipeline Integrity | 6. Operational | Emergent | Exposure Remediation | 730 |  |  | 729.71 | 730 | 0 | Green |  |  |  | 730 |  |  | 427000 |  |  | 427000 | Phase | 427000 | 23946 |  | 23946 | No | Green | 2022-03-01 | 2022-02-15 | 2022-02-15 | 2022-04-01 | 2022-12-31 |  |  | 729.71 | [18 empty] | 1/10/23 NV- Final assessment charges hit. 4.7.22.NAW-Determined assessment report not needed at several sites | 2023-01-10 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | St. Louis | WO160BN - WOOD RIVER TO BARNETT |  | 730 | 0 |  |  | 23216 |  | Hurley, Brian | Guenther, Steve |  |  | 1 | 42929 |  | Meitzler, Antoinette | Independent | Aqua | 2022-02-11 | Int - Accel Exposures
WO180ST – Cutout of Temporary Repair | Item | Open | MCAP | WO180XXM2201 | Project Framework | 1954861 | Kosior, Albert | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | 12448 |  |  | 12447.75 | 12193 | 255 | Yellow |  |  |  | 12448 |  | Scheduling | 78000 | 779000 |  | 857000 | Full | 857000 | 834799 |  | 834799 | No | Green | 2022-03-01 | 2022-03-02 | 2022-03-02 | 2022-07-31 | 2022-11-04 |  |  | 11037.13 | -4244.38 | 5400.3 | 254.7 |  |  | 255 | Red | [11 empty] | 12-8-22 The project was completed in October and just finishing up cleanup and working closeout. 11-4-22 The line was purged and the cutouts performed the end of October, working pipe coating and restoration. 10-10-22 Project kicked off on 10/10 with purge scheduled for 10/24 followed by tie-ins. Principally all work to be performed in October. 9-12-22 The purge and cutout are scheduled for October. Developing the AFE now. 8-9-22 Received permit from NSRR. Two additional cutouts were added to the project since the line is going to be purged. The work is schedule for September. 7-12-22 Finalizing permitting with NSRR. 6/9/22 - Waiting on the NSRR permit review. 5-9-22 NSRR permit application was submitted and getting ready to bid the project this month. 4-7-22 Working permitting, hope to go to bid by end of April. 3-7-22 A Phase 1 AFE for permitting and bid support services was approved. PI added two additional cutouts to the project. They are located in the Valero/P66 tank farm. 1-4-22 With the change of contractors, need to go out to O/S to prepare R/R permit. Will get a staged AFE submitted this month for the permitting services. Hope to complete work by end of 1st QTR. 11-8-21 Project moved to 2022 due to NS R/R permitting constraints. 11-1-21 The work is within NS R/R ROW and we need to get an access permit. Looking to pay $9k expediting fee to see if we can get it by the end of the month. It is a 50/50 chance that this will get done in December. 10-4-21 Conducting planning meetings to figure out how to complete this cutout. It is located on a long, sweeping bend next to a road and beside a railroad track. 9-2-21 Working on plan and AFE. | 2022-12-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | St. Louis | WO180XX - WOOD RIVER TO MO S/L |  | 12193 | 255 |  |  | 822351 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40335 |  | Guest, ProSight | Independent | Aqua | 2021-06-29 | Int - Planned Cutouts
WS209WW - Cutouts | Item | Open | MCAP | WS209WWM2201 | Maintenance Framework | 1945788 | Kizzire, Jerrod | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | 1133 |  |  | 1132.82 | 1133 | 0 | Green |  |  |  | 1133 |  |  | 32000 | 571000 |  | 603000 | Full | 603000 | 596196 |  | 596196 | No | Green | 2022-03-01 | 2022-02-03 | 2022-02-03 | 2022-07-01 | 2022-07-01 |  |  | 1132.82 | [18 empty] | 11/2/2022 NAV- Delayed environmental costs (non-PO costs set up by asset team), not forecasted 9/9/2022 NAV- Variance due to contractor costs higher than anticipated. 8/5/2022- Variance due to accrual error, should have accrued ~$50K more costs for Roberts Pipeline completing most work in July. 3/4/2022 - This project will be completed with the 211 cutouts by the same contractor. Those scopes are being evaluated to include any B sleeves that may need to be cutout. | 2022-11-02 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | WS209WW - WOODHAVEN TO WAYNE |  | 1133 | 0 |  |  | 595063 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40726 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Accel Cutouts
WW203WF 60 Day Dig & other BPL Dig | Item | Open | MCAP | WW203WCM2302 | Maintenance Framework | 2120564 | Melcer, Paul | ECS Pipeline Integrity | 2. Pending AFE |  | Pipeline Digs |  | 200000 |  | 200000 |  | 200000 | Red |  |  |  | 200000 | [6 empty] | Interim |  |  | 200000 | 200000 | No | Green | 2023-05-01 |  |  |  | 2023-06-23 | [12 empty] | 100000 | 100000 | [11 empty] | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | WC203WF - CLARKSTON TO FLINT |  |  | 200000 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 47012 |  | Melcer, Paul | Independent | Aqua | 2023-05-02
WW203WF-1 Interim Repair Cutouts 2023 | Item | Open | MCAP |  | Project Framework |  | Melcer, Paul | ECS Pipeline Integrity | 2. Pending AFE | Defined | Pipeline Digs | 0 | 400000 |  | 400000 | 400000 | 0 | Green | 400000 |  | 400000 | 0 | [8 empty] | 0 | 400000 | 400000 | No | Green | 2023-06-01 |  |  |  | 2023-05-31 | [5 empty] | 0 |  |  | 0 | Green |  |  |  | 200000 | 200000 | [10 empty] | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | WW203WC - WAYNE TO CLARKSTON |  |  | 200000 | 200000 |  |  |  | Bartal, Nick |  |  |  | 1 | 44933 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Cutouts
WW211DS - Cutouts | Item | Open | MCAP | WW211XXM2201 | Maintenance Framework | 1945790 | Kizzire, Jerrod | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | 41618 |  |  | 41617.65 | 39717 | 1901 | Yellow |  |  |  | 41618 |  |  | 74000 | 4872000 |  | 4946000 | Full | 5325922 | 5239362 |  | 5239362 | No | Green | 2022-03-01 | 2022-02-03 | 2022-02-03 | 2022-07-01 | 2022-07-01 |  |  | 27908.01 | 11060.5 | 748.14 | 1901 |  |  | 1901 | Red | [11 empty] | 11/2/2022 NAV- Several expected costs came in under budget/forecast resulting in the variance. 10/10/2022 NAV- Variance due to past accruals based on anticipated change order amount, when the change order was processed it came in lower than expected. 9/9/2022 NAV- Variance due to over-accruing in August. 8/5/2022- Variance due to interest costs & nonPO environmental costs. NV 7/12/22 - Work ahead of schedule. Three additional dig sites complete in close proximity. DC 5/10/22 - Work planned for June. 3/10/22 - Delayed due to scheduling availability, pushed to May/June. DC 3/4/2022 - The scope for this project being evaluated to include any B sleeves that may need to be cutout. | 2022-11-02 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | WW211XX - WAYNE TO OHIO S/L SOUTH |  | 39717 | 1901 |  |  | 5197744 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40727 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Accel Cutouts
XB003XX - 2022 Buckeye Criteria Digs | Item | Open | MCAP | XB003XXM2203 | Maintenance Framework | 2037287 | Taylor, Ryan | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | 5108 |  |  | 5107.9 | 5108 | 0 | Green |  |  |  | 5108 |  |  | 118000 |  |  | 118000 | Full | 118000 | 127983 |  | 127983 | No | Green | 2022-10-01 | 2022-10-18 | 2022-10-18 | 2022-09-09 | 2022-12-31 |  |  |  | 4887.94 | 219.96 | [16 empty] | 10/10/2022 RT - Crew experienced delay at previous dig site, started work onsite begining of Oct. 10/7/2022 NAV- Work should have started end of september but did not begin until first week of October. 9/9/22 NAV- Delayed start, work will start & complete in September. 5/9 NAW - Forecasting to start in August 2022 2/2/22 - No Change 1/3/22 - No Change | 2022-10-10 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Huntington | XB003XX - HUNTINGTON TO OHIO S/L- EAST |  | 5108 | 0 |  |  | 122875 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40987 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
XB003XX - DOT Digs 2021 UCD ILI | Item | Open | MCAP | XB003XXM2202 | Maintenance Framework | 1972577 | Taylor, Ryan | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | -220555 | 32199 |  | -188355.67 | -138883 | -49473 | Red |  |  |  | -188356 |  |  | 4152000 |  | 1058000 | 5210000 | Supplemental | 5210000 | 4842915 | 32199 | 4875114 | No | Green | 2022-05-01 | 2022-06-27 | 2022-06-27 | 2022-09-01 | 2022-11-30 |  |  | -10998.69 | 34841.44 | -194924.48 | -49472.94 |  |  | -49473 | Red |  |  | 15000 | 17199 | [7 empty] | 20230509 NV- Accurals ceased due to confirmation of billing completion. 4.6.23 - added -$196,952 to March forecast due to MEXP Flip XB003XXE2201 (AS) 20230309 NV- Trailing inspector invoices. 1/10/23 NV- Missed accrual back in November. 12/9/22 NV- Invoice submitted after accrual due date ~$150K difference from accrual. Change order provided by contractor overestimated and there were several no repairs at the end of the project. by ~ 11/9/2022 NV- Repairs not as severe as expected. 10/21/22 RT - Updated forecast for Nov. moving forward with the three additional dig sites after guidance from integrity. ECO and supplemental AFE submitted. 10/10/22 RT - Forecast decrease due to one crew being laid off. All digs will be completed by 10/30/22 *Dependent upon Integrity guidance there could be an additional ~$400K+ spend for November 9/9/22 RT- Forecast increase due increased length of sleeves installed, hydrovacing, safety inspection, and number of trenchboxes utilized on dig sites. 9/9/22 NAV- Variance due to work ahead of schedule. 8/9/22 NAV- Variance due to unforecasted CWIP costs and vactruck on site. 6/9/22 NAV- Contractor mobilized a week later than expected. 6/8/22 NB - digs planned primarily Jun-Aug 5/9 NAW-Forecasting as digs starting on 5/13, dependent upon inspector and contractor availability. 4/29 85 Criteria and Proximity digs were issued project number XB003XXM2201. | 2023-05-09 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Huntington | XB003XX - HUNTINGTON TO OHIO S/L- EAST |  | -171082 | -17274 |  |  | 5063470 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 43392 |  | Taylor, Ryan | Independent | Aqua | 2022-04-13 | Int- Planned Digs
XB003XX HDD and Interim Repair Cutouts 2023 | Item | Open | MCAP | XB003XXM2301 | Project Framework | 2074682 | Taylor, Ryan | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Digs | 216936 | 2300000 |  | 2516935.55 | 2504574 | 12362 | Yellow | 3800000 |  | 3800000 | -1283064 |  |  | 206186 |  |  | 206186 | Phase | 206186 | 216936 | 2300000 | 2516936 | No | Green | 2023-01-01 | 2023-03-08 | 2023-03-08 | 2023-08-01 | 2023-05-31 |  |  | 45900 | 40455.87 | 63217.78 | 67361.9 | 55000 | 55000 | 12362 | Red |  |  | 200000 | 1500000 | 600000 | [6 empty] | 20220411 RJT - Updated start of major spends. 20220308 RT - Project was moved up to May construction start. | 2023-04-11 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Huntington | XB003XX - HUNTINGTON TO OHIO S/L- EAST |  | 149574 | 1767362 | 600000 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44934 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Cutouts
XB403CL Interim Repair Cutouts 2023 | Item | Open | MCAP |  | Project Framework |  | Melcer, Paul | ECS Pipeline Integrity | 2. Pending AFE | Defined | Pipeline Digs | 0 | 400000 |  | 400000 | 400000 | 0 | Green | 400000 |  | 400000 | 0 | [8 empty] | 0 | 400000 | 400000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [5 empty] | 0 |  |  | 0 | Green |  |  |  |  | 400000 | [10 empty] | West | Pipelines and Terminals | Integrity |  | Huntington | XB403CL - HUNTINGTON TO CLERMONT |  |  | 0 | 400000 |  |  |  | Bartal, Nick |  |  |  | 1 | 44935 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Cutouts
XX163KK Feature F-0245776 Like & Similar Pipeline Cutout | Item | Open | MCAP | XX163KKM2204 | Project Framework | 2045725 | Kosior, Albert | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Replacements | 19770 |  |  | 19770.37 | 19771 | -1 | Yellow |  |  |  | 19770 |  | Scheduling | 574000 |  |  | 574000 | Full | 574000 | 454970 |  | 454970 | No | Green | 2022-11-01 | 2023-01-03 | 2023-01-03 | 2022-12-30 | 2022-12-31 |  |  | 16364.8 | 1986.73 | 1419.73 | -0.89 |  |  | -1 | Red | [11 empty] | 1-10-22 Dig was completed in December. Working project closeout 12-8-22 Project kicked off on 11/28 and will complete in December. | 2023-01-10 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Argo | XX163KK - IN S/L TO KANKAKEE |  | 19771 | -1 |  |  | 435200 |  | Oldham, David | Bartal, Nick |  |  | 1 | 46234 |  | Guest, ProSight | Independent | Aqua | 2022-11-16 | Int - Planned Cutouts
XX760IMEP121D Exposure Remediation | Item | Open | MCAP | XX760IMM2102 | Project Framework | 1909912 | Bevevino, Jared | ECS Pipeline Integrity | 6. Operational | Defined | Exposure Remediation | 47523 |  |  | 47523.26 | 45184 | 2339 | Yellow |  |  |  | 47523 |  |  | 188000 | 2273000 |  | 2461000 | Full | 2461000 | 2348536 |  | 2348536 | No | Green | 2022-03-01 | 2022-03-07 | 2022-03-07 | 2022-10-01 | 2022-10-01 |  |  | 34982.97 | 3633.74 | 6567.46 | 2339.09 |  |  | 2339 | Red | [11 empty] | 1/10/23 NV- Additional mud disposal costs. 11/3/2022 NV- Variance due to final costs/change orders coming in higher than expected ~$180K. 10/11/2022 NAV- Purge more expensive than originally forecasted. 9/12/2022 NAV- Under forecasted 8/9/22 NAV- forecast adjusted based on schedule changes. 07-19-2022- Moved forecast from L701 Dresserville Creek Exposure project to this project. | 2023-01-10 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Eastern Iowa | XX760IM - IA S/L TO MILAN STATION |  | 45184 | 2339 |  |  | 2301013 |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 42535 |  | Clark, David | Independent | Aqua | 2021-12-02 | Int - Accel Exposures
XX761NB DOT 60-Day Digs 2020 | Item | Closed | MCAP | XX761NBM2001 | Exempt | 1671614 | Kosior, Albert | ECS Pipeline Integrity | 7. Closed | Drawdown | Pipeline Digs | -3267 |  |  | -3267.46 | -3267 | 0 | Green |  |  |  | -3267 | [6 empty] | Full |  | 0 |  | 0 | No | Green | 2020-01-01 |  |  | 2020-01-31 | 2020-03-06 |  |  |  |  | -3267.46 | [16 empty] | 5/11/2020 Project was flipped and all cost should be reclassed. 3/7/20 - work complete, working project closeout - Project flipped to MEXP 1/8/20 - Project to be completed in January | 2020-05-11 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | XX761NB - MO S/L TO COUNCIL BLUFFS |  | -3267 | 0 |  |  |  |  | Bartal, Nick | Bassani, Joel D. |  |  | 1 | 35696 |  | Kabaria, Erika | Independent | Aqua | 2020-01-03
XX761NBEP126A Exposure Remediation | Item | Candidate | MCAP |  | Project Framework |  | Bevevino, Jared | ECS Pipeline Integrity | 2. Pending AFE |  | Exposure Remediation | 0 |  |  | 0 |  | 0 | Green | 1550000 |  | 1550000 | -1550000 | [8 empty] | 0 |  | 0 | No | Green |  |  |  |  | 2023-06-30 | [5 empty] | 0 |  |  | 0 | Green | [11 empty] | 2/2/23 - BMH Project deferred $1550000 reallocated to other exposures | 2023-02-02 |  |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | XX761NB - MO S/L TO COUNCIL BLUFFS |  |  | 0 |  |  |  |  | Hurley, Brian |  |  |  | 1 | 44556 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Int - Planned Exposures
XX761NBEP136 Exposure Remediation | Item | Open | MCAP | XX761NBM2203 | Project Framework | 1947079 | Bevevino, Jared | ECS Pipeline Integrity | 6. Operational | Defined | Exposure Remediation | -13086 |  |  | -13085.83 | -11218 | -1868 | Red |  |  |  | -13086 |  |  | 164000 | 1522000 |  | 1686000 | Full | 1686000 | 1194307 |  | 1194307 | No | Green | 2022-02-01 | 2022-02-25 | 2022-02-25 | 2022-10-01 | 2022-12-31 |  |  | -9104.7 | -8348 | 6235.2 | -1868.33 |  |  | -1868 | Red | [11 empty] | 1/10/23 NV_ Additional mud disposal costs. 11/2/2022 NV- Variance due to more N2 needed than expected on purge. 10/11/2022 NAV- Contractor mobilized to site few days earlier than expected. 09-09-2022 Accrued to much in July, actuals now properly reflecting 9/6/2022 NAV- Variance due to $51K accrued last month that should have been $15K... transposition error on my part. NV 8/9/2022 NAV- Engineering ahead of schedule. Forecast adjusted due to contractor schedule recieved. 07-12-2022- Golder Engineering and permitting sped up in June. Will have final construction numbers on 07-20 03-09-2022 Spends flipped to this project from 42450 | 2023-01-10 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | XX761NB - MO S/L TO COUNCIL BLUFFS |  | -11218 | -1868 |  |  | 1207393 |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 41165 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Accel Exposures
XX761NBEP149 Exposure Remediation | Item | Candidate | MCAP |  | Project Framework |  | Bevevino, Jared | ECS Pipeline Integrity | 2. Pending AFE |  | Exposure Remediation | 0 |  |  | 0 |  | 0 | Green | 1550000 |  | 1550000 | -1550000 | [8 empty] | 0 |  | 0 | No | Green |  |  |  |  | 2023-06-30 | [5 empty] | 0 |  |  | 0 | Green | [11 empty] | 2/2/23 - BMH Project deferred $1550000 reallocated to other exposures | 2023-02-02 |  |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | XX761NB - MO S/L TO COUNCIL BLUFFS |  |  | 0 |  |  |  |  | Hurley, Brian |  |  |  | 1 | 44558 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Int - Planned Exposures
XX761NBEP163 Exposure Remediation | Item | Open | MCAP | XX761NBM2204 | Project Framework | 1947081 | Bevevino, Jared | ECS Pipeline Integrity | 6. Operational | Defined | Exposure Remediation | -1694 |  |  | -1693.99 | 420 | -2114 | Red |  |  |  | -1694 |  |  | 136000 | 1608000 |  | 1744000 | Full | 1744000 | 1369078 |  | 1369078 | No | Green | 2022-02-01 | 2022-02-25 | 2022-02-25 | 2022-10-01 | 2022-12-31 |  |  | -36574.01 | -4623.13 | 41617.28 | -2114.13 |  |  | -2114 | Red | [11 empty] | 4/11/23 NV- Unexpected reclass for $27K hit in March. 1/10/23 NV- Accrual error in November. 12/9/22 NV- UPI change order more than expected. 11/9/2022 NV- Purge assistance less than expected. 10/4/2022 NAV- Drilling contractor delayed, spend pushed through next month. 09/8/22 -Project changed from Open cut to HDD. Engineer has to remob for geotech and survey 8/22 NAV- Forecast adjusted given contractor updated schedule. 07-12-2022 Adjusted Forecast to accommodate change from open cut to HDD 03-09-2022 spends flipped from 42450 to this project | 2023-04-11 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | XX761NB - MO S/L TO COUNCIL BLUFFS |  | 420 | -2114 |  |  | 1370772 |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 41162 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Planned Exposures
XX761NBEP166D Exposure Repair 2022 | Item | Open | MCAP | XX761NBM2205 | Project Framework | 1947083 | Bevevino, Jared | ECS Pipeline Integrity | 6. Operational | Defined | Exposure Remediation | -17071 | 75000 |  | 57929.49 | 56692 | 1238 | Yellow |  |  |  | 57929 |  |  | 182000 | 1790000 |  | 1972000 | Full | 1972000 | 1209760 | 75000 | 1284760 | No | Green | 2022-02-01 | 2022-02-25 | 2022-02-25 | 2022-10-01 | 2023-04-30 |  |  | -8747.02 | -4291.39 | -5269.68 | 1237.58 | 0 | 0 | 1238 | Red |  |  |  | 75000 | [7 empty] | 12/9/2022 NV- Road tar work delayed until next year for weather. 11/9/2022 NV- UPI downtime less than expected. 10/4/2022 NAV- Drilling contractor delayed, spend pushed through next month. 09-08-2022 UPI did not mobilize until 08-31. Were supposed to mobilize 3 days earlier. 8/9/22 NAV- Engineering ahead of schedule. Forecast adjusted given updated schedule. 03-09-2022 spends flipped from OPPM ID 42450 to this project | 2022-12-09 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | XX761NB - MO S/L TO COUNCIL BLUFFS |  | -18308 | 76238 |  |  | 1226830 |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 37618 |  | Guest, ProSight | Independent | Aqua | 2020-08-11 | Int - Planned Exposures
XX762UC Spans-Exposures Captial Upgrade Engineering | Item | Open | MCAP | XX762UCM2201 | Project Framework | 1971061 | Taylor, Ryan | ECS Pipeline Integrity | 6. Operational | Defined | Exposure Remediation | 1336 |  |  | 1335.74 | 1336 | 0 | Green |  |  |  | 1336 |  |  | 357000 |  |  | 357000 | Phase | 357000 | 36487 |  | 36487 | No | Green | 2022-12-01 | 2022-04-12 | 2022-04-12 | 2022-04-01 | 2022-04-01 |  |  | 1335.74 | [18 empty] | 1.10.23 NV- Final assessment calls hit. | 2023-01-10 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | XX762UC - MO S/L TO CRESTON STATION |  | 1336 | 0 |  |  | 35151 |  | Hurley, Brian | Guenther, Steve |  |  | 1 | 43106 |  | Meitzler, Antoinette | Independent | Aqua | 2022-03-04 | Int - Accel Exposures
ZG701JC - Cutouts | Item | Open | MCAP | DP701NSM2201 | Project Framework | 1945865 | Taylor, Ryan | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Digs | 113896 | 3150000 |  | 3263895.96 | 3182272 | 81624 | Yellow | 1400000 |  | 1400000 | 1863896 |  |  | 54000 |  |  | 54000 | Phase | 54000 | 161216 | 3150000 | 3311216 | No | Green | 2022-03-01 | 2022-02-04 | 2022-02-04 | 2022-07-01 | 2023-10-01 |  |  | 12014.06 | 4028.81 | 16229.55 | 81623.54 |  |  | 81624 | Red |  | Forecasting |  |  | 1500000 | 1600000 | 50000 |  |  |  |  | 20230509- NV - $70K invoice hit earlier than expected. 20230405 - RJT- Material arrived early. 1/24/2023 RT-Forecast adjusted to project start. Also increased forecast to reflect known estimates. 1/16/2023 RT-Project construction will begin in Q2 (July-Aug). 12/2/2022 NAV- Ryan Taylor has taken over this project and design work will begin in January 2023. 9/9/2022 NAV- Forecast updated for permitting costs in Oct/Nov 8/30/2022 - JK. Project pushed to Q1 2023 8/5/2022- Variance due to Kiely purge planning being pushed into August (did not occur in July). NV 8.5.22.DLC: Reduced by $452k to cover UB760AREP250A... 7/12/2022- Kiely began purge planning ahead of schedule. 5.25.22.DLC: allocated funds from advanced strategy line to this one for additional cutouts 3/4/2022 - The scope for this project being evaluated to include any B sleeves that may need to be cutout. | 2023-05-09 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Macungie Pipe | DP701NS - DUPONT TO NICHOLSON-16IN |  | 32272 | 81624 | 3150000 |  | 47320 |  | Bartal, Nick | Guenther, Steve |  |  | 1 | 40728 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Accel Cutouts
ZG714RG_RT-73_Criteria Cutout | Item | Open | MCAP | ZG714RGM2203 | Maintenance Framework | 1954930 | Taylor, Ryan | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | 14733 |  |  | 14733.11 | 26733 | -12000 | Red |  |  |  | 14733 |  |  | 538000 |  |  | 538000 | Full | 538000 | 439958 |  | 439958 | No | Green | 2022-05-01 | 2022-10-12 | 2022-10-12 | 2022-12-30 | 2022-12-31 |  |  | 13750.59 | 522.52 | 460 |  | 12000 | 12000 | -12000 | Red | [11 empty] | 1/10/22 NV- Misc close out costs. 12/9/22 NV- Work complete in conjunction with 714 cutout project, contractor costs hit other project. Forecast was locked after decsion made. 10/10/22 RT - Project was pushed back several times due to permitting and scheduling. During last months update, it was not reflected latest schedule delay. Work to start Oct. and end Nov. 9/9/22 NAV- Project work to start/complete in September, Purge to take place in October, forecast adjusted to reflect. 7.12.22 NAV- Project pushed back to October due to scheduling. 6.9.22 NAV- Permitting invoice came in, was unsure of when this would take place. 5.25.22.DLC: allocated from L714 OPPM record and cancelled other recordHOP submitted to PennDot. Will not be able to fully scope project until feedback is received from PennDot on road closure and crossing. | 2023-01-10 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Macungie Pipe | ZG714RG - MACUNGIE TO TUCKERTON |  | 14733 | 0 |  |  | 425224 |  | Bartal, Nick | Guenther, Steve |  |  | 1 | 43011 |  | Meitzler, Antoinette | Independent | Aqua | 2022-02-18 | Int - Planned Cutouts
ZG714SN 2022 NDT UCD ILI IMMEDIATE DIGS | Item | Open | MCAP | ZG714RGM2204 | Maintenance Framework | 2044376 | Taylor, Ryan | ECS Pipeline Integrity | 3. Active | Defined | Pipeline Digs | 1432175 | 50000 |  | 1482175.35 | 1467909 | 14266 | Yellow |  |  |  | 1482175 |  |  | 1970000 |  |  | 1970000 | Full | 1970000 | 1988189 | 50000 | 2038189 | No | Green | 2022-11-01 | 2023-01-10 | 2023-01-10 | 2022-12-31 | 2023-05-31 |  |  | 684779.61 | 24675.49 | 383453.82 | 339266.43 | 365000 | 365000 | -25734 | Yellow |  | Other | 50000 | [8 empty] | 5/9/2023 - April variance due to site conditions and encountering rock. Resulted in delay. Reduced forecast to reflect last remaining dig being completed. 5.8.23 - Reduced May forecast from $60,000 to $55,000 due to $5,000 MEXP Flip to ZG714RGE2303 (AS) 4/5/23 - RJT Variance due to weather and site access. 2/3/23 - Nick Bartal submitting accrual for $11,125 (AS) 12/9/22 NV- TBD combining both ZG714SN projects. 12/9/22 NEB - reforecast Nov variance, digs still in process | 2023-05-09 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Macungie Pipe | ZG714RG - MACUNGIE TO TUCKERTON |  | 1092909 | 389266 |  |  | 556014 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46165 |  | Guest, ProSight | Independent | Aqua | 2022-11-06 | Int- Planned Digs
ZG714ZN - Cutouts | Item | Open | MCAP | ZG714RGM2201 | Project Framework | 1945866 | Taylor, Ryan | ECS Pipeline Integrity | 6. Operational | Defined | Pipeline Digs | 235419 |  |  | 235419 | 210917 | 24502 | Red |  |  |  | 235419 |  |  | 50000 | 1319000 |  | 1369000 | Full | 1369000 | 1367477 |  | 1367477 | No | Green | 2022-03-01 | 2022-02-04 | 2022-02-04 | 2022-07-01 | 2022-12-31 |  |  | 86318.44 | 246871.35 | -147273.04 | 49502.25 | 25000 | 25000 | 24502 | Red | [11 empty] | 20230309 NV- Negative forecast for March to reflect over accrual that took place in February. 2/2/23 Trailing invoices12/9/22 NV- Project coming to a close, remaining spend will be minimal. 11/2/2022 NAV- Variance due to contractor costs coming in at half of what was anticipated. Forecast adjusted/increased for November/December due to scheduling pushed back. 10/10/2022 NAV- Progress on the purge delayed. Forecast has been updated to reflect. 8.5.22.DLC: Reduced by $472k to cover UB760AREP250A... 7/12/2022- Kiely has began purge planning, but not moving forward as quickly as expected. 5.25.22.DLC: allocated funds from advanced strategy line to this one for additional cutouts 3/4/2022 - The scope for this project being evaluated to include any B sleeves that may need to be cutout. | 2023-03-10 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Macungie Pipe | ZG714RG - MACUNGIE TO TUCKERTON |  | 185917 | 49502 |  |  | 1132058 |  | Bartal, Nick | Guenther, Steve |  |  | 1 | 40729 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Accel Cutouts
ZI165CM Historic Cutouts 2022 | Item | Open | MCAP | ZI165CMM2201 | Project Framework | 1981438 | Oldham, David | ECS Pipeline Integrity | 6. Operational | Drawdown | Pipeline Digs | 9950 |  |  | 9950.11 | 9635 | 315 | Yellow |  |  |  | 9950 |  |  | 123000 | 1872000 |  | 1995000 | Full | 1995000 | 1574588 |  | 1574588 | No | Green | 2022-06-01 | 2022-05-23 | 2022-05-23 | 2022-08-19 | 2022-08-19 |  |  | 1917.11 | 718 | 7000 | 315 |  |  | 315 | Red | [11 empty] | 10/10/22: dwo - completed work early. 9/6/22: dwo - cutouts and site restoration completed. ~$56k variance from completing work early. 7/29/22: dwo - Positive variance due to one week delay in mobilization due to elimination of one cutout location. 7/11/22: dwo - CONTRACTOR awarded. Two crews to begin work 7/18 in preparation for outage the week of 8/15. 6/6/22: Added $1.46 million to forecast (from CN165ZI2202, OPPM ID 43339) as placeholder for ~8 cutouts. Scope to be finalized and contractor quotes provided in June. Construction to follow 211 Line cutouts anticipated to be after July 4th. | 2022-10-10 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity |  | Indianapolis | ZI165CM - ZIONSVILLE TO CARMEL |  | 9635 | 315 |  |  | 1564638 |  | Bartal, Nick | Guenther, Steve |  |  | 1 | 43814 |  | Meitzler, Antoinette | Independent | Aqua | 2022-05-20 | Int - Accel Cutouts
ZN701ABEP303060 2022 Exposure Remediation | Item | Open | MCAP | ZN701ABM2101 | Project Framework | 1909916 | Taylor, Ryan | ECS Pipeline Integrity | 3. Active | Defined | Exposure Remediation | 161336 | 2200000 |  | 2361335.86 | 2354497 | 6839 | Yellow | 2100000 |  | 2100000 | 261336 |  |  | 196000 |  |  | 196000 | Phase | 196000 | 307723 | 2200000 | 2507723 | No | Green | 2021-12-01 | 2022-02-16 | 2022-02-16 | 2021-12-31 | 2023-09-30 |  |  | 6039.67 | 2740.9 | 105716.15 | 46839.14 | 40000 | 40000 | 6839 | Red |  |  | 600000 | 1500000 | 100000 | [6 empty] | 4/5/2023 RJT - Variance due to material arriving a week early. 3/9/2023 RJT - Updated Construction start and associated spends 10/11/22 NAV- Final Golder invoice came in under amount that had been accrued. 08-24-2022 Forecast pushed to 2023 8/9/22 NAV- Engineering ahead of schedule. 12-08-21 Preliminary Engineering and assessment submittal in December | 2023-04-05 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Auburn Pipeline | ZN701AB - MAINE TO AUBURN-14IN |  | 114497 | 2146839 | 100000 |  | 138387 |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 42446 |  | Meitzler, Antoinette | Independent | Aqua | 2021-11-15 | Int - Accel Exposures
ZT820ICEP62120 Exposure Remediation | Item | Open | MCAP | ZT820ICM2201 | Project Framework | 1954858 | Bevevino, Jared | ECS Pipeline Integrity | 6. Operational | Defined | Exposure Remediation | 4994 |  |  | 4993.54 | 4994 | 0 | Green |  |  |  | 4994 |  |  | 60000 | 312000 |  | 372000 | Full | 372000 | 333829 |  | 333829 | No | Green | 2022-03-01 | 2022-03-02 | 2022-03-02 | 2022-10-01 | 2022-10-01 |  |  | 4810.73 | 182.81 | [17 empty] | 09-08-2022 Inspector costs for all instream coded to this project. Will have to relcass 07-19-2022 Contractor bid came in higher than expected. Forecast adjusted up 100k | 2022-09-08 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | Coraopolis | ZT820IC - MIDLAND TANK TO CORAOPOLIS JCT |  | 4994 | 0 |  |  | 328836 |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 42534 |  | Clark, David | Independent | Aqua | 2021-12-02 | Int - Accel Exposures
Bayonne Dock Mooring Upgrade Phase II | Item | Closed | MCAP | BBTQY00M1806 | Exempt | 1472977 | Fetchko, Mark | ECS Pipes and Terminals | 7. Closed | Emergent | Marine | 243 |  |  | 243.12 | 243 | 0 | Green |  |  |  | 243 |  |  | 1274000 |  | 1110000 | 2384000 | Supplemental | 2384000 | 2109922 |  | 2109922 | No | Green | 2022-11-01 | 2018-06-11 | 2018-06-11 | 2019-07-01 | 2019-07-01 |  |  | 243.12 | [18 empty] | 9/4/2020: EC- Marked ready to close. Work continues on Phase III BU. 9/5/19 DNM No additional updates 8/4/19 DNM- Fabrication complete and in storage. Awaiting release to ship. 7/3/19 DNM Material storage cost finalized. Working on shipping plan for 2020. 6/4/19 DNM- Aligning material storage at TTI until needed in construction phase. TexMarine provide delivery/testing schedule on fender from this month. 5/3/19 DNM Scheduling fender testing 4/3/19 DNM- TexMar fender system in transit 1/5/19 DNM- Fenders on order. Finalizing plans for project transition to Mark Fetchko for execution 12/4/18 DNM- Fabrication at 80% 11/4/18 DNM-Fender systems out for bid. Contracting pile extensions to improve installation plan along with catwalks and decks. 10/2/18 DNM Design of catwalks complete. Pile and walks under fabrication 9/6/19 DNM TTI has processed materials for receipt. Fabrication underway 8/1/18 DNM Material acquisition and fabrication underway. Working on catwalk and fender acquisition. | 2020-09-04 | Chabot, Emily |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor North Terminals | BBTQY - BBT BAYONNE TERMINAL | BBTQY00M1700 | 243 | 0 |  |  | 174760 |  | Spari, Markella | Votta, Joseph T. |  |  | 1 | 29056 |  | Kabaria, Erika | Child (Major Project) | Olive | 2018-05-22 | Other Programs
Bayonne Refurb Barge dock substructures | Item | Open | MCAP | BBTQY00M2201 | Maintenance Framework | 1938776 | Petry, Gregory | ECS Pipes and Terminals | 1. Proposed | Defined | Marine | 172 | 1200000 |  | 1200171.67 | 1200102 | 69 | Yellow | 1200000 |  | 1200000 | 172 |  |  | 32000 | 314000 |  | 32000 | Phase | 346000 | 14594 | 1200000 | 1214594 | No | Green | 2022-02-01 | 2022-01-20 | 2022-01-20 | 2024-08-30 | 2024-08-30 |  |  |  | 33.79 | 68.55 | 69.33 |  |  | 69 | Red |  |  |  | 100000 | 100000 | 300000 | 300000 | 300000 | 100000 |  |  | 3/17/23: Bowman Consulting; Engineering Firm. 3/8/23 PC: AFE to be submitted, forecasts base on that. 11.9.22 TN - Forecast for December removed 9.30.22 SDB: Discussions ongoing to decide which structures are critical and should need to be repaired first. Upgrades to be completed in 2023. 9.16.22 SDB: Received revised proposal from Anchor Consultants. 9.9.22:MKS 2022 Forecast for AFE level funding sourced from outside of marine portfolio. 2023 forecast (1.7M) was for upgrades in South and North loading platform and turning dolphin. 9.2.22 SDB: AFE was removed from the workflow. Working on another path forward with this project. 8.19.22 SDB: AFE in the system to fund the engineering and bid package. 8.10.22.DLC: put December to $250k for engineering only in 2022.. 7.29.22.DLC: Removed $240k, left enough for permitting and engineering for 2022. Balanced in 2023 7.8.22 SDB: Structural Inspections have not been completed by Anchor Consultants in order to determine SOW for repairs. 5.31.22 SDB: Structural inspections are being conducted at the present time and the report is expected to be received in early June. 5.2.22 SDB: Structural Inspection to be completed in May in order to determine SOW. 3.31.22 SDB: Detailed inspection to be completed by early April to determine extent of required repairs to be made at the dock facility. 2.18.22.DLC: Performing secondary inspection to validate some gaps on prior inspections. | 2023-03-17 | Carter, Paige |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor North Terminals | BBTQY - BBT BAYONNE TERMINAL |  | 102 | 100069 | 700000 | 400000 | 14422 |  | Spari, Markella | Martin, David N. |  |  | 1 | 41531 |  | Administrator, System | Independent | Aqua | 2021-08-19 | Marine
BETQT - Tampa North Dredging 2022 | Item | Open | MCAP | BETQT00M2201 | Maintenance Framework | 1957333 | Denblanken, Stefan | ECS Pipes and Terminals | 7. Closed | Unplanned | Marine | 4906 |  | 2211 | 4905.78 | 4906 | 0 | Green |  |  |  | 4906 |  |  | 122000 |  |  | 122000 | Full | 122000 | 93362 | 2211 | 95573 | No | Green | 2022-03-01 | 2022-03-28 | 2022-03-28 | 2022-04-10 | 2022-04-10 |  |  |  | 4694.53 | 211.25 | [15 empty] | 2211 | 10/11/22 - Cost savings, accrual dropped as previously posted costs were less than quoted by Army Corp. DC 05.02.22 SDB: Terminal is Operational. 03.31.22 SDB: AFE and PO produced. Payment was made to the Tampa Port Authority. | 2022-10-18 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Florida | BETQT - BET TAMPA NORTH TERMINAL |  | 4906 | 0 |  |  | 88457 |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 43184 |  | Meitzler, Antoinette | Independent | Aqua | 2022-03-16 | Marine
Bronx Remove Mooring Cells | Item | Candidate | MEXP |  | Project Framework |  | Denblanken, Stefan | ECS Pipes and Terminals | 8. Canceled | Defined | Marine |  | 1 |  | 1 | 1 | 0 | Green |  |  |  | 1 | [9 empty] | 1 | 1 | No | Green | 2023-12-01 |  |  |  | 2023-02-28 | [19 empty] | 1 |  | 3.3.23 TN/DLC - Project will be re-entered in the future as needed 10.5.22 SDB: LEI is producing the draft of the document to request an extension for the DEC permit. 8/2/22: MKS: 626K Funding from this project was reallocated within marine program to fund emergent projects. 8.1.22 SDB: Obtaining Budget proposals for demolition costs. 7.8.22 SDB: Received an extension by USACOE permitting us to delay demolition of the cells. Project is deferred. 5.31.22 SDB: Lloyd Engineering requested an extension of the USACE permit in order to avoid removing the cells in 2022. Presently waiting for the reply. 5.2.22 SDB: Discussing path forward with work. Lloyd Engineering working on different options to provide adequate berthing for vessels. Working to modify permit in order to demolish cells at a later date. 4.20.22 SDB: Project assigned to Sdenblanken. 4/10/2021 DNM- Obtaining quote from contractor for phased cell removal. 10/25/2021 DNM- Project carries over the Marine MEXP 2022 Phase 1 for first cell removal in Q4 2022. Phase 2 will be part of Marine MEXP 2023 for completion in Q1 2023 to avoid double mobilization/demobilization costs from contractor. | 2023-03-03 | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor North Terminals | BETQX - BET BRONX TERMINAL |  |  | 0 |  | 1 |  |  | Spari, Markella |  | N/A |  | 1 | 30918 |  | Meitzler, Antoinette | Independent | Aqua | 2018-08-27 | Marine
BTXHF - VRU 3 Train B Carbon Replacement - 2022 | Item | Open | MCAP | BTXHF00M2217 | Maintenance Framework | 2037456 | Dalton, James | ECS Pipes and Terminals | 6. Operational | Unplanned | Vapor Management | 528791 |  |  | 528790.92 | 521041 | 7750 | Yellow | 120000 |  | 120000 | 408791 |  |  | 656000 |  |  | 656000 | Full | 656000 | 562591 |  | 562591 | No | Green | 2022-12-01 | 2022-12-21 | 2022-12-21 | 2022-11-01 | 2023-02-28 |  |  | 4284.4 | 165813.21 | 335943.67 | 22749.64 | 15000 | 15000 | 7750 | Red | [11 empty] | 4.4.23 Ml Project is complete pending Carbon testing and follow up visit from Vapercom. 11.8.22 Delay Reclass due to John Zink not invoicing RCL to take place in December. 10/19/2022 AJ: Name needs to be changed to trane A. Interim for Carbon reclass to be filed by 10/21. Full afe will be submitted early Nov. 10/3/22 AJ : Adjusted forecast to handle reclasses from VRU C ("A")of Carbon and delivery in Nov. Total project will be 540k ish but unable to adjust next year's carry over forecast. Prior to this adjustment there was 700k in this years forecast. 9/12/2022 - Project deferred to 2023 | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 506041 | 22750 |  |  | 33800 |  | Karl, Marissa | Pappas, John |  |  | 1 | 44050 |  | Guest, ProSight | Independent | Aqua | 2022-06-29 | Other Programs
Chesapeake - Tank 5605 Return to 6 Oil Service | Item | Open | MCAP | BETQC00M2003 | Exempt | 1704254 | Petry, Gregory | ECS Pipes and Terminals | 6. Operational | Unplanned | Tanks | 4264 |  |  | 4263.6 | 4080 | 184 | Yellow |  |  |  | 4264 |  | Scope Increase | 652000 |  |  | 652000 | Full | 652000 | 334041 |  | 334041 | No | Green | 2020-04-01 | 2020-06-03 | 2020-06-03 | 2020-07-06 | 2022-07-02 |  |  |  |  | 4080 | 183.6 |  |  | 184 | Red | [11 empty] | 3/17/23: Align invoice processing, then good to close. 3/3/2023-PC: Final billing from Align being invoiced ASAP. Working toward project closeout. Not expecting to spend remaining 329k. 1/25/23-CES-This tank is being left idle. I believe the April forecast is incorrect based on latest project discussions. This may be a duplicate entry. Deleting forecast. 3/22/22 The new fire pump and green foam are on site. The foam proportioner arrives this week. The city water system upgrade will be 3 years out, so they are allowing us to move forward with final design of our connections in the street. Expect final design of fire system about 2 months. Construction this summer 2022. 09/24/2021 - RTC changed to Yes M Crandall May 28 - Tank 5605 ready to receive #6 oil. Arrival of ship slipped from 5/28, to 5/31, to 6/2. May 21 - replaced rupture disk and assembly. Verified operation of 2 check valves. April 29 - dock lines, dock hoses, candy canes all pressure tested. April 15, 2020 - steam coils in tank pressure tested. | 2023-05-02 | Carter, Paige |  | East | Pipelines and Terminals | Integrity |  | Virginia | BETQC - BET CHESAPEAKE TERMINAL |  | 4080 | 184 |  |  | 1459 |  | Stine, Carlton | Clay, Chris |  |  | 1 | 36582 |  | Kabaria, Erika | Independent |  | 2020-04-15 | Int - Tanks
Dock Program 3rd Party Support | Item | Open | MEXP | 1348200E1601 | Exempt | 1239313 | Martin, Dave | ECS Pipes and Terminals | 7. Closed | Defined | Marine | 11 |  |  | 11.12 | 11 | 0 | Green |  |  |  | 11 |  |  | 75000 |  |  | 75000 | Full | 75000 | 63824 |  | 63824 | No | Green | 2023-03-01 | 2016-08-26 | 2016-08-26 | 2016-12-31 | 2016-12-31 |  |  |  |  | 11.12 | [18 empty] | Meitzler, Antoinette |  | Corporate | Corporate | Station/Terminal |  | Corporate | Corporate |  | 11 | 0 |  |  |  |  | Spari, Markella | Pepe, David J. |  |  | 1 | 16343 |  | Guest, ProSight | Independent | Aqua | 2015-09-09
Forbes Rack Line Repair | Item | Open | MEXP | BNTNF00E2207 | Maintenance Framework | 2045810 | Manchester, Justin | ECS Pipes and Terminals | 6. Operational | Emergent | Truck Racks | 74248 |  |  | 74248.25 | 74248 | 0 | Green |  |  |  | 74248 |  |  | 90000 |  |  | 90000 | Full | 90000 | 74248 |  | 74248 | No | Green | 2023-01-01 | 2022-11-23 | 2022-11-23 | 2022-12-31 | 2022-12-31 |  |  | 69815 | 4433.25 | [17 empty] | 2/10/23 NV: Trailing invoice | 2023-02-10 | Williams, Nikole |  | East | Pipelines and Terminals | Station/Terminal |  | New Haven Harbor | BNTNF - New Haven Forbes Termina |  | 74248 | 0 |  |  |  |  | Younce, Michael | Orischak, Bob |  |  | 1 | 46230 |  | Meitzler, Antoinette | Independent | Aqua | 2022-11-15 | Other Programs
Ft. Lauderdale (BETQD) Dock Line Relocation - 2020 | Item | Open | MCAP | BETQD00M2001 | Exempt | 1674241 | Martin, Dave | ECS Pipes and Terminals | 3. Active | Defined | Marine | 109185 | 250000 |  | 359184.57 | 360550 | -1366 | Yellow |  |  |  | 359185 |  |  | 72000 | 260000 |  | 332000 | Phase | 332000 | 896265 | 250000 | 1146265 | No | Green | 2020-02-01 | 2020-01-26 | 2020-01-26 | 2022-07-01 | 2023-07-20 |  |  | 3440.36 | 3522.59 | 3587.53 | 98634.09 | 100000 | 100000 | -1366 | Yellow |  |  | 0 | 80000 | 0 |  |  | 120000 | 50000 |  |  | 05/02/2023 DNM- Gonzalez mobilized to site. Work schedule will be slow due to multiple company's scope being undertaken. 04/05/2023 DNM-Installation contract to Gonzalez and Sons for line relocation work issued. Contractor mobilzing to site. Work will be in 2 parts based on Port Everglades scheduling requirements. Phase 1 in Q2 and Phase 2 in Q4.. Forecast adjusted to reflect new schedule. 03/02/2023 DNM- Contract for line relocation awarded to Gonzalez and Sons. Work to begin in April. Coordination in March for delivery of materials to site along with general site improvements by the Port Everglades. 02/03/2023 DNM- Project Time line shifts to late Q2/early Q3 completion.Shah Drotos unable to complete single contractor installation plan. Chevron/Motiva requesting Attaway as GC, CITGO/TransMontaigne requesting Gonzalez. Negotiation underway to determine single versus dual contractor execution of SFPS Manifold Piping Relocation Project in which Buckeye has one of the thirty-nine lines being relocated. Buckeye will execute an installation PO with either contractor dependent on most advantageous timing for FLL Line Relocation. 1/4/2023 DNM-Awaiting Shah Drotos to execute field construction contract. 12/05/2022 DNM- Project start in 2023 once Shah Drotos completed contracting review and award notification. 11/2/2022 DNM- Installation will not start until Q1 2023 based on contracting delays. Shah Drotos is still trying to the Terminal Consortium to accept a single contractor. See note from 10/4/22 for November/December removal and transferred to BETQJ00M2203. 10/4/2022 DNM- Shah Drotos prepared to award overall Industry Constorium project to low bidder. Buckeye will contract the low bidder for installation of the one Buckeye line. Work is anticipated to begin in Q1 2023. Project spend for Q4 will be realigned to other marine project to avoid caryover. Plan is to advance BETQJ Jacksonville fabrication into Q4, thus reducing funding needs in 2023 that will be used to fund Ft Lauderdale. Forecasting to be updated once Cy+1 is unlocked. 09/06/2022 DNM- Contractor Bids due 9/9/2022. Project spend will be shifted after bid review. Anticipated 2023 carryover to be offset by advancing BETQJ East Dolphin Fabrication into Q4 2022. 08/02/22 DNM- Contractor Bid Submission Date extended by Shah/Drotos 7/6/22 DNM- Project Bidsbeing received in July. 06/02/22 DNM-Project out for bid. Spend plan shifted based on anticipated contracting date in August. 05/03/2022 DNM-Shah Drotos release of bid package delayed. Pt Everglades is adjusting project start and completion date into 2023. Forecast spend adjusted to reflect shifting schedule. 04/02/22 DNM- Shah Drotos processing bid package for Fuel Company Consortium to review prior to issuance. Project forecast will be realigned in April based on delays on Bid Package processing outside the control of Buckeye. 02/03/22 DNM- Awaiting contractor installation bids to access final funding requirements. Shah Drotos awaiting bid receipt. 12/2/21 DNM- Materials for line relocation on site. Awaiting bid package processby Shah Drotos. 11/2/2021 DNM-Relocation pipe and fittings shipped to Tampa Complex for storage. Shah Drotos has been granted an extension on bid issuance until January 2022 to incorporate aterminal to terminal transfer manifold into design. Anticipated award of piping field construction contract for April 2022. 10/3/2021 DNM- Pipe, Valves and Fittings to be ordered in October. Anticipate General Contractor Bid Review and Contract award in January 2022. 09/02/2021 DNM- Bid package now delayed issuance in the end of October based on CITGO delay for review of consortium package. Plan is to purchase materials in October/November for Contractor installation in 2022 following contract issuance. 07/06/2021 DNM-Shah Drotos bid package delayed by Fuel Terminal Consortium contracting as CITGO failed to contract their portion of the design work until 7/2/21. Anticipated bid package issuance date is 8/10/21. Installation contractor estimated contract date is now 10/1/21. 04/05/2021 DNM Project Implementation Plan awaiting move forward approval between ShahDrotos and Pt Everglades Administration. 03/03/2021 DNM ShahDrotos working. Minor mechanical staged 02/03/2021 DNM- Shah Drotos working on manifold design outside SPFS manifold. Tentative schedule for line relocation package is late April. 01/06/2021 DNM- Shah Drotos advancing bid package. Spend plan for 2021 will be evaluated once bids are received. 12/3/2020 DNM Project layout being reviewed on 12/8/2020 with Shah Drotos. 11/4/2020- Working with design company on layout and contracting plan. 9/30/2020 - Supplemental funding has been approved! PO has been issued to Engineering Firm. Kickoff meeting is scheduled for 10/2. 8/26/2020 District to submit a supplemental AFE later this year. 8/1/2020 - We have positioned our pipeline in the final manifolddesign. This project is still waiting funding for full engineering design of our pipeline. 6/29/2020 - Final Design quotes have come in. The amount is substantially greater than what was budgeted for this year. Supplemental funding will be needed to continue this project. 6/1/2020 - Engineering has begun preliminary screening of contractors. We are still waiting for SFPS to revise themanifold design per the industries comments. 5/4/2020 - We are waiting for SFPS to revise the manifold design per the industries comments. Workingon completing our final SOW for detailed design on our specific pipeline with the engineering company. 3/31/2020 - Engineering has sent a response to SFPS "master plan" for all companies manifold connection. Final design of our SOW willfollow once the Manifold design is set. 3/3/2020 - We have acquired engineering support to help guide the project in alignment with the rest of the industry in the port. 2/3/2020 - Submitted supplemental AFE on 1/10/2019. Held internal scope discussion. Working with a third party engineering firm to submit our scope to SFPS. The new required construction dates are July 2021-July 2022. 1/2/2020 -The new pipe manifold that Buckeye's Pipe needs to tie into is scheduled to be complete by May 2021. Buckeye will then have from May 2021-Aug 2022 to complete the tie in. Currently, scope development is on going. | 2023-05-02 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Florida | BETQD - BET FORT LAUDERDALE TERMINAL |  | 10550 | 178634 | 0 | 170000 | 153036 |  | Spari, Markella | Miller, Michael A. |  |  | 1 | 35172 |  | Administrator, System | Independent | Aqua | 2019-09-17 | Marine
Groton P&ID and tagging updates | Item | Open | MEXP | BETQG00E2203 | Maintenance Framework | 2013129 | Manchester, Justin | ECS Pipes and Terminals | 6. Operational | Drawdown | East | -19704 |  |  | -19704.16 | 299 | -20003 | Red |  |  |  | -19704 |  |  | 101000 |  |  | 101000 | Full | 101000 | 66896 |  | 66896 | No | Green | 2022-09-01 | 2022-08-23 | 2022-08-23 | 2022-12-31 | 2022-12-23 |  |  | 298.89 | 0 | 0 | -20003.05 |  |  | -20003 | Red | [11 empty] | 12/8/22 NV: Lagging invoices | 2022-12-08 | Williams, Nikole |  | East | Pipelines and Terminals | Station/Terminal |  | Jet Lines | BETQG - BET GROTON TERMINAL |  | 299 | -20003 |  |  | 86600 |  | Orischak, Bob | Wing, Stephen W. |  |  | 1 | 44635 |  | Clark, David | Independent | Aqua | 2022-08-16 | Other Programs
Hamilton Commons Construction Buckeye | Item | Open | MCAP | 1348821M2003 | Exempt | 1775547 | Tulio, Timothy | ECS Pipes and Terminals | 6. Operational | Defined | Hamilton Commons | 34834 | 170000 |  | 204833.67 | 204834 | 0 | Green |  |  |  | 204834 |  |  | 1987000 |  |  | 1987000 | Full | 1987000 | 584579 | 170000 | 754579 | No | Green | 2021-04-01 | 2020-11-05 | 2020-11-05 | 2021-11-01 | 2021-10-01 |  |  |  | 22663.48 | 12170.19 | [8 empty] | 70000 | 100000 | [6 empty] | 3/17/23: Library door reader addition, artwork projected costs. 3/1/23- Adding Cell phone antennas 1/11/23 NV- $100K forecasted for June '23 for artwork purchase & installation. Per GP -the Wood Lot modifications did not start until November 4, this work was delayed by Township final approval. 3/8/22 - Previously requested from contractor cash flow forecast, and final billing forecast. Billing finally received. | 2023-04-03 | Carter, Paige |  | Corporate | Corporate | Corporate | Corporate | Corporate | Corporate | 1348821M2000 | 34834 | 70000 | 100000 |  | 341308 |  | Kunow, Ashley | Malecky, Robert A. |  |  | 1 | 38813 |  | Meitzler, Antoinette | Child (Major Project) | Olive | 2020-10-19 | Office Relocation
Hamilton Commons Furniture | Item | Open | MCAP | 1348821M2004 | Exempt | 1775548 | Petry, Gregory | ECS Pipes and Terminals | 7. Closed | Defined | Hamilton Commons | 2254 |  |  | 2253.64 | 2254 | 0 | Green |  |  |  | 2254 |  |  | 2430000 |  |  | 2430000 | Full | 2430000 | 1545673 |  | 1545673 | No | Green | 2021-05-01 | 2020-11-05 | 2020-11-05 | 2021-11-01 | 2021-10-01 |  |  | 1094 | 1159.64 | [17 empty] | Per GP Furniture, added scope items are delayed, due to supply chain issues. 12/3- Bid event in progress, plan to place the Furniture order in April 2/3-Finalizing finish selections |  | Carter, Paige |  | Corporate | Corporate | Corporate | Corporate | Corporate | Corporate | 1348821M2000 | 2254 | 0 |  |  | 31839 |  | Kunow, Ashley | Malecky, Robert A. |  |  | 1 | 38815 |  | Meitzler, Antoinette | Child (Major Project) | Olive | 2020-10-19 | Office Relocation
Hydrographic & Side Scan Surveys MEXP 2021 | Item | Open | MEXP | 1348250E2145 | Exempt | 1810213 | Martin, Dave | ECS Pipes and Terminals | 6. Operational | Defined | Marine | 8500 |  |  | 8500 |  | 8500 | Red |  |  |  | 8500 |  |  | 125000 |  |  | 125000 | Full | 125000 | 124546 |  | 124546 | No | Green | 2021-03-01 | 2021-01-29 | 2021-01-29 | 2021-12-30 | 2021-12-31 | [5 empty] | 8500 |  |  | 8500 | Red | [11 empty] | 08/02/22 DNM-Tracking down final invoice processing to allow for close. 07/06/22 DNM- Invoice in OpenInvoice. Processing in July 06/02/22 DNM- Contractor to submit final invoice 2nd week of June. 05/03/2022 DNM- Contacted contractor with final request for invoice in May. 04/02/22 DNM- Still working to resolve Open Invoice 03/02/22 DNM- OpenInvoice issue to upload invoices. 02/03/22 DNM Contractor difficulty in uploading invoices. Working with AP 01/03/22 DNM Awaiting submission into OpenInvoice 12/2/21-DNM- Final scan in Tampa completed. Awaiting invoices 11/1/21 DNM- Final Side Scans in November/December 6/28/2021 DNM- Angela Mirandi is scheduling hydrographic survey and will update this project in the future. | 2022-08-02 | Walker, Carol |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  |  | 8500 |  |  | -1925 |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 37993 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Marine
INDIAN BRANCH EXPOSURE MP 69.27 | Item | Open | MCAP | IM760UGM1701 | Exempt | 1288203 | Rolando, Doug | ECS Pipes and Terminals | 8. Canceled | Drawdown | Exposure Remediation | -5000 |  |  | -5000 |  | -5000 | Red |  |  |  | -5000 |  |  | 5000 |  |  | 5000 | Full | 5000 | 0 |  | 0 | No | Green |  | 2017-01-03 | 2017-01-03 | 2018-12-30 | 2019-08-31 | [5 empty] | -5000 |  |  | -5000 | Red | [11 empty] | 3/7/18: Project did not receive 2018 funding. Will be re-evaluated for 2019. Initial Site Visit and due diligence completed in fall 2016. No work planned for 2017 due to budget constraints. Will re-evaluate project for 2018 funding both engineering and construction. | 2018-03-07 | Cheng, Debra |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | IM760UG - MILAN STA TO SUGAR CREEK TERM |  |  | -5000 |  |  |  |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 22348 |  | Kabaria, Erika | Independent | Aqua | 2017-01-03
Jacksonville Eastern Dolphin Replacement | Item | Open | MCAP | BETQJ00M2203 | Project Framework | 2002653 | Martin, Dave | ECS Pipes and Terminals | 3. Active | Defined | Marine | 725116 | 1500000 |  | 2225116.29 | 2210780 | 14337 | Yellow | 2700000 |  | 2700000 | -474884 |  |  | 57000 |  |  | 57000 | Phase | 57000 | 1448177 | 1500000 | 2948177 | No | Green | 2022-08-01 | 2022-07-11 | 2022-07-11 | 2022-12-31 | 2023-08-31 |  |  | 212522.75 | 113459.62 | 84797.24 | 314336.68 | 300000 | 300000 | 14337 | Yellow |  |  | 600000 | 500000 | 250000 | 150000 | [5 empty] | 05/02/2023 DNM- Mobilization of materials to Jacksonville completed. Kick of meeting for field installation completed. Anticipated start of construction is May 10th. 04/05/2023 DNM-Fabrication of dolphin completed and load out underway. Coordination meeting on April 5th with Operations for mobilization to site for field installation in May. 03/02/2023 DNM- Dolphin fabrication complete. Retainage held until loadout in April. Scheduling is coordinating with Customers for 4 day dock shutdown starting on May 8th for 6 weeks to install dolphin and demolish old dolphin. Installation contractor, Callan Marine finalizing contract. Mobilization to start in March. 02/03/2023 DNM- Fabrication of dolphin at 90%. Bid Event completed for installation. Award in progress to Callan Marine. Scheduling project execution review for 2/28/23. Anticipate start of field installation is mid-May. 01/04/2023 DNM- Fabrication of dolphin progressing. Installation bids due January 10th. Anticipate field construction in May. 12/4/22 DNM-Materials received for Dolphin Fabrication to begin December 5th. 11/02/2022 DNM- Fabrication of easterly dolphin underway by New Industrial in Morgan City. Q4 Spend forecast updated with funding diverted from BETQ Ft Lauderdale Project that is delayed into Q1 2023. Spend advance in offset by 2023 forecast reduction. 10/10/2022 DNM- Fabrication of replacement east dolphin awarded to New Industries. Material procurement is underway. Shop fabrication drawings to be provided by end of October. Contract delivery date for fabrication is April 2023. 8/8/22 DNM- East Dolphin Replacement Estimate for 2023 updated based on current steel pricing and adjusted 2022 Contractor Installation pricing. Timing for project implementation is fabrication and installation bidding in October 2022, contract awards if 2023 budget is approved in December. Structure fabrication 2023 Q1, Contractor mobilization and installation in 2023 Q2 around RVPseason. 7/8/22- Engineering analysis determined that the eastern dolphin is unfit for long term service. Evaluated cost benefit of repairs vs. replacement. Path forwardto replace the dolphin. 2022 funding will go towards engineering/permitting and material purchase. MKS 2/28/2022 - The new path forward is to complete an overall evaluation ofthe eastern dolphin. The AFE will be submitted in March with an evaluation completion by 4/30 2/2/2022 - Meeting with Markella to discuss path forward. | 2023-05-02 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Florida | BETQJ - BET JACKSONVILLE TERMINAL |  | 410780 | 1414337 | 400000 |  | 723061 |  | Spari, Markella | Spari, Markella |  |  | 1 | 24662 |  | Administrator, System | Independent | Aqua | 2017-07-31 | Marine
New Haven 85 East Tank 5A Roof Insulation Refurb | Item | Open | MCAP | BNTNX00M2201 | Maintenance Framework | 1937237 | Manchester, Justin | ECS Pipes and Terminals | 6. Operational | Defined | Tanks | -780 |  |  | -780 | -780 | 0 | Green |  |  |  | -780 |  |  | 260000 |  |  | 260000 | Full | 260000 | 285830 |  | 285830 | No | Green | 2022-03-01 | 2022-01-05 | 2022-01-05 | 2022-12-31 | 2022-09-01 |  |  |  | -780 | [17 empty] | 2/23/23 NV- Reclass to come 12/21/22 NV- CWIP charges hitting after project has gone operational, talking to accounting to discuss charges rolling off. 11/3/2022 NV- Negative forecast for reclass 9/23/22 - Forecast updated to reflect accruals falling off. 9/1/22 NV- Project completed earlier than planned, ready to close. Negative forecast to reflect anticipated reclass. 8/8/22 NV- Work completed ahead of schedule 5/10/22 NAW- prep work being completed earlier than anticipated | 2023-02-23 | Williams, Nikole |  | East | Pipelines and Terminals | Integrity |  | New Haven Harbor | BNTNX - New Haven 85 East Terminal |  | -780 | 0 |  |  | 286610 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41295 |  | Administrator, System | Independent | Aqua | 2021-08-10 | Int - Tanks
New Haven Harbor Terminal Switchgear Replacement Phase II | Item | Open | MCAP | BNTNV00M2201 | Maintenance Framework | 1917288 | Manchester, Justin | ECS Pipes and Terminals | 6. Operational | Defined | Electrical | 413 |  |  | 413.02 | 413 | 0 | Green |  |  |  | 413 |  |  | 476000 |  |  | 476000 | Full | 476000 | 497309 |  | 497309 | No | Green | 2022-04-01 | 2021-12-27 | 2021-12-27 | 2022-06-01 | 2022-11-30 |  |  | 413.02 | [18 empty] | 2/10/23 NV- Forecast mistake 12/8/22 NV: Project complete. 9/12/22 NAV- 50% invoiced earlier than expected. Adjusted forecast to reflect 10% cost in December & remaining 40% in November. 6.9.22 NAW- work delayed due to other activity at the terminal. 5/10/22 NAW- Missed forecast due to project work starting later than anticipated. 2/9/22 NAW- Project expected to start May '22 | 2023-02-10 | Williams, Nikole |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  | 413 | 0 |  |  | 496896 |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 40549 |  | DeSocio, David | Independent | Aqua | 2021-07-16 | Other Programs
New Haven Waterfront Construct Electrical Room | Item | Open | MCAP | BNTNV00M2303 | Maintenance Framework | 2077119 | Manchester, Justin | ECS Pipes and Terminals | 3. Active | Defined | Electrical | 25063 |  | 2150 | 25062.8 | 23929 | 1134 | Yellow | 25000 |  | 25000 | 63 |  |  | 25478 |  |  | 25478 | Full | 25478 | 25063 | 2150 | 27213 | No | Green | 2023-03-01 | 2023-01-31 | 2023-01-31 | 2023-12-01 | 2023-04-07 |  |  |  |  | 23928.75 | 1134.05 |  |  | 1134 | Red | [10 empty] | 2150 |  |  | Williams, Nikole |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  | 23929 | 1134 |  |  |  |  | Ashley, Robert | Orischak, Bob |  |  | 1 | 44529 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Other Programs
New Haven Waterfront Electrical Upgrade Phase 3 | Item | Open | MCAP | BNTNV00M2302 | Maintenance Framework | 2077279 | Manchester, Justin | ECS Pipes and Terminals | 3. Active | Defined | Electrical | 182969 | 288000 | 41191 | 470968.5 | 456156 | 14812 | Yellow | 493000 |  | 493000 | -22032 |  |  | 493115 |  |  | 493115 | Full | 493115 | 182969 | 329191 | 512160 | No | Green | 2023-03-01 | 2023-01-31 | 2023-01-31 | 2023-12-01 | 2023-12-31 |  |  |  |  | 108656.2 | 74312.3 | 59500 | 59500 | 14812 | Red |  |  | 72000 | 72000 | 72000 | 72000 |  |  |  |  | 41191 |  |  | Williams, Nikole |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  | 108656 | 218312 | 144000 |  |  |  | Ashley, Robert | Orischak, Bob |  |  | 1 | 44452 |  | Guest, ProSight | Independent | Aqua | 2022-08-08 | Other Programs
Perth Amboy Berth 2 Upgrades - 2022 | Item | Open | MCAP | BPTPC00M2216 | Project Framework | 2012082 | Smith, Rachele | ECS Pipes and Terminals | 2. Pending AFE | Emergent | Marine | 45981 | 150098 |  | 196078.78 | 289809 | -93730 | Red |  | 156000 | 156000 | 40079 |  |  | 654000 |  |  |  | Interim | 654000 | 472078 | 150098 | 622176 | No | Green | 2022-09-01 |  |  | 2023-05-02 | 2023-10-13 |  |  | 3148.49 | 7115.55 | 31186.68 | 4530.06 | 24615 | 24615 | -20085 | Red |  |  | 150098 | [8 empty] | 05.05.23KB: Bowman engineering will be charged to 2023 Bollard refurbishment. Once the 2022 Bollard refurb costs are reclassed to this project. It will be closed. 04.07.23 KB: Bowman began engineering design. Construction to expected to begin in September. 03.17.23 KB: Still pending engineering report from Bowman to determine total scope and cost. 03.06.23 KB: full AFE will be submitted once the final costs are determined. 03.02.23- Kicked off engineering effort to determine additional work at the bollard. | 2023-05-05 | Boyd, Kim |  | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 41451 | 154628 |  |  | 426097 |  | Spari, Markella | Spari, Markella |  |  | 1 | 44112 |  | Clark, David | Independent | Aqua | 2022-07-12 | Marine
Perth Amboy Biodiesel Arm 4 Refurbishment | Item | Open | MCAP | BPTPC00M2302 | Project Framework | 2083138 | Smith, Rachele | ECS Pipes and Terminals | 3. Active | Emergent | Marine |  | 430645 | 39355 | 430645 | 430645 | 0 | Green |  |  |  | 430645 |  |  | 469215 |  |  | 469215 | Full | 469215 |  | 470000 | 470000 | No | Green | 2023-06-01 | 2023-04-19 | 2023-04-19 | 2023-11-01 | 1900-09-30 | [13 empty] | 4760 | 4760 | 4760 | 59760 | 154760 | 159300 | 42545 | 39355 | 04/05/23: MKS Reallocated 470K in funds from 85 East Dredging project OPPM ID 03.17.23 KB: PM to submit AFE by 3/24/23 03.02.23. KB - PM has requested additional funds for the installation of these critical parts, no funding to date. | 2023-04-05 | Boyd, Kim |  | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  |  | 4760 | 69280 | 356605 |  |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 46566 |  | Clark, David | Independent | Aqua | 2023-02-01 | Other Programs
Perth Amboy Fire Protection Upgrades | Item | Open | MCAP | BPTPC00M2219 | Maintenance Framework | 2022468 | Sikkema, Jim | ECS Pipes and Terminals | 6. Operational | Emergent | Fire Protection | 42493 |  |  | 42493.11 | 36289 | 6204 | Red |  |  |  | 42493 |  |  | 162000 |  | 25000 | 162000 | Supplemental | 187000 | 192493 |  | 192493 | No | Green | 2022-12-01 | 2022-09-12 | 2022-09-12 | 2023-01-01 | 2022-12-31 |  |  | 27693.13 | 7488.3 | 1108.02 | 6203.66 |  |  | 6204 | Red | [11 empty] | 04.21.23 KB: CO was fully executed 4/16/23 and supplemental was submitted by K. Walton on 4/19/23. 04.07.23 KB: Project is complete. Pending CO approval and supplemental for close-out. 03.06.23 KB: Still pending CO approval 02.09.23 KB: CO executed for appx $13k. 12.07.22 KB: $51k of scope additions (HDPE to DIP clarifications) to original PO will cause the project cost to exceed the budget. Additional risk of increased cost to cross Colonial Pipeline. Meeting on Dec. 12th to expose pipe and define strategy. 11.09.22 KB: No work has begun 9.3.22.DLC: Initial forecast | 2023-04-21 | Boyd, Kim | Werner, Nate | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 36289 | 6204 |  |  | 150000 |  | Jakubowski, Gregory | Jakubowski, Greg |  |  | 1 | 44120 |  | Clark, David | Independent | Aqua | 2022-07-12 | Other Programs
Perth Amboy Sidewalk Installation/Replacement | Item | Open | MCAP | BPTPC00M2217 | Maintenance Framework | 2022620 | Smith, Rachele | ECS Pipes and Terminals | 3. Active | Emergent | East | 6519 | 526225 | 122618 | 532744.46 | 532747 | -2 | Yellow | 338000 | 191000 | 529000 | 3744 |  |  | 778000 |  |  | 778000 | Full | 778000 | 129157 | 648843 | 778000 | No | Green | 2022-09-01 | 2022-09-14 | 2022-09-14 | 2022-06-30 | 2023-06-30 |  |  | 565.47 | 575.92 | 4560.27 | 817.8 |  |  | 818 | Red |  |  | 113765 | 371560 | 40900 | [5 empty] | 122618 | 04.07.23 KB: Per Jim Sikkema, S&B will be applying for the Rd Opening Permit, expected to be granted Mid-May with work commencing in late May and completing by the end of June. 03.07.23 KB: No update 02.08.23 KB: Still pending permit; forecast has been moved to 2nd Qtr. 01.09.23 KB: No activity anticipated in January due to permitting. 12.07.22 KB: "Road Opening and Construction" Permit was rejected pending Air Quality Permit on the overall Biodiesel Project. 11/10/22 - Awaiting City Permitting for work. DC 11.07.22 KB: No construction pending bond. Currently, in the bidding process expected fully executed PO by Thanksgiving and work commencing in Dec. 10.10.22 KB: Re-accrue $110k reclass. 9.12.22.DLC: Slid forecast 2 months per PM 9.8.22 KB: Sept forecast includes $110k reclass of actuals currently charged to Perth Amboy Biodiesel Project. | 2023-04-07 | Boyd, Kim |  | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 5702 | 486143 | 40900 |  | 122638 |  | Orischak, Bob | Orischak, Bob |  |  | 1 | 44115 |  | Clark, David | Independent | Aqua | 2022-07-12 | Other Programs
Port Reading- North Ship Dock Repairs | Item | Open | MCAP |  | Project Framework |  | Smith, Rachele | ECS Pipes and Terminals | 4. On-Hold |  | Marine |  |  |  | 0 |  | 0 | Green | 760000 | -760000 | 0 | 0 | [11 empty] | No | Green |  |  |  |  | 2023-07-31 | [21 empty] | 04.05.23 KB: CY Budget transferred to South Dock Refurbishment and the forecast removed. 03.23.23 KB: Placed on hold to prioritize South Dock Refurbishment per M. Spari email. 03.17.23 KB: No update 03.07.23 KB: Maybe on hold due to issues with the South Docks, per email from Markella Spari on 2/28/23. Rachele Smith was assigned this project as of 02/14/23. March forecast should be revised to $50k. There will be no work in April or May. Remaining work to be done June, July and August. | 2023-04-05 | Boyd, Kim |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 0 |  |  |  |  | Spari, Markella | Spari, Markella |  |  | 1 | 41545 |  | Administrator, System | Independent | Aqua | 2021-08-19 | Marine
Port Reading South Dock Refurbishment 2023 | Item | Open | MCAP | BPRPR00M2305 | Project Framework | 2096409 | Smith, Rachele | ECS Pipes and Terminals | 3. Active | Emergent | Marine | 19154 | 727296 | 13550 | 746449.94 | 146734 | 599716 | Red | 760000 |  | 760000 | -13550 |  |  | 160284 |  |  | 160284 | Phase | 160284 | 19154 | 740846 | 760000 | No | Green | 2023-04-01 | 2023-03-28 | 2023-03-28 | 2023-12-29 | 2023-12-29 | [5 empty] | 19153.94 | 18185 | 18185 | 969 | Yellow |  |  | 101370 | 8570 | 4980 | 4420 | 261870 | 343370 | 2716 |  | 13550 | 04.11.23 KB: Phase AFE for Engineering design and Core Samples. Total budget of $760k estimated to cover construction expected to begin in Sept. Forecast will be updated for construction once the scope and pricing are defined. | 2023-04-11 | Boyd, Kim |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 129094 | 271270 | 346086 |  |  | Spari, Markella | Spari, Markella |  |  | 1 | 46825 |  | Meitzler, Antoinette | Independent | Aqua | 2023-03-22
Port Reading Tank 1202 Fixed and Floating Roof Replacement | Item | Open | MCAP | BPRPR00M2307 | Maintenance Framework | 2120198 | Petry, Gregory | ECS Pipes and Terminals | 2. Pending AFE | Defined | Tanks |  | 4200000 |  | 4200000 | 4200000 | 0 | Green |  |  |  | 4200000 | [6 empty] | Interim |  |  | 4200000 | 4200000 | No | Green | 2023-06-01 |  |  |  | 2023-11-30 | [13 empty] | 500000 | 500000 | 1200000 | 1000000 | 500000 | 500000 |  |  | 4/7/23-CES-Gregory Petry is now Project Manager. Adjusting forecast and cost based on latest data. Repairs should start shortly after demolition, targeting May through December for tank repairs. | 2023-04-07 |  |  | East | Pipelines and Terminals | Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 500000 | 2700000 | 1000000 |  |  | Stine, Carlton | Korth, Jeremy |  |  | 1 | 46594 |  | Clark, David | Independent | Aqua | 2023-02-14 | Int - Tanks
Port Reading Tank 1202 Roof Demo | Item | Open | MEXP | BPRPR00E2306 | Maintenance Framework | 2112817 | Petry, Gregory | ECS Pipes and Terminals | 3. Active | Emergent | Tanks | 4500 | 1137000 |  | 1141500 |  | 1141500 | Red |  | 1485020 | 1485020 | -343520 |  |  | 1485020 |  |  | 1485020 | Full | 1485020 | 4500 | 1137000 | 1141500 | No | Green | 2023-04-01 | 2023-04-27 | 2023-04-27 | 2023-05-01 | 1900-06-30 | [5 empty] | 4500 |  |  | 4500 | Red |  |  | 890000 | 212000 | 10000 | 17000 | 2000 | 2000 | 2000 | 2000 |  |  |  | Carter, Paige |  | East | Pipelines and Terminals | Tank Integrity |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  |  | 1106500 | 29000 | 6000 |  |  | Stine, Carlton | Korth, Jeremy |  |  | 1 | 46943 |  | Clark, David | Independent | Aqua | 2023-04-14
Port Reading-Superstructure and substructure structural repairs of the South Dock Main Access Trestle. | Item | Open | MCAP | BPRPR00M2203 | Project Framework | 1938781 | Smith, Rachele | ECS Pipes and Terminals | 6. Operational | Defined | Marine | 602097 | 5474 | 151748 | 607570.81 | 590321 | 17250 | Yellow |  |  |  | 607571 |  |  | 32000 | 1748000 | 1950000 | 3730000 | Phase | 3730000 | 3572778 | 157222 | 3730000 | No | Green | 2022-02-01 | 2022-01-20 | 2022-01-20 | 2022-12-31 | 2023-02-01 |  |  | 326658.03 | 98548.9 | 119597.36 | 57292.52 | 45517 | 45517 | 11776 | Red |  |  | 5474 | [7 empty] | 151748 | 04.07.23 KB: CO approved 4/5/23 incurred costs have been accrued. 03.17.23 KB: Anchor CO cancelled. New PO executed under new company Bowman. CO Simpson & Brown for punch list items awaiting approval. 03.08.23 KB: Currently awaiting another S&B invoice and CO from Anchor. 03.06.23 KB: Expecting punch-list items to complete by the end of March. 12.12.22 KB: Supplemental submission pending ECO approval. 11.07.22 KB: Additional accrual of $586K has been forecasted in November. The approved AFE scope include North & South Dolphin only. The forecast reflects original scope N&S Dolphins, Emergency Repairs at the dock and Spring Line Dolphins. 10.5.22 SDB: Project was transferred to Ms. Rachele Smith to be PM on 09/26. 9.20.22 SDB: Bids for emergency work received on 09/16/22. KT is the low bidder in the process. Discussion continues as to the SOW to be completed in 2022 and 2023. 9.7.22 MKS: PM is getting estimates for 2023 scope. 2023 carryover 1.5M. 9.2.22 SDB: Bid process started by Supply Chain. Contractor bids due 09/16/22. 8.22.22 SDB: Received revised bid package for emergency work from Anchor Consultants for review. 8.15.22 SDB: Anchor working on the repair procedures and bid package for the emergency work to be completed at Port Reading. 8.1.22 SDB Anchor consultants is putting together the bid documents and repair procedures to take this emergency work through the supply chain bid process. 7.29.22.DLC: Moved $240k from Bayonne project that pushed 7.26.22 SDB: Anchor consultants completed an initial evaluation of the dock and placed two structures needing emergency repairs. These will be addressed immediately. 7.8.22 SDB: Anchor consultants received a PO to conduct a structural inspection of the marine structures, determine repairs to be completed and develop repair procedures. 5.31.22 SDB: Request submitted to provide Anchor Consultants LLC with a PO to complete the Structural Inspection, provide repair procedures and permits support forthe Port Reading work. 5.25.22.DLC: Moved funds into this recordand cancelled others. 5.2.22 SDB: Structural inspection to be completed at the marine facilities in May in order to determine the extent of repairs and repair methods. 3.31.22 SDB: Detailed inspection is planned to better determine the extent of the repair scope needed to be completed. 2.18.22.DLC: Performing secondary inspection to validate some gaps on prior inspections. | 2023-04-07 | Boyd, Kim |  | East | Pipelines and Terminals | Operating Infrastructure |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 544804 | 62767 |  |  | 2970682 |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 41544 |  | Administrator, System | Independent | Aqua | 2021-08-19 | Marine
Tampa North - Dock loading platform and access trestle replacement | Item | Open | MCAP | BETQT00M2202 | Project Framework | 1970330 | Martin, Dave | ECS Pipes and Terminals | 3. Active | Defined | Marine | 384124 | 1495000 |  | 1879123.88 | 1921333 | -42209 | Yellow | 2159999 |  | 2159999 | -280875 |  |  | 39000 | 99000 |  | 138000 | Phase | 138000 | 1934501 | 1495000 | 3429501 | No | Green | 2022-04-01 | 2022-04-04 | 2022-04-04 | 2022-06-01 | 2023-12-31 |  |  | 84282.26 | 33587.63 | 83463.13 | 182790.86 | 100000 | 100000 | 82791 | Red |  |  | 0 | 75000 | 100000 | 150000 | 250000 | 250000 | 370000 | 300000 |  | 05/03/2023 DNM-Installation of test pile delayed until June. Forecasting adjusting Q2 Spend based on advanced spend in April by early completion of Kanon fabrication. 04/05/2023 DNM-Callan Marine Invoice ($304K) submitted. Scheduling Test Pile and PDA analysis on B1 pile on April 19th. Anticipate PDA test in May to allow for final pile length decision for platform. Installation bid planned for late May. 3/2/2023 DNM- Establishing location for Dock B1 Installation based on survey data. B1 Test Pile to be driven in Q2 to finalize all deck pile lengths based on PDA report. Anticipate Installation Bid in in June. Spend plan adjusted from Q2 into Q4 based installation schedule discussion with Operations to coordinate work within the Complex between North and South. 2/3/2023 DNM- Site Survey completed for layout of replacement dock position. Deck fabrication in detailing to begin shop fabrication. 01/04/12023 DNM- Phase 1 Trestle support upgrade is complete. FFS has all steel in shop and fabrication of deck is underway. 12/04/22 DNM-Callan Marine mobilized to site to begin execution of Phase 1 Trestle Stabilization. Work to begin on December 5th. Anticipated completion is December 16th. 11/02/2022 DNM- MLA Fabrication underway. Callan Marine contracted and mobilizing for installation of Phase 1 Trestle Bents.Q4 spend projects for November and December increased based on advancing Q1 2023 work. Increase in MCAP spend offset by BETSS funds be reallocated. Q1 2023 forecasting reduced accordingly. 10/4/2022 DNM- Relocation of Dock Operator Building at 70%. Award of Phase 1 Trestle Support Work to begin in November. 8/2/22 DNM-Project plan is for trestle support structure replacement in late Q3 and Q4. Loading arm options to be reviewed with Operations in August. Bid for loading arms and contracting in September, award in October (9-10 month delivery). Bid of platform structure and trestle walk in Q4 with contract award after 2023 budget isapproved. nIstallation bid in 2023 Q2 with field construction in Q4 2023. 7/8/22:PM developing project charter and BOD document for new platform, access trestle andfuel loading option. MKS 6/9/22: MKS 260K additional funding moved from other Tampa project. 4/1/2022 - Phase 1 AFE routed for approval. Lloyd Engineering to focus on developing details of two conceptual designs. 2/1/2022 - Project Charter and Scope underway. Working on conceptual design with Dave Martin and Lloyd Engineering. Need to review with Angela and increase priority within the dock program | 2023-05-02 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Florida | BETQT - BET TAMPA NORTH TERMINAL |  | 201333 | 257791 | 500000 | 920000 | 1550378 |  | Spari, Markella | Burke, Kevin |  |  | 1 | 41944 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Marine
Tampa North - Ship Berth - Bollard replacement | Item | Open | MCAP | BETQT00M2204 | Project Framework | 2022476 | Martin, Dave | ECS Pipes and Terminals | 6. Operational | Defined | Marine | 3035 |  |  | 3034.96 | 2066 | 969 | Red |  |  |  | 3035 |  | CY Budget Estimate Incorrect | 190000 |  |  | 190000 | Full | 190000 | 227780 |  | 227780 | Yes | Red | 2022-09-01 | 2022-09-12 | 2022-09-12 | 2022-12-22 | 2022-12-31 |  |  | -18690.36 | -767.5 | 21524.24 | 968.58 |  |  | 969 | Red | [11 empty] | 03/02/2023 DNM-Tracking final invoices 02/03/2023 DNM- Project in closeout. 01/04/2023 DNM- North Bollard installation. Working with Scheduling for window to install South Bollard. 12/05/2022 DNM Bollard Templates completed. Installation in December around vessel traffic. 11/02/2022 DNM- Bolt Pattern Template being completed. Installation of anchor bolts to follow. 10/10/2022 DNM- Marine bollards delivered to site. Contractor drilling new anchor bolt pattern around vessel traffic. Installation of new bollards to be coordinated with Tampa North Trestle Bent Installation in November. 9/1/22: MKS This item will be added to the scope of BETQT00M2202 2/1/2022 - Scope and Project Charter development underway. | 2023-03-02 | Williams, Nikole |  | South | Pipelines and Terminals | Operating Infrastructure |  | Florida | BETQT - BET TAMPA NORTH TERMINAL |  | 2066 | 969 |  |  | 224745 |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 41946 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Marine
Tampa North Dock Line Atmospheric Coating Refurbishment | Item | Open | MEXP | BETQT00E2205 | Maintenance Framework | 2022566 | Martin, Dave | ECS Pipes and Terminals | 6. Operational | Defined | Atmospheric Corrosion | 343 |  |  | 343 | 343 | 0 | Green |  |  |  | 343 |  |  | 69000 |  |  | 69000 | Full | 69000 | 72267 |  | 72267 | No | Green | 2022-10-01 | 2022-09-13 | 2022-09-13 | 2022-12-22 | 2022-03-31 |  |  | 0 | 343 | 0 | 0 |  |  | 0 | Green | [11 empty] | 04/05/2023 DNM- Awaiting invoice. 03/02/2023 DNM- Tracking final coating invoice 02/03/2023 DNM- Project in close out 01/04/2023 DNM- Work complete. Awaiting final invoice for close out 11/02/2022 DNM- Advanced preparation work into October to align schedules with dock trestle work in December. 10/10/22 DNM-Project scheduled to coincide with Tampa Bock work being contracted. 2/1/2022 - Project work to be performed during dock rebuild project. AFE targeted for late Q2 approval. | 2023-04-05 | Williams, Nikole |  | South | Pipelines and Terminals | Corrosion |  | Florida | BETQT - BET TAMPA NORTH TERMINAL |  | 343 | 0 |  |  | 71924 |  | Geib, Rob | Miller, Michael A. |  |  | 1 | 41368 |  | Guest, ProSight | Independent | Aqua | 2021-08-10 | Int - Planned Corr & FI
Utica Terminal Multiload Upgrade | Item | Open | MCAP | BETCA00M2202 | Maintenance Framework | 1945728 | Harris, Mark | ECS Pipes and Terminals | 3. Active | Defined | Truck Racks | 6031 | 30833 | 45190 | 36863.63 | 35118 | 1746 | Yellow |  |  |  | 36864 |  |  | 350000 |  |  | 350000 | Full | 350000 | 275723 | 76023 | 351746 | No | Green | 2022-03-01 | 2022-02-03 | 2022-02-03 | 2023-05-15 | 2023-06-05 |  |  | 1195.83 | 1198.5 | 1239.53 | 2396.77 | 651 | 651 | 1746 | Red |  |  | 5793 | 11008 | 11008 | 1008 | 1008 | 1008 |  |  | 45190 | 9/9/2022: : Project construction delayed due to Electrical Equipment delayed delivery and awaiting an environmental decision on extended scope for Bay 3 draining issues. 8/8/2022: Multiload upgrade delay due to biodiesel upgrade delay. 5/10/2022: Due to logistics delays, ordered parts earlier than anticipated because lead times longer than originally scheduled. 2/1/2022 AFE approved and need to schedule a job walk with Triad and MidStream. Have received updated quotes for material. 5/9/22: Due to the long lead times on electrical and automation equipment; we were forced to purchase a lot more equipment now in order to have it on time. We’d forecasted for automation work that is being conducted in connection with the Utica Biodiesel Upgrade (which construction takes place between May and June). However, equipment had to be ordered early in order to have delivered on time. | 2023-03-09 | Ruiz, Antonio |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BETCA - BET UTICA TERMINAL |  | 3634 | 19198 | 13024 | 1008 | 269692 |  | Younce, Michael | Tracey, Steve | N/A |  | 1 | 30724 |  | Guest, ProSight | Independent | Aqua | 2018-08-20 | Other Programs
2022 Hydrographic and Side Scan Surveys Allocation | Item | Open | MEXP | 1348250E2215 | Exempt |  | Spari, Markella | Engineering and Design | 3. Active | Drawdown | Marine |  |  |  | 0 | 10000 | -10000 | Red | [6 empty] | 220000 |  |  | 220000 | Full | 220000 |  |  |  | No | Green |  | 2022-02-17 | 2022-02-17 |  | 2022-09-30 | [6 empty] | 10000 | 10000 | -10000 | Red | [11 empty] | 3/7/22: Survey at St. Louis not completed yet due to unfavorable low water conditions. Survey scheduled for the week of March 13th. 11/9/22: Surveys at Groton, Raritan Bay, Pennsauken and St. Louis are scheduled in November. 9/12/22: MKS Issued 55.7K up to date. Remaining available funding 164K will fund BBH structural assessments (bid came back at 160K). I am forecasting the spend in 3 months October-December 54,600K each. No returns to the portfolio are anticipated. 8/5/22: MKS Issued 55.7K in POs remaining 164K from this project will fund 1348250E2214 2022 Routine Dock inspections. Notes are provided in the children project forms. | 2023-03-07 | Holt, Camellia |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  |  | 0 |  |  |  |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 41965 |  | Administrator, System | JDE Parent | Yellow | 2021-08-23 | Marine
2023 Drawing Updates Budget Allocation | Item | Open | MEXP | 1348250E2324 | Maintenance Framework |  | Finney, Matthew | Engineering and Design | 2. Pending AFE | Defined | Corporate |  | 1000000 |  | 1000000 | 1000000 | 0 | Green | 1000000 |  | 1000000 | 0 |  |  | 1000000 |  |  |  | Full | 1000000 |  | 1000000 | 1000000 | No | Green | 2023-05-01 |  |  | 2023-12-31 | 2023-12-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 200000 | 200000 | 150000 | 150000 | 150000 | 75000 | 50000 | 25000 |  |  |  | McKee, Linda |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal | Station/Terminal | Corporate | Corporate |  |  | 400000 | 450000 | 150000 |  |  | Clark, Dave | Clark, David |  |  | 1 | 45783 |  | Clark, David | Independent | Aqua | 2022-09-09 | Other Programs
2023 Marine Coating Budget Allocation | Item | Candidate | MEXP |  | Project Framework |  | Spari, Markella | Engineering and Design | 1. Proposed |  | Marine |  | 800000 |  | 800000 | 800000 | 0 | Green | 800000 |  | 800000 | 0 | [9 empty] | 800000 | 800000 | No | Green | 2023-07-01 |  |  |  | 2023-11-30 | [14 empty] | 200000 | 100000 | 100000 | 200000 | 200000 | [6 empty] | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  |  | 0 | 400000 | 400000 |  |  | Spari, Markella |  |  |  | 1 | 45374 |  | Spari, Markella | Independent | Aqua | 2022-08-26 | Marine
Allentown New Office Space Design Buildout (Allentown-PA) Capital AFE | Item | Open | MCAP | 1348817M2001 | Exempt | 1680827 | Kunow, Ashley | Engineering and Design | 3. Active | Defined | Corporate | 352 |  |  | 351.73 | 262 | 90 | Red |  |  |  | 352 |  |  | 401000 |  |  | 401000 | Phase | 401000 | 18932 |  | 18932 | No | Green | 2020-02-01 | 2020-02-21 | 2020-02-21 | 2020-12-30 | 2021-09-30 |  |  | 85.71 | 87.25 | 88.83 | 89.94 |  |  | 90 | Red | [11 empty] | 12/3- On track with schedule for furniture bid event 10/5/2020 Construction documents 100% complete. Furniture RFP prep in progress. 8/7/2020 Demand planning updated to trigger to CY+1. Project to be completed next year. 6/3/2020 Pending construction forecasts for 2021. 5/4/2020 EK Design Development on track for kick off in May 3/10/20- AK- Currently working on Schematic Design with MKSD, anticipated completion in mid April | 2020-12-03 | Williams, Nikole |  | Corporate | Corporate | Corporate |  | Corporate | Corporate | 1348817M2000 | 262 | 90 |  |  | 814 |  | Clark, Dave | King, David |  |  | 1 | 36136 |  | Kabaria, Erika | Child (Major Project) | Olive | 2020-02-20 | Office Relocation
Baltimore Routine Level Dock Inspection 2022 | Item | Open | MEXP | BETQB00E2202 | Exempt | 1955650 | Spari, Markella | Engineering and Design | 3. Active | Drawdown | Marine | 11510 |  |  | 11510 | 11510 | 0 | Green |  |  |  | 11510 |  |  | 33000 |  |  | 33000 | Full | 33000 | 53510 |  | 53510 | No | Green | 2022-10-01 | 2022-03-09 | 2022-03-09 | 2022-12-31 | 2022-12-31 |  |  | 0 | 0 | 11510 | [16 empty] | 3/7/22: Waiting on final reporting to be issued. 11/9/22: Inspection complete waiting on reporting. 10/10/22: Inspection on going. 9/12/22: Inspection moved to November due to contractor availability. 8/2/22:Inspection moved to late August. 7/8/22: Inspection moved to August. 6/9/22:Inspection moved to July. 5/9/22: Inspection planned for late May. 4/1/22: PO issued. Working with dock scheduler to find availability window in April. | 2023-04-05 | Williams, Nikole |  | East | Pipelines and Terminals | Station/Terminal |  | Baltimore | BETQB - BET BALTIMORE TERMINAL |  | 11510 | 0 |  |  | 42000 |  | Spari, Markella | Spari, Markella | N/A |  | 1 | 43154 |  | Meitzler, Antoinette | JDE Child | Burnt Orange | 2022-03-10 | Marine
Bayonne Routine and Design Dock Level Inspection 2022 | Item | Open | MEXP | BBTQY00E2205 | Exempt | 1955648 | Spari, Markella | Engineering and Design | 6. Operational | Drawdown | Marine | -44980 |  |  | -44980 | -44980 | 0 | Green |  |  |  | -44980 |  |  | 33000 |  |  | 33000 | Full | 33000 | 44980 |  | 44980 | No | Green | 2022-05-01 | 2022-03-09 | 2022-03-09 | 2022-12-31 | 2022-10-04 |  |  | 0 | -44980 | [17 empty] | 04/04/23: Actuals posting correctly. Project complete. Need to close out. 11/8/22: Close out project. 9/12/22: Project complete. There seems to be an error with actuals posted. Total cost off the project should be $44,950. 8/1/22: Project complete. Processing invoices. 7/8/22: Draft report issued. 6/7/22: Inspection complete. two additional inspection days approved. Waiting on report. 4/1/22: Inspection started on 4/1. Report will be issued in 6 weeks. Project will be closed by end of May. | 2023-04-04 | Williams, Nikole |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor North Terminals | BBTQY - BBT BAYONNE TERMINAL |  | -44980 | 0 |  |  | 89960 |  | Spari, Markella | Spari, Markella | N/A |  | 1 | 43153 |  | Meitzler, Antoinette | JDE Child | Burnt Orange | 2022-03-10 | Marine
Brewerton OOS Dock Inspection | Item | Open | MEXP | BETBW00E2201 | Maintenance Framework | 2011881 | Spari, Markella | Engineering and Design | 6. Operational | Drawdown | Marine | -10700 |  |  | -10700 | -10700 | 0 | Green |  |  |  | -10700 |  |  | 10700 |  |  | 10700 | Full | 10700 | 10700 |  | 10700 | No | Green | 2022-09-01 | 2022-08-09 | 2022-08-09 |  | 2022-12-31 |  |  | 0 | -10700 | [17 empty] | 04/04/23: Actuals posted are correct ($10,700). Project is complete. Need to close out. 03/7/23: Project closeout. 11/08/22: Accrued $10,700 in September. Waiting on invoicing. 10/10/22: Inspection complete waiting on report. | 2023-04-04 | Holt, Camellia |  | East | Pipelines and Terminals | Station/Terminal |  | Auburn Terminals | BETBW - BET BREWERTON TERMINAL |  | -10700 | 0 |  |  | 21400 |  | Spari, Markella | Mirandi, Angela | N/A |  | 1 | 44456 |  | Holt, Camellia | JDE Child | Burnt Orange | 2022-08-08 | Marine
Cleveland Bulkhead Repairs | Item | Candidate | MEXP |  | Maintenance Framework |  | Spari, Markella | Engineering and Design | 1. Proposed |  | Marine |  | 195000 |  | 195000 | 195000 | 0 | Green |  |  |  | 195000 | [9 empty] | 195000 | 195000 | No | Green | 2023-05-01 |  |  |  | 2024-12-31 | 8 | Yellow | [10 empty] | 25000 | 80000 | 90000 | [6 empty] | 04/12/2023: Received updated quote for bulkhead repairs. Ground conditions are favorable for foam injection repair method that would significantly reduce contraction cost. Waiting on approval from region VP and commercial to proceed with repair project. 01/04/23: Unfavorable frozen ground conditions for foam injection. Subcontractor unavailable. Waiting to hear back from commercial group on future agreement terms with neighbor operator. 11/08/22: Project delays. Supply chain requested additional quotes and ISNET waiver is required for sub. Repair approach was revised so we are looking at a total cost of 150K. 10/11/22: Funding for this project sourced from: Port reading target removal projects (20K+50K) Yabucoa main dock support pile repair and coating (120K) Structural engineering assessments (60K) | 2023-04-12 |  |  | West | Pipelines and Terminals | Station/Terminal |  | Mantua |  |  |  | 105000 | 90000 |  |  |  | Spari, Markella |  |  |  | 1 | 46024 |  | Clark, David | Independent | Aqua | 2022-10-07
Development of SPCC/DOT Risk Ranking System | Item | Open | MEXP | 1348250E2233 | Exempt | 1981577 | Spari, Markella | Engineering and Design | 6. Operational | Drawdown | Secondary Containment | 12195 |  |  | 12195 | 12195 | 0 | Green |  |  |  | 12195 |  |  | 3000 |  |  | 3000 | Full | 3000 | 12195 |  | 12195 | No | Green | 2023-02-01 | 2022-05-24 | 2022-05-24 | 2022-12-31 | 2022-12-31 |  |  |  | 12195 | 0 | [16 empty] | 04/04/23: This project went over budget due to additions to the scope. Actuals posted correctly. Project complete. Need to close out. 03/07/23: Project complete. | 2023-04-04 | Holt, Camellia |  | Corporate | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  | 12195 | 0 |  |  |  |  | Spari, Markella | Mirandi, Angela | N/A |  | 1 | 43830 |  | Meitzler, Antoinette | JDE Child | Burnt Orange | 2022-05-24 | Other Programs
Engineering and Design Effort for Linden 3-Port Check Valve Replacements | Item | Open | MCAP | LN00000M2209 | Maintenance Framework | 1945608 | Oey, Alex | Engineering and Design | 3. Active | Defined | Valves | 38198 | -120000 |  | -81802.27 | -75550 | -6252 | Yellow | 85000 | 191000 | 276000 | -357802 |  |  | 58000 | 227000 |  | 285000 | Full | 285000 | 266734 | -120000 | 146734 | No | Green | 2022-04-01 | 2022-02-01 | 2022-02-01 | 2022-12-31 | 2023-03-31 |  |  | 193673.04 | -175281.36 | 16058.43 | 3747.62 | 10000 | 10000 | -6252 | Red |  |  | 65000 | [6 empty] | -185000 |  | -185K -- it looks like there is no accrual reversal for this record for the 12/2022 accrual. Accounting will reverse this entry in February. 2/14/23 - Discussed with Alex and there have been delays with materials. All valves have arrived but due to operations restraints won't be installed for a couple months. Need to move forecast to 10k March, 10k April, 65k May RLO12/12/22 - Valves expected to received December for Feb/Mar 23 install. DC 7.20.2022.DLC: Removed $35k to allocate to baltimore boiler 12/12/2022 - Invoices were received for materials this month on 12/9. The full $200k should hit the AFE and be accrued. 3/28/23 - Operations had some concerns with certain aspects of valve design that has delayed installation but after discussions with manufacturer we will proceed with installation of one valve during the 1st week of April. | 2023-03-28 | Holt, Camellia |  | East | Pipelines and Terminals | Operating Infrastructure |  | Linden | LN - LINDEN STATION |  | 34450 | 68748 |  | -185000 | 228536 |  | Oey, Alex | Oey, Alexander |  |  | 1 | 41730 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Ethanol Pump Offload assessments | Item | Candidate | MEXP |  | Maintenance Framework |  | Frey, Nathaniel | Engineering and Design | 1. Proposed |  | Rotating Equipment |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 | [9 empty] | 100000 | 100000 | No | Green | 2023-05-01 |  |  |  | 2023-09-30 | 8 | Yellow | [10 empty] | 20000 | 20000 | 20000 | 20000 | 20000 | [8 empty] | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  |  | 40000 | 60000 |  |  |  | Posipanko, Dan |  |  |  | 1 | 45900 |  | Clark, David | Independent | Aqua | 2022-09-22 | Other Programs
Groton 2022 Hydrographic and Side Scan Surveys | Item | Open | MEXP | BETQG00E2201 | Maintenance Framework | 1954793 | Spari, Markella | Engineering and Design | 6. Operational | Drawdown | Marine | 0 |  |  | 0 | 0 | 0 | Green |  |  |  | 0 |  |  | 10300 |  |  | 10300 | Full | 10300 | 10300 |  | 10300 | No | Green | 2022-12-01 | 2022-03-01 | 2022-03-01 | 2022-12-31 | 2022-12-31 |  |  |  | 10300 | -10300 | [16 empty] | 4/5/23: Variance due to over accruals. 04/04/23: Survey completed. Actuals posted correctly ($10,300). This project needs to close out. 11/8/22: Delay due to terminal availability. Rescheduled in November and adjusted forecast. 3/9/22: This survey will be scheduled in October. | 2023-04-05 | Williams, Nikole |  | East | Pipelines and Terminals | Station/Terminal |  | Jet Lines | BETQG - BET GROTON TERMINAL |  | 0 | 0 |  |  | 10300 |  | Spari, Markella | Spari, Markella | N/A |  | 1 | 43073 |  | Meitzler, Antoinette | JDE Child | Burnt Orange | 2022-03-01 | Marine
ITT Remote Condition Monitoring and Engineering Services | Item | Open | MEXP | 1348250E2323 | Maintenance Framework | 2110436 | Frey, Nathaniel | Engineering and Design | 3. Active | Defined | Rotating Equipment |  | 180000 |  | 180000 | 330000 | -150000 | Red | 300000 |  | 300000 | -120000 |  |  | 330000 |  |  | 330000 | Full | 330000 |  | 180000 | 180000 | No | Green | 2023-05-01 | 2023-04-10 | 2023-04-10 | 2023-12-31 | 2023-09-30 | [6 empty] | 150000 | 150000 | -150000 | Red |  |  | 60000 | 0 | 60000 | 0 | 0 | 60000 | [5 empty] | McKee, Linda |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  |  | 60000 | 60000 | 60000 |  |  | Posipanko, Dan | Posipanko, Daniel A. |  |  | 1 | 45444 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Other Programs
Marine Asset Management Program 2023 | Item | Open | MEXP | 1348250E2322 | Project Framework | 2096549 | Spari, Markella | Engineering and Design | 3. Active | Defined | Marine | 21500 | 1000000 |  | 1021500 | 1007200 | 14300 | Yellow | 1000000 |  | 1000000 | 21500 |  |  | 566000 |  |  | 566000 | Phase | 566000 | 21500 | 1000000 | 1021500 | No | Green | 2023-03-01 | 2023-03-30 | 2023-03-30 | 2023-12-31 | 2023-12-31 |  |  |  |  | 7200 | 14300 |  |  | 14300 | Red |  |  | 50000 | 50000 | 100000 | 100000 | 100000 | 200000 | 200000 | 200000 |  | 03/07/23: Bidding out a number of inspections in late March-April. Not likely to start till May. | 2023-03-07 | McKee, Linda |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  | 7200 | 114300 | 300000 | 600000 |  |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 45119 |  | Spari, Markella | Independent | Aqua | 2022-08-19 | Marine
Marine CP Systems Evaluations MEXP - 2023 | Item | Candidate | MEXP |  | Project Framework |  | Spari, Markella | Engineering and Design | 1. Proposed |  | Marine |  | 120000 |  | 120000 | 120000 | 0 | Green | 120000 |  | 120000 | 0 | [9 empty] | 120000 | 120000 | No | Green | 2023-09-01 |  |  |  | 2023-04-30 | [16 empty] | 30000 | 30000 | 30000 | 30000 | [5 empty] | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  |  | 0 | 30000 | 90000 |  |  | Spari, Markella |  |  |  | 1 | 45748 |  | Clark, David | Independent | Aqua | 2022-09-03 | Marine
Midland OOS Dock Inspection | Item | Open | MEXP | ZD00000E2201 | Maintenance Framework | 2011883 | Spari, Markella | Engineering and Design | 3. Active | Drawdown | West | -10000 |  |  | -10000 | 6044 | -16044 | Red |  |  |  | -10000 |  |  | 16044 |  |  | 16044 | Full | 16044 | 0 |  | 0 | No | Green | 2022-12-01 | 2022-08-09 | 2022-08-09 | 2022-12-31 | 2022-12-31 |  |  | 0 | 0 | 6044 | -16044 |  |  | -16044 | Red | [11 empty] | 04/04/23: Waiting on final deliverable. The consultant had to revisit the dock to complete the inspection reporting. MHA is having issues uploading their invoice in the system. Received invoice ($16,040) via email on the 04/04. Negative variance due to delayed invoicing. 3/7/23: Resolving issues with the vendor. Inspection complete but no report issued yet. | 2023-04-04 | Holt, Camellia |  | West | Pipelines and Terminals | Station/Terminal |  | Coraopolis | ZD - MIDLAND TERMINAL (MPS) |  | 6044 | -16044 |  |  | 10000 |  | Gardner, Travis | Mirandi, Angela | N/A |  | 1 | 44457 |  | Holt, Camellia | JDE Child | Burnt Orange | 2022-08-08 | Other Programs
New Haven Facilities Secondary Containment Engineering | Item | Candidate | MEXP |  | Maintenance Framework |  | Spari, Markella | Engineering and Design | 1. Proposed |  | Secondary Containment |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 | [9 empty] | 100000 | 100000 | No | Green | 2023-10-01 |  |  |  | 2023-07-31 | [17 empty] | 25000 | 50000 | 25000 | [5 empty] | East | Pipelines and Terminals | Station/Terminal |  | New Haven Harbor | BNTNX - New Haven 85 East Terminal |  |  | 0 |  | 100000 |  |  | Spari, Markella |  |  |  | 1 | 45820 |  | Clark, David | Independent | Aqua | 2022-09-12 | Other Programs
Pennsauken 2022 Hydrographic and Side Scan Surveys | Item | Open | MEXP | BPNQP00E2202 | Maintenance Framework | 1954796 | Spari, Markella | Engineering and Design | 6. Operational | Drawdown | Marine | 0 |  |  | 0 | 0 | 0 | Green |  |  |  | 0 |  |  | 8334 |  |  | 8334 | Full | 8334 | 8334 |  | 8334 | No | Green | 2022-12-01 | 2022-03-01 | 2022-03-01 | 2022-12-31 | 2022-12-31 |  |  |  | 8334 | -8334 | [16 empty] | 4/5/23: Variance due to over accrual 04/04/23: Survey completed. Invoice in December. Actuals posting correctly ($8,334). Project is complete and need to close out. 11/08/22: Scheduling delays due to terminal availability. Rescheduled for November and forecast adjusted. 3/9/22: This survey is scheduled for October. | 2023-04-05 | Williams, Nikole |  | East | Pipelines and Terminals | Station/Terminal |  | Pennsauken | BPNQP - BPN PENNSAUKEN TERMINAL |  | 0 | 0 |  |  | 8334 |  | Spari, Markella | Spari, Markella | N/A |  | 1 | 43076 |  | Meitzler, Antoinette | JDE Child | Burnt Orange | 2022-03-01 | Marine
Perth Amboy Routine and Repair Design Level Inspection | Item | Open | MEXP | BPTPC00E2214 | Maintenance Framework | 2003558 | Spari, Markella | Engineering and Design | 6. Operational | Drawdown | Marine | -37050 |  |  | -37050 | -37050 | 0 | Green |  |  |  | -37050 |  |  | 50000 |  |  | 50000 | Full | 50000 | 49400 |  | 49400 | No | Green | 2022-10-01 | 2022-07-21 | 2022-07-21 | 2022-12-31 | 2022-12-31 |  |  | 0 | -37050 | [17 empty] | 04/04/23: Actuals posted are correct ($49,400). Project complete. Need to close out. 02/03/23: Report reviewed with stakeholders. 11/08/22: Inspection complete waiting on report. 10/4/22: Inspection started the week of 10/2. 8/5/22: Waiting on terminal to schedule inspection in late August/September. | 2023-04-04 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | -37050 | 0 |  |  | 86450 |  | Spari, Markella | Mirandi, Angela | N/A |  | 1 | 44201 |  | Holt, Camellia | JDE Child | Burnt Orange | 2022-07-21 | Marine
Port Reading 2022 Hydrographic and Side Scan Surveys | Item | Open | MEXP | BPRPR00E2206 | Maintenance Framework | 1954794 | Spari, Markella | Engineering and Design | 6. Operational | Drawdown | Marine | -13934 |  |  | -13934 | -13934 | 0 | Green |  |  |  | -13934 |  |  | 13934 |  |  | 13934 | Full | 13934 | 13934 |  | 13934 | No | Green | 2022-09-01 | 2022-03-01 | 2022-03-01 | 2022-12-31 | 2022-12-31 |  |  | 0 | -13934 | [17 empty] | 11/08/22: Accrued in September. Still waiting for invoice. 10/4/22: Survey complete awaiting on final invoicing 3/9/22: This survey is planned for September. | 2022-11-08 | Williams, Nikole |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | -13934 | 0 |  |  | 27868 |  | Spari, Markella | Spari, Markella | N/A |  | 1 | 43074 |  | Meitzler, Antoinette | JDE Child | Burnt Orange | 2022-03-01 | Marine
Port Reading Routine and Design Level Dock Inspection (South) 2022 | Item | Open | MEXP | BPRPR00E2207 | Exempt | 1955644 | Spari, Markella | Engineering and Design | 6. Operational | Drawdown | Marine | -22388 |  |  | -22387.5 | -22388 | 0 | Green |  |  |  | -22388 |  |  | 33000 |  |  | 33000 | Full | 33000 | 74800 |  | 74800 | No | Green | 2022-05-01 | 2022-03-09 | 2022-03-09 | 2022-12-31 | 2022-10-04 |  |  | 0 | 0 | -22387.5 | [16 empty] | 4/5/23: Large variance due to over accruals. LM/MS 10/4/22: Final report issued. Project closeout. 8/5/22: Waiting on final report. 6/9/22: Inspection completed. Waiting on report. 5/9/22: Inspection will be completed the week of 5/9. 4/1/22: PR dock not available until April 18th. Customer traffic will be reduced by then. Inspection will still happen in April. | 2023-04-05 | Williams, Nikole |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | -22388 | 0 |  |  | 97188 |  | Spari, Markella | Spari, Markella | N/A |  | 1 | 43152 |  | Meitzler, Antoinette | JDE Child | Burnt Orange | 2022-03-10 | Marine
Port Reading Routine and Repair Design Inspection of Bulkhead | Item | Open | MEXP | BPRPR00E2217 | Maintenance Framework | 2003559 | Spari, Markella | Engineering and Design | 3. Active | Drawdown | Marine | -10483 |  |  | -10482.5 | -10483 | 0 | Green |  |  |  | -10483 |  |  | 30000 |  |  | 30000 | Full | 30000 | 29950 |  | 29950 | No | Green | 2022-09-01 | 2022-07-21 | 2022-07-21 | 2022-12-31 | 2022-12-31 |  |  | 0 | -29950 | 19467.5 | [16 empty] | 11/08/22: Behind in invoicing due to acquisition from another firm and accounting changes. Final deliverable expected on 11/22. 10/4/22: Inspection complete. Waiting on final report 8/4/22: Inspection planned on 8/8. | 2022-11-08 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | -10483 | 0 |  |  | 40433 |  | Spari, Markella | Mirandi, Angela | N/A |  | 1 | 44202 |  | Holt, Camellia | JDE Child | Burnt Orange | 2022-07-21 | Marine
Port Reading South Dock Mooring and Berthing Analysis | Item | Open | MEXP | BPRPR00E2211 | Exempt | 1972651 | Spari, Markella | Engineering and Design | 6. Operational | Drawdown | Marine | 23910 |  |  | 23910 | 23910 | 0 | Green |  |  |  | 23910 |  |  | 43780 |  |  |  | Full | 43780 | 56560 |  | 56560 | No | Green | 2022-05-01 |  |  | 2022-12-31 | 2022-12-31 |  |  |  |  | 23910 | [16 empty] | 11/08/22: Waiting on final invoicing. 10/10/22: Error with accruals posted. Accruals should be $39,800. 10/4/22: Additional work is needed to develop mooring arrangements for the dock. Waiting on Change order. 8/5/22: Waiting on final report 7/8/22: Reviewing preliminary results with consultant.. 6/7/22: Work started in May. No invoices yet. | 2022-11-08 | Williams, Nikole |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BPRPR - BPT PORT READING TERMINAL |  | 23910 | 0 |  |  | 32650 |  | Spari, Markella | Mirandi, Angela | N/A |  | 1 | 43547 |  | Meitzler, Antoinette | JDE Child | Burnt Orange | 2022-04-27 | Marine
Port Wilmington Mooring and Berthing Analysis | Item | Open | MEXP | BNTUE00E2202 | Maintenance Framework | 2003560 | Spari, Markella | Engineering and Design | 6. Operational | Drawdown | Marine | 10849 |  |  | 10848.68 | 23260 | -12412 | Red |  |  |  | 10849 |  |  | 76000 |  |  |  | Full |  | 78676 |  | 78676 | No | Green | 2022-09-01 | 2022-07-21 |  |  | 2022-12-31 |  |  | 53029.67 | 9338.6 | -39107.9 | -12411.69 |  |  | -12412 | Red | [11 empty] | 4/5/23: large variance due to accruals. LM/MS 3/7/23: Moffat and Nichol is revising final report per Buckeye comments. 11/08/22: Basis of design report submitted and reviewed the week of Oct. 31st. Buckeye revised vessels to be used for the analysis. M&N will issue revised BOD report and proceed with the vessel simulations. | 2023-04-05 | Sautter, Maureen |  | East | Pipelines and Terminals | Station/Terminal |  | Port Wilmington | BNTUE - WIlmington(DE) Terminal |  | 23260 | -12412 |  |  | 67828 |  | Spari, Markella | Mirandi, Angela | N/A |  | 1 | 44203 |  | Holt, Camellia | JDE Child |  | 2022-07-23 | Marine
Raritan Bay 2022 Hydrographic and Side Scan Surveys | Item | Open | MEXP | BFRQF00E2204 | Maintenance Framework | 1954795 | Spari, Markella | Engineering and Design | 3. Active | Drawdown | Marine | 8185 |  |  | 8185 | 8185 | 0 | Green |  |  |  | 8185 |  |  | 8185 |  |  | 8185 |  | 8185 | 8185 |  | 8185 | No | Green | 2023-02-01 | 2022-03-01 | 2022-03-01 | 2022-12-31 | 2022-12-31 |  |  |  | 16370 | -8185 | [16 empty] | 4/5/23: Variance due to over accrual. LM 3/9/22: This survey is scheduled for December. | 2023-04-05 | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | Harbor South Terminals | BFRQF - BFR RARITAN BAY TERMINAL |  | 8185 | 0 |  |  |  |  | Spari, Markella | Spari, Markella | N/A |  | 1 | 43075 |  | Meitzler, Antoinette | JDE Child | Burnt Orange | 2022-03-01 | Marine
Routine and Design Level Inspection | Item | Open | MEXP | BETQE00E2205 | Exempt | 2023149 | Spari, Markella | Engineering and Design | 3. Active | Drawdown | Marine | 0 |  |  | 0 | 0 | 0 | Green |  |  |  | 0 |  |  | 35855 |  |  | 35855 | Full | 35855 | 35855 |  | 35855 | No | Green | 2022-11-01 | 2022-09-19 | 2022-09-19 | 2022-12-31 | 2022-12-31 |  |  | 0 | 17927.5 | -17927.5 | [16 empty] | 4/5/23: Large variance due to over accruals. LM/MS 03/07/23: Inspection complete. Reviewing final report. 11/08/22: Delays with scheduling the inspection. Inspection scheduled on Nov. 16th and 17th. Updated forecast. 10/4/22: Issued PO scheduling inspection | 2023-04-05 | Holt, Camellia |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Roseton and Rensselaer | BETQE - BET RENSSELAER TERMINAL |  | 0 | 0 |  |  | 35855 |  | Spari, Markella | Mirandi, Angela | N/A |  | 1 | 45875 |  | Perry, Betty | JDE Child | Burnt Orange | 2022-09-20 | Marine
Secondary Containment Engineering Assesments 2023 | Item | Open | MEXP |  | Maintenance Framework |  | Spari, Markella | Engineering and Design | 1. Proposed |  | Secondary Containment |  | 40000 |  | 40000 | 40000 | 0 | Green | 50000 |  | 50000 | -10000 | [9 empty] | 40000 | 40000 | No | Green | 2023-10-01 |  |  |  | 2023-08-31 | [17 empty] | 20000 | 20000 | [6 empty] | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  |  | 0 |  | 40000 |  |  | Spari, Markella |  |  |  | 1 | 45204 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
St. Louis South 2022 Hydrographic and Side scan survey | Item | Open | MEXP | BETSS00E2202 | Exempt | 1972069 | Spari, Markella | Engineering and Design | 3. Active | Drawdown | Marine | 15595 |  |  | 15595 |  | 15595 | Red |  |  |  | 15595 |  |  | 14987 |  |  | 14987 | Full | 14987 | 15595 |  | 15595 | No | Green | 2022-07-01 | 2022-04-20 | 2022-04-20 | 2022-12-31 | 2022-12-31 | [5 empty] | 15595 |  |  | 15595 | Red | [11 empty] | 11/08/22: Rescheduled due to terminal availability on Nov. 29th. Engineering firm pushed the survey in October due to limited resources. 8/9/22: Scheduled in August | 2022-11-08 | Williams, Nikole |  | West | Pipelines and Terminals | Station/Terminal |  | St. Louis | BETSS - BET ST LOUIS SOUTH TERMINAL |  |  | 15595 |  |  | 0 |  | Spari, Markella | Spari, Markella | N/A |  | 1 | 43514 |  | Meitzler, Antoinette | JDE Child | Burnt Orange | 2022-04-22 | Marine
Structural Integrity Engineering Assessments | Item | Open | MEXP | 1348250E2218 | Maintenance Framework | 1957039 | Spari, Markella | Engineering and Design | 3. Active | Defined | Marine | -156252 |  |  | -156252.35 | -144587 | -11665 | Yellow |  |  |  | -156252 |  |  | 160000 |  |  | 160000 | Phase | 160000 | 562033 |  | 562033 | No | Green | 2022-06-01 | 2022-03-25 | 2022-03-25 | 2022-12-31 | 2022-12-31 |  |  | 26805 | -29992.6 | -141399.75 | -11665 |  |  | -11665 | Red | [11 empty] | 4/5/23: Large variance due to accruals. LM/MS 03/07/23: Issues with a few vendors not being able to upload their invoices in the system (namely Mclean, T&T and Bowman). Forecasting 5k for T&T remainder of work. 1/10/23: Most projects are complete and waiting for final invoicing. 50K carry over in January. 12/2/2022 Reclass submitted for $23K to BPTPC00E2220 for Marine Solutions invoice. 11/08/22: Adjusted November forecast by 46K to offset negative accruals. 11/3/2022 $23k accrued for Marine Solutions invoice. 10/1/2022: Updating forecast for remainder of the year. Moved 160K from 1348250E2215 and 10 K from 134825OE2235 to cover BBH Structural assessments. 09/12/22: MKS Perth Amboy rapid assessment scheduled for Sept.26-30. Raritan Bay, New Haven and Groton rapid assessments in October. 08/03/22: MKS: Asset inventory efforts (New Haven, Groton, Perth Amboy and Raritan Bay) and mooring analyses (Port Wilmington and Yabucoa) forecasted in 4rth quarter (322K total). 06/07/22:Jacksonville assessment complete (68K). Invoicing delays. Louisville jumper arm study to be completed in June. Louisville and Cincy erosion assessments pushed to July due to terminal request. Asset inventory and condition assessments at Chesapeake and Port Wilmington pushed to July. 05/09/22: Jacksonville assessment complete. Additional analysis (29K) is needed. Louisville jumper arm analysis 5K to be completed. 4/1/22: Jacksonville Dolphin engineering assessment (37K)awarded to contractor. 3/9/22: Planning phase | 2023-04-05 | Holt, Camellia |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  | -144587 | -11665 |  |  | 718285 |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 41969 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Marine
Yabucoa Dock Routine and Repair Design Inspection | Item | Open | MEXP | BCTYA00E2204 | Maintenance Framework | 1947568 | Spari, Markella | Engineering and Design | 3. Active | Drawdown | Marine | 32640 |  |  | 32640 | 32640 | 0 | Green |  |  |  | 32640 |  |  | 133000 |  |  | 133000 | Full | 133000 | 108800 |  | 108800 | No | Green | 2022-05-01 | 2022-02-18 | 2022-02-18 | 2022-12-31 | 2022-12-31 |  |  | 27200 | 76160 | -70720 | 0 |  |  | 0 | Green | [11 empty] | 4/5/23: Large variance due to accruals. LM/MS 03/07/23: Inspection completed in December waiting for inspection report and mooring analysis report deliverables. Forecasting $10,880 in April. 01/10/23: 32 K carryover in January. Final reporting is delayed. 12/2/22: Inspection ongoing in December. 10/10/22: Due to hurricane activity and Hurricane Fiona inspection scheduled in December. 9/12/22: MKS Work to be awarded the week of 9/12. Bid pricing 8/5/22: Bid closing date 8/15. 6/9/22: Inspection scope out for bid in June. | 2023-04-05 | Williams, Nikole |  | East | Pipelines and Terminals | Station/Terminal |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | 32640 | 0 |  |  | 76160 |  | Spari, Markella | Davalos, Glenda |  |  | 1 | 43014 |  | Meitzler, Antoinette | JDE Child | Burnt Orange | 2022-02-22 | Marine
2023 Vapor Corrosion Inhibitor Budget Allocation | Item | Candidate | MCAP |  | Maintenance Framework |  | Geib, Rob | HSSE | 2. Pending AFE |  | Cathodic Protection |  | 80000 |  | 80000 | 80000 | 0 | Green | 80000 |  | 80000 | 0 | [9 empty] | 80000 | 80000 | No | Green | 2023-09-01 |  |  |  | 2023-09-30 | [16 empty] | 80000 |  |  |  |  | 3/7/23 AFE Pending | 2023-03-07 |  |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Integrity |  | Corporate | Corporate |  |  | 0 | 80000 |  |  |  | Geib, Rob |  |  |  | 1 | 45345 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Buffalo Vapor Corrosion Inhibitor Installation | Item | Candidate | MCAP |  | Maintenance Framework |  | Herndon, Andrea | HSSE | 1. Proposed |  | Cathodic Protection |  | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 | [9 empty] | 30000 | 30000 | No | Green | 2023-09-01 |  |  |  | 2023-09-30 | [16 empty] | 30000 | [8 empty] | East | Pipelines and Terminals | Integrity |  | Auburn Terminals | BETBO - BET BUFFALO TERMINAL |  |  | 0 | 30000 |  |  |  | Geib, Rob |  |  |  | 1 | 45347 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Columbus South VRU Carbon Change 2023 | Item | Open | MCAP | BETIL00M2202 | Exempt | 1971123 | Scannell, Adam | HSSE | 4. On-Hold | Defined | Vapor Management | 5221 |  |  | 5220.68 | 5221 | 0 | Green |  |  |  | 5221 |  |  | 228000 |  |  | 228000 | Full | 228000 | 117404 |  | 117404 | No | Green | 2022-06-01 | 2022-04-12 | 2022-04-12 | 2022-06-30 | 2023-09-09 |  |  | 5029.56 | 191.12 | [17 empty] | 1/5/23 - Keep project open per Chelsea (AS) 9/12/2023 - This project will be cancelled. We have received the carbon material and some shipping cost to relocated the portable VCU. The remaining project forecast has been zero'd and remaining POs will be closed. 8/1/2022 - Emergency carbon replacement at Lima South 8/2-5. All of the resource for the Columbus South carbon replacement have be redirected to Lima South. Columbus execution date TBD. 6/2/22 - Carbon to be shipped in June ($118k) and field work/replacement in July ($90k) 5/12/2022 - Carbon replacement is scheduled for week of July 11th. Forecast will be readjusted 5/2/2022 - Project AFE approved. Hosted a project kick-off meeting 4/29 and waiting for operations to provide available schedule to execute project. Forecast moved from Dec. to June. 3/8/2022 - Project is out to bid through supply chain. AFE to come... | 2023-04-04 | Schultz, Amy |  | West | Pipelines and Terminals | Operating Infrastructure |  | Southern Ohio | BETIL - BET COLUMBUS SOUTH |  | 5221 | 0 |  |  | 112184 |  | Karl, Marissa | Gardner, Travis W. |  |  | 1 | 42041 |  | Schultz, Amy | Independent | Aqua | 2021-09-02 | Other Programs
Harristown VRU Release Prevention | Item | Open | MCAP | BETHT00M2301 | Maintenance Framework | 2110636 | Scannell, Adam | HSSE | 3. Active | Defined | Vapor Management |  | 43000 |  | 43000 | 43000 | 0 | Green |  |  |  | 43000 |  |  | 22048 |  |  | 22048 | Phase | 22048 |  | 43000 | 43000 | No | Green | 2023-07-01 | 2023-03-30 | 2023-03-30 | 2023-07-31 | 2023-08-31 | [14 empty] | 11000 | 32000 | [5 empty] | 05/08/23 - Site visit with contractor is planned for the week of May 15th to get estimate for spool modifications and installation. Planning for August installation. 4/11/23 - mrk - forecast pushed to july/aug to allow for time to develop engineering drawings. Engineering anticipated completion in July. 03/25/23 - Phase I AFE submitted to the workflow. Phase I will cover the engineering for mechanical and electrical. Once design is complete the mechanical and electrical will be bid for installation. Budget from Sugar Creek VRU Release Prevention (OPPM ID 44953) project being utilized to fund this. Sugar Creek was completed in 2018. (OPPM ID 44953) - Original Budget $61k. $18k remaining | 2023-05-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Central-Illinois | BETHT - BET HARRISTOWN TERMINAL |  |  | 0 | 43000 |  |  |  | Karl, Marissa |  |  |  | 1 | 44949 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Other Programs
Harristown VRU Release Prevention Program | Item | Open | MCAP | BETHT00M2101 | Exempt | 1845963 | Schumacher, Chelsea | HSSE | 8. Canceled | Defined | Vapor Management | -48 |  |  | -47.9 | -48 | 0 | Green |  |  |  | -48 |  |  | 44000 |  |  |  | Full | 44000 | 0 |  | 0 | No | Green | 2021-08-01 |  |  | 2021-12-31 | 2023-11-17 |  |  |  |  | -47.9 | [18 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Operating Infrastructure |  | Central-Illinois | BETHT - BET HARRISTOWN TERMINAL |  | -48 | 0 |  |  |  |  | Karl, Marissa | Serra, William R. |  |  | 1 | 39814 |  | Meitzler, Antoinette | Independent | Aqua | 2021-04-21
Houston Office Space Relocation Security Upgrades | Item | Open | MCAP | 1348811M2105 | Exempt | 1879057 | Clark, Chris | HSSE | 6. Operational | Defined | Corporate | 102 | 5429 |  | 5530.99 | 5531 | 0 | Green |  |  |  | 5531 |  |  | 205000 |  |  | 205000 | Full | 205000 | 199571 | 5429 | 205000 | No | Green | 2021-09-01 | 2021-08-25 | 2021-08-25 | 2022-02-09 | 2022-02-09 |  |  | 101.99 | [11 empty] | 5429 | [6 empty] | 04.07/23 KB - No update 03.06.23 KB - Work on door contacts has been postponed until HVAC work is complete. The forecast has been moved to Q3. 02.06.23 KB - No change on door contacts 01.09.23 KB: Modifying contacts is still pending. Buckeye 's position is building contractor should bare the financial burden to correct. 12.07.22 KB: Correcting the contacts on the doors has been delayed until 1st Qtr. 11.07.22 KB: Still pending contacts on doors 10.10.22 KB: see notes from 9.7.22 9.7.22 KB: Still pending modifications to doors to trigger locks upon contact. 8.4.22 KDB: Badge printer installation complete. Only pending installation of additional contacts for doors. 7.11.22 KDB: Badge printer delivered pending, labor charges and remote door upgrade. 6.8.22 KDB: Delayed delivery of badges for badge printer, remote door upgrade and contacts for door closure pushed out one month. $7k additional labor to install new contacts on several doors. 5/6/22 KB | 2023-04-07 | Boyd, Kim |  | Corporate | Corporate | Corporate |  | Corporate | Corporate |  | 102 | 0 | 5429 |  | 62529 |  | Clark, Dave | Hollis, Bill |  |  | 1 | 40159 |  | Administrator, System | Independent | Aqua | 2021-05-24 | Office Relocation
Lima South VRU Carbon Replacement | Item | Open | MCAP | BETLI00M2203 | Maintenance Framework | 2010988 & 2010986 | Schumacher, Chelsea | HSSE | 7. Closed | Emergent | Vapor Management | -40701 |  |  | -40700.55 | -40701 | 0 | Green |  |  |  | -40701 |  |  | 150000 |  |  | 150000 | Full | 150000 | 143334 |  | 143334 | No | Green | 2022-08-01 | 2022-08-25 | 2022-08-25 | 2022-08-10 | 2022-09-30 |  |  | -12800.45 | -27000 | -900.1 | [16 empty] | 3.2.23 - Accrual $70,000. Working through final invoice issues (AS) 2/3/23 - Waiting on final invoices (AS) 1/5/23 - Waiting on final invoices (AS) 12/2/22 - Waiting on final invoices (AS) 11/2/22 - Waiting on final invoices (AS) 10/11/22 - Variance due to forecast change 10/6/2022 - Waiting for final invoices to close the project. 9/2/2022 - Completed week of Aug 1st. | 2023-03-02 | Schultz, Amy |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Terminals | BETLI - BET LIMA SOUTH TERMINAL |  | -40701 | 0 |  |  | 184034 |  | Karl, Marissa | Spitz, Nicholas P. |  |  | 1 | 44579 |  | Gardner, Travis | Independent | Aqua | 2022-08-12 | Other Programs
Pennsauken VRU UPS and CPU Replacement 2020 | Item | Open | MCAP | BPNQP00M2008 | Exempt | 1674243 | Schumacher, Chelsea | HSSE | 5. Deferred | Defined | Vapor Management |  | 27000 |  | 27000 | 27000 | 0 | Green |  |  |  | 27000 |  |  | 27000 |  |  | 27000 | Full | 27000 |  | 27000 | 27000 | No | Green | 2023-12-01 | 2020-01-27 | 2020-01-27 | 2020-04-15 | 2022-12-21 | [19 empty] | 27000 |  | 8/26/20 - mrk - deferred until 2021 due to requested 139k reduction in forecast. | 2020-08-26 | Schultz, Amy |  | East | Pipelines and Terminals | Operating Infrastructure |  | Pennsauken | BPNQP - BPN PENNSAUKEN TERMINAL |  |  | 0 |  | 27000 |  |  | Karl, Marissa | Klumpp, Eugene |  |  | 1 | 35788 |  | Kabaria, Erika | Independent | Aqua | 2020-01-21 | Other Programs
South Williamsport Terminal - Replace Obsolete Refrigeration VRU | Item | Open | MCAP | BETAM00M2101 | Exempt | 1902005 | Schumacher, Chelsea | HSSE | 7. Closed | Defined | Vapor Management | 3614 |  |  | 3613.81 | 3614 | 0 | Green |  |  |  | 3614 |  |  | 298000 |  | 64000 | 362000 | Supplemental | 362000 | 363341 |  | 363341 | No | Green | 2021-10-01 | 2021-10-13 | 2021-10-13 | 2021-12-10 | 2022-07-29 |  |  | 2398.9 | 107.95 | 1106.96 | [16 empty] | 1/5/23 - Waiting on final invoices (AS) 12/2/22 - Waiting on final invoices (AS) 11/2/22 - Waiting on final Invoices (AS) 7/29/22 VCU commissioned on 7/27/2022. Waiting on final invoices to close. 6/2/22 - Work expected to be completed in June. 5/12/22 - Mechanical contractor to mob. May 31st. VCU to be relocate the week of June 6th. The Air Permit to be approved 5/17. 4/4/2022 - Forecast pushed out... Still waiting on final approved air permit. 3/9/2022 - Forecast pushed out... Still waiting on final approved air permit. 2/9/2022 - Forecast pushed out... Still waiting on final approved air permit. 12/12/21 - Completed foundations and pipe support. Piping fabrication completed and hydrotested. Air Permit is still under PADEP review and not expected to be approved until Feb 2022. 7/22/2021 - completed the initial site walk with operations. Currently developing a SOW for the installation of an idled VCU.cks 10-5-2020 Updated Q2 2021 forecast. CS | 2023-01-05 | Schultz, Amy |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Terminal | BETAM - BET SOUTH WILLIAMSPORT |  | 3614 | 0 |  |  | 243259 |  | Karl, Marissa | Orischak, Bob | N/A |  | 1 | 23839 |  | Guest, ProSight | Independent | Aqua | 2017-07-12 | Other Programs
Woodhaven VRU Vacuum Pump Replacement | Item | Open | MCAP | BETWS00M2203 | Maintenance Framework | 1954878 | Schumacher, Chelsea | HSSE | 7. Closed | Drawdown | Vapor Management | 2633 |  |  | 2633.4 | 2633 | 0 | Green |  |  |  | 2633 |  |  | 59000 |  |  | 59000 | Full | 59000 | 62605 |  | 62605 | No | Green | 2022-03-01 | 2022-03-17 | 2022-03-17 | 2022-03-24 | 2022-03-24 |  |  | 0 | 2520 | 113.4 | [16 empty] | 2/3/23 - Waiting on final invoices (AS) 1/5/23 - Waiting on final invoices (AS) 12/2/22 - Waiting on final invoice from John Zink (AS) 11/2/22 - Waiting on final invoice from John Zink (AS) 10/6/2022- Still waiting on final invoice from John Zink. CKS 7/21/2022 - The replacement pump had issues and was replaced under warranty. The warranty covered the pump only and not the field work to replace. Pump replaced on 7/18. All work completed and waiting for final invoices to close. 6/2/2022 - issues with replacement pump and manufacture sent a replacement pump. Additional $5,500 to replace the pump a second time. 4/26/2022 - Pump picked up on April 12th. Still waiting on final invoice. 3/22/2022 - Pump replaced and aligned on March 21st. Will close after invoices are paid. 3/18/2022 - The replacement pump is onsite and contractor is schedule to install March 21. | 2023-04-04 | Schultz, Amy |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETWS - BET WOODDHAVEN TERMINAL |  | 2633 | 0 |  |  | 59971 |  | Karl, Marissa | Gardner, Travis W. |  |  | 1 | 43177 |  | Meitzler, Antoinette | Independent | Aqua | 2022-03-15 | Other Programs
Alignment Sheet Generator | Item | Open | MCAP |  | Exempt |  | Kralik, Ron | IT | 8. Canceled | Defined | OT & IT Field Ops |  | 0 |  | 0 | 0 | 0 | Green | 180000 | -180000 | 0 | 0 | [9 empty] | 0 | 0 | No | Green |  |  |  |  | 2023-08-18 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 0 | 0 | 0 | [5 empty] | 2/22/23: Jeff Watson reviewed with Mark Shook and confirmed that this project will be cancelled. Forecast has been adjusted accordingly. 2/7/23: GIS and Asset Integrity considering cancellation of this project. Will adjust forecast once cancellation confirmation has been received. 1/9/23: No change in status. 12/7/22 Forecast moved to 2Q-3Q 2023 due to higher priority GIS and Asset Integrity projects now proposed for 1Q2023 10/5/22: No change in status. 9/21/22: Per Steve Mengle, this project is deferred to 2023. $180k to be budgeted in 2023.//bo 9/8/22: New Century provided SaaS assessment. Still awaiting requested customer reference and rescheduled date for SW Demo. IT Ops Apps continues to have concerns about New Century's readiness to move forward with the project. 8/17/22: IT Ops Apps, GIS, and Asset Integrity met on 8/16 regarding concerns about New Century's readiness to move forward with the project. GIS will inform New Century of an 8/26 deadline to provide requested information. Forecast adjusted to reflect possibility of 2023 carryover spend. 8/5/22: Still awaiting SaaS questionnaire responses from New Century in order to schedule/proceed with ARC review. Forecast adjusted accordingly. 7/6/22: GIS and IT Operations Applications met with New Century in June to discuss vendor readiness to proceed. New Century to provide information in preparation for ARC review. 6/7/22: No change to status. 5/6/22: No change to status. 4/7/22: Due to business resource constraints, Asset Integrity has requested that we move the project to a 3Q start. Forecast has been updated accordingly. 3/3/22: Pushed out forecast to May per conversation with RK. LK 2/7/22: No change to status. 1/7/22: No change to status. 12/7/21: No change to status. 11/7/21: No change to status. 10/25/21 Update: Reduced 2022 Budget from $163,430 to $120k based on change made in Tracker by Steve M.//bo 10/8/21: No change to status. 9/8/21: Planning to submit AFE for In-line Inspection Data Integration in September. Will borrow $36K from CAS Replacement to coverbudget shortfall. ?7/8/21: Data Integration and GIS team is considering a doing a “PHMSA Mega Rule” Project before moving forward with Alignment Sheet Generator project. May result in using 2021 Alignment Sheet budget money for "PHMSA Mega Rule", and a 2022 budget request to complete Alignment Manager. Discussions continuing inJuly. -6/22/2021: Moved Cash Flow Start date to 8/01/2021 per Steve Mengle.//bo 6/7/21: Will work with Data Integration and GIS team and New Century vendor in June to confirm timeline. 5/7/21: Cash flow start forecast for 3Q. Will reach out to Derek Lutchko in May to begin work on AFE and Charter. 4/7/21 Cash flow startforecast for 3Q. Derek Lutchko has indicated he has the necessary info to complete AFE and Charter; will contact Derek in April to begin work on AFE and Charter. | 2023-02-22 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 | 0 |  |  |  | Gingras, Stephan |  |  |  | 1 | 38304 |  | Administrator, System | Independent | Aqua | 2020-08-24 | IT
Analysis Tool (AT) EOL BIRD Conversion | Item | Open | MCAP | 1348173M2207 | Exempt | 2046213 | Kralik, Ron | IT | 6. Operational | Emergent | OT & IT Field Ops | 10987 | 720 | 3691 | 11706.82 | 10428 | 1279 | Red |  |  |  | 11707 |  |  | 43000 |  |  | 43000 | Full | 43000 | 35143 | 4411 | 39554 | No | Green | 2022-12-01 | 2022-11-28 | 2022-11-28 | 2023-01-31 | 2023-01-31 |  |  | 6519.5 | 768.21 | 1840.16 | 1858.95 | 1300 | 1300 | 559 | Red |  |  | 720 | [7 empty] | 3691 | 5/4/23: SAI confirmed final invoice will be submitted in May. 4/5/23: expecting final invoicing in April. 3/6/23: expecting final invoicing in March. 2/6/23: expecting final invoicing in February. 1/9/23: Jeanette reports that work has been completed and has been tested successfully. Will promote to Prod prior to 1/15 due date. 12/722 AFE approved on 11/28. SAI360 to begin work on this in Dec 2022, | 2023-05-04 | IT |  | Corporate | Corporate | IT |  | Corporate | Corporate |  | 9128 | 2579 |  |  | 24156 |  | Gingras, Stephan | Tran, Hung |  |  | 1 | 46259 |  | Meitzler, Antoinette | Independent | Aqua | 2022-11-22 | IT
ArcGIS Portal Conversion | Item | Open | MCAP | 1348173M2105 | Exempt | 1900414 | Kralik, Ron | IT | 6. Operational | Defined | OT & IT Field Ops | 605 |  | 4625 | 605.31 | 605 | 0 | Green |  |  |  | 605 |  |  | 61000 |  |  | 61000 | Full | 61000 | 43568 | 4625 | 48193 | No | Green | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2022-01-31 | 2022-07-20 |  |  | 198.18 | 201.75 | 205.38 | [15 empty] | 4625 | 1/9/2023: No additional spend is forecast for 2023. 12/7/22: No additional spend is forecast. Will begin project closeout in December. 10/7/22: Will begin project closeout in October. 9/8/22: Will begin project closeout in September. 8/5/22: GIS met with IT Security on 7/19 to review 3rd party connection issues; firewall ruleset updates have resolved all connection issues. Will begin project closeout in August. 7/6/22: GIS working with Infrastructure Ops to setup local SQL authentication accounts, which is expected to address performance issue. GIS will meet with IT Security in mid-July to review reverse proxy setup as it relates to 3rd party connection issues. 6/7/22: Project team to coordinate a workshop with IT Infrastructure in June to resolve remaining data connection and performance issues. 5/6/22: GIS Team looking for IT assistance to research/resolve several data connection and performance issues. Project team to coordinate a workshop with IT Infrastructure in May to resolve these remaining issues. 4/7/22: GIS Team has identified a SQL access method to substantially minimize the manual effort to republish/repoint assets to the web portal from existing GISP1 server; server federation will not be required. GIS Team looking for IT assistance to research/resolve several data connection and performance issues. Project team to coordinate a workshop with IT Infrastructure to resolve these remaining issues. 3/7/22: GIS Team investigating Server federation and per app VPN options to reduce post-project migration effort. 2/7/22: Esri "ArcGIS Enterprise Jumpstart" completed Jan 18-20. GIS Team investigating Server federation to reduce post-project migration effort. 1/9/22: Server builds completed on 1/7. GIS DB Upgrade to SQL Server 2016 completed on 1/8. Esri "ArcGIS Enterprise Jumpstart" is scheduled for Jan 18-20. 12/7/21: Esri "ArcGIS Enterprise Jumpstart" is scheduled for Jan 18-20. Jumpstart planning uncovered the need to upgrade the GIS DB to SQL Server 2016; the upgrade will result in an additional $7K in project costs. Infrastructure team scheduled to complete server setup and DB upgrade workin January. 11/7/21: Esri "ArcGIS Enterprise Jumpstart", is tentatively planned for December; Esri working to identify technical resource to perform Jumpstart. Infrastructure team to resume server setup work in November. 10/8/21: obtained ARC approval on 9/8, AFE approval on 9/29. 9/8/21: No change to status. 8/6/21: No change to status. 7/6/21 Cash flow start forecast for 4Q. 6/7/21 Planning meetings held in May with Data Integration and GIS team, IT, and Esri to discuss proposed architecture options. 6/11 meeting scheduled with Data Integration and GIS team, IT, and Esri on 6/11 to discuss proposed server configuration, IT security , and mobile app usage. 5/7/21 Cash flow start forecast for 3Q. 4/7/21 Cash flow start forecast for 3Q. | 2023-01-09 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 605 | 0 |  |  | 9383 |  | Gingras, Stephan | Shook, Mark B. |  |  | 1 | 35176 |  | Kabaria, Erika | Independent | Aqua | 2019-09-18 | IT
Asset Management, CMDB, Service Identification and Vuln Class | Item | Open | MCAP |  | Exempt |  | Gingras, Stephan | IT | 1. Proposed |  | Infrastructure & IT Ops |  | 900000 |  | 900000 | 200000 | 700000 | Red | 200000 |  | 200000 | 700000 | [9 empty] | 900000 | 900000 | No | Green | 2023-08-01 |  |  |  | 2023-12-31 | [15 empty] | 50000 | 50000 | 50000 | 25000 | 725000 |  | 5/8/23 Project Expected to increase in cost and forecast updated. SG 4/11/23: PER JL, changed Cash Flow Start date to Aug.//bo Larger Discussions for Ownership forecast migrated to Q2, SG | 2023-05-08 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 | 100000 | 800000 |  |  | Gingras, Stephan |  |  |  | 1 | 45492 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
Azure DR | Item | Open | MCAP | 1348179M2206 | Exempt | 2045633 | Gingras, Stephan | IT | 6. Operational | Emergent | Infrastructure & IT Ops | 938 |  |  | 937.65 | 938 | 0 | Green |  |  |  | 938 |  |  | 34000 |  |  | 34000 | Full | 34000 | 25612 |  | 25612 | No | Green | 2022-12-01 | 2022-11-18 | 2022-11-18 | 2022-12-31 | 2023-01-27 |  |  | 937.65 | [18 empty] | 1/31/2023 Devices installed and Tested. SG 12/30/22 Kick-off happened in 2022 and will be completed in Jan. SG 12/5/22 - Adjusted forecast for equipment expected to arrive in late December | 2023-02-08 | IT |  | Corporate | Corporate | IT |  | Corporate | Corporate |  | 938 | 0 |  |  | 24675 |  | Gingras, Stephan | Tran, Hung |  |  | 1 | 46243 |  | Meitzler, Antoinette | Independent | Aqua | 2022-11-17 | IT
Backup Lifecycle Refresh Program 2022 | Item | Open | MCAP | 1348172M2201 | Exempt | 1957073 | Geier, John | IT | 6. Operational | Defined | Infrastructure & IT Ops | 3000 |  | 1465 | 3000.46 | 3000 | 0 | Green |  |  |  | 3000 |  |  | 25000 |  |  | 25000 | Full | 25000 | 25859 | 1465 | 27324 | No | Green | 2022-04-01 | 2022-03-25 | 2022-03-25 | 2022-12-31 | 2023-01-31 |  |  | 2106.2 | 894.26 | [16 empty] | 1465 | 2/5/23: Updated Feb '23 forecast one remaining invoice. Will close out by EOM - JG 1/23/23: Updated Operational Date from 11/30/2023 to 1/31/2023 based on Forecast.//bo 12/30/22-Moved away from 3 boot controllers due to availability. PO in place for 4 SSD drives and a single boot device. Forecast updated - JG 12/7/22 - Forecast updated to account for remaining controllers that are still pending 10/27/22 - Forecast and schedule remain the same no new updates this month. 9/30/22 - Forecast and schedule remain the same no new updates this month. 9/1/22 - Forecast and schedule remain the same no new updates this month. 8/1/22 - Forecast and schedule remain the same no new updates this month. 7/5 - Forecast and schedule remain the same no new updates this month. 6/3 - Forecast and schedule remain the same no new updates. 5/2 - We were very fortunate to get one server in early as this was forecasted to come in during June. Forecast has been adjusted to reflect this early arrival. 4/5/22 - AFE has been approved and the equipment has been ordered. Forecast updated to reflect this. 3/7/22 - Steve is getting the most updated quotes for this project and this will not kick off in Q1. We do meet every Tuesday to review this project as a team. The forecast is up to date. 2/4/22 - I met with Steve on 2/2 to start to gather quotes and work on the Project Charter. Steve is getting the most updated quotes for this project and this will not kick off in Q1. 1/3/22 - This is the Backup Lifecycle Refresh Program for 2022. I will work with Steve on getting the most updated quote for this project and building out a schedule and charter and submitting the AFE for this project. This will not kick off in Q1. | 2023-02-06 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 3000 | 0 |  |  | 22859 |  | Gingras, Stephan |  |  |  | 1 | 41715 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
Backup Solution Replacement | Item | Open | MCAP |  | Exempt |  | Geier, John | IT | 1. Proposed |  | Infrastructure & IT Ops |  | 300000 |  | 300000 | 300000 | 0 | Green | 600000 | -300000 | 300000 | 0 | [9 empty] | 300000 | 300000 | No | Green | 2023-06-01 |  |  |  | 2023-11-30 | [13 empty] | 200000 | 50000 |  |  | 50000 |  |  |  | 4/10/23 - Forecast spend start pushed to May // jg 2/9/22 Budget Reduced to match expected Spend. SG | 2023-04-10 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 200000 | 50000 | 50000 |  |  | Gingras, Stephan |  |  |  | 1 | 45476 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
Bank Interface App | Item | Open | MCAP | 1348174M2205 | Exempt | 2036775 | Bartlett, Hilary | IT | 3. Active | Defined | Enterprise Business Apps | 36046 | 42000 | 9632 | 78045.85 | 68890 | 9156 | Red |  | 80000 | 80000 | -1954 |  |  | 131000 |  |  | 131000 | Full | 131000 | 62530 | 51632 | 114162 | No | Green | 2022-10-01 | 2022-10-12 | 2022-10-12 | 2023-02-28 | 2023-06-30 |  |  | 5522.96 | 6694.36 | 14772.55 | 9055.98 | 15000 | 15000 | -5944 | Red |  | Buckeye/Customer Schedule | 26000 | 16000 | [6 empty] | 9632 | 5/4/23: Adjusted forecast to reflect additional licensing fees through June.//HB (reclass to be submitted in May.//bo) 4/7/23: Adjusted forecast to reflect change in schedule. New completion date of 6/30 due to late start. 3/6/23: Feb variance based on late start with vendor; forecast updated based on work to be completed (testing and vendor configuration) No change to schedule HB 2/6/23: Labor hours under reported; addressing with project team to report going forward HB 1/4/23: Updated forecast; delay with vendors & EOY activities. HB 12/1/22: Updated forecast to reflect kickoff & schedule. HB 11/9/22 - Delay due to onboarding and schedule. DC 10/18/22: Budget change based on schedule and onboarding vendor, HB 9/8/22: No change to forecast at this time. 8/25/22 Moved forecast to Q4 per LK, SG 8/5/22: This will be a Q4 2022 project. -6/09/2022: Shifted forecast to October Cash Flow Start date.//bo -4/06/2022: Shifted forecast to June Cash Flow Start date.//bo | 2023-05-09 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 26990 | 51056 |  |  | 26484 |  | Gingras, Stephan | Gardner, Dale |  |  | 1 | 42138 |  | Clark, David | Independent | Aqua | 2021-09-11 | IT
BBH TMS7 | Item | Open | MCAP |  | Exempt |  | Gay, Elena | IT | 4. On-Hold |  | OT & IT Field Ops |  | 75000 |  | 75000 | 75000 | 0 | Green | 75000 |  | 75000 | 0 | [9 empty] | 75000 | 75000 | No | Green | 2023-07-01 |  |  |  | 2023-10-31 | [14 empty] | 15000 | 20000 | 20000 | 20000 | [7 empty] | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 | 55000 | 20000 |  |  | Gingras, Stephan |  |  |  | 1 | 45477 |  | Administrator, System | Independent | Aqua | 2022-08-30 | IT
BIRD IH Module | Item | Open | MCAP | 1348173M2303 | Exempt |  | Kralik, Ron | IT | 2. Pending AFE | Defined | OT & IT Field Ops |  | 76500 |  | 76500 | 80500 | -4000 | Yellow | 80500 |  | 80500 | -4000 |  |  | 50207 |  |  |  | Full | 50207 |  | 76500 | 76500 | No | Green | 2023-05-01 |  |  | 2023-06-18 | 2023-06-18 | [6 empty] | 4000 | 4000 | -4000 | Red |  |  | 26834 | 26833 | 22833 | [6 empty] | 5/4/23: AFE review held with IT Ops Management on 4/28; approval for AFE routing was provided. AFE amount is $50K; will reduce forecast accordingly from full budget amount once AFE is approved. 4/6/23: Due to delays in BIRD SaaS Migration Planning (to research possible additional AFE costs), IH Module now planned to start in April (prior to BIRD SaaS). Forecast adjusted accordingly. 3/7/23: Shifting forecast 1 month due to dependency on BIRD SaaS Migration. 2/7/23: No change in status/forecast. 12/7/22: Forecast moved to 2Q2023 to accommodate higher priority BIRD efforts in 1Q2023 (SaaS Migration and AT EOL) 5/31/22: Will be deferred to 1Q2023, per Steve Mengle. 1/10/22: Updated Cash Flow Start Date to 7/01/2022 based on Tracker.//bo 9/6 - Deferred to 2022 - DB 10/28/2020 Update: Deferred from 2021 to 2022.//bo 10/7 - Same as August. 9/2 - Same as August. 8/4 - This is being moved to 2021. I will keep the current charter and business case in BW so we are ready to go in 2021. 7/1 - This is being moved to 2021. I emailed Cliff Lester and copied Lauren letting him know that this decision has been made. I will keep the current charter and business case in BW so we are ready to go in 2021. 6/8 - Doug Markel and myself had a planning meeting a couple of weeks ago with Meridith Wilson and Tim Manning and the Houston Cintellate IH team. They have hired their IH Specialist Cliff. Based on our previous meeting with the management team and with the coronavirus outbreak, we are moving this project's financials to Q3 for now. Doug and the team met with SAI for a demo of this Cintellate software. Once Cliff and the team feel they are ready for the next steps and he is fully acclimated, they will reach out to me to discuss the equipment needed to purchase. I have kept Chris Parker in the loop every step of the way. 5/1 - They have hired their IH Specialist. Based on our meeting with Dale and the management team and with the coronavirus outbreak, we are moving this project to Q3 for now. I have updated my financials to reflect this. I have a planning meeting scheduled with the team on May 7th. 3/31 - I received an email from Meridith Wilson and Tim Manning that we can push this out to Q3. They have hired their IH Specialist. Based on our meeting with Dale and the management team and with the coronavirus outbreak, we are moving this project to Q3 for now. I have updated my financials to reflect this. 2/28 - No new updates as they are still in the process of hiring an IH Specialist now for this project. 1/31 - This is the newCintellate IH Module project for 2020. I have the businesscase completed. Doug reached outto Jeanette to find out why our strategy meeting got cancelled on 1/30, and they saidthey arein the process of hiring an IHSpecialist now for this project. I will make sure to adjust all the financial updates to reflect this. I spoke with Tim Manning on the phone an he said thenew person they will hire, will need some training and this is more likely to start April/May 2020. | 2023-05-04 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 53667 | 22833 |  |  |  | Gingras, Stephan | Kasdano, Lauren |  |  | 1 | 35311 |  | Kabaria, Erika | Independent | Aqua | 2019-10-03 | IT
BIRD Migration to SaaS | Item | Open | MCAP | 1348173M2305 | Exempt |  | Kralik, Ron | IT | 2. Pending AFE | Defined | OT & IT Field Ops |  | 117000 |  | 117000 | 120000 | -3000 | Yellow | 120000 |  | 120000 | -3000 |  |  | 85839 |  |  |  | Full | 85839 |  | 117000 | 117000 | No | Green | 2023-05-01 |  |  | 2023-07-21 | 2023-07-21 | [6 empty] | 3000 | 3000 | -3000 | Red |  |  | 25000 | 25000 | 67000 | [6 empty] | 5/4/23: AFE review held with IT Ops Management on 5/4. Planning to route AFE for approval in May. AFE amount is $86K; will reduce forecast accordingly from full budget amount once AFE is approved. 4/6/23: ARC/ARB review process identified potential additional labor costs (for BOOMI configuration and BI Reporting adjustments to use SAI reporting API). Working with EA and BI Teams to gather additional costs for inclusion in AFE. AFE submission now expected for April. Forecast shifted 1 month, and full budget amount now included in forecast, due to uncertainty over AFE costs. 2/6/23: ARC/ARB review and approval, AFE submission will occur in March. Forecast shifted 1 month. 2/6/23: Expecting to complete ARC/ARB review and approval and AFE submission in February. 1/9/23: Expecting to complete ARC review and AFE submission in January. 12/7/22: HSSE has requested that this project be started in January 2023. Refresh quote from SAI has been requested, forecast moved to 1Q-2Q 2023. | 2023-05-04 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 50000 | 67000 |  |  |  | Gingras, Stephan | Kasdano, Lauren |  |  | 1 | 45493 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
BIRD Risk Management Module | Item | Open | MCAP | 1348173M2205 | Exempt | 2036691 | Kralik, Ron | IT | 3. Active | Defined | OT & IT Field Ops | 26098 | 36574 | 0 | 62672.47 | 62493 | 180 | Yellow | 15000 |  | 15000 | 47672 |  |  | 70000 |  |  | 70000 | Full | 70000 | 35602 | 36574 | 72176 | No | Green | 2022-10-01 | 2022-10-11 | 2022-10-11 | 2023-02-10 | 2023-06-23 |  |  | 6051.29 | 3088.32 | 9349.13 | 7609.73 | 13801 | 13801 | -6191 | Red |  |  | 17402 | 19172 | [6 empty] | 0 | 5/4/23: HSSE scheduling conflicts in May will push UAT to June. 4/6/23: Two CRs will increase forecast spend:: $6450 CR approved on 3/21 to include Incident risk Assessment, and $6370 CR pending approval as of 4/6 to cover increased SAI costs per revised estimate after final specifications update on 3/31. Forecast has been adjusted accordingly to reflect this $12,820 in increased costs. 3/7/23: HSSE and SAI analysis in February to determine that a financial change order will not be required, and to refine project scope, resulted in reduced February spend vs forecast. Forecast has been adjusted accordingly. 2/7/23: HSSE is reviewing SAI workshop feedback to determine whether a change request will be needed. Will update forecast once this has been determined. 1/9/23: HSSE to review / sign off on Specifications in January. SAI reviewing feasibility of doing this project concurrently with BIRD Migration to SaaS. 12/7/22: Forecast adjusted in 4Q2022 and 1Q2023 to accommodate higher priority BIRD efforts in 1Q2023 (SaaS Migration and AT EOL) 11/7/22: AFE approved in October. Project kickoff to occur in November. 10/6/22: AFE Routed for approval. Cash flow expected to begin in October. 9/8/22: SAI to provide updated SOW by 9/9. 8/17/22: SAI to provide updated SOW and feedback regarding workplan option by 8/19. Forecast adjusted to account for possibility of 2023 carryover. 8/5/22: Awaiting SAI revisions to SOW and determination about whether the workplan option can be used for the Risk Management Module implementation. Forecast adjusted accordingly. 7/6/22: Draft AFE and Charter has been developed. HSSE is meeting with SAI in mid-July to discuss updates to the proposed SOW. Based on preliminary discussions with HSSE, final AFE costs are expected to be less than the $80K budgeted for the project. Forecast adjusted accordingly. 7/6/22: Draft AFE and Charter has been developed. HSSE is meeting with SAI in mid-Julyto discuss updates to the proposed SOW. Based on preliminary discussions with HSSE, final AFE costs are expected to be less than the $80K budgeted for the project. Forecast adjusted accordingly. 6/7/22: AFE, Charter being developed. Expecting AFE submission in June. | 2023-05-04 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 18489 | 44184 |  |  | 9504 |  | Gingras, Stephan | Gardner, Dale |  |  | 1 | 41710 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
Booth TAA System Upgrades | Item | Open | MCAP | BH00000M2204 | Exempt | 1956978 | Gay, Elena | IT | 6. Operational | Emergent | OT & IT Field Ops | 1287 |  |  | 1287.43 | 986 | 302 | Red |  |  |  | 1287 |  |  | 63000 |  |  | 63000 | Full | 63000 | 63513 |  | 63513 | No | Green | 2022-05-01 | 2022-03-24 | 2022-03-24 | 2022-05-01 | 2022-10-14 |  |  | 395.27 | 292.47 | 297.98 | 301.71 |  |  | 302 | Red | [11 empty] | 8-2-2022 - (EG) PC delay has delayed work getting started. Not expecting to invoice until next month. Moved forecast to future months. 7-5-2022 - EG Project is underway but experiencing delays due to hardware supply chain issues. Everything is ordered just waiting on delivery. 6-1-2022 EG - Delay in receiving the updated quotes and approval for solution. Moved forecast to July. 5-3-2022 EG - there is an issue with an expired MSA that the legal departments are in the process of reviewing and getting signed. No work was done in April due to this. Shifted forecast to June as start date is pending legal review. | 2022-08-09 | IT |  | East | Pipelines and Terminals | IT |  | Booth | BH - BOOTH STATION |  | 986 | 302 |  |  | 62226 |  | Gingras, Stephan | Parker, Brian K. |  |  | 1 | 43189 |  | Meitzler, Antoinette | Independent | Aqua | 2022-03-17 | IT
Broadway I & II - PlantPAx Upgrade Project | Item | Open | MCAP | 1348181M2303 | Exempt | 2111238 | Gay, Elena | IT | 3. Active | Defined | OT & IT Field Ops | 851 | 319800 |  | 320650.87 | 321900 | -1249 | Yellow | 332900 |  | 332900 | -12249 |  |  | 320369 |  |  | 320369 | Full | 320369 | 851 | 319800 | 320651 | No | Green | 2023-04-01 | 2023-04-18 | 2023-04-18 | 2023-09-30 | 2023-12-31 | [5 empty] | 850.87 | 0 | 0 | 851 | Red |  |  | 56000 | 50000 | 85000 | 55000 | 40000 | 33800 | 0 | 0 |  | 4/10/23: Per EG, variance to previous forecast ($11k) due to not planning on using Contingency.//bo 1-25-2023 EG - updated forecast | 2023-04-10 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 106851 | 180000 | 33800 |  |  | Gingras, Stephan | Parker, Brian K. |  |  | 1 | 45486 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
BTP – OT Domain Control For Process Controls Network 2022 | Item | Open | MCAP | BTXPP00M2213 | Exempt | 2011995 | Gay, Elena | IT | 6. Operational | Defined | OT & IT Field Ops | 8872 |  |  | 8872.14 | 12948 | -4076 | Red |  |  |  | 8872 |  |  | 203000 |  |  | 203000 | Full | 203000 | 138828 |  | 138828 | No | Green | 2022-09-01 | 2022-08-11 | 2022-08-11 | 2022-12-18 | 2022-12-18 |  |  | 1085.43 | 8484.08 | 3378.66 | -4076.03 |  |  | -4076 | Red | [11 empty] | 11-8-2022 - Project is expected to come in under budget at around $171K - adjusted forecast 11-29-2022 - Project is coming in under budget. Adjusted forecast. | 2022-12-08 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 12948 | -4076 |  |  | 129956 |  | Gingras, Stephan | Painter, P. Russell |  |  | 1 | 41701 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
BTP DeltaV Cyber Security, Software 14.3.1 and Controllers Upgrade 2022 | Item | Open | MCAP | BTPTSV0M2201 | Exempt | 1956625 | Gay, Elena | IT | 3. Active | Defined | OT & IT Field Ops | 186814 | 336941 |  | 523754.79 | 513003 | 10751 | Yellow | 320000 | 234000 | 554000 | -30245 |  |  | 559000 |  |  | 559000 | Full | 559000 | 205195 | 336941 | 542136 | No | Green | 2022-04-01 | 2022-03-18 | 2022-03-18 | 2022-10-15 | 2023-10-13 |  |  | 84.79 | 298.81 | 175678.88 | 10751.31 | 0 | 0 | 10751 | Red |  |  | 0 | 0 | 0 | 200000 | 77661 | 59280 |  |  |  | 5/1/23 - HW vendor is configuring and SW not implemented until July-Sept. Forecast reflects changes. Vendor resource constraints reason for calendar gap. (EG) 4/11/23: Per EG, Vendor decisions are undecided due to Cyber Security portion.//bo 4-4-2023 (EG) - Accrued for $176K but will be under forecast due to internal work has not started due to hardware delays. Adjusted forecast for July and August to reflect installation and software implementation timeline. 1-25-2023 EG Some spreadsheets are showing C/O $320K but project is expected to spend AFE remaining amount of $540K. Actuals for 2022 were only $18K. Delays due to Hardware as previously reported. Forecast to reflect $540. 12-8-2022 EG - Project is still targeted to start in 2023 and we are still waiting on the Hardware. Adjusted forecast to reflect anticipated spend - Did not spend the $60K. 8/17/22: Forecast updated after Elena and team confirmed with vendor. $60k remaining in 2022 and $437k moved to 2023.//bo 8-4-2022 EG - vendor not able to acquire hardware and need to now find a new vendor. Will not be billing for the $70K I have been accruing for. 6-1-2022 EG - vendor has updated that Hardware ETA is now not expected until December 2022. Some software work can occur and moved forecasts into 2023. Will have to fine tune forecasts in Sept when updates to shipping are updated. Delays due to supply chain issues. 5-3-2022 EG - vendor billing 20% of invoice. Moving future months forecasts due to equipment is delayed in shipping and not all is expected to be received until September. Working this week on revised timelines to accurately update forecast. 4-4-2022 EG - Project is underway but had later than expected start. 6-24-21 - Renamed project. Original project name was "BTP Delta V Cyber Security/Backup and Disaster Recovery Plan/DeltaV Mobile" //LK -6/23/2021: Updated funds to $571.9k for 2022 based on email from Darbyn. Combined with other project. Need to change name in OPPM.//bo 10/15/2020 - Project deferred to 2022 based on GMT Operations Management. Deferment cost increased by 5% to account for anyCPI increase that may occur from Vendors, software or services. from 120K to 126K.(note from Angel from BrightWork).//bo | 2023-05-01 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 176062 | 10751 | 277661 | 59280 | 18381 |  | Gingras, Stephan | Burke, Kevin |  |  | 1 | 38297 |  | Administrator, System | Independent | Aqua | 2020-08-24 | IT
BTP Insight Blackbox Hardware and Software Upgrade | Item | Open | MCAP |  | Exempt |  | Gay, Elena | IT | 1. Proposed |  | OT & IT Field Ops |  | 15000 |  | 15000 | 15000 | 0 | Green | 15000 |  | 15000 | 0 | [9 empty] | 15000 | 15000 | No | Green | 2023-06-01 |  |  |  | 2023-07-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 10000 | 5000 | [6 empty] | 5/08/23: Changed Operational Date to 7/31/23 from 6/01/23 based on OPPM Forecast.//bo | 2023-05-08 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 10000 | 5000 |  |  |  | Gingras, Stephan |  |  |  | 1 | 45487 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
BTP SILAlarm Hardware Upgrade | Item | Open | MCAP |  | Exempt |  | Gay, Elena | IT | 1. Proposed |  | OT & IT Field Ops |  | 12000 |  | 12000 | 12000 | 0 | Green | 12000 |  | 12000 | 0 | [9 empty] | 12000 | 12000 | No | Green | 2023-08-01 |  |  |  | 2023-09-29 | [15 empty] | 10000 | 2000 | [8 empty] | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 | 12000 |  |  |  | Gingras, Stephan |  |  |  | 1 | 45488 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
CAS Replacement (Pipeline Scheduler) | Item | Open | MCAP | 1348173M1902 | Exempt | 1632767 | Gingras, Stephan | IT | 3. Active | Defined | OT & IT Field Ops | 254177 | 657898 |  | 912074.58 | 795523 | 116552 | Red | 758051 |  | 758051 | 154024 |  |  | 5199000 |  |  | 5199000 | Full | 5199000 | 3308893 | 707898 | 4016791 | No | Green | 2020-01-01 | 2019-09-30 | 2019-09-30 | 2022-07-30 | 2024-01-31 |  |  | 50278.9 | 45481.5 | 64992.48 | 93423.7 | 65247 | 65247 | 28177 | Red |  | WorkAhead of Schedule | 88543 | 88355 | 86000 | 86000 | 84000 | 75000 | 75000 | 75000 |  | 5/5/2023 Rollout going as expected and forecast updated based on expected CR for the project. SG 4/1/2023 forecast adjusted in April for CRs. SG 1/31/2023 UAT has been extended to March to accommodate limited resources in Transportation. SG 12/30/2022 Unit testing complete and UAT to start 1/3/23. The schedule and budget remain the same. SG 11/30/2022 Project on Track and Budget, Forecast increased for Monitors to fit the UI. SG 10/31/2022 Project on Track and Unit Testing Started, Budget variance based on lower than expected run rate. SG 9/30/2022 CR9 and Project on track. SG 8/31/2022 CR9 in progress, defect resolution in progress. SG 8/24/2022 2023 budget changes with possible contract resource added. SG 7/29/2022 CR9 for Laurel line reversals has been approved. The forecast has been updated to reflect the schedule and cost changes. Desk Rollout starting 1/2023. SG 6/30/2022 UAT will be delayed with a expected CR9, budget up[dated with CR9 costs. Junes fore cast variance based on Westshore reclass. SG 4/27/2022 April forecast underspent due to run rate and resource contention. Overall Project schedule delayed 3+ months. Forecast shifted with delay in UAT, $75K to be removed from year budget for Terminal Charge Record Reconciliation Report. SG 3/31/2022 On budget/ monthly variance due to extra testing and additional resource time. SG 2/28/2022 PLS Budget variance based on CR that was not billed in Jan and delivered/approved in February. March and future forecast updated to match previous schedule delays. SG 1/31 Finishing Defect resolution, Testing and rollout to start in June. SG 12/31 Schedule changed to reflect vendor defect resolution rate. SG 11/30 Emerson near the end of high priority defects and ready to finish UAT. SG . 10/29 Emerson missed milestone and Completing CRs lead to a 51K shortfall in actuals. Schedule in flux and may be extended 3 months. SG 9/30 Possible shift in UAT and overall project Schedule pending defect resolution from Emerson. SG 8/31 UAT progresses, CRs are approved, on schedule and budget. SG 7/30 UAT 2 in progress 100% of the pipelines have been tested with 56 defects found and 20 are required to be completed before UAT 3. Schedulers will be testing in UAT 3. UAT Extended to end of October with not change to the end of the project. 6/30 On Scheduleand Budget, UAT in process. SG 5/31 On schedule and Underbudget, UAT 52% complete first pass.SG 4/30 Schedule Updated based on resources, Unit Testing Complete, Some defect reaming and are being worked throughduring UAT. SG 4/27/2021 Budget Adjustedbased on forecast for schedule delay from Aug to October 2022. Current activities not affected only rollout based on resource constraints.SG3/29 On Budget and time. Working through unit testing before UAT starts in May. SG 3/8 On budget and time. Plan to finish development thismonth. SG 2/8 On time and budget SG 1/5 Forecasted updated based on milestones and resource allocation. SG 12/9 Status report- On time and budget working ondevelopment items and writing UAT Test Scripts SG 11/9 On time and Budget, CR approved 10/11 Milestone delayed 1 month, OctoberIteration and CR Dev Work Completed, Work to be completed - Interface testing, Updating Synthesis, Reviewing Dev for Milestone #4 SG 10/8 on time and budget pending CR negotiations SG 8/31 On timeand budget all deskconfiguration have been delivered, budget updated base on milestones, August Forecast to actuals off Due to double billing by Emerson and Reclass from West Shore in August Instead of September. Updated November forecast for possible CR. SG 7/31/20 on time and budget, removed $10k for chit chat project and move $65k to November from September. 6/30 on time and budget Working through the configuration of pipelines. Next month - Review User Guide, Continued Pipeline Configuration Testing, June Development Iteration 5/29On time and budget. Working on PLS Development and Desk group configuration. 4/29 ON Budgetand Time. Budget Updated for May. SG 4/9 Budget Updated due to low resource run rate. Project on schedule. SG 3/23 Project on schedule SG 10/08 - Required CEO signoff on AFE; AFE and contract approved spend to occur in Q4SFD Project to finish by 7/31/2021 12/11 Project on Budget and Schedule 12/31 Global Nomination Development is next all other tasks are on time and on budget1/31 on budget and on schedule asset modeling completed and beginning to configure assets, beginning global nomination Work completed: Model Individual Assets Completed 1/23 Global Nomination Development 1/6. Looking forward to the first iteration of the development cycle which includes 'User Stories' and demo of completed development items. First iteration on 1/31 Work Planned: Global Nomination Development Iteration(1) 1/31 User Story Review Weekly demos/meetings to see development and provide feedback Training Plan 2/28 Test Plan 3/13Configuring Individual Assets 8/30(8 Month Duration) 3/9 Budget Updated to reflect new milestone dates. No Change to over all project schedule. SG | 2023-05-05 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 160753 | 270322 | 256000 | 225000 | 757888 | 50000 | Gingras, Stephan | Arnold, David |  |  | 1 | 24862 |  | Administrator, System | Independent | Aqua | 2017-08-08 | IT
CheckPoint Server Refresh | Item | Open | MCAP | 1348171M2201 | Exempt | 2037523 | Geier, John | IT | 3. Active | Emergent | Infrastructure & IT Ops | 2280 |  |  | 2280.18 | 3939 | -1659 | Red |  |  |  | 2280 |  |  | 128000 |  |  | 128000 | Full | 128000 | 113984 |  | 113984 | No | Green | 2022-11-01 | 2022-10-21 | 2022-10-21 | 2022-12-31 | 2023-05-31 |  |  | 678.98 | 524.95 | 534.78 | 541.47 | 2200 | 2200 | -1659 | Red | [11 empty] | 5/5/23 - Prof Serv works remains in progress. // jg 4/6/23 - Prof Serv works remains in progress. // jg\ 3/7/2023 - Engaged professional services to assist in completing installation. // jg 2/22/23 - Updated March forecast for Prof Svc PO. //JG 2/17/23: Charges from Checkpoint Log Server will be coded to this project since Equipment was already purchased on this AFE in 2022. $110k not needed for 2023 Budget.//bo 2/5/23 - All equipment on PO received. Closing project out by EOM // JG 12/30/22 - Operational date and forecast updated for use of professional services support - JG 12/7/22 -Equipment arrived in November 10/24/22 - Initial forecast and PO submitted | 2023-05-05 | IT |  | Corporate | Corporate | IT |  | Corporate | Corporate |  | 1739 | 541 |  |  | 111704 |  | Gingras, Stephan | Gehringer, Todd |  |  | 1 | 46095 |  | Meitzler, Antoinette | Independent | Aqua | 2022-10-20 | IT
CheckPoint Spark | Item | Open | MCAP | 1348171M2202 | Exempt | 2037524 | Geier, John | IT | 6. Operational | Emergent | Infrastructure & IT Ops | 450 |  |  | 450.37 | 450 | 0 | Green |  |  |  | 450 |  |  | 80000 |  |  | 80000 | Full | 80000 | 73217 |  | 73217 | No | Green | 2022-11-01 | 2022-10-21 | 2022-10-21 | 2022-12-31 | 2023-01-31 |  |  | 450.37 | [18 empty] | 2/5/23 - All equipment on PO received. Closing project out by EOM // JG 12/30/22 - Operational date and forecast updated for use of professional services support - JG 12/20/22 - Equipment came in early. No supplemental AFE needed. Forecast for December is incorrect 12/7/22 - No changes to schedule or forecast 10/24/22 - initial forecast and PO submitted | 2023-02-22 | IT |  | Corporate | Pipelines and Terminals | IT |  | Corporate | Corporate |  | 450 | 0 |  |  | 72767 |  | Gingras, Stephan | Gehringer, Todd |  |  | 1 | 46104 |  | Meitzler, Antoinette | Independent | Aqua | 2022-10-20 | IT
Cisco Unified Communication Installs 2023 (MCAP) | Item | Open | MCAP | 1348183M2301 | Exempt | 2120143 | Schneider, David | IT | 3. Active | Defined | Infrastructure & IT Ops |  | 47640 |  | 47640 | 47200 | 440 | Yellow | 50000 |  | 50000 | -2360 |  |  | 53171 |  |  | 53171 | Full | 53171 |  | 47640 | 47640 | No | Green | 2023-05-01 | 2023-05-04 | 2023-05-04 | 2023-08-11 | 2023-08-31 | [6 empty] | 200 | 200 | -200 | Red |  |  | 12772 | 13806 | 12045 | 9017 | [5 empty] | 5/5/23: AFE approved. Forecast updated. 4/7/23: AFE, Business Case & IT Charter pending review & approval before submitting into workflow for approval. Forecast updated based on AFE approval. 2/7/23: Project to be started in Q2. | 2023-05-05 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 26578 | 21062 |  |  |  | Gingras, Stephan | Virupakshi, Sudhakar |  |  | 1 | 45470 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
Condition-Based Safety App | Item | Open | MCAP | 1348173M2103 | Exempt | 1877589 | Kralik, Ron | IT | 6. Operational | Emergent | OT & IT Field Ops | 309 |  | 4374 | 309.23 | 309 | 0 | Green |  |  |  | 309 |  |  | 53000 |  |  | 53000 | Full | 53000 | 33527 | 4374 | 37901 | No | Green | 2021-08-01 | 2021-08-06 | 2021-08-06 | 2021-09-24 | 2022-07-20 |  |  | 153.23 | 156 | [16 empty] | 4374 | 2/6/2023: No additional spend is forecast for 2023. 1/9/2023: No additional spend is forecast for 2023. 12/7/22: Final AppIt-related issued have been resolved. No additional spend is forecast. Will begin project closeout in December. 10/7/22: AppIt vendor continuing to research post-production issues; will complete project closeout once AppIt has resolved issues. 9/8/22: AppIt vendor continuing to research post-production issues; will complete project closeout once AppIt has resolved issues. 8/5/22: AppIt vendor continuing to research post-production issues; will complete project closeout once AppIt has resolved issues. 7/6/22: AppIt vendor is researching several post-production issues; will complete project closeout once AppIt has resolved issues. 6/7/22: Planning to complete project closeout activities in June. 5/6/22: Planning to complete project closeout activities in May. 4/7/22: Deployment completed on 3/28. Project closeout activities to begin in April. 3/7/22: UAT completion and deployment planned for the week of 3/7/22. 2/7/22: Priority comments feature completed on 2/3. UAT and Prod deployment planned for February. 1/7/22: Additional development requested to implement priority comments feature; UAT to occur in January, Prod deployment planned for February. 12/7/21: UAT to occur in December. Prod deployment planned for January. 11/7/21: AppIt development work is complete, UAT planned for November. 10/8/21: Revised target date of 10/31 for AppIt to complete app development work / UAT. BI dashboard work (as needed) to begin once app development is complete. 9/8/21: App Hierarchy requirements confirmed by HSSE on 8/30. BI, Network Security, and Infrastructure Teams have successfully established Azure-Azure connection needed for BI Reporting. 8/6/21: AFE approved on 8/6. | 2023-02-07 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 309 | 0 |  |  | 8451 |  | Gingras, Stephan | Wilson, Meridith B |  |  | 1 | 41028 |  | Perry, Betty | Independent | Aqua | 2021-08-04 | IT
EC/Terminal Scheduling Tool Consolidation | Item | Open | MCAP |  | Exempt |  | Gay, Elena | IT | 1. Proposed |  | OT & IT Field Ops |  | 200000 |  | 200000 | 200000 | 0 | Green | 200000 |  | 200000 | 0 | [9 empty] | 400000 | 400000 | No | Green | 2023-10-01 |  |  |  | 2023-12-31 | [17 empty] | 80000 | 80000 | 40000 | [5 empty] | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 |  | 200000 |  | 200000 | Gingras, Stephan |  |  |  | 1 | 45478 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
Enraf EntisXL replacement | Item | Open | MCAP |  | Exempt |  | Gay, Elena | IT | 1. Proposed |  | OT & IT Field Ops |  | 337211 |  | 337211 | 337211 | 0 | Green | 337110 |  | 337110 | 101 | [9 empty] | 337211 | 337211 | No | Green | 2023-07-01 |  |  |  | 2023-11-30 | [14 empty] | 67422 | 67422 | 67422 | 67422 | 67523 |  |  | -LK 9/28 - Renamed Enraf Entis XL replacement | 2022-09-28 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 | 202266 | 134945 |  |  | Gingras, Stephan |  |  |  | 1 | 38292 |  | Administrator, System | Independent | Aqua | 2020-08-24 | IT
Enterprise Time and Attendance Solution:MCAP | Item | Open | MCAP |  | Exempt |  | Splawn, Kimberly | IT | 1. Proposed |  | Enterprise Business Apps |  | 150000 |  | 150000 | 150000 | 0 | Green | 600000 |  | 600000 | -450000 | [9 empty] | 600000 | 600000 | No | Green | 2023-10-01 |  |  |  | 2024-05-31 | [17 empty] | 50000 | 50000 | 50000 |  | 4/11/23: Per RD, updated Cash Flow Start date to 10/01/23 and decreased CY EAC to $150k and pushing out remaining amount of $450k to 2024.//bo Forecast updated with cash flow 7/1 SG | 2023-04-17 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 |  | 150000 |  | 450000 | Gingras, Stephan |  |  |  | 1 | 45913 |  | Administrator, System | Independent | Aqua | 2022-09-26 | IT
ESG Data & Decarbonization Capture | Item | Candidate | MCAP |  | Exempt |  | Sridhar, Malini | IT | 4. On-Hold |  | Infrastructure & IT Ops |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 | [9 empty] | 100000 | 100000 | No | Green | 2023-07-01 |  |  |  | 2023-12-29 | [14 empty] | 20000 | 20000 | 20000 | 20000 | 10000 | 10000 |  | Forecast pushed to May due to planning process. SG | 2023-04-10 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 | 60000 | 40000 |  |  | Gingras, Stephan |  |  |  | 1 | 45893 |  | Administrator, System | Independent | Aqua | 2022-09-22 | IT
Factory Talk Asset Centre Enterprise Pilot | Item | Open | MCAP | 1348173M2102 | Exempt | 1847673 | Kralik, Ron | IT | 3. Active | Defined | OT & IT Field Ops | 91919 | 9640 | 26014 | 101559.09 | 111614 | -10055 | Yellow | 40000 | 52000 | 92000 | 9559 |  |  | 340000 |  |  | 340000 | Full | 340000 | 196455 | 35654 | 232109 | No | Green | 2021-06-01 | 2021-05-25 | 2021-05-25 | 2021-12-17 | 2023-05-23 |  |  | 12847.2 | 32224.22 | 29674.63 | 17173.04 | 18834 | 18834 | -1661 | Yellow |  |  | 9640 | [7 empty] | 26014 | 5/5/23: Forecast reduced for May to reflect reduced Maverick costs, per their latest estimated hours to complete the project. Expecting final invoicing in May. 4/6/23: Forecast reduced for April and May to reflect reduced Maverick costs, per their latest estimated hours to complete the project. 3/7/23: February underspend due to reduced labor, software, and hardware cost vs original forecast. Remaining month forecasts adjusted due to expected reduced labor, software, and hardware cost vs original forecast. 2/7/23: SQL Server install complete, preparations underway for East Chicago configuration. -1/23/23: Updated Operational date based on current forecast.//bo 1/9/23: No change to forecast. 12/7/22: Maverick effort delayed due to staffing changes on their side. Maverick has provided a revised completion date of May 2023. Forecast has been updated accordingly. 11/7/22: In October Maverick suggested a review of new features that have been released (or are about to be released) that may benefit Buckeye's use case. After discussion with Maverick, Buckeye has elected to continue with original scope and objectives. October underspend due to Maverick labor effort less than forecast. 10/6/22: September underspend due to unplanned additional work needed on the Buckeye side to address vendor AD access issues (which delayed vendor work). 9/8/22: Work underway to grant Maverick vendor access to OT Domain Controllers and VMs. 8/17/2022 Forecast updated to reflect estimated 2023 Carryover. 8/7/22: OT Domain setup and base FT VM builds are complete. Project team to work with Infrastructure Ops to define access restrictions, accounts, GPO policies, AV solution, and backup policy in August. Expecting to resume project activities with Maverick in August. Forecast has been adjusted accordingly. 7/6/22: OT Domain controller work is underway, which will be followed by FT VM Builds, Will work with IT Infrastructure Ops and Security in Julyto ensure that OT domain controller and VM builds conform with expected Everline guidance. Expecting to resume major project activities with Maverick in July-August. Forecast has been adjusted accordingly. 6/7/22: Prerequisite VLAN work has been completed. OT Domain controller work is underway, which will be followed by FT VM Builds, Expecting to resume major project activities with Maverick in July. Forecast has been adjusted accordingly. 5/6/22: Revised ETA on completion of prerequisite VLAN and OT Domaincontroller work, and subsequent FT VM Builds, is now 6/3. Expecting to resume major project activities with Maverick in June. Forecast has been adjusted accordingly. 4/7/22: Revised ETA on completion of prerequisite VLAN and OT Domain controller work, and subsequent FT VM Builds, is now 4/30. Expecting to resume major project activities with Maverick in May. Forecast has been adjusted to shift costs by 1 month. 3/7/22: Due to additional IT security consideration architecture planning discussions (firewall and other), prerequisite VLAN and OT Domain controller work was not completed in February as expected. VLAN and OT Domain activities now planned for March. Once these prerequisite activities have been completed, major project activities will resume. Forecast Update: Feb variance due to delays in planned VLAN and OT Domain work. Forecast extended into 3Q. 2/7/22: OT Domain controller work expected to be completed in February. oncethis prerequisite activity has been completed, major project activities will resume. 1/7/22:Expecting to resume major project activities in January once OT Domain controller work is completed. 12/7/21: No change to status. 11/8/21: Prerequisite OT Domain controller work will not be completed until January 2022. 10/8/21: Per Security Directives, a prerequisite step to build OTDomain controllers will be required before IT Infrastructure can build the required Factory Talk Asset Centre VMs. Until the OT Domain controllers are in place, Maverick and Buckeye labor efforts are on hold. IT Infrastructure team estimates that OT Domain Controller Work will begin in November, with the VM builds to follow in December. As a result of the delay, 4Q project actuals will be $70K lower than currently forecast, and an additional $70K of carryover into 2022 will be required. 9/8/21: Discussions with Infrastructure team underway to develop new VM build timeline (prerequisite to Maverick vendor beginning work). 8/6/21: No change to status. 7/6/21: Project kickoff held on 6/28. Buckeye resource constraints due to competing priorities are expected to result in schedule delays. Team will work with Maverick vendor to adjust schedule accordingly. 6/7/21: Obtained ARC, AFE, Charter, and Business Case approval in May. Project kickoff planned for mid-June. 5/7/21: Project AFE and Charter have been completed. Project will be presented for ARC review in May; AFEand Charter will be submitted for approval once ARC review is complete. 4/7/21: Project deferral was under consideration, but on 4/2/21 decision was made to proceed with the project. Planning to submit AFE for approval in April 2021. | 2023-05-05 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 74746 | 26813 |  |  | 25494 |  | Gingras, Stephan | Sinatore, Kathleen J. |  |  | 1 | 38293 |  | Administrator, System | Independent | Aqua | 2020-08-24 | IT
FactoryTalk AssetCentre Enterprise (Phase Two) | Item | Open | MCAP |  | Exempt |  | Kralik, Ron | IT | 1. Proposed | Defined | OT & IT Field Ops |  | 340000 |  | 340000 | 340000 | 0 | Green | 340000 |  | 340000 | 0 | [9 empty] | 340000 | 340000 | No | Green | 2023-06-01 |  |  |  | 2023-12-31 | [13 empty] | 5000 | 45000 | 60000 | 60000 | 60000 | 60000 | 50000 |  | 5/4/23: No update to status / forecast. 4/6/23: No update to status / forecast. 3/7/23: No update to status / forecast. 2/7/23: No update to status / forecast. 12/7/22: Forecast adjusted to reflect June 2023 start date, based on FT Asset Centre Pilot expected completion date of May 2023. 3/17/22: Project has been deferred until 2023 at the earliest. $275K removed from 4Q forecast. 3/3/22: Project will likely be deferred. Until this is confirm, shifted forecast to Q4. Will update accordingly after deferment is confirmed. LK | 2023-05-04 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 5000 | 165000 | 170000 |  |  | Gingras, Stephan |  |  |  | 1 | 41700 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
Geonamic BAP/CAP Software Module | Item | Open | MCAP |  | Exempt |  | Kralik, Ron | IT | 1. Proposed |  | OT & IT Field Ops |  | 90000 |  | 90000 | 90000 | 0 | Green | 90000 |  | 90000 | 0 | [9 empty] | 90000 | 90000 | No | Green | 2023-05-01 |  |  |  | 2023-10-13 | 8 | Yellow |  |  |  |  | 0 | 0 | 0 | Green |  |  | 5000 | 15000 | 20000 | 20000 | 20000 | 10000 |  |  |  | 5/4/23: No change to status/forecast. 4/6/23: No change to status/forecast. 3/7/23: GIS and Asset Integrity would like to start this project once related Dig Sheet project completes. Dig Sheet to start later than originally forecast due to additional time needed for Geonamic SOW development. Forecast has been shifted accordingly. 2/7/23: No change to status/forecast. 1/9/23: GIS and Asset Integrity requested that this begin after DIG Sheet Generation has been completed. Forecast has been adjusted accordingly. 12/7/22: GIS and Asset Integrity have asked to start this project in January 2023. Forecast has been adjusted accordingly. | 2023-05-04 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 20000 | 60000 | 10000 |  |  | Gingras, Stephan |  |  |  | 1 | 45495 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
Geonamic Dig Sheet Generation | Item | Open | MCAP | 1348173M2302 | Exempt | 2096319 | Kralik, Ron | IT | 3. Active | Defined | OT & IT Field Ops | 21333 | 15000 | 3758 | 36333.33 | 42590 | -6257 | Red | 60000 |  | 60000 | -23667 |  |  | 49856 |  |  | 49856 | Full | 49856 | 21333 | 18758 | 40091 | No | Green | 2023-03-01 | 2023-03-24 | 2023-03-24 | 2023-05-12 | 2023-05-26 |  |  |  |  | 18090 | 3243.33 | 11000 | 11000 | -7757 | Red |  |  | 15000 | [7 empty] | 3758 | 5/4/23: Dig Sheet build delivery delayed until 5/12 due to vendor illness. Still expecting to complete UAT in May. 4/6/23: March overspend due to vendor completing work ahead of schedule. Forecast has been updated accordingly. 3/7/23: Project to start later than originally forecast due to additional time needed for Geonamic SOW development. Forecast has been shifted accordingly. 2/7/23: Additional scope clarifications needed prior to moving forward with AFE. Meeting scheduled with Geonamic on 2/10 to discuss. 1/9/23: GIS and Asset Integrity requested that this begin in 1Q2023. Anticipating AFE submission / approval in January. 12/7/22: GIS and Asset Integrity confirmed original plan to do this project in 1Q-2Q 2023. No change to forecast. | 2023-05-04 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 18090 | 18243 |  |  |  |  | Gingras, Stephan | Kasdano, Lauren |  |  | 1 | 45496 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
Hammond Scheduling Tool Software and Hardware Upgrade | Item | Open | MCAP | BETEH00M2302 | Exempt | 2094250 | Gay, Elena | IT | 3. Active | Defined | OT & IT Field Ops | 25937 | 85884 |  | 111820.66 | 110000 | 1821 | Yellow | 70000 | 43000 | 113000 | -1179 |  |  | 111457 |  |  | 111457 | Full | 111457 | 25937 | 85884 | 111821 | No | Green | 2023-03-01 | 2023-03-07 | 2023-03-07 | 2023-05-30 | 2023-08-31 |  |  |  |  | 24115.61 | 1821.05 |  |  | 1821 | Red |  |  | 0 | 0 | 50000 | 35884 | [5 empty] | 4/27/23 - After discussions with vendor (Triad) - they are unable to work on this project until July 2023. Moved forecast to reflect. 4/10/23: per EG, waiting on timeline details (vendor/resource constraints).//bo 3-17-2023 EG - AFE is approved 3/8/2023 - PO's have been ordered. PO's were having system issues that were stuck in workflow. Received PO's on 3/28 and work to be started. Kick-off meeting 4/5/2023. 1-25-2023 EG Waiting on last two vendor quotes. Met with Chris P. AFE expected to route by the end of the month. 1-6-2023 EG Routing AFE upon Chris Approval next week, expecting updated quote from vendor. AFE will be higher than budget amount but notified management last year. 11-18-22 EG - after meeting with vendor today, moving 20k forecast to 2023. Resource constraints and hardware delays are impacting the start date. Still planning to start in Q1 2023. 9-13-2022 EG - After meeting with Operations and work and resource constraints, this effort can not be completed until Q1 of 2023. Moved forecast 20K in Dec 2022, so vendor can work, order hardware/software and work to complete in Q1 2023. | 2023-04-27 | IT |  | Corporate | Corporate | IT |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  | 24116 | 1821 | 85884 |  |  |  | Gingras, Stephan | Tran, Hung |  |  | 1 | 41709 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
Houston Office Space Relocation - IT | Item | Open | MCAP | 1348172M2101 | Exempt | 1847145 | Kralik, Ron | IT | 6. Operational | Defined | Infrastructure & IT Ops | 130 |  | 25975 | 129.81 | 130 | 0 | Green |  |  |  | 130 |  |  | 734000 |  |  | 734000 | Full | 734000 | 711345 | 25975 | 737320 | No | Green | 2021-06-01 | 2021-09-21 | 2021-09-21 | 2022-03-31 | 2022-07-22 |  |  | 129.81 | [17 empty] | 25975 | 2/7/2023: No additional spend is forecast for 2023. 1/9/2023: No additional spend is forecast for 2023. 12/7/22: No additional spend is forecast. 11/7/22: All IT hardware decommissioning was completed in October. October overspend due to vendor decommissioning costs not originally forecast. No additional spend is expected on the project. 10/6/22: Expecting to begin project closeout in October. 9/8/22: Expecting to begin project closeout in September. 8/5/22: In scope Webex kit setup work was completed in July. Originally quoted Presidio professional services were not required, resulting in July underspend. Expecting to begin project closeout in August. 7/6/22: Expecting remaining Presidio webex kit setup work to be completed in July. 6/7/22: Expecting to complete webex kit setup with Presidio in June. 5/6/22: Caching server work underway. Supplemental webex room kit hardware delivered earlier than expected, will begin setup activities in May. April overspend due to equipment arriving earlier than expected. 4/7/22: Equipment decommissioning and caching server work to continue through April. Due to supply chain delays, expecting supplemental webex room kit delivery and setup to be completed in June. 3/7/22: Network setup, firewall and voice equipment move completed on 2/11. Equipment decommissioning and caching server work to continue through March. Due to supply chain delays, expecting supplemental webex room kit delivery and setup to be completed in June. Forecast Update: Feb variance due to unplanned labor costs (internal and vendor). Forecast increased by $28K due to increased internal and vendor labor costs, and additional PDU and cabling hardware costs. Forecast extended through 2Q due to supply chain delays in delivering supplemental webex room kits. 2/7/22: Onsite work to complete network setup, firewall and voice equipment move to occur week of 2/7. Equipment decommissioning to continue through March. 1/7/22:Network Hardware procurement substantially complete. Onsite IDF/MDF room setup and hardware Installation to occur week of 1/10, firewall and voice equipmentmove to occur week of 2/7. 12/7/21: Network Hardware procurement substantially complete. Wireless network design complete. Network Installation, IT equipment move and decommissioning planning continuing in December. 11/7/21: Activities for November: Network Installation, IT equipment move and decommissioning planning, Wireless network design, Complete Network Hardware procurement. 10/8/21: Full AFE approval obtained 9/21. 9/8/21: Full AFE submitted for approval in August. 8/6/21: Estimated full AFE amount is now $784K to accommodate additional costs due to enhanced videoconferencing requirements. Planning to submit full AFE for approval in August. Interimextension granted for additional 30 days by Ben Clark with Jeff Crone in copy. KB 7/13/21 7/6/21: Estimated full AFE amount is now $711K; AV costs have been removed from the IT AFE (will be covered under Tenant Improvement Allowance). Full AFE to be submitted for approval in July. 5/27/21: Interim AFE for $511K approved. PO issued for long lead time network equipment. | 2023-02-07 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 130 | 0 |  |  | 335307 |  | Gingras, Stephan | Sinatore, Kathleen J. |  |  | 1 | 40130 |  | Meitzler, Antoinette | Independent | Aqua | 2021-05-17 | Office Relocation
IBM Power Hardware Management Console | Item | Open | MCAP | 1348172M2102 | Exempt | 1876291 | Geier, John | IT | 6. Operational | Emergent | Infrastructure & IT Ops | 2136 |  | 4961 | 2136.29 | 2136 | 0 | Green |  |  |  | 2136 |  |  | 39000 |  |  | 39000 | Full | 39000 | 35465 | 4961 | 40426 | No | Green | 2021-08-01 | 2021-08-01 | 2021-08-01 | 2021-10-31 | 2023-04-14 |  |  | 153.74 | 156.51 | 1826.04 | [15 empty] | 4961 | 3/28/23 - Project completed .Closing out. // jg 3/7/2023: In final stages of configuration // jg 2/5/23 - 3 of 4 tasks complete. Task remaining is Prod a2x to go to v3 (approx. 8-9 hours) // JG 12/30/22 - Fiber work continues. Forecast and operational date updates made. - JG 12/7/22 - Fiber configuration remains in progress 10/27/22 - Remains in progress. Fiber configuration underway 10/1/22 - Remains in progress. Currently awaiting network cabling to be completed 9/1/22 - Brandon continues to work with the vendor Flagship and his goal is to have this completed in August. We meet every Tuesday to review this project. 8/1/22 - Brandon continues to work with the vendor Flagship and his goal is to have this completed in August. We meet every Tuesday to review this project. 7/5/22 - Brandon and Don have worked with the vendor in June and should complete this project in July. 6/3/22 - Brandon did not get to final install of this project in May and is planning to complete this in June/July time frame. 5/2/22 - We are hoping to get our vendor Flagship in the building to help out with this in May. This should close out in May, with final paperwork completed in June/July time frame. 4/5/22 - Brandon has completed most of the install for this project, and needs to finalize the last equipment connections. We are hoping to get our vendor Flagship in the building to help out with this in April. This should close out in May. 3/7/22 - Brandon has completed most of the install for this project. This should close out late Q1, to early Q2. 2/4/22 - Brandon continues to complete the install fully for this project. This should close out early Q1. We review this every Tuesday with Steve and Brandon Smith. 1/3/22 - Brandon has completed most of the install over the Thanksgiving weekend. This should close out early Q1. We review this every Tuesday with Steve and Brandon Smith.12/1/21 - AFE approved and equipment ordered and received for Steve's team for this project. Brandon has completed most of the install over the Thanksgiving weekend. This should close out early Q1. We review this every Tuesday with Steve and Brandon Smith. 11/5 - AFE approved andequipment ordered and received for Steve's team forthis project. We are now planning the install of this with the InfraOPS team for November/December time frame. We review this every Tuesday with Steveand Brandon Smith. 10/5 - AFE is approved and equipment ordered and received for Steve's team for this project. We are now planning the install of this with theInfraOPS team for October/November time frame. We review this every Tuesday with Steve and Brandon Smith. 9/6- The AFE is approved and equipment ordered and received for Steve's team for this project. We are now planning the install of this with the InfraOPS team for September. 8/2- AFE approved and equipment ordered for Steve's team for this project. We are counting on this coming in during August and it is forecasted this way. Steve's team is ready to implement the moment this comes in from Flagship. | 2023-03-28 | IT |  | Corporate | Corporate | IT |  | Corporate | Corporate |  | 2136 | 0 |  |  | 2094 |  | Gingras, Stephan | Sinatore, Kathleen J. |  |  | 1 | 40816 |  | Meitzler, Antoinette | Independent | Aqua | 2021-07-28 | IT
Identity Management/Orchestration/Elevated Privilege Mgmt | Item | Candidate | MCAP |  | Exempt |  | Camacho, Juan | IT | 1. Proposed |  | Infrastructure & IT Ops |  |  |  | 0 |  | 0 | Green | 250000 |  | 250000 | -250000 | [11 empty] | No | Green |  |  |  |  | 2023-11-30 | [21 empty] | 3/08/2023: Duplicate entry with PAM. Removing forecast for now. Looking to re-distribute the 2023 Budget.//bo 3/2 did not hit milestone due to vendor delays with design SG | 2023-03-08 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 |  |  |  |  | Gingras, Stephan |  |  |  | 1 | 45892 |  | Administrator, System | Independent | Aqua | 2022-09-22 | IT
iGen Move to SaaS | Item | Open | MCAP |  | Exempt |  | Gingras, Stephan | IT | 1. Proposed |  | OT & IT Field Ops |  | 35000 |  | 35000 | 35000 | 0 | Green | 35000 |  | 35000 | 0 | [9 empty] | 35000 | 35000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 25000 | 10000 | [9 empty] | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 | 35000 |  |  |  | Gingras, Stephan |  |  |  | 1 | 45498 |  | Administrator, System | Independent | Aqua | 2022-08-30 | IT
Indirect Tax Software Implementation | Item | Open | MCAP | 1348174M2204 |  | 2036817 | Aili, Suresh | IT | 3. Active | Defined | Enterprise Business Apps | 274497 | 175000 |  | 449497.36 | 450062 | -564 | Yellow |  | 330000 | 330000 | 119497 |  |  | 551000 |  |  | 551000 | Full | 551000 | 341524 | 175000 | 516524 | No | Green | 2022-11-01 | 2022-10-13 | 2022-10-13 | 2023-03-31 | 2023-06-30 |  |  | 125271.11 | 32333.16 | 45128.54 | 71764.55 | 97329 | 97329 | -25564 | Red |  | Buckeye/Customer Schedule | 80000 | 55000 | 40000 | [6 empty] | 5/8/23 Go-Live Delay to 6/1 forecast adjusted. SG 3/8 The Feb forecast is under by $26K due to additional time for requirements and pushing go live by one month: internal labor $12K less, $4K reclass to be processed for contractor in March vs. Feb and vendor under by $10K. -KS 2/7 Updated Est. Op date to 5/31/23 due to go live moving to 5/1/23. One month added for addt'l testing, forecast updated through May for work plan based on approved requirements. KS 1/9 $193K of $203K 2022 forecast on track. $193K in vendor invoicing is behind. Additionally reclass of $98K that was processed in Dec. -KS 12/6 Forecast increased by $95K in December due to reclass of software expenses and incorporating vendor work plan. -KS 11/7 Project kicked off 11/4. Forecast updated for expense related requirements gathering during Nov-Dec. - KS | 2023-05-08 | IT |  | Corporate | Pipelines and Terminals | IT |  | Corporate | Corporate |  | 202733 | 206765 | 40000 |  | 67026 |  | Gingras, Stephan | Virupakshi, Sudhakar |  |  | 1 | 46007 |  | Meitzler, Antoinette | Independent | Aqua | 2022-10-06 | IT
Internal Checkpoint Firewall Refresh | Item | Open | MCAP |  | Exempt |  | Hagerty, Sean | IT | 1. Proposed |  | Infrastructure & IT Ops |  | 60000 |  | 60000 | 60000 | 0 | Green | 60000 |  | 60000 | 0 | [9 empty] | 120000 | 120000 | No | Green | 2023-10-01 |  |  |  | 2024-03-31 | [16 empty] | 0 | 20000 | 20000 | 20000 |  | 5/5/23 - no expected change to start or budget. SH 4/11/23: $60k forecasted for 2023 and 2024. Updated monthly spread based in Project Tracker.//bo | 2023-05-05 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 | 0 | 60000 |  | 60000 | Gingras, Stephan |  |  |  | 1 | 45499 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
IT Service Management Transformation | Item | Open | MCAP |  | Exempt |  | Gingras, Stephan | IT | 1. Proposed |  | Infrastructure & IT Ops |  | 250000 |  | 250000 | 250000 | 0 | Green | 250000 |  | 250000 | 0 | [9 empty] | 250000 | 250000 | No | Green | 2023-07-01 |  |  |  | 2023-11-30 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 0 | 40000 | 30000 | 30000 | 30000 | 30000 | 90000 |  | 3/24/24 Budget moved to Q3 per Justin Lee. SG -10/31/22 - Reduction in 2023 budget by $50k due to ELT budget reduction request.//bo | 2023-03-24 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 | 100000 | 150000 |  |  | Gingras, Stephan |  |  |  | 1 | 45479 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
ITT - In Tank Transfer | Item | Open | MCAP |  | Exempt |  | Gay, Elena | IT | 1. Proposed | Defined | OT & IT Field Ops |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 | [9 empty] | 50000 | 50000 | No | Green | 2023-08-01 |  |  |  | 2023-11-15 | [15 empty] | 17000 | 17000 | 16000 |  |  |  | -8/09/22: Changed status back to proposed so not duplicated during budget process. Added $50k in Q2 2023 for now.//bo 7-20-2022 EG - Project Team deferring to 2023 due to other pressing competing priorities and resource issues. | 2022-11-09 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 | 34000 | 16000 |  |  | Gingras, Stephan |  |  |  | 1 | 41723 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
Ivanti Application Control | Item | Open | MCAP | 1348179M2203 | Exempt | 1991180 | Geier, John | IT | 8. Canceled | Emergent | Infrastructure & IT Ops | -3112 |  |  | -3112.34 | -3112 | 0 | Green |  |  |  | -3112 |  |  | 54000 |  |  | 54000 | Full | 54000 | 0 |  | 0 | No | Green | 2022-08-01 | 2022-06-20 | 2022-06-20 | 2022-12-30 | 2022-12-30 |  |  |  | -3112.34 | [17 empty] | 3/04/23: Project actuals reclassed to 1348179. Project to be cancelled.//bo 10/20/22 - Placing project on hold as team is looking into utilizing BeyondTrust as the alternative 10/1 Decision made to start with a pilot. Prerequisite hardware build out is underway. Kickoff with vendor this month 8/31/2022 Planning with Vendor expect kick off shortly. SG 7/29/2022 Planning project and working with vendor. SG 6/30/222 Vendor still in onboarding process. SG | 2023-03-04 | IT |  | Corporate | Pipelines and Terminals | IT |  | Information Systems |  |  | -3112 | 0 |  |  | 3112 |  | Gingras, Stephan | Gardner, Dale |  |  | 1 | 43983 |  | Meitzler, Antoinette | Independent | Aqua | 2022-06-14 | IT
JDE AS400 Conversion to SQL Server | Item | Open | MCAP | 1348174M2304 | Exempt | 2120217 | Schneider, David | IT | 3. Active | Emergent | Enterprise Business Apps |  | 350600 |  | 350600 | 275000 | 75600 | Red |  |  |  | 350600 |  |  | 396027 |  |  | 396027 | Full | 396027 |  | 350600 | 350600 | No | Green | 2023-05-01 | 2023-05-05 | 2023-05-05 | 2023-08-21 | 2023-11-30 | [12 empty] | 52200 | 82300 | 83300 | 98300 | 34500 | 0 | 0 |  |  | 5/5/23: AFE approved. Forecast updated. -?4/10/23: Project not budgeted for 2023 (was normal status). Emergent project for 2023. Updated CY EAC in Tracker from $400k to $275k//bo | 2023-05-08 | IT |  | Corporate | Pipelines and Terminals | IT |  | Information Systems | Corporate |  |  | 134500 | 216100 | 0 |  |  | Gingras, Stephan | Virupakshi, Sudhakar |  |  | 1 | 46921 |  | Meitzler, Antoinette | Independent | Aqua | 2023-04-10
Leak Detection Software Replacement | Item | Open | MCAP | 1348176M1906 | Exempt | 1653051 | Geier, John | IT | 3. Active | Defined | OT & IT Field Ops | 577470 | 1112867 |  | 1690336.96 | 1664580 | 25757 | Yellow | 1375000 | 350000 | 1725000 | -34663 |  |  | 2865000 | 3579000 | 2335000 | 8779000 | Phase | 8779000 | 5489536 | 2763221 | 8252757 | No | Green | 2020-01-01 | 2019-11-18 | 2019-11-18 | 2020-11-30 | 2025-04-30 |  |  | 173139.68 | 104315.8 | 126030.55 | 173983.93 | 148227 | 148227 | 25757 | Red |  | Other | 144302 | 146533 | 147642 | 148696 | 149803 | 150870 | 136968 | 88053 |  | 5/5/23 - Forecast and budget tracking after supplemental AFE approval. // jg 4/25/23 - Supplemental Approved. WO# 1653051 // jg 4/10: Forecast reduced due to SCADA team not adding resource as expected in March/April.//bo 4/6 - PIM Upgrade. Preparing for P2 go-live. CR/AFE submitted for approvals. AVEVA software issue with non-billable hours // jg 3/7/23 - PIM2023 upgrade continues. Working towards P2 Go-Live. CR for remaining work under review. // jg 2/5/23 - Reworking remaining schedule but maintaining completion by 4/25. PIM2023 initiated in Jan 2023 and planning for PIN2024 in Jan 2024 // JG 12/30/22 Schedule was delayed on the second go-live and expecting more delays with possible upgrades needed to PIM. Tranferring to John Geier SG 11/30/2022 Schedule delayed on second go-live and December forecast reflects increased work expected in December. SG 10/31/2022 First consoles went live, CC7 and 8. Preparing for Second Deployment in February. SG 9/30/2022 Variance based on pass run rate and will be updated going forward, Prepping for first go-live. SG 8/23/22 - DB - Updated the financials for the rest of the project after meeting with the Sponsors yesterday and getting confirmation from them. We are going to add MB7 which will be CR # 5, roughly 295k and the MPT2 template is approved by management for 75k, and this will be CR # 4. This totals 370k combined, and CR's will be submitted this week to the Sponsors. 8/1/22 - P1 Go Live has been tentatively set for 10/17/22. Forecast has been updated and reflects current schedule. Met with Sponsors on 8/1 and have another meeting on 8/4 to review financials. 7/5/22 - P1 Go Live date has not been finalized. Forecast has been updated and reflects current schedule. West Shore Re-class hit this month thus the large variance for June. Next Sponsor meeting 7/15. 6/3/22 - The month of May posted a lower total than expected with a larger credit applied to the invoice by Aveva. Forecast and schedule updated. 5/6/22 $14,534 credit expected for Feb and March on April monthly invoice was not applied. CWIP was more than anticipated and this added to the overage for this month. Corrected future forecasts to reflect these changes. DB 4/5/2022 The run rate for this project has been higher than anticipated bythe vendor and future forecasts have been updated to reflect it. The variance in March was caused by an inaccurate amount typed in the accrual workbook. This project remains at risk of needing a supplemental AFE as reported to management during sponsor meetings. DB 3/4/22 - Forecast has beenupdated with New CR #4 being proposed that is currently forecasted at $135k to implement on top of the budget already planned for this year. We are at risk for a supplemental AFE with this new CR, and the extra time the team needsto solve the Virtual Meter Issue. This is discussed in every monthly Sponsor Meeting.2/4/22 - We had a Sponsor Meeting on 2/3 to review our current position. We are asking for two months to do adeep dive to examine and fine tune the Virtual Meter findings based on the Control Center's needs. We have been granted those two months. We continue to send over the data to Aveva for P4 as well. We continue to complete CVT's within these priorities. We meet at least three to four times a week to review current tasks and review processes. Chris and Jesse met with Avevaleadership last week and this week. We now have a weekly recurring meeting with Aveva leadership. 1/3/22 - The team continues to work on Priority 2 with Aveva. We are working on the implementing of theP1Priority as well. We continue to send over the data to Aveva for P4as well. We continue to complete CVT's within these priorities. We meet at least three to four times a week to review current tasks and review processes. We hada Sponsor meeting with Kathy and Dave Arnold and the Directors to give our updates. Our next Sponsor meetingis scheduled on 1/6/22.12/1/21- The team continuesto work on Priority 2 with Aveva. We areworking on the P1 Priority as well. We continue to completeCVT's within these priorities. We meet at least three to four times a week to review currenttasksand reviewprocesses. We had a Sponsor meeting on 11/8 with Kathy and Dave Arnold and the Directors to give our updates. Our next Sponsor meeting is scheduled on 12/13. Our CR001, CR002, and CR003 have been approved. We had a Program Meeting with Chris Parker on 12/1 to review our status as well. 11/5 - The team continues to work on Priority 2withAveva. We are working on the P1 Priority as well. We continue to complete CVT's within these priorities. We meet at least three to four times a week to review current tasks and review processes. We had a Sponsor meeting on 10/4 with Kathy and Dave Arnold and the Directors to give our updates. We had an Executive Sponsor Meeting with Bob and Keith on 10/6. Our next Sponsor meeting is scheduled on 11/8. Our CR001, CR002, and CR003 have been approved. 10/5 - The team is working on Priority 2 currently with Aveva. We are working on the P1 Priority as well. We continue to complete CVT's within these priorities. We meet at least three times a week to review current tasks and review processes. We did an accrual for $75,000 for labor completed and not billed for September. We had a Sponsor meeting on 10/4 with Kathy and Dave Arnold and the Directors to give our updates. We have an Executive Sponsor Meeting with Bob and Keith on 10/6. 9/6 - The team is working on Priority 2 currently with Aveva. We are working on the P1 Priority as well. We continue to complete CVT's within these priorities, recently the 802/803 line. . We meet at least three times a week to review current tasks and review processes. We did an accrual for $96,000 for labor completed and not billed for August. We had a Sponsor meeting on 8/31 with Kathy and Dave Arnold and the Directors to give our updates. 8/4 - The team is working on Priority 2 currently with Aveva. We meet at least three times a week to review current tasks and review processes. We met yesterday (8/5) as a team and with Chris Parker for our status updates. 7/6 - The team is working on Priority 2 currently with Aveva. We had a meeting on (6/3) with Chris Parker and the team to review our current status. We meet at least three times a week to review current tasks and review processes. We did an accrual for $52,000 for labor completed and not billed for June. 6/3 - Phase project with Phase 3 Kicking off 5/11. The team is working on Priority 2 currently with Aveva. We had a meeting today (6/3) with Chris Parker and the team to review our current status. (DB) 5/1 - Phase project with Phase 3 Kicking off 5/11 with a new PM Dave Barnett. SG 3/29 Delays and Plan on closing project when the pipelines tuning is completed. Expected this month. SG 3/29 Plan to Close Phase 1 end of Month, Planning Phase 2 expect budget Updated/ Phased Project SG3/8 Delayed Due to Pipeline tuning and over all 2 month delay in Schedule from Custom Displays late delivery. On Budget. SG 2/3 Budget Adjusted due to scheduling delays on budget delayed phase 1 close 2/11, SG 1/5 Budget Updated Due to Schedule delay SG 12/9 Status report schedule delay, budget on Schedule. SAT to be completed 12/11 and Phase 1 Closed 1/19 SG 12/2 Forecast Updated based on CVB project and delay in finishing SAT. SG 11/9 Delayed due toDisplay Development Not complete and CR for CVB pilot. New Completion dated for Phase 12/18, Work Completed: SAT Document, FDS, Display Design Review. Work to be Completed SA, Security Scan, Display Design. SG 10/22 Budget for phase 3 updated based on current SOW SG 10/8 On time and Budget 8/31 On time and budget, SimSuite Install: Work to complete, Finish installing hardware and software, Actual vs Forecast variance due to reclass by West Shore instead of inOctober. Budget adjust for CR SG Finish approving displays Finalizing OCM strategy SG 8/18 add draft budget for phase 2/ removed west shore reclass $236,977 from October budget SG 7/31 on budget and time FAT completed, next SCADA interface, displays, final hardware and software installs SG 6/30 Budget and Schedule CR pending -Enginering Training 6/26 - Pre FAT testing document approved 6/29 - CR approval 7/6 - FAT 7/22 5/29 On-time and budget. Pending schedule change for CR CVB and rebuild of hardware due to an error in the SOW by Aveva. FDS and design specs complete. ?Finalizing CR, FAT prep, schedule update based on CR and SOW miss with 2012 SQL instead of 2016. Engineering training Scheduled for the week on 6/22. 3/31 Project on Budget and on schedule: FDS 90% complete and need to finish section 9 displays. Section 9 is behind schedule but is not on the critical path and will not delay the project. 3/23 Schedule on Track SG 3/31 project on schedule and budget: Planned work training plan approval, test plan, pipeline configuration, development of global nominations completed. 1/31 KickoffMeeting, Provided Data, Started reviewing default visuals. next steps FDS 12/31 Kick off plannedfor1/21 12/10 SOW to be signed before 12/20, Kick Off Meeting Moved to Late December or Jan 10/08 - AFEwillbe approved in Q4 – completed the vendor selection process and initial planningRFP sent 4/2. Two week delay has impacted the implementation start date and the forecast has slid one Month. 8/7 Vendor Selected moving into Design Phase. 5/15 Aveva Reference call, Aveva scoring, Sponsor approval of vendor selection. | 2023-05-05 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 403486 | 464819 | 446141 | 375891 | 1650621 | 1300000 | Gingras, Stephan | Ingalls, Robert T. | N/A |  | 1 | 31075 |  | Ohlsen, Becca | Independent | Aqua | 2018-08-28 | IT
Macungie Data Center Remediation | Item | Open | MCAP |  | Exempt |  | Geier, John | IT | 1. Proposed |  | Infrastructure & IT Ops |  | 400664 |  | 400664 | 400664 | 0 | Green | 370000 | -100000 | 270000 | 130664 | [9 empty] | 400664 | 400664 | No | Green | 2023-06-01 |  |  |  | 2023-10-31 | [13 empty] | 100000 | 61666 | 41666 | 35666 | 100000 | 61666 |  |  | 4/10 Budget reduced increased based on quotes SG | 2023-04-10 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 100000 | 138998 | 161666 |  |  | Gingras, Stephan |  |  |  | 1 | 45500 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
MOC Implementation (2022) | Item | Open | MCAP | 1348174M2202 | Exempt | 2012614 | Schneider, David | IT | 3. Active | Defined | Enterprise Business Apps | 73013 | 141100 |  | 214112.63 | 202124 | 11989 | Yellow | 101950 |  | 101950 | 112163 |  |  | 346000 |  |  | 346000 | Full | 346000 | 215193 | 141100 | 356293 | No | Green | 2022-08-01 | 2022-08-18 | 2022-08-18 | 2023-02-15 | 2023-06-05 |  |  | 28532.88 | -1300.88 | 13291.57 | 32489.06 | 40900 | 40900 | -8411 | Red |  |  | 49900 | 41800 | 49400 | [6 empty] | 5/5/23: Configurations & demo's completed. Vendor system testing in progress. UAT scheduled for 5/22 to 6/2. Vendor estimates additional work needed to complete project. Change order 2 approved. Estimate EAC to be over budget, but under amount requiring supplemental. Forecast updated. 4/7/23: Configurations in progress. Completed 2 demo's of sprint 1 & 2 configurations. Forecast updated. 3/6/23: Configurations were supposed to start in Feb, but were delayed until 3/6. ETA for completion of configurations is 4/28. Integration development in progress. Under forecast as the implementation vendor did not do any configuration work in Feb. Additionally, having some issues with invoices and work completed. A credit of $15K was sent as they incorrectly charged for hours on an early invoice. They are also one month behind in invoicing us hours from the implementation vendor, which has caused some challenges with estimating forecast. Forecast updated. 2/7/23: Design signoff completed. Configurations started. A change request from the vendor based on the final design has been approved increasing the EAC and using most of the contingency. Forecast updated. 1/6/23: Design review in progress. Pending signoff on designs. Under forecasts as configurations & development were not started in December as planned. Configurations and designs should start in Jan. Forecast updated. 12/6/22: Design meetings completed. Pending design signoff. Over forecast due to vendor reconciling hours used by 3rd party integrator. Forecast updated. 11/7/22: Requirements and design workshop completed. Under forecast due to delay in vendor getting started. 10/5/22: Vendor onboarded. Project kickoff completed 10/5. Forecast updated. 9/28/22: Updated forecast based on vendor project kickoff. 9/8/22: AFE approved. MSA & contract completed. Pending project kickoff with vendor. 8/17: Updated forecast based on AFE submitted. 8/5: SOW, MSA & Order form negotiations in progress. Sponsor updated completed. AFE pending. Project kickoff in early September. Forecast updated. 7/6: SOW, MSA & Contract negotiations in progress. AFE pending Sponsor update & approval. Project kickoff end of August or early September. Forecast updated. ??6/6: Completed calls with Enablon on installation, IT &Security, and customer reference. Pushing cost to start in July. Forecast updated. 5/4: Demos completed.Selection process in progress. No change to forecast at this time. 4/4: RFP closed 3/11. Responses being evaluated. Demos to be scheduled. No change to forecast at this time. 3/1: RFP Kickoff 2/14. AFE to be submitted end of Apr or early May. Forecast updated, but rough estimate. A more accurate forecast will be available once a vendor is selected. 1/31: RFP process in progress. Sourcing event planned for Feb. | 2023-05-05 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 40524 | 124189 | 49400 |  | 142181 |  | Gingras, Stephan | Gardner, Dale |  |  | 1 | 41721 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
MultiLoad and AccuLoad register change monitoring | Item | Open | MCAP | 1348181M2202 | Exempt | 2002074 | Gay, Elena | IT | 6. Operational | Defined | OT & IT Field Ops | 4975 |  |  | 4974.56 | 584 | 4391 | Red |  |  |  | 4975 |  |  | 85000 |  |  | 85000 | Full | 85000 | 76623 |  | 76623 | No | Green | 2022-07-01 | 2022-07-06 | 2022-07-06 | 2022-09-30 | 2023-03-31 |  |  | 190.99 | 194.6 | 198.1 | 4390.87 |  |  | 4391 | Red | [11 empty] | -4/10/2023: Per EG, no additional funds needed for 2023. Re-accruing from 2022 (waiting on final invoice)//bo -1/23/23: Updated Operational date based on Forecast.//bo 11-9-2022 EG - Vendor is delayed with the Accuload portion of the project and this effort will carry over to 2023. The Multiload portion of the project will be completed by the end of the year (Dec). 8-2-2022 - AFE was approved in late July and project started late. Adjusting forecasts. 7-5-2022 - AFE is in working and pending final approval (EG) | 2023-04-10 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 584 | 4391 |  |  | 71649 |  | Gingras, Stephan | Gardner, Dale |  |  | 1 | 41708 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
NAC Implementation for SCADA Network | Item | Open | MCAP | 1348179M2301 | Exempt | 2110547 | Geier, John | IT | 3. Active | Defined | OT & IT Field Ops |  | 164000 |  | 164000 | 165000 | -1000 | Yellow | 165000 |  | 165000 | -1000 |  |  | 171141 |  |  | 171141 | Full | 171141 |  | 164000 | 164000 | No | Green | 2023-05-01 | 2023-04-12 | 2023-04-12 | 2023-10-30 | 2023-11-30 | [6 empty] | 16500 | 16500 | -16500 | Red |  | Buckeye/Customer Schedule | 32000 | 16500 | 32000 | 16500 | 16500 | 18500 | 32000 |  |  | 5/5/23 - POs submitted awaiting vendor order. // jg | 2023-05-05 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 48500 | 65000 | 50500 |  |  | Gingras, Stephan | Tran, Hung |  |  | 1 | 45894 |  | Administrator, System | Independent | Aqua | 2022-09-22 | IT
Network Lifecycle Refresh Program 2022 | Item | Open | MCAP | 1348179M2201 | Exempt | 1972496 | Geier, John | IT | 3. Active | Defined | Infrastructure & IT Ops | 718718 | 3000 |  | 721717.59 | 694791 | 26927 | Yellow |  | 678000 | 678000 | 43718 |  |  | 1006000 |  |  | 1006000 | Full | 1006000 | 1114243 | 3000 | 1117243 | Yes | Red | 2022-05-01 | 2022-05-02 | 2022-05-02 | 2022-12-31 | 2023-07-31 |  |  | 113982.69 | 81567.33 | 495470.67 | 27696.9 | 770 | 770 | 26927 | Red |  | Other | 1000 | 1000 | 1000 | [6 empty] | 5/8/23 April variance to forecast due to under due to not forecasting CWIP. SG 5/5/23 -. Rolling install remains pending. // jg 4/6/23 -Updated forecast as equipment has been received. Rolling install remains pending. // jg 3/7/23 - Awaiting remaining CISCO equipment // jg 2/10/23 - Invoices processed from December missed based on accounting timing. DC 2/09/23: $678k will be adjusted from Network 2023 Budget to 2022 Carry-over.//bo 2/5/23 - Awaiting arrival of remaining equipment expected in May/.Jun 2023 // JG -1/31/2023: Updated Operational Date based on current forecast.//bo 12/30/22 - Awaiting remaining equipment in 2023. Variance due to supply chain issues. No change in forecast. JG 12/7/22 - Still awaiting equipment. High probability of pushing into 2023. Forecast adjusted. Variance due to supply chain issues. November variance due to early arrival of equipment 10/27/22 - Forecast remain the same as we are awaiting on equipment 10/07/22 - Removed 2023 forecast. Dollars in the 2023 forecast of this project were duplicated with the 2023 Network Lifecycle refresh project. Removed per direction of Dale Gardner. //jkn 10/1/22 Awaiting of arrival of equipment 9/7/2022 Forecast updated per Jamie for new servers. SG 9/1/22 - Forecast remains the same for this project, no real changes. Some equipment we were hoping to come in August, will arrive in September. 8/1/22 - The order for $88,455 for Core BTS came in early, thus the difference for this month. Forecast for August adjusted because of this early shipment. Forecast updated based on labor being pushed to 2023 with late December equipment arrival. 7/5/22 - Forecast remains the same for this project, no real changes. 6/3/22 - On small piece of equipment arrived in late May. Forecast remains the same. 5/2/22 - AFE has been submitted and forecast is updated. 4/5/22 - Met with Jamie on 4/5 to review quotes for this project.Financial forecast has been updated based on our meeting reflecting more equipment delays. 3/22/22 - Confirmed budget is $1,050,000 with Becca. This was reduced from 1,200,000 with the 2021 Network Refresh carry overfrom last year. - DB 3/7/22 - I continue to meet with Jamie about getting the most updated quotes for this project. The expectations arethis will kick off in Q2 and the forecast has been updated. 2/4/22 - I met with Jamie on 2/3, on getting the most updated quote for this project and building out aschedule and charter and the next steps for submitting the AFE for this project. This will not kick off in Q1. 1/3/22 - Jamie is gathering quotes from the vendors for this project. | 2023-05-09 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 691021 | 29697 | 1000 |  | 395525 |  | Gingras, Stephan | Sinatore, Kathleen J. |  |  | 1 | 41691 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
Network Lifecycle Refresh Program 2023 | Item | Open | MCAP |  | Exempt |  | Hagerty, Sean | IT | 1. Proposed |  | Infrastructure & IT Ops |  | 833000 |  | 833000 | 833000 | 0 | Green | 1711000 | -878000 | 833000 | 0 | [9 empty] | 833000 | 833000 | No | Green | 2023-05-01 |  |  |  | 2023-10-31 | 8 | Yellow |  |  |  |  | 0 | 0 | 0 | Green |  |  | 20000 | 20000 | 718000 | 15000 | 20000 | 20000 | 20000 |  |  | 5/5/23 - AFE submission planned for this month. SH 3/31/23 - Pushed forecast to May as planning is still underway for needed equipment // jg 3/7/2023: Moving cash flow start date to 4/1/23 // jg 2/09/23: $678k will be adjusted from Network 2023 Budget to 2022 Carry-over.//bo | 2023-05-05 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 40000 | 753000 | 40000 |  |  | Gingras, Stephan |  |  |  | 1 | 45471 |  | Administrator, System | Independent |  | 2022-08-30 | IT
Omega Firewalls / OT Domain | Item | Open | MCAP | 1348171M2203 | Exempt | 2037898 | Camacho, Juan | IT | 7. Closed | Emergent | Infrastructure & IT Ops | 6846 | 0 | 10912 | 6846.28 | 6172 | 675 | Red |  |  |  | 6846 |  |  | 128000 |  |  | 128000 | Full | 128000 | 116013 | 10912 | 126925 | No | Green | 2022-11-01 | 2022-10-25 | 2022-10-25 | 2022-12-30 | 2022-12-30 |  |  | 4372.86 | 1039.98 | 758.88 | 674.56 | 0 | 0 | 675 | Red |  |  | 0 | 0 | [6 empty] | 10912 | 20 Feb 2023- All project / AFE requirements met. Can commence closing of project. JC 27 Jan 2023- Rack and Stack Completed. Only one invoice remains (Network Team ran out of fiber had to procure more cost 370.70). Will proceed with project close-out- JC 31 Jan- Final expenses are to hit Feb 2023.- JC 1 Nov- Expect Equipment End of November beginning of December. SG | 2023-03-07 | IT |  | Corporate | Corporate | IT |  | Corporate | Corporate |  | 6172 | 675 |  |  | 109167 |  | Gingras, Stephan | Gehringer, Todd |  |  | 1 | 46112 |  | Meitzler, Antoinette | Independent | Aqua | 2022-10-24 | IT
OneStream - Reconciliation and Transaction Matching Implementation (MCAP) | Item | Open | MCAP | 1348174M2102 | Exempt | 1901905 | Bartlett, Hilary | IT | 8. Canceled | Defined | Enterprise Business Apps | -432 |  |  | -431.54 | -432 | 0 | Green | 300000 | -300000 | 0 | -432 |  |  | 396000 |  |  | 396000 | Full | 396000 | 0 |  | 0 | No | Green | 2022-11-01 | 2021-10-12 | 2021-10-12 | 2023-04-30 | 2023-05-31 |  |  |  |  | -431.54 | [16 empty] | -4/03/23: Project Actuals are now $0 after reclass has been completed. Cancelling project.//bo -2/22/23: Reclass submitted for $432 in Actuals.//bo -2/08/23: Changed project status to ONHOLD and removed forecast for 2023 and moved to other ONESTREAM Entry. 2023 budget amount of $300k will need to be moved to other OPPM entry as well BEFORE project canceled.//bo -Cancelling this project. We will reclass the $432 until the new AFE is approved. Forecast will be removed once the new project entry is created. LK 1-17-23 -5/19/22: Adjusted forecast to Q4. Confirming if this project will occur in 2022. LK -3/02/2022: After discussion with LK, we shifted Forecast to Q3 Cash Flow Start Date.//bo | 2023-04-03 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | -432 | 0 |  |  | 432 |  | Gingras, Stephan | Bohnsack, Gary |  |  | 1 | 42255 |  | Clark, David | Independent | Aqua | 2021-10-06 | IT
OneStream - Reconciliation and Transaction Matching Implementation 2023 | Item | Open | MCAP | 1348174M2302 | Exempt | 2085451 | Bartlett, Hilary | IT | 6. Operational | Defined | Enterprise Business Apps | 262203 | 112000 | 29912 | 374203.13 | 297614 | 76589 | Red |  | 300000 | 300000 | 74203 |  |  | 368725 |  |  | 368725 | Full | 368725 | 262203 | 141912 | 404115 | No | Green | 2023-02-01 | 2023-01-30 | 2023-01-30 | 2023-04-30 | 2023-04-28 |  |  |  | 42900 | 110713.91 | 108589.22 | 106000 | 106000 | 2589 | Yellow |  |  | 102000 | 10000 | [6 empty] | 29912 | 5/7/23: Adjusted forecast to reflect change in internal labor cost anticipated for go live and to reflect difference in actual vs acrual. 4/6/23: Budgeted Buckeye contractor labor was removed. ~13,000. Updated forecast to reflect this change. 3/6/23: Updated forecast based on schedule and JDE issues. HB 3/2/23: Vendor billed with less than expected hours. Addressing with vendor to update forecast for next week. HB 2/9/23 Adjusted Forecast to match schedule. HB 2/08/2023: AFE issues. THIS is the project OPPM Entry that will be used in 2023 (other project will be cancelled once $432.00 in Actuals and 2023 Budget amount of $300k is moved over).//bo | 2023-05-08 | IT |  | Corporate | Pipelines and Terminals | IT |  | Information Systems | Corporate |  | 153614 | 220589 |  |  |  |  | Gingras, Stephan | Gardner, Dale |  |  | 1 | 46488 |  | Guest, ProSight | Independent | Aqua | 2023-01-17 | IT
OneStream Transformation | Item | Open | MCAP |  | Exempt |  | Bartlett, Hilary | IT | 1. Proposed |  | Enterprise Business Apps |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 | [9 empty] | 100000 | 100000 | No | Green | 2023-10-01 |  |  |  | 2023-12-31 | [17 empty] | 33334 | 33333 | 33333 |  | 4/11/23: Per RD, updated Cash Flow Start date to 10/01/2023 for now. Kept CY EAC of $100k the same for now.//bo | 2023-04-11 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 |  | 100000 |  |  | Gingras, Stephan |  |  |  | 1 | 45501 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
OT Digital SIMOPs | Item | Open | MCAP | 1348173M2301 | Exempt | 2085445 | Schneider, David | IT | 3. Active | Defined | OT & IT Field Ops | 6227 | 132600 |  | 138827.06 | 169698 | -30871 | Red | 300000 |  | 300000 | -161173 |  |  | 191843 |  |  | 191843 | Phase | 191843 | 6227 | 132600 | 138827 | No | Green | 2023-03-01 | 2023-05-05 | 2023-05-05 | 2023-07-14 | 2023-12-31 |  |  |  |  | 2698.38 | 3528.68 | 15000 | 15000 | -11471 | Red |  | Buckeye/Customer Schedule | 10900 | 71000 | 48700 | 2000 | 0 | 0 | 0 | 0 |  | 5/8/23: Full AFE approved. 5/5/23: Making good progress with RFI. We received estimates from 4 vendors and we are narrowing down the solution and costs for equipment, but process taking longer than planned. Actual less than forecast due to equipment not ordered in April per plan as we analyze options. We are reducing forecast as we are finding lower costs options for equipment and software. Forecast updated. 4/10/23: Per SG, savings were found in overall costs while working with Supply Chain to use local vendors for installs. Resulting in reduction in forecast.//bo 4/7/23: AFE pending review and approval to submit to workflow. Digital signage vendors engaged for RFI. Equipment ordered for initial testing. Forecast updated based on pending AFE. 3/6/23: Interim AFE approved on 2/22. Planning in progress for pilot sites. Equipment to be ordered based on pilot site requirements. Forecast updated. | 2023-05-08 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 2698 | 85429 | 50700 | 0 |  |  | Gingras, Stephan | Sauger, Joseph M. |  |  | 1 | 45489 |  | Administrator, System | Independent | Aqua | 2022-08-30 | IT
OT Enterprise VMs Backup and Disaster Recovery | Item | Open | MCAP | 1348181M2201 | Exempt | 1991963 | Gay, Elena | IT | 6. Operational | Defined | OT & IT Field Ops | -213 |  |  | -212.94 | -1064 | 851 | Red | 43000 | -43000 | 0 | -213 |  |  | 183000 |  |  | 183000 | Full | 183000 | 151903 |  | 151903 | No | Green | 2022-07-01 | 2022-06-27 | 2022-06-27 | 2023-01-15 | 2023-01-31 |  |  | 700.06 | -2175.87 | 412 | 850.87 |  |  | 851 | Red | [11 empty] | 1/25/23: Spoke to Elena, $258k should not have been forecasted in 2023. Only $4.4k is expected in Jan 2023. Unable to change Jan forecast.//bo 1/19/2023: Updated Operational date to reflect forecast.//bo 12-8-2022 (EG) - forecast amounts for 2023 are not entered by me and was instructed not to remove. This project is still coming in under budget. 12-2-2022(EG) - project will be under around $14K for November. As team was implementing, more affordable solutions were found to cause project savings. 11-21-2022 (EG) - forecast fields locked - will not need a supplemental. Project will come in at or below budget. 6/16/2022 - AFE Submitted and moved forecasts - expect delays in hardware - vendor provided 90-120 days. 3/9/22 - Delayed due to availability of resources from reprioritization of projects. DC | 2023-02-10 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | -1064 | 851 |  |  | 152116 |  | Gingras, Stephan | Parker, Brian K. |  |  | 1 | 41703 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
OT Enterprise VMs Backup and Disaster Recovery Phase II | Item | Open | MCAP | 1348181M2305 | Exempt |  | Gay, Elena | IT | 2. Pending AFE | Defined | OT & IT Field Ops |  | 180000 |  | 180000 | 180000 | 0 | Green | 180000 | -32000 | 148000 | 32000 |  |  | 176188 |  |  |  | Full | 176188 |  | 180000 | 180000 | No | Green | 2023-05-01 |  |  | 2023-10-01 | 2023-12-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 60000 | 60000 | 30000 | 30000 | [5 empty] | 4-4-2023 - AFE pending review from mgmt. AFE not approved yet. Moved forecast. 1/25/23: Leaving Operational Date as 12/31/23 right now per EG.//bo | 2023-04-04 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 120000 | 60000 |  |  |  | Gingras, Stephan | Parker, Chris |  |  | 1 | 45490 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
OT Windows 10 HMIs IPC Upgrade | Item | Open | MCAP | 1348181M2203 | Exempt | 2011338 | Gay, Elena | IT | 6. Operational | Defined | OT & IT Field Ops | 6745 |  |  | 6745.19 | 6745 | 0 | Green | 266000 | -234000 | 32000 | -25255 |  |  | 126000 |  |  | 126000 | Full | 126000 | 89268 |  | 89268 | No | Green | 2022-08-01 | 2022-08-04 | 2022-08-04 | 2022-12-22 | 2023-01-20 |  |  | 6498.26 | 246.93 | [17 empty] | 1/25/23: $5k forecasted in Jan is not expected to occur. Unable to remove.//bo 8-29-2022 - EG Adjusted Forecast - project does not need supplemental. Delayed start due to resource constraints. 12-8-2022 EG - removed the large $89K from 2023 - not sure where they came from. Adjusted the project to the proper amounts. | 2023-03-09 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 6745 | 0 |  |  | 82522 |  | Gingras, Stephan | Parker, Brian K. |  |  | 1 | 41696 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
PAM / SIMEIO BEYOND TRUST | Item | Open | MCAP | 1348171M2204 | Exempt | 2053660 | Camacho, Juan | IT | 3. Active | Emergent | Infrastructure & IT Ops | 18993 | 67696 |  | 86688.6 | 88183 | -1494 | Yellow |  | 100000 | 100000 | -13311 |  |  | 254000 |  |  | 254000 | Full | 254000 | 157299 | 67696 | 224995 | No | Green | 2022-12-01 | 2022-12-23 | 2022-12-23 | 2023-04-19 | 2023-06-30 |  |  | 5575.33 | 3510.91 | 4494.38 | 5411.98 | 6906 | 6906 | -1494 | Red |  |  | 6640 | 61056 | [7 empty] | 5 May- Asset / server onboarding has been given the green light to be coordinated and re-planned. The Network Department efforts will be initiated under a separate "Phase II" approach. The Disaster Recovery solution has been defined and approved by SME's and Leadership. D/R server will be installed in Culpepper, primary D/R approach to retrieve emergency passwords will be via Cell/Hotspot. Focus now will be on end user training, asset cutovers, and Network Phase II efforts 7 Apr- Onboarding and cutover of server assets have been put on hold effective 4 Apr due to unforeseen issues between the PAM Password Safe solution and existing solutions already existing within our current environment. In depth functional testing will be required between the PAM solution and solutions within the network. 7 Apr- Forecast -9k due to initial adjusted resource involvement. Vendor led initial environment build and team Buckeye was in a support posture. 3 Mar- Team Simeio have commenced importing PAM / Password Safe solution onto the Buckeye environment. JC 21 Feb- Held updated ARC review with project team per the request of Buckeye Security Team to discuss the remaining requirements (ports, firewall, URL) and to ensure we met internal security measures and practices. JC 27 Jan- Project kick-off held 27 Jan. No resource Time/Entry for Jan due to kick-off during the end of Jan 2023.Will now collaborate with vendor to compile implementation Plan & timeline. Remaining costs are to cover Resource Time/Entry. JC 11 Jan- Collaborating with vendor to commence project kick-off asap followed by verification workshop. JC | 2023-05-04 | IT | Camacho, Juan | Corporate | Pipelines and Terminals | IT |  | Corporate | Corporate |  | 13581 | 73108 |  |  | 138306 |  | Gingras, Stephan | Gehringer, Todd |  |  | 1 | 46393 |  | Meitzler, Antoinette | Independent | Aqua | 2022-12-20 | IT
Patching Solution - SD Related | Item | Open | MCAP |  | Exempt |  | Pellum, Brianna | IT | 1. Proposed |  | Infrastructure & IT Ops |  | 125000 |  | 125000 | 125000 | 0 | Green | 125000 |  | 125000 | 0 | [9 empty] | 125000 | 125000 | No | Green | 2023-05-01 |  |  |  | 2023-09-30 | 8 | Yellow |  |  |  |  | 0 | 0 | 0 | Green |  |  | 25000 | 25000 | 25000 | 25000 | 25000 |  |  |  |  | 3/08/23: Changed Cash Flow to May start date per Hung. Project going through ARC.//bo Cash flow pushed out to March due to ACR process review. BP | 2023-03-08 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 50000 | 75000 |  |  |  | Gingras, Stephan |  |  |  | 1 | 45474 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
PC Purchase - 2022 | Item | Open | MCAP | 1348178M2201 | Exempt | 2045125 | Geier, John | IT | 3. Active | Emergent | Infrastructure & IT Ops | 27563 | 9600 |  | 37162.52 | 38868 | -1706 | Yellow |  |  |  | 37163 |  |  | 361000 |  |  | 361000 | Full | 361000 | 314607 | 9600 | 324207 | No | Green | 2022-12-01 | 2022-11-17 | 2022-11-17 | 2022-12-31 | 2023-07-31 |  |  | 22073.27 | 2413.16 | 1581.84 | 1494.25 | 3200 | 3200 | -1706 | Red |  | Buckeye/Customer Schedule | 3200 | 3200 | 3200 | [6 empty] | 5/5/23 - Imaging and shipping underway. // jg 3/31/23 - Imaging commenced. Expected to continue over the next couple of months. // jg 3/6/23 - Imaging is last remaining item open on PO. Forecast and operational date adjusted. // jg 1/31/23 - All equipment received. Imaging to begin week of 2/6. Moved operation date till EOM // JG 12/30/22 - Awaiting remaining equipment. Forecast updated for early 2023. Variance due to supply chain. JG 12/7/22 - no changes to forecast or budget. expected ship date is 12/21 | 2023-05-05 | IT |  | Corporate | Corporate | IT |  | Corporate | Corporate |  | 26068 | 7894 | 3200 |  | 287044 |  | Gingras, Stephan | Tran, Hung |  |  | 1 | 46229 |  | Meitzler, Antoinette | Independent | Aqua | 2022-11-15 | IT
PC Refresh Program 2022 | Item | Open | MCAP | 1348179M2202 | Exempt | 1981084 | Geier, John | IT | 3. Active | Defined | Infrastructure & IT Ops | 124014 | 12150 |  | 136163.9 | 137196 | -1032 | Yellow |  |  |  | 136164 |  |  | 649000 |  | 377000 | 649000 | Supplemental | 1026000 | 655630 | 12150 | 667780 | No | Green | 2022-06-01 | 2022-05-20 | 2022-05-20 | 2022-12-31 | 2023-07-31 |  |  | 110344.08 | 7485.59 | 3166.24 | 3017.99 | 4050 | 4050 | -1032 | Red |  |  | 4050 | 4050 | 4050 | [6 empty] | 5/5/23 - Imaging and shipping underway. // jg 3/31/23 - Imaging commenced. Expected to continue over the next couple of months. // jg 3/7/23 - Imaging and shipping to Houston remaining on effort. // jg 2/09/23: $180k will be adjusted from PC Refresh 2023 Budget to 2022 Carry-over.//bo 2/5/23 - All equipment received. Imaging and shipping to Houston this month. // JG 12/30/22 - Awaiting the remaining equipment and imaging to be complete. Forecast updated - JG 12/7/22 - Still awaiting equipment from Advantek. No changes otherwise 11/8/22 - Updating November forecast for pending Advantek and December for supplement equipment AFE 10/27/22 - Awaiting quote for additional hardware. Once received a supplemental AFE will be submitted 10/1/22 - Waiting on arrival of docking stations which have been backordered. Vendor advised they could be available next month. 9/1/22 - Jim and his team are getting started on the 22 refresh portion. Some equipment we were hoping to come in during August will come in September now. 8/1/22 - Our $355,000 order that was coming in late August and September, came in full at the end of July. Jim and his team now can get started on the 22 refresh portion. August and September have been adjusted to reflect this change. 7/5 - Our one shipment of PC's forecasted for the 2nd week of July came in the last week of June, thus the overage for this month. Made the adjustments for July totals. 6/3/22 - No new updates on forecast as we are expecting some equipment to arrive in June. 5/4 - Jim Flynn will be getting me the quotes this week and I will submit the AFE this week. This forecast is updated after talking with Jim Flynn on 5/4. 4/5/22 - Met with Jamie on 4/5 to review quotes for this project. Financial forecast has been updated based on our talks and latest estimates from our vendors. 3/7/22 - I continue to meet with Jamie on getting the mostupdated quotes for this project. Financial forecast has been updated to show the bulk of the equipment coming in late Q2, based on our latest estimates from our vendors and my talk with Jim Flynn. 2/4/22 - This the PC Refresh Project for 2022. I met with Jamie on 2/3, on getting the most updated quote for this project and building out a schedule and charter and the next steps forsubmitting the AFE for this project. This will not kick off in Q1. 1/3/22 -This the PCRefreshProject for 2022. I will work with Jamie on getting the most updatedquote for this project and building out a schedule and charter and submitting the AFE for this project. | 2023-05-05 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 120996 | 11118 | 4050 |  | 531616 |  | Gingras, Stephan | Virupakshi, Sudhakar |  |  | 1 | 41692 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
PC Refresh Program 2022 PN Correction | Item | Open | MCAP | 1348179M2205 | Exempt | 2045125 | Geier, John | IT | 8. Canceled | Emergent | Infrastructure & IT Ops | -10414 |  |  | -10413.75 | -10414 | 0 | Green |  |  |  | -10414 | [6 empty] | Full |  | 483 |  | 483 | No | Green | 2022-12-01 |  |  | 2023-12-31 | 2023-12-31 |  |  | -10457.08 | -439.24 | 482.57 | [16 empty] | 3/04/23: Project actuals are zero (costs reclassed to PC Purchase 2022). Project created erroneously. Cancelled project.//bo | 2023-03-04 | IT |  | Corporate | Pipelines and Terminals | IT |  |  |  |  | -10414 | 0 |  |  | 10896 |  | Gingras, Stephan | Virupakshi, Sudhakar |  |  | 1 | 46450 |  | Meitzler, Antoinette | Independent | Aqua | 2023-01-11 | IT
PC Refresh Program 2023 | Item | Open | MCAP |  | Exempt |  | Hagerty, Sean | IT | 1. Proposed |  | Infrastructure & IT Ops |  | 332500 |  | 332500 | 332500 | 0 | Green | 512500 |  | 512500 | -180000 | [9 empty] | 332500 | 332500 | No | Green | 2023-06-01 |  |  |  | 2023-09-30 | [13 empty] | 320000 | 5000 | 5000 | 2500 |  |  |  |  | 5/5/23 - delay start due to resource constraints. SH 4/6/23 - delay start due to resource constraints. SH 3/31/23 - Still on track for May start // jg 2/09/23: $180k will be adjusted from PC Refresh 2023 Budget to 2022 Carry-over.//bo budget and forecast reduced SG | 2023-05-05 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 320000 | 12500 |  |  |  | Gingras, Stephan |  |  |  | 1 | 45472 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
Procedure Management Software | Item | Open | MCAP | 1348174M2203 | Exempt | 2023051 | Schneider, David | IT | 3. Active | Defined | Enterprise Business Apps | 42648 | 283300 |  | 325948.26 | 323489 | 2459 | Yellow | 159450 | 180000 | 339450 | -13502 |  |  | 561000 |  |  | 561000 | Full | 561000 | 164035 | 283300 | 447335 | No | Green | 2022-10-01 | 2022-09-19 | 2022-09-19 | 2023-02-28 | 2023-07-31 |  |  | 21733.7 | 3535.61 | 6819.91 | 10559.04 | 14400 | 14400 | -3841 | Red |  |  | 11100 | 63500 | 77000 | 74700 | 57000 |  |  |  |  | 5/5/23: Designs in progress, but taking longer than planned. Configurations are being pushed to June. Forecast updated. 4/7/23: Designs in progress. Team provided overview and demo's with SME's and OM's on ATR application to gain feedback on designs. Under forecast as configuration work still pending design completion. Forecast updated. 3/7/23: Designs in progress. Team meeting with key stakeholders on design decisions to get feedback. Under forecast as less work completed than planned. Forecast updated. 2/7/23: Designs discussion are in progress and moving slowly. Pending design decisions will delay design signoff and the start of configurations. Actual less than forecast as less work completed by vendor and Buckeye team. Forecast updated. 1/19/2023: updated Operational Date to reflect forecast.//bo 1/6/23: Design & Azure build discussions in progress. Draft schedule created. Forecast updated. 12/6/22: Kickoff completed on 11/30. Vendor delayed in scheduling project kickoff until the end of the month, so under forecast due to no work being completed in Nov. Forecast updated based on updated project schedule. 11/7/22: Contracts signed. Vendor onboarded. Pending project kickoff. Delays in getting vendor onboarded and kickoff scheduled impacted actuals. Forecast updated. 10/7/22: AFE approved. SOW's & Software Agreement signed. Project kickoff pending. Forecast updated. 9/28/22: Vendor contract process taking longer than planned. Forecast updated. 9/8/22: Sponsor update completed. SOW, MSA, order form & AFE pending. Planning for September project kickoff. Forecast updated. 8/5/22: SOW, MSA & order form in progress. Sponsor update & AFE pending. Planning for September project kickoff. Based on discussions with vendor it looks like costs will be $500K to $550K MCAP and another $400K to $450K in expense to digitize all procedures and manuals. Expense costs would be in Q1 & Q2 of 2023. Forecast updated to show estimated capital costs only. 7/6/22: SOW, contract and business case in progress. AFE pending sponsor update and project approval. Planning early September projectkickoff. Completion may slip into 2023. Forecast updated. -6/23/2022: Updated Operational Date based on Forecast.//bo 6/6: Completed calls with ATR Smart Procedures on installation, IT & Security, and procedure/manualconversion/digitization. Pushing costs to start in July. Forecast updated. 5/4: Demos completed. Selection process in progress. No change to forecast at this time. 4/6:Demos scheduled for late April, so we may not spend as planned in May. Forecast adjusted. 4/4: RFP closed 3/11. Responses being evaluated. Demos to be scheduled. No change to forecast at this time. 3/1: RFP Kickoff 2/14. AFE to be submittedend of Apr or early May. Forecast updated, but rough estimate. A more accurate forecast will be available once a vendor is selected. 1/31: RFP process in progress. Sourcing event planned for Feb. -12/10/2021: Cash Flow Start date moved to 4/01/22 per SG.//bo -9/29/2021: Increased 2022 Budget from $700k to $914k per Jaime Juan.//bo | 2023-05-05 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 32089 | 85159 | 208700 |  | 121387 |  | Gingras, Stephan | Gardner, Dale |  |  | 1 | 41720 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
Project & Portfolio Management | Item | Open | MCAP | 1348170M2301 | Exempt | 2109792 | Gingras, Stephan | IT | 3. Active | Emergent | Infrastructure & IT Ops | 60211 | 89633 | 26478 | 149843.87 | 151013 | -1169 | Yellow |  |  |  | 149844 |  |  | 179725 |  |  | 179725 | Full | 179725 | 60211 | 116111 | 176322 | No | Green | 2023-04-01 | 2023-04-12 | 2023-04-12 | 2023-06-15 | 2023-06-30 | [5 empty] | 60210.87 | 61380 | 61380 | -1169 | Yellow |  |  | 18714 | 68077 | 2842 | [5 empty] | 26478 | 4/6/23 Forecast Entered SG | 2023-04-07 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 147002 | 2842 |  |  |  | Gingras, Stephan | Tran, Hung |  |  | 1 | 46853 |  | Meitzler, Antoinette | Independent | Aqua | 2023-03-29
Railhand Solution Rollout to Remaining Rail Sites | Item | Open | MCAP |  | Exempt |  | Gay, Elena | IT | 1. Proposed |  | OT & IT Field Ops |  | 170000 |  | 170000 | 170000 | 0 | Green | 175000 |  | 175000 | -5000 | [9 empty] | 170000 | 170000 | No | Green | 2023-06-01 |  |  |  | 2023-12-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 40000 | 40000 | 30000 | 25000 | 35000 | [7 empty] | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 40000 | 95000 | 35000 |  |  | Gingras, Stephan |  |  |  | 1 | 41704 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
RCA Replacement | Item | Open | MCAP |  | Exempt |  | Gingras, Stephan | IT | 1. Proposed |  | OT & IT Field Ops |  | 485000 |  | 485000 | 485000 | 0 | Green | 485000 |  | 485000 | 0 | [9 empty] | 485000 | 485000 | No | Green | 2023-08-01 |  |  |  | 2023-11-30 | [13 empty] | 0 | 0 | 62500 | 62500 | 62500 | 187500 | 110000 |  | 5/8/23 forecast changed to later in the year. SG -2/9/2023 Budget Adjusted based on pilot running longer than expected. ?-10/31/22 - Cost Reduction by $140,000 per ELT reduction request.//bo | 2023-05-08 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 | 125000 | 360000 |  |  | Gingras, Stephan |  |  |  | 1 | 45510 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
RCA Replacement Solution Pilot | Item | Open | MCAP | 1348176M2201 | Exempt | 1981786 | Schneider, David | IT | 6. Operational | Defined | OT & IT Field Ops | 1806 | 0 | 15361 | 1805.51 | 12263 | -10457 | Red |  |  |  | 1806 |  |  | 199000 |  |  | 199000 | Full | 199000 | 103440 | 15361 | 118801 | No | Green | 2022-06-01 | 2022-05-30 | 2022-05-30 | 2022-12-31 | 2023-04-07 |  |  | 418.03 | 1121.65 | 4323.31 | -4057.48 | 3200 | 3200 | -7257 | Red |  |  | 0 | [7 empty] | 15361 | 5/4/23: Pilot completed. Pending project close. The pilot did prove that we could replace the RCA with a new Edge device, but we determined that there could potentially be a failover issue with this device. The new version of SCADA would support this device and failover so it was determined that we would stop the pilot and future installs until the SCADA upgrade is completed. Equipment is being removed and returned to the vendor. We have a negative actual as we have been accruing for equipment received but not invoiced and now it is being returned. 4/7/23: Fullerton testing completed. Macungie & TierPoint pending. Forecast updated. 3/6/23: Pilot install at Fullerton completed on March 1. Testing in progress. Macungie & TierPoint pilot install ETA is April. Under forecast as less work done than planned. Forecast updated. 2/7/23: The pilot install for first site has been pushed to the end of February due to availability of local technicians to support install. Other operational activities are taking priority. The remaining 2 install dates are TBD. Actual less than forecast due to delays in pilot install. Forecast updated. Estimated operational date updated. -1/24/23: Updated Operational Date based on forecast.//bo 12/15/2022 Supply chain issues and resource availability have caused delays until Jan and possibly Feb and caused variance. SG 10/31/2022 Work Continues to be on pace to complete this year, reduced forecast to be more inline wis SOW and progress of work completed. SG 9/30/2022 Behind schedule working with the vendor to get access for the team and software installed. SG 9/1/22 - We met on Tuesday with our vendor and continue to follow the project plan and our on schedule for completion this year. Some equipment and licenses we were hoping would hit and come in during August have been pushed to September. 8/1/22 - The equipment order did not come in during July as hoped, and is now scheduled to come in August. Schedule updated and reflects current projected forecast. 7/5/22 - The AFE is approved and we have a kickoff call with the vendor on 7/7. 6/3/22 - AFE approved this week. Schedule updated and reflects current forecast. 5/2/22 - We are hoping to submit the AFE after the 5/11 ARC meeting. The forecast is updated to our best current estimate. 4/5/22 - We are hoping to submit the AFE later in the week. The forecast is updated to our best estimate but will have a more accurate picture once the AFE is submitted. 3/7/22 - This projectwas handed over to me from Stephan. Jen and I met with the vendor last week and we are reviewing the updated SOW. Right now the forecast is updated to our best estimate, but I will have the full picture by the end of the month of March. 2/28/2022 changed to Dave Barnette as PM SG ?- 10/19/2020 Deferred to 2022 per conversation between Dale and Chris P.//bo | 2023-05-04 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 5863 | -4057 |  |  | 101634 |  | Gingras, Stephan | Virupakshi, Sudhakar |  |  | 1 | 38303 |  | Administrator, System | Independent | Aqua | 2020-08-24 | IT
Replace Splitter/Merger Process | Item | Open | MCAP | 1348173M2201 | Exempt | 1956154 | Pellum, Brianna | IT | 8. Canceled | Defined | OT & IT Field Ops | -6605 |  |  | -6604.76 | -6605 | 0 | Green |  |  |  | -6605 |  |  | 7000 |  |  | 7000 | Full | 7000 | 0 |  | 0 | No | Green | 2022-03-01 | 2022-03-15 | 2022-03-15 | 2022-04-15 | 2022-09-29 |  |  | -6485.41 | -119.35 | [17 empty] | 3/04/23: Project actuals are zero (costs reclassed to 1348173). Project no longer considered Capital. Cancelled project.//bo 1/12/2023: Reclass submitted to move expenses to 1348174 since Asset of $2.1k is less than $2.5k required for project to be Capitalized.//bo 9/30/22 Project Work Completed, in process of closing the project. To be closed by the end of Oct. SG 8/31/2022 Still waiting for data and email program to be moved. SG 7/29/2022 Software in production still pending migration of data and email program expected in August. SG 6/30/2022 Still in process of going live/ will be completed 7/30. SG 5/30/22 UAT will be completed after month end close and go-live is expected before end of month. SG 4/29/22 Setting up end users and doing UAT this month and should be closed by 5/27. SG 3/29/2022 Due to PO slowness and AFE approval work delated until My and should be complete in May. SG 3/31/20222 On Schedule and Budget, AFE Approved, Software purchased, in process of setting up on IT PCs. Next month Test Plan, Test Scripts, functional testing. SG 2/28/20222 Forecast updated to reflect approved schedule, software purchase, test, go-live. SG | 2023-03-04 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | -6605 | 0 |  |  | 6605 |  | Gingras, Stephan | Sinatore, Kathleen J. |  |  | 1 | 41719 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
Replatform Cognos Cubes to Microsoft Platform | Item | Open | MCAP | 1348175M2301 | Exempt | 2112821 | Sridhar, Malini | IT | 3. Active | Defined | Infrastructure & IT Ops | 2400 | 946000 |  | 948400 | 524000 | 424400 | Red | 1270000 |  | 1270000 | -321600 |  |  | 1264574 |  |  | 1264574 | Full | 1264574 | 2400 | 1074000 | 1076400 | No | Green | 2023-04-01 | 2023-04-27 | 2023-04-27 | 2023-12-31 | 2024-03-31 | [5 empty] | 2400 | 33000 | 33000 | -30600 | Red |  |  | 90000 | 96000 | 109000 | 161000 | 150000 | 150000 | 105000 | 85000 |  | 05/04/23 Update: The contract with Vendor was received only on 4/28/23 around 5 PM. Hence the 50% 0f $61,500 (Quick launch installation) is accrued in May. 04/25/23 Update: Forecast now includes some additional expenses related to Outside consultants and misc. - 04/0/23 Update: Will be using Preferred Strategies as the solution provider instead of Sierra Digital. This reduces the MCAP demand and increases OPEX. The project is planned to carry into the first couple months of 2024. Forecasts and budgets have been adjusted. Some of the extra MCAP funds will be used to fund the ITTha PMO PPM solution emergent project. -10/31/22 Update: An alternate solution has been proposed and we are therefore reevaluating the forward path for the project. This will delay the capital spend and AFE submission until early Q1 2023. - 09/08/22 Update: Adjusted forecast as capital portion of the project is not scheduled to start until late Q4.//jn - 08/04/22 Update: estimated ROM from Sierra Digital for Phase 2 = $900K. Plus Buckeye labor, fringe, interest, CWIP, and contingency.//jn - 08/02/22 Update: estimated ROM from Sierra Digital for Phase 2 = $800K. Plus Buckeye labor, fringe, interest, CWIP, and contingency.//jn -07/28/2022 Update: $15K of this project budget was reallocated to an emergent project. The 2022 Budget was adjusted accordingly.//jn -07/27/2022 Update: $150K of this project budget was reallocated to the Right Angle Project (RAP). The 2022 Budget was adjusted accordingly.//jn - 07/26/22 Update: Phase 1 requirements will be through Q3. Due to the nature of the initial work, the initial spend will need to be MEXP instead of MCAP. Shifted forecast to Q4 and added forecast to 2023 as it will be a carry-over project.//jn -07/12/2022 Update: Project will have a Phase 1 for requirements gathering. Capital portion of project will begin later this year. Removed capital forecast for July and August and shifted to Q3.//jn -6/23/2022 Update: $54k will be sourced from this Budget to Ivanti Application Control Project. July Forecast removed and balance from $70.5k will bemoved into Aug Forecast.//bo -5/10/2022: Shifted Forecast to July start date. Moved $200k into 2023 forecast.//bo -10/25/2021: Reduced 2022 Budget from $1M to $900k.//bo | 2023-05-04 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 188400 | 420000 | 340000 |  | 128000 | Gingras, Stephan | Virupakshi, Sudhakar |  |  | 1 | 41690 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
RightAngle Enhancements | Item | Candidate | MCAP |  | Exempt |  | Martin, John T | IT | 8. Canceled |  | Enterprise Business Apps |  |  |  | 0 | 200000 | -200000 | Red | 200000 |  | 200000 | -200000 | [11 empty] | No | Green |  |  |  |  | 2023-11-30 | [6 empty] | 0 | 0 | 0 | Green | [11 empty] | 5/09/23: This initiative will now be considered MEXP under Value Creed (1358174) and will no longer be MCAP. Cancelling project in OPPM.//bo 3/6 budget adjusted per Rahul, SG | 2023-05-09 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 |  |  |  |  | Gingras, Stephan |  |  |  | 1 | 45932 |  | Administrator, System | Independent | Aqua | 2022-09-29 | IT
RightAngle Project (RAP) | Item | Open | MCAP | 1358174M2101 | Exempt | 1847631 | Splawn, Kimberly | IT | 6. Operational | Defined | Enterprise Business Apps | -89625 |  |  | -89625.23 | -89625 | 0 | Green |  |  |  | -89625 |  |  | 4089000 |  | 266000 | 4089000 | Supplemental | 4355000 | 4348269 |  | 4348269 | No | Green | 2021-05-01 | 2021-05-24 | 2021-05-24 | 2022-07-31 | 2022-07-31 |  |  | -89625.23 | [18 empty] | 3/24/23: Confirmed with CL that POs are closed. I confirmed in JDE that WO is closed.//bo 2/10/23 - Reclass correction. Funds incorrectly reclassed to RAP instead of Indirect Software. DC 12/6 No forecast for December. Plan to close project by 12/31.-KS 11/9/22 - Variance due to duplication of forecast/reaccrual. DC 11/4 No forecast for November. -KS 10/7 Still pending Veritas invoice submittal, pushed to Oct forecast. Tax group will reclass $26K in charges related to the RA upgrade. -KS 9/8 Final invoice for Veritas will be paid, along with Mark Stiles invoicing in Sept. No further costs planned and project will be closed late Sept. -KS 8/8 AFE supplement approved. Revised Aug and Sep forecast for Veritas change.-KS 8/5 Right Angle went live on Aug. 1. AFE supplement is routing for approval. -KS 7/25 Remaining contingency $328,600 removed. AFE supplement submitted for $266,206- KS 7/7 Issued new change for Mark Stiles 46.5 hours $12,797.50. New PO issued for Veritas change $300,975 to address additional effort and travel. Supplemental AFE will be processed in July for final offer. Go Live on track for 8/1/22 - KS 6/9/22 - 290k change order added to June forecast. Additional work currently being bid out for work to be performed July-September. Amount to come, supplemental pending. DC 6/7-Change order for $60K approved for Mark Stiles, Int and UAT testing in progress with cutover and day 1 planning underway.-KS 5/10 - Expected 290k change order for June/July to be enacted. DC 5/4/22 Decreased forecast by $253K until all changes are approved. Remaining contingency updated to 328,600. UAT on target to begin mid-May. -KS 4/7/22 March over by $15,389 due to internal labor billing error corrected from January. Vendor change order for $290K approved internalin in Ja 2022 will be processed within the next month. Updated contingency to $293,577. -KS 3/7/22 February is over by $24k due to reclass of January internal charges. March reduced by $86k due to vendor delivery date change and contingencyremoved from forecast.-KS 2/6/22 Training and Test Strategies delivered, cutover and archiving planning, report development and unit testing for integrations has begun.-KS 1/6/22 Workplan updated with Buckeye activities and completed change assessment. The data validation andintegration activities continued. -KS 12/6/21 Completed review of 34 business scenarios, two report designs, pricing integrations are completeon the Veritas side and current state network design is complete. -KS 11/5/21 High level project work plan received concurrence and baseline costs pendingdelivery in early November. BES business RA requirements reviewed with respective stakeholders. SMEs are now set up to access Right Angle S21 Cloud environment. -KS 10/11/21 - Lauren to send additional accrual to be submitted to scoresheet process pending possible add in to September accruals, otherwise expected invoice payment to reforecast to October. DC 10/7/21 Veritas is close to finishing the Planning phase. Sprint 2 completed and Sprint 3 is in progress. Design/testing of the interfaces and data conversions is in progress. Infrastructure Plan and Scope Baseline are in approval. Workplan has been delivered for review. -KS 9/8/21-Planning phase is still in progress, Sprint 1 completed and Sprint 2 is in progress. Veritas is working to resolve the project execution issues and will baseline the project in September. TheS21 development prototype was installed. Design/testing of the interfaces and data conversions is in progress and functional work with the daily risk exposure tie outs. -KS 8/5/21 - 9 of the 15 Planning deliverables have been submitted and two deliverables have been approved. Implementation phase will proceed on August 9th with Planning deliverables approvals completing during Implementation. -KS 7/6/21 - Requirements development and change management strategy in development. Comm plan created along with change management planning. Riskassessment conducted. -KS 6/7/21 - AFE, SOW and kickoff completed. Planning and onboarding in progress and requirements sessions have been scheduledfor week of June 7. KS Assessment period is wrapping up and an 8-week planning/scoping analysis will begin in March/April. Forecastsadjusted to reflect planning period. | 2023-03-24 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | -89625 | 0 |  |  | 2526933 |  | Gingras, Stephan | Stiles, Mark |  |  | 1 | 38289 |  | Administrator, System | Independent | Aqua | 2020-08-24 | IT
S2C Phase 1B - Coupa Buying:MCAP | Item | Open | MCAP |  | Exempt |  | Schneider, David | IT | 1. Proposed |  | Enterprise Business Apps |  | 0 |  | 0 | 0 | 0 | Green | 350000 | -280000 | 70000 | -70000 | [9 empty] | 630000 | 630000 | No | Green | 2024-01-01 |  |  |  | 2025-03-31 | [17 empty] | 0 |  |  |  | 4/11/23: Per RD, no longer happening in 2023. Moved original 2023 Budget of $350k to 2024 and $280k to 2025.//bo 2/24/23: 2024 forecast is currently $280k per Dale G. Total EAC is $350k (with $70k CY EAC).//bo 2/13/2023: Per Dale & SCM Team, the cash flow will start in Nov 2023.//DS 1/19/2023: Updated Operational date based on forecast.//bo forecast moved to Q3 start date. SG | 2023-04-17 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 |  | 0 |  | 350000 | Gingras, Stephan |  |  |  | 1 | 45914 |  | Administrator, System | Independent | Aqua | 2022-09-26 | IT
SCADA Citrix Upgrade | Item | Open | MCAP | 1348172M2204 | Exempt | 1991881 | Kralik, Ron | IT | 3. Active | Defined | Infrastructure & IT Ops | 63956 | 2800 | 9053 | 66756.17 | 66806 | -50 | Yellow |  |  |  | 66756 |  |  | 200000 |  |  | 200000 | Full | 200000 | 188003 | 11853 | 199856 | No | Green | 2022-07-01 | 2022-06-27 | 2022-06-27 | 2022-12-31 | 2023-06-30 |  |  | 15048.22 | 39914.86 | 7442.96 | 1550.13 | 4400 | 4400 | -2850 | Red |  |  | 2200 | 600 | [6 empty] | 9053 | 5/5/23: Schedule updated to accommodate additional Mocado and Coffeebean setup work required, per CoreBTS internal review. No financial CR required for additional effort, per CoreBTS. Testing to occur in May. 4/6/23: Due to vendor resource changes, Testing activities to occur in April. Sean Hess has replaced Will Elliott as the CoreBTS Technical resource. 3/7/23: In Stabilize Phase. Testing activities to occur in March. 2/7/23: Will complete Build Phase and enter Stabilize Phase in February. 1/9/23: No updates to forecast. 12/7/22: Forecast adjustment made to shift $20K of 4Q2022 spend to 1Q2023. 11/7/22: CoreBTS resource has been granted the necessary Buckeye systems access to begin project discovery activities. Project discovery and documentation activities are underway. 10/7/22 CoreBTS work to begin on the project in October. September $50K underspend vs forecast was due to early acceptance of SOW in August instead of September; this resulted in $50K "upon SOW acceptance" payment to CoreBTS occurring in August instead of September as forecast. 9/1/22 - We are scheduling CoreBTS to come onsite during September or early October for our upgrade. The 50k CoreBTS got signed and approved in August not September, thus the difference for this month. 8/1/22 - We are scheduling CoreBTS to come onsite during September for our upgrade. Schedule and forecast are updated to reflect this. 7/5/22 - AFE is approved and we have signed off on the SOW. Now that we have the counter-signed SOW, we are scheduling time for Sean to come into the office in August to work on this 14-week project. 6/27/22 - AFE approved today. 6/22/22 - The AFE has been submitted today. Note ** We are borrowing 100k from the SCADA Server Replacement - Virtual Servers at MB & BCC project, and this was noted in the AFE as well. ** 6/3/22 - Forecast is updated for Q3 start. Will get the AFE approved in June. 5/2/22 - We continue to work with our vendor as we start to gather and finalize quotes. Forecast is updated for Q3 start. 4/5/22 - We continue to work with Sean Hess as we start to gather quotes and work on the Project Charter.Forecast is updated for Q3 start. 3/7/22 - We are working with Sean Hess as we start to gather quotes and work on the Project Charter. Steve is getting the most updated quotes for this project and this willnot kick off in Q1. Forecast is updated for Q3 start. 2/4/22 - I met with Steve on 2/2 to start to gather quotes and work on the Project Charter. Steve is getting the most updated quotes for this project and this will not kick off in Q1. 1/3/22 - This is the Scada Citirx Upgrade Project for 2022. I will work with Steve on getting the most updated quotefor this project and building out a schedule and charter and submitting the AFE for this project. | 2023-05-05 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 62406 | 4350 |  |  | 124047 |  | Gingras, Stephan | Gardner, Dale |  |  | 1 | 42196 |  | Administrator, System | Independent | Aqua | 2021-09-21 | IT
SCADA Inf. Lifecycle Program 2022 | Item | Open | MCAP | 1348172M2202 | Exempt | 1957036 | Geier, John | IT | 6. Operational | Defined | Infrastructure & IT Ops | 1481 |  | 500 | 1481.43 | 1481 | 0 | Green |  |  |  | 1481 |  |  | 50000 |  |  | 50000 | Full | 50000 | 36147 | 500 | 36647 | No | Green | 2022-04-01 | 2022-03-25 | 2022-03-25 | 2022-12-31 | 2023-02-28 |  |  | 821.43 | 550 | 110 | [15 empty] | 500 | 2/5/23 - All equipment received. Awaiting final invoice then closeout // JG 1/24/23: Updated Operational Date based on current forecast.//bo 12/30/22 - Wrapping up effort. Target is February EOM. JG 12/7/22 - No new updates this month. 10//27/22 - No new updates this month. 9/1/22 - No new updates this month. 8/1/22 - No new updates this month. 7/5/22 - Forecast updated and reflects current schedule. 6/3/22 - Forecast updated and reflects current schedule. 5/2/22 - We were very fortunate to get one server in early from IntegraONE, as this was forecasted to come in during June. Forecast has been adjusted and updated. 4/5/22 - AFE has been approved and the equipment has been ordered. Schedule reflects these updates. 3/7/22 - Steve is getting the most updated quotes for this project and this will not kick off in Q1. 2/4/22 - This is the Scada Infrastructure Lifecycle Program for 2022. I met with Steve on 2/2 to start to gather quotes and work on the Project Charter. Steve is getting the most updated quotes for this project and this will not kick off in Q1. 1/3/22 - This is the Scada Infrastructure Lifecycle Program for 2022. I will work with Steve on getting the most updated quote for this project and building out a schedule and charter and submitting the AFE for this project. | 2023-02-16 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 1481 | 0 |  |  | 34665 |  | Gingras, Stephan | Sinatore, Kathleen J. |  |  | 1 | 41714 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
SCADA Inf. Lifecycle Program 2023 | Item | Open | MCAP |  | Exempt |  | Geier, John | IT | 1. Proposed |  | OT & IT Field Ops |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 | [9 empty] | 10000 | 10000 | No | Green | 2023-06-01 |  |  |  | 2023-07-31 | [13 empty] | 5000 | 5000 | [6 empty] | 3/7/2023: Awaiting additional information prior to completing charter and AFE // jg | 2023-03-07 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 5000 | 5000 |  |  |  | Gingras, Stephan |  |  |  | 1 | 45483 |  | Administrator, System | Independent |  | 2022-08-30 | IT
SCADA Server Replacement - Virtual Servers at MB & BCC | Item | Open | MCAP | 1348176M2202 | Exempt | 2037450 | Geier, John | IT | 3. Active | Defined | OT & IT Field Ops | 78952 | 248000 |  | 326952.12 | 327453 | -501 | Yellow | 301000 |  | 301000 | 25952 |  |  | 708000 |  |  | 708000 | Full | 708000 | 422860 | 248000 | 670860 | No | Green | 2022-11-01 | 2022-10-20 | 2022-10-20 | 2023-06-30 | 2023-08-31 |  |  | 12835.14 | 2903.24 | 2715.09 | 60498.65 | 1000 | 1000 | 59499 | Red |  | Supply Chain | 1000 | 240000 | 5000 | 2000 | [5 empty] | 5/5/23 - Equipment expected later this month. Install being planned for June or July. // jg 4/6/23 - No updates. // jg 3/7/23 - Remaining network equipment expected in May/June. // jg 2/5/23 - Remaining network equipment expected in May/June. // JG 12/30/22 - Supply chain causing delay in network equipment arrival. JG 12/15/22 - Equipment arrived early and forecast was not reduced in December. Does not need a supplemental AFE JG 12/7/22 - No updates. Still experiencing supply chain issues 11/3/22 - Forecast update to account for equipment arriving in 2023 to complete effort 10/1/22 - No change to forecast or budget Scope changed to just MB and will carryover to 2023 due to equipment delays. SG 9/09/22: Per SG, equipment less than expected. Meeting to review carryover with team and sponsors.//bo ? 9/1/22 - We have decided to move ahead and get quotes from Steve and Jamie's vendors for equipment purchases this year for MB. Forecast updated to show equipment arriving this year. 8/1/22 - This project is still on hold until the assessment is completed for the Data Center. 7/5/22 - This project is still on hold until the assessment is completed for the Data Center. 6/22/22 - Note ** We are using 100k from our budget this year for the SCADA Citrix Upgrade project. ** 6/3/22 - This project is still on hold until the assessment is completed for the Data Center. 5/1/22 - After meeting with Chris, Dale and Todd we have decided to put this project on hold until we do an assessment on the data center. 4/5/22 -The financial forecast is updated from the vendor estimates and quotes. We will have a complete picture once we have all vendor quotes in, and decide if we are doing equipment only this year. 3/7/22 - Jen and I have met with Aveva initially and they are working on a price for their labor for this project. This project will be very dependent on the availability of the equipment needed to complete this virtual upgrade. For right now the financial forecast is updated to our best estimates. 2/4/22 - We have met twice as a team in the month of January. I willwork with Steve, Jen and Jamie on getting the most updated quotes forthis project and building out a schedule and charter and submitting the AFE for this project. I have Steve's quote from IntegraONE from 2/1 so far and Jen and Jamie are still working on gathering their quotes for this project. 1/3/22 - This is the SCADA Server Replacement upgrade project. I willwork with Steve, Jen and Jamie on getting the most updated quotes for this project and building out a scheduleand charter and submitting the AFE for this project. We have a planning meeting on 1/3/22. -6/18/2021: Project part of 2022 Budget; 1,365,395 estimated. Entered intoOPPM per month for now but dates need to be updated.//bo | 2023-05-08 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 18453 | 301499 | 7000 |  | 343908 |  | Gingras, Stephan | Gardner, Dale |  |  | 1 | 38291 |  | Administrator, System | Independent | Aqua | 2020-08-24 | IT
Server Lifecycle & Growth Program 2022 | Item | Open | MCAP | 1348172M2203 | Exempt | 1957546 | Geier, John | IT | 6. Operational | Defined | Infrastructure & IT Ops | 2363 |  | 5200 | 2362.88 | 2253 | 110 | Yellow |  |  |  | 2363 |  |  | 260000 |  |  | 260000 | Full | 260000 | 204585 | 5200 | 209785 | No | Green | 2022-04-01 | 2022-03-31 | 2022-03-31 | 2022-12-31 | 2022-11-30 |  |  | 1592.88 | 330 | 330 | 110 |  |  | 110 | Red | [10 empty] | 5200 | 2/5/23 - Closing out project by EOM // JG 12/30/22 -Due to supply chain issue, a change was made for alternate equipment. Awaiting for final build out. JG 12/7/22 - Forecast and schedule tracking 10/27/22 - Forecast and schedule are updated and on schedule. 9/1/22 - Forecast and schedule are updated and on schedule. 8/1/22 - Forecast and schedule are updated and on schedule. 7/5/22 - Forecast and schedule are updated and on schedule. 6/3/22 - We received in some equipment that was scheduled for June, thus the slight overage for the month of May. Schedule and forecast have been updated. 5/2/22 - AFE has been approved and some equipment has arrived as scheduled. Schedule and forecast are updated based on our latest estimates from IntegraONE. 4/5/22 - AFE has been approved and the equipment has been ordered. We are expecting some equipment that was in stock to come in during April. Schedule reflects these changes. 3/7/22 - Steve is getting the most updated quotes for this project and this will not kick off in Q1. Forecast is updated for a late Q2/Q3 start. 2/4/22 - I met with Steve on 2/2 to start to gather quotes and work on the Project Charter. Steve is getting the most updated quotes for this project and this will not kick off in Q1. 1/3/22 - This is the Server Lifecycle & Growth Drawdown Program for 2022. I will work with Steve on getting the most updated quote for this project and building out a schedule and charter and submitting the AFE for this project. | 2023-02-07 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 2253 | 110 |  |  | 202222 |  | Gingras, Stephan | Sinatore, Kathleen J. |  |  | 1 | 41697 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
Server Lifecycle & Growth Program 2023 | Item | Open | MCAP |  | Exempt |  | Hagerty, Sean | IT | 1. Proposed |  | Infrastructure & IT Ops |  | 250000 |  | 250000 | 250000 | 0 | Green | 250000 |  | 250000 | 0 | [9 empty] | 250000 | 250000 | No | Green | 2023-06-01 |  |  |  | 2023-08-31 | [12 empty] | 0 | 235000 | 5000 | 5000 | 5000 |  |  |  |  | 5/5/23 - Moved forecast start to June // SH 3/31/23 - Moved forecast start to May // jg 3/6/23 - Push forecast till April '23 as equipment quotes are still pending. // jg | 2023-05-05 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 235000 | 15000 |  |  |  | Gingras, Stephan |  |  |  | 1 | 45473 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
SharePoint Transformation | Item | Open | MCAP | 1348180M2201 | Exempt | 2002758 | Sridhar, Malini | IT | 3. Active | Defined | Enterprise Business Apps | 269583 | 283903 | 89899 | 553485.92 | 552462 | 1024 | Yellow | 567807 |  | 567807 | -14321 |  |  | 1104000 |  |  | 1104000 | Full | 1104000 | 717767 | 373802 | 1091569 | No | Green | 2022-07-01 | 2022-07-12 | 2022-07-12 | 2023-08-31 | 2023-08-31 |  |  | 54706.68 | 73457.46 | 69419.01 | 71999.77 | 70976 | 70976 | 1024 | Yellow |  |  | 70976 | 70976 | 70976 | 70975 |  |  |  |  | 89899 | 3/8/2023 Variance in Feb from over forecsting. SG 2/2/23: January forecast was down by $14544. That has been added to Feb 2023 forecast. 10/10/22: BirlaSoft was paid twice ($ 47,957 each) for migration work during the period 07/01/22 to 07/31/22. This contributed to the variance. This amount will be credited back by BirlaSoft. The forecast for October has been adjusted accordingly. 8/17/22: The forecast was changed as per the AFE from September 2022 to August 2023. For July 2022, the actual forecast is $71,145 and August 2022 is $73,335. These could not be edited. 8/09/2022: PM invoice coded to Expense for July. PO to be issued and reclassed in Aug.//bo -6/17/2022: Per call with RD, slight increase to 2022 Forecast but increase in 2023 to $384k (from $100k listed in 2023 previously in Tracker only).//bo -5/10/2022: Shifted Cash Flow Start date to July. Combined funds for October and November to December (totaling $10.5k).//bo -3/7/22- Project is still on hold after meeting with Jaime Juan. Forecast updated with best approximate guess of start date. - DB 2/1/22- Project on hold after meeting with Jaime Juan - DB 1/3/22 - This is the SharePoint/ Automation Online Migration Project for 2022. I will work with Ganesh and Vivian on getting the most updated quotes for this project and building out a schedule and charter and submitting the AFE for this project. 11/05/2021: Removed remaining forecast from 2021.//bo 8/9/2021 - Forecast pushed to October. DC 6/09/2021: Shifted forecasted to start in August. Need to confirm forecast and dates.//bo | 2023-03-08 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 197583 | 213952 | 141951 |  | 448185 |  | Gingras, Stephan | Virupakshi, Sudhakar |  |  | 1 | 38294 |  | Administrator, System | Independent | Aqua | 2020-08-24 | IT
SheetCutter Software Purchase | Item | Open | MCAP | 1348173M2107 | Exempt | 1910831 | Kralik, Ron | IT | 6. Operational | Emergent | OT & IT Field Ops | 174 |  | 2249 | 174.18 | 174 | 0 | Green |  |  |  | 174 |  |  | 27000 |  |  | 27000 | Full | 27000 | 18885 | 2249 | 21134 | No | Green | 2021-12-01 | 2021-11-30 | 2021-11-30 | 2022-02-28 | 2022-09-30 |  |  | 86.31 | 87.87 | [16 empty] | 2249 | 3/7/23: With the cancellation of the related Alignment Sheet Generator project, no further action on floating license upgrades will be funded under this project. No additional spend is forecast. 2/7/23: No change to status / forecast. 1/9/23: No change to status. 11/7/22: No change to status. 10/6/22: Remaining project work is related to Alignment Sheet generator project and will be deferred until 2023. 9/8/22: New Century provided SaaS assessment. Still awaiting requested customer reference and rescheduled date for SW Demo. IT Ops Apps continues to have concerns about New Century's readiness to move forward with the project. 8/5/22: Still awaiting SaaS questionnaire responses from New Century in order to schedule/proceed with ARC review. 7/6/22: GIS and IT Operations Applications met with New Century in June to discuss vendor readiness to proceed. New Century to provide information in preparation for ARC review. 6/7/22: New Century meeting to be rescheduled in June. Will determine next steps regarding floating license upgrade. 5/6/22: Meeting with New Century planned for May. Will determine next steps regarding floating license upgrade. 4/7/22: GIS Team requested we include floating license upgrade as part of Alignment Sheet Generator project. May look to close out this project. 3/7/22: GIS Team continuing review of floating software licensing options with New Century. 2/7/22: GIS Team working with New Century to investigate floating software licensing options. 1/7/22: Software purchased in 2021, 50% discount obtained. GIS team to complete install in January 2022. -12/09/2021: added $2k BACK to CY+1 Forecast.//bo -12/08/2021: Removed 2022 CY+1 Forecast for $2k for now./bo 12/6/21: AFE approved on 11/30. | 2023-03-07 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 174 | 0 |  |  | 791 |  | Gingras, Stephan | Shook, Mark B. |  |  | 1 | 42498 |  | Perry, Betty | Independent | Aqua | 2021-11-23 | IT
SolarWinds Segregation Project | Item | Open | MCAP | 1348179M2204 | Exempt | 2023223 | Geier, John | IT | 3. Active | Emergent | Infrastructure & IT Ops | 21164 |  | 16113 | 21164.02 | 21833 | -669 | Yellow |  |  |  | 21164 |  |  | 190000 |  |  | 190000 | Full | 190000 | 154485 | 16113 | 170598 | No | Green | 2022-10-01 | 2022-09-21 | 2022-09-21 | 2022-12-23 | 2023-06-02 |  |  | 16197.72 | 1758.68 | 1376.36 | 1831.26 | 2500 | 2500 | -669 | Red | [10 empty] | 16113 | 5/5/23 - Initial cut-over complete. Remaining work expected to be completed in May. // jg 3/31/23 - Project tracking to complete by end of month. // jg 2/09/23: "Approved Contingency" field shows $187,709. AFE approved at $16,113. Made update.//bo 2/6/23 - Operational date for forecast adjusted for remaining tasking.//JG 1/19/23: Operational Date updated based on forecast.//bo 12/30/22 - all equipment received. Build and cutover being planned. Supply chain delayed equipment arrival JG 12/7/22 - Still awaiting some equipment to proceed 11/8/22 - Adjusted forecast for December as license arrived in October 10/27/22 - No change. Awaiting on equipment 10/1/22 PO Created. Awaiting estimated arrival of hardware and software. JG | 2023-05-05 | IT |  | Corporate | Corporate | IT |  | Corporate | Corporate |  | 19333 | 1831 |  |  | 133321 |  | Gingras, Stephan | Gehringer, Todd |  |  | 1 | 45863 |  | Meitzler, Antoinette | Independent | Aqua | 2022-09-19 | IT
Stratus Dual Node – Top (9) Sites by Truck Rack Volume | Item | Open | MCAP | 1348181M2304 | Exempt | 2112722 | Gay, Elena | IT | 3. Active | Defined | OT & IT Field Ops |  | 77340 |  | 77340 | 77340 | 0 | Green | 78800 |  | 78800 | -1460 |  |  | 76176 |  |  | 76176 | Full | 76176 |  | 77340 | 77340 | No | Green | 2023-05-01 | 2023-04-26 | 2023-04-26 | 2023-07-30 | 2023-08-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 31000 | 30500 | 15840 | [6 empty] | 4/05/23: name change to reflect 9 sites instead of 10 sites per EG.//bo 3-7-2023 EG - AFE docs are in process of review. Moved forecast to start in April. | 2023-04-05 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 61500 | 15840 |  |  |  | Gingras, Stephan | Parker, Chris |  |  | 1 | 45503 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
Synthesis BOL Auto Load | Item | Open | MCAP | 1348173M2206 | Exempt | 2036848 | Pellum, Brianna | IT | 3. Active | Defined | OT & IT Field Ops | 60559 | 189024 | 25000 | 249582.6 | 252178 | -2596 | Yellow | 151080 |  | 151080 | 98503 |  |  | 362000 |  |  | 362000 | Full | 362000 | 121597 | 214024 | 335621 | No | Green | 2022-10-01 | 2022-10-13 | 2022-10-13 | 2023-06-30 | 2023-06-23 |  |  | 389.48 | 314.19 | 29193.57 | 30661.36 | 33257 | 33257 | -2596 | Yellow |  |  | 62186 | 63394 | 63444 | [5 empty] | 25000 | 5/3/23 Deliverables are on track. Vendor has early delivery of project. BP 4/4/23 There is an variance this month because deliverables have been extended. BP 3/2/23 development is in process and is going according to schedule. BP 2/7/2023 Updated based on forecast. Demo from vendor due 2/22/23. BP 1/19/23: Operational Date updated based on Forecast. BP 1/3/2023 Vendor delayed end of month. Forecast update. BP 12/2/2022 Vendor delayed end of month. Forecast updated per kick of meeting and milestone payments. BP 11/2/2022 Vendor delayed end of month. Forecast updated per kick of meeting and milestone payments. BP 9/30/2022 AFE and Kick-off meeting in October $94K to 2023 SG 8/31/2022 Still pending negotiations with the vendor. SG 7/29/2022 Still pending negotiations with the vendor. SG 6/30/22 Still pending negotiations with the vendor. SG 6/23/2022: Updated Operational Date based on OPPM forecast.//bo 5/31/2022 Still working through SOW( requirements and pricing) SG 4/29/2022 Working on SOW and other documents for project in June. SG 3/31/2022 Working on SOW and other documents for project in June. SG | 2023-05-03 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 29897 | 156241 | 63444 |  | 61038 |  | Gingras, Stephan | Gardner, Dale |  |  | 1 | 41699 |  | Administrator, System | Independent | Aqua | 2021-08-20 | IT
SYNTHESIS JOINT TARIFF AND CHARGE REC | Item | Open | MCAP | 1348173M2202 | Exempt | 2011086 | Pellum, Brianna | IT | 3. Active | Emergent | OT & IT Field Ops | 7862 | 46856 |  | 54717.86 | 54772 | -54 | Yellow | 13312 |  | 13312 | 41406 |  |  | 95000 |  |  | 95000 | Full | 95000 | 36425 | 46856 | 83281 | No | Green | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2023-01-27 | 2023-06-30 |  |  | 4362.91 | 826.27 | 1776.9 | 895.78 | 21111 | 21111 | -20215 | Red |  |  | 31253 | 15603 | [7 empty] | 5/2/23 Design should not be at risk anymore. Work has resumed. 4/6/23 Design delays have cause milestone payment delays. Forecast has been updated. BP 3/1/23 Design delays have cause milestone payment delays. Forecast has been updated. BP 2/8/23 Delays pushed out until issues is resolved. BP 1/3/23 Schedule on track. Unit Testing to start mid Jan, BP 11/28/22 Delays pushed out until Feb based on designs between vendor and project team. BP 11/1/22 Schedule at risk, design phase taking longer than expected. No budget adjustments at this time. BP 9/30/2022 Working sessions are in progress and and budget and schedule on track. SG 8/31/2022 Kick of Schedule for 9/12 SG -8/11/22: Need to update AFE operational date to 2023 once OPPM unlocks.//bo 7/29/2022 AFE pending approval and SOW to be signed to start work in August. SG | 2023-05-02 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 6966 | 47752 |  |  | 28564 |  | Gingras, Stephan | Gardner, Dale |  |  | 1 | 44288 |  | Meitzler, Antoinette | Independent | Aqua | 2022-07-27 | IT
Synthesis OTI Server Upgrade | Item | Open | MCAP | 1348173M2203 | Exempt | 2022776 | Pellum, Brianna | IT | 6. Operational | Emergent | OT & IT Field Ops | 11053 |  |  | 11053.49 | 11053 | 0 | Green |  |  |  | 11053 |  |  | 25000 |  |  | 25000 | Full | 25000 | 22360 |  | 22360 | No | Green | 2022-09-01 | 2022-09-16 | 2022-09-16 | 2022-11-01 | 2023-01-31 |  |  | 10577.5 | 475.99 | [17 empty] | 1/31/2023 Project closed. BP 11/1/2022 Vendor delays expected to end this month. BP 9/30/2022 Project to be completed in Oct re platform software. SG 9/19/202022 AFE approved updated forecast need to PO for Emerson SG | 2023-01-31 | IT |  | Corporate | Pipelines and Terminals | IT |  | Corporate | Corporate |  | 11053 | 0 |  |  | 11307 |  | Gingras, Stephan | Gardner, Dale |  |  | 1 | 45827 |  | Meitzler, Antoinette | Independent | Aqua | 2022-09-13 | IT
Synthesis Server Upgrade to OS/SQL 2019 | Item | Open | MCAP |  | Exempt |  | Pellum, Brianna | IT | 1. Proposed |  | OT & IT Field Ops |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 | [9 empty] | 100000 | 100000 | No | Green | 2023-07-01 |  |  |  | 2023-10-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 0 |  |  | 4/10/23: Per SM/SG, this project is going to be Expense. Pushing out forecast for now since there are Emergent projects through SM that need to be added to OPPM.//bo 3/2 Forecast adjusted based on later start date. SG | 2023-04-10 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 | 75000 | 25000 |  |  | Gingras, Stephan |  |  |  | 1 | 45504 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
Synthesis Terminal BOL Consolidation | Item | Open | MCAP |  | Exempt |  | Gingras, Stephan | IT | 8. Canceled |  | OT & IT Field Ops |  |  |  | 0 |  | 0 | Green | 135000 |  | 135000 | -135000 | [11 empty] | No | Green |  |  |  |  | 2023-12-31 | [21 empty] | 5/08/23: ok to CXL per SG./bo 3/08/23: Removing forecast from 2023 since this is the same as Synthesis BOL Auto Load. Looking to re-distribute 2023 Budget of $135k.//bo | 2023-05-08 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 |  |  |  |  | Gingras, Stephan |  |  |  | 1 | 45505 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
TAA OT Terminal Business Continuity | Item | Open | MCAP |  | Exempt |  | Gay, Elena | IT | 1. Proposed |  | OT & IT Field Ops |  | 320000 |  | 320000 | 320000 | 0 | Green | 320000 |  | 320000 | 0 | [9 empty] | 620000 | 620000 | No | Green | 2023-08-01 |  |  |  | 2023-12-15 | [15 empty] | 60000 | 70000 | 70000 | 60000 | 60000 | [5 empty] | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 | 130000 | 190000 |  | 300000 | Gingras, Stephan |  |  |  | 1 | 45475 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
TCD Replacement | Item | Open | MCAP | 1348176M2101 | Exempt | 1903402 | Geier, John | IT | 3. Active | Defined | Infrastructure & IT Ops | 161193 | 505000 |  | 666193.36 | 665229 | 964 | Yellow | 701000 |  | 701000 | -34807 |  |  | 62000 | 687000 |  | 749000 | Phase | 749000 | 413960 | 2945000 | 3358960 | No | Green | 2021-11-01 | 2021-10-29 | 2021-10-29 | 2021-12-31 | 2024-07-31 |  |  | 72943.47 | 35143.28 | 21392.3 | 31714.31 | 30750 | 30750 | 964 | Yellow |  |  | 55000 | 55000 | 55000 | 50000 | 50000 | 50000 | 110000 | 80000 |  | 5/5/23 - Additional locations scheduled. Purchased additional radios. No change to forecast or budget. // jg 3/31/23 - Updated forecast based on work planned for April. // jg 3/7/23 - Additional locations scheduled for March and April. Learned on some locations where TCD is no longer being used. // jg 2/5/23 - Vestal and Dupont completed in January. Additional sites being scheduled. // JG 12/30/2022 Attempted to complete sites at the end of November and help meeting to schedule in 2023. Variance from delayed equipment arriving. SG - 11/30/2022 December forecast reduced with no deployments planned. The plan has changed from vendor invoicing us for hardware when it was received to when they install them in the field. This will result in an over-accrual in October, so November will have a negative variance. SG -11/09/22: Dec forecast updated to $10k per SG.//bo -11/1/22 Issues with tech resources and scheduling sites downtime. SG -10/31/22 - Cost Reduction by $160,000 per ELT reduction request. //bo 9/30/2022 Some equipment is still pending delivery causing a variance in September. ?Long Island City Completed working on scheduling 4 more sites and then 2 more in the next couple of months. SG 9/1/22 - Forecast and schedule are updated. We are counting on the bulk of the equipment to come in during September. Arseal has confirmed this and forecast reflect this. 8/1/22 - Part of the large August equipment order came in at the end of July, thus the difference for this month. August has been adjusted to reflect this. (8/8/22) Forecast and scheduled are updated after speaking with the vendor to reflect current projections, specifically, a large order for this project in August has moved to September and this reflects that change now. 7/5/22 - Forecast and schedule are updated. We are expecting a large equipment delivery next month per our vendor. 6/3/22 - After speaking with Arseal, no equipmentis forecasted coming in during June now. The timing is tricky, but the equipment is now forecasted for late July orearly August. I have updated my forecast and schedule to reflect these changes. 5/2/22 - The bulk of our equipment is still forecasted coming in at the end of June. I continue to reach out tothe vendor for the latest updates and forecast any changes. 4/4/22 - The bulk of our equipment is forecasted coming in during Q2. I continue to reach out to the vendor for the latest updates and forecast any changes appropriately.3/7/22 - Our goal is to install Vestal, Rochester, Marcy, and Brewerton sites by the end of April. The bulk of our equipment is coming in during Q2 and I continue to reach out to Mike Craver from Arseal for the latest updates and forecast any changes appropriately. 2/4/22 - Jen McSweeney and I met with Chris Parker on 2/3 to reviewthe TCD Replacement project. Our goal is to install at Vestal, Rochester,Marcy, and Brewerton sites by end of March, early April. We gave Chris Parkerour update on the Program meeting on 2/3 as well. We meet on 2/4 to review with Bob O. the field technicians that would be needed for these sites and future install sites. A lot of equipment iscoming in early Q2 and I continue to reach out to Mike Craver from Arseal for updates. ?1/3/22 - The AFE has been approved.Arseal will finish working on the programming portionover the next two months for the Vestal, Rochester, Marcy, Aurora and Brewerton sites. Thisshould finish up in early Q1 for that portion. We gave Chris Parker our update on the Program meeting to let him know where we stand on this issue. We meet on 1/12/22 to review sites to visit and timing of installation with our vendor. 12/1/21 - The AFE has been approved. Arsealwill work on the programming portion over the next two months for the Vestal, Rochester, Marcy, Aurora and Brewerton sites. We gave Chris Parkerour update during the Program meeting to let him know where we stand on this issue. 11/5 - The budget amount approved was 62,000. The AFE has been submitted for 2021 and has been approved. Arseal will work on theprogramming portionover the next two months for the Vestal, Rochester, Marcy, Aurora and Brewerton sites. 10/5 - This will not kick off till late Q4. We have met with all the districts and didthree presentations to these sites. The next step is to finalize the AFE and charter and have them both approved. I am working with Jen McSweeney and met with her a few times last week to finalize the budget portion. We should have a finalized draft of the AFE to review with Chris early next week and once we get approval we will submit for the equipment needed for 2021. 9/6 - The budget amount approved is 450K. This will not kick off till late Q4. We have met with all the districts and did three presentations to these sites and received the feedback we were hoping for to move forward with this project. The next step is to finalize the AFE and charter and have them both approved. I am waiting final quotes for hardware from Steve Z, and then we can proceed with the AFE. 8/5 - The budget amount approved is 450K. This will not kick off till late Q3. This past week we met with all the districts and did three presentations to these sites andrequested feedback. The next step is to finalize the AFE and charter and have them approved. 7/6 - The budget amount approved is 450K. This will not kick off till late Q3 at the earliest. I have a meeting with the TCD team this week (7/7) to start the planning sessions and preparations to kick this off and review the sites we may be able to visit this year. 6/3 - The same update for May applies to this project. 5/3- The same update for April applies to this project. 4/2 - This is the TCD Replacement Project for 2021. The budget amount approved is 450K. This will not kick off till late Q3 at the earliest. 3/4 - This is the TCD Replacement Project for 2021. The budget amount approved is 450K. I have a team meeting scheduled for 3/15 with Jen McSweeney, Kyle Thomas and Steve Zimmerman. This will not kick off till late Q3 at the earliest. 2/19/2021: Assigned project to Dave Barnett per Resource Planning document. Verify dates and forecast in OPPM and BrightWork.//bo -10/19/2020 Update: delayed the TCD start to Q4; increased Q4 budget to $450k from $429k. Added $1,266,000 to 2024.//bo. | 2023-05-05 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 129479 | 141714 | 155000 | 240000 | 201356 | 955000 | Gingras, Stephan | Sinatore, Kathleen J. |  |  | 1 | 38288 |  | Administrator, System | Independent | Aqua | 2020-08-24 | IT
Terminal Volume Accounting Automation Assessment | Item | Open | MCAP |  | Exempt |  | Gingras, Stephan | IT | 1. Proposed |  | Enterprise Business Apps |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 | [9 empty] | 50000 | 50000 | No | Green | 2023-08-01 |  |  |  | 2023-11-30 | [15 empty] | 15000 | 15000 | 15000 | 5000 |  |  | forecast updated for cashflow to start in Aug per Rahul. SG | 2023-04-07 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 | 30000 | 20000 |  |  | Gingras, Stephan |  |  |  | 1 | 45506 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
Terminal Web Portal Upgrade or Replacement | Item | Open | MCAP |  | Exempt |  | Gay, Elena | IT | 1. Proposed |  | OT & IT Field Ops |  | 150000 |  | 150000 | 150000 | 0 | Green | 150000 |  | 150000 | 0 | [9 empty] | 350000 | 350000 | No | Green | 2023-10-01 |  |  |  | 2023-12-31 | [17 empty] | 50000 | 50000 | 50000 |  | ?-10/31/22 - Reduction in 2023 budget by $150k due to ELT budget reduction request.//bo | 2022-10-31 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 |  | 150000 |  | 200000 | Gingras, Stephan |  |  |  | 1 | 45481 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
Time Planning Solution (TPS) | Item | Open | MCAP | 1348174M2201 | Exempt | 1957591 | Aili, Suresh | IT | 3. Active | Defined | Enterprise Business Apps | 66263 | 81000 |  | 147262.79 | 88539 | 58724 | Red | 80371 |  | 80371 | 66892 |  |  | 394000 |  | 79000 | 473000 | Supplemental | 473000 | 297861 | 81000 | 378861 | No | Green | 2022-05-01 | 2022-03-31 | 2022-03-31 | 2022-10-03 | 2023-06-12 |  |  | 2118.07 | 14894.05 | 22537.76 | 26712.91 | 36989 | 36989 | -10276 | Red |  |  | 38000 | 43000 | [7 empty] | 5/4/2023: Go Live date has been pushed to 06/05 for BBH and 06/12 for Saint Lucia. Updated forecast reflecting change in amount from vendor services and Internal labor due to delays in project go live dates. 4/10/23: Updated forecast due schedule delay.//bo 3/8 Feb under forecast, internal labor and D&E reclass pending. April forecast now includes UKG travel change for $13,406.37. Production will be live by 4/1. -KS 2/7 New go live is 4/1 for BBH and 4/9 for STL. Changed AFE op date to 4/28. Forecast increased by $10,880 with additional UKG charges for date change and 3rd party badge integration services. - KS 1/9 UKG and System Consulting change costs $10,880. Test case issues caused a delay with go live. New dates: 3/1 for BBH and 3/5 for STL. - KS 12/6 December forecast increased by $20K to complete testing and training. -KS 11/7 Reduced scope by removing Control Center from deployment and reduced scope for two software modules. Forecast decreased by $40K in Nov and $40K in Dec.-KS 10/7 Reduced labor forecast for October due to design delays falling into the first part of the month. Change order will be processed for additional data needs for $15K in Oct.-KS 9/12 Updated forecast for additional labor. - KS 9/8 Moved $66K to Jan/Feb 2023 to support first two weeks in Feb 2023 go live. Training and travel moved to Jan. KS 8/17 Moved $12K to Jan 2023 and changed operational date to Jan 31, 2023. KS 8/5 UltiPro business structure data changes have delayed the project by potentially two months, which pushes go live Dec 22 or Jan 23. AFE supplemental to be submitted Aug. 8 and forecast will be updated accordingly. -KS 7/7 Vendor set up delays, but $43K invoice will be processed in July. Core team internal labor will begin late July. AFE supplemental for $67,448.70 will be submitted in July. -KS 6/7/22 Kickoff planned for June 10. Change order for additional scope of approximately $60K will be processed this week (includes control center timekeeping & buy vs lease equipment change). Go live pushed to Dec. 2022 due to later start and new scope. -KS 5/4/22 Vendor will begin work week of May 16 preparing for kickoff. No changes to forecast. -KS 4/7/22 AFE approved. Vendor will begin work in mid-May. Forecast has been adjusted accordingly.- KS 3/7/22 AFE will begin processing for approval. Vendor will begin work mid April.-KS 2/8/2022 Finalizing business case and AFE for approval in late Feb/early March. - KS 1/10/22 Currently reviewing enterprise requirements to ensure BBH and STL are complete, ARC review planned for Jan 12.Plan for AFE approval by end of Jan/early Feb. -KS -12/10/2021: Cash Flow will not start in December as forecasted.//bo 6/9/2021 - Project under review ?-2/18/2021: Assigned project to Kimberly Splawn per Resource Planning document. Dates and forecast in OPPM and BrightWork.//bo | 2023-05-04 | IT |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  | 39550 | 107713 |  |  | 231598 |  | Gingras, Stephan | Serra, William R. |  |  | 1 | 38295 |  | Administrator, System | Independent | Aqua | 2020-08-24 | IT
TMS7 Pilot | Item | Open | MCAP |  | Exempt |  | Gay, Elena | IT | 1. Proposed |  | OT & IT Field Ops |  | 75000 |  | 75000 | 75000 | 0 | Green | 75000 |  | 75000 | 0 | [9 empty] | 75000 | 75000 | No | Green | 2023-10-01 |  |  |  | 2023-12-21 | [17 empty] | 50000 | 25000 | [6 empty] | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 |  | 75000 |  |  | Gingras, Stephan |  |  |  | 1 | 45507 |  | Administrator, System | Independent | Aqua | 2022-08-29 | IT
UKG Payroll Implementation BBH/STL:MCAP | Item | Open | MCAP |  | Exempt |  | Splawn, Kimberly | IT | 1. Proposed |  | Enterprise Business Apps |  | 125000 |  | 125000 | 125000 | 0 | Green | 250000 |  | 250000 | -125000 | [9 empty] | 250000 | 250000 | No | Green | 2023-10-01 |  |  |  | 2024-02-28 | [17 empty] | 41667 | 41667 | 41666 |  | 4/11/23: Per RD, updated Cash Flow Start Date to 10/01. Kept CY EAC of $125k.//bo Fore cash updated SG | 2023-04-12 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 0 |  | 125000 |  | 125000 | Gingras, Stephan |  |  |  | 1 | 45915 |  | Administrator, System | Independent |  | 2022-09-26 | IT
Unticketed Batch Replacement + CC Line Sheets + SODB | Item | Candidate | MCAP |  | Exempt |  | Pellum, Brianna | IT | 1. Proposed |  | OT & IT Field Ops |  | 315000 |  | 315000 | 315000 | 0 | Green | 315000 |  | 315000 | 0 | [9 empty] | 315000 | 315000 | No | Green | 2023-06-01 |  |  |  | 2023-12-31 | [6 empty] | 0 | 0 | 0 | Green |  |  |  | 5000 | 33000 | 33000 | 66000 | 65000 | 66000 | 47000 |  | -10/31/22 - Cost Reduction by $85,000 per ELT reduction request.//bo | 2022-10-31 |  |  | Corporate | Corporate | IT |  | Information Systems | Corporate |  |  | 5000 | 132000 | 178000 |  |  | Gingras, Stephan |  |  |  | 1 | 34713 |  | Guest, ProSight | Independent | Aqua | 2019-08-29 | IT
Urjanet Invoice Receipt Automation | Item | Open | MCAP | 1348174M2206 | Exempt | 2044301 | Kralik, Ron | IT | 3. Active | Emergent | Enterprise Business Apps | 14389 | 10897 | 9451 | 25285.99 | 35217 | -9931 | Red |  |  |  | 25286 |  |  | 122000 |  |  | 122000 | Full | 122000 | 63813 | 20348 | 84161 | No | Green | 2022-11-01 | 2022-11-08 | 2022-11-08 | 2023-03-24 | 2023-05-19 |  |  | 3156.12 | 2298.59 | 3762.55 | 5171.73 | 14000 | 14000 | -8828 | Red |  |  | 10897 | [7 empty] | 9451 | 5/5/23: BI Report completed, sftp process will be completed in May. 4/7/23: Forecast adjusted to shift some contract labor for BU reporting to 2Q. 3/7/23: February underspend due to fewer internal and contract hours consumed vs forecast. 2/7/23: Custom PDF file naming development, sftp transfer setup underway.? 1/9/23: Forecast adjusted to account for $23K of prorated Subscription license expense costs occurring in 2022 instead of 2023. 12/7/22: No change to forecast. 11/8/22 AFE approved on 11/8. | 2023-05-05 | IT |  | Corporate | Pipelines and Terminals | IT |  | Corporate | Corporate |  | 9217 | 16069 |  |  | 49424 |  | Gingras, Stephan | Kelly, Michael J. |  |  | 1 | 46114 |  | Meitzler, Antoinette | Independent | Aqua | 2022-10-24 | IT
Website Redesign - Phase 2 | Item | Open | MCAP | 1348180M2202 | Exempt | 2044295 | Reeves, Dottie | IT | 6. Operational | Emergent | Enterprise Business Apps | 154836 |  |  | 154835.77 | 198316 | -43480 | Red |  | 140000 | 140000 | 14836 |  |  | 225000 |  |  | 225000 | Full | 225000 | 227598 |  | 227598 | No | Green | 2022-11-01 | 2022-11-07 | 2022-11-07 | 2023-04-01 | 2023-04-30 |  |  | 23875.3 | 33990.93 | 100449.33 | -3479.79 | 40000 | 40000 | -43480 | Red |  | Forecasting | [9 empty] | 2023-04-26 Monthly forecast for April is off due to a $32K miscalculation back in Feb that I just discovered, plus some challenges with vendor providing timely estimates. 2023-04-12 - Updated status to Operational. Went live on 3/29. 2023-03-29 - Received news that Corp Comm signed agreement with FTI for additional work, including an interactive map that will cost an additional $39K which I have added to April's forecast. 2023-03-07 - On track. 2023-02-07 On track to spend budget (not contingency). Forecast was off this month because vendor told me to expect $60K for December work and invoice was only $20K. 1/31/2023: Updated Operational Date based on Forecast (showed Apr 2022).//bo 23-01-09 - Forecast was off in December because vendor and I agreed the monthly expectation of cost would be the same each month, however, in reality they did a lot of work on the front end and billed for that. The ETC is the same, so we are on budget. 2022-12-07 - AFE was approved. Entered forecast for the first time. | 2023-05-08 | IT |  | Corporate | Corporate | IT |  | Corporate | Corporate |  | 158316 | -3480 |  |  | 72762 |  | Gingras, Stephan | Gardner, Dale |  |  | 1 | 46157 |  | Meitzler, Antoinette | Independent | Aqua | 2022-11-03 | IT
Windows 10 HMI Upgrades plus Aereon | Item | Open | MCAP | 1348181M2204 | Exempt | 2013249 | Gay, Elena | IT | 3. Active | Emergent | OT & IT Field Ops | 14049 |  |  | 14048.74 | 9058 | 4990 | Red |  |  |  | 14049 |  |  | 78000 |  |  | 78000 | Full | 78000 | 61632 |  | 61632 | No | Green | 2022-09-01 | 2022-08-24 | 2022-08-24 | 2022-12-10 | 2023-05-15 |  |  | 273.44 | 133.39 | 8651.46 | 4990.45 |  |  | 4990 | Red | [11 empty] | 1-3-2023 - Last charge will be for PC for around $1,700.00 12-2-2022 speaking with vendor and work will extend to January due to PO issues. -12-1-2022 EG - issue with PO and in process of getting corrected. Last invoice is $19,320 and will re-accrue. | 2023-02-08 | IT |  | Corporate | Pipelines and Terminals | IT |  | Information Systems | Corporate |  | 9058 | 4990 |  |  | 47583 |  | Gingras, Stephan | Parker, Chris |  |  | 1 | 45121 |  | Perry, Betty | Independent | Aqua | 2022-08-20 | IT
*2023 Casualty Loss Capital 2 Budget Allocation | Item | Candidate | MCAP |  | Maintenance Framework |  | Clark, Dave | Maintenance Support | 1. Proposed |  | Corporate |  | 860000 |  | 860000 | 956000 | -96000 | Red | 956000 |  | 956000 | -96000 | [9 empty] | 860000 | 860000 | No | Green | 2023-06-01 |  |  |  | 2023-11-30 | [7 empty] | 100000 | -100000 | Red |  |  |  | 100000 | 100000 | 150000 | 150000 | 120000 | 120000 | 120000 |  | 4.13 Reduced allocation for the 3+9 Initial Allocation for CL2 incorporating into MCAP portfolio in 2023 |  |  |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corporate |  | Corporate | Corporate |  |  | 100000 | 400000 | 360000 |  |  | Clark, Dave |  |  |  | 1 | 45810 |  | Administrator, System | Independent | Aqua | 2022-09-12 | Casualty Loss 2
*2023 Casualty Loss Expense 2 Budget Allocation | Item | Open | MEXP |  | Maintenance Framework |  | Clark, Dave | Maintenance Support | 1. Proposed | Defined | Corporate |  | 167000 |  | 167000 | 400000 | -233000 | Red | 400000 |  | 400000 | -233000 | [9 empty] | 167000 | 167000 | No | Green | 2023-09-01 |  |  |  | 2023-10-31 | [7 empty] | 60000 | -60000 | Red | [6 empty] | 60000 | 47000 | 60000 | [6 empty] | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal | Station/Terminal | Corporate | Corporate |  |  | 0 | 60000 | 107000 |  |  | Clark, Dave |  |  |  | 1 | 45812 |  | Administrator, System | Independent | Aqua | 2022-09-12 | Other Programs
*MEXP Confidence Adjustment - Tank Integrity | Item | Candidate | MEXP |  | Exempt |  | Walton, Kathleen | Maintenance Support | 3. Active | Emergent | Corporate |  | -1 |  | -1 | -1 | 0 | Green |  |  |  | -1 | [9 empty] | -1 | -1 | No | Green |  |  |  |  | 2023-12-31 | [19 empty] | -1 |  | 4.27 - Topsides removed ahead of 4+8 forecast 4.13 -$2M topside to baseline 4.3 Removed Topside for 3+9 3.17.2020 - Shift 1.5M from Q2 to Q3 |  | Kabaria, Erika |  | Corporate | Corporate | Tank Integrity | Tank Integrity | Corporate | Corporate |  |  | 0 |  | -1 |  |  | Clark, Dave |  | N/A |  | 1 | 23108 |  | Inman, Connie L. | Independent | Aqua | 2017-04-18
*MEXP Forecast Balance | Item | Candidate | MEXP |  |  |  | Clark, Dave | Maintenance Support | 1. Proposed |  | Corporate |  | 0 |  | 0 | 0 | 0 | Green |  |  |  | 0 | [9 empty] | 0 | 0 | No | Green | 2023-08-01 |  |  |  | 1900-12-31 | [12 empty] | -500000 | -2000000 | -3000000 | 500000 | 1500000 | 1000000 | 1000000 | 1500000 | [5 empty] | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal | Station/Terminal |  |  |  |  | -2500000 | -1000000 | 3500000 |  |  | Clark, Dave |  |  |  | 1 | 45987 |  | Administrator, System | Independent | Aqua | 2022-10-05 | Other Programs
*Unplanned Carryover 2023 MCAP | Item | Candidate | MCAP |  | Maintenance Framework |  | Clark, Dave | Maintenance Support | 8. Canceled |  | Corporate |  |  |  | 0 |  | 0 | Green | 1967945 | -1967945 | 0 | 0 | [11 empty] | No | Green |  |  |  |  | 2023-01-31 | [21 empty] | Unplanned Carryover allocated on 2.20.2023 Project # CY Budget Adjustment BETHY00M2202 325,000 BH00000M2207 140,945 BPTPC00M2216 156,000 BPTPC00M2217 191,000 BTTUG00M2203 200,000 BTXPP00M2216 141,000 CY802CAM2301 245,000 IM760UGM2202 183,000 LN00000M2209 191,000 MP00000M2204 195,000 |  |  |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Corporate | Corporate | Corporate | Corporate |  |  | 0 |  |  |  |  | Clark, Dave |  |  |  | 1 | 45785 |  | Clark, David | Independent | Aqua | 2022-09-10 | Other Programs
*Unplanned Carryover 2023 MEXP | Item | Candidate | MEXP |  | Maintenance Framework |  | Clark, Dave | Maintenance Support | 8. Canceled |  | Corporate |  |  |  | 0 |  | 0 | Green | 295000 | -295000 | 0 | 0 | [11 empty] | No | Green |  |  |  |  | 2023-01-31 | [21 empty] | 02.20.2023 Allocated full $295K to BBH - Jetty Piping 2022 Inspections $ 8410811E2202 per Dave Clark |  |  |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal | Station/Terminal | Corporate | Corporate |  |  | 0 |  |  |  |  | Clark, Dave |  |  |  | 1 | 45786 |  | Clark, David | Independent | Aqua | 2022-09-10 | Other Programs
2022 Marine Terminal Dockline Testing Updates | Item | Open | MEXP | 1550000E2202 | Exempt | 1939407 | White, Stephen | Maintenance Support | 6. Operational | Emergent | Marine | 28252 |  |  | 28252.45 | 22054 | 6198 | Red |  |  |  | 28252 |  |  | 231000 | 120000 |  | 351000 | Full | 351000 | 274572 |  | 274572 | No | Green | 2022-02-01 | 2022-01-21 | 2022-01-21 | 2022-12-31 | 2023-03-31 |  |  | -7500 | 29554.45 |  | 6198 |  |  | 6198 | Red | [11 empty] | 5/1/23 - TN/SW - Project is operational. 3/2/23 - TN/SW - All submittals received from contractor. Project is ready to close 12/21/22 SGW - For the final 14 marine terminals reviewed by ESDC, a list of proposed MCAP/MEXP projects for 2023 has been forwarded to David Clark. 12/1/22 TN - ESDC Waiting for clarification on JDE tagging, forecast pushed 8.1.22 SDB: This Project is being transferred to Mr. Steve White. 7.25.22 SDB: ESDC has transmitted for review 17 of 32 inspection reports. 7.8.22 SDB: ESDC continue visiting terminals and has transmitted 14 of 32 inspection reports. These reports are being reviewed internally. An additional PO has been issued to ESDC. for additional scope. We will receive additional inspection reports as they are completed. 5.31.22 SDB: ESDC continues visiting terminals and has produced reports on 14 of the 32 terminals. ESDC will produce required drawings for each terminal and will write the test procedures for each of the terminals utilizing the Buckeye maintenance form. 5.2.22 SDB: ESDC continues visiting terminals and producing reports. Meeting with Integrity and discussing joint path forward. 2.18.22.DLC: ESDC started in Feb in TX/LA & FA | 2023-05-01 | Nguyen, Tong |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  | 22054 | 6198 |  |  | 246319 |  | Spari, Markella | Martin, David N. |  |  | 1 | 42763 |  | Clark, David | Independent | Aqua | 2022-01-14 | Marine
2023 BTXPP AIFR Budget Allocation | Item | Open | MCAP |  | Maintenance Framework |  | Clark, Dave | Maintenance Support | 1. Proposed |  | Tanks |  |  |  | 0 |  | 0 | Green | 500000 |  | 500000 | -500000 | [11 empty] | No | Green |  |  |  |  | 2023-09-30 | [21 empty] | 1/25/23-CES-Reducing forecast to $0 after transferring funds over to BTP tanks 1002, 1004, 1006, 3003, and 2004 for IFR repairs and replacements. | 2023-01-25 |  |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 0 |  |  |  |  | Stine, Carlton |  |  |  | 1 | 44909 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
2023 Drawdown Tanks MEXP | Item | Open | MEXP | 1348250E2301 | Maintenance Framework |  | Stine, Carlton | Maintenance Support | 3. Active | Defined | Tanks |  | 375000 |  | 375000 | 775000 | -400000 | Red | 1000000 |  | 1000000 | -625000 |  |  | 1260000 |  |  | 1260000 | Full | 1260000 |  | 375000 | 375000 | No | Green | 2023-06-01 | 2022-12-12 | 2022-12-12 | 2023-12-31 | 2023-11-30 | [13 empty] | 115000 | 160000 | 100000 | [5 empty] | 4.14.23.DLC: Reduced by $400k to support tank 1202 demo... 4/4/23-CES-Reducing to offset Port Reading leg repair project. 3/20/23-CES-Reducing for Raritan Bay 0245 cleaning and idle and Port Reading tank 1210 emergent IFR findings. Also reducing for Tampa tank maintenance painting. 2/7/23-CES-Reducing Forecast by $140,000 to fund Carribean RBI project and another $25,000 to fund BBH Roof Failure cleaning and inspection. 11/29/22-CES-Reduced forecast on Effingham tank 12 and rolling into drawdown ($260,000). | 2023-04-14 | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Tank Integrity | Tank Integrity | Corporate | Corporate |  |  | 115000 | 260000 |  |  |  | Stine, Carlton | Shook, Mark B. |  |  | 1 | 45219 |  | Administrator, System | JDE Parent | Yellow | 2022-08-23 | Other Programs
Albany GA API 570 INSP 2022 | Item | Open | MEXP | BSEVY00E2201 | Maintenance Framework | 2003582 | Logan, Sam | Maintenance Support | 7. Closed | Drawdown | Facility Integrity | 2800 |  |  | 2800 | 2800 | 0 | Green |  |  |  | 2800 |  |  | 26000 |  |  | 26000 | Full | 26000 | 25058 |  | 25058 | No | Green | 2022-12-01 | 2022-07-21 | 2022-07-21 | 2022-12-31 | 2022-12-31 |  |  | 0 | 2800 | [17 empty] | 3/2/23 SL - Project complete 12/2/22 - Project delayed due to contractor 10/28/22 - Project delayed due to contractor | 2023-03-02 | Nguyen, Tong |  | South | Pipelines and Terminals | Station/Terminal |  | Southeast Terminals |  |  | 2800 | 0 |  |  | 22258 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 44139 |  | Meitzler, Antoinette | Independent | Aqua | 2022-07-14 | Int - Planned Corr & FI
Albany replace PIVs and Hydrants | Item | Candidate | MEXP |  | Maintenance Framework |  | Weirsky, Edward | Maintenance Support | 1. Proposed |  | Fire Protection |  | 60000 |  | 60000 | 60000 | 0 | Green | 60000 |  | 60000 | 0 | [9 empty] | 60000 | 60000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 20000 | 20000 | 20000 | [6 empty] | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | Albany | BATNY - BAT ALBANY |  |  | 0 | 60000 |  |  |  | Jakubowski, Gregory |  |  |  | 1 | 44601 |  | Guest, ProSight | Independent | Aqua | 2022-08-15 | Other Programs
Atlanta API 570 INSP 2022 | Item | Open | MEXP | BSEVZ00E2201 | Maintenance Framework | 2003583 | Logan, Sam | Maintenance Support | 7. Closed | Drawdown | Facility Integrity | -2090 |  |  | -2090 | -2090 | 0 | Green |  |  |  | -2090 |  |  | 37000 |  |  | 37000 | Full | 37000 | 32489 |  | 32489 | No | Green | 2022-12-01 | 2022-07-21 | 2022-07-21 | 2022-12-31 | 2022-12-31 |  |  | -2800 | 710 | [17 empty] | 2/17/23 SL - Project complete 12/2/22 - TN - contractor delayed 10/28/22 - TN - Contractor still delayed 9.30.22 - TN - Contractor delayed, work will be completed one month later. | 2023-03-02 | Nguyen, Tong |  | South | Pipelines and Terminals | Station/Terminal |  | Southeast Terminals |  |  | -2090 | 0 |  |  | 34579 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 44140 |  | Meitzler, Antoinette | Independent | Aqua | 2022-07-14 | Int - Planned Corr & FI
Auburn CO2 Fire System Replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Weirsky, Edward | Maintenance Support | 1. Proposed |  | Fire Protection |  | 35000 |  | 35000 | 35000 | 0 | Green | 35000 |  | 35000 | 0 | [9 empty] | 35000 | 35000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 35000 | [8 empty] | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Pipeline | AB - AUBURN STATION |  |  | 0 | 35000 |  |  |  | Jakubowski, Gregory |  |  |  | 1 | 44285 |  | Guest, ProSight | Independent | Aqua | 2022-07-27 | Other Programs
BBH - Delta V Upgrades Phase 2023 | Item | Candidate | MCAP |  | Maintenance Framework |  | White, Stephen | Maintenance Support | 1. Proposed |  | Instrumentation & Controls |  | 500000 |  | 500000 | 500000 | 0 | Green | 500000 |  | 500000 | 0 | [9 empty] | 500000 | 500000 | No | Green | 2023-05-01 |  |  |  | 2023-09-30 | 8 | Yellow |  |  |  |  | 25000 | 25000 | -25000 | Red |  |  | 75000 | 50000 | 125000 | 150000 | 100000 |  |  |  |  | 05/02/2023 -April forecast pushed to May as the scope is now defined to the point of AFE submission for approval. April 17, 2023 SGW - Rotork confirmed that 72 ea. A-range Actuators in Brownfield were changed out to Type IQ in during 2014. April 16, 2023 SGW - Greg Brunetta and Ed Miller arrive on island to start a 5-day technical survey of RIEs and Substations to determine what was installed/ what's missing from the 2011 - 2012 engineering design. April 6, 2023 SGW - meet with Bob Orischak and Dave DeSocio to review current situation with BBH Delta V system. Discussed recommendations for next steps. April 3, 2023 SGW - additional information obtained from Control Southern re: their 2021 walkdown of BBH Delta V. March 22, 2023 - Monthly update with IT. SGW showed photographs of each RIE, with extensive work remaining to be performed from 2016. The conclusion is that $500,000 to complete the Delta V system is not sufficient. Technical consultants must be brought in to assess existing conditions. March 13, 2023 SGW - walkdown of RIEs with QSL (local contractor). They provided more background information for why work was not completed in 2016. March 8, 2023 SGW - walk-down of RIEs with Carl Gibson (local contractor). Work from 2016 was not completed in any of the RIEs, and work from 2012 was not completed in some of the RIEs. 03/02/2023 - Per PM forecast in good. 2/12/2023 - Per PM forecast in good. | 2023-05-02 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 125000 | 375000 |  |  |  | Forsey, Frank |  |  |  | 1 | 35004 |  | Guest, ProSight | Independent | Aqua | 2019-08-30 | Other Programs
BBH - NLJ - Structural repairs 2023 | Item | Candidate | MCAP |  | Project Framework |  | White, Stephen | Maintenance Support | 1. Proposed |  | Marine |  | 1300000 |  | 1300000 | 650000 | 650000 | Red | 650000 |  | 650000 | 650000 | [9 empty] | 1300000 | 1300000 | No | Green | 2023-06-01 |  |  |  | 2023-09-30 | [13 empty] | 70000 | 150000 | 312500 | 312500 | 292500 | 162500 |  |  | 05/2023 - Forecast increased to prject full scope of 2023 project. $650K as budgeted for OLJ 2023 Structural repairs added. April 14, 2023 SGW - Teams meeting to review proposed Jetty projects with Tom Nash, Markella Spari and Angela Mirandi. April 13, 2023 SGW - Meeting with BIT re: budgetary pricing for jetty repairs. April 6, 2023 SGW - Review proposed 2023 Jetty projects with Bob Orischak and David DeSocio. April 4, 2023 SGW - Monthly update with Markella Spari and Angela Mirandi as to Jetty Projects at BBH. March 13, 2023 SGW - meeting today with Mechanical Engr (local contractor) re: pricing for blasting and coating on the jetties. They will revert with cost estimates. March 10, 2023 SGW - meeting with GB Insulators (local contractor) re: pricing for scaffolding on the jetties. They will revert with cost estimates. March 6, 2023 SGW - Meeting today with BIT re: order-of-magnitude pricing for various repairs. BIT will provide cost estimates. 03/02/2023 CC - Forecast pushed by two months per PM to run from months June to October. | 2023-05-02 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 70000 | 775000 | 455000 |  |  | Spari, Markella |  |  |  | 1 | 45327 |  | Spari, Markella | Independent | Aqua | 2022-08-25 | Marine
BBH - NSJ Minor Repairs - 2023 | Item | Candidate | MEXP |  | Project Framework |  | White, Stephen | Maintenance Support | 1. Proposed |  | Marine |  | 155000 |  | 155000 | 155000 | 0 | Green | 155000 |  | 155000 | 0 | [9 empty] | 155000 | 155000 | No | Green | 2023-10-01 |  |  |  | 2023-12-31 | [17 empty] | 90000 | 65000 |  |  | 05/02/2023 - Preliminary scope well defined. AFE is being drafted. 03/02/2023 - Forecasts has been confirmed per PM. 2/12/2023 - Forecasts has been confirmed per PM. | 2023-05-02 |  |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 0 |  | 155000 |  |  | Spari, Markella |  |  |  | 1 | 45907 |  | Clark, David | Independent | Aqua | 2022-09-25 | Other Programs
BBH - NSJ Structural repairs 2023 | Item | Candidate | MCAP |  | Project Framework |  | White, Stephen | Maintenance Support | 1. Proposed |  | Marine |  | 650000 |  | 650000 | 650000 | 0 | Green | 650000 |  | 650000 | 0 | [9 empty] | 650000 | 650000 | No | Green | 2023-05-01 |  |  |  | 2023-09-30 | 8 | Yellow |  |  |  |  | 20000 | 20000 | -20000 | Red |  |  | 20000 | 30000 | 150000 | 150000 | 150000 | 150000 |  |  |  | 05/02/2023 - Forecast adjusted to account for Interim AFE submittal and approval. Scope has now been defined. April 14, 2023 SGW - Teams meeting to review proposed 2023 jetty projects with Tom Nash, Markella Spari and Angela Mirandi. April 13, 2023 SGW - Meeting with BIT re: budgetary pricing for jetty repairs. April 6, 2023 SGW - review proposed 2023 jetty projects with Bob Orischak and Dave DeSocio. April 4, 2023 SGW - Monthly update with Markella Spari and Angela Mirandi as to Jetty Projects at BBH. March 13, 2023 SGW - Meeting today with Mechanical Engineering (local contractor) re: pricing for blasting and coating work on the jetties. They will revert with cost estimates. March 10, 2023 SGW - Meeting today with GB Insulators (local contractor) re: pricing for scaffolding on the jetties. They will revert with cost estimates. March 6, 2023 SGW - Meeting today with BIT (local contractor) re: pricing for structural repairs to jetties. They will revert with cost estimates. 03/02/2023 CC - Forecast adjusted to account for a pending delay per PM. The spends now run through September. 2/12/2023 CC - Recent change to PM assignment. Forecasts has been confirmed per PM. | 2023-05-02 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 50000 | 450000 | 150000 |  |  | Spari, Markella |  |  |  | 1 | 45324 |  | Spari, Markella | Independent | Aqua | 2022-08-25 | Marine
BBH - OLJ - Structural repairs 2023 | Item | Candidate | MCAP |  | Project Framework |  | White, Stephen | Maintenance Support | 1. Proposed |  | Marine |  |  |  | 0 | 650000 | -650000 | Red | 650000 |  | 650000 | -650000 | [11 empty] | No | Green |  |  |  |  | 2023-09-30 | [6 empty] | 20000 | 20000 | -20000 | Red | [11 empty] | 05/02/2023 - Forecast zeroed of $650K to be added to the NLJ 2023 Structural Repairs. 03/02/2023 - Forecast will be accurately adjusted once scope is defined. There is a possible delay in original forecasted spending. Forecast currently extended through to Septemeber. 2/12/2023 - Forecasts has been confirmed per PM. | 2023-05-02 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  |  | 0 |  |  |  |  | Spari, Markella |  |  |  | 1 | 45326 |  | Spari, Markella | Independent | Aqua | 2022-08-25 | Marine
BBH - Structural Upgrades - 2021 | Item | Open | MCAP | 8410811M2118 | Project Framework | 1856986 | White, Stephen | Maintenance Support | 6. Operational | Defined | Marine | 39935 | 995 | 29004 | 40929.83 | 37905 | 3024 | Yellow |  |  |  | 40930 |  |  | 2046000 |  | 1092000 | 3138000 | Supplemental | 3138000 | 3111026 | 29999 | 3141025 | No | Green | 2021-09-01 | 2021-11-08 | 2021-11-08 | 2021-12-31 | 2022-10-28 |  |  | -2616.8 | 12205.49 | 12321.65 | 18024.49 | 15000 | 15000 | 3024 | Red |  |  | 995 | [7 empty] | 29004 | March 9, 2023 SGW - Final walkthrough of 2022 structural repairs was accomplished today. Final Job Books remain to be completed. March 3, 2023 SGW - Final walkthrough of 2022 structural repairs scheduled for today has been cancelled due to high H2S levels on tanker at Berth 10. Ship's ETD is March 7. 1/19/23 SGW - Conducted a preliminary job site walk-thru this morning. Contractor has not removed all of his equipment, scaffolding and scrap material. Contractor notified to clean up the work site. 12/22/22 SGW - Change Order No 3 agreed to with BIT for work on NLJ. Bulk of additional cost is due to 78 days of Standby Time (29 days due to weather, and 49 days due to operational constraints). Other issues deal with VAT payments in 2021. Total Change Order amount is $346,296.28. Project Status awaiting final on-site walk through for clearance to be marked Operational. This will take place in Jan. 2023. 12/20/22 SGW - working with BIT (contractor) to reconcile final invoice; not quite finished. 11/17/22 SGW - working with Buckeye Accounting and Tom Nash to understand how VAT paid in calendar year 2021 and 2022 gets charged to the AFE, or not. 10/31/22 SGW - Construction work is complete, with minor de-mobilization tasks remaining. 10/5/22: Original BIT PO did not include VAT in budget 40 days of standby time for BIT worth $158,000 Balance of BIT CO#3 is for VAT for the remainder of PO. 6/8/22: Time Lost Weather – 18.5 Days Operations – 19.5 Days Schedule discussion Every delay we encounter pushes the completion back by the same amount (day for day). Due to weather and operational delays completion is now expected to be the week of July 11th. 5/11/22: Berth 10 – 90% completion of filler plates installation on the 4 accessible piles Berth 10 - 50% completion of saddle plates installation on 4 accessible piles Berth 10 – Delivery of 6 full lengths of pipes into near position. Flat rack material for additional jetty work received at BIT Time Lost Weather – 16.5 Days Operations – 12.5 Days (4.5 days in the past week and is are expecting more this week) Schedule discussion There has been a pretty large impact to the construction schedule due to High activity (w/ H2S) on Berths 9 and 10. This is expected to continue through Thursday (per the contractor). The project is 1 week delayed and expected completion is now July 1st. 3/1/22: Installation of berth 9 level 12’ installation approx. 75% complete. Anticipate 4/1/22 completion . Berth 10 to follow. -KB 1/11/22 - Change order for BIT added for existing piling work processed earlier than expected. DC 9/10/21 - Had the bid walk last week at BBH.Bids are due on Monday (9/13/21).Bidders were told project needs to be completed before end of year (12/31/21) Need to see where the bids come in (Cost &Schedule). Adjusted forecast based on AFE timing and will review with Kevin when he is back in the office. | 2023-04-04 | Ruiz, Felix |  | East | Pipelines and Terminals | Operating Infrastructure |  | Bahamas Hub | 841811 - BOR - MAINTENANCE |  | 21910 | 19019 |  |  | 1391514 |  | Spari, Markella | Nash, Tom |  |  | 1 | 38028 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Marine
BBH Jetty Piping 2023 Inspections | Item | Open | MEXP |  | Maintenance Framework |  | White, Stephen | Maintenance Support | 1. Proposed |  | Facility Integrity |  | 600000 |  | 600000 | 600000 | 0 | Green | 600000 |  | 600000 | 0 | [9 empty] | 600000 | 600000 | No | Green | 2023-06-01 |  |  |  | 2023-07-31 | [13 empty] | 300000 | 300000 | [6 empty] | 05/02/2023 - PM and team confirming project is duplicate to 2022 Jetty Inspections project carryover managed by Carnetta McDonald. | 2023-05-02 |  |  | East | Pipelines and Terminals | Station/Terminal |  | Bahamas Hub | 841818 - BOR - CAPITAL PROJECT DEPARTME |  |  | 300000 | 300000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 44986 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
BMTUA-Marrero Dock 3 Power | Item | Candidate | MCAP |  | Maintenance Framework |  | Brazzil, Cade | Maintenance Support | 1. Proposed |  | Electrical |  | 25000 |  | 25000 | 25000 | 0 | Green | 25000 |  | 25000 | 0 | [9 empty] | 25000 | 25000 | No | Green | 2023-08-01 |  |  |  | 2023-08-31 | [15 empty] | 25000 | [7 empty] | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Marrero | BMTUA - Marrero Terminal |  |  | 0 | 25000 |  |  |  | Ashley, Robert |  |  |  | 1 | 44414 |  | Guest, ProSight | Independent | Aqua | 2022-08-04 | Other Programs
BTXHF - Upgrade Relay Protection 15kV SWGR & AC | Item | Open | MCAP | BTXHF00M2212 | Maintenance Framework | 2023394 | Brazzil, Cade | Maintenance Support | 3. Active | Defined | Electrical | 58845 | 77602 |  | 136446.53 | 137217 | -770 | Yellow |  |  |  | 136447 |  |  | 250000 |  |  | 250000 | Phase | 250000 | 68254 | 77603 | 145857 | No | Green | 2022-10-01 | 2022-09-26 | 2022-09-26 | 2022-12-31 | 2023-09-30 |  |  | 25898.75 | 27164.92 | 5250.98 | 529.88 |  |  | 530 | Red |  |  |  | 7300 | 34000 | 27302 | 9000 |  |  |  |  | 1.3.2023 TN - GE Grid shipped in January. Forecast shifted. 12.1.22 - TN - Saber Power for an outage, work will take place next year, forecast shifted 11.1.22 - TN - Project pushing into next year, forecast has been shifted to reflect the delay 10/26/22 Powell was issued a PO last week and provided deliverables today. Prinst were issued to Bob Ashely, Mattew Finely, and Jorge Valquez for record. 8-29-22 Saber dropped the ball and had there salesman quit 3 weeks ago. No one had pursued our quotes for this project. PM is now working on quotes. 8.8.22.DLC: reallocated $80k from overall arc flash OPPM entry3.24.22.DLC: Possible change in scope. PM ready to change relays. If we do parallel building need additional funds. In holding pattern | 2023-01-23 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 58315 | 7830 | 70302 |  | 9409 | 1 | Ashley, Robert |  |  |  | 1 | 41815 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
BTXPP - Arc Flash Mitigation 2022 - E1000, E5000, E6000 | Item | Open | MCAP | BTXPP00M2221 | Maintenance Framework | 2023391 | Brazzil, Cade | Maintenance Support | 3. Active | Defined | Electrical | 5914 | 118840 |  | 124753.76 | 123349 | 1404 | Yellow | 200000 |  | 200000 | -75246 |  |  | 401000 |  |  | 401000 | Phase | 401000 | 295622 | 168840 | 464462 | No | Green | 2022-11-01 | 2022-10-03 | 2022-10-03 | 2022-12-31 | 2023-09-30 |  |  | 1760.99 | 1361.48 | 1386.97 | 1404.32 |  |  | 1404 | Red |  |  |  |  | 118840 | [6 empty] | 4.3.23 - TN/Per Cade, Forecasting of 81k removed to be transferred to STGT. 11.1.22 - No delay, project was to start in November | 2023-04-03 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 4509 | 1404 | 118840 |  | 289708 | 50000 | Ashley, Robert | Johnson, AJ |  |  | 1 | 44495 |  | Clark, David | Independent | Aqua | 2022-08-09 | Other Programs
BTXPP - Arc Flash Mitigation at PDC2 | Item | Open | MCAP | BTXPP00M2222 | Maintenance Framework |  | Brazzil, Cade | Maintenance Support | 8. Canceled |  | Electrical |  |  |  | 0 |  | 0 | Green | 75000 |  | 75000 | -75000 | [6 empty] | Interim |  |  |  |  | No | Green |  |  |  |  | 2023-05-31 | [21 empty] | <12.7.22.DLC> item no longer needed - rolled into different12.1.22 TN - Forecast of 75k removed. Project will be closed 8.17.22.DLC: Removed $160k as scope decreased | 2022-12-07 |  |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 0 |  |  |  |  | Ashley, Robert |  |  |  | 1 | 44496 |  | Clark, David | Independent | Aqua | 2022-08-09 | Other Programs
BTXPP - Arc Flash Mitigation for Control Room Breakers (3) | Item | Candidate | MCAP |  | Maintenance Framework |  | Brazzil, Cade | Maintenance Support | 4. On-Hold | Defined | Electrical |  | 20000 |  | 20000 | 20000 | 0 | Green | 20000 |  | 20000 | 0 | [9 empty] | 20000 | 20000 | No | Green | 2023-10-01 |  |  |  | 2023-10-31 | [17 empty] | 20000 |  |  |  | 8.17.22.DLC: Moved $160k in from PDC2 item, then moved all $275k out to fund Charging pumps project for 2022. This effort to be reviewed for 2023 execution 8.9.22.DLC: Moved $950k into new entry for BTXPP Arc Flash Mitigation 20228.8.22.DLC: moved $80k into 15kV SWGR&AC 6.29.22.DLC: Allocated funds to 2 other projects. 5.25.22.DLC: Funds merged over from BTXHF project3.24.22.DLC: Will present AFE to develop options next week. | 2022-08-17 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 0 |  | 20000 |  |  | Ashley, Robert |  |  |  | 1 | 41775 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
BTXPP - Arc Flash Mitigation Placeholder 2023 | Item | Candidate | MCAP |  | Maintenance Framework |  | Brazzil, Cade | Maintenance Support | 8. Canceled |  | Electrical |  |  |  | 0 |  | 0 | Green | 250000 |  | 250000 | -250000 | [11 empty] | No | Green |  |  |  |  | 2023-08-31 | [21 empty] | 2.1.23 TN - Funds used for carry over on other BTP Electrical projects . Record Canceled. 12.7.22.DLC: Funds include requirements for BTXHF and BTXPP as needed | 2023-02-01 |  |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 0 |  |  |  |  | Ashley, Robert |  |  |  | 1 | 45258 |  | Clark, David | Independent | Aqua | 2022-08-24 | Other Programs
BTXPP - Charging Pumps Aux Feed | Item | Open | MCAP | BTXPP00M2220 | Maintenance Framework |  | Brazzil, Cade | Maintenance Support | 2. Pending AFE | Drawdown | Electrical |  | 330000 |  | 330000 | 330000 | 0 | Green | 330000 |  | 330000 | 0 |  |  | 330000 |  |  |  | Interim | 330000 |  | 680000 | 680000 | No | Green | 2023-08-01 |  |  | 2023-01-31 | 2023-11-30 | [15 empty] | 50000 | 100000 | 100000 | 80000 |  |  | 12.1.22 - Still waiting on engineering prints to be issued, forecast shifted | 2022-12-01 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 0 | 150000 | 180000 |  | 350000 | Ashley, Robert | Ashley, Robert |  |  | 1 | 44658 |  | Clark, David | Independent | Aqua | 2022-08-17 | Other Programs
BTXPP - LPG Bus Bar for Temp Generator | Item | Open | MCAP | BTXPP00M1723 | Exempt | 1359168 | Brazzil, Cade | Maintenance Support | 4. On-Hold | Emergent | South | -117 |  |  | -117.06 | -117 | 0 | Green |  |  |  | -117 |  |  | 135000 |  |  | 135000 | Phase | 135000 | 20828 |  | 20828 | No | Green | 2020-01-01 | 2017-07-27 | 2017-07-27 | 2017-12-31 | 2023-02-28 |  |  |  |  | -117.06 | [16 empty] | 2.1.23 - TN - To be reclassed to Expense and Closed/Canceled. 12.1.22 - Still waiting on engineering prints to be issued, forecast shifted 11.1.22 - TN - Still on hold waiting on contractor to issue engineering prints 9.29.22 - TN - Moved forecast of 30k to Nov/Dec as we wait on contractor response 8.8.22.DLC: moved $30k from Arc Flash Program Budget to continue or complete engineering 7/9/18 - Working on path forward with management and decision on load list. 6/7/18 - Working on path forward with management. 5/4/18 - Options assessment is complete meeting with management to discuss path forward. 4/8/18 - Options assessment is complete meeting with management to discuss path forward. 2/7/18 - Options assessment and detail engineering to being this month. 12/8/17 - Engineering options / assessment complete 11/8/17 - Engineering Design is progressing 10/6 - Engineering Design is progressing 9/8 - PO placed for Engineering and feasibility analysis. 7/10/2017 - Engineering firm selected. Feasibility study in Progress. | 2023-02-01 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | -117 | 0 |  |  | -30874 |  | Johnson, AJ | Mann, Richard | N/A |  | 1 | 21697 |  | Administrator, System | Independent | Aqua | 2016-09-23 | Other Programs
Buffalo Fire Water System Upgrades - Phase 1 | Item | Open | MCAP | BETBO00M2202 | Maintenance Framework | 2004063 | Weirsky, Edward | Maintenance Support | 3. Active | Defined | Fire Protection | 596 | 230000 |  | 230596 | 230490 | 106 | Yellow | 230000 |  | 230000 | 596 |  |  | 75000 |  |  | 75000 | Phase | 75000 | 22350 | 230000 | 252350 | No | Green | 2022-08-01 | 2022-07-26 | 2022-07-26 | 2022-12-31 | 2023-09-30 |  |  | 308.74 | 76.19 | 104.9 | 106.17 |  |  | 106 | Red |  |  |  |  | 50000 | 90000 | 90000 |  |  |  |  | 5/8/23 - Funding may need to be diverted to New Haven for regulatory foam projects (GJ);3/30/23 - Per Ed, project is on hold waiting for response from fire department 1/3/23 - Per Ed, engineering design completed. 9/6/22 (GJ) STV On Site in August for Engineering, awaiting report. Forecast is accurate 5/5/2022 EC- Forecasts entered. 4/7/2022 EC- No change forecasts. 2/7/2022 EC- Forecasts entered. | 2023-05-08 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BETBO - BET BUFFALO TERMINAL |  | 490 | 106 | 230000 |  | 21754 |  | Jakubowski, Gregory | Jakubowski, Greg |  |  | 1 | 24524 |  | Administrator, System | Independent | Aqua | 2017-07-27 | Other Programs
Charlotte I - (BSEVC) New Security Cameras & NVR | Item | Open | MCAP | BSEVC00M2201 | Maintenance Framework | 1991119 | Logan, Sam | Maintenance Support | 6. Operational | Defined | Security & Cameras | 37204 |  |  | 37203.88 | 46437 | -9233 | Red |  |  |  | 37204 |  |  | 35000 | 37000 |  | 72000 | Full | 72000 | 64956 |  | 64956 | No | Green | 2022-07-01 | 2022-06-18 | 2022-06-18 | 2022-12-31 | 2023-03-31 |  |  | 8965.02 | 35639 | 1833.01 | -9233.15 |  |  | -9233 | Red | [11 empty] | 5/2/23 SL - Project complete; 4/3/23 - TN/Per SL, Project is operational and complete. 3/2/23 SL - To complete in March; 2/2/23 - TN - Contractor delay due to local operations limiting work hours 12.2.22 - TN - Contractor delay 10.28.22 - November forecast changed to 30k due to pricing updates 6.30.22.DLC: Inputted initial forecast | 2023-05-02 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | North Carolina | BSEVC - CHARLOTTE I TERMINAL |  | 46437 | -9233 |  |  | 27752 |  | Clark, Chris | Clark, Chris B |  |  | 1 | 43957 |  | Clark, David | Independent | Aqua | 2022-06-10 | Other Programs
Charlotte II - (BSEVD) New Security Cameras & NVR | Item | Open | MCAP | BSEVD00M2201 | Maintenance Framework | 1991125 | Logan, Sam | Maintenance Support | 6. Operational | Defined | Security & Cameras | 47934 |  |  | 47934.14 | 76101 | -28167 | Red |  |  |  | 47934 |  |  | 36000 | 37000 |  | 73000 | Full | 73000 | 82846 |  | 82846 | Yes | Red | 2022-07-01 | 2022-06-18 | 2022-06-18 | 2022-12-31 | 2023-04-17 |  |  | 261.12 | 33815.33 | 35649.59 | -21791.9 | 6375 | 6375 | -28167 | Red | [11 empty] | 5/2/23 SL - Project complete; 4/5/23 SL - almost complete, waiting for final work, 3/2/23 SL - To complete in March; 2/17/23 SL - Work scheduled to start end of Feb 12.9.22 - Convergint technology equipment bill* 10/28/22 TN - Old Dominion work for install added for december 6.30.22.DLC: Inputted initial forecast | 2023-05-02 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | North Carolina | BSEVD - CHARLOTTE II TERMINAL |  | 69726 | -21792 |  |  | 34912 |  | Clark, Chris | Clark, Chris B |  |  | 1 | 43958 |  | Clark, David | Independent | Aqua | 2022-06-10 | Other Programs
Chesapeake Ship Pile Wraps, Berth, Dolphins | Item | Open | MCAP | BETQC00M2203 | Project Framework | 1938778 | Clark, Dave | Maintenance Support | 6. Operational | Defined | Marine | 39281 |  |  | 39281.03 | 39281 | 0 | Green |  |  |  | 39281 |  |  | 32000 | 1133000 |  | 1165000 | Full | 1165000 | 1113533 |  | 1113533 | No | Green | 2022-03-01 | 2022-01-20 | 2022-01-20 | 2022-12-31 | 2022-12-12 |  |  | 45534.35 | -6253.32 | [17 empty] | 02.09.23 SDB: Project to be closed. Missing one last invoice from MSI. 01.31.23 SDB: MSI completed and submitted as-built drawings for ship dock. 01.03.23 SDB: MSI working on as-built drawings for the dock. 12.14.22 SDB: Completing Job Book for the project. 12.12.22 SDB: Marine Solutions completed the work, cleaned and demobilized from the jobsite. Dock is operational. 12.2.22 TN - Marine Solutions ahead of schedule 11.28.22 SDB: Contractor returned. Installing jackets on MD piles and welding anodes. 11.25.22 SDB: Contractor finished coating of access trestle and breasting dolphins. Left the jobsite during Thanksgiving week. 10/31.22 SDB: Contractor completed splice plates on both the North and South breasting dolphins. 10.19.22 SDB: Started installation of splice plates on the North BD. 10.17.22 SDB: Contractor MSI working installing pile jacket on main platform. Completed the 17 pile jackets on the main platform. Moved to the North breasting dolphin to start installation of the splice plates. 10.5.22 SDB: Contractor Marine Solutions Inc (MSI) mobilized to the jobsite on 10/3. Started working but slight delay due to weather. 9.20.22 SDB: Contractor will make one site pre-mob visit on 09/29/22. Splice plates delivered to the galvanizer. 9.16.22 SDB: Contractor preparing for mobilization. All permanent materials are ordered. Mobilization for 10/03/22. 9.9.22 MKS No 2023 carryover 9.2.22 SDB. Marine Solutions preparing for the project. Presently scheduled to mob on 10/03/22. 8.22.22 SDB: Marine Solutions Inc. received their PO for the work. 7.29.22 SDB: Completed TRC for the project. Awaiting final approvals for the AFE prior to issuing PO to the Contractor. 7.20.2022.DLC: Allocated funds from Bronx and Perth Projects postponed to 2023... 7.8.22 SDB: Marine Solutions completed an inventory and inspection at the terminal. Contractor to present a revised proposal which will include the revised repair procedures to be used. 6.10.22 SDB: LOI wassent and accepted by the winning contractor Marine Solutions. 5.31.22 SDB: Bid process was extended and additional contractors were invited. Bid process closed on 05/25 and we are presently reviewing proposals with short listed contractors in order to award the work. 5.2.22 SDB: Received proposals from bidding contractors. Will review the proposals and schedules to determine award and issue a PO. 4.11.22 SDB: This project is presently being bid out by supply chain. Bids due 3rd week of April. 3.31.22SDB: Supply Chain scheduled to hold the bid process in the first half of April. 2.18.22.DLC Bidding out with supply chain | 2023-02-10 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | Virginia | BETQC - BET CHESAPEAKE TERMINAL |  | 39281 | 0 |  |  | 1074252 |  | Spari, Markella | Martin, David N. |  |  | 1 | 38020 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Marine
Corp Engineering Surveys | Item | Candidate | MEXP |  | Exempt |  | Clark, Dave | Maintenance Support | 1. Proposed |  | Corporate |  | 200000 |  | 200000 | 200000 | 0 | Green | 200000 |  | 200000 | 0 | [9 empty] | 200000 | 200000 | No | Green | 2023-06-01 |  |  |  | 2023-09-30 | [13 empty] | 50000 | 50000 | 50000 | 50000 | [8 empty] | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal | Station/Terminal | Corporate | Corporate |  |  | 50000 | 150000 |  |  |  | Clark, Dave |  |  |  | 1 | 45885 |  | Clark, David | Independent | Aqua | 2022-09-21 | Other Programs
Detroit - Waterfront restoration | Item | Open | MCAP | BETWD00M2303 | Maintenance Framework | 2121573 | Logan, Sam | Maintenance Support | 3. Active | Defined | Marine |  | 300000 |  | 300000 | 300000 | 0 | Green | 300000 |  | 300000 | 0 |  |  | 80730 |  |  | 80730 | Phase | 80730 |  | 4100000 | 4100000 | No | Green | 2023-05-01 | 2023-05-09 | 2023-05-09 | 2023-08-15 | 2023-07-31 | [12 empty] | 20000 | 50000 | 50000 | 50000 | 50000 | 80000 |  |  |  | 5/2/23 SL - AFE is processing; 4/4/23 SL - Eng firm chosen to do 1st step in project, 3/2/23 SL - Bids due 3/3; 2/17/23 SL - Set up bid event, Proposals due Feb 24 | 2023-05-02 | Nguyen, Tong |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETWD - DETROIT BET TERMINAL |  |  | 70000 | 150000 | 80000 |  | 1800000 | Spari, Markella | Miller, Michael A. |  |  | 1 | 45794 |  | Clark, David | Independent | Aqua | 2022-09-10 | Marine
Doraville I - (BSEVH) New Security Cameras & NVR | Item | Open | MCAP | BSEVH00M2201 | Maintenance Framework | 1991126 | Logan, Sam | Maintenance Support | 6. Operational | Defined | Security & Cameras | 45884 |  |  | 45883.68 | 72745 | -26862 | Red | 33200 |  | 33200 | 12684 |  |  | 36000 | 37000 |  | 73000 | Full | 73000 | 62348 |  | 62348 | No | Green | 2022-09-01 | 2022-06-18 | 2022-06-18 | 2022-12-31 | 2023-04-14 |  |  | 75.95 | 77.32 | 70169.03 | -24438.62 | 2423 | 2423 | -26862 | Red | [11 empty] | 5/2/23 SL - Cameras are functional, contractor to make a few adjustments; 4/3/23 - TN/SL - Contractor delay, expecting to finish 2nd week of April. 3/2/23 TN/SL - Contractor is expecting to finish in March 2/17/23 SL - Work scheduled to start in April; 6.30.22.DLC: Inputted initial forecast | 2023-05-02 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Georgia | BSEVH - DORAVILLE I TERMINAL |  | 70322 | -24439 |  |  | 16465 |  | Clark, Chris | Clark, Chris B |  |  | 1 | 43959 |  | Clark, David | Independent | Aqua | 2022-06-10 | Other Programs
Doraville II - (BSEVK) New Security Cameras & NVR | Item | Open | MCAP | BSEVK00M2201 | Maintenance Framework | 1991128 | Logan, Sam | Maintenance Support | 6. Operational | Defined | Security & Cameras | 46195 |  |  | 46194.58 | 73037 | -26842 | Red | 33200 |  | 33200 | 12995 |  |  | 36000 | 37000 |  | 73000 | Full | 73000 | 62980 |  | 62980 | No | Green | 2022-09-01 | 2022-06-18 | 2022-06-18 | 2022-12-31 | 2023-04-14 |  |  | 77.43 | 78.83 | 70170.56 | -24132.24 | 2710 | 2710 | -26842 | Red | [11 empty] | 5/2/23 SL - Cameras are functional, contractor to make a few adjustments; 4/3/23 - TN, Per SL, contractor is expecting to finish 2nd week of April 3/2/23 - TN/SL - Contractor is now expecting to complete work in March 2/17/23 SL - Work scheduled to start in April; 6.30.22.DLC: Inputted initial forecast | 2023-05-02 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Georgia | BSEVK - DORAVILLE II TERMINAL |  | 70327 | -24132 |  |  | 16785 |  | Clark, Chris | Clark, Chris B |  |  | 1 | 43960 |  | Clark, David | Independent | Aqua | 2022-06-10 | Other Programs
Fairfax Truck Rack Fire Piping Replacement | Item | Open | MCAP | BETFF00M2204 | Maintenance Framework | 2004050 | Weirsky, Edward | Maintenance Support | 3. Active |  | Fire Protection | 10503 | 99954 |  | 110457.19 | 103678 | 6779 | Yellow |  |  |  | 110457 |  |  | 177000 |  | 50000 | 227000 | Supplemental | 227000 | 120888 | 99954 | 220842 | No | Green | 2022-09-01 | 2022-07-26 | 2022-07-26 | 2022-12-31 | 2023-06-30 |  |  | -230.91 | 431.22 | 5523.97 | 4778.91 | 32150 | 32150 | -27371 | Red |  | Contractor/Vendor Issue | 68954 | 31000 | [7 empty] | 5/2/23 - TN/EW - Installation issue, work rescheduled for following month 3/30/23 - TN/EW - Permit delay from fire department 3/2/23 - TN/EW - Waiting for Fairfax Permit Approval 2/27/23 - TN - Supplement AFE Submitted 2/2/23 - TN - Vendor delay due to electrical work, forecast pushed. 12/15/22 - TN - Permit approval was issued late, vendor pushed work 10/10/22 Fire pipe was delivered last week, and install will start this week. The equipment for fire suppression system delivery date is being pushed to the end of October early November. Moved some of the money in October to November. 9/15/22 TN - Contractor was unable to start in August, work was pushed. Will be starting at end of September. 7/12/22.GJ - Allocated Funds from fire alarm panel upgrade to be used for this, funding from Perth Amboy tank 769 deferred project | 2023-05-02 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | Virginia | BETFF - BET FAIRFAX |  | 5724 | 104733 |  |  | 110385 |  | Jakubowski, Gregory | Jakubowski, Greg |  |  | 1 | 44086 |  | Clark, David | Independent | Aqua | 2022-07-07 | Other Programs
Greensboro 2 API 570 INSP 2022 | Item | Open | MEXP | BSEVV00E2201 | Maintenance Framework | 2003587 | Logan, Sam | Maintenance Support | 7. Closed | Drawdown | Facility Integrity | -11420 |  |  | -11419.6 | -11420 | 0 | Green |  |  |  | -11420 |  |  | 33000 |  |  | 33000 | Full | 33000 | 17129 |  | 17129 | No | Green | 2022-11-01 | 2022-07-21 | 2022-07-21 | 2022-12-31 | 2022-12-31 |  |  |  | -11419.6 | [17 empty] | 2/17/23 SL - Project complete 10/28/22 TN - Contractor Delayed work 9.30.22 TN - Contractor Delayed work | 2023-03-02 | Nguyen, Tong |  | South | Pipelines and Terminals | Station/Terminal |  | Southeast Terminals |  |  | -11420 | 0 |  |  | 28549 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 44136 |  | Meitzler, Antoinette | Independent |  | 2022-07-15 | Int - Planned Corr & FI
JDE Field Tagging Updates and Validation - Round 1 - 2022 | Item | Open | MEXP | 1348250E2240 | Exempt | 2023786 | Clark, Dave | Maintenance Support | 3. Active | Emergent | Corporate | 8045 | 5091 |  | 13136 | 17942 | -4806 | Red |  |  |  | 13136 |  |  | 33000 |  |  | 33000 | Full | 33000 | 16227 | 5091 | 21318 | No | Green | 2022-11-01 | 2022-09-27 | 2022-09-27 | 2022-12-31 | 2023-07-31 |  |  | 0 | -919 | 3942 | 5022 | 2500 | 2500 | 2522 | Red |  |  | 2500 | 1250 | 1341 | [6 empty] | 12/22/22 SGW - Contractor continues working on this project on a part-time basis due to commitments with Project Ocean. Limited availability in Dec 2022. Work with switchgear will commence during the week of Dec. 26 - 30. 12/1/22 TN - Contractor started work in November but only part time due to workload associated with project ocean. Forecast pushed into next year. 10/28/22 TN - Contractor pushed work due to project ocean 11/30/22 SGW - Contractor has finished the Round 1 work for Pumps and Motors. Will start working on the Switchgear portion of the assignment in early December. Work is being performed on a part-time basis, as the consultant is fully engaged in Project Ocean. | 2023-03-02 | Nguyen, Tong |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Station/Terminal | Station/Terminal | Corporate | Corporate |  | 3023 | 8772 | 1341 |  | 8182 |  | Clark, Dave | Clark, David |  |  | 1 | 44636 |  | Clark, David | Independent | Aqua | 2022-08-16 | IT
Knoxville 2 API 570 INSP 2022 | Item | Open | MEXP | BSEUK00E2201 | Maintenance Framework | 2003567 | Logan, Sam | Maintenance Support | 7. Closed | Drawdown | Facility Integrity | -17220 |  |  | -17220 | -17220 | 0 | Green |  |  |  | -17220 |  |  | 20000 |  |  | 20000 | Full | 20000 | 17220 |  | 17220 | No | Green | 2022-10-01 | 2022-07-21 | 2022-07-21 | 2022-12-31 | 2022-12-16 |  |  | -17220 | [18 empty] | 2/17/23 SL - Project complete | 2023-03-02 | Nguyen, Tong |  | South | Pipelines and Terminals | Station/Terminal |  | Southeast Terminals |  |  | -17220 | 0 |  |  | 34440 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 44148 |  | Meitzler, Antoinette | Independent | Aqua | 2022-07-14 | Int - Planned Corr & FI
Knoxville I - (BSEUI) New Security Cameras & NVR | Item | Open | MCAP | BSEUI00M2201 | Maintenance Framework | 1991129 | Logan, Sam | Maintenance Support | 3. Active | Defined | Security & Cameras | 1219 | 40940 |  | 42158.86 | 42087 | 72 | Yellow | 30000 |  | 30000 | 12159 |  |  | 35000 | 37000 |  | 72000 | Full | 72000 | 15146 | 40940 | 56086 | No | Green | 2022-09-01 | 2022-06-18 | 2022-06-18 | 2022-12-31 | 2023-05-31 |  |  | 64.24 | 992.57 | 90.1 | 71.95 |  |  | 72 | Red |  |  | 40940 | [8 empty] | 5/2/23 SL - Work scheduled for this month; 6.30.22.DLC: Inputted initial forecast | 2023-05-02 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Tennessee | BSEUI - KNOXVILLE I TERMINAL |  | 1147 | 41012 |  |  | 13927 |  | Clark, Chris | Clark, Chris B |  |  | 1 | 43961 |  | Clark, David | Independent | Aqua | 2022-06-10 | Other Programs
Knoxville II - (BSEUK) New Security Cameras & NVR | Item | Open | MCAP | BSEUK00M2201 | Maintenance Framework | 1991130 | Logan, Sam | Maintenance Support | 3. Active | Defined | Security & Cameras | -10189 | 41669 |  | 31479.59 | 31402 | 78 | Yellow | 30000 |  | 30000 | 1480 |  |  | 36000 | 37000 |  | 73000 | Full | 73000 | 16324 | 41669 | 57993 | No | Green | 2022-09-01 | 2022-06-18 | 2022-06-18 | 2022-12-31 | 2023-05-31 |  |  | -10417.73 | 74.19 | 76.59 | 77.54 |  |  | 78 | Red |  |  | 41669 | [8 empty] | 5/2/23 SL - Work scheduled for this month; 6.30.22.DLC: Inputted initial forecast | 2023-05-02 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Tennessee | BSEUK - KNOXVILLE II TERMINAL |  | -10267 | 41747 |  |  | 26513 |  | Clark, Chris | Clark, Chris B |  |  | 1 | 43962 |  | Clark, David | Independent | Aqua | 2022-06-10 | Other Programs
Louisville - Jumper arm rework | Item | Open | MEXP | BETVL00E2208 | Project Framework | 2036909 | Logan, Sam | Maintenance Support | 3. Active | Emergent | Marine | 3750 |  |  | 3750 | 3750 | 0 | Green |  |  |  | 3750 |  |  | 25000 |  |  | 25000 | Phase | 25000 | 17750 |  | 17750 | No | Green | 2022-11-01 | 2022-10-14 | 2022-10-14 | 2022-12-31 | 2023-05-31 |  |  | 0 | 3750 | [17 empty] | 5/2/23 SL - PO being processed but will be processed under another project of Markellas 4/5/23 SL - waiting for proposal from new eng firm, 3/2/23 SL - Gathering costs for different options; 2/17/23 SL - Secured data for decision on best path forward 12.14.22 SDB: LEI presented their evaluation memo for the three repair options being considered. 11.25.22 SDB: Lloyd completed inspection at the Louisville terminal in order gather additional information to provide an evaluation of the alternate proposed repair methods. 10.31.22 SDB: Lloyd completed the additional drawings requested for the exhibits. Reviewed with stakeholders on 10/31. Additional solutions to the jumper arm issue are now being considered and evaluated. 10.17.22 SDB: Lloyd completed and transmitted the exhibits for our review on 10/17. Added additional sow to the project. Once approved they will need to finish engineering and produce the IFC documents. 9.29.22 SDB Obtaining proposals from Contractors for the work. Working with Lloyd reviewing quotes and documentation. | 2023-05-03 | Nguyen, Tong |  | West | Pipelines and Terminals | Station/Terminal |  | Southern Ohio | BETVL - BET LOUISVILLE |  | 3750 | 0 |  |  | 14000 |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 45905 |  | Clark, David | Independent | Aqua | 2022-09-25 | Marine
Macon - (BSEUJ) New Security Cameras & NVR | Item | Open | MCAP | BSEUJ00M2201 | Maintenance Framework | 1991131 | Logan, Sam | Maintenance Support | 3. Active | Defined | Security & Cameras | 272 | 40458 |  | 40729.92 | 40660 | 70 | Yellow | 30000 |  | 30000 | 10730 |  |  | 35000 | 37000 |  | 72000 | Full | 72000 | 14652 | 40458 | 55110 | No | Green | 2022-09-01 | 2022-06-18 | 2022-06-18 | 2022-12-31 | 2023-05-31 |  |  | 66.05 | 67.53 | 68.74 | 69.6 |  |  | 70 | Red |  |  | 40458 | [8 empty] | 5/2/23 SL - Still on target for end of May; 4/3/23 - TN/SL - Work scheduled for completion by end of May 2/17/23 SL - Work scheduled for April; 6.30.22.DLC: Inputted initial forecast | 2023-05-02 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Georgia | BSEUJ - MACON TERMINAL |  | 202 | 40528 |  |  | 14380 |  | Clark, Chris | Clark, Chris B |  |  | 1 | 43963 |  | Clark, David | Independent | Aqua | 2022-06-10 | Other Programs
Macon API 570 INSP 2022 | Item | Open | MEXP | BSEUJ00E2201 | Maintenance Framework | 2003581 | Logan, Sam | Maintenance Support | 6. Operational | Drawdown | Facility Integrity | -2800 |  |  | -2800 | 0 | -2800 | Red |  |  |  | -2800 |  |  | 9000 |  | 2470 | 11470 | Full | 11470 | 8670 |  | 8670 | No | Green | 2022-12-01 | 2022-07-21 | 2022-07-21 | 2022-12-31 | 2022-12-31 |  |  | -2800 | 2800 | 0 | -2800 |  |  | -2800 | Red | [11 empty] | 3/2/23 SL - Project complete 10.28.22 TN - Project pushed a month | 2023-03-06 | Nguyen, Tong |  | South | Pipelines and Terminals | Station/Terminal |  | Southeast Terminals |  |  | 0 | -2800 |  |  | 11470 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 44143 |  | Meitzler, Antoinette | Independent | Aqua | 2022-07-14 | Int - Planned Corr & FI
Macungie Fire Panel Replacement | Item | Open | MCAP | BESZG00M2301 | Maintenance Framework | 2077029 | Weirsky, Edward | Maintenance Support | 3. Active | Defined | Fire Protection | 18705 | 18375 |  | 37079.73 | 39752 | -2672 | Yellow | 30000 |  | 30000 | 7080 |  |  | 45793 |  |  | 45793 | Full | 45793 | 18705 | 18375 | 37080 | No | Green | 2023-02-01 | 2023-01-30 | 2023-01-30 | 2023-03-31 | 2023-05-31 |  |  |  | 5000 | 13505 | 199.73 | 21247 | 21247 | -21047 | Red |  | Contractor/Vendor Issue | 18375 | [8 empty] | 5/2/23 - TN/EW - Permit delay, work pushed 3/2/23 TN/EW - Scheduling work for Kistler in mid to late March with expected project completion by end of April. | 2023-05-02 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | Macungie Terminal | BESZG - BES MACUNGIE #1 TERM FH 1&2 |  | 18505 | 18575 |  |  |  |  | Jakubowski, Gregory |  |  |  | 1 | 45774 |  | Clark, David | Independent | Aqua | 2022-09-08 | Other Programs
New Haven 85 East Fire Foam Tank Replacement | Item | Open | MCAP | BNTNX00M2106 | Maintenance Framework | 1903401 | Weirsky, Edward | Maintenance Support | 3. Active | Defined | Fire Protection | 34190 | 719600 |  | 753789.59 | 747502 | 6288 | Yellow | 720000 |  | 720000 | 33790 |  |  | 172000 | 627000 |  | 799000 | Phase | 799000 | 223739 | 719600 | 943339 | No | Green | 2021-12-01 | 2021-10-29 | 2021-10-29 | 2021-12-31 | 2023-08-31 |  |  | 873.71 | 8260 | 8653.03 | 16402.85 | 12365 | 12365 | 4038 | Red |  |  | 12250 | 257350 | 200000 | 250000 | [5 empty] | 5/8/23 - Plumbing/fire permits received for truck rack upgrade (GJ); 3/3/23 TN/EW - Continue to coordinate with fire department for design approval. 2/2/23 TN - Coordinating with fire department for design approval - forecast pushed 9/9/22 TN - 800k forecasted into 2023 per Ed and Greg's request 8/25/22 TN - Forecasts incorrectly swapped with another project. Resolved. 4/7/2022 EC- Forecasts entered. 2/7/22 EC: Forecasts updated. 1/11/22 - Scope expanded more than expected. In process to ascertain costs. Forecasts for 2022 to be updated. DC 1/10/2021 EC- Forecasts updated. | 2023-05-08 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNX - New Haven 85 East Terminal |  | 17787 | 286003 | 450000 |  | 173948 |  | Jakubowski, Gregory | Buchalski, Edwin |  |  | 1 | 37117 |  | DeSocio, David | Independent | Aqua | 2020-07-16 | Other Programs
New Haven Forbes Terminal Replace Fire Foam | Item | Open | MCAP | BNTNF00M2102 | Maintenance Framework | 1901340 | Weirsky, Edward | Maintenance Support | 3. Active | Defined | Fire Protection | 74519 | 317424 |  | 391943.29 | 389864 | 2079 | Yellow | 456000 |  | 456000 | -64057 |  |  | 284000 | 421000 |  | 705000 | Full | 705000 | 300144 | 317424 | 617568 | No | Green | 2021-10-01 | 2021-10-10 | 2021-10-10 | 2021-12-31 | 2023-07-31 |  |  | 1907.58 | 12512.26 | 6175.16 | 53924.29 | 44500 | 44500 | 9424 | Red |  |  | 189564 | 66058 | 61802 | [6 empty] | 5/8/23 - Water cutover being completed, water tank to be removed (GJ); 3.3.23 - TN/EW - Awaiting on equipment delivery 2.2.23 - Contractor delay, forecast pushed. 1.3.23 - Contractor delay, forecast pushed. 12/15/22 - Disposal work was completed. Remaining PO closed. 12/1/22 - Contractor delay due to permits pushed to next year 10/28/22 - 150k added and split between November and December. Rapid Fire is working on getting permits to advance the work. 9/22/22 Currently working on supplement EJW 9/15/22 TN - variance for August was due to forecast numbers being swapped with another project on accident. 9/9/22 TN - forecasted estimated additional project cost in 2023 per Ed and Greg's request. 7/12/22.GJ - added $118k in forecast allocated from Perth TK769 deferred project to this project to continue progress; 6/7/2022: Engineering and design behind schedule. 5/5/2022 EC- Forecasts entered. Work ahead of schedule. 4/7/2022 Mar variance: engineering and materials delays EC- Forecasts entered. 3/7/2022 Reclass submitted for 7,830 (Foam Tech) from BNTNV00M2106, to be applied to this AFE. 3/1/2022= Feb variance: Needed to install new test headers for Forbes Avenue site before scope could be completed. 2/7/22 EC: Forecasts updated. 1/10/2022 EC- Forecasts entered. | 2023-05-08 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNF - New Haven Forbes Termina |  | 20595 | 309546 | 61802 |  | 137353 |  | Jakubowski, Gregory | DeSocio, David |  |  | 1 | 40886 |  | DeSocio, David | Independent | Aqua | 2021-08-02 | Other Programs
New Haven Waterfront Dredging | Item | Open | MCAP | BNTNV00M2202 | Project Framework | 1954938 | Denblanken, Stefan | Maintenance Support | 3. Active | Defined | Marine | 426984 |  |  | 426984.18 | 420137 | 6847 | Yellow | 800000 |  | 800000 | -373016 |  |  | 81000 | 175000 |  | 614000 | Full | 614000 | 521499 |  | 521499 | No | Green | 2022-03-01 | 2022-03-03 | 2022-03-03 | 2022-10-30 | 2023-10-31 |  |  | 369044.13 | 17604.49 | 33488.59 | 6846.97 |  |  | 6847 | Red | [11 empty] | 2.9.23 SDB: Need to issue additional PO or CO to TCC to cover additional services provided outside current PO's. 1.24.23 SDB: USACE permit received on 01/19. Leveling work was started on 01/22 and substantially completed on 01/24 removing most high spots as the dock needed to be placed back in operation. 1.3.23 SDB: USACE permit has not yet been received for dredging/leveling. Tier III lab reports were received but need to be reviewed by USACE. 1.3.23 TN - Dredging/Leveling Work incomplete due to USACE Permits not being received 12.2.22 TN - Triton work is delayed, forecast shifted 11.25.22 SDB: ACOE permit has not yet been received for drag beam. TCC has obtained quotes for contractors to be evaluated. 11.9.22 TN - Leveling/Dredging Work was forecasted for end of the year 10.31.22 TN - Triton only did sample corings and lab test, some work pushed to next month 10.31.22 SDB: Received permit for drag beam from CT DEEP. ACOE has asked for additional information which is being prepared by TCC. 10.17.22 SDB: Contractor submitted and we approved the drag beam RFP package. 10.5.22 SDB: Contractor putting together an RFP package to level the area using a drag beam. 9.27.22 SDB: Obtained sediment coring. Continue with processing the cores. 9.7.22: MKS 2023 forecast adjusted to 800K. 9.2.22 SDB: TCC received PO for Tier III testing. 8.25.22 SDB: Proposal accepted and a Full AFE to cover these costs is being approved. A new PO for these additional services will be issued to TCC. 8.15.22 SDB: TCC to provide us with a proposal for the elutriate and biological testing required. 8.1.22 SDB: TCC received suitability determination from the ACOE. TCC reviewed the reply in order to determine path forward as a Full Tier III will be the most likely at the moment. 7.8.22 SDB: Triton Coastal is waiting on the reply by the ACOE for the suitability determination presently under review. Waiting on a reply on the COP/ACOE process for the drag beam as the Fall dredge season starts on Oct 1st. 6.9.22.DLC: Added funds from Pennsauken project which is placed on-hold 6.6.22 KDB: Project Estimate $797k; $716k has yet to be forecasted. 5.31.22 SDB: TCC presently waiting for the reply regarding the suitability determination from the ACOE. Once received we can then submit theapplication to the CT DEEP / ACOE. 5.2.22 SDB: TCC continues working on submittal documentation and looking at alternate dredging and disposal scenarios. 3.3.22 SDB: Data was submitted to ACOE/ CT DEEP on first week of March. Waiting for ACOE Suitability Determination in 3-6 months. 3.7.22 SDB: Soil samples received. Discussing path forward with TCC and Options. 3.1.22 SDB: Requested Phase 1 AFEand is routed for Approval. 2.18.22.DLC: Getting sample results in Feband wall inspected to finalize scope. | 2023-02-10 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  | 420137 | 6847 |  |  | 94515 |  | Spari, Markella | Spari, Markella |  |  | 1 | 41970 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Marine
Perth Amboy Rail Spur Lighting Upgrades | Item | Open | MCAP | BPTPC00M2215 | Maintenance Framework | 2012083 | Clark, Dave | Maintenance Support | 3. Active | Emergent | East | 358 |  |  | 358.36 | 267 | 92 | Red |  |  |  | 358 |  |  | 19000 |  |  | 19000 | Full | 19000 | 19290 |  | 19290 | No | Green | 2022-09-01 | 2022-11-18 | 2022-11-18 | 2022-12-31 | 2022-12-31 |  |  | 87.33 | 88.9 | 90.5 | 91.63 |  |  | 92 | Red | [11 empty] | 9.1.22.DLC: Initial Entry | 2022-09-28 | Ruiz, Felix |  | East | Pipelines and Terminals | Operating Infrastructure |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 267 | 92 |  |  | 18931 |  | Orischak, Bob | Clark, David |  |  | 1 | 44114 |  | Clark, David | Independent | Aqua | 2022-07-12 | Other Programs
Perth Amboy Tank 16 Internal Liner | Item | Open | MCAP | BPTPC00M2214 | Maintenance Framework | 2012085 | Clark, Dave | Maintenance Support | 3. Active | Emergent | Tanks | 883 |  |  | 883 | 657 | 226 | Red |  |  |  | 883 |  |  | 47000 |  |  | 47000 | Full | 47000 | 47529 |  | 47529 | No | Green | 2022-09-01 | 2022-11-21 | 2022-11-21 | 2022-12-31 | 2022-12-31 |  |  | 215.17 | 219.06 | 222.99 | 225.78 |  |  | 226 | Red | [11 empty] | 9.1.22.DLC: Initial Entry | 2022-09-28 | Ruiz, Felix |  | East | Pipelines and Terminals | Integrity |  | Perth Amboy | BPTPC - BPT PERTH AMBOY |  | 657 | 226 |  |  | 46646 |  | Stine, Carlton | Crone, Jeff |  |  | 1 | 44113 |  | Clark, David | Independent | Aqua | 2022-07-12 | Int - Tanks
Port Wilmington Fire Alarm System Replacements | Item | Open | MCAP | BNTUE00M2211 | Maintenance Framework | 2004058 | Weirsky, Edward | Maintenance Support | 6. Operational | Defined | Fire Protection | -3345 |  |  | -3345.13 | -3345 | 0 | Green |  |  |  | -3345 |  |  | 80000 |  |  | 80000 | Full | 80000 | 70311 |  | 70311 | No | Green | 2022-10-01 | 2022-07-26 | 2022-07-26 | 2022-12-31 | 2022-12-31 |  |  | -3308.13 | -37 | [17 empty] | 3/2/23 TN - Final invoice came through, project will be closed. 10/28/22 - Forecast Pushed. Oliver Fire will charge when on site. 6/2/22 obtained quotes and working on afe submittal. ek5507 4/26/22 Had an additional two contractors come down to provide quotes. Waiting for them to send them over. ek5507 4/5/2022 -Working with Supply Chain for bidding out quotes. 3/3/2022 - Getting quotes. 2/3/22 Plan on scoping in Feb.ek5507 | 2023-03-02 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | Port Wilmington | BNTUE - WIlmington(DE) Terminal |  | -3345 | 0 |  |  | 73656 |  | Jakubowski, Gregory | Jakubowski, Greg |  |  | 1 | 41385 |  | Guest, ProSight | Independent | Aqua | 2021-08-11 | Other Programs
Project Ocean Arc Flash Studies | Item | Open | MEXP | 1790000E2201 | Exempt | 1989627 | Logan, Sam | Maintenance Support | 6. Operational | Drawdown | Arc Flash | -8121 |  |  | -8121.25 | 2479 | -10600 | Red |  |  |  | -8121 |  |  | 391000 |  |  | 391000 | Full | 391000 | 368956 |  | 368956 | No | Green | 2022-07-01 | 2022-06-05 | 2022-06-05 | 2022-12-31 | 2023-02-28 |  |  | 0 | 2478.75 | 0 | -10600 |  |  | -10600 | Red | [11 empty] | 3/2/23 SL - Project complete; 2/17/23 SL - Work to complete by end of Feb 1.4.23 TN - Per Sam, contractor delay, project will complete in January 2023 12.2.22 TN - Work ahead of schedule 10.28.22 TN - NC work was pushed to November 9.16.22 TN - Missed accruals for work from contractors. Will be captured in September. 6/28 contractors provided scope of work and will return bids within 5 business days | 2023-03-02 | Nguyen, Tong |  | Corporate | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  | 2479 | -10600 |  |  | 377077 |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 43702 |  | Clark, David | Independent | Aqua | 2022-05-10 | Other Programs
Richmond North - (BSEVA) New Security Cameras & NVR | Item | Open | MCAP | BSEVA00M2201 | Maintenance Framework | 1991132 | Logan, Sam | Maintenance Support | 6. Operational | Defined | Security & Cameras | 16536 |  |  | 16535.51 | 16536 | 0 | Green |  |  |  | 16536 |  |  | 38000 | 37000 |  | 75000 | Full | 75000 | 68812 |  | 68812 | No | Green | 2022-09-01 | 2022-06-18 | 2022-06-18 | 2022-12-31 | 2023-01-31 |  |  | 15823.45 | 712.06 | [17 empty] | 2/17/23 SL - Project complete 1.4.23 TN - Contractor delay 12.2.22 TN - Contactor delay 10.28.22 TN - Convergint charged half, dominion is doing the install in November 6.30.22.DLC: Inputted initial forecast | 2023-03-02 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | Virginia | BSEVA - RICHMOND TERMINAL |  | 16536 | 0 |  |  | 52277 |  | Clark, Chris | Clark, Chris B |  |  | 1 | 43964 |  | Clark, David | Independent | Aqua | 2022-06-10 | Other Programs
Richmond Terminal Fire Protection Upgrades | Item | Candidate | MEXP |  | Maintenance Framework |  | Weirsky, Edward | Maintenance Support | 1. Proposed | Defined | Fire Protection |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 | [9 empty] | 40000 | 40000 | No | Green | 2023-06-01 |  |  |  | 2023-07-31 | [13 empty] | 20000 | 20000 | [6 empty] | 7/22/21 - Gregory Petry will work on this with myself, funding to be used for urgent fire system needs at Fairfax and this project will be deferred to 2022 - GJ 6/1/21 - I reached out to Matt Logan to see if he had a PM to take this on. Will most likely go to Gregory Petry.BSK 1/24/22 Assigned to contract fire PM Ed Weirsky to oversee getting engineering study done in 2023 GJ | 2023-01-24 | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | Virginia | BETRH - BET RICHMOND |  |  | 20000 | 20000 |  |  |  | Jakubowski, Gregory |  |  |  | 1 | 37790 |  | Guest, ProSight | Independent | Aqua | 2020-08-12 | Other Programs
Roanoke API 570 INSP 2022 | Item | Open | MEXP | BSEVR00E2201 | Maintenance Framework | 2003565 | Logan, Sam | Maintenance Support | 7. Closed | Drawdown | Facility Integrity | 0 |  |  | 0 | 0 | 0 | Green |  |  |  | 0 |  |  | 16000 |  |  | 16000 | Full | 16000 | 13745 |  | 13745 | No | Green | 2022-10-01 | 2022-07-21 | 2022-07-21 | 2022-12-31 | 2022-12-31 |  |  | 0 | [18 empty] | 2/17/23 SL - Project complete | 2023-03-02 | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | Virginia |  |  | 0 | 0 |  |  | 13745 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 44151 |  | Meitzler, Antoinette | Independent | Aqua | 2022-07-14 | Int - Planned Corr & FI
Roanoke I - (BSEVR) New Security Cameras & NVR | Item | Open | MCAP | BSEVR00M2201 | Maintenance Framework | 1991133 | Logan, Sam | Maintenance Support | 6. Operational | Defined | Security & Cameras | 5673 |  |  | 5673.38 | 5673 | 0 | Green | 33200 |  | 33200 | -27527 |  |  | 36000 | 37000 |  | 73000 | Full | 73000 | 60437 |  | 60437 | No | Green | 2022-09-01 | 2022-06-18 | 2022-06-18 | 2022-12-31 | 2023-02-28 |  |  | 572.89 | 4880.85 | 219.64 | [16 empty] | 2/17/23 SL - Project complete 12.2.22 - Work ahead of schedule, vendor was available 6.30.22.DLC: Inputted initial forecast | 2023-03-02 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | Virginia | BSEVR - ROANOKE TERMINAL |  | 5673 | 0 |  |  | 54764 |  | Clark, Chris | Clark, Chris B |  |  | 1 | 43965 |  | Clark, David | Independent | Aqua | 2022-06-10 | Other Programs
Rochester North Terminal - Replace Loading Rack Fire System | Item | Open | MCAP | BETRC00M2201 | Maintenance Framework | 2013340 | Weirsky, Edward | Maintenance Support | 3. Active | Defined | Fire Protection | 14180 | 123318 |  | 137497.96 | 103578 | 33920 | Red | 280000 |  | 280000 | -142502 |  |  | 58000 | 252000 |  | 310000 | Full | 310000 | 166635 | 123318 | 289953 | No | Green | 2022-09-01 | 2022-08-25 | 2022-08-25 | 2023-05-31 | 2023-06-30 |  |  | 11640.12 | 1093.07 | 718.39 | 728.38 |  |  | 728 | Red |  |  | 15000 | 28193 | 45847 | 34278 | [5 empty] | 4/4/23 - TN/Per Ed, forecast pushed due to one-time waiver request 2/2/23 - TN - Contractor delayed work due to permit issues 12/15/22 - TN - Contractor delayed work due to permit issues 12/1/22 - TN - Error in forecast for November. November was supposed to be 68k and not 108k. This has been fixed for future forecasting. 11/21/22 - TN - Contractor submitted permits to begin work in December, forecast pushed 8/12/22 GJ - Bid event held, only 1 bid received at $475k from Vanguard. Regrouping but may not be able to be executed this year due to budget 7/12/22 GJ - Added 5k to Nov budget allocated from Perth Amboy TK769 deferred project; 5/5/2022 EC- Forecasts entered. 4/7/2022 EC- No change to forecasts. 3/2/22 EC: Schedule accelerated. Forecast start July. 2/7/22 EC: Forecasted for September. | 2023-04-04 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BETRC - BET ROCHESTER N TERMINAL AGWAY |  | 13452 | 43921 | 80125 |  | 152455 |  | Jakubowski, Gregory | Jakubowski, Greg |  |  | 1 | 41807 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Rochester South Video System Replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Logan, Sam | Maintenance Support | 1. Proposed |  | Security & Cameras |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 | [9 empty] | 50000 | 50000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 50000 | [6 empty] | 5/2/23 SL - Quotes in, trying to source additional funding; 4/4/23 SL - waiting for lower bids after initial were high, 3/2/23 SL - Bids due March 20; 2/16/23 SL - Scheduling bid call in March | 2023-05-02 | Nguyen, Tong |  | East | Pipelines and Terminals | Operating Infrastructure |  | Auburn Terminals | BETRQ - BET ROCHESTER S TERMINAL XOM |  |  | 0 | 50000 |  |  |  | Clark, Chris |  |  |  | 1 | 34142 |  | Guest, ProSight | Independent | Aqua | 2019-08-20 | Other Programs
Selma - (BSEVS) New Security Cameras & NVR | Item | Open | MCAP | BSEVS00M2201 | Maintenance Framework | 1991134 | Logan, Sam | Maintenance Support | 6. Operational | Defined | Security & Cameras | 30249 |  |  | 30249.18 | 32139 | -1890 | Yellow | 30000 |  | 30000 | 249 |  |  | 40000 | 37000 |  | 77000 | Full | 77000 | 67181 |  | 67181 | No | Green | 2022-09-01 | 2022-06-18 | 2022-06-18 | 2022-12-31 | 2023-02-28 |  |  | 473.01 | 29987.21 | 1678.96 | -1890 |  |  | -1890 | Red | [11 empty] | 3/2/23 SL - Project complete; 2.2.23 TN - Delay due limited working hours 6.30.22.DLC: Inputted initial forecast | 2023-03-02 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | North Carolina | BSEVS - SELMA TERMINAL |  | 32139 | -1890 |  |  | 36932 |  | Clark, Chris | Clark, Chris B |  |  | 1 | 43966 |  | Clark, David | Independent | Aqua | 2022-06-10 | Other Programs
Selma API 570 INSP 2022 | Item | Open | MEXP | BSEVS00E2201 | Maintenance Framework | 2003584 | Logan, Sam | Maintenance Support | 7. Closed | Drawdown | Facility Integrity | -2800 |  |  | -2800 | -2800 | 0 | Green |  |  |  | -2800 |  |  | 23000 |  |  | 23000 | Full | 23000 | 19535 |  | 19535 | No | Green | 2022-11-01 | 2022-07-21 | 2022-07-21 | 2022-12-31 | 2022-12-31 |  |  | -2800 | [18 empty] | 4/5/23 SL - Project complete, 2/16/23 SL - Project complete; 10/28/22 - Vendor Project delay | 2023-04-05 | Nguyen, Tong |  | South | Pipelines and Terminals | Station/Terminal |  | Southeast Terminals |  |  | -2800 | 0 |  |  | 22335 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 44137 |  | Meitzler, Antoinette | Independent | Aqua | 2022-07-14 | Int - Planned Corr & FI
South Texas Arc Flash Updates | Item | Open | MEXP | BTXHF00E2207 | Maintenance Framework | 1972391 | Brazzil, Cade | Maintenance Support | 6. Operational | Drawdown | Arc Flash | 10287 |  |  | 10287.29 | 57108 | -46821 | Red |  |  |  | 10287 |  |  | 120000 |  |  | 120000 | Full | 120000 | 160976 |  | 160976 | No | Green | 2022-06-01 | 2022-04-16 | 2022-04-16 | 2022-04-18 | 2022-12-31 |  |  | 0 | 10287.29 | 46820.65 | -46820.65 |  |  | -46821 | Red | [11 empty] | 1.3.2023 - Per Cade, arc flash studies completed. Project is completed. New AFE for Arc Flash Mitigation will be created. 7/6/22 Formulating a new mitigation plan to reduce original project cost and form installation plan with operations- Cade 4.25.22.DLC: Initial Forecast | 2023-01-03 | Nguyen, Tong |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 57108 | -46821 |  |  | 150688 |  | Ashley, Robert | Ashley, Robert | N/A |  | 1 | 43411 |  | Clark, David | JDE Child | Burnt Orange | 2022-04-16 | Other Programs
St Louis South - Mooring Dolphin 1 and 2 replacement and cell repairs | Item | Open | MCAP | BETSS00M2101 | Maintenance Framework | 1900731 | White, Stephen | Maintenance Support | 3. Active | Defined | Marine | 106647 | 977000 |  | 1083646.99 | 1092610 | -8963 | Yellow | 700000 |  | 700000 | 383647 |  |  | 78000 |  |  | 78000 | Phase | 78000 | 363779 | 977000 | 1340779 | No | Green | 2021-11-01 | 2021-10-04 | 2021-10-04 | 2021-12-31 | 2023-12-31 |  |  | 7261.44 | 36033.6 | 49314.88 | 14037.07 | 20000 | 20000 | -5963 | Red |  |  | 20000 | 20000 | 3000 | 3000 | 3000 | 350000 | 350000 | 228000 |  | May 1. 2023 SGW/TN - Per SGW. Forecast shifted to Q4 after meeting with Markella. Mar. 21, 2023 SGW - emailed Collins with a list of questions/comments regarding their draft report. They will follow-up with a revised report in about 2 weeks. Mar. 17, 2023 SGW - Draft report of findings and recommendations received from Collins. Feb. 24, 2023 SGW - Collins Engineers worked a full day at site, completing their inspection activities. Feb. 20, 2023 SGW - Collins Engineers arrived into St Louis to commence their inspection activities tomorrow AM. (Note: today is a public holiday for Buckeye). 2/8/23 SGW - Collins Engineers has submitted an updated proposal for inspection of the dock structures. They have also submitted a revised set of Safety Plans, draft JSAs, and engineering calculations associated with their proposed rigging tie-off points. Documents have been circulated to Operations and H&S for review. 1/27/23 SGW - Met with Matt Rogers (Collins Engineers) on site this AM, as Collins has not previously been to the terminal. They will revise their proposal based upon today's site visit. 1/19/23 SGW - Bids have been received for a detailed inspection of the dock structures. Two companies have proposed utilizing ropes to conduct above-water inspection tasks. Concept is under review. 12/14/22 SGW - RFP for Engineering Inspection Services was issued by Supply Chain to 4 companies. Bid Due Date is Dec. 27 end-of-day. 11/30/22 SGW - PowerPoint presentation to Mike Ricke et al reviewed previous technical work performed in 2016 and 2021. PM recommendation is to conduct a more detailed ASCE Inspection of the waterfront structures. This more detailed information is necessary prior to making recommendations as to the 3 Cells and 3 Mooring Dolphins. Replacement of 2 ea. Staircases is still proposed; order of magnitude pricing was discussed. 11/02/2022 DNM- Project scope being revised from stairway repair to replacement. Project Managerbeing changed to Stephen White for overall project going forward. Project funds for November and December being reduced to meet new project plan. Unspent October funds along with November/December projection being shifted to BETQT00M2202 which is advancing 2023 spend into Q4 2022. 10/10/2022 DNM-Mobilizing Barr-None, Budrovich and U/T inspection service for an October 17th start on hydroblasting, inspection and recoating of the Main Dock Cells. Anticipated spend based on MSA agreements. 8/8/22 DNM- 2023 Forecasted updated for structural fabrication of replacement dolphins from January-August 2023. Installation bid in late Q2 2023 with installation of new mooring dolphins and demolition of old dolphin starting September through October 2023. 8/2/22 DNM- Geotechnical Investigation completed and under review. Planning Phase I Field Work for execution. 06/02/22 DNM- Site meeting on May 25th developed value engineering concepts for Phase I repairs. Geotechnical investigation moved to July based on Operational requirements. Forecast shifted accordingly. 04/04/2022 DNM- Establishing ISNetworld Marine Contractors in the St Louis Area for project bidding of Phase 2 work in 2023. Budget forecasting adjusted for Phase 1 Immediate Repair Execution in later part of Q2 based on predicted river conditions. 02/03/22 DNM- Phase II reviewed with Kinder Morgan who is partially responsible for repair cost based on lease contract. Permit plan to be executed in Q1. 01/11/22 DNM- Phase II AFE to be routed in February 01/03/22 DNM- Triage review of repair options in January for presentation to Commercial for discussions with KM regarding repair cost funding. 12/2/21 DNM- Design review for repair plan underway. Permitting to begin in December 10/25/2021 DNM- Design plan underway as Phase 1 work. Phase 2 will be field installation work as part of2022 Marine MCAP program. | 2023-05-01 | Nguyen, Tong |  | West | Pipelines and Terminals | Operating Infrastructure |  | St. Louis | BETSS - BET ST LOUIS SOUTH TERMINAL |  | 92610 | 54037 | 9000 | 928000 | 200242 |  | Spari, Markella | Decker, Paul |  |  | 1 | 41940 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Marine
St. Charles - (BSEVO) New Security Cameras & NVR | Item | Open | MCAP | BSEVO00M2202 | Maintenance Framework | 1991135 | Logan, Sam | Maintenance Support | 3. Active | Defined | Security & Cameras | -2661 | 34557 |  | 31895.51 | 30448 | 1448 | Yellow | 33200 |  | 33200 | -1304 |  |  | 33000 | 36000 |  | 69000 | Full | 69000 | 18092 | 34557 | 52649 | No | Green | 2022-09-01 | 2022-06-18 | 2022-06-18 | 2022-12-31 | 2023-05-31 |  |  | 237.44 | -4410.15 | 63.38 | 1447.84 |  |  | 1448 | Red |  |  |  | 34557 | [7 empty] | 5/2/23 SL - work to complete in June, 3/2/23 TN/SL - Contractor changed the order of the terminals they are working on 2/17/23 SL - Work scheduled for May; 6.30.22.DLC: Inputted initial forecast | 2023-05-02 | Nguyen, Tong |  | West | Pipelines and Terminals | Operating Infrastructure |  | St. Louis | BSEVO - ST CHARLES TERMINAL |  | -4109 | 36005 |  |  | 20753 |  | Clark, Chris | Clark, Chris B |  |  | 1 | 43967 |  | Clark, David | Independent | Aqua | 2022-06-10 | Other Programs
STXXI - Electrical Clean up | Item | Open | MEXP | STXXI00E2202 | Maintenance Framework | 1989697 | Brazzil, Cade | Maintenance Support | 3. Active | Drawdown | South | 27095 | 276400 |  | 303495.47 | 300893 | 2602 | Yellow | 200000 |  | 200000 | 103495 |  |  | 100000 |  |  | 100000 | Phase | 100000 | 61387 | 276400 | 337787 | No | Green | 2022-07-01 | 2022-06-07 | 2022-06-07 | 2022-09-30 | 2023-08-31 |  |  |  | 6000 | 3800 | 17295.47 | 14693 | 14693 | 2602 | Red |  |  | 3800 | 58800 | 103800 | 110000 | [5 empty] | 4.3.23 CB - Utility Services is onsite today for sub 400. 3/14/23 Rust mitgation 1/19/23 Team approved to proceed with rust mitigation on switchgear only. 1/15/23 MV SWGR 6000 faulted, resulting site wide outage. See report for findings 11.1.22 - TN - Warranty on all items, Waiting on contractor to respond to that request 9.19.22 TN - Waiting for final contractor approval. Forecast was pushed out. 8.8.22.DLC: Moved funds from Marrero arc flash study which was overforecasted | 2023-04-03 | Nguyen, Tong |  | South | Pipelines and Terminals | South Texas Gateway |  | Corpus Christi | STXXI - Ingleside |  | 9800 | 79895 | 213800 |  | 34291 |  | Johnson, AJ | Asiedu, Saka |  |  | 1 | 43866 |  | Guest, ProSight | Independent | Aqua | 2022-05-31 | Other Programs
Utica Terminal - Replace 2 Fire Hydrants at Loading Rack | Item | Candidate | MEXP |  | Maintenance Framework |  | Weirsky, Edward | Maintenance Support | 1. Proposed |  | Fire Protection |  | 25000 |  | 25000 | 25000 | 0 | Green | 25000 |  | 25000 | 0 | [9 empty] | 25000 | 25000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 25000 | [8 empty] | Nguyen, Tong |  | East | Pipelines and Terminals | Station/Terminal |  | Auburn Terminals | BETCA - BET UTICA TERMINAL |  |  | 0 | 25000 |  |  |  | Jakubowski, Gregory |  |  |  | 1 | 44163 |  | Guest, ProSight | Independent | Aqua | 2022-07-18 | Other Programs
Yabucoa - Dock Fender 3 Lower section & fender 2 upper section | Item | Open | MCAP | BCTYA00M2211 | Maintenance Framework | 1947048 | White, Stephen | Maintenance Support | 6. Operational | Defined | Marine | -96096 | 63700 |  | -32396 | -32396 | 0 | Green |  |  |  | -32396 |  |  | 684000 |  |  | 684000 | Full | 684000 | 629580 | 63700 | 693280 | No | Green | 2022-02-01 | 2022-02-16 | 2022-02-16 | 2022-12-31 | 2022-12-29 |  |  | -96096 | [9 empty] | 63700 | [8 empty] | 05/02/2023 - Forecast for Fenders for May was confirmed to be concrete by Carmelo S. 04/05/2023 - Fenders were not installed in March as anticipated due to contractor delivery issues. Installation now scheduled for May and forecast adjusted to reflect same. 03/02/2023 - Due to Commercial Divers experiencing issues with the delivery of the 7 compression rubber fenders, Februarys forecast was not met and pushed to March per PM. Material is expected to be received at San Juan week of March 3rd, with installation to follow. 01.31.23 SDB: Rubber fenders on dolphin #1 will be installed once they are received. Delay in the import of the fender elements. 12.22.22 SDB: Contractor completed work on the fender #2 work and dock was returned to service today at 16:00 hrs. Rubber compression members will be installed next year as they are imported and did not arrive on time. 12.01.22 SDB: Prefabrication of the fender elements was completed. Presently waiting for the jobsite work window in order to start the work. There is a possibility to start on 12/13 but is depending on vessel traffic. 11.25.22 SDB: Contractor to complete prefabrication by 12/12. Work window is scheduled to start on 12/19. 10.31.22 TN - Material delay, installation will be done in December 2022 10.18.22 SDB: Contractor Commercial Divers continues prefabrication of fender panel components. 10.05.22 SDB: SHELL requested that we delay the work window due to low ULSD inventory in the island after the hurricane. Commercial department agreed and work window is being rescheduled for December 2022. 9.20.22 SDB: Hurricane Fiona struck Puerto Rico on 09/18/22. Impact on the project is being evaluated. 9.16.22 SDB: Contractor continues with the prefabrication of the structural elements at their yard. 9.7.22 MKS No 2023 carryover. 9.2.22 SDB: Contractor continues with prefabrication of structural elements for repair. 8.15.22 SDB: Contractor continues with prefabrication of structural fender elements. Work window at the dock scheduled for 11/02/22. 8.1.22 SDB: Contractor working on the prefabrication of the upper section of fender panel #2. 7.8.22 SDB: Lower section of fender #3 has been replaced completing this on 07/07 well within the 10 day work window permitted. Contractor is starting to prefabricate structural components for the replacement of the upper section of fender #2 scheduled for November 2022. 6.20.22 SDB: First work window for the repair of the fender system has been rescheduled to start on 07/03/2022.6.6.22 SDB: Contractor received PO for 7 fender rubber elements which are part of SOW for the project. 5.31.22 SDB: Contractorcompleted prefabrication of fender elements for both dolphins. Ready to complete the work using the two work windows to be provided by the company, firstone starting in late June, the second in early November. 5.27.22 KB: Revised EAC to original budget per C. Silva 5.2.22 SDB: Contractor continues fabrication of fender panels at his workshop. Fender panels, jackets and wood fenders for #3 are complete. 3.31.22 SDB: Contractor is fabricating jackets and subassembly sections of the #2 & #3 fender systems in preparation to their June and November scheduled work windows. 2.18.22.DLC: 2 mobs required.spread out costs accordingly 3.1.22 SDB: AFE has been submitted. PO to Contractor is in process. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | -96096 | 63700 |  |  | 725676 |  | Spari, Markella | Davalos, Glenda |  |  | 1 | 41092 |  | Guest, ProSight | Independent | Aqua | 2021-08-06 | Marine
Yabucoa - Dredging Permiting and Planning | Item | Open | MEXP | BCTYA00E2211 | Maintenance Framework | 1992087 | White, Stephen | Maintenance Support | 3. Active | Defined | Marine | -60728 |  |  | -60727.85 | -60728 | 0 | Green |  |  |  | -60728 |  |  | 250000 | 192000 |  | 442000 | Full | 442000 | 0 |  | 0 | No | Green | 2022-08-01 | 2022-06-29 | 2022-06-29 | 2024-05-30 | 2022-12-31 |  |  | -18278.4 | -42449.45 | [17 empty] | 03/2/2023 - $180K was zeroed and added to BCTYA00M2219 per Dave Clark. A reclass totalling $50,435.05 was posted in February to move the remaining actuals on BCTYA00E2211 to BCTYA00M2219. The forecast for BCTYA00E2211 will need to be zeroed and incorporated in BCTYA00M2219 to reflect the MEXP to MCAP flip. 01.05.23 SDB: Benthic dive inspections 90% complete. MCJ initiating contacts with agencies. 12.13.22 SDB: Revised schedule was transmitted to project stakeholders. 12.01.22 SDB: Upper management made the decision to continue with permitting using 43'+2'. MCJ was notified of the decision and continue working on the permitting documentation. A revised schedule is being prepared. 11.25.22 SDB: Presented dredging costs for 5 options to upper management for their review. Waiting for their decision in order to continue with permitting effort. 10.31.22 TN - Project will push into 2023, McFarland is working on another presentation for upper management.10.18.22 SDB: McFarland Johnson is putting together a second presentation for upper management which will include dredging scenarios, costs and silting rates to help the Company make the decision on the dredging scope for the project. 10.7.22 SDB: AFE for second phase was submitted and approved. Second PO was issued to McFarland-Johnson for second phase.9.20.22 SDB: Meeting held on 09/13 and 09/16 to discuss changes in the SOW for the first PO to MJ and funding for the second phase proposal.9.9.22: MKS Updated 2022 forecast to 240K.9.5.22 SDB: Held meeting with Commercial and Operations. MJ to present various dredging scenarios by 9/9/22. MJ to send proposal for Phase II work on 09/09/22.8.15.22 SDB: MJ is registered and has received the PO for the first part of the permitting process. 8.1.22 SDB. MJ has not yet been granted registration by the Company. 7.15.22 SDB: PO to MJ is delayed as the company is being registered as a Buckeye services provider.7.8.22 SDB: Revised proposal for the first part of the permitting process from McFarland Johnson was received and a PO is being issued to them. Stakeholder meeting to be held on 07/12.6.6.10 SDB: Revised proposal was received from MJ. Report was distributed among Buckeye stakeholders and a meeting was held to discuss. Additional questions were generated which are in the process of being responded.5.31.22 SDB: Received revised proposal from McFarland Johnson. Reviewedbut additional SOW needs to be included. They will resubmit by 06/02.5.2.22 SDB: Received proposal from Environmental engineering firm and quote for legal services. Presently under review prior to submitting an AFE and issuing a PO.3.31.22 SDB: Awaiting proposals from the environmental engineers and lawyers to be utilized in securing the required dredging permits for the 2022 maintenance dredging efforts.3.1.22 SDB: Discussing path forward to obtaindredging and disposal permits. | 2023-03-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | -60728 | 0 |  |  | 60728 |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 41953 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Marine
YABUCOA - Main Berth Concrete Deck Repairs MEXP | Item | Open | MEXP | BCTYA00E2210 | Maintenance Framework | 1991271 | Clark, Dave | Maintenance Support | 6. Operational | Defined | Marine | 41388 |  |  | 41388 | 42000 | -612 | Yellow |  |  |  | 41388 |  |  | 72000 |  |  | 72000 | Full | 72000 | 74888 |  | 74888 | No | Green | 2022-07-01 | 2022-06-21 | 2022-06-21 | 2022-09-13 | 2023-01-31 |  |  |  | 19500 | 3500 | 18388 | 10000 | 10000 | 8388 | Red | [11 empty] | 05/02/2023 - Final invoice accrued for April 2023. Project was completed. Main Dock coating for breasting dolphin. May forecast zeroed. Once invoice posted, project can be closed. 04/04/2023 - Initial contractor was not responding in timely manner and so new contractor has been engaged to complete project (H.C Coating.) Forecast adjusted to reflect their expected progress. 03/03/2023 Notes indicate the $19,500 forecast is the balance for Aqua Vac Services Inc PO C1-23113 balance expected in February. February works completed per Carmelo and remaining woks forecatsed for April. 1.31.23 SDB: Deck substantially completed with topcoat. Contractor to procure additional material to finish. remaining 25% of topcoat to be completed once material arrives. 1.23.23 SDB: Deck is substantially finished. Epoxy top coat will be placed on 01/26 when the ship departs from the dock. 1.3.23 TN - Forecast pushed due to contractor delay 12.2.22 TN: Forecast pushed due to previous note 11.25.22 SDB: Contractor started the work but was stopped due to weather. Ops/Scheduling will provide them with another work window. 10.31.22 TN - Weather delay for contractor 10.18.22 SDB: Contractor AquaVac moved all the materials and equipment and stored it at the terminal. Working with scheduling to obtain a long enough work window to be able to complete the work. 10.5.22 SDB: Terminal scheduling presented available windows for the dock to the contractor in order to schedule the work. 9.30.22 TN - Delayed due to Hurricane 9.29.22 SDB: Working with terminal schedulers to provide contractor with a work window. 9.20.22 SDB: Hurricane Fiona struck Puerto Rico on 09/18/22. Impact on the project is being evaluated. 9.7.22 SDB: Terminal scheduling to provide contractor a work window in order to complete their work. 9.7.22 MKS No 2023 carryover. 8.1.22 SDB Waiting on delivery of materials by 08/22 in order to provide the contractor with a work window at the dock. 7.26.22 SDB: Material expected to be available on the island on 08/22. 7.8.22 SDB: PO was issued to the contractor Aqua Vac for this work. Contractor is presently purchasing and importing the required materials to the island. Once received, we will schedule the work around the operational needs of the terminal. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  | 23000 | 18388 |  |  | 33500 |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 43994 |  | Meitzler, Antoinette | Independent | Aqua | 2022-06-15 | Marine
Yabucoa - Main Dock - Structural Upgrade 2023 | Item | Candidate | MCAP |  | Project Framework |  | White, Stephen | Maintenance Support | 1. Proposed |  | Marine | 0 | 375000 |  | 375000 | 375000 | 0 | Green | 375000 |  | 375000 | 0 | [8 empty] | 0 | 375000 | 375000 | No | Green | 2023-06-01 |  |  |  | 2023-10-16 | [5 empty] | 0 |  |  | 0 | Green |  |  |  | 30000 | 125000 | 140000 | 60000 | 20000 |  |  |  | 05/02/2023 - Meeting to be held first week of May. Following meeting forecast may be adjusted. 040/04/2023 - Forecast adjusted to Q2 spend. Inspection reports were just received. 03/02/2023 - Inspection Reports remain pending as they have not been received to date. Markella working on reports to be received. Forecast was adjusted per PM based on updates. 1.4.23 SDB: MSI completed inspection of the terminal structures. Will send the inspection report of their finding EOM January 2023. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Operating Infrastructure |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 30000 | 325000 | 20000 |  |  | Spari, Markella |  |  |  | 1 | 44506 |  | Guest, ProSight | Independent | Aqua | 2022-08-10 | Marine
YABUCOA - Small Dock and Catwalk #4 Repairs | Item | Open | MEXP | BCTYA00E2212 | Maintenance Framework | 2011153 | Clark, Dave | Maintenance Support | 7. Closed | Emergent | Marine | 28333 |  |  | 28332.67 | 28333 | 0 | Green |  |  |  | 28333 |  |  | 188000 |  | 200 | 188200 | Supplemental | 188200 | 206955 |  | 206955 | No | Green | 2022-08-01 | 2022-08-02 | 2022-08-02 | 2022-11-18 | 2023-01-31 |  |  | 32652.67 | -4320 | [17 empty] | 03/03/2023 - January accrual to Efficiency Construction Corp totaled $15K. Feburary actuals for Efficiency Corp total $10,680 resulting in February's $4,320 current variance. Confirmed by Carmelo that the project is ready to be closed. No additional billings are expected. 1.27.23 SDB: The contractor continues to be delayed as they are not permitted to do hot work while the ship is at berth, the new scheduled completion is week of 02/06. 1.9.23 SDB: Efficiency Contruction scheduled to complete catwalk #4 week of 01/23 depending on ship traffic. 1.3.23 TN - Efficiency Construction work was delayed. Forecast pushed 11.25.22 SDB: Efficiency Construction continues working on catwalk #4 when permitted between vessels. Scheduled to complete work in December. 11.01.22 SDB: Efficiency Construction continues working on catwalk #4. Work scheduled to be completed this year. 10.31.22 TN - Efficiency Construction material delay, weather delay, and ship schedule delay 10.31.22 SDB: Contractor Commercial Divers finished all work on the small dock. 10.17.22 SDB: Contractor CD completed work on West side BD of the small dock. Moved to the east side BD to work on pile jacket and fender system. 10.5.22 SDB: Contractor CD working on the small dock. Lost some days due to weather. Contractor Efficiency Construction (EC) working on repairs of walkway #4 between ships. 9.26.22 SDB: Contractor Commercial Divers (CD) mobilized to the small dock to start the work. 9.20.22 SDB: Hurricane Fiona struck Puerto Rico on 09/18/22. Impact on the project is being evaluated. 9/13/22 - Project kickoff earlier than expected. DC 9.7.22: No 2023 carryover. PM to update 2022 forecast. 8.15.22 SDB: Contractor Commercial Divers received PO's for the work at the small dock West side and jacket. Started prefabrication of structural elements. Efficiency Contractor received PO for catwalk #4, material being purchased and scaffolding to be started to be installed next week. 8.1.22 SDB: Awaiting approval of the AFE which is in the system. | 2023-03-03 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | St. Lucia | BSLQL - BUCKEYE ST. LUCIA LIMITED |  | 28333 | 0 |  |  | 178622 |  | Spari, Markella | Mirandi, Angela |  |  | 1 | 44200 |  | Guest, ProSight | Independent | Aqua | 2022-07-21 | Marine
Yabucoa Docks Catwalks Refurbishment 2023 | Item | Candidate | MEXP |  | Project Framework |  | White, Stephen | Maintenance Support | 1. Proposed |  | Marine | 0 | 250000 |  | 250000 | 250000 | 0 | Green | 250000 |  | 250000 | 0 | [8 empty] | 0 | 250000 | 250000 | No | Green | 2023-06-01 |  |  |  | 2023-12-31 | [5 empty] | 0 |  |  | 0 | Green |  |  |  | 25000 | 30000 | 25000 | 43750 | 43750 | 43750 | 38750 |  | 05/02/2023 - Scope defined for project. AFE will be drafted to submission. Current forecast holds. 03/02/2023 - Forecast adjusted per PM to account for actual timing of works to be completed. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 25000 | 98750 | 126250 |  |  | Spari, Markella |  |  |  | 1 | 44505 |  | Guest, ProSight | Independent | Aqua | 2022-08-10 | Marine
Yabucoa Dredging | Item | Candidate | MCAP |  | Project Framework |  | White, Stephen | Maintenance Support | 1. Proposed |  | Marine | 0 | 0 |  | 0 | 0 | 0 | Green | 960000 | -960000 | 0 | 0 | [8 empty] | 0 | 21960000 | 21960000 | No | Green | 2024-01-01 |  |  |  | 2023-12-31 | [5 empty] | 0 |  |  | 0 | Green |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 03/02/2023 - $600K forecast for 2023 zeroed and added to BCTYA00M2219 per Dave Clark. 1/19/23 SGW - monthly review with consultant and Buckeye mgmt team. Actual dredging is forecast for Q3 2024, dependent upon permits being acceptable. Draft Permit package is scheduled for filing with US Army Corps of Engineers on March 20, 2023. 1/11/2023 SGW - review project status with Stefan Denblanken. His MEXP project is covering the upfront costs of engineering with McFarland. This MCAP project will pick up the costs of sampling and lab testing starting in July 2023 thru year-end. Dredging is forecast to happen in mid-year 2024. | 2023-03-02 |  |  | East | Pipelines and Terminals | Operating Infrastructure |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 0 | 0 | 0 |  | 21960000 | Spari, Markella |  |  |  | 1 | 45805 |  | Clark, David | Independent | Aqua | 2022-09-10 | Marine
Yabucoa Main Dock Support Piles repairs and coating | Item | Candidate | MEXP |  | Maintenance Framework |  | White, Stephen | Maintenance Support | 1. Proposed | Defined | Marine | 0 | 120000 |  | 120000 | 120000 | 0 | Green | 120000 |  | 120000 | 0 | [8 empty] | 0 | 120000 | 120000 | No | Green | 2023-07-01 |  |  |  | 2023-09-15 | [5 empty] | 0 |  |  | 0 | Green |  |  |  |  | 40000 | 40000 | 40000 |  |  |  |  | 05/02/2023 - Meeting being held first week of May to discuss. Following meeting, forecast may be adjusted. 04/04/2023 - Inspection reports were just received. Forecast adjusted to account for timing of receiving the report. 03/02/2023 - Forecast of $40K moved from April to July as Inspection reports are still outstanding. 12.14.22 SDB: Marine Solutions will complete the inspection of the marine facility and structures on a work window starting on 12/15/22 and running for 10 days. Dock is closed for the replacment of fender at BD#2. 9.7.22: MKS This is likely to slip in 2023. Commercial divers are not available till November. 2022 is kept as 120K and funding will be reallocated within the portfolio. 120K is 2023 carryover. 7.8.22 SDB: Waiting for the structural inspection of the marine facility to be conducted later this year in order to determine condition, scope of work for items to be repaired and proposed repair methods. 5.31.22 SDB: Waiting for the completion of the structural inspection of marine structures at Yabucoa to be completed in order to determine extent and repair methods to be used. 5.2.22 SDB: A structural inspection to be completed on the Yabucoa dock facilities to determine extent and repair methods to be used. 4.2.22 SDB: Correction to description of work: Repairs to be on the Breasting dolphins and not the Mooring dolphins. 3.31.22 SDB: Local contractor will present a technical proposal for the repairs of the piles. This will need to be reviewed and approved by Engineering if we are to start repairing piles in 2022. | 2023-05-02 | Coverley, Colleen |  | East | Pipelines and Terminals | Station/Terminal |  | Yabucoa | BCTYA - BCT YABUCOA TERMINAL |  |  | 0 | 120000 |  |  |  | Spari, Markella |  |  |  | 1 | 41097 |  | Guest, ProSight | Independent | Aqua | 2021-08-06 | Marine
160L - Barnett to Auburn ROW CLEARING | Item | Open | MEXP | BN160ASE2301 | Maintenance Framework | 2085421 | McBryan, Jeannette | Right of Way | 5. Deferred | Drawdown | ROW Clearing | 16585 |  |  | 16584.93 | 16585 | 0 | Green |  |  |  | 16585 |  |  | 50000 |  |  | 50000 | Full | 50000 | 16585 |  | 16585 | No | Green | 2023-03-01 | 2023-02-22 | 2023-02-22 | 2023-04-30 | 2023-04-30 |  |  |  |  | 16584.93 | [16 empty] | 4.27.23 - 2024 work ground conditions did not improve | 2023-04-27 | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | Central-Illinois | BN160AS - BARNETT TO AUBURN |  | 16585 | 0 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46607 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-02-16
160L - Exposure and Span Emergent ROW CLEARING | Item | Open | MEXP | WO160BNE2302 | Maintenance Framework | 2074846 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 19753 |  |  | 19752.68 | 19753 | 0 | Green |  |  |  | 19753 |  |  | 25000 |  |  | 25000 | Full | 25000 | 19753 |  | 19753 | No | Green | 2023-01-01 | 2023-01-10 | 2023-01-10 | 2023-02-28 | 2023-02-28 |  |  | 12965.75 |  | 6786.93 | [18 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | St. Louis | WO160BN - WOOD RIVER TO BARNETT |  | 19753 | 0 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46413 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-01-04 | Other Programs
160L - Harristown to Dewitt II ROW CLEARING | Item | Open | MEXP | HT160DQE2301 | Maintenance Framework | 2085428 | McBryan, Jeannette | Right of Way | 5. Deferred | Drawdown | ROW Clearing |  |  |  | 0 | 30000 | -30000 | Red | [6 empty] | 35000 |  |  | 35000 | Full | 35000 |  |  |  | No | Green |  | 2023-02-22 | 2023-02-22 | 2023-04-30 | 2023-04-30 | [21 empty] | 4.27.23 - 2024 work ground conditions did not improve | 2023-04-27 | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | Central-Illinois | HT160DQ - HARRISTOWN JCT TO DEWITT |  |  | 0 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46609 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-02-16
160L - Wood River to Barnett ROW CLEARING | Item | Open | MEXP | WO160BNE2303 | Maintenance Framework | 2084499 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 32625 | 30000 |  | 62624.99 | 77625 | -15000 | Red |  |  |  | 62625 |  |  | 110000 |  |  | 110000 | Full | 110000 | 32625 | 30000 | 62625 | No | Green | 2023-02-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-12-31 |  |  |  | 24910.41 | 7714.58 |  | 15000 | 15000 | -15000 | Red |  |  |  |  | 15000 | 15000 | [7 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | St. Louis | WO160BN - WOOD RIVER TO BARNETT |  | 32625 | 0 | 30000 |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46585 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-02-10 | Other Programs
162L - Hazard Brush Removal - ROW CLEARING | Item | Open | MEXP | SG162DUE2301 | Maintenance Framework | 2075638 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 14667 |  |  | 14666.96 | 14667 | 0 | Green |  |  |  | 14667 |  |  | 25000 |  |  | 25000 | Full | 25000 | 14667 |  | 14667 | No | Green | 2023-01-01 | 2023-01-17 | 2023-01-17 | 2023-04-30 | 2023-04-30 |  |  | 3249.98 | 11416.98 | [19 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | St. Louis | SG162DU - SAUGET (ESL) TO DUPO |  | 14667 | 0 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46454 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-01-11 | Other Programs
165L - Casey to State Line II ROW Clearing | Item | Open | MEXP | CS165XXE2201 | Exempt | 1937600 | McBryan, Jeannette | Right of Way | 6. Operational | Drawdown | ROW Clearing | 18 |  |  | 17.63 | 18 | 0 | Green |  |  |  | 18 |  |  | 45000 |  |  | 45000 | Full | 45000 | 13530 |  | 13530 | No | Green | 2022-07-01 | 2022-01-06 | 2022-01-06 | 2022-04-30 | 2022-11-30 |  |  | 17.63 | [18 empty] | 4.12.22 - Saturated ground conditions - crew obligated to another operator after 4.1.22 | 2022-04-12 |  |  | West | Pipelines and Terminals | Right of Way |  | St. Louis | CS165XX - CASEY TO IN S/L |  | 18 | 0 |  |  | 13513 |  | McBryan, Jeannette | Ostach, Carl A. | N/A |  | 1 | 42705 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2022-01-06 | Other Programs
190L - Horseshoe Lake Station Mow and Spray ROW CLEARING | Item | Open | MEXP | HO00000E2301 | Maintenance Framework | 2085350 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 1596 | 6000 |  | 7595.94 | 7596 | 0 | Green |  |  |  | 7596 |  |  | 7500 |  |  | 7500 | Full | 7500 | 1596 | 6000 | 7596 | No | Green | 2023-03-01 | 2023-02-21 | 2023-02-21 | 2023-08-31 | 2023-08-31 |  |  |  |  | 1595.94 | [9 empty] | 6000 | [8 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | St. Louis | HO - HORSESHOE LAKE PUMP STATION |  | 1596 | 0 | 6000 |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46606 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-02-16
2023 ROW Clearing Budget Allocation | Item | Open | MEXP | 1348340E2300 | Maintenance Framework |  | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing |  | 1450000 |  | 1450000 | 1925000 | -475000 | Red | 3400000 |  | 3400000 | -1950000 |  |  | 3400000 |  |  | 3400000 | Full | 3400000 |  | 1450000 | 1450000 | No | Green | 2023-06-01 | 2022-12-12 | 2022-12-12 | 2023-12-31 | 2023-12-31 | [13 empty] | 280000 | 200000 | 200000 | 200000 | 200000 | 200000 | 170000 |  |  |  | Schultz, Amy |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Right of Way |  | Corporate | Corporate |  |  | 280000 | 600000 | 570000 |  |  | McBryan, Jeannette | Ostach, Carl A. |  |  | 1 | 44567 |  | Guest, ProSight | Independent | Aqua | 2022-08-12 | Other Programs
203L - Wayne to Flint ROW CLEARING | Item | Open | MEXP | WW203WCE2301 | Maintenance Framework | 2086146 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 71482 | 10000 |  | 81481.84 | 55000 | 26482 | Red |  |  |  | 81482 |  |  | 80000 |  |  | 80000 | Full | 80000 | 71482 | 10000 | 81482 | No | Green | 2023-04-01 | 2023-02-28 | 2023-02-28 | 2023-06-30 | 2023-06-30 | [5 empty] | 71481.84 | 45000 | 45000 | 26482 | Red |  |  | 5000 | 5000 | [9 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | Wayne Pipeline | WW203WC - WAYNE TO CLARKSTON |  |  | 81482 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46649 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-02-27
208L - Flint to Bay City ROW CLEARING | Item | Open | MEXP | WF208WBE2302 | Maintenance Framework | 2096448 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 2390 | 121000 |  | 123390.36 | 185000 | -61610 | Red |  |  |  | 123390 |  |  | 185000 |  |  | 185000 | Full | 185000 | 2390 | 121000 | 123390 | No | Green | 2023-04-01 | 2023-03-29 | 2023-03-29 | 2023-07-01 | 2023-07-01 | [5 empty] | 2390.36 | 64000 | 64000 | -61610 | Red |  |  | 64000 | 57000 | [9 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | Wayne Pipeline | WF208WB - FLINT TO BAY CITY |  |  | 123390 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46841 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-03-24
209L - Woodhaven to Wayne ROW CLEARING | Item | Open | MEXP | WS209WWE2302 | Maintenance Framework | 2086151 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 24841 |  |  | 24841.02 | 27848 | -3007 | Red |  |  |  | 24841 |  |  | 25000 |  |  |  | Full | 25000 | 24841 |  | 24841 | No | Green | 2023-03-01 |  |  | 2023-04-30 | 2023-04-30 |  |  |  |  | 22848.27 | 1992.75 | 5000 | 5000 | -3007 | Red | [13 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | Wayne Pipeline | WS209WW - WOODHAVEN TO WAYNE |  | 22848 | 1993 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46654 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-02-27
304L - State Line to Flat Rock ROW CLEARING | Item | Open | MEXP | XX304FKE2301 | Maintenance Framework | 2086155 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 10362 | 65000 |  | 75361.81 | 70712 | 4650 | Yellow |  |  |  | 75362 |  |  | 85000 |  |  | 85000 | Full | 85000 | 10362 | 65000 | 75362 | No | Green | 2023-03-01 | 2023-02-28 | 2023-02-28 | 2023-06-30 | 2023-06-30 |  |  |  |  | 5712.07 | 4649.74 | 40000 | 40000 | -35350 | Red |  |  |  | 40000 | 25000 | [8 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | Wayne Pipeline | XX304FK - MICH S/L - FLAT ROCK-NORTH |  | 5712 | 44650 | 25000 |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46650 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-02-27
402L- Lima to Huntington II ROW Clearing | Item | Open | MEXP | LA402XXE2202 | Maintenance Framework | 1979737 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 655 |  |  | 654.71 | 655 | 0 | Green |  |  |  | 655 |  |  | 35000 |  |  | 35000 | Full | 35000 | 13907 |  | 13907 | No | Green | 2022-06-01 | 2022-05-04 | 2022-05-04 | 2022-08-31 | 2022-08-31 |  |  | 654.71 | [20 empty] | Hill, Elizabeth |  | West | Pipelines and Terminals | Right of Way |  | Lima Pipelines | LA402XX - LIMA-IND S/L/HUNTINGTON W |  | 655 | 0 |  |  | 13252 |  | McBryan, Jeannette | Ostach, Carl A. | N/A |  | 1 | 43582 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2022-05-04 | Other Programs
604L - Hazard Brush Removal | Item | Open | MEXP | PR604LNE2301 | Maintenance Framework | 2074842 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 2932 |  |  | 2932.19 | 2932 | 0 | Green |  |  |  | 2932 |  |  | 3000 |  |  | 3000 | Full | 3000 | 2932 |  | 2932 | No | Green | 2023-01-01 | 2023-01-10 | 2023-01-10 | 2023-01-31 | 2023-01-31 |  |  | 2932.19 | [20 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | Linden | PR604LN - PORT READING TO LINDEN |  | 2932 | 0 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46411 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-01-04 | Other Programs
714L - Macungie to Tuckerton ROW CLEARING | Item | Open | MEXP | ZG714RGE2301 | Maintenance Framework | 2074847 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 85466 |  |  | 85466.01 | 81446 | 4020 | Yellow |  |  |  | 85466 |  |  | 115000 |  |  | 115000 | Full | 115000 | 85466 |  | 85466 | No | Green | 2023-02-01 | 2023-01-10 | 2023-01-10 | 2023-04-30 | 2023-04-30 |  |  |  | 36916.26 | 44529.75 | 4020 |  |  | 4020 | Red | [13 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | Macungie Pipe | ZG714RG - MACUNGIE TO TUCKERTON |  | 81446 | 4020 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46436 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-01-06 | Other Programs
714L -Tuckerton to Sinking Springs ROW CLEARING | Item | Open | MEXP | RG714SNE2301 | Maintenance Framework | 2074849 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 40103 |  |  | 40102.67 | 20192 | 19910 | Red |  |  |  | 40103 |  |  | 35000 |  |  | 35000 | Full | 35000 | 40103 |  | 40103 | No | Green | 2023-02-01 | 2023-01-10 | 2023-01-10 | 2023-04-30 | 2023-04-30 |  |  |  | 230 | 14962.26 | 24910.41 | 5000 | 5000 | 19910 | Red | [13 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | Macungie Pipe | RG714SN - TUCKERTON-SINKING SPRING |  | 15192 | 24910 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46437 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-01-06 | Other Programs
718L - Duncansville to Delmont Canopy II ROW MOWING | Item | Open | MEXP | DT718DME2301 | Maintenance Framework | 2086158 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 24 | 70000 |  | 70023.75 | 120024 | -50000 | Red |  |  |  | 70024 |  |  | 210000 |  |  | 210000 | Full | 210000 | 24 | 70000 | 70024 | No | Green | 2023-03-01 | 2023-02-28 | 2023-02-28 | 2022-09-30 | 2022-09-30 |  |  |  |  | 23.75 |  | 50000 | 50000 | -50000 | Red |  |  | 10000 | 15000 | 45000 | [8 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | Duncansville | DT718DM - DUNCANSVILLE STA-DELMONT |  | 24 | 25000 | 45000 |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46652 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-02-27
720L - Carlisle to Luther Herbicide ROW CLEARING | Item | Open | MEXP | CR720LSE2301 | Maintenance Framework | 2086159 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing |  | 75000 |  | 75000 | 75000 | 0 | Green |  |  |  | 75000 |  |  | 75000 |  |  | 75000 | Full | 75000 |  | 75000 | 75000 | No | Green | 2023-06-01 | 2023-02-28 | 2023-02-28 | 2023-10-31 | 2023-10-31 | [13 empty] | 20000 | 40000 | 15000 | [7 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | Mechanicsburg | CR720LS - CARLISLE TO SHIELD'S PUMP STA |  |  | 20000 | 55000 |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46653 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-02-27
720L - Mount Union to Dville Herbicide ROW CLEARING | Item | Open | MEXP | MU720DTE2301 | Maintenance Framework | 2086156 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 27784 | 65000 |  | 92783.53 | 92784 | 0 | Green |  |  |  | 92784 |  |  | 65000 |  |  | 65000 | Full | 65000 | 27784 | 65000 | 92784 | No | Green | 2023-03-01 | 2023-02-28 | 2023-02-28 | 2023-09-30 | 2023-09-30 |  |  |  |  | 27783.53 | [8 empty] | 25000 | 25000 | 15000 | [7 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | Duncansville | MU720DT - MOUNT UNION TO DUNCANSVILLE ST |  | 27784 | 25000 | 40000 |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46651 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-02-27
720L - Mount Union to Dville Spot Clearing ROW CLEARING | Item | Open | MEXP | MU720DTE2201 | Maintenance Framework | 1991155 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 6918 |  |  | 6918.36 | 6918 | 0 | Green |  |  |  | 6918 |  |  | 9000 |  |  | 9000 | Full | 9000 | 128457 |  | 128457 | No | Green | 2022-06-01 | 2022-06-20 | 2022-06-20 | 2022-09-30 | 2022-09-30 |  |  | 6918.36 | [18 empty] | 10.6.22 - intensity of work | 2022-10-06 | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | Duncansville | MU720DT - MOUNT UNION TO DUNCANSVILLE ST |  | 6918 | 0 |  |  | 121538 |  | McBryan, Jeannette | Ostach, Carl A. | N/A |  | 1 | 44007 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2022-06-17 | Other Programs
751L - Malvern to Reading Jct II ROW CLEARING | Item | Open | MEXP | MX751REE2301 | Maintenance Framework | 2075634 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 57099 |  |  | 57098.96 | 64099 | -7000 | Red |  |  |  | 57099 |  |  | 47000 |  |  | 47000 | Full | 47000 | 57099 |  | 57099 | No | Green | 2023-01-01 | 2023-01-17 | 2023-01-17 | 2023-05-31 | 2023-05-31 |  |  | 43111.95 |  | 13987.01 |  | 7000 | 7000 | -7000 | Red | [13 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | Malvern | MX751RE - MALVERN TO READING JCT |  | 57099 | 0 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46452 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-01-11 | Other Programs
751L- Geneva to Rochester II ROW Clearing | Item | Open | MEXP | GQ751RXE2201 | Exempt | 1937595 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 1780 |  |  | 1780 | 1780 | 0 | Green |  |  |  | 1780 |  |  | 90000 |  |  | 90000 | Full | 90000 | 44807 |  | 44807 | No | Green | 2022-05-01 | 2022-01-06 | 2022-01-06 | 2022-08-31 | 2022-08-31 |  |  | 1780 | [18 empty] | 10.6.22 - crew now on this section delay due to intensity of rochester segment 7.12.22 - crew on Rochester Segment - pushed out funds | 2022-10-06 | Sautter, Maureen |  | East | Pipelines and Terminals | Right of Way |  | Auburn Pipeline | GQ751RX - GENEVA JCT - ROCHESTER JCT |  | 1780 | 0 |  |  | 43027 |  | McBryan, Jeannette | Ostach, Carl A. | N/A |  | 1 | 42701 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2022-01-06 | Other Programs
751L- Geneva to Rochester III ROW Clearing | Item | Open | MEXP | GQ751RXE2301 | Maintenance Framework | 2074837 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 89365 |  |  | 89365.35 | 72793 | 16572 | Red |  |  |  | 89365 |  |  | 45000 |  |  | 45000 | Full | 45000 | 89365 |  | 89365 | No | Green | 2023-01-01 | 2023-01-10 | 2023-01-10 | 2023-03-31 | 2023-03-31 |  |  | 25909.61 | 28410.35 | 18473 | 16572.39 |  |  | 16572 | Red | [13 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | Auburn Pipeline | GQ751RX - GENEVA JCT - ROCHESTER JCT |  | 72793 | 16572 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46410 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-01-04 | Other Programs
751L- Rochester to Batavia II ROW Clearing | Item | Open | MEXP | RX751BXE2201 | Exempt | 1937594 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 1268 |  |  | 1267.56 | 1268 | 0 | Green |  |  |  | 1268 |  |  | 115000 |  |  | 115000 | Full | 115000 | 208684 |  | 208684 | No | Green | 2022-05-01 | 2022-01-06 | 2022-01-06 | 2022-08-31 | 2022-08-31 |  |  | 1267.56 | [18 empty] | 5.3.22 - crew 2.5 weeks behind due to wet conditions will reach Batavia by end of May | 2022-05-03 | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | Auburn Pipeline | RX751BX - ROCHESTER JCT - BATAVIA STATIO |  | 1268 | 0 |  |  | 207417 |  | McBryan, Jeannette | Ostach, Carl A. | N/A |  | 1 | 42700 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2022-01-06 | Other Programs
751L-Malvern to Reading Jct Mowing ROW CLEARING | Item | Open | MEXP | MX751REE2201 | Maintenance Framework | 2023936 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 460 |  |  | 460 | 460 | 0 | Green |  |  |  | 460 |  |  | 95000 |  |  | 95000 | Full | 95000 | 66097 |  | 66097 | No | Green | 2022-11-01 | 2022-09-29 | 2022-09-29 | 2022-12-31 | 2022-12-31 |  |  | 460 | [20 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | Malvern | MX751RE - MALVERN TO READING JCT |  | 460 | 0 |  |  | 65637 |  | McBryan, Jeannette | Ostach, Carl A. | N/A |  | 1 | 45928 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-09-29 | Other Programs
751L-Reading Jct to Macungie Mowing ROW CLEARING | Item | Open | MEXP | RE751ZPE2201 | Maintenance Framework | 2023927 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 24 |  |  | 23.92 | 24 | 0 | Green |  |  |  | 24 |  |  | 95000 |  |  | 95000 | Full | 95000 | 29760 |  | 29760 | No | Green | 2022-10-01 | 2022-09-29 | 2022-09-29 | 2022-12-31 | 2022-12-31 |  |  | 23.92 | [20 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | Macungie Pipe | RE751ZP - READING JCT - MACUNGIE JCT |  | 24 | 0 |  |  | 29736 |  | McBryan, Jeannette | Ostach, Carl A. | N/A |  | 1 | 45927 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-09-29 | Other Programs
755L-Hallowell to Bangor II ROW Clearing | Item | Open | MEXP | HW755BME2201 | Exempt | 1937815 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 21805 |  |  | 21804.65 | 21805 | 0 | Green |  |  |  | 21805 |  |  | 240000 |  |  | 240000 | Full | 240000 | 860042 |  | 860042 | No | Green | 2022-01-01 | 2022-01-06 | 2022-01-06 | 2022-05-30 | 2022-05-30 |  |  | 21804.65 | [18 empty] | 10.6.22 - continuing needed work within 2022 total budget 7.12.22 - continuing project beyond scope due to optimal conditions 5.3.22 - continuing project beyond planned end point due to need 4.5.22 - on track on target. 2.10.22 - on track for feb | 2022-10-06 | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | Maine | HW755BM - HALLOWELL - BANGOR TERM |  | 21805 | 0 |  |  | 838237 |  | McBryan, Jeannette | Ostach, Carl A. | N/A |  | 1 | 42718 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2022-01-07 | Other Programs
755L-Hallowell to Bangor III ROW Clearing | Item | Open | MEXP | HW755BME2301 | Maintenance Framework | 2074845 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 305802 | 60000 |  | 365802 | 256177 | 109625 | Red |  |  |  | 365802 |  |  | 265000 |  |  | 265000 | Full | 265000 | 305802 | 60000 | 365802 | No | Green | 2023-01-01 | 2023-01-10 | 2023-01-10 | 2023-04-30 | 2023-04-30 |  |  | 55240 | 65784 | 100153 | 84625 | 35000 | 35000 | 49625 | Red |  |  | 60000 | [8 empty] | 3.10.23 - variance due to AP error delaying payment to vendor | 2023-03-10 | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | Maine | HW755BM - HALLOWELL - BANGOR TERM |  | 221177 | 144625 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46412 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-01-04 | Other Programs
760L - Dubuque To Milan Canopy Hot Spot ROW CLEARING | Item | Open | MEXP | UB760ARE2301 | Maintenance Framework | 2076569 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 22965 |  |  | 22964.59 | 22965 | 0 | Green |  |  |  | 22965 |  |  | 25000 |  |  | 25000 | Full | 25000 | 22965 |  | 22965 | No | Green | 2023-02-01 | 2023-01-26 | 2023-01-26 | 2023-01-31 | 2023-01-31 |  |  |  | 22964.59 | [19 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | Eastern Iowa | UB760AR - DUBUQUE VLV - CEDER RAPIDS TER |  | 22965 | 0 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46497 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-01-19 | Other Programs
760L- Dubuque to Cedar Rapids ROW CLEARING | Item | Open | MEXP | UB760ARE2302 | Maintenance Framework | 2084488 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 88000 |  |  | 88000 | 97214 | -9214 | Yellow |  |  |  | 88000 |  |  | 100000 |  |  | 100000 | Full | 100000 | 88000 |  | 88000 | No | Green | 2023-03-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-12-31 |  |  |  |  | 22214.05 | 65785.95 | 35000 | 35000 | 30786 | Red | [13 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | Eastern Iowa | UB760AR - DUBUQUE VLV - CEDER RAPIDS TER |  | 22214 | 65786 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46583 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-02-10 | Other Programs
760L-Cedar Rapids to Harper ROW CLEARING | Item | Open | MEXP | AR760HHE2301 | Maintenance Framework | 2084493 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 1956 | 20000 |  | 21955.73 | 95556 | -73601 | Red |  |  |  | 21956 |  |  | 100000 |  |  | 100000 | Full | 100000 | 1956 | 20000 | 21956 | No | Green | 2023-02-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-12-31 |  |  |  | 529.23 | 27.19 | 1399.31 | 40000 | 40000 | -38601 | Red |  |  | 20000 | [10 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | Eastern Iowa | AR760HH - CEDER RAPIDS TO HARPER STA |  | 556 | 21399 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46584 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-02-10 | Other Programs
803L - Caledonia to Rochester ROW CLEARING | Item | Open | MEXP | CD803RCE2301 | Maintenance Framework | 2075637 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 20566 |  |  | 20566.06 | 32000 | -11434 | Red |  |  |  | 20566 |  |  | 96000 |  |  | 96000 | Full | 96000 | 20566 |  | 20566 | No | Green | 2023-04-01 | 2023-01-17 | 2023-01-17 | 2023-05-31 | 2023-05-31 | [5 empty] | 20566.06 | 32000 | 32000 | -11434 | Red | [13 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | Auburn Pipeline | CD803RC - CALEDONIA TO ROCHESTER |  |  | 20566 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46453 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-01-11 | Other Programs
803L - Waterloo to Caledonia III ROW CLEARING | Item | Open | MEXP | WL803CDE2301 | Maintenance Framework | 2074826 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 75559 |  |  | 75558.81 | 45401 | 30158 | Red |  |  |  | 75559 |  |  | 45000 |  |  | 45000 | Full | 45000 | 75559 |  | 75559 | No | Green | 2023-01-01 | 2023-01-10 | 2023-01-10 | 2023-03-31 | 2023-03-31 |  |  | 34444.35 | 10956.6 |  | 30157.86 |  |  | 30158 | Red | [13 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | Auburn Pipeline | WL803CD - WATERLOO TO CALEDONIA |  | 45401 | 30158 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46409 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-01-04 | Other Programs
803L - Waterloo to Caledonia Phase II ROW CLEARING | Item | Open | MEXP | WL803CDE2202 | Maintenance Framework | 2013154 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 486 |  |  | 485.86 | 486 | 0 | Green |  |  |  | 486 |  |  | 90000 |  |  | 90000 | Full | 90000 | 75755 |  | 75755 | No | Green | 2022-09-01 | 2022-08-23 | 2022-08-23 | 2022-12-31 | 2022-12-31 |  |  | 485.86 | [18 empty] | 10.6.22 - crew ahead of schedule | 2022-10-06 | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | Auburn Pipeline | WL803CD - WATERLOO TO CALEDONIA |  | 486 | 0 |  |  | 75269 |  | McBryan, Jeannette | Ostach, Carl A. | N/A |  | 1 | 45152 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2022-08-22 | Other Programs
999L - Hamden to 85 East Street ROW CLEARING | Item | Open | MEXP | BNTNV00E2303 | Maintenance Framework | 2110051 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing |  | 28000 |  | 28000 | 28000 | 0 | Green |  |  |  | 28000 |  |  | 28000 |  |  | 28000 | Full | 28000 |  | 28000 | 28000 | No | Green | 2023-05-01 | 2023-04-07 | 2023-04-07 | 2023-05-31 | 2023-05-31 | [12 empty] | 28000 | [10 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | New Haven Harbor | BNTNV - New Haven Waterfront Terminal |  |  | 28000 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46877 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-04-04
999L - Rochester Shipper Lines ROW CLEARING | Item | Open | MEXP | RC999A4E2301 | Maintenance Framework | 2086154 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 38 |  |  | 38.39 | 10000 | -9962 | Red |  |  |  | 38 |  |  | 25000 |  |  | 25000 | Full | 25000 | 38 |  | 38 | No | Green | 2023-04-01 | 2023-02-28 | 2023-02-28 | 2023-04-30 | 2023-04-30 | [5 empty] | 38.39 | 10000 | 10000 | -9962 | Red | [13 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | Auburn Pipeline | RC999A4 - ROCHESTER TO ALASKAN OIL |  |  | 38 |  |  |  |  | McBryan, Jeannette | Ostach, Carl A. | N/A |  | 1 | 46648 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-02-27
999L - St Charles Jct to Terminal ROW CLEARING | Item | Open | MEXP | VO999A1E2301 | Maintenance Framework | 2075640 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 3250 |  |  | 3249.98 | 3250 | 0 | Green |  |  |  | 3250 |  |  | 10000 |  |  | 10000 | Full | 10000 | 3250 |  | 3250 | No | Green | 2023-01-01 | 2023-01-17 | 2023-01-17 | 2023-01-31 | 2023-01-31 |  |  | 3249.98 | [20 empty] | Schultz, Amy |  | West | Pipelines and Terminals | Right of Way |  | St. Louis | VO999A1 |  | 3250 | 0 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46455 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-01-11 | Other Programs
999L - Tuckerton to Berks ROW CLEARING | Item | Open | MEXP | RG999A1E2301 | Maintenance Framework | 2094004 | McBryan, Jeannette | Right of Way | 3. Active | Drawdown | ROW Clearing | 10331 |  |  | 10331.18 | 35000 | -24669 | Red |  |  |  | 10331 |  |  | 65000 |  |  | 65000 | Full | 65000 | 10331 |  | 10331 | No | Green | 2023-04-01 | 2023-03-06 | 2023-03-06 | 2023-05-31 | 2023-05-31 | [5 empty] | 10331.18 | 35000 | 35000 | -24669 | Red | [13 empty] | Schultz, Amy |  | East | Pipelines and Terminals | Right of Way |  | Macungie Pipe | RG999A1 - TUCKERTON TO FARM & HOME |  |  | 10331 |  |  |  |  | McBryan, Jeannette | Boone, David G. | N/A |  | 1 | 46695 |  | McBryan, Jeannette | JDE Child | Burnt Orange | 2023-03-02
2022 - XW999A2 - Pressure Test | Item | Open | MEXP | BTXXW00E2203 | Maintenance Framework | 2053658 | Garcia, Monica | South | 6. Operational | Defined | Assessments | 69803 | 4000 |  | 73802.73 | 82075 | -8273 | Red | 125000 |  | 125000 | -51197 |  |  | 125000 |  |  | 125000 | Full | 125000 | 69803 | 4000 | 73803 | No | Green | 2023-01-01 | 2022-12-23 | 2022-12-23 | 2023-03-01 | 2023-01-20 |  |  | 88369.92 | -7973.55 | 1679.09 | -12272.73 |  |  | -12273 | Red |  |  | 4000 | [8 empty] | 5.9.23 ML Variance is due to an issue with the accrual file PMO recommended forecasting missing accruals for May 4.4.23 Project is Complete 2/2/23: MLG: awaiting final invoices. 1/23/23 MLG Pressure test was completed on 1/20/23 and was successful. This line will be placed under a nitrogen blanket of 15 psi. 1/4/23 MLG: Pressure test is scheduled for the week of Jan 16th. 8.8.22 ML The pipeline is not scheduled for a pressure test this year. A pressure test was done 2020 and is not scheduled until 2023 per PM. | 2023-05-09 | Landeros, Melisa |  | South | Pipelines and Terminals | Pipeline Integrity |  | Corpus Christi | BTXXW - George West |  | 82075 | -8273 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40651 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Assessments
2023 Drawdown South Region MCAP | Item | Open | MCAP |  | Maintenance Framework |  | Johnson, AJ | South | 1. Proposed |  | South |  | 98000 |  | 98000 | 248000 | -150000 | Red | 1000000 |  | 1000000 | -902000 | [9 empty] | 98000 | 98000 | No | Green | 2023-09-01 |  |  |  | 2023-11-30 | [16 empty] | 28000 |  | 70000 | 0 |  | 5/4/2023 AJ- removed 150k for Marero Storm Water project. 4/12/2023 AJ - reduced 162 k to cover Btp t-102 bybass 4/10/2023 AJ - Reduces Drawdown by 200k to cover HUB boiler overages 3/7/23 AJ - removed 160k and moved to BTP Stripper Bypass removed 30k and moved to Greensboro II tank 8 pump electrical feed | 2023-05-04 |  |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Operating Infrastructure | Operating Infrastructure | Corporate | Corporate |  |  | 0 | 28000 | 70000 |  |  | Johnson, AJ |  |  |  | 1 | 45216 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
2023 Drawdown South Region MEXP | Item | Open | MEXP | 1348687E2300 | Maintenance Framework |  | Johnson, AJ | South | 3. Active | Defined | South |  | 229000 |  | 229000 | 229000 | 0 | Green | 500000 | -40000 | 460000 | -231000 |  |  | 500000 |  |  |  | Full | 500000 |  | 229000 | 229000 | No | Green | 2023-06-01 |  |  | 2023-12-31 | 2023-11-30 | [12 empty] | 0 | 69000 | 100000 | 60000 | [5 empty] | 4/12/2023 AJ reduced 100 k to cover the BTP cyanide temp chiller project. 4/10/23 AJ - Removed 28k to cover Tampa South Generator removed 20k to cover North Augusta Backflow preventor. removed 20k to cover Wilmington lubricity. Removed 43k to cover Ft Lauderdale lagoon cleaning. removed 20k to cover overage of north augusta asphalt. 3/7/23 - removed 40k for Wilmington piping quality and cleaning | 2023-04-12 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal | Station/Terminal | Corporate | Corporate |  |  | 69000 | 160000 |  |  |  | Johnson, AJ | Burke, Kevin |  |  | 1 | 45217 |  | Administrator, System | JDE Parent | Yellow | 2022-08-23 | Other Programs
2023 HF999A2 - ILI | Item | Open | MEXP | HF999A2E2301 | Maintenance Framework | 2086049 | Garcia, Monica | South | 6. Operational | Defined | Assessments | 94353 |  |  | 94352.64 | 82431 | 11922 | Red | 107700 |  | 107700 | -13347 |  |  | 105650 |  |  | 105650 | Full | 105650 | 94353 |  | 94353 | No | Green | 2023-02-01 | 2023-03-10 | 2023-03-10 | 2023-03-31 | 2023-03-31 |  |  |  | 4828 | 77602.57 | 11922.07 |  |  | 11922 | Red |  | Contractor/Vendor Issue | [9 empty] | 5/1/23 MLG: Variance due to contractor 3rd party additional charges 4/4/23 MLG: Variance due to savings on labor from AFE estimate. 3/1/23 MLG: Variance due to delay with another project where this line was supposed to be lowered, thereby causing a delay with the commencement of this project. | 2023-05-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Pipeline Integrity |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 82431 | 11922 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44687 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
Albany, GA (BSEVY): new video recorder | Item | Candidate | MCAP |  | Maintenance Framework |  | Magouirk, Josh | South | 1. Proposed |  | Security & Cameras |  | 15000 |  | 15000 | 15000 | 0 | Green | 15000 |  | 15000 | 0 | [9 empty] | 15000 | 15000 | No | Green | 2023-08-01 |  |  |  | 2023-02-28 | [15 empty] | 15000 | [9 empty] | South | Pipelines and Terminals | Operating Infrastructure |  | Georgia | BSEVY - ALBANY GEORGIA TERMINAL |  |  | 0 | 15000 |  |  |  | Clark, Chris |  |  |  | 1 | 45146 |  | Guest, ProSight | Independent | Aqua | 2022-08-22 | Other Programs
Atlanta (BSEVZ) Tank 8702 - OOS API 653 Insp Seal Insp & Refurb | Item | Open | MEXP | BSEVZ00E2301 | Maintenance Framework | 2085560 | Bryant, Ben | South | 3. Active | Defined | Tanks | 129181 | 100000 |  | 229180.95 | 236000 | -6819 | Yellow | 230000 |  | 230000 | -819 |  |  | 215050 |  |  | 215050 | Phase | 215050 | 129181 | 100000 | 229181 | No | Green | 2023-03-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-05-31 |  |  |  |  | 36000 | 93180.95 | 100000 | 100000 | -6819 | Yellow |  |  | 100000 | [8 empty] | 5/1/23 Tank has been inspected by DJA. Repair contractor is currently onsite making repairs to tank 8702. Accrue 42k to Don Miller 7K to DJA, 40K to FHG 19K to ATP. 4/1/20 Tank has been Isolated and Cleaned. DJA will be onsite this week to conduct API 653 Inspection. Accrue 22K Don Miller/Streamtech 14 K To American Tank Partners. 3/2/2023 - Tank to be OOS this month. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Tank Integrity |  | Georgia | BSEVZ - ATLANTA TERMINAL |  | 36000 | 193181 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44770 |  | Administrator, System | Independent |  | 2022-08-18 | Int - Tanks
Belton - New asphalt installation phase 1 | Item | Open | MCAP | BETTN00M2202 | Maintenance Framework | 1990764 | Corman, Chris | South | 7. Closed | Defined | South | 823 |  |  | 823.01 | 823 | 0 | Green |  |  |  | 823 |  |  | 63000 | 37000 |  | 100000 | Phase | 100000 | 39595 |  | 39595 | No | Green | 2022-07-01 | 2022-06-16 | 2022-06-16 | 2022-09-01 | 2022-11-30 |  |  | 160.51 |  | 662.5 | [16 empty] | 1/3/22 - IFC drawings have been received. Project will continue as a different project in 2023. 12/5/22- Received IFC drawings for concrete install, initial bid came back substantially higher and new project created for 2023. Will look into rebidding and phasing out project. 11/1/2022 - IFC drawings are being finalized. 10/3/2022 - Accrue additional $7k to arseal. 9/12/2022 - Geotech completed. 8/29/2022 - Accrue $17k to Arseal. Geotech was not completed in August due to contractor conflicts and is planned for September1st. Remaining $16k will be spent in September. 8/8/2022 - Laser scan completed in August. Geotech scheduled for August. Engineering through September. 8/2/22- Scheduling delayed due to contractor availability 6/16/22 - Submitted AFE for approval. 3/29/2022 - Reviewing scope with terminal | 2023-01-03 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | South Carolina | BETTN - BET BELTON |  | 823 | 0 |  |  | 38772 |  | Johnson, AJ | Asiedu, Saka |  |  | 1 | 37727 |  | Guest, ProSight | Independent |  | 2020-08-12 | Other Programs
Belton - New asphalt installation phase 2 | Item | Candidate | MCAP |  | Maintenance Framework |  | Pitkin, Colton | South | 1. Proposed |  | South |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 | [9 empty] | 100000 | 100000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 100000 | [10 empty] | South | Pipelines and Terminals | Operating Infrastructure |  | South Carolina | BETTN - BET BELTON |  |  | 0 | 100000 |  |  |  | Johnson, AJ |  |  |  | 1 | 45267 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Other Programs
Belton Concrete Repair and Seal | Item | Candidate | MEXP |  | Maintenance Framework |  | Pitkin, Colton | South | 1. Proposed |  | Secondary Containment |  | 45000 |  | 45000 | 45000 | 0 | Green | 43843 |  | 43843 | 1157 | [9 empty] | 45000 | 45000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 45000 | [10 empty] | South | Pipelines and Terminals | Station/Terminal |  | South Carolina | BETTN - BET BELTON |  |  | 0 | 45000 |  |  |  | Spari, Markella |  |  |  | 1 | 44272 |  | Guest, ProSight | Independent | Aqua | 2022-07-26 | Other Programs
Belton Tank 101 Pump Replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Bryant, Ben | South | 1. Proposed |  | Rotating Equipment |  | 40650 |  | 40650 | 40650 | 0 | Green | 40650 |  | 40650 | 0 | [9 empty] | 40650 | 40650 | No | Green | 2023-06-01 |  |  |  | 2023-04-30 | [12 empty] | 0 | 40650 | [7 empty] | 5/1/23 Awaiting quotes for Pump replacement. 4/3/23 Meeting with Belton OPS this week to discuss replacement of pump. | 2023-05-01 |  |  | South | Pipelines and Terminals | Operating Infrastructure |  | South Carolina | BETTN - BET BELTON |  |  | 40650 |  |  |  |  | Posipanko, Dan |  |  |  | 1 | 44455 |  | Guest, ProSight | Independent | Aqua | 2022-08-08 | Other Programs
BET Wilmington NC - ULSD Pipe Sampling, Clearing, and Cleaning | Item | Open | MEXP | BETQM00E2301 | Maintenance Framework | 2093227 | Johnson, AJ | South | 3. Active | Drawdown | South | 72848 |  |  | 72848.01 | 46200 | 26648 | Red |  | 40000 | 40000 | 32848 |  |  | 40000 |  |  | 40000 | Full | 40000 | 72848 |  | 72848 | No | Green | 2023-03-01 | 2023-02-28 | 2023-02-28 | 2023-04-30 | 2023-04-30 |  |  |  |  | 36200 | 36648.01 | 10000 | 10000 | 26648 | Red |  | Forecasting | [11 empty] | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | North Carolina | BETQM - BET WILMINGTON TERMINAL |  | 36200 | 36648 |  |  |  |  | Johnson, AJ | Clay, Chris | N/A |  | 1 | 46655 |  | Johnson, AJ | JDE Child | Burnt Orange | 2023-02-28
BETGH - Lykens JCT Pipe Alignment | Item | Open | MCAP | BETGH00M2202 | Maintenance Framework | 2023245 | Leal, Trey (Tony) | South | 7. Closed | Drawdown | South | 4789 |  |  | 4789.02 | 4789 | 0 | Green |  |  |  | 4789 |  |  | 100000 |  |  | 100000 | Full | 100000 | 105122 |  | 105122 | No | Green | 2022-11-01 | 2022-09-21 | 2022-09-21 | 2022-12-31 | 2022-12-16 |  |  | 3902.47 | 886.55 | 0 | [16 empty] | 4/3/23 Ready to Close 3/1/23 Re-accrue M&S Contracting $29K 1/29/2023 - Re-accrue $29k to M&S Contracting 1/3/23- Accrue $29k to M&S Contracting. Project complete. 12/5/22- Accrue $27k to M&S Contracting 11/1/22- Requested outage in December, if not approved, project will push to Jan. | 2023-04-03 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Alabama | BETGH - BET BIRMINGHAM |  | 4789 | 0 |  |  | 100333 |  | Johnson, AJ | Burke, Kevin |  |  | 1 | 45756 |  | Johnson, AJ | Independent | Aqua | 2022-09-07 | Other Programs
BETQJ - Jacksonville Diffuser | Item | Open | MEXP | BETQJ00E2206 | Maintenance Framework | 1981449 | Corman, Chris | South | 7. Closed | Drawdown | South | 150 |  |  | 150 | 150 | 0 | Green |  |  |  | 150 |  |  | 95000 |  |  | 95000 | Full | 95000 | 73575 |  | 73575 | No | Green | 2022-11-01 | 2022-05-23 | 2022-05-23 | 2022-09-30 | 2022-11-30 |  |  | 150 | [18 empty] | 1/3/23- Project complete, ready to close 12/5/2022 - Project was completed week of 11/28. Accrue 64k to MILTON J WOOD FIRE PROTECTION 11/1/2022 - Foam chambers expected to arrive 11/2. Work scheduled the week of 11/14. Will complete by 11/22. 10/4/2022- shipping of chambers delayed until November. Shifted forecast to reflect this. 9/6/2022 - Project still on track to be complete in October. Chambers expected the week of 10/17 8/9/22 - After further review, project schedule for start date October per Chris Corman. DC 6/2/22 - Forecast adjusted to July for start of project. MC | 2023-01-03 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | Florida | BETQJ - BET JACKSONVILLE TERMINAL |  | 150 | 0 |  |  | 73425 |  | Johnson, AJ | Asiedu, Saka |  |  | 1 | 43801 |  | Guest, ProSight | Independent | Aqua | 2022-05-17 | Other Programs
BETQJ Jacksonville Terminal Painting | Item | Open | MCAP | BETQJ00M2202 | Maintenance Framework | 1956001 | Wirfs, Mike | South | 6. Operational | Defined | Atmospheric Corrosion | 4948 | 210000 |  | 214948.08 | 214948 | 0 | Green |  |  |  | 214948 |  |  | 253000 | 210000 |  | 253000 | Phase | 463000 | 255647 | 210000 | 465647 | No | Green | 2022-04-01 | 2022-03-14 | 2022-03-14 | 2022-12-31 | 2022-09-27 |  |  |  | 4735 | 213.08 | [8 empty] | 210000 | [7 empty] | September 2022 - Project complete & Operational. July 2022 - Project scheduled to end August 6, 2022. Accrual $45K to Barr None. June 2022- Work stop to take care of small tank project at Marrero. Spend is at $209K May 2022 - Work in progress, invoicing is up to date. Accrue 40K to Barr None April 2022 - Work to begin early May February 2022 - Job walk completed with Barr-None coaters, preliminary quotes received for sections of facility piping to be painted. AFE approved by Kevin Burke, waiting on action item # 10253017 to be completed by Rob Geib prior to project start. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | Florida | BETQJ - BET JACKSONVILLE TERMINAL |  | 4948 | 210000 |  |  | 250699 |  | Geib, Rob | Jones, Kevin |  |  | 1 | 40520 |  | Guest, ProSight | Independent | Aqua | 2021-07-13 | Int - Accel Corr & FI
BETTK REK Dock Lines -Atmospheric Refurbishment 2022 | Item | Open | MCAP | BETTK00M2203 | Maintenance Framework | 2014042 | Wirfs, Mike | South | 7. Closed | Drawdown | Atmospheric Corrosion | 571 |  |  | 571.37 | 571 | 0 | Green |  |  |  | 571 |  |  | 16000 |  |  | 16000 | Full | 16000 | 15607 |  | 15607 | No | Green | 2022-12-01 | 2022-08-31 | 2022-08-31 | 2022-10-31 | 2022-12-30 |  |  | 571.37 | [18 empty] | 1/3/2023 - Project complete and ready to Close. 12/1/2022 - work delayed due to availability of man lift from recent hurricane events. 11/31/22 - Project delay due to rescheduling for Hurricane Ian. Work will be completed in November. Moved forecast to November. September 2022 - Resetting schedule with Barr None post Hurricane Ian. 9/6/22- Work scheduled to begin in Oct | 2023-01-04 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | Florida | BETTK - BET TAMPA |  | 571 | 0 |  |  | 15036 |  | Geib, Rob | Johnson, AJ |  |  | 1 | 45316 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Int - Planned Corr & FI
BETTK Replace Truck Rack Concrete 2022 | Item | Open | MCAP | BETTK00M2204 | Maintenance Framework | 2021909 | Campbell, William | South | 3. Active | Emergent | South |  | 250000 |  | 250000 | 500000 | -250000 | Red |  |  |  | 250000 |  |  | 250000 |  |  | 250000 | Full | 250000 | 62 | 250000 | 250062 | No | Green | 2022-12-01 | 2022-09-06 | 2022-09-06 | 2022-12-31 | 2023-02-28 | [6 empty] | 250000 | 250000 | -250000 | Red |  | Contractor/Vendor Issue | [5 empty] | 250000 |  |  |  | 5/1/23=Project delayed, getting more quotes 4/1/23-Project to begin this month 3/1/23-Met with leadership and plan finalized. Will complete supplemental when final quote is received. 1/1/23-Meeting next week with another contractor to get additional quote. Work expected to be completed in March '23. MC 12/1/22-Updated quote for 750K. 11/9/22-Forecast increased due to higher quotes. Supplemental will be done next week. 11/1/22-Forcast for October needs to be moved to December due to higher quote than originally proposed. Path forward is in discussions. 10/1/22-AFE approved, work to begin in October 9/1/22-AFE submitted. Work to be completed in October 8.29.22 AJ 250k for this emergent was pulled from south drawdown. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Florida | BETTK - BET TAMPA |  |  | 0 |  | 250000 | 62 |  | Johnson, AJ | Johnson, AJ |  |  | 1 | 45466 |  | Guest, ProSight | Independent | Aqua | 2022-08-29 | Other Programs
Birmingham Daylight Supply Piping Above Containment Dike | Item | Open | MCAP | BETGH00M2001 | Exempt | 1681200 | Leal, Trey (Tony) | South | 7. Closed | Defined | Facility Integrity | 6885 |  |  | 6884.77 | 6885 | 0 | Green |  |  |  | 6885 |  |  | 190000 | 354000 |  | 785000 | Phase | 785000 | 821123 |  | 821123 | No | Green | 2020-03-01 | 2020-02-14 | 2020-02-14 | 2021-09-30 | 2022-12-31 |  |  | 6469.43 | 415.34 | [17 empty] | 1/3/23- Project complete and all invoicing has been received. 10/24/2022 - Project ongoing, Pipe is being put on the racks. Tie ins and outages to occur during the two weeks following Thanksgiving 9/6/22- Project ongoing, expected completion date 11/30. 8/1/2022- Steel supports are being installed now. Will continue with pipe install once supports are done. Completion date expected to be 11/30. 7/5/2022 - Have approval to bring in 2023 scope into 2022 and complete project. Have adjusted forecast 6/1/2022- Work has kicked off. Looking to complete the project by 10/31 EAC 544k 5/4/2022 - Work is scheduled to begin May 23 and complete in October 4/5/2022 - PO has been issued. Working to schedule the work. Looking to start in early June. 2/28/2022 - Bids will be received by 3/4. Will work to schedule work, anticipating a May start date. Accrue $50k TPC Industrial 2/3/2022 - Engineering package has been completed. Working to bid out project. Bid walk 2/3. Will work to schedule work once bids are back 1/3/2022 - Piping has been received. Working to create package for bid. Will split into 2 scopes -civil/structural -piping 12/1/2021 - Piping order to be placed by end of week and will be delivered by the end of the year. Detail design is currently be finished and will aslo be complete by 12/31. 11/2/2021 - We decided to uncover a section of the piping to reinforce our decision to move forward. Looking to get a BOM by 11/12 to buy piping. 10/4/2021 - Updated guidance on phased approach is to submit an afe for 350k, spend 100k this year and 250k next year. Working to submit an AFE by 10/8. 9/13/2021 - This project will continue to be completed under a phased approach. The next phase will be to optimize the engineering design, buy materials, and pre fabricate the supports/piping. In 2023 we will complete the project with installation of piping/steel. 9/30/2020 - Bids for installation have been received. Email from Joel Bassani on 9/12 has questioned the path forward on this project. Will hold untildirection has been given. Direction is to hold project until further notice. Engineering drawings and Bids have been stored in BOX. 8/28/2020 - Bid walk is set for August 31. Will look to separate out this years budget approval amount from the quotes. 8/1/2020- Engineering has published IFR drawings for the final design.Review will take approximately1 week. Bid documents are ready for formal bid walks. Bidding process will take place late august. Procurement of steel pipe rack will follow. 6/30/2020 - Engineering Design is close to completion. Formal bid walks for installation are the next steps. Working oncompiling bid documents and vendors. 6/1/2020 - Engineering delayed due to TransMontaigne weighing the option of bringing their lines aboveground. Completion date for IFC package is 7/5. Wewill move forward with procurement afterpackage is issued. 5/4/2020 - Soil borings and surveys are complete. 60% design review scheduled forweek of 5/11. IFC package expected on 6/5. 3/31/2020 - Engineering has begun. Site survey and soil borings are schedule for week of 4/6. Engineering is expected to be complete early June. 3/3/2020 - Site walk with engineering and operations was held on 2/11. PO will be placed with engineering firmby 3/6. 2/2/2020 - Submitted AFE on 1/10. Site walk with engineering firm and operations will take place 2/11. 1/2/2020 - Scopedevelopment is on going | 2023-01-03 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | Alabama | BETGH - BET BIRMINGHAM |  | 6885 | 0 |  |  | 650093 |  | Aiken, Elaine | Burke, Kevin |  |  | 1 | 24647 |  | Administrator, System | Independent | Aqua | 2017-07-31 | Int - Planned Corr & FI
Birmingham South - Repair Goulds loading pump | Item | Open | MEXP | BSEVE00E2304 | Maintenance Framework | 2112954 | Pitkin, Colton | South | 3. Active | Drawdown | South |  | 15000 |  | 15000 |  | 15000 | Red |  |  |  | 15000 |  |  | 15000 |  |  | 15000 | Full | 15000 |  | 15000 | 15000 | No | Green | 2023-05-01 | 2023-04-28 | 2023-04-28 | 2023-12-31 | 2023-06-01 | [12 empty] | 15000 | [8 empty] | 5-4-2023 Pump at repair shop. Waiting on quote to cut PO. Buckeye tech will commision. | 2023-05-04 | Landeros, Melisa |  | South | Pipelines and Terminals | Station/Terminal |  | Alabama | BSEVE - BIRMINGHAM SOUTH TERMINAL |  |  | 15000 |  |  |  |  | Johnson, AJ | Defee, Daniel | N/A |  | 1 | 46999 |  | Johnson, AJ | Independent | Aqua | 2023-04-28
Birmingham South (BSEVE) Tank 1 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | BSEVE00E2301 | Maintenance Framework | 2085576 | Bryant, Ben | South | 3. Active | Defined | Tanks |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 |  |  | 11000 |  |  | 11000 | Phase | 11000 |  | 10000 | 10000 | No | Green | 2023-05-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-10-31 | [12 empty] | 10000 | [8 empty] | 5/1/23 Will move up due to having another tank needing inspection and to save on mobilization costs. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Tank Integrity |  | Alabama | BSEVE - BIRMINGHAM SOUTH TERMINAL |  |  | 10000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44781 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Birmingham South (BSEVE) Tank 2 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | BSEVE00E2302 | Maintenance Framework | 2085577 | Bryant, Ben | South | 3. Active | Defined | Tanks | 10000 |  |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 |  |  | 11000 |  |  | 11000 | Phase | 11000 | 10000 |  | 10000 | No | Green | 2023-04-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-04-30 | [5 empty] | 10000 | 10000 | 10000 | 0 | Green | [11 empty] | 5/1/23 Inspection completed. Accrue 10K to DJA. 4/3/23 Up Close seal inspection due by 4/30. Will work with operations to set a date for inspection. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Tank Integrity |  | Alabama | BSEVE - BIRMINGHAM SOUTH TERMINAL |  |  | 10000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44782 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Birmingham South (BSEVE) Tank 24 - Jet Cleaning Inspection | Item | Open | MEXP | BSEVE00E2303 | Maintenance Framework | 2085563 | Bryant, Ben | South | 5. Deferred | Defined | Tanks |  |  |  | 0 | 130000 | -130000 | Red | 130000 |  | 130000 | -130000 |  |  | 113850 |  |  | 113850 | Phase | 113850 |  | 130000 | 130000 | No | Green | 2024-06-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-07-31 | [21 empty] | 5/1/23 Tank removed from 2023 project list. 4/14/23-CES-Updated documentation allows this tank to be pushed to 2024. Reflecting this change by moving forecast to CY+1 and changing status to deferred. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Tank Integrity |  | Alabama | BSEVE - BIRMINGHAM SOUTH TERMINAL |  |  | 0 |  |  |  | 130000 | Stine, Carlton | Stine, Carlton |  |  | 1 | 44783 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Birmingham South (BSEVE): new video recorder | Item | Candidate | MCAP |  | Maintenance Framework |  | Magouirk, Josh | South | 1. Proposed |  | Security & Cameras |  | 15000 |  | 15000 | 15000 | 0 | Green | 15000 |  | 15000 | 0 | [9 empty] | 15000 | 15000 | No | Green | 2023-08-01 |  |  |  | 2023-02-28 | [15 empty] | 15000 | [9 empty] | South | Pipelines and Terminals | Operating Infrastructure |  | Alabama | BETGH - BET BIRMINGHAM |  |  | 0 | 15000 |  |  |  | Clark, Chris |  |  |  | 1 | 45145 |  | Guest, ProSight | Independent | Aqua | 2022-08-22 | Other Programs
Birmingham Terminal (BETGH) Tank 13 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | BETGH00M2301 | Maintenance Framework | 2094131 | Bryant, Ben | South | 8. Canceled | Defined | Tanks |  |  |  | 0 |  | 0 | Green | 832559 |  | 832559 | -832559 |  |  | 342160 |  |  | 342160 | Phase | 342160 |  |  |  | No | Green |  | 2023-01-24 | 2023-01-24 | 2023-12-31 | 2023-04-30 | [21 empty] | 2/13/23-CES-Per BECHT RBI report, tank can be pushed back to 2027. Removing forecast and cancelling project. 2/1/23 This project has been postponed due to commercial requests. This project is expected to start in second quarter. | 2023-02-13 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | Alabama | BETGH - BET BIRMINGHAM |  |  | 0 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44784 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
BMTUA - Marrero Comms Repairs | Item | Open | MEXP | BMTUA00E2204 | Maintenance Framework | 1970506 | Corman, Chris | South | 7. Closed | Drawdown | South | 1090 |  |  | 1090.05 | 1090 | 0 | Green |  |  |  | 1090 |  |  | 13000 |  |  | 13000 | Full | 13000 | 12090 |  | 12090 | No | Green | 2022-11-01 | 2022-04-07 | 2022-04-07 | 2022-05-31 | 2022-10-13 |  |  | 1090.05 | [18 empty] | 3/2/2023 - Invoicing Complete project ready to close. 1/3/23- Re-accrue 11k to bearcom 12/5/2022 - Accrue 11k to bearcom 11/1/2022 - Equipment installed. Awaiting invoicing. 10/3/2022 - Equipment shipped on 9/30. Programming and installation planned in Oct/November. 8/29/2022 - Request to add contractor in Coupa has not been approved since June. 7/26/2022 - Contractor delays, project to start in Sept 6/1/22- PO has been submitted, work to begin July | 2023-03-02 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | Marrero | BMTUA - Marrero Terminal |  | 1090 | 0 |  |  | 11000 |  | Johnson, AJ | Asiedu, Saka |  |  | 1 | 43340 |  | Guest, ProSight | Independent | Aqua | 2022-04-05 | Other Programs
BMTUA Marrero East Dock Hose Rack Repairs | Item | Open | MEXP | BMTUA00E2211 | Maintenance Framework | 2011759 | Bryant, Ben | South | 6. Operational | Drawdown | South | 21634 |  |  | 21633.7 | 22428 | -794 | Yellow |  |  |  | 21634 |  |  | 107000 |  |  | 107000 | Full | 107000 | 72384 |  | 72384 | No | Green | 2022-09-01 | 2022-08-08 | 2022-08-08 | 2022-12-31 | 2023-01-31 |  |  | 30500 | -7000 | -1072.5 | -793.8 |  |  | -794 | Red | [11 empty] | 5/3/23 Accrue 4K to Lloyds Engineering. 4/3/23 Accrue 4K to Lloyds Engineering 3K to CATSI. 3/123 Change Order has been sent for Stewart Engineering. Awaiting Invoicing. Accrue $4K to Lloyds Engineering, $3K to Catsi and $63k to Stewart Construction. 2/1/23 Contractor has completed work on East Dock. Awaiting invoicing. Accrue 5K to Lloyd Engineering and 3K to Catsi Accrue 69K to Stewart Engineering 1/2/23 Contractor will begin work following Corp work being done in Marrero. Will accrue all material costs for Stewart Engineering for 2022. Accrue 6500 to Lloyd Engineering and 40K to Stewart Construction 12/9/22 Construction bids have been awarded. Contractor will start work the week of Dec. 26th. Will move 38K to next year. 12/1/22 Project will start and complete this month. Reviewing Construction Bids. 11/1/22 Lloyd's Engineering has completed BiD Design. Accrue 6,500 to Lloyd Engineering. We will go out for bids to compete design work. 10/3/22 Lloyd's Engineering are 90% complete with BID design. Expect to receive formal package the week of Oct. 10th. 9/1/22 Lloyd's Engineering has begun designing an East Dock Design to withhold the hoses of the dock. The design will then go out for bid for construction. 8/1/22 Project has been approved at AFE Meeting. AFE currently in Routing Process. 7/1/22 AFE will be crafted to award contractor with work. 6/1/22 Requested bids for design from two contractors. 4/1/2022 - Target AFE submission date of 4/17. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | Marrero | BMTUA - Marrero Terminal |  | 22428 | -794 |  |  | 50750 |  | Johnson, AJ | Asiedu, Saka |  |  | 1 | 43301 |  | Guest, ProSight | Independent | Aqua | 2022-03-30 | Other Programs
BTH 115 Series 20" Valve Replacement | Item | Open | MCAP | BTXHF00M2215 |  | 2037459 | Matthews, Clayton | South | 6. Operational | Emergent | Valves | 3824 |  |  | 3823.53 | 3824 | 0 | Green |  |  |  | 3824 |  |  | 157000 |  |  | 157000 | Full | 157000 | 144929 |  | 144929 | No | Green | 2022-10-01 | 2022-10-20 | 2022-10-20 | 2022-10-24 | 2022-10-21 |  |  | 3242.56 | 580.97 | 0 | 0 |  |  | 0 | Green | [11 empty] | 5.2.23 ML Re-Accrue 1k ACTT, 10k Ohmstede, 5k PBI, 3.5k TNT 4.5.23 ML Re-Accrue 1k ACTT, 10k Ohmstede, 5k PBI, 3.5k TNT 3.3.23 CAM Re-Accrue 1k ACTT, 10k Ohmstede, 5k PBI, 3.5k TNT 2.2.23 ML Re-Accrue 1k ACTT, 10k Ohmstede, 5k PBI, 3.5k TNT 1/4/23 CAM Re accrue all prior 12/5/22 CAM Incorrect 150K Forecast discovered for 2023. This has been removed. 12/2/22 CAM Re Accrue 1,000 ACTT, Re Accrue 10k Ohmstede, Re Accrue 47K Vapor Point, Accrue 3500 TNT, Maintenance reclass for valves?? 11.3.22 ML Accrue 47k Vapor Point, 9k TNT, 10k Ohmstede,1000 ACTT, 5k PBI AFE approved Mid-October incurred October 20th. 10/21/22 CAM Field work complete. Accrue 47k Vapor Point, 9k TNT, 10k Ohmstede,1000 ACTT, 5k PBI Reclass all costs from maintenance work order 2013958 (60k valves) | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 3824 | 0 |  |  | 141105 |  | Oey, Alex | Oey, Alexander |  |  | 1 | 46005 |  | Meitzler, Antoinette | Independent | Aqua | 2022-10-06 | Other Programs
BTH West VCU UPGRADES | Item | Open | MCAP | BTXHF00M2106 | Maintenance Framework | 1902987 | Corman, Chris | South | 7. Closed | Emergent | Vapor Management | 5579 |  |  | 5579.04 | 5579 | 0 | Green |  |  |  | 5579 |  |  | 138000 |  |  | 138000 | Full | 138000 | 100533 |  | 100533 | No | Green | 2021-11-01 | 2021-11-16 | 2021-11-16 | 2021-12-31 | 2022-09-30 |  |  | 4174.82 | 187.87 | 1216.35 | [16 empty] | 11/1/2022 Final invoices have been received. Project can be closed. 10/4/2022 Re-accrue 21k Knight 9/6/2022 - Re-accrue 21k Knight 8/1/2022 - Re-accrue 21k Knight 7/5/2022 - Re-accrue 21k Knight and 21K Zeeco 5/31/2022 - All parts expected to arrived by 6/30. Will work to schedule maintenance to install once parts are received. Re-accrue 21k Knight and 21K Zeeco 3/1/2022 - Zeeco parts still have not been received. Still waiting on Knight Industrial invoicing. Accrue $21k to Zeeco, $21k Knight Ind. 2/3/2022 - Zeeco parts mid February, Installation will be coordinated once received. 1/1/2022 - Refractory and rigidizer installed. At completion of original refractory install, inspection identified numerous issues with installation. Knight was instructed to remove all new refractory and correct issues with pins. VCU placed back in service using spare equipment. New blower fan installed. Still waiting on delivery of new Zeeco parts. Installation will be coordinated with operations once received. 12/1/2021 - Damaged refractory removed as well as old pins and keepers. NDE on metal stack completed with no new issues discovered. New refractory installation completed as of 12/1. Zeeco order placed. Rigidizer order placed. 11/1/2021 - Full AFE to be presented 11/4. Funding source still needs to be identified. PO issued to Knight to begin demo work. 10/20/21 - Interim AFE requested on 10/20. Full AFE development underway. | 2022-11-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 5579 | 0 |  |  | 37228 |  | Karl, Marissa | Burke, Kevin |  |  | 1 | 42342 |  | Guest, ProSight | Independent | Aqua | 2021-10-19 | Other Programs
BTP Tank 1002 Tank Cleaning and Steel IFR Installation | Item | Open | MCAP | BTXPP00M2304 | Maintenance Framework | 2084418 | Matthews, Clayton | South | 2. Pending AFE |  | Tanks | 1070675 | 325000 |  | 1395674.66 | 1518474 | -122799 | Yellow |  |  |  | 1395675 | [6 empty] | Interim |  | 1070675 | 325000 | 1395675 | No | Green | 2023-02-01 |  |  |  | 2023-06-30 |  |  |  | 130000 | 413473.88 | 527200.78 | 500000 | 500000 | 27201 | Yellow |  |  | 200000 | 100000 | 25000 | [6 empty] | 5/2/23 CAM Accrue 22k ATP, 1378 Gainco, 1k JM Supply, 7009 Knight, 8253 National Tank, 1623 Pro-Surve, 1451 Select Safety, 200k Tarsco, 6486 UPS, 241444 Vapor Point 4.5.23 ML Accrue 11.2k ATP, 2k Gainco, 9k Knight, 360k Tarsco, 3k UPS, 145K Vapor 3.3.23 CAM Accrue 30K Vapor point, Accrue 100K Vaporpoint/LH 1/25/23-CES-New Project for 2023. Steel IFR Replacement. Forecast $1.5MM. Funding from Tank Capital Improvements Program. | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 543474 | 827201 | 25000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46534 |  | Stine, Carlton | Independent | Aqua | 2023-01-24 | Int - Tanks
BTP Tank 1004 IFR Inspection and Repair | Item | Open | MCAP | BTXPP00M2227 | Maintenance Framework | 2037864 | Matthews, Clayton | South | 3. Active | Drawdown | Tanks | 1123377 | 350000 |  | 1473377.35 | 1059017 | 414361 | Red |  |  |  | 1473377 |  |  | 502000 |  |  | 502000 | Full | 502000 | 1617058 | 350000 | 1967058 | Yes | Red | 2022-11-01 | 2022-10-25 | 2022-10-25 | 2023-04-15 | 2023-05-15 |  |  | 63916.85 | 306183.04 | 468916.73 | 284360.73 | 220000 | 220000 | 64361 | Red |  |  | 175000 | 150000 | 25000 | [6 empty] | 5/2/23 CAM Accrue 2143 Adler, Re-Accrue 15k FHG, re accrue 18K KAR engineering, 3763 PBI, re accrue 1.2k ProSurve, 4150k Tarsco, re accrue 285k WM 4.5.23 ML 1k Adler, 4k Applied, Re-Accrue 15k FHG, accrue 18K KAR engineering, 10k PBI, 1.2k ProSurve, 450k Tarsco, 6.9k UPS, 285k WM 3.3.23 CAM Discussions underway with senior leadership on potential bottom replacement (PHMSA driven) forecast will be updated when decision is made, potential for 500K adder. Accrue 1K adler, accrue 7200 ATP, accrue 175300 Eisco, accrue, 15K FHG, accrue 18K KAR engineering, accrue, 3100 PBI, accrue 25K Tarsco, accrue 6K UPS, accrue WM 2.2.23 ML - Accrue 18k Adler, 10k ATP, 13.3k Applied, 150k EISCO, 1.1k Lk Jordan, 2k National, 5.5k PBI, 2.7k Select Safety, 54.9k 3L, 6k UPS, 89.5k Vapor, 125k WM CAM No january forecast changes at direction of management due to scope development and leadership decision on path forward. See below note. Feb/March forecast updated. 1/25/23-CES-Updating forecast to $1MM per PM estimated cost and agreement with leadership to replace IFR with new steel IFR. Funding from tank capital improvements program. 1/11/23 CAM No changes to forecast. Keeping as is at the direction of Tank Program Manager and Maintenance Manager. Forecast will be updated shorty upon approval of maintenance plan. 1/4/23 CAM Accrue 23K Adler, 13500K ATP, 10K Applied Consultants, 14320 PBI, 29K 3L, 7k UPS, 150K Eisco, 89K Vapor Point, 125K WM, 15K FHG, 2k National equipment, 8800 HPC 12/2/22 CAM Accrue 15K Adler, 5K ATP, 5K Applied Consultants, 7500 PBI, 29K 3L, 120K Eisco, 25KVapor Point, 125K WM, 15K FHG 10/28/22 CAM 20,000 Designated for additional STX safety rep. 10/21/22 CAM AFE submitted. Forecast adjusted to include bulk of cleaning costs in November. | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 839017 | 609361 | 25000 |  | 493681 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46096 |  | Guest, ProSight | Independent | Aqua | 2022-10-20 | Int - Tanks
BTP Tank 2004 IFR Inspection and Repair | Item | Open | MCAP | BTXPP00M2228 | Maintenance Framework | 2037892 | Matthews, Clayton | South | 6. Operational | Drawdown | Tanks | 514656 | 35000 |  | 549655.58 | 480332 | 69324 | Red |  |  |  | 549656 |  |  | 268000 |  |  | 268000 | Full | 268000 | 630336 | 35000 | 665336 | Yes | Red | 2022-12-01 | 2022-10-25 | 2022-10-25 | 2023-04-15 | 2023-03-31 |  |  | 25177.25 | 142078.33 | 313076.16 | 34323.84 |  |  | 34324 | Red |  |  | 35000 | [8 empty] | 5/2/23 CAM Accrue 4516 Adler, Accrue 18k ATP, 2.5k PBI, accrue 5016 UPS 4.5.23 ML Re-Accrue 2.7k Adler, 2.5k PBI, 376k Phillips Tk, 16k WM Variance - Growth of PTS scope is substantial to original Pontoon. 3.3.23 CAM Potential for scope change based on discovery work once IFR work started. Pontoon replacement costs will drive total EAC. Forecast to be updated when inspection/testing is completed. Accrue 2783 Adler, accrue 7500 ATP, accrue 13540 DJA, accrue103000 Eisco, accrue2500 PBI, accrue 100K Phillips tank, 2.2.23 ML- Accrue 2.7k Adler, 9.6k Applied, 13.5k DJA, 75k EISCO, 2.5k PBI, 15k WM CAM No january forecast changes at direction of management due to scope development and leadership decision on path forward. See below note. Feb/March forecast updated with best assumptions pending scope finalization. 1/25/23-CES-Updating Forecast to $400,000 per agreement with PM and AIFR repair plan. Funding from tank capital improvements program. 1/11/23 CAM Keeping as is at the direction of Tank Program Manager and Maintenance Manager. Forecast will be updated shorty upon approval of maintenance plan. 1/4/23 CAM Accrue 14k ATP, Accrue 9680 Applied Consultants, Accrue 75K Eisco, Accrue 2k UPS, Accrue 15k WM 12/5/22 CAM Project kickoff date pending with customer. 10/28/22 CAM 10,000 Designated for additional STX safety rep. 10/21/22 CAM AFE submitted. Forecast adjusted to include bulk of cleaning costs in November. | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 480332 | 69324 |  |  | 115680 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46099 |  | Guest, ProSight | Independent | Aqua | 2022-10-20 | Int - Tanks
BTP Tank 3003 IFR Inspection and Refurb | Item | Open | MCAP | BTXPP00M2229 | Maintenance Framework | 2038111 | Matthews, Clayton | South | 6. Operational | Drawdown | Tanks | 498431 |  |  | 498431.23 | 467183 | 31249 | Yellow |  |  |  | 498431 |  |  | 318000 |  |  | 318000 | Full | 318000 | 800574 |  | 800574 | Yes | Red | 2022-11-01 | 2022-10-28 | 2022-10-28 | 2023-04-15 | 2023-03-31 |  |  | -7668.6 | 213208.86 | 226642.45 | 66248.52 | 35000 | 35000 | 31249 | Red | [11 empty] | 5/2/23 CAM Accrue 20k ATP, 2.8k PBI, 39145 Phillips Tk, re accrue 43k WM, accrue 5210 UPS 4.5.23 ML Accrue 4.2k ATP, 2.8k PBI, 391k Phillips Tk, 43k WM 3.3.23 CAM Forecast adjusted to accommodate growth of original scope. Accrue 6500 ATP, 190K Phillips tank, 55K waste management 2.2.23 ML - Accrue 20k Adler, 3k ATP, 8k Applied, 4k National, 5k PBI, 53.9k Vapor, 55k WM CAM No january forecast changes at direction of management due to scope development and leadership decision on path forward. See below note. Feb/March forecast updated with best assumptions pending scope finalization. 1/25/23-CES-Updating forecast to $325,000 per direction of the PM and agreement with plan to repair AIFR. Funding from tank capital improvements program.1/11/23 CAM No changes to forecast. Keeping as is at the direction of Tank Program Manager and Maintenance Manager. Forecast will be updated shorty upon approval of maintenance plan. 1/4/23 CAM Accrue 22k Adler, Accrue 16400 ATP, Accrue 10k Applied Consultants, Accrue 102K Eisco, Accrue 4000 National tank and equipment, Accrue 14500 PBI, Accrue 11300 UPS, accrue 53900 Vapor Point, Accrue 55k Waste Management 12/2/22 CAM Accrue 18K Adler, 5K ATP, 2K Applied COnsultant, 92K Eisco, 9500, PBI, 9K UPS, 25K Vapor Point, 35K WM 10/28/22 CAM 10,000 Designated for additional STX safety rep. 10/21/22 CAM AFE submitted. Forecast adjusted to include bulk of cleaning costs in November. | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 432183 | 66249 |  |  | 302143 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46097 |  | Guest, ProSight | Independent | Aqua | 2022-10-20 | Int - Tanks
BTXHF - 115 Series High Level Switches Phase I | Item | Open | MCAP | BTXHF00M1610 | Exempt | 1217085 | Burke, Joshua | South | 7. Closed | Emergent | Instrumentation & Controls | -14314 |  |  | -14314.42 | -14314 | 0 | Green |  |  |  | -14314 |  |  | 36000 |  |  | 36000 |  | 36000 | 0 |  | 0 | No | Green |  | 2016-06-02 | 2016-06-02 | 2016-08-29 | 2017-08-31 |  |  |  |  | -14314.42 | [16 empty] | 5/1/2021 - Project complete, waiting on property accounting to close, invoicing finalized 05/02/2016 PM will begin Scope of Work later in Q3 6/28/16 Project has been scoped and waiting on proposals from engineering firms. Engineering to begin in July. Full AFE will be submitted once engineering is complete. 11/8/19 - SF - No activity. | 2022-03-24 | Fogg, Sherry |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | -14314 | 0 |  |  |  |  | Forsey, Frank | Collings, B Lewis, Jr |  |  | 1 | 16606 |  | White, Julie | Independent | Aqua | 2015-09-15
BTXHF - Add valve on storm water ditch by Mississippi Sands building | Item | Open | MCAP | BTXHF00M2210 | Maintenance Framework | 1991324 | Garcia, Monica | South | 7. Closed | Defined | Secondary Containment | -4000 |  |  | -4000 | -4000 | 0 | Green |  |  |  | -4000 |  |  | 42000 |  |  | 42000 | Full | 42000 | 25875 |  | 25875 | No | Green | 2022-07-01 | 2022-06-21 | 2022-06-21 | 2022-12-31 | 2022-08-17 |  |  | -4000 | [18 empty] | 2/2/23 MLG: WO closed, Project Closed. 12.5.22 ML Work is Complete - awaiting final invoicing 11/2/22 MLG: variance is a savings from an AFE estimate; awaiting final invoices 10/4/22 MLG: variance is a savings from an AFE estimate; awaiting final invoices 9/13/22 MLG-installation is complete; awaiting final invoices. 8/2/22 MLG: - Variance due to delay in AFE approval and the lead time for valves; forecast shifted to August. Valves on order and should arrive the week of 8/1/22. 1/4/22 MLG-Project scope of work development will occur in January. | 2023-02-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | -4000 | 0 |  |  | 29875 |  | Clark, Dave | Asiedu, Saka | N/A |  | 1 | 31520 |  | Kabaria, Erika | Independent | Aqua | 2018-08-29 | Other Programs
BTXHF - Asphalt Pump Seal Upgrade | Item | Open | MCAP |  | Maintenance Framework |  | Garcia, Monica | South | 1. Proposed |  | Storm Water Management |  | 75000 |  | 75000 | 75000 | 0 | Green | 75000 |  | 75000 | 0 | [9 empty] | 75000 | 75000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 75000 | [6 empty] | 4/4/23 MLG: Reliability still working on the various types of seals and what will work best for this application. 3-1-23 MLG: Working with Reliability and Ops to determine the appropriate seal upgrade, due to various types of seal failures. 2/2/23 MLG: In scope development, using information from other seal upgrades to determine this seal upgrade. | 2023-04-04 |  |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  |  | 0 | 75000 |  |  |  | Bonenberger, Mark |  |  |  | 1 | 41911 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Other Programs
BTXHF - Boiler Discharge Engineering & Construction | Item | Open | MCAP | BTXHF00M2303 | Maintenance Framework | 2095087 | Burke, Joshua | South | 3. Active | Defined | Storm Water Management | 30125 | 105000 |  | 135125 | 140000 | -4875 | Yellow | 145000 |  | 145000 | -9875 |  |  | 33599 |  |  | 33599 | Phase | 33599 | 30125 | 105000 | 135125 | No | Green | 2023-03-01 | 2023-03-15 | 2023-03-15 | 2023-10-31 | 2023-07-31 |  |  |  |  | 25000 | 5125 | 10000 | 10000 | -4875 | Red |  |  |  | 30000 | 40000 | 35000 | [5 empty] | 5.3.23 JHB - Testengeer has completed FEL 1 and delivered their report. They are developing a FEL 2 proposal. Phase 2 AFE to be developed pending proposal and review of scope/TIC. Adjusting forecast to reflect anticipated timing. Accrue $29k to Testengeer. 4.3.23 JHB - Testengeer has largely completed FEL 1 engineering and is developing their report. Next phase engineering to be executed late April/early May. Accrue $25k to Testengeer. FC adjusted to allow time for FEL 2 initiation. 3.1.23 JHB - AFE development in progress. Adjusting forecast based on anticipated spend curve. 2.1.23 JHB - Initial engineering walkdown complete, Testengeer developing FEL 1 proposal. Moved FEB forecast to March based on anticipated proposal receipt/AFE generation. | 2023-05-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 25000 | 35125 | 75000 |  |  |  | Bonenberger, Mark | Johnson, AJ |  |  | 1 | 45558 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
BTXHF - Butane Rail Offloading | Item | Open | MCAP | BTXHF00M2302 | Maintenance Framework | 2094856 | Burke, Joshua | South | 3. Active | Defined | South | 312264 | 220000 | 45000 | 532263.6 | 528424 | 3839 | Yellow |  |  |  | 532264 |  |  | 565063 |  |  | 565063 | Full | 565063 | 312264 | 265000 | 577264 | No | Green | 2023-03-01 | 2023-04-12 | 2023-04-12 | 2023-05-19 | 2023-05-31 |  |  |  |  | 108424.42 | 203839.18 | 200000 | 200000 | 3839 | Yellow |  |  | 220000 | [7 empty] | 45000 | 5.3.23 JHB - Full AFE approved. Hoses and ESVs have been received, platforms on track for 5/15 delivery. Mechanical civil work ~80% complete. Electrical work ~60% complete. Final welding and boltup to complete week of 5/8 and platform setting/final installation on platform to complete week of 5/15. Accrue $40k to Benko, $6k to CC Electric, $40k to Eriks, $27k to HST, $5k to Knight, $62k to UPS, and $25k to Zadok, $5k to LK Jordan. 4.3.23 JHB - Full AFE submission pending. All long lead equipment has been ordered. Civil installation is nearing completion - all pier locations have been excavated and concrete prep is underway. Piping is 100% pre-coated and shop welding has begun. Accrue $5k to Benko, $10k to Eriks, $6k to Hose of ST, $14k to JM Supply, $13k to Knight, $12k to PBI, $20k to UPS, 8k to Sky Eye. Additional FC of 65k added to May based on Full AFE total - $45k placed in contingency. | 2023-05-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 108424 | 423839 |  |  |  |  | Johnson, AJ | Johnson, AJ |  |  | 1 | 46696 |  | Burke, Joshua | Independent | Aqua | 2023-03-03
BTXHF - Dock 3 Mooring Refurbishment | Item | Open | MEXP | BTXHF00E2210 | Project Framework | 2051601 | Burke, Joshua | South | 7. Closed | Defined | Marine | -39 |  |  | -38.9 | -39 | 0 | Green |  |  |  | -39 |  |  | 18000 |  |  | 18000 | Full | 18000 | 14961 |  | 14961 | No | Green | 2022-12-01 | 2022-12-05 | 2022-12-05 | 2022-12-31 | 2022-12-30 |  |  | -4527.23 | 4488.33 | [17 empty] | 3.1.23 JHB - ready to close 2.1.23 JHB - ready to close pending final invoicing. Re-Accrue 4k Knight 1.4.23 JHB - Recoating complete, accrue $15k to Knight 12.1.22 JHB - AFE routing for approval, plan to execute mooring fixture refurbishment in December. 10.3.22 JHB - onsite coating contractor Knight reviewing corrosion on mooring bollards and providing proposal to recoat in December. 9.1.22 JHB - moved funds to December. Limited bandwidth to identify and execute. 7.1.22 JHB - moved funds to September 4.28.22 JHB - Funds moved to August. 3.1.22 JHB - Funds moved to June to allow time to identify if any remaining fixture refurbishment is required or alternate repairs can be conducted using funds. 1.31.22 JHB - Dock 3 fixtures cleaned & recoated in 2021 with available MEXP dollars. | 2023-03-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | -39 | 0 |  |  | 15000 |  | Spari, Markella |  |  |  | 1 | 37942 |  | Guest, ProSight | Independent | Aqua | 2020-08-13 | Marine
BTXHF - Facility Painting | Item | Open | MCAP | BTXHF00M2209 | Maintenance Framework | 2002854 | Garcia, Monica | South | 6. Operational | Defined | Facility Painting | 15194 |  |  | 15194.11 | 13330 | 1864 | Red |  |  |  | 15194 |  |  | 166000 |  |  | 166000 | Phase | 166000 | 153389 |  | 153389 | No | Green | 2022-07-01 | 2022-07-13 | 2022-07-13 | 2022-12-31 | 2022-12-30 |  |  | 13733.7 | -6775.34 | 6371.38 | 1864.37 |  |  | 1864 | Red | [11 empty] | 2/2/23 MLG: Awaiting invoices. 1/4/23 MLG: Dock 3 painting update as follows: 6" Naphtha Line - 100% complete; 3" Natural Gas Line - 100% complete 16" Naphtha Line - 100% complete 8" Butane Line - 100% complete 4" Butane Vapor Line - 100% complete Additional painting to Dock 1 loading arms area was started. 12/5/22 MLG: Variance is due to difficulty scheduling work in conjunction with vessel schedules, in addition to weather delays. Painting on Dock 1 has been initiated in order to supplement down time. Dock 3 painting update as follows: 6" Naphtha Line - 100% complete; 3" Natural Gas Line - 85% complete 16" Naphtha Line - 75% complete 8" Butane Line - 80% complete 4" Butane Vapor Line - 40% complete 11/3/22 MLG: Painting update as follows: 6" Naphtha Line - 100% complete; 3" Natural Gas Line - 80% complete 16" Naphtha Line - 60% complete 8" Butane Line - 80% complete 4" Butane Vapor Line - Not Yet Started 10/4/22 MLG: variance is due to schedule conflicts with the dock and the loading of the vessels versus the ability to perform the work.at that time. 9/1/22 MLG: The forecast variance is due to schedule conflicts with the dock and the loading of the vessels versus the ability to perform the work.at that time. 8/2/22 MLG: Forecast variance was due to delay in AFE approval. Work commenced 7/14/22. 2/1/22 MLG: Scope development will occur in February. | 2023-03-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 13330 | 1864 |  |  | 138195 |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 20509 |  | Guest, ProSight | Independent | Aqua | 2016-08-22 | Int - Planned Corr & FI
BTXHF - HUB Boiler Replacement - MCAP | Item | Open | MCAP | BTXHF00M2205 | Maintenance Framework | 1946262 | Corman, Chris | South | 3. Active | Defined | Boilers | 394864 | 150000 |  | 544863.91 | 382795 | 162069 | Red |  |  |  | 544864 |  |  | 864000 |  | 449000 | 1313000 | Supplemental | 1313000 | 1267538 | 150000 | 1417538 | Yes | Red | 2022-02-01 | 2022-02-07 | 2022-02-07 | 2022-12-31 | 2023-03-31 |  |  | 51879.03 | 56331.08 | 74584.59 | 212069.21 | 50000 | 50000 | 162069 | Red |  |  | 150000 | [8 empty] | 3/2/2023 Project is nearing completion. PSSR is scheduled for this week. Commissioning will follow 1/3/23- Re-Accrue 25k HGA, UPS $25k, Accrue $24k to Western Oilfield Supply. 12/5/22- Re-Accrue 25k HGA. Accrue $25k to UPS Industrial. Boiler piping is 80% installed, electrical will finish week of 12/12. 11/1/2022 - Boiler has been set an now working on installation. Expected to complete mechanical install nov 23. 10/4/2022 - Boiler is expected to be on site 10/7. We will proceed with install. Expect to complete by the end of November. Moved 75k to December. 8/1/2022 - Bids are expected by 8/12. Boiler still on track to arrive in late September 7/5/2022 - Working to bid out install of the boiler. Boiler is expected to arrive in late September 6/1/2022 - Boiler has be receipted in JDE at full cost. Demo of old boiler has begun. Putting together estimate for final phase. 5/4/2022 - Drawings have been approved and the Boiler is to Begin Fabrication. Accrue 120k to Cleaver Brooks 4/5/2022 - Received the first set of drawings for the boiler. NG line tie will take place today 4/5. Working to schedule the demo of the boiler. Variance due to reclass from CASLOSS project 2/28/2022 - PO was placed on 2/17. Working to schedule Natural Gas demo and Boiler removal. New Boiler is expected in August. 2/2/2022 - Waiting for funding to place PO for Boiler. Will work on scheduling NG tie in and old boiler removal 2/2/2022 - AFE was submitted. Waiting for funding to place PO for boiler. | 2023-03-02 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 182795 | 362069 |  |  | 872675 |  | Stine, Carlton | Asiedu, Saka |  |  | 1 | 42837 |  | Guest, ProSight | Independent | Aqua | 2022-01-31 | Other Programs
BTXHF - Qualtech Backpressure control valve | Item | Open | MCAP | BTXHF00M2213 | Maintenance Framework | 2023709 | Burke, Joshua | South | 6. Operational | Emergent | Valves | 63034 |  | 0 | 63034.42 | 56446 | 6588 | Red | 60000 |  | 60000 | 3034 |  |  | 90000 |  |  | 90000 | Full | 90000 | 97534 | 0 | 97534 | No | Green | 2022-11-01 | 2022-09-26 | 2022-09-26 | 2023-01-31 | 2023-03-16 |  |  | 5325.06 | 15402.03 | 28719.28 | 13588.05 | 7000 | 7000 | 6588 | Red | [10 empty] | 0 | 5.3.23 JHB - Project complete, ready for closeout once final invoicing received. Reaccrue $7k to Applied consultants, $5k to Knight, and $10k to UPS. 4.3.23 JHB - Valve installed, tested, ready for turnover to Operations. Accrue 9k to B&E, $5k to Knight, $2k to LK Jordan, $12k to UPS, and $5k to Applied Consultant. Forecast of $7k added to April for Safety Coordinator billing. 3.1.23 JHB - Material received, spool pieces in fabrication, conduit and cable partially pulled. Accrue $6k to JM supply, $8k to UPS, $6k to B&E. Not sure where $5k FEB accrual came from - this is an error. Variance due to minor schedule delays - remaining FC based on aniticpated spend placed in March. Excess funds placed in contingency. 2.1.23 JHB - Tomohawk fault identified as water intrusion damage to board. Puffer replacing board under warranty. Contractors engaged to bid mechanical scope. Targeting late FEB for installation with potential to push to March. 1.4.23 JHB - valve selected for this application is same style that was installed in DEC on Tomohawk - the valve has experienced a fault issue. Installation is postponed until fault issue has been root caused and Operations is comfortable with installation. Moving FC to FEB. 12.1.22 JHB - control valve received, planning installation for January. Accrue $30k to Puffer. 11.1.22 JHB - Valve on order, expected mid-late November. Installation planned for January 2023. 10.3.22 JHB - AFE approved, valve to be ordered week of 10/3. 9.21.22 JHB - adjusted forecast to $30k in 2022 and $60k in 2023. Valve will be purchased this year and installed next year. 9/12/22 AJ: moved 90k into q4 this year. This project will be funded from MCAP drawdown | 2023-05-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 49446 | 13588 |  |  | 34500 |  | Oey, Alex | Johnson, AJ |  |  | 1 | 45568 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
BTXHF - Secondary containment upgrades 2023 | Item | Open | MCAP | BTXHF00M2304 | Maintenance Framework | 2110561 | Dalton, James | South | 3. Active | Defined | Secondary Containment | 35000 | 150000 |  | 185000 | 180000 | 5000 | Yellow | 180000 |  | 180000 | 5000 |  |  | 84066 |  |  | 84066 | Phase | 84066 | 35000 | 150000 | 185000 | No | Green | 2023-04-01 | 2023-04-12 | 2023-04-12 | 2023-12-31 | 2023-07-31 | [5 empty] | 35000 | 30000 | 30000 | 5000 | Red |  |  | 20000 | 10000 | 30000 | 40000 | 40000 | 10000 |  |  |  | 4.3.23 JHB - AFE routing for approval, Diamond Z targeting mid-April for site visit. Adjusting forecast based on James Dalton support cost. 3.1.23 JHB - James Dalton preparing AFE Documents. Adjusting forecast based on anticipated spend curve 2.1.23 JHB - Proposal for phase 1 engineering design received from Diamond Z. Developing AFE documents. | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  |  | 65000 | 110000 | 10000 |  |  | Clark, Dave | Johnson, AJ |  |  | 1 | 45162 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
BTXHF - Supports for transfer lines from BTXPP | Item | Open | MCAP |  | Maintenance Framework |  | Garcia, Monica | South | 1. Proposed |  | Facility Integrity |  | 120000 |  | 120000 | 120000 | 0 | Green | 120000 |  | 120000 | 0 | [9 empty] | 120000 | 120000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 42000 | 78000 | [5 empty] | 3-1-23 MLG: a meeting is tentatively scheduled for mid-March in order to develop scope of work and plan of action. 2/2/23 MLG: Tentatively scheduled for scope development in mid-to-late February. | 2023-03-01 |  |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  |  | 0 | 120000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45533 |  | Administrator, System | Independent |  | 2022-08-29 | Int - Planned Corr & FI
BTXHF - Tomohawk Backpressure control valve | Item | Open | MCAP | BTXHF00M2214 | Maintenance Framework | 2035971 | Burke, Joshua | South | 6. Operational | Emergent | Valves | 5685 |  |  | 5685.47 | 5685 | 0 | Green |  |  |  | 5685 |  |  | 100000 |  |  | 100000 | Full | 100000 | 124739 |  | 124739 | Yes | Red | 2022-11-01 | 2022-10-03 | 2022-10-03 | 2022-12-02 | 2022-12-15 |  |  | 5572.45 | -708.05 | 821.07 | [16 empty] | 4.3.23 JHB - supplemental/ECO to be completed. 3.1.23 JHB - Supplemental/ECO required. Ready to close pending supplemental and final invoicing. Re-accrue $49k to B&E. 2.1.23 JHB - valve repaired under warranty. Work complete, ready to close pending final invoicing. Accrue $64k to B&E. 1.4.23 JHB - valve installation complete during second attempt. Valve currently in fault and technician scheduled to identify root cause, potential for incremental spend depending on issue. Accrue $64k to B&E, $5k to PBI, $2k to LK Jordan, $2k to Sentinel. Variance due to failed first attempt at installation due to Ops unable to clear line plus standby time on second attempt due to slow de-inventory. 12.1.22 JHB - Valve received, contractor on site for installation 11/30. Operations unable to isolate and turn over line due to leaking valve. Work deferred pending revised isolation plan. Contingency will be used to cover change orders associated with standby/delays. Accrue $30k to Puffer, $20k to B&E, $2k to TEAM. 11.1.22 JHB - Valve ordered and expected mid-late November. Mechanical/electrical scope walked down and pricing being developed. Execution planned for week of 11/28 or 12/5. 10.3.22 JHB - AFE approved, valve to be ordered week of 10/3. Walking down scope with mechanical/electrical contractors week of 10/10 to award and schedule installation. | 2023-05-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 5685 | 0 |  |  | 119053 |  | Oey, Alex | Johnson, AJ |  |  | 1 | 45569 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
BTXHF - VCU Corrosion | Item | Open | MCAP |  | Maintenance Framework |  | Garcia, Monica | South | 1. Proposed |  | Vapor Management |  | 80000 |  | 80000 | 80000 | 0 | Green | 80000 |  | 80000 | 0 | [9 empty] | 80000 | 80000 | No | Green | 2023-07-01 |  |  |  | 2023-06-30 | [14 empty] | 30000 | 30000 | 20000 |  |  |  |  | 4/3/23 MLG: Waiting on one final quote for the painting material, then the painting contractor will submit their proposal. 3-1-2 MLG: a walk down was performed on 2/15/23 with the Vapor group, Ops, Reliability, and Knight Industrial. The corrosion SME was contacted and we requested specific painting standards. A work scope is being developed at this time. 2/2/23 MLG: Working with Reliability on scope development. | 2023-04-04 |  |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  |  | 0 | 80000 |  |  |  | Karl, Marissa |  |  |  | 1 | 41913 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Other Programs
BTXHF - Viola Line Lowering | Item | Open | MCAP | BTXHF00M2206 | Project Framework | 1956700 | Corman, Chris | South | 6. Operational | Drawdown | Pipeline Replacements | 393124 | 27000 |  | 420123.72 | 382052 | 38072 | Yellow | 1200000 |  | 1200000 | -779876 |  |  | 82000 | 1443000 |  | 1525000 | Full | 1525000 | 544136 | 27000 | 571136 | No | Green | 2022-04-01 | 2022-03-21 | 2022-03-21 | 2022-12-31 | 2023-03-31 |  |  | 99956.53 | 41058.23 | 241037.37 | 11071.59 |  |  | 11072 | Red |  |  | 27000 | [8 empty] | 5/1/2023 - Project ready to be closed 3/2/2023 - Line was discovered to be lower than what is needed for relocation. Project has been canceled. Working through re survey of line and invoicing 2/2/23- Line was improperly surveyed/marked. Project scope has dramatically changed and could possibly be cancelled. 1/3/23- Project will kickoff Jan 16 and should be complete by Feb 28. 11/1/2022 - PO's have been issued to all vendors. Working on kickoff meeting. Construction still scheduled for Jan. Accrue $60k to TPC Industrial 10/4/2022 - Pipe Expected to arrive in October Awarding the winning bid this week. 9/6/2022 - PO for piping was placed. Looking to kickoff construction in early 2023. Bid walk was completed, evaluating bids now 8/8/2022 - Entering forecast for 2023 8/1/2022- TRC is going to be scheduled to submit project for approval. 6/1/2022 - preliminary HDD design complete. Looking to complete construction estimate. Accrue 15k to HGA 5/4/2022 - Civil Survey, Environmental survey, and geo bores will be complete this week. Looking to complete design by 5/30. Accrue 25k to HGA 4/5/2022 - Engineering has begun. Working on getting permits from Union Pacific to perform the survey and geotechical bores. 2/28/2022 - AFE has been completed. Working to identify funding for the project. Once funding is provided work will be scheduled | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 382052 | 38072 |  |  | 151012 |  | Oldham, David | Burke, Kevin |  |  | 1 | 42967 |  | Guest, ProSight | Independent | Aqua | 2022-02-16 | Int - Planned Cutouts
BTXHF - VRU 3 Train A Carbon Replacement - 2022 | Item | Open | MCAP | BTXHF00M2207 | Maintenance Framework | 1971235 | Johnson, AJ | South | 6. Operational | Drawdown | Vapor Management | -279820 |  |  | -279819.67 | -271903 | -7916 | Yellow |  |  |  | -279820 |  |  | 718000 |  |  | 718000 | Phase | 718000 | 678207 |  | 678207 | No | Green | 2022-04-01 | 2022-04-14 | 2022-04-14 | 2022-10-15 | 2022-12-09 |  |  | -5903.56 | 42946.66 | -308946.55 | -7916.22 |  |  | -7916 | Red | [11 empty] | 2.4.23 - Final invoicing is less than anticipated. ML 1.4.23 - Project is complete, waiting on final invoicing (WM,Traf & Vapor com) AJ 12.1.22 - Negative forecast reflected in cost division reclass to Train B project once AFE approved. AJ 11.8.22 - Negative forecast reflected in cost division reclass to Train B project once AFE approved. DC 10/11/22 - Negative forecast reflected in cost division reclass to Train B project once AFE approved. DC 10/4/22 - September Accrual $640,000 per Chelsea Schumacher (AS) 7/11/2022 - Carbon delivery expected in October. $100k for project execution was pushed to November. Continuing to re-accrue $615k, per past PM. CKS 6/30/2022 - PM changed to Chelsea Schumacher. 6/1/2022- Re-accrue $615K for John Zink 5/3/2022 - Accrue $615,000 for John Zink Company LLC for 152,000 lb of JACOBI Super Carbon. Shipping was estimated at $0.29/lb. Received 6% discount based on Coupa Bid Event with Vapor Program.. 3/31/2022 - Forecast to purchase 2 units. 3.1.21.DLC: Issued drawdown to cover replacement for 1 unit - 2nd unit will need additional funds | 2023-05-02 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | -271903 | -7916 |  |  | 958027 |  | Karl, Marissa | Asiedu, Saka |  |  | 1 | 42940 |  | Guest, ProSight | Independent | Aqua | 2022-02-14 | Other Programs
BTXHF API 570 Program Development | Item | Open | MEXP |  | Maintenance Framework |  | Garcia, Monica | South | 1. Proposed |  | Facility Integrity |  | 210000 |  | 210000 | 210000 | 0 | Green | 210000 |  | 210000 | 0 | [9 empty] | 210000 | 210000 | No | Green | 2023-06-01 |  |  |  | 2023-12-30 | [13 empty] | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 |  | 4/3/23 MLG: The team has reached out to to 2 out of 3 engineering companies and held preliminary scope meetings, we need to provide drawings,. We will reach out to the 3rd engineering company as well.. 3/1/23 MLG: Continuing to work with Reliability on the scope; held a meeting with a contractor to discuss our goals in conjunction with their ability to achieve our goals. 2/2/23 MLG: Working with Reliability on scope development. | 2023-04-04 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  |  | 30000 | 90000 | 90000 |  |  | Aiken, Elaine |  |  |  | 1 | 44996 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
BTXHF Cathodic Protection | Item | Candidate | MCAP |  | Maintenance Framework |  | Wirfs, Mike | South | 1. Proposed |  | Cathodic Protection |  | 95000 |  | 95000 | 95000 | 0 | Green |  |  |  | 95000 | [9 empty] | 95000 | 95000 | No | Green | 2023-07-01 |  |  |  | 2023-03-31 | [14 empty] | 95000 | [6 empty] | 5-1-2023 - Project study being done when complete AFE will be submitted. | 2023-05-01 |  |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  |  | 0 | 95000 |  |  |  | Geib, Rob |  |  |  | 1 | 45721 |  | Guest, ProSight | Independent | Aqua | 2022-08-30 | Int - Planned Corr & FI
BTXHF CUI Program Development | Item | Open | MEXP |  | Maintenance Framework |  | Garcia, Monica | South | 1. Proposed |  | Facility Integrity |  | 95000 |  | 95000 | 95000 | 0 | Green | 95000 |  | 95000 | 0 | [9 empty] | 95000 | 95000 | No | Green | 2023-09-01 |  |  |  | 2023-12-30 | [16 empty] | 30000 | 30000 | 35000 |  |  | 4/3/23 MLG: Team has met with a couple of engineering companies; this will be worked in conjunction with the BTXHF API 570. We will reach out to a 3rd engineering company. 3/1/23 MLG: Continuing to work with Reliability on the scope; held a meeting with a contractor to discuss our goals in conjunction with their ability to achieve our goals. 2/2/23 MLG: Working with Reliability on scope development. Team has already reached out to a couple of vendors regarding their ability to assist in the program development. | 2023-04-04 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  |  | 0 | 30000 | 65000 |  |  | Aiken, Elaine |  |  |  | 1 | 44995 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
BTXHF Dock 3 Corrosion Remediation | Item | Open | MEXP |  | Maintenance Framework |  | Garcia, Monica | South | 1. Proposed |  | Facility Integrity |  | 85000 |  | 85000 | 85000 | 0 | Green | 85000 |  | 85000 | 0 | [9 empty] | 85000 | 85000 | No | Green | 2023-08-01 |  |  |  | 2023-06-30 | [15 empty] | 45000 | 40000 |  |  |  |  | 4/3/23 MLG: The inspection and the painting teams are focused on the Unit 200 outage but a walk down is tentatively scheduled for mid-April. 3/1/23 MLG: Working with Reliability on scope; we have reached out to the corrosion SME and are using inspection reports to develop the scope. 2/2/23 MLG: Working with Reliability group on scope. A walk down is scheduled for week of February 13th. | 2023-04-04 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  |  | 0 | 85000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 44997 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
BTXHF Hub 250 Series Tanks ER Probe Replacements | Item | Candidate | MEXP |  | Maintenance Framework |  | Wirfs, Mike | South | 8. Canceled |  | Cathodic Protection |  |  |  | 0 |  | 0 | Green | 35000 |  | 35000 | -35000 | [11 empty] | No | Green |  |  |  |  | 2023-03-31 | [21 empty] | 12/1/22- Mike Wirfs completed this project in conjunction with the Galvanic Coupon installation project. | 2022-12-01 |  |  | South | Pipelines and Terminals | Corrosion |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  |  | 0 |  |  |  |  | Geib, Rob |  |  |  | 1 | 45687 |  | Guest, ProSight | Independent | Aqua | 2022-08-29 | Int - Planned Corr & FI
BTXHF Idle Unused Piping | Item | Open | MEXP |  | Maintenance Framework |  | Garcia, Monica | South | 1. Proposed |  | Facility Integrity |  | 55000 |  | 55000 | 55000 | 0 | Green | 55000 |  | 55000 | 0 | [9 empty] | 55000 | 55000 | No | Green | 2023-09-01 |  |  |  | 2023-12-29 | [16 empty] | 30000 | 25000 |  |  |  | 3/1/23 MLG: The outcome from the meeting on 2/13/23 is to perform a walkdown in late April/early May, with execution in June/July due to the manpower utilization for the unit 200 outage and other seal failures. 2/2/23 MLG: a meeting with PSM, Environmental, Scheduling, Ops, and Processing is scheduled for 2/13/23 to discuss scope and identify the idle lines. | 2023-03-01 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  |  | 0 | 30000 | 25000 |  |  | Aiken, Elaine |  |  |  | 1 | 44998 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
BTXHF MEXP FLIP | Item | Open | MEXP | BTXHF00E2212 | Maintenance Framework | 2052505 | Matthews, Clayton | South | 3. Active | Drawdown | Tanks | 282 |  |  | 282.27 | 282 | 0 | Green |  |  |  | 282 |  |  | 283 |  |  | 283 | Full | 283 | 565 |  | 565 | No | Green | 2022-12-01 | 2022-12-16 | 2022-12-16 | 2022-12-31 | 2022-12-31 |  |  | 282.27 | [20 empty] | Schultz, Amy |  | South | Pipelines and Terminals | Tank Integrity |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 282 | 0 |  |  | 282 |  | Stine, Carlton | Shook, Mark B. | N/A |  | 1 | 46385 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-12-16 | Int - Tanks
BTXHF Tank 1152 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | BTXHF00M2301 | Maintenance Framework |  | Matthews, Clayton | South | 3. Active | Defined | Tanks | 64 | 442000 |  | 442063.56 | 442064 | 0 | Green | 442000 |  | 442000 | 64 |  |  | 266930 |  |  | 266930 | Phase | 266930 | 64 | 442000 | 442064 | No | Green | 2023-03-01 | 2023-01-17 | 2023-01-17 | 2023-12-30 | 2023-11-30 |  |  |  |  | 63.56 | [10 empty] | 200000 | 200000 | 42000 |  |  |  | 9/23/22-CES-Revising Budget/Estimate based on sister tank 115-1. Changing $1,142,146 to $542,000 based on projection of minor repairs vs bottom replacement. | 2022-09-23 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 64 | 0 | 400000 | 42000 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44888 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
BTXHF VRU3B Carbon Replacement | Item | Open | MCAP |  | Maintenance Framework |  | Garcia, Monica | South | 8. Canceled |  | Vapor Management |  |  |  | 0 |  | 0 | Green | 600000 |  | 600000 | -600000 | [11 empty] | No | Green |  |  |  |  | 2023-08-31 | [25 empty] | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  |  | 0 |  |  |  |  | Karl, Marissa |  |  |  | 1 | 44959 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Other Programs
BTXPP - 100 T-102 Bypass | Item | Open | MCAP | BTXPP00M2306 | Maintenance Framework | 2095051 | Burke, Joshua | South | 6. Operational | Emergent | South | 176230 |  |  | 176229.61 | 161942 | 14287 | Yellow |  | 164610 | 164610 | 11620 |  |  | 164610 |  |  | 164610 | Full | 164610 | 176230 |  | 176230 | No | Green | 2023-03-01 | 2023-03-14 | 2023-03-14 | 2023-01-16 | 2023-01-16 |  |  |  |  | 161942.21 | 14287.4 |  |  | 14287 | Red | [11 empty] | 5.3.23 JHB - Accrue $7k to Ferguson. Ready to close pending final payment. 4.4.23 JHB - Reclass complete, ready to close. Variance due to reclass and no forecast entered when entering project. 3.1.23 JHB - Preparing AFE documents and reclass. ~$156k total cost. 2.1.23 JHB - Work complete under temporary work order due to emergency. Developing AFE to reclass cost againt. | 2023-05-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 161942 | 14287 |  |  |  |  | Johnson, AJ | Johnson, AJ |  |  | 1 | 46498 |  | Guest, ProSight | Independent | Aqua | 2023-01-19
BTXPP - 200-E-109 to 200-V-102 Piping Replacement | Item | Open | MCAP | BTXPP00M2204 | Maintenance Framework | 1957477 | Garcia, Monica | South | 6. Operational | Defined | Facility Integrity | 48391 |  |  | 48391.35 | 91322 | -42931 | Red | 75000 |  | 75000 | -26609 |  |  | 108000 |  |  | 108000 | Full | 108000 | 84578 |  | 84578 | No | Green | 2022-03-01 | 2022-03-30 | 2022-03-30 | 2022-12-31 | 2023-05-31 |  |  | 167.1 | 169.93 | 45984.99 | 2069.33 | 45000 | 45000 | -42931 | Red |  | Forecasting | [9 empty] | 5/1/23 MLG: Work completed, waiting on invoices. 4/4/23 MLG: Work actively being performed during the Unit 200 outage. 2/2/23 MLG: Fabrication will begin in March and installation will be during the Unit 200 outage scheduled for March and April. 1/4/23 MLG: Work is scheduled for installation during the 200 unit outage which is scheduled to begin on Feb 26 and will last for 10 days. 8/2/22 MLG- Forecast shifted into 2023, work will be completed during outage. 6/3/22 MLG- Reliability is working on the installation date, it may be installed in the outage in 2023, unless the end of life for some of the piping is reached prior to 2023; this data is being assessed.. Variance due to installation date 4-4-22 MLG: approved AFE is for unit 200. A 4 foot section near 200-E-109 was installed on 3-31-22. the remaining section of pipe will be installed as soon as Reliability analyzes inspection data and makes determination of installation date Adding both the 100 and 200 and if scoped out | 2023-05-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 46322 | 2069 |  |  | 36186 |  | Aiken, Elaine | Gee, Ryan |  |  | 1 | 42135 |  | Clark, David | Independent | Aqua | 2021-09-10 | Int - Planned Corr & FI
BTXPP - 5000 Corken Pump Upgrade | Item | Open | MCAP | BTXPP00M2216 | Maintenance Framework | 2011897 | Burke, Joshua | South | 3. Active | Defined | Rotating Equipment | 140859 | 28000 |  | 168858.67 | 154949 | 13909 | Yellow |  | 141000 | 141000 | 27859 |  |  | 226000 |  |  | 226000 | Full | 226000 | 348730 | 28000 | 376730 | Yes | Red | 2022-08-01 | 2022-08-10 | 2022-08-10 | 2022-12-31 | 2023-05-31 |  |  | 90751.75 | -20165.58 | 79363.19 | -9090.69 | 5000 | 5000 | -14091 | Red |  | Contractor/Vendor Issue | 28000 | [8 empty] | 5.3.23 JHB - Work complete, final cost negotiated with H&S. Supplemental AFE in development. Accrue $8k to ferguson, $40k to H&S, $1k to JM supply, $4k to UPS. FC of $20k added to May to account for additional hot tap in units for return - additional scope from AFE development. Variance due to negotiation of final H&S cost. 4.3.23 JHB - H&S nearing completion. Both propane pumps installed pending pipe strain/alignment. Butane pumps targeted completion 4/5. Accrue $85k to H&S,11.8k B&E , 1k Lk Jordan, 2k Teams, 8k Wolseley - move $5k to April based on small carryover. 3.7.23 JHB - Additional $30k added to March to account for H&S total requested CO. Unlikely to be this high - currently negotiating additional cost. 3.1.23 JHB - H&S mechanical work on hold due to numerous quality issues. Meeting to address issues held week of 2/20 - Quality improvement plan to be submitted by H&S. FC pushed into March, final CO value TBD. Reaccrue $7k to B&E, $20k to H&S, 8k to Wolseley. Variance due to schedule change when work placed on hold due to quality issues. 2.1.23 JHB - Mechanical field work ongoing for propane pumps and butane pump work slated for February. H&S requesting change orders due to Operations delays, pump grouting, and piping scope change. Final amount TBD. Accrue $7k to B&E, $11k to H&S, $19k to JM supply, and $8k to Wolseley. H&S CO forecast into FEB. Assuming full requested CO amount but likely will dispute based on true scope addition. 1.4.23 JHB - Pumps received, foundations poured, piping procured and largely fabrication complete. Final piping fabrication & installation scheduled for January. Currently developing hot tap book for butane system tie in. Accrue $135k to Furey, $50k to H&S, $18k to JM supply. Variance due to work completed ahead of schedule. Forecast reduced for January due to higher than anticipated December spend. 12.1.22 JHB - 3 of 4 pumps shipping week of 12/5. James Dalton coordinating installation and outage with Operations. It is likely that either partial or full installation will slip to 2023, forecast adjusted accordingly - $56k pushed into JAN 2023. Targeting minimum of piping prefab & foundations poured prior to end of year. Reaccrue $90k to Furey. Variance due to delayed start of work. 11.28.22 JHB - Furey has been able topull pump delivery back to DEC 2022. Manufacturer still working on relief valves. $100k slip into January reduced to ~$70k with potential to reduce further/eliminate as relief valve timing is defined. 11.8.22 JHB - Informed by Furey that pump manufactuerer has delayed delivery of pumps to January. Furey working with manufacturer to pull back into 2022. Potential for ~$100k to slip from December to January.11.1.22 JHB - Pump schedule to ship end of November. Re-accrue $45k to Furey and an additional $45k to Furey (total $90k) for progress payments.10.3.22 JHB - Pumps on order, ETA late NOV/early DEC. Re-accrue $45k to Furey per commercial terms. 9.1.22 JHB - 4 EA recirc pumps ordered to replace 5013, 14, 15, 16. Accrue $45k to Furey for placement of order per terms. 7.1.22 JHB - Pump hydraulics to be updated in early July to match process needs. Updated hydraulics will be used to re-quote pumps and define project scope. Adjusting forecast to account for recycle time over the past month. 6.7.22 JHB - Moved forecast start to July. Still reviewing pump options before preparing/presenting AFE. 6.2.22 JHB - Pump proposals received. To be reviewed with Reliability stakeholders to determine selection. AFE documents will be prepared accordingly.4.28.22 JHB - Piping mods determined to be insufficient to remedy LDAR failures. Alternative seal-less pump model proposals have been solicited. Will review pump options with SME/reliability to determine appropriate selection.4.1.22 JHB - Working with Reliability/Tech services to define piping modifications required as a "phase 1" effort to resolve the pump issue.2.25.22 JHB - Corkin site visit completed and operational/maintenance improvements identified. Trial period will be conducted with suggestions implemented to determine pump longevity & further define scope. Pushing out forecast to allow trial period before pursuing replacements/modifications.1.31.22 JHB - Meeting held with Corkin to review seal design and leak by condition. Corkin advised leak by through weep hole is inherent to design. Corkin to perform site visit to review system and make recommendations tohelp define project scope. | 2023-05-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 149949 | 18909 |  |  | 207871 |  | Posipanko, Dan | Posipanko, Daniel A. |  |  | 1 | 41915 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Other Programs
BTXPP - 7000 Blowers to Flare | Item | Open | MCAP | BTXPP00M2218 | Maintenance Framework | 2014094 | Garcia, Monica | South | 7. Closed | Defined | Vapor Management | 1759 |  |  | 1758.85 | 1759 | 0 | Green |  |  |  | 1759 |  |  | 37000 |  |  | 37000 | Full | 37000 | 33230 |  | 33230 | No | Green | 2022-09-01 | 2022-08-31 | 2022-08-31 | 2022-12-31 | 2022-11-02 |  |  | 53.21 | 1409.19 | 296.45 | [16 empty] | 2/2/23 MLG: WO closed and Project status changed to Closed. 1/4/23 MLG: waiting on final invoice. 11/2/22 MLG variance is due to issues with Operations rescheduling the work. Work is now completed. Awaiting final invoices. No future forecasts 10/4/22 MLG: variance is due to issues with Operations rescheduling the work. work anticipated to be completed in October. 8-25-22 AJ added 7k to forecast per the AFE that is getting routed. Additional 7k came from south region drawdown | 2023-02-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 1759 | 0 |  |  | 31471 |  | Karl, Marissa |  |  |  | 1 | 41916 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Other Programs
BTXPP - Access Security and Instrumentation Upgrades | Item | Open | MCAP | BTXPP00M1610 | Exempt | 1219423, 1297884 | Garcia, Monica | South | 6. Operational | Unplanned | South | -7687 |  | 0 | -7687.3 | -7687 | 0 | Green |  |  |  | -7687 |  |  | 120000 | 515000 |  | 635000 | Full | 1327000 | 1252426 | 0 | 1252426 | No | Green | 2020-01-01 | 2017-02-14 | 2017-02-14 | 2018-12-31 | 2022-08-31 |  |  | -7687.3 | [17 empty] | 0 | 5/1/23 MLG: Phase 3 AFE has been developed and will be submitted upon confirmation of a recent charge. 3/1/23 A Phased AFE/Supplemental will be submitted . 2/2/23:MLG: A meeting with IT and Fortress was held yesterday and it was stated that any Dahua brand cameras need to be removed due to a security risk per the National Defense Authorization Act. This removal is a government required regulation. IT instructed Fortress to remove all of these cameras from the network. Unfortunately, the 2 cameras that were installed in this project are Dahua cameras. These cameras have been removed from the network. A copy this email will posted in the Attachments tab. No further work will be performed. All invoices have been submitted , no outstanding invoices, a phased AFE will be submitted for the overage of the approved Full AFE Amount shown. 12/5/22 MLG: Working with Buckeye IT to determine remaining work. Will develop a Supplemental AFE. 11/8/22 MLG: There have been issues with the installation of the cameras on the network. IT has installed a new server called Exactavision, although, the camera design, connections and equipment were designed for the 192 network. There have been several meetings with IT and IT has stated that if we connect the cameras to the Exactavision we will need to purchase additional equipment for compatibility. The remaining forecast if for equipment and labor. 8/2/22 MLG: Variance due to communication issues between new equipment and existing equipment. 7/5/22 MLG; Variance is a due to technical issues. Cameras have been installed. 4/4/22 MLG: The camera portion is moving forward, the variance is due to uncompleted, remaining work. 2/23/22 MLG: On 18 Feb 2022, the wireless network infrastructure was successfully completed. The camera portion of the project has been placed on hold for project cost evaluation. 2/9/22 MLG: Due to Buckeye policy with LAN connectivity, the servers and switches were delivered to Emerson in Houston on 2/7/22 for upgrades. This has caused a shift in the commissioningdate to 2/14/22. 2/1/22 MLG: Emerson will arrive onsiteon Feb 7th to begin commissioning of the wireless network. Work is scheduled to last for 2 weeks. 1/4/22 MLG- Additional fiber has been installed; remaining work is the commissioning of wireless network, although, Emerson was unable to perform commissioningin Q4 of 2021; working with Emerson to commission in Q1 of 2022. Commissioning will take approximately 2 weeks. 12/1/21 MLG: Additional fiber is scheduled for installation on 12/2/21. 11/18/21 MLG- Emerson will not be able to commission the wireless network until January, at the earliest. More information will provided as it becomes available. 11/2/2021 MLG - The fiber issue has been reviewed and it has been determined that additional fiber will need to be installed. Quotes are being obtained, forecast will updated as soon as the additional costs are obtained and a change order will be issued. The forecast for November is for Puffer-Sweiven' s commissioning, this amount is the remaining open amount on their PO. 10/4/21 MLG: discussions with Emerson and the engineering company are still in progress in order to determine the costs associated with the installation of additional fiber and/or equipment. 9/9/21 MLG: A meeting was held today regarding the fiber cable lengths. Emerson, engineering and Buckeye will re-evaluate if an additional switch will need to be installed for the device access point or if we can reconfigure one of the switches that is overthe fiber length. We are approximately 300 feet over the fiber spec at one of the locations Due to this issue, commissioning has been rescheduled for mid-to-late October. 9/2/21 MLG: Emerson/Puffer-Sweiven have commissioning tentatively scheduled for week of September 13th and will last about 2 weeks. Commissioning was delayed in August. 8/3/21 MLG-Need to obtain IP addresses for 3 cameras, the remaining equipment has the IP addresses assigned. Installation is complete; commission is tentatively scheduled for the week of August 23rd. 6/30/21 Need to obtain IP addresses from I.T. and thenPuffer Sweiven/Emerson will arrive onsite forcommissioning. Commissioning will take 2 weeks to complete. Phase 3 AFE has been submitted through RemedyForce for approval routing. 6-9-21 MLG: the 2021 budget is $270k. There is a duplicate PO to Zadok, the PO that was cancelled is C1-214021. This PO was generated but was rejected by final approver due to some discovery issues. Rather than keeping the PO open and waiting for approval in the system, it was rejected until the issues could be resolved. The issues were resolved and the proposal and costs remained the same; a new PO was generated due to a change as to who would be the finalapprover. The active PO is C1-214932. If the duplicate PO is subtracted from OPPM actuals, the Project Actuals becomes $822,262. The final EA, for this phase, is $905k. The Cognos report shows actuals as $666,772, this is because Zadok has not submitted an invoice for their PO of $24,783. We cannot move forward with additional work until Zadok is 100% complete due to this project is a step work scope. 6-8-21 MLG: Installation progress is asfollows: *Fiber installation is 100% complete *conduit is 100% complete *mesh points and antennas is 100% complete *power and communication wire is 100% *terminations are 100% complete. *fiber termination and testing is 100% complete *Tubing for PJB-5000 purge is 100% complete *Cisco switches, ethernet switched and power supplies are 100% complete *2 wireless cameras and antenna are 80% complete I.T. will assign the IP addresses, then Emerson/Puffer will arrive onsite and make the Delta V configuration, install core servers and switches, make the connections, and testing; thiswill take approximately 2 weeks. 5-3-21 MLG: Installation progress is as follows: *Fiber installation is 100% complete *conduit is 70% complete *mesh points and antennas are 75% complete *power and communication wire is 70% *terminations are 47% complete.4/1/2021 - Project kickoff was 3/23/2021, scheduled to last 4-10 weeks. 10/8/2020 MLG- Based on reporting issues, cost reporting, and IFA package deliverable, this project was taken away from Onyx Engineering. S. Series Solutions has been awarded the remaining work to take this project to IFC. They are incorporating Buckeye's comments along with the lack of / insufficient drawings; IFR package will be reviewed the week of 10/12/20. Construction Bid package will be generated and issued for bids.. Emerson Delta V migration scheduled for Q1 2021. 6/4/20 MLG-Engineering company has issued the IFA package for the wireless network infrastructure. The package is currently being reviewed and will be returned to engineering company with our comments. When we receive the IFC, a bid package will be developed and then submitted for construction bids. 3/9/20 MLG- Engineering for the wireless infrastructure is at/near 60%. 1/21/20 MLG-The Estimated Operational Date has been changed to 12/21/20 to accommodate theengineering and installation. 1/21/20 MLG- The Purchase Order was issued to the engineering company on 12/16/19. 12/12/19 MLG-Requested engineering detail design IFC package proposal from 3 different engineering firms. A field walk down of every access point was performed at the same time the week before Thanksgiving. I have received and reviewed all three proposals, I will make a decision on Monday 12/16/19 after I meet with the proposed winner. I have a few questions to ask them in person before I award them the PO. 10-10-19 MLG - BTP, Corporate's Network and Security along with Emerson team members are working together to address questions regarding access, operability, and functionality regarding the installation, IP addresses, post installation maintenance, and server location. Once all the questions and concerns have been addressed, a bid document will be generated and submitted to 3 engineering companies. Engineering is planned for the 2019 year. Engineering is needed to determine the location of power, fiber and structural installation. Installation / construction has been budgeted for 2020. 6-10-19 MLG- Puffer-Sweiven issued their revised Detail Design Package on June 5, 2019. I will use this document to develop a Bid Package for the Detail Design Engineering package. 1/11/2019 MLG-PO for equipment was issued to Puffer in Dec 2018. Emerson has begun engineering. 11/28/18 MLG- Phase III AFE approved on 11/26/18. PO to Puffer-Sweiven was issued and PM has requested Puffer to immediately purchase the necessary equipment. 11/6/2018 MLG - Phase III AFE submitted for approval. 10/4/2018 MLG-Emerson submitted their revised proposal. HSE has questions pertaining to the Muster Point badging. A meeting is scheduled for the week of 10/8/2018 to review this issue prior to generating the P.O.09/10/18 MLG-Several meetings between Emerson and Buckeye's IT Network group have taken place. One of the items that was discussed was to purchase equipment through a different provider. It was decided not to go that routedue to the connection to the Delta V and the Emerson exclusivity of that system. This will ensure that equipment and communication works cohesively. Emerson is currently in the process of developing an updated quote. 08/07/18 MLG0 A meeting was conducted in July to allow Security and the Network group to discuss the project. Four (4) action items came out the meeting, these are being address. A deep divemeeting is schedule between the Network team and Emerson. Emerson has been selected as the contract provider. 07/10/18 MLG-A technical meeting is being scheduled to allow Emerson's technical team to discuss/answer/address all of Buckeye's questions and concerns regarding the new wireless infrastructure. 06/07/18 MLG - Project meeting will be held to revisit the project scope, ensure all questions/issues have been addressed, and vendor's quote meets the scope of work. 01/08/2018 MLG- Operational Date changed to coincide with forecast installation. 12/8/2017 MLG-Fencing around Shipping & Receiving Warehouse was completed in November. The next AFE phases will occur in 2018. 11/7/2017 MLG - Phase II Fencing around Shipping and Receiving Warehouse commenced on 11/3/2017. Phase III scope will begin late November. 10/6/2017 MLG- Phase II 2017 will bebroken up into additional Phases. New Phase II scope is fencing around Shipping & Receiving Warehouse. Currently awaiting bids from fence contractors. Phase III scope will be cameras & new badging access points, Phase IV willbe smart tracker and wireless infrastructure. 9/11: BMR - Updated project name to security upgrades. 2016 is Phase I. 2017 will be Phase II with the addition of smart tracker for mustering points and otherareas with BTXPP 9/9: Most card readers installed. Need additional control panel to activate many of the new readers. Expected to be complete by EOM. Training on Phase I to employees and contractors TBD by HSSE group. 8/16: Added Phase II of the project (2017): To include intelltrac (including emergency exits), fencing around the maintenance building, creating an access point between maintenance building and ISBL, and additional cameras. Budget dollars are just placeholders. | 2023-05-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | -7687 | 0 |  |  | 117140 |  | Johnson, AJ | Burke, Kevin | N/A |  | 1 | 19303 |  | Guest, ProSight | Independent | Aqua | 2016-06-15 | Other Programs
BTXPP - ATB pump API seal plan upgrades | Item | Open | MCAP | BTXPP00M2209 | Maintenance Framework | 1990656 | Burke, Joshua | South | 7. Closed | Defined | Rotating Equipment | 6592 |  |  | 6591.84 | 6592 | 0 | Green |  |  |  | 6592 |  |  | 223000 |  |  | 223000 | Full | 223000 | 209368 |  | 209368 | No | Green | 2022-06-01 | 2022-06-15 | 2022-06-15 | 2022-11-04 | 2022-12-30 |  |  | 5220.46 | 1469.38 | -98 | [16 empty] | 4.10.23 ML - Ready to Close 3.1.23 JHB - re-accrue $60k to B&E. Ready to close pending final invoicing. 2.1.23 JHB - both systems operational. Ready to close pending final invoicing. Reaccrue $60k to B&E. 1.4.23 JHB - Seal systems installed. 100 Unit kicked on but experienced vibration. Troubleshooting ongoing. Accrue $60k to B&E, $3k to Reladyne. $3k to LK Jordan, 12.1.22 JHB - Seal systems received, installation scheduled for week of 12/5. Accrue $45k to B&E, $27k to Flexaseal 11.1.22 JHB - Electrical pulls, junction box mounting, and all prep work completed in anticipation of seals arriving late November completed. Plan to execute seal install week of 11/28 or 12/5. Accrue $15k to B&E. 10.4.22 JHB - forecast adjusted to reflect November delivery and December final installl10.3.22 JHB - Flexaseal advise that seal assemblies are delayed due to instrumentation. Pending feedback on revised ETA. Forecast likely to adjust based on response. Accrue $10k to Flexaseal. 9.8.22 JHB - moved majority of forecast into October/November per delay of seal assemblies. Bid event for electrical tubing underway, will begin work late September/early October. 9.1.22 JHB - Seal assemblies delayed to October due to supply chain issues. Entering bid event for electrical/tubing work in September, starting work early October.8.1.22 JHB - Seal assemblies on track for September Delivery, IFA drawings issued and in review. Accrue $31k to Flexaseal. Variance due to forecasting error, originally quoted through Odessa and then purchased directly from flex-a-seal, didn't account for new payment terms.7.5.22 JHB - seal assemblies ordered with 12 week delivery, adjusting forecast accordingly. Variance due to commercial terms of procurement agreement and "seal alliance" savings. AFE budget generated without seal alliance savings, savings to be added to contingency7.5.22 Accrue 19.5k Flexaseal Eng6.7.22 JHB - Moved forecast start to July based on delays in AFE submission and subsequent seal plan order timing. 6.2.22 JHB - AFE reviewed and approved by stakeholders, pending submission based on incremental funding source. S. Asiedu determining funding source.4.28.22 JHB - 53s will not remedy the issue, as they require the pump to be operating to circulate barrier fluid through the seal. Plan 54s have been selected as the appropriate technology. A revisedproposal is being prepared by Flexaseal and will be used for AFE generation. Forecast adjusted for last proposed lead time on 54s.4.1.22 JHB - Investigating API plan 53 conversion from the existing seal assemblies as a comparable but cost-reducing alternative. Pending pricing fromFlowserve on the 53 A conversion.2.25.22 JHB - Site visitheld with flexiseal to review API 54 proposal & seal plan selection justification. Flowserve has been engaged as an alternate vendor to provide competitive pricing and identify potential alternatives to total seal plan replacement. Once alternatives have been defined, the AFE will be revised and reviewed. Targeting submission is now the first or second week or March. Current AFE estimate is ~$360k based on budgetary pricing and API 54 plan proposal. Reviewing alternates/partial installations to reduce project cost.1.31.22 JHB - Proposal for new API 54 seal plan reviewed withOdessa & Reliability. Gathering budgetary pricing for Electrical and mechanical support to complete AFE package. Target AFE submission 2/18. | 2023-04-10 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 6592 | 0 |  |  | 202776 |  | Posipanko, Dan | Posipanko, Daniel A. |  |  | 1 | 42046 |  | Clark, David | Independent | Aqua | 2021-09-03 | Other Programs
BTXPP – BOG to Flare Flow Meter Installation | Item | Open | MCAP | BTXPP00M2206 | Maintenance Framework | 1972379 | Burke, Joshua | South | 7. Closed | Drawdown | South | 4877 |  | 0 | 4876.8 | 4877 | 0 | Green |  |  |  | 4877 |  |  | 55000 | 349000 |  | 764000 | Full | 764000 | 782055 | 0 | 782055 | No | Green | 2022-05-01 | 2022-05-23 | 2022-05-23 | 2022-05-23 | 2022-11-30 |  |  | 543.56 | 4364.48 | -31.24 | [15 empty] | 0 | 3.1.23 JHB - Reaccrue $15k to Knight. ready to close pending final invoicing. 2.1.23 JHB - reaccrue $15k to knight, accrue $1k to Allesco, ready to close pending final invoicing. 1.4.23 JHB - Installation complete, Accrue $72k to H&S, $15k to Knight, $3k to Sentinel, 3k Jk Kolb 12.1.22 JHB - punchlist items for insulation cladding & PI/TIs pushed to December. Additional forecast of $20k added to account for this. Accrue $ 19k to B&E, $85k to H&S, $3k to JIS, $25k to Knight.11.1.22 JHB - Project mechanically complete as of 10/27, punchlist items remain for installation of PI/TIs, final insulation. Accrue $19k to B&E, $135k to H&S (need CO for scope changes), $9k to JIS, $35k to Knight, $5k to LK Jordan, and $17k to Sentinel. $7k added to November for punchlist items. 10.11.22 JHB - reduced forecast by $25k to reconcile with OPPM adjustments, EAC still $764k. 10.7.22 JHB - added $106k to forecast to reflect phase 3 AFE value of $764k.10.3.22 JHB - Onsite mechanical underway - exchanger set, shop fab 95% complete, piping being flown in and insulated. Target mechanical complete 10/14 and commissioned by 10/21. Accrue $159k to H&S, $7k to Job Industrial, $25k to Knight9.2.22 ML 20k funded MCAP Drawdown 9.2.22 JHB - Added $20k for comms work to October.9.1.22 JHB - Trim cooler piping design complete, off-gas design to be complete early September. Trim cooler piping fab awarded to H&S, fabrication kicking off week of 9/5 with targeted in-service date of ~10/14. Accrue $10k to JIS8.29.22 AJ: reduced South MCAP drawdown by 280k to cover the additional cost/forecast per JHB note below8.29.22 JHB - Added forecast for "phase 3" effort, construction & installation of trim cooler piping, ~$280k. No funding source has been allocated yet.8.1.22 JHB - Flare header flow meters installed & operational, trim cooler IFA piping/civil package to be delivered week of 8/1, on track for August fabrication and September field construction. Accrue $5k to ISS, $4k to B&E, $4kto Ohmstede, $25k to Job Industrial, $1k to Knight, $4k to LK Jordan, $7k to Puffer,$26k to Emerson, $1k to Knight. Variance due to forecasting error, dollars spent in June which were forecast in July.7.5.22 JHB - Phase 2 AFE to be submitted pending stakeholder review. Phase 2 efforts include dual flow meter procurement and installation via hot tops on flare header. 1 of 2 meters received and hot tap books are being prepared.Phase 3 efforts include installation of a trim cooler between AC6045 and V6045, and all associated mechanical/civil/structural/I&E. Trim cooler fabricated and received 7/5, detailed engineering underway. Accrue $10k to job industrial, $1k to Ohmstede, $1k to Knight, $43k to Ohmstede LTD, $6k to Techstar. Needto reclass $50k from Energy Stream OPEX PO to project. Emergent project executed urgently due tocommercial loss. Original OPPM entry was for "phase 1" of the project, and further phases have been executed due to urgency. Variance due to subsequent phases not originally forecast.6.29.22.DLC: Updated costs, allocating from Arc Flash lines where funds are unable to be used in 2022...6.2.22 JHB - Flow meter installed on V6045 on 5/18. Developing AFE documentsfor next phase efforts in overall LPG recovery project. Accrue $2k to Ohmstede, $3k to Knight, $3k to B&E, $3k to LK Jordan. Variance due to savings from AFE estimate - support/overhead time.5.6.22 JHB - Forecast updated to $52,000 to reflect current phase 1 AFE estimate. Pending review for submission of phase 1 AFE.4.28.22 JHB - Meter ordered and piping fabrication scheduled for week of5/2. Pending vendor confirmation of meter ETA. Targeting week of 5/9 for installation. | 2023-03-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 4877 | 0 |  |  | 777179 |  | Johnson, AJ | Asiedu, Saka |  |  | 1 | 43515 |  | Guest, ProSight | Independent | Aqua | 2022-04-22 | Other Programs
BTXPP - Boiler & Cooling Tower Blowdown Reroute to 2600 Tanks | Item | Open | MCAP | BTXPP00M2201 | Maintenance Framework | 1910795 | Burke, Joshua | South | 3. Active | Defined | Storm Water Management | 13359 | 56000 |  | 69358.53 | 69281 | 77 | Yellow |  |  |  | 69359 |  |  | 38000 |  |  | 38000 | Phase | 38000 | 77712 | 56000 | 133712 | No | Green | 2021-12-01 | 2021-11-29 | 2021-11-29 | 2022-05-01 | 2023-07-31 |  |  | 3759.63 | 5724.32 | -6202.84 | 10077.42 | 10000 | 10000 | 77 | Yellow |  |  |  |  | 20000 | 25000 | 11000 |  |  |  |  | 5.3.23 JHB - Scope pushed out due to priority/workload. Adjusting forecast to Q3. Reaccrue $5k to JIS, 16k to Knight, $12k to UPS. 4.3.23 JHB - JIS developing scope recommendations. Reaccrue $5k to JIS, 16k knight, 12k UPS. 3.1.23 JHB - JIS reviewing scope options. Accrue $5k to JIS. Moving remaining FC based on preliminary schedule. 2.1.23 JHB - JIS developed investigation proposal to help define scope. FGR piping complete, pending installation. Reaccrue $6k JM Supply, $12k Knight, accrue $12k UPS. Forecast adjusted based on new scope development timeline. 1.4.23 JHB - work deferred due to insufficient scope justification. Dollars moved to FGR piping project created in DEC. Accrue $6k to JM supply, $10k to Knight, $20k to UPS. 12.1.22 JHB - JIS developing proposal to upsize small bore piping per their recommendation. Targeting install before end of year. Potential for underspend if unable to execute in time. 11.1.22 JHB - JIS performed site visit and is working on recommendation. 10.3.22 JHB - Job Industrial engaged for project front end scoping/kickoff in 2022. 9.1.22 JHB - re-engaging stakeholders early September to get buy-in on scope. AFE to follow. Moved September funding to Q4. 7.5.22 JHB - budgetary pricing for parallel line installation received and AFE documents to be prepared in coming weeks. Forecast moved out of August to Q4. 6.2.22 JHB - Developing budgetary pricing for parallel line install. To be used for AFE document generation. 4.4.22 JHB - Have not reviewed alternate scopes yet. Moving forecast into Q3. 4.28.22 JHB - No update, moving funds further out. 2.25.22 JHB - Budgetary construction pricing received. Construction estimate is ~$300k + exchanger costs, alternative approaches are being reviewed. Forecast adjusted to allow time to review alternates. 1.31.22 JHB - IFB package delivered 1/21. Requesting budgetary construction estimates from vendors in early February to developfull AFE package. 1.3.22 JHB - Percheron contracted to perform detailed engineering of new exchanger and piping to cool and reroute boiler & cooling tower blowdown. 30% design review complete and 90% design review scheduled for 1/5/22.IFB packages to be delivered early January to prepare construction estimates for final AFE. | 2023-05-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 3281 | 10077 | 56000 |  | 43782 |  | Bonenberger, Mark | Asiedu, Saka |  |  | 1 | 41765 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
BTXPP - Cyanide Effluent Reduction Temporary Chiller Installation | Item | Open | MEXP | BTXPP00E2305 | Maintenance Framework | 2109864 | Burke, Joshua | South | 2. Pending AFE | Drawdown | South | 40000 | 15000 |  | 55000 | 100000 | -45000 | Red |  | 150000 | 150000 | -95000 |  |  | 150000 |  |  | 150000 | Full | 150000 | 40000 | 15000 | 55000 | No | Green | 2023-04-01 | 2023-04-05 | 2023-04-05 | 2023-12-31 | 2023-05-31 | [5 empty] | 40000 | 50000 | 50000 | -10000 | Red |  | Other | 15000 | [8 empty] | 5.3.23 JHB - Temporary chiller on site, prep work for electrical/mechanical work complete. Pending installation window from Operations in coming weeks. Accrue $7k to B&E, $21k to JIS, $7k to UPS, $2k to LK Jordan, $3k to United Rentals. FC adjusted down based on EAC of ~$55k - $45k can be returned to MEXP Drawdown. Variance due to emergent project without accurate estimating. | 2023-05-03 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 55000 |  |  |  |  | Johnson, AJ | Johnson, AJ |  |  | 1 | 46836 |  | Burke, Joshua | JDE Child | Burnt Orange | 2023-03-23
BTXPP - Cyanide Iron Treatment | Item | Open | MCAP | BTXPP00M2305 | Maintenance Framework | 2094239 | Burke, Joshua | South | 3. Active |  | Storm Water Management | 45307 | 50000 |  | 95306.97 | 95000 | 307 | Yellow | 120000 |  | 120000 | -24693 |  |  | 32620 |  |  | 32620 | Phase | 32620 | 45307 | 50000 | 95307 | No | Green | 2023-03-01 | 2023-03-07 | 2023-03-07 | 2023-10-31 | 2023-06-30 |  |  |  |  | 20000 | 25306.97 | 30000 | 30000 | -4693 | Red |  |  | 10000 | 30000 | 10000 | [6 empty] | 5.3.23 JHB - JIS performed on-site chemical testing which was inconclusive due to testing lab issues, attempting to repeat testing using onsite lab for facilitation and different lab for testing. Accrue $22k to JIS. FC adjusted based on current delays with peroxide testing. 4.3.23 JHB - JIS has delivered a preliminary report with potential solutions. In addition, they have conducted chemical testing and are performing engineering of a temporary chiller installation to maintain compliance. Next phase AFE forthcoming. Accrue $20k to JIS. 3.1.23 JHB - Phase 1 AFE routing for approval. JIS developing interim and long-term project solutions with report anticipated mid-March. Accrue $20k to JIS. Forecast adjusted down from $130k to $120k to match budget - previous forecasting error. 2.1.23 JHB - walkdown with JIS complete in January, proposal received. Developing AFE documents. Variance due to optimistic forecasting. Adjusting forecast based on current proposal/AFE timing. | 2023-05-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 20000 | 65307 | 10000 |  |  |  | Bonenberger, Mark | Bonenberger, Mark |  |  | 1 | 45560 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
BTXPP - Cyanide reduction in WW Phase I | Item | Open | MCAP | BTXPP00M2223 | Maintenance Framework | 2022693 | Burke, Joshua | South | 7. Closed | Emergent | South | 4290 |  |  | 4289.88 | 4290 | 0 | Green |  |  |  | 4290 |  |  | 69000 |  |  | 69000 | Full | 69000 | 74059 |  | 74059 | No | Green | 2022-09-01 | 2023-02-15 | 2023-02-15 | 2022-11-30 | 2022-10-30 |  |  | 3379.79 | 910.09 | [17 empty] | 3.1.23 JHB - Ready to close 2.1.23 JHB - Reaccrue $5k to suez, ready to close pending final invoicing. 1.4.23 JHB - Reclass processed, Accrue $5k to Suez. Variance due to reclass processing in different month than accrual. 12.1.22 JHB - HSE has advised that the current available cyanide test methods dissociate the cyanide that has bound with the current treatment molecule - there is still a cyanide issue that needs to be addressed. HSE scheduling meeting to review options & project scope will be developed from here. New OPPM entry for 2023 work has been created - this project will close once final invoicing is complete. Reaccrue $37k to Suez 11/1/22 JHB - HSE has advised no further modifications are required at this time. Moving dollars into December pending additional scope development. Reaccrue $37k to suez for reclass and $2k to JM Supply for restocking fee. 10.11.22 JHB - moving most of remaining FC to November - current mods are showing improvements in samples, minor mods required in October. 10.4.22 JHB - variance due to emergent project, fluid scope, and inability to forecast in previous month. 10.3.22 JHB - Injection stations operational at ISBL 200 sump and WWTP permeate pumps/boiler frac. Long-term solution pending sample results with injection. Need to reclass ~$35k for chemical + injection pump + containments. Accrue $5k to Suez and $10k to JM supply. 9/23/2022 AJ: Project Funded from BTP Cooling tower and Blowdown (pushing that forecast into 2023) | 2023-04-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 4290 | 0 |  |  | 69769 |  | Johnson, AJ | Johnson, AJ |  |  | 1 | 45822 |  | Johnson, AJ | Independent | Aqua | 2022-09-12 | Other Programs
BTXPP - ESD and Grounding at LPG Truck Loading Area | Item | Open | MCAP | BTXPP00M1631 | Exempt | 1238941 | Rathka, Brent | South | 6. Operational | Emergent | West | -3032 |  |  | -3031.53 | -3032 | 0 | Green |  |  |  | -3032 |  |  | 42000 |  |  | 42000 |  | 42000 | 0 |  | 0 | No | Green |  | 2016-09-07 | 2016-09-07 | 2016-09-05 | 2016-09-05 |  |  |  |  | -3031.53 | [18 empty] | Landeros, Melissa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | -3032 | 0 |  |  |  |  | Gardner, Travis |  | N/A |  | 1 | 20623 |  | Guest, ProSight | Independent | Aqua | 2016-08-25
BTXPP - Exchanger 100 E-100A Bundle Replacement | Item | Open | MCAP | BTXPP00M2226 | Maintenance Framework | 2036869 | Garcia, Monica | South | 6. Operational | Emergent | South | -3466 |  |  | -3466.23 | -3466 | 0 | Green |  |  |  | -3466 |  |  | 522000 |  |  | 522000 | Full | 522000 | 528744 |  | 528744 | No | Green | 2022-10-01 | 2022-11-18 | 2022-11-18 | 2022-12-31 | 2022-11-14 |  |  | 5467.74 | 591.79 | -9525.76 | [16 empty] | 4/4/23 MLG: Variance due to no remaining outstanding invoices, savings from AFE estimate. 3/1/23 MLG: Variance due to savings from AFE 2/2/23 MLG: Awaiting final invoices. 1/4/23 MLG: Awaiting final invoices. Work has been completed. 12/5/22 MLG: Variance is marked as "Other" due to this project being marked as emergent with no predetermined forecast. Work has been completed. Awaiting final invoices. 11/2/22 MLG: Interim AFE was approved 10/13/22, this was an emergent outage, work completed in October, awaiting invoices, forecast for full AFE expected to be near $420k. | 2023-04-04 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | -3466 | 0 |  |  | 532210 |  | Johnson, AJ | Johnson, AJ |  |  | 1 | 46039 |  | Johnson, AJ | Independent | Aqua | 2022-10-11 | Other Programs
BTXPP - Firewater Pump Covers | Item | Open | MCAP | BTXPP00M2230 | Maintenance Framework | 2043758 | Garcia, Monica | South | 3. Active | Defined | Fire Protection | 6553 | 10000 |  | 16553.19 | 14130 | 2423 | Red |  |  |  | 16553 |  |  | 82000 |  |  | 82000 | Full | 82000 | 72336 | 10000 | 82336 | No | Green | 2022-11-01 | 2022-11-03 | 2022-11-03 | 2022-12-31 | 2023-06-30 |  |  | 1011.88 | 5573.12 | -454.63 | 422.82 | 8000 | 8000 | -7577 | Red |  |  |  | 10000 | [7 empty] | 5/1/23 MLG: Meeting with leadership will be scheduled for mid-May to review the engineering Review Package. 3/1/23 MLG: Variance is due to customer schedule. The Issue For Review package was submitted on 2/27/23 to Buckeye. It has been distributed to Buckeye Stakeholders for review and a meeting will be scheduled mid-March to collect comments and submit back to ESDC for any revisions. 2/2/23 MLG: The Approval package is expected to be issued mid-February due to multiple members of the engineering team were out of work due to being tested positive for COVID. 1/4/23 MLG: Variance is due to delay in receiving approval regarding the drilled piers. 12/5/22 MLG: Variance due to issues obtaining the Geotech report. Engineering was delayed in performing the topology survey. Structural was delayed due to the topology report. 7/12/22.GJ - 2022 funds to be used for engineering, construction to be budgeted for 2023; 1/4/22 MLG-Project scope of work development will occur in January. | 2023-05-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 6130 | 10423 |  |  | 65783 |  | Jakubowski, Gregory |  | N/A |  | 1 | 31503 |  | Kabaria, Erika | Independent | Aqua | 2018-08-29 | Other Programs
BTXPP - Flare Gas Recovery Unit Installation Study | Item | Open | MEXP | BTXPP00E2203 | Maintenance Framework | 1970219 | Burke, Joshua | South | 4. On-Hold | Drawdown | South | 1094 |  |  | 1094 | 1094 | 0 | Green |  |  |  | 1094 |  |  | 21000 |  | 160000 | 181000 | Supplemental | 181000 | 132552 |  | 132552 | No | Green | 2022-04-01 | 2022-04-04 | 2022-04-04 | 2022-08-31 | 2022-06-14 |  |  |  |  | 1094 | [16 empty] | 3.1.23 JHB - JIS has advised ~$20k additional spend required to meet deliverables matrix for FEL2. All spending for this project currently on hold. Variance due to spending hold. 2.1.23 JHB - JIS reviewing deliverables maturity matrix and developing proposal to close gaps between their FEL 2 and our class 3. Adding placeholder forecast to February. 1.4.23 JHB - TIC updated and FEL 3 proposal delivered. 12.1.22 JHB - JIS performing TIC updates based on equipment quotes and review of design deliverables. Add $10k forecast to December for additional revisions. Accrue $5k to JIS. 11.15.22 JHB - JIS spend ticking up with additional hours to update TIC with equipment quotes and perform cost risk analysis. Will adjust forecast when opens back up. 11.8.22 JHB - Engineers are tracking to underspend. adjusted forecast -$40k to reflect new engineering EAC. 11.1.22 JHB - AFE approved per C. Kauffman 10/3/22 although budget not populated. 10.3.22 JHB - FEL 2 assessment underway. Feasibility AFE routed in early September. Pending approval, PO to be issued for ~$135k FEL 2 work. Class 3 TIC on track for 10/24 completion. 7/5/2022 - +/- 50% estimate has been completed. Waiting on direction to move into FEL 2 6/1/2022 - Waiting for final invoices 5/4/2022 - PFDs have been created. Looking to receive all deliverables by 5/30. Accrue 5k to Job Industrial 4/5/2022 - Project has been approved. Working on get PO issued. Work will take about 4 weeks from PO approval. | 2023-03-10 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 1094 | 0 |  |  | 131458 |  | Johnson, AJ | Asiedu, Saka |  |  | 1 | 43284 |  | Guest, ProSight | Independent | Aqua | 2022-03-29 | Other Programs
BTXPP - Galvanic Line Coupon Test Stations | Item | Open | MEXP | BTXPP00E2207 | Maintenance Framework | 2022502 | Wirfs, Mike | South | 7. Closed | Drawdown | South | -4945 |  |  | -4944.97 | -4945 | 0 | Green |  |  |  | -4945 |  |  | 63000 |  |  | 63000 | Full | 63000 | 25489 |  | 25489 | No | Green | 2022-09-01 | 2022-09-12 | 2022-09-12 | 2022-12-31 | 2022-12-31 |  |  | -9002.07 | 4057.1 | [17 empty] | 1/3/2023 - All invoicing is in project ready to close. Work Order Closed. 12/1/022 - Project is complete. Project cost came in under estimate due to the reduction of locations required. Accrual $8000 for Knight and $9k for Titan 10/31/22 - All materials have arrived Baytown, work scheduled to start 11/7/2022. Reduce October forecast to 15K. Delay in materials arriving. September 2022 - All materials ordered, waiting on Borin Stealth 7 coupons to arrive. | 2023-01-04 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | -4945 | 0 |  |  | 30434 |  | Johnson, AJ | Burke, Kevin |  |  | 1 | 45771 |  | Johnson, AJ | Independent | Aqua | 2022-09-08 | Other Programs
BTXPP - Increase Propane Recovery - Temporary Chiller Installation MEXP | Item | Open | MEXP | BTXPP00E2211 |  | 2037237 | Burke, Joshua | South | 6. Operational | Emergent | Trafigura | 158633 | 10000 |  | 168632.75 | 158633 | 10000 | Yellow |  |  |  | 168633 |  |  | 309000 |  |  | 309000 | Full | 309000 | 321672 | 10000 | 331672 | No | Green | 2022-10-01 | 2022-10-17 | 2022-10-17 | 2022-09-09 | 2022-09-09 |  |  | 13557.25 | 857.25 | 144218.25 | [7 empty] | 10000 | [8 empty] | 5.3.23 ML Add Positive forecast to account for reclass. 3.1.23 JHB - reclass to be complete once JIS submits final invoice. 12.1.22 JHB - reclass ongoing from MCAP project. | 2023-05-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 158633 | 10000 |  |  | 163039 |  | Clark, Ben | Johnson, AJ |  |  | 1 | 46006 |  | Meitzler, Antoinette | Independent | Aqua | 2022-10-06 | Other Programs
BTXPP – Jet Certification Sight Glasses | Item | Open | MCAP | BTXPP00M2225 | Maintenance Framework | 2036694 | Burke, Joshua | South | 6. Operational | Defined | South | 2254 |  |  | 2253.87 | 1297 | 957 | Red |  |  |  | 2254 |  |  | 42000 |  | 57351 | 99351 | Supplemental | 99351 | 102308 |  | 102308 | No | Green | 2022-10-01 | 2022-10-11 | 2022-10-11 | 2022-10-28 | 2022-12-31 |  |  | 4111.98 | -4814.96 | 2000 | 956.85 |  |  | 957 | Red | [11 empty] | 5.3.23 JHB - Reaccrue $2k to B&E. Checking to see if this got picked up on another cost account. 4.3.23 JHB - Sample stations fixed per permit requirements. Accrue $2k to B&E. 3.16.23 JHB - additional cost of ~$3k to hit in March due to Environmental notification that Sample station tubing must be <=1/2" per our air permit. 2.1.23 JHB - Reaccrue $5k to b&E. 1.4.23 JHB - sample stations added to Dock 1 and 2. Accrue $5k to B&E,84.9k Precision Filtration. 12.1.22 JHB - developing water handling scope, cost, and schedule for presentation to Traf. Additional funding request will be submitted pending approval. 11.1.22 JHB - Sight flow indicators installed on tanks. Accrue $5k to Puffer, $1k to Ohmstede. 10.11.22 JHB - Project scope revised to in-line sight glasses, AFE routing for approval, FC approximately $10k based on new scope | 2023-05-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 1297 | 957 |  |  | 100054 |  | Johnson, AJ | Johnson, AJ |  |  | 1 | 45919 |  | Meitzler, Antoinette | Independent | Aqua | 2022-09-27 | Other Programs
BTXPP - Lab Satellite Waste Area | Item | Open | MCAP | BTXPP00M2210 | Maintenance Framework | 1991358 | Garcia, Monica | South | 6. Operational | Defined | South | 8736 |  |  | 8735.93 | 8555 | 181 | Yellow |  |  |  | 8736 |  |  | 88000 |  | 48000 | 136000 | Supplemental | 136000 | 137228 |  | 137228 | No | Green | 2022-06-01 | 2022-06-22 | 2022-06-22 | 2022-12-31 | 2022-11-04 |  |  | -4 | 4529 | 4029.6 | 181.33 |  |  | 181 | Red | [11 empty] | 4/3/23 MLG: Ready to close POs and work order. 3/1/23 MLG: Supplemental was approved, final invoices have been submitted and approved. No future charges. 2/2/23 MLG: Supplemental AFE has been submitted; project is complete and no future work is expected. Final invoices will be submitted into OpenInvoice as soon as the Supplemental is approved. 1/4/23 MLG: Variance is due to field installation issue. Supplemental has been developed and needs to be reviewed/discussed with REM. Work has been completed. 12/5/22 MLG Work is complete, lighting has been installed, no future work. Supplemental is in development and will be submitted for approval. 11/9/22 MLG: The increase in cost is due to the increase of the cost of materials from the time AFE was approved to the time when materials were purchased. In addition, the construction contractor quoted a different grade of steel as well as different steel connections when they submitted their proposal, the material was spec'd during engineering. The steel connections required clips and stiffeners which resulted in more fabrication by the contractor. After installation of the concrete pad ramps, it was determined that there was a construction error with the incline of 3 ramps. The toe of the ramps were extended in order to repair the incline angle; additional concrete was required. After the cover was installed, it was determined that light is needed under the cover due to the area being dark in the evening. A Supplemental will issued. 11/2/22 MLG: The variance from October is due to delays with schedule, contractor and commencing the AFE. 9/13/22 MLG-the monthly variance is due to delay in commencing the project. 8.2.22 Variance delayed due to AFE approval and detail design 1/4/22 MLG- Project scope of work and AFE development will begin in Jan 22. 12/1/21 MLG: Project work scheduled for 2022. 11/17/20 MLG- Project Manager changed to Monica Garcia. | 2023-04-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 8555 | 181 |  |  | 128492 |  | Johnson, AJ | Gee, Ryan |  |  | 1 | 34364 |  | Guest, ProSight | Independent | Aqua | 2019-08-23 | Other Programs
BTXPP - OWS Sump Piping Upgrades | Item | Open | MCAP |  | Maintenance Framework |  | Burke, Joshua | South | 1. Proposed |  | Storm Water Management |  | 80000 |  | 80000 | 80000 | 0 | Green | 80000 |  | 80000 | 0 | [9 empty] | 80000 | 80000 | No | Green | 2023-07-01 |  |  |  | 2023-04-28 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 0 | 40000 | 40000 | [5 empty] | 5.3.23 JHB - Pushed forecast out to Q3 based on current workload/priority. 3.9.23 JHB - Pushed forecast out 1 MO considering current workload/project priority. 3.1.23 JHB - AFE documents pending proposal from UPS. Adjusting forecast based on delayed start. 2.1.23 JHB - UPS developing cost estimate to replace 200 unit piping. Forecast adjusted based on anticipated timing. | 2023-05-03 |  |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 0 | 80000 |  |  |  | Bonenberger, Mark |  |  |  | 1 | 45559 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
BTXPP - Pond Cattail Reduction | Item | Open | MEXP | BTXPP00E2204 | Maintenance Framework | 1990654 | Garcia, Monica | South | 7. Closed | Defined | Secondary Containment | -1 |  |  | -0.85 | -1 | 0 | Green |  |  |  | -1 |  |  | 114000 |  |  | 114000 | Full | 114000 | 117441 |  | 117441 | No | Green | 2022-06-01 | 2022-06-15 | 2022-06-15 | 2022-12-31 | 2022-07-14 |  |  | -0.85 | [18 empty] | 3/1/23 MLG: Work Order closed 2/2/23 MLG: Environmental is confirming if all invoices have been submitted from Waste Management, otherwise, project is ready to close. 1/4/23 MLG: Waiting on final invoices from Waste Management. 11/5/22 MLG; The variance is due to a forecasting error. Once the cleanup was complete, all the roll off boxes had to sit onsite and wait for the US Ecology to provide the ok to remove the waste, which in turn would allow us to take roll off boxes off of rental. Due to a delay with the US Ecology, the waste, disposal fees, and the rental of the roll off boxes did not have an estimated date of removal. The boxes and waste were removed on 8/24/22, the estimated date of removal was a week after completion, but this took over a month. The US Ecology would not provide an estimated date for approval nor for invoicing as well. We were receiving rental costs while the roll off boxes remained onsite. 11/2/22 MLG- The accrual of $58k is for the Waste Management Sustainability Services. 10/11/22 - Negative actuals from dropped accruals, WM invoices amounted to less than expected. DC 10/4/22 MLG: variances are based on delays from invoicing from the US Ecology and the Waste Management Group due to roll off boxes remained onsite for an extended period of time. awaiting final invoices. Roll off boxes were removed 8/22/22. 9/13/22 MLG-awaiting final invoices; variances are based on delays from invoicing from the US Ecology and the Waste Management Group due to roll off boxes remained onsite for an extended period of time. 9.2.22 Total EAC reduced 19k from previous month 8/2/22 MLG: Variance due to delay with US Ecology and the Waste Management group. Cattails have been removed but cannot be removed offsite due to delay in materials verification, which in turn is causing additional daily charges for the roll off boxes. The Environmental group is pushing US Ecology for resolution. 7/5/22 MLG- Variance is due to the delay of the issuance of the AFE, therefore project got a late start. Clean up began 6//27/22. 6/8/22 MLG: The $94k overage will be supplemented from the MEXP Drawdown. | 2023-03-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | -1 | 0 |  |  | 117442 |  | Spari, Markella | Asiedu, Saka |  |  | 1 | 41920 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Other Programs
BTXPP - Propane Recirc Pump Seal Plan Replacements | Item | Open | MCAP | BTXPP00M2224 | Maintenance Framework | 2023843 | Garcia, Monica | South | 6. Operational | Defined | Rotating Equipment | 30397 | 15000 |  | 45396.63 | 32097 | 13300 | Red |  | 65000 | 65000 | -19603 |  |  | 79000 |  | 135000 | 214000 | Supplemental | 214000 | 171014 | 15000 | 186014 | No | Green | 2022-10-01 | 2022-09-28 | 2022-09-28 | 2022-12-15 | 2023-03-01 |  |  | -3132.84 | 13473.99 | 15755.94 | 4299.54 | 6000 | 6000 | -1700 | Red |  |  |  |  | 15000 | [6 empty] | 5/1/23 MLG: Future forecast is for the collection pots and installation. Awaiting invoices. 4/4/23 MLG: Punchlist items remain 3/1/23 MLG: The 6005 seal upgrade was completed today 3/1/23 and the project has been marked operational. A Supplemental will be submitted. 2/2/23: MLG: The 6007 seal failed and Reliability is going to conduct an investigation as to the cause, then these findings will be implemented into the 6005 seal upgrade. It is undetermined at this time as to when the 6005 seal upgrade will be implemented, although, they are projecting around March for the findings to be confirmed. 1/4/23 MLG: Reliability wants to install the 6005 seal, tubing, and orifice plates the first week of February. The 6007 seal upgrade has been running without any issues as of today. A Supplemental is being developed and will be submitted prior to work being completed. 12/5/22 MLG: The seal, seal pot, 5 orifice plates, and tubing has been installed for 6007; it is up and running. Reliability and Ops wants to run 6007 for sometime prior to installing the seal for 6005. Reliability wants to install remaining work for 6005 in 2023. Remaining work for 6005 is the installation of the seal, the tubing, and the 5 orifice plates. A Supplemental is in development and it will be submitted for approval. 11/9/22 MLG: It has been determined that orifice plates need to be installed, this will require additional piping material, fabrication, orifice plates, NDT, and labor; this will be a scope change and is in the process of being developed and will be submitted for approval. Once the scope change has been approved, a Supplement will submitted. This scope change is not being executed as part of the current schedule for the existing work. 11/2/22 MLG; Variance due to vendor long lead time and the availability of materials for fabrication. 10/4/22 MLG: seal pots have been ordered, and other equipment is being ordered as well. Part of the installation is anticipated to occur in October and the other part in November. 7/29/2022 - AFE was rejected due to needing more information. The seals have been approved. Once the AFE goes through there is a 6 week lead time. Installation to happen the first part of October. 5/31/2022 - Per the stake holder's request the AFE won't be submitted until August. 5/3/2022 - Meetings are being held with multiple stakeholders to determine the best seal solution. 4/11/2022 - The nitrogen on the seals were lowered and the Operational guidelines were updated on the pump. Additional training was given.3/31/2022 - Project on hold while a new OPs procedure is tried. 3/1/2022 - There is an onsite meeting with a vendor in mid March on a proposed seal. A decision will made on which manufacture to go with. 2/21/2022 - Working with multiple vendors on coming up with the correct seal and costs. 1/29/2022 - Working with Engineering andlocal ops to determine which is the best seal to use. | 2023-05-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 26097 | 4300 | 15000 |  | 140617 |  | Posipanko, Dan | Burke, Kevin |  |  | 1 | 42045 |  | Clark, David | Independent | Aqua | 2021-09-03 | Other Programs
BTXPP - SIS Testing procedures | Item | Open | MEXP | BTXPP00E2208 | Maintenance Framework | 2023747 | Garcia, Monica | South | 6. Operational | Drawdown | South | 1210 | 12545 |  | 13754.56 | 13755 | 0 | Green |  |  |  | 13755 |  |  | 158000 |  |  | 158000 | Full | 158000 | 137500 | 12545 | 150045 | No | Green | 2022-10-01 | 2022-09-27 | 2022-09-27 | 2023-03-31 | 2023-02-10 |  |  | 8177.28 | 8177.28 | -2600 | -12545 |  |  | -12545 | Red |  |  | 12545 | [8 empty] | 5/9/23 ML: Variance is due to an issue with the accrual file PMO recommended forecasting missing accruals for May. Re- Accrue 12k 5/1/23 MLG: No future forecast 3/1/23 MLG: No future forecasts 2/2/23 MLG: These test procedures are being reviewed and the intention is to test some of these procedures during the Unit 200 outage, which is scheduled for March and April. The forecast in May will be for any corrections to the procedures. 1/30/2023 MLG: Proof Test Procedures received on 12/22/2022 and needs to be reviewed by the Maintenance Supervisor and the Process Control Manager. The goal is to test 12 SIFs for Units 100 & 200 during the Unit 200 outage in March. The FSM report was received on 1/24/2023 and a meeting is scheduled for 2/3/2023 to discuss the draft. The BMS Verification report was received on 1/24/2023 and a meeting is scheduled on 2/6/2023 to discuss this report. 1/4/23 MLG: Variance is due to work completed ahead of schedule; work is 95% complete. 12/5/22 MLG: Work is 50% complete. 11/2/22 MLG: Variance is due to delay in Puffer-Sweiven schedule. 9/19/2022 AJ: Project getting pulled forward to this year with MEXP drawdown | 2023-05-09 | Landeros, Melisa |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 13755 | 0 |  |  | 136290 |  | Johnson, AJ | Johnson, AJ |  |  | 1 | 45551 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
BTXPP - Storm Drain Cleanout | Item | Open | MEXP |  | Maintenance Framework |  | Garcia, Monica | South | 1. Proposed |  | South |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 | [9 empty] | 50000 | 50000 | No | Green | 2023-08-01 |  |  |  | 2023-10-27 | [15 empty] | 25000 | 25000 |  |  |  |  | 4/3/23 MLG: Due to the Unit 200 outage focus and heavy traffic, scope development is tentatively being targeted for late April/ early March. 3/1/23 MLG: Scope development was not performed in February, it is tentatively scheduled for mid-to late March. 2/2/23 MLG: Scope development tentatively scheduled for mid-to late February. | 2023-04-03 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 0 | 50000 |  |  |  | Johnson, AJ |  |  |  | 1 | 41921 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Other Programs
BTXPP - Tank 1006 IFR Insp & Refurb | Item | Open | MCAP | BTXPP00M2217 | Maintenance Framework | 2014095 | Matthews, Clayton | South | 6. Operational | Emergent | Tanks | 591193 |  |  | 591193.23 | 556075 | 35119 | Yellow |  |  |  | 591193 |  |  | 445000 |  | 748124 | 1193124 | Full | 1193124 | 1078280 |  | 1078280 | No | Green | 2022-09-01 | 2022-08-31 | 2022-08-31 | 2022-11-15 | 2023-03-01 |  |  | 56100.13 | 399111.19 | 75863.18 | 60118.73 | 25000 | 25000 | 35119 | Red | [11 empty] | 5/3/23 CAM Project to be closed out 4.5.23 ML Accrue 321k Phillips Tk, 4.5k UPS, 3.3.23 CAM Forecast adjusted to accommodate growth of original scope. Accrue 15K ATP, accrue 1600 Applied consultant, accrue 19100 Knight, accrue 300K Phillips, accrue 5160 Saybolt, accrue 18K Vapor Point 2.2.23 ML - Accrue 1.2k Adler, 15k ATP, 3.4k Applied,6k Select Safety, 25k 3L, 91k WM CAM No january forecast changes at direction of management due to scope development and leadership decision on path forward. See below note. Feb/March forecast updated. 1/25/23-CES-Updating forecast to $325k per PM's estimate and agreement with leadership to repair existing AIFR and return to service. Funding from tank capital improvements program. 1/11/23 CAM No changes to forecast. Keeping as is at the direction of Tank Program Manager and Maintenance Manager. Forecast will be updated shorty upon approval of maintenance plan. 1/4/23 CAM Re accrue all. Accrue 3k Knight. 12/2/22 CAM Accrue 12k Adler, Accrue 4700 Applied Consultant, Accrue 5500 DJA, Accrue 45k Eisco, Accrue 5600 Select Safety, Re accrue 27k 3L, Re accrue 60k WM. 11/2/22 CAM Re Accrue 10k Adler, Accrue 20k ATP, re accrue 120k Environmental industrial, re accrue 29k FHG, re accrue 3700 Ohmstede, re accrue 27000 Three L BECHT ops/engineering evaluation continuing. No new spends until RCA conclusion. Working with regional and program management on path forward. Open bid event with supply chain for OWSBL potential IFR replacements. 10/28/22 CAM 10,000 Designated for additional STX safety rep. 10/3/22 CAM Accrue 10k Adler, Accrue accrue 14k ATP, accrue 120k Environmental industrial, accrue 29k FHG, accrue 3700 Ohmstede, accrue 27000 Three L 9/2/22 CAM AFE Approved 9/1/22. OOS Compliance date is now 9/16/22. Cleaning bid open in Coupa. Forecast verified. | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 531075 | 60119 |  |  | 487087 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 45149 |  | Guest, ProSight | Independent | Aqua | 2022-08-22 | Int - Tanks
BTXPP - TK 2002 - Gauge Pole Negotiator Plate repair on IFR - 2022 | Item | Open | MEXP | BTXPP00E2212 | Maintenance Framework | 2036814 | Matthews, Clayton | South | 6. Operational | Drawdown | South | -16922 | 15091 |  | -1831 | 12518 | -14349 | Red |  |  |  | -1831 |  |  | 30000 |  |  | 30000 | Full | 30000 | 10232 | 15091 | 25323 | No | Green | 2022-11-01 | 2022-10-12 | 2022-10-12 | 2022-11-30 | 2022-11-30 |  |  | -1932.5 | 10.5 | 14440 | -29440 |  |  | -29440 | Red |  | Other | 15091 | [8 empty] | 5.2.23 ML Re Accrue 15K FHG Variance due to Accrual Error & an issue with the accrual file PMO recommended forecasting missing accruals in May 4.5.23 ML Re Accrue 29K FHG, 3.3.23 CAM Re Accrue 15K FHG, 2.2.23 ML Re Accrue 15K FHG, 1/4/23 CAM Re Accrue 15K FHG, Accrue 5500 Select Safety. 12/2/22 CAM Accrue 15K FHG, Accrue 3500 Select Safety. Work Executing 11.3.22 | 2023-05-09 | Landeros, Melisa |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 12518 | -14349 |  |  | 27154 |  | Johnson, AJ | Stine, Carlton | N/A |  | 1 | 46062 |  | Johnson, AJ | JDE Child | Burnt Orange | 2022-10-12 | Other Programs
BTXPP - Unit 200 Turnaround - 2023 | Item | Open | MCAP | BTXPP00M2301 | Maintenance Framework | 2052408 | Garcia, Monica | South | 6. Operational | Defined | South | 1567438 | -322044 |  | 1245393.86 | 1042704 | 202690 | Red | 1100000 |  | 1100000 | 145394 |  |  | 999834 |  |  | 999834 | Full | 999834 | 1644163 | -322044 | 1322119 | Yes | Red | 2022-12-01 | 2023-03-11 | 2023-03-11 | 2023-04-30 | 2023-04-28 |  |  | 131703.78 | 117399.63 | 593600.67 | 724733.78 | 200000 | 200000 | 524734 | Red |  | Other | -337044 |  | 15000 | [6 empty] | 5/1/23 MLG: Variance is due to Amortization and OPEX costs being charged to MCAP, these costs are being evaluated and will be reclassed to the appropriate category as necessary. There is a future forecast due to equipment with a long lead time, this equipment can be installed outside of the outage. 4/4/23 MLG: Some of the project actuals will be reclassed to Amortization and/or OPEX based on the equipment and work being performed. 3/10/23 MLG - Variance is due to costs not being reclassed at this time. Costs will be reclassed due to some costs will go towards Amortization and OPEX. Only one work order exists at this time, which is this MCAP work order number. 3/1/23 MLG: The MCAP projected forecast is $1MM. Full AFE submitted on 3/1/23. 2/2/23 MLG: Received full AFE submission extension for March 1st to allow for additional scopes that were submitted after the scope freeze. These scope changes were due to discovery findings or inspections performed after the scope freeze. The projected forecast has increased to approximately 2.2MM and the Unit outage has been moved to March and will carry into April, on will be on a 24 hour schedule for 10 days. 1/4/23 MLG: The outage is scheduled to begin on Feb 26th and is scheduled to last for 10 days, on a 24 hour schedule. | 2023-05-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 842704 | 387690 | 15000 |  | 76725 |  | Johnson, AJ |  |  |  | 1 | 45944 |  | Clark, David | Independent | Aqua | 2022-09-30 | Other Programs
BTXPP - Vessel V-5015 OOS Inspection | Item | Open | MEXP | BTXPP00E2210 | Maintenance Framework | 2036766 | Bryant, Ben | South | 6. Operational | Defined | Pressure Vessels | -29101 |  |  | -29101.05 | -29101 | 0 | Green | 50000 |  | 50000 | -79101 |  |  | 125000 |  | 75002 | 200002 | Supplemental | 200002 | 189644 |  | 189644 | No | Green | 2022-11-01 | 2022-10-12 | 2022-10-12 | 2022-12-31 | 2022-12-31 |  |  | 8904.7 | -38005.75 | 0 | 0 |  |  | 0 | Green | [11 empty] | 5/1/23 Re-Accrue Waygate for 43K. 4/3/23 Re-Accrue Waygate for 43K. Supplemental AFE has been approved. 3/2/23 - Re-accrue Waygate Tech for $43K. Working on supplemental AFE. Vendor having issue with their invoicing. Their credit posted and the original invoice is being re-done for $43K. 2/1/23 Re-accrue 40K to Waygate. 3K to Rosemont. 1/2/23 Accrue 40K to Waygate. Accrue $700 to Advanced Corrosion Technologies & Training 10K to UPS 12/1/22 PV 5015 inspection completed this week. Accrue $102K USES. 11/2/22 Pressure Vessel 5015 has been emptied and degassed. Tank floor was cleaned with human-less entry. However, some sludge and debris remained. Conducting review to allow human entry into vessel. Variance was due to longer time needed to gas free pressure vessel. A supplemental AFE will be required. 10/3/22 AFE has been presented. Awaiting approval for routing. Looking to complete Inspections the week of Oct 24th. 9/12/22 While we are waiting for Trafigura to grant permission to begin. Moved portion to 2023. 4/1/22 Project meeting will be set up this month to discuss taking this tank out of service. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Tank Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | -29101 | 0 |  |  | 218745 |  | Stine, Carlton | Shook, Mark B. |  |  | 1 | 41346 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
BTXPP - Vessel V-5024 OOS Inspection | Item | Open | MEXP | BTXPP00E2209 | Maintenance Framework | 2036818 | Bryant, Ben | South | 6. Operational | Defined | Pressure Vessels | 192743 |  |  | 192742.81 | 207162 | -14419 | Yellow | 50000 |  | 50000 | 142743 |  |  | 125000 |  | 107100 | 232100 | Supplemental | 232100 | 194945 |  | 194945 | No | Green | 2022-11-01 | 2022-10-13 | 2022-10-13 | 2022-12-31 | 2023-02-28 |  |  |  | 170174.93 | 36986.93 | -14419.05 |  |  | -14419 | Red | [11 empty] | 5/1/23 Supplemental AFE has been approved. Accrue 54K to Catspec. 32K to Miller environmental. 4/3/23 Accrue 89K to Vapor Point, 25K to Waygate, 54K to Cat Spec. Supplemental AFE ready for routing. 3/2/2023 - Accrue $89K to Vapor Point & $20K to UPS & $23K for Waygate Tech. PM working on supplemental AFE. . 2/1/23 Project was moved from the week of January 9th to the week of January 30th due to Operational and customer needs. Bullet was switched to 5024. 5024 degassing is in progress. 1/2/23 Jan 9th will take PV 5002 OOS for Inspection. 12/9/22 Operations has notified me move of this project to the week of Jan 9th. This will carryover $125K to next year. 12/1/22 The week of December 12th we will take this Vessel out of service to conduct inspection. 11/2/22 Due to a damaged heat exchanger, PV 5002 had to stay in service. We are looking to tentatively take the vessel out of service the first week of December. 10/3/22 AFE has been presented. Awaiting approval for routing. Looking to complete Inspections the week of Oct 24th. 9/12/22 While we are waiting for Trafigura to grant permission to begin. Moved portion to 2023. 4/1/22 Project meeting will be set up this month to discuss taking this tank out of service. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Tank Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 207162 | -14419 |  |  | 2202 |  | Stine, Carlton | Shook, Mark B. |  |  | 1 | 41345 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
BTXPP 100/200 E-101B Exchanger Rerate and Piping Upgrade | Item | Open | MCAP | BTXPP00M2302 | Maintenance Framework | 2073868 | Burke, Joshua | South | 6. Operational | Defined | South | 32454 |  |  | 32453.73 | 32454 | 0 | Green | 30000 |  | 30000 | 2454 |  |  | 30885 |  |  | 30885 | Phase | 30885 | 32454 |  | 32454 | No | Green | 2023-01-01 | 2022-12-29 | 2022-12-29 | 2023-03-05 | 2023-02-28 |  |  | 29000 | 3305 | 148.73 | 0 |  |  | 0 | Green | [11 empty] | 5.3.23 JHB - Reaccrue $2k to Becht - need to issue CO for this $2k. 4.3.23 JHB - Reaccrue $31k to Becht. 3.1.23 JHB - Accrue $31k to Becht, project ready to close pending final invoicing. 2.1.23JHB - Becht completed evaluation and issued recommendations. $2k additional work required to design supports. Improvements scope to be covered under outage project. Accrue $29k to Becht. $2k added to FEB for support design. 1.4.23 JHB - AFE approved, Becht conducting evaluation in January to provide recommendations by end of month. 12.1.22 JHB - Becht contacted to develop proposal for rerate evaluation/recommendations. Phase 1 AFE to be developed based on this cost. | 2023-05-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 32454 | 0 |  |  |  |  | Johnson, AJ | Johnson, AJ |  |  | 1 | 44051 |  | Guest, ProSight | Independent | Aqua | 2022-06-29 | Other Programs
BTXPP Boiler System Deaerator Inspection | Item | Open | MEXP |  | Maintenance Framework |  | Garcia, Monica | South | 1. Proposed |  | Boilers |  | 20000 |  | 20000 | 20000 | 0 | Green | 20000 |  | 20000 | 0 | [9 empty] | 20000 | 20000 | No | Green | 2023-07-01 |  |  |  | 2023-06-30 | [14 empty] | 20000 | [6 empty] | 3/1/23 MLG: Actively working on scope, although, the inspection team is limited in time and resources due to the Unit 200 outage, and does not anticipate with scope development until mid-April. 2/2/23 MLG: Actively working on scope development. | 2023-03-01 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 0 | 20000 |  |  |  | Stine, Carlton |  |  |  | 1 | 44740 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Other Programs
BTXPP Bunkered Pressure Vessel Structural Inspection | Item | Candidate | MEXP |  | Maintenance Framework |  | Bryant, Ben | South | 1. Proposed |  | Pressure Vessels |  | 20000 |  | 20000 | 20000 | 0 | Green | 20000 |  | 20000 | 0 | [9 empty] | 20000 | 20000 | No | Green | 2023-06-01 |  |  |  | 2023-05-31 | [13 empty] | 20000 | [11 empty] | South | Pipelines and Terminals | Tank Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 20000 |  |  |  |  | Stine, Carlton |  |  |  | 1 | 45280 |  | Stine, Carlton | Independent | Aqua | 2022-08-25 | Int - Tanks
BTXPP CUI Program Development | Item | Open | MEXP |  | Maintenance Framework |  | Garcia, Monica | South | 1. Proposed |  | Facility Integrity |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 | [9 empty] | 40000 | 40000 | No | Green | 2023-08-01 |  |  |  | 2023-07-31 | [15 empty] | 20000 | 20000 |  |  |  |  | 4/3/23 MLG: This project will be worked in concert with the BTXPP LPG API 570 because the LPG lines have insulation. 3/1/23 MLG: Continuing to work with Reliability on the scope; held a meeting with a contractor to discuss our goals in conjunction with their ability to achieve our goals. 2/2/23 MLG: Actively working with Reliability on scope development. | 2023-04-03 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 0 | 40000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 44992 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
BTXPP East Combustor Burner Replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Burke, Joshua | South | 1. Proposed |  | South |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 | [9 empty] | 50000 | 50000 | No | Green | 2023-06-01 |  |  |  | 2023-05-31 | [12 empty] | 0 | 50000 | [7 empty] | 5.3.23 JHB - Hot spot observed during operation in April 2023. Maintenance repairs and supplemental inspeciton performed. James Dalton is developing revised SOW along with AFE documents. 3.1.23 JHB - Inspection report indicates repairs needed are assist gas lance replacement, Kao wool replacement in small areas, and rain guard plate replacement. Zeeco preparing proposal for assist gas lance. Project may be handed off to James Dalton. Moving FC to June - will update pending lance lead time. 2.1.23 JHB - Inspection report received and reviewed. Need to engage suppliers/contractors to develop cost estimates. | 2023-05-03 |  |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 50000 |  |  |  |  | Johnson, AJ |  |  |  | 1 | 43711 |  | Clark, David | Independent | Aqua | 2022-05-11 | Other Programs
BTXPP LPG API 570 Program Development and Phase 1 Inspection | Item | Open | MEXP |  | Maintenance Framework |  | Garcia, Monica | South | 1. Proposed |  | Facility Integrity |  | 200000 |  | 200000 | 200000 | 0 | Green | 200000 |  | 200000 | 0 | [9 empty] | 200000 | 200000 | No | Green | 2023-05-01 |  |  |  | 2023-12-29 | 8 | Yellow | [10 empty] | 25000 | 25000 | 30000 | 30000 | 30000 | 30000 | 30000 |  |  | 4/3/23 MLG: Spoke with Sentinel to discuss the development of the LPG systems and circuits based on the ITP from Becht. Meeting scheduled for the second week of April. Drawings and PFDs have been sent to them for scope development. 3/1/23 MLG: Held a meeting with Becht on 3/1/23 to discuss and review the ITP plan they developed. There were several action items that were identified, this will aid in AFE development, as well as the multi-year plan for program development. 2/2/23 MLG: Actively working with Reliability on scope development. 10/31/22 AJ: removed the 50k forecast this year since a new project was created for phase 1. 10/25/22 AJ: Pulling project forward. 2022 funds (50k) Project will be funded from South Region MEXP drawdown | 2023-04-03 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 50000 | 90000 | 60000 |  |  | Aiken, Elaine |  |  |  | 1 | 44994 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
BTXPP OSBL Flare Modifications | Item | Open | MCAP | BTXPP00M1611 | Exempt | 1219424 | De Leon, Maria | South | 6. Operational | Unplanned | South | 461971 |  |  | 461971 | 442078 | 19893 | Yellow |  |  |  | 461971 |  |  | 1936000 | 3402000 |  | 5338000 | Full | 5338000 | 5944712 |  | 5944712 | Yes | Red | 2020-01-01 | 2016-12-21 | 2016-12-21 | 2018-07-31 | 2020-11-09 |  |  |  |  | 442077.51 | 19893.49 |  |  | 19893 | Red | [11 empty] | 4.11.23 ML - Variance is due to an unforseen RCL from RCAP processed by Property Accounting. 4.5.22 per MDL- (Variance is due to unpaid POs - PCA is working with Vendors to determine if we can cancel open POs ) Working with Ben Clark / PMO to transfer $90K on fencing and Connex boxes that were not part of OSBL Flare project. Puchase Orders shows fencing belonged to another project and another facility. Need to complete 1-day programming to ensure only one-blower is running and remove cross over piping then can close project. 1.11.22 Needing to correct programming to ensure only one VFD is operating at one time. Once relcass is complete and programming can close project. 7-6-21 - Property accounting working with Maria to move out some of the dollars. Currently, no supplemental is required. More reclasses to occur. MC 6-17-21 - Needs supplemental AFE MC 9/20/20 MD - Construction is 99% complete and we are working on commissioning the new flare. 4/9/20 SF - Civil and Mechanical construction is continuing. I&E construction began 4/6. Project is on budget and on schedule. 2/5/20 SF - Construction has Started and Full AFE has been Approved 11/8/19 SF - Looking for Construction Kickoff in Nov 10/3/19 MD - Engineering should be complete by end of Oct 9/5/2019 MD - OSBL Flare Permit Approved. Target construction start date October. 7/15/2019 ML -OSBL Flare permitting approval moved another month out and forecasting was adjusted to reflect as such. 1/4/2019 LL - OSBL Flare construction package to be issued for bid. 12/08/2018 LL - OSBL pipe rack complete. OSBL flare construction package to be issued for bid. 11/5/2018 LL - work is complete for pipe rack work other than spreading of some soil. the weather continued to impede this. 10/03/2018 LL - rain delays working on footers. work will progress thru early October. 09/04/2018 LL - Move spending to 2019 based on vent permit. Main rack complete, working on footersand grounding. 08/01/2018 LL - Piperack under construction 07/05/2018 LL - 80% of piperack to be installed July/Aug to support Oil/Gas project which requires the road crossing. 06/05/2018 LL - PSD permit has shifted to end of Sept. 05/01/2018 LL - PSD permit has shifted to end of August. PO issued for hot tap vendor. Work on construction bid package continues as time permits. 4/17/2018 - PMO - $150K forecast in Dec'18 shifted to Jan'19 for MCAP reductions. 4/10/2018 BMR - Per conversation with S White. Updated forecast to reflect current schedule of receiving PSD permit(July). Existing flare to be removed in 2019. 4/5/2018 KK - PVF in paint shop, PO issued for structural steel and helical piles. Re-engineered change to hot tap location. Site environmental permit shifted to June. SOW for overall construction package still in process of assembly.3/5/2018 LL - procured PVF, bid out on structural steel and helical piles. Mtg with Operations changed location of one hot tap. SOWfor overall construction package in process. Intent is still to issue assoon as complete. Site environmental permit has moved toMay. 2/2/2018 -LL- Magnum issued IFC package. Piping/valve package issued for bid. Hot tap package bids received. Construction packages to be created for Flare assembly, and SOW for overall construction package. Goal is to issue before end of Feb. Waiting on siteenvironmental permit to begin construction which is still an April forecast. 01/04/2018-LL-Flare and misc parts arrived on site in DEC. Magnum is wrapping ENGR, estimatedcompletion JAN. Construction bids estimated to be issued end of Jan or early Feb for budgetary numbers. 12/8/2017 BMR/LL - No new update. 11/7/2017 - PB/LL - engineering complete in November, vent permit forecast isfor April 2018. 9/8//17 LPL - Fabbing of Flare stackis 30% completed. Electrical equipment has been order, deliveryin December. 08/7/2017 PB - Engineering is nearing completion. Flare stack is in fabrication. Flow meter and analyzer purchase orders under review. Phase 3 AFE to be submitted in August 2017. Environmental permit expected in Mid December to late January. 7/10/2017 BMS: flare drawings received and reviewed. Phase III AFE to be submitted this week. Lee Luetge will be taking overthis project. 6/8/17: HSSE group has determined that construction cannot begin until PSD application is received from TCEQ. Updated forecast to reflect start of construction in January 2018. Project schedule is at risk of slipping if Tile V permit is notreceived. 3/9/17: Investigating change in flare siting. Cost estimates for location options are being developed. Current forecast is based on moving the flare location to the east side of the property. 9/9: 2016 forecast reflects engineering and material purchase for most likely option: gas assist. Engineering costs will increase and overall project cost will increase if another option is chosen. 9/7: FEED study ongoing to include permitting/modeling. Operational date has been updated to 2017. Operational date will depend on availability of funds, final solution chosen, and permitting requirements. Project submitted as MCAP | 2023-04-11 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 442078 | 19893 |  |  | 7765 |  | Johnson, AJ | Burke, Kevin | N/A |  | 1 | 18869 |  | Guest, ProSight | Independent | Aqua | 2016-04-15 | Other Programs
BTXPP Site survey to verify secondary containment volumes | Item | Open | MEXP | BTXPP00E2306 | Maintenance Framework | 2110559 | Dalton, James | South | 3. Active | Defined | Secondary Containment | 16000 | 18000 |  | 34000 | 48000 | -14000 | Red | 48000 |  | 48000 | -14000 |  |  | 45295 |  |  | 45295 | Full | 45295 | 16000 | 18000 | 34000 | No | Green | 2023-04-01 | 2023-04-12 | 2023-04-12 | 2023-12-31 | 2023-05-31 | [5 empty] | 16000 | 30000 | 30000 | -14000 | Red |  | Forecasting | 18000 | [8 empty] | 4.3.23 JHB - AFE routing for approval. Diamond Z scheduled to perform survey mid-April. Adjusting FC to reflect partial engineering effort in May. 3.1.23 JHB - James Dalton preparing AFE documents. 2.1.23 JHB - proposal received from Diamond Z. Developing AFE documents. | 2023-04-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 34000 |  |  |  |  | Spari, Markella | Johnson, AJ |  |  | 1 | 45127 |  | Spari, Markella | Independent | Aqua | 2022-08-22 | Other Programs
BTXPP Tank V-5008 - Pressure Vessel API 510 Internal Inspection | Item | Open | MEXP | BTXPP00E2302 | Maintenance Framework | 2085575 | Bryant, Ben | South | 3. Active | Defined | Pressure Vessels |  | 150000 |  | 150000 | 150000 | 0 | Green | 150000 |  | 150000 | 0 |  |  | 150150 |  |  | 150150 | Phase | 150150 |  | 150000 | 150000 | No | Green | 2023-06-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-07-31 | [13 empty] | 50000 | 100000 | [6 empty] | 5/1/23 Authorization to begin project will be aimed for either the week of May 15th or May 22nd. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Tank Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 50000 | 100000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44743 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
BTXPP Tank V-5001 - Pressure Vessel API 510 Internal Inspection | Item | Open | MEXP | BTXPP00E2301 | Maintenance Framework | 2085568 | Bryant, Ben | South | 3. Active | Defined | Pressure Vessels |  | 150000 |  | 150000 | 150000 | 0 | Green | 150000 |  | 150000 | 0 |  |  | 150150 |  |  | 150150 | Phase | 150150 |  | 150000 | 150000 | No | Green | 2023-06-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-07-31 | [13 empty] | 50000 | 100000 | [6 empty] | 5/1/23 Authorization to begin project will be aimed for either the week of May 15th or May 22nd. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Tank Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 50000 | 100000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44742 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
BTXPP-FGR-Replace Hoses with Hard Pipe | Item | Open | MCAP | BTXPP00M2303 | Maintenance Framework | 2073927 | Burke, Joshua | South | 6. Operational | Unplanned | South | 21864 |  | 5000 | 21863.88 | 21864 | 0 | Green |  |  |  | 21864 |  |  | 58268 |  |  | 58268 | Full | 58268 | 21864 | 5000 | 26864 | No | Green | 2023-01-01 | 2022-12-29 | 2022-12-29 | 2023-01-31 | 2023-03-24 |  |  | 12000 | 20540 | -10676.12 | [15 empty] | 5000 | 5.3.23 JHB - Need to reclass from BTXPP00M2201 4.3.23 JHB - Work complete 3.1.23 JHB - Installation now scheduled for March due to prioritization of other work by contractor - FC adjusted accordingly (on-site maintenance contractor). Reaccrue $12k to UPS. 2.1.23 JHB - Fabrication complete, pending final paint for install. Installation planned for early FEB. Reaccrue $12k to UPS. Remainder pushed to FEB for install. 1.4.23 JHB - Fabrication 90% complete, installation planned for January. Accrual captured under BTXPP boiler & cooling tower reroute (dollars were shifted from that project to this one). $17k FC added to January to account for installation. | 2023-05-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 21864 | 0 |  |  |  |  | Johnson, AJ | Johnson, AJ |  |  | 1 | 46401 |  | Johnson, AJ | Independent | Aqua | 2022-12-23 | Other Programs
BTXPP-Upgrade 15 Burner Pilot Tips on 100/200 Unit Burners | Item | Open | MCAP | BTXPP00M2211 | Maintenance Framework | 2002071 | Burke, Joshua | South | 7. Closed | Unplanned | South | 724 |  |  | 723.93 | 724 | 0 | Green |  |  |  | 724 |  |  | 18000 |  |  | 18000 | Full | 18000 | 15278 |  | 15278 | No | Green | 2022-07-01 | 2022-07-06 | 2022-07-06 | 2022-08-31 | 2022-08-31 |  |  |  |  | 723.93 | [16 empty] | 1.4.23 JHB - project ready for closeout. 12.1.22 JHB - Reaccrue $12k, work complete 11.1.22 JHB - Reaccrue $17k - work complete. 10.3.22 JHB - Re-accure $17k 9.1.22 JHB - Re-accure $17k 8.1.22 JHB - Pilot tips received and installed, Accrue $12k to John Zink, $5k to Buckeye | 2023-03-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 724 | 0 |  |  | 14555 |  | Johnson, AJ | Burke, Kevin |  |  | 1 | 44046 |  | Guest, ProSight | Independent | Aqua | 2022-06-29 | Other Programs
BTXXW TK 1001 Bottom Replacement | Item | Open | MCAP | BTXXW00M2102 | Maintenance Framework | 1908589 | Matthews, Clayton | South | 6. Operational | Defined | Tanks | -14953 |  | 92000 | -14952.93 | -14953 | 0 | Green |  |  |  | -14953 |  |  | 400000 | 967000 |  | 1367000 | Full | 1367000 | 1244687 | 92000 | 1336687 | No | Green | 2021-11-01 | 2021-11-02 | 2021-11-02 | 2022-03-15 | 2022-03-15 |  |  | 52 | -11493.68 | -3511.25 | [15 empty] | 92000 | 3.3.23 CAM Close project. WM invoice less than previously accrued 2.2.23 ML - Re accrue 20k WM 1/4/23 CAM Re accrue 20k Wm 12/2/22 CAM Re accrue 20K WM 11/2/22 CAM Re Accrue 4.5k to Adler, Re-Accrue 20k WM Tank remains Idle 10/3/22 CAM Accrue 4.5k to Adler, Re-Accrue 20k WM Variance - Customer opted continue to keep tank idle. Blind remove did not happen. Unknown date future blind removal 9/2/22 CAM 8.2.22 Accrue 4.5k to Adler, Re-Accrue 20k WM 8.2.22 Re-Accrue 5k to Adler, 20k WM 6.1.22 CAM Tank is still isolated and on standby for customer RTS notification. Forecast for september blinding removal is accurate. Accrue 7k Adler, 20 WM 5/4/22 CAM all field work completed. Final invoicing/closeout. 4.1.22 Cost far less than Originally Estimated 3/1/22 CAM Accrue 100,000 WV Paint, 25,000 American Tank, 26,5k Select Safety, 20,000 WM, 5,000 Ohmstede, 5,000 Adler, 16k Knights Industrial, 6k Hydrochem Variance is due to savings on internal coating and strapping vendor mobilization (Saybolt). Contingency removed. 12/2/21 AFE Approval sitting with PMO there is a potential 80k to 100k reduction in December Accruals pending AFE approval and contractor mobilization. 11/18/21 CAM Product removal complete 11/9/21 CAM Cleaning crew mob | 2023-03-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXXW - George West |  | -14953 | 0 |  |  | 572113 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41266 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Cactus Hub Reclass MEXP | Item | Open | MEXP | BTXHF00E2202 | Maintenance Framework | 1945609 | Johnson, AJ | South | 4. On-Hold | Emergent | South |  | 1 |  | 1 | 1 | 0 | Green |  |  |  | 1 |  |  | 1272200 |  |  | 1272200 | Full | 1272200 |  | 1 | 1 | No | Green | 2023-12-01 | 2022-02-01 | 2022-02-01 | 2022-02-28 | 2023-12-31 | [19 empty] | 1 |  |  |  | Rodela, Robert |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  |  | 0 |  | 1 |  |  | Johnson, AJ |  |  |  | 1 | 42843 |  | Meitzler, Antoinette | Independent | Aqua | 2022-02-01 | Other Programs
Charleston Remove diesel line dead leg | Item | Open | MEXP |  | Maintenance Framework |  | Magouirk, Josh | South | 1. Proposed |  | Facility Integrity |  | 15000 |  | 15000 | 15000 | 0 | Green | 15000 |  | 15000 | 0 | [9 empty] | 15000 | 15000 | No | Green | 2023-07-01 |  |  |  | 2023-06-30 | [14 empty] | 15000 | [10 empty] | South | Pipelines and Terminals | Station/Terminal |  | Southeast Terminals | BETQH - BET NORTH CHARLESTON TERMINAL |  |  | 0 | 15000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45632 |  | Administrator, System | Independent | Aqua | 2022-08-30 | Int - Planned Corr & FI
Charleston Secure low point drains near the shoreline. | Item | Open | MCAP | BETQH00M2301 | Maintenance Framework | 2096480 | Pitkin, Colton | South | 3. Active | Drawdown | Facility Integrity |  | 27721 |  | 27721 | 25000 | 2721 | Red | 30000 |  | 30000 | -2279 |  |  | 27721 |  |  | 27721 | Full | 27721 |  | 27721 | 27721 | No | Green | 2023-05-01 | 2023-03-29 | 2023-03-29 | 2023-07-15 | 2023-07-31 | [12 empty] | 25000 | 2721 | [7 empty] | 3/23- Project presented and approved 3/27- AFE submitted | 2023-05-03 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | Southeast Terminals | BETQH - BET NORTH CHARLESTON TERMINAL |  |  | 27721 |  |  |  |  | Aiken, Elaine | Johnson, AJ |  |  | 1 | 45633 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Int - Planned Corr & FI
Charleston Verify #6 oil line idled | Item | Open | MEXP |  | Maintenance Framework |  | Magouirk, Josh | South | 8. Canceled |  | Facility Integrity |  | 0 |  | 0 | 0 | 0 | Green | 15000 |  | 15000 | -15000 | [9 empty] | 0 | 0 | No | Green |  |  |  |  | 2023-04-30 | [13 empty] | 0 | [7 empty] | 2/2/2023 Confirmed 6 Oil line is idled. Will clear out forecast and cancel project. | 2023-02-02 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Southeast Terminals | BETQH - BET NORTH CHARLESTON TERMINAL |  |  | 0 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45631 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Int - Planned Corr & FI
Charlotte I (BSEVC) Tank 13 OOS Corrosion Inspection and Refurb | Item | Open | MCAP | BSEVC00M2202 | Maintenance Framework | 2011936 | Bryant, Ben | South | 7. Closed | Drawdown | Tanks | 154873 |  |  | 154873.11 | 154969 | -96 | Yellow |  |  |  | 154873 |  |  | 226000 |  |  | 226000 | Phase | 226000 | 258878 |  | 258878 | No | Green | 2022-09-01 | 2022-08-10 | 2022-08-10 | 2022-12-31 | 2023-02-28 |  |  | 96532.17 | 55920.6 | 2516.43 | -96.09 |  |  | -96 | Red | [11 empty] | 5/1/23 All invoicing has been received. 4/3/23 Accrue 52K to FHG. Tank back in Service. Waiting Completion of invoicing. 3/2/2023 - $52K to FHG. Tank back in service. Waiting completion of invoicing. 2/1/23 Repair crew has completed repairs for this tank. Coating being applied to the floor. Accrue 52K to FHG, 14k to American Tank Partners, and 15K to Barr None. 1/2/23 Repair crew will be mobilizing to start repairs the week of Jan 16. Painting Contractor will be onsite at completion of repairs. 12/9/22 Repair contractor will be onsite the first week of January. This will move 180K carryover to next year. 12/1/22 Tank Bottom needed to be scanned again for verifications of indications. We brought in HMT Inspection to conduct scanning. Repair was pushed back causing forecasting error. Accrue 10K to DJA, $9k HMT. Should floor need new bottom, tank will need to carryover into 2023. 11/2/22 Tank was taken out of service this week for API 653 Inspection. Tank will be cleaned this week and DJA will be onsite next week for Inspection. Accrue 10K to W9Y. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | North Carolina | BSEVC - CHARLOTTE I TERMINAL |  | 154969 | -96 |  |  | 104005 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 43522 |  | Stine, Carlton | Independent | Aqua | 2022-04-25 | Int - Tanks
Charlotte II (BSEVD) Tank 6G OOS Corrosion Inspection and Refurb | Item | Open | MCAP | BSEVD00M2202 | Maintenance Framework | 2011937 | Bryant, Ben | South | 6. Operational | Drawdown | Tanks | 105820 |  |  | 105819.73 | 99047 | 6772 | Yellow | 100000 |  | 100000 | 5820 |  |  | 301000 |  |  | 301000 | Phase | 301000 | 232700 |  | 232700 | No | Green | 2022-11-01 | 2022-08-10 | 2022-08-10 | 2022-12-31 | 2023-03-01 |  |  | 92968.82 | 5605.37 | 473.24 | 6772.3 |  |  | 6772 | Red | [11 empty] | 5/1/23 Re-accrue 3K to Barr None. 4/3/23 Re-accrue 3K to Barr None. Awaiting Invoicing. 3/2/2023 - $3K to Barr-None. Tank back in service. Awaiting final invoicing. 2/1/23 Repair crew has completed repairs and tank liner has been applied. Tank has been buttoned up. Legs will be set this week. Please accrue 34k to FHG, 37K to Barr none, 18K to W9Y and 26K to ATP. 1/2/23 Repair crew mobilizing to site to begin repairs. Tank floor will be coated at the completion of the repair. Accrue $20k to FHG and $20K to Barr None 12/9/22 DJA has completed inspection. FHG will begin work the week of Dec 19th. Awaiting Unit Pricing from them. 12/2/22 Tank has been cleaned and inspection is in progress, 22K to GEMS, 7K to DJA 11/2/22 Tank will be taken out of service 11/14/22. Tank will be isolated, cleaned and inspected. 10/3/22 Tank will kick off at the end of the month. 5.10.22.DLC: Initial Forecast | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | North Carolina | BSEVD - CHARLOTTE II TERMINAL |  | 99047 | 6772 |  |  | 126880 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 43523 |  | Stine, Carlton | Independent | Aqua | 2022-04-25 | Int - Tanks
Chattanooga I (BSEVT) Tank 2 - OOS API 653 + Seal Insp & Refurb | Item | Open | MEXP | BSEVT00E2301 | Maintenance Framework | 2085554 | Bryant, Ben | South | 3. Active | Defined | Tanks | 134749 | 120000 |  | 254748.62 | 294000 | -39251 | Red | 300000 |  | 300000 | -45251 |  |  | 237050 |  |  | 237050 | Phase | 237050 | 134749 | 120000 | 254749 | No | Green | 2023-03-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-05-31 |  |  |  |  | 24000 | 110748.62 | 150000 | 150000 | -39251 | Red |  | Contractor/Vendor Issue | 120000 | [8 empty] | 5/1/23 Repairs have been delayed due to lead time items on seal and metal for sketch plates. Accrue 60K to FHG. 4/3/23 Tank has been Isolated and cleaned. Tank inspection is in progress. Accrue 10K to DJA Accrue 14 K to ATP. 9/23/22-CES-Reducing budget 10% for calibration. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Tank Integrity |  | Tennessee | BSEVT - CHATTANOOGA I TERMINAL |  | 24000 | 230749 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44790 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Chattanooga I (BSEVT) Tank 1 OOS Corrosion Inspection and Refurb | Item | Open | MCAP | BSEVT00M2201 | Maintenance Framework | 2011938 | Bryant, Ben | South | 6. Operational | Drawdown | Tanks | 181907 |  |  | 181907.2 | 180149 | 1759 | Yellow | 100000 |  | 100000 | 81907 |  |  | 254000 |  |  | 254000 | Phase | 254000 | 284019 |  | 284019 | No | Green | 2022-11-01 | 2022-08-10 | 2022-08-10 | 2022-12-31 | 2023-03-01 |  |  | 105930.63 | 51645.67 | 22572.23 | 1758.67 |  |  | 1759 | Red | [11 empty] | 5/1/23 - Re-accrue Barr-None $3K 4/3/23 Forecasting didn't include button up and Leg setting. Awaiting final invoice from Barr None. Accrue 3K to Barr None. 3/2/2023 - Tank back in service. Accrue $10K to W9Y. .2/1/23 Tank has been repaired. Liner will be added to this tank. Accrue 64K to Tarsco, 20K to ATP 20K to Barr None. 1/2/23 Purchase order has been awarded. Awaiting seal parts. 12/9/22 Awaiting unit pricing and schedule from contractor. 12/1/22 Tank has been cleaned and inspected. Repair contractor is reviewing the recommendations and preparing the unit price. 25K to W9Y. 11/2/22 Tank has been isolated. Tank will be cleaned this week. Tank will have DJA onsite next week for inspection. 9/2/22-CES-Tank cannot come OOS until November 1. Updating forecast to reflect a carryover into January. 5.10.22.DLC: Initial Forecast | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | Tennessee | BSEVT - CHATTANOOGA I TERMINAL |  | 180149 | 1759 |  |  | 102112 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 43526 |  | Stine, Carlton | Independent | Aqua | 2022-04-25 | Int - Tanks
Chattanooga II (BSEVF) Tank 20 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | BSEVF00E2301 | Maintenance Framework | 2085578 | Bryant, Ben | South | 3. Active | Defined | Tanks |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 |  |  | 11000 |  |  | 11000 | Phase | 11000 |  | 10000 | 10000 | No | Green | 2023-05-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-05-31 | [12 empty] | 10000 | [8 empty] | 5/1/23 Will schedule DJA for inspection. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Tank Integrity |  | Tennessee | BSEVF - CHATTANOOGA II TERMINAL |  |  | 10000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44791 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Chattanooga II (BSEVF) Tank 21 - OOS API 653 Insp | Item | Open | MCAP | BSEVF00M2301 | Maintenance Framework | 2094130 | Bryant, Ben | South | 3. Active | Defined | Tanks |  | 168013 |  | 168013 | 168013 | 0 | Green | 168013 |  | 168013 | 0 |  |  | 157499 |  |  | 157499 | Phase | 157499 |  | 168013 | 168013 | No | Green | 2023-06-01 | 2023-01-24 | 2023-01-24 | 2023-12-31 | 2023-08-31 | [13 empty] | 42003 | 84007 | 42003 | [7 empty] | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | Tennessee | BSEVF - CHATTANOOGA II TERMINAL |  |  | 42003 | 126010 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44792 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Chattanooga II (BSEVF) Tank 26 - OOS Seal Insp | Item | Open | MEXP | BSEVF00E2302 | Project Framework | 2085709 | Bryant, Ben | South | 8. Canceled | Defined | Tanks |  |  |  | 0 |  | 0 | Green | 108000 |  | 108000 | -108000 |  |  | 106150 |  |  | 106150 | Phase | 106150 |  |  |  | No | Green |  | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-11-30 | [21 empty] | 1/17/23-CES-Confirmed tank is in ULSD service (originally transferred over as gasoline per Magellan records) and seal inspection is not required per Air Compliance. Cancel project and remove forecast. Reset interval in BEST. | 2023-01-17 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Tank Integrity |  | Tennessee | BSEVF - CHATTANOOGA II TERMINAL |  |  | 0 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44793 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Chattnooga II (BSEVF) Vessel 104 - API 510 Inspection and PSM Refurbishments | Item | Open | MEXP | BSEVF00E2303 | Maintenance Framework | 2085580 | Bryant, Ben | South | 3. Active | Defined | Pressure Vessels |  | 60000 |  | 60000 | 60000 | 0 | Green | 60000 |  | 60000 | 0 |  |  | 66000 |  |  | 66000 | Phase | 66000 |  | 60000 | 60000 | No | Green | 2023-06-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-07-31 | [13 empty] | 50000 | 10000 | [8 empty] | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Tank Integrity |  | Tennessee | BSEVF - CHATTANOOGA II TERMINAL |  |  | 50000 | 10000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44751 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Doraville 1 TK 503 Pump Relief | Item | Open | MEXP | BSEVH00E2301 | Maintenance Framework | 2075810 | Leal, Trey (Tony) | South | 3. Active | Drawdown | South | 25000 | 5000 |  | 30000 | 30000 | 0 | Green |  | 33600 | 33600 | -3600 |  |  | 33600 |  |  | 33600 | Full | 33600 | 25000 | 5000 | 30000 | No | Green | 2023-04-01 | 2023-01-19 | 2023-01-19 | 2023-04-30 | 2023-04-30 | [5 empty] | 25000 | 30000 | 30000 | -5000 | Red |  |  | 5000 | [8 empty] | 5/1/2023 - Valve received. Piping is prefabricated. To be installed this week. Accrue $25k to W9Y 4/3/23 - Relief valve delayed, move forecast to April 1/27/2023 Working on getting PO's cut for material and contractor. Work to be completed in March - TL | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | Georgia | BSEVH - DORAVILLE I TERMINAL |  |  | 30000 |  |  |  |  | Johnson, AJ | Asiedu, Saka |  |  | 1 | 46431 |  | Guest, ProSight | Independent | Aqua | 2023-01-05 | Other Programs
Doraville I (BSEVH) Tank 502 Out of Service Corrosion Inspection and Refurb | Item | Open | MCAP | BSEVH00M2202 | Maintenance Framework | 1991847 | Matthews, Clayton | South | 6. Operational | Defined | Tanks | 714004 |  |  | 714003.79 | 711524 | 2480 | Yellow | 399000 |  | 399000 | 315004 |  |  | 407000 |  |  | 407000 | Phase | 407000 | 780086 |  | 780086 | No | Green | 2022-07-01 | 2022-06-27 | 2022-06-27 | 2022-12-31 | 2023-04-07 |  |  | 81850.52 | 377075.55 | 212597.99 | 42479.73 | 40000 | 40000 | 2480 | Yellow | [11 empty] | 5.2.23 ML Re-Accrue 55K Catsi, 35k FHG, 28k WM, 12k Valves, 15k W9Y Construction, 10k ATP 4.4.23 ML Re-Accrue 55K Catsi, 35k FHG, 28k WM, 85k West Virginia, 12k Valves, 15k W9Y Construction 3.3.23 CAM Forecast reduced for mechanical scope reduction and coating scope/hydro test addition (see note below-2.15.23) Accrue 10K Catsi, 5k W9Y Constr, 28k WM, 25k Knight, 15k DJA, 325K FHG 2.15.23 CAM Repair scope has been reduced from an El Segundo bottom replacement to misc bottom patches, annular installation, insert plates, and noozzle work. Forecast locked at time of confimation. 2.2.23 ML 15k CASTI, 5k W9Y Constr, 1.7k WM, 25k Knight, 15k DJA, 3k West Viriginia 1/1123 CAM Forecast adjusted for 2023 project start. Assuming similar scope as 503, forecasted dollars include El Segundo install. Assume 330k spend in Feb and remiaing el segundo cost of 225K in March. Liner cost TBD at 90K, also in March 1/9/23-CES-Per PM, December variance is due to delay in returning to service tank 503, which had to be complete prior to taking this tank out of service. 1/4/23 CAM Accrue 17k Catsi, Re accrue 20k HMT. Forecast tio be verified with 503 Hydro Exemption completion. 12/2/22 CAM Re accrue 5K Catsi, 20k HMT Variance due to 503 Tk liner install 11/2/22 CAM Re accrue 5k catsi, accrue 17k WM 10/3/22 CAM Tank 503 work underway. Accrue 5k Catsi, accrue 5k W9Y. Variance - Invoice billed to wrong project cost went to DORAVILLE I BSEVH TK 503 9/2/22 CAM Tank 503 scope finalized. This project forecast adjusted based on new 503 schedule. Cost roll over to 2023 with sim scope assumed. W9Y charge should be on 503 project, 23k reclass. Accrue 5k Catsi, accrue 10k WM 8.2.22 CAM Accrue 5k Catsi, 10K W9Y Construction 10k WM. 502/503 flip on schedule, underspend on this project. 7/27/2022-CES-Updating forecast based on Clayton's schedule sent 7/14. Project will carry over into January/February. Startingin September after tank 503. 7.1.22 CAM AFE Approved. Work scheduled for mid july. Variance on schedule. 6/21/22 CAM AFE submitted on 6/15 6/7/22 CAM AFE generation in process. Forecast adjusted. 5.10.22.DLC: Initial Forecast | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Georgia | BSEVH - DORAVILLE I TERMINAL |  | 671524 | 42480 |  |  | 66082 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 43528 |  | Stine, Carlton | Independent | Aqua | 2022-04-25 | Int - Tanks
Doraville I (BSEVH) Tank 503 Out of Service Corrosion Inspection and Refurb | Item | Open | MCAP | BSEVH00M2203 | Maintenance Framework | 1991844 | Matthews, Clayton | South | 6. Operational | Defined | Tanks | 122426 |  |  | 122426.1 | 125449 | -3023 | Yellow |  |  |  | 122426 |  |  | 407000 |  |  | 407000 | Phase | 407000 | 942078 |  | 942078 | No | Green | 2022-07-01 | 2022-06-27 | 2022-06-27 | 2022-12-31 | 2022-12-31 |  |  | 104373.77 | 19852.31 | 1222.69 | -3022.67 |  |  | -3023 | Red | [11 empty] | 5.2.23 ML Re-Accrue , 2K Parker&Son, 9.5k WM 4.5.23 ML Re-Accrue 45K FHG, 2K Parker&Son, 9.5k WM 3.3.23 CAM Accrue 45K FHG, accrue 2K Parker and son, accrue 22K W9Y, accrue 9500 WM 2.2.23 ML- Accrue 130k FHG, 2k Parker, Re-Accrue 9.5k WM, 3k ZZZ CAM Final invoicing and change orders generated for FHG. Second change order to account for material variances with unit pricing reviewed with contractor and leadership. Change order complete and ready for submission with Phase2 AFE being generated. 1/4/23 CAM Accrue 55K Catsi, Accrue 55604 FHG, Accrue 7654 Saybolt, Accrue 15K HMT, accrue 22625 W9Y, Accrue 59000 WV paint, Re Accrue 9500K WM 12/2/22 CAM Accrue 55K Catsi, Accrue 157K FHG, Accrue 15K HMT, Re accrue 35000 W9Y, Re Accrue 15K WM 11/2/22 CAM Accrue 23k Catsi, Accrue 340k FHG, Accrue 20K HMT, Accrue 35k WY9, accrue 15k WM 10/3/22 CAM El Segundo liner installed. Concrete work underway. All mechanical prep work in process. Accrue 15,000 catsi, accrue 30k FHG. Re accrue 15k HMT, re accrue 10k WM, 9/11/22-CES Negative variance represents a pause in work for a month to further inspect the bottom. Tank will receive El Segundo in 4Q. 9/2/22 CAM program approved new bottom. FHG Mobilization on 9/12. 535k PO to be issued, 45 day schedule. Forecast updated to reflect engineering delays and new scope. Accrue 15k Catsi, Accrue 10k WM, Accrue 15k HMT, re accrue 35k W9Y, 8.18.22 CAM HMT completed OOS inspection. No indications on bottom scan. Working on liner removal and rescan for verification. Additional inspection/ coating costs anticipated. 8.2.22 CAM Accrue 35k W9Y Construction, Accrue 25k Catsi, 5k WM 7.1.22 CAM AFE Approved. Work scheduled for mid july. 6/21/22 CAM AFE submitted on 6/15. Forecast to be adjusted. 5.10.22.DLC: Initial Forecast | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Southeast Terminals |  |  | 125449 | -3023 |  |  | 819652 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 43529 |  | Stine, Carlton | Independent | Aqua | 2022-04-25 | Int - Tanks
Doraville I (BSEVH) Tank Outage Project | Item | Open | MEXP | BSEVH00E2201 | Maintenance Framework | 2003289 | Matthews, Clayton | South | 6. Operational | Drawdown | Tank Outage | -64269 | 105000 |  | 40731.07 | 65731 | -25000 | Red |  |  |  | 40731 |  |  | 285000 |  |  | 285000 | Full | 285000 | 116776 | 105000 | 221776 | No | Green | 2022-07-01 | 2022-07-16 | 2022-07-16 | 2022-12-31 | 2022-12-31 |  |  | 20641.32 | 12000 | 8089.75 | -105000 | 25000 | 25000 | -130000 | Red |  | Forecasting | 105000 | [8 empty] | 5.2.23 ML Re-Accrue 35.5K CATSI, 5.5k HMT, 34k WM, 30k West Virginina 105k Variance is due to an issue with the accrual file PMO recommended forecasting missing accruals in May. 4.5.23 ML Re-Accrue 35.5K CATSI, 5.5k HMT, 34k WM, 30k West Virginina 3.3.23 CAM Forecast adjusted for 503 spec cleaning Accrue 35K Catsi, 5.5k HMT, 27.7k to W9Y Construction, 34k WM, 30k West Virginina 2.2.23 ML Re Accrue 27.7k CATSI, 5.5k HMT, 27.7k to W9Y Construction, 34k WM, 30k West Virginina 1/11/23 CAM Forecast uodated to include potential tank support during 502 outage. 1/5/22 CAM Re Accrue 3500 ATP, Re accrue 5500 HMT, Re accrue 27750 W9Y, Re accrue 16800 WM, accrue 30,000 WV Paint, accrue 20k Catsi 12/2/22 CAM Re Accrue all prior. 11/3/22 CAM Re Accrue all prior. Additional work on 503 tank impacts october spends. 10/3/22 CAM Re accrue 10k CATSI, Re accrue 5,500 HMT, Re accrue 27,750 W9Y, Accrue 16,800 WM, Accrue 3500 ATP 9/2/22 CAM Underspend based on Tank 503 project engineering/scope changes. Cost shifted to october/novemeber Accrue 5k ATP, Accrue 42k W9Y, Accrue5,500 HMT, Accrue 10K Catsi, Re accrue 10k WM. 8.8.22 Project ingoing as support to 502/503 tank projects 8.1.22 CAM Accrue 79k W9Y, Accrue 15k ATP, Accrue 9500 WM 6/21/22 CAM AFE revision underway. Expect to submit for approvals by 6/22. June variance expected. 6/7/22 CAM AFE generation in process. Forecast adjusted. | 2023-05-09 | Landeros, Melisa |  | South | Pipelines and Terminals | Tank Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 40731 | 0 |  |  | 181045 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 43710 |  | Clark, David | Independent | Aqua | 2022-05-10 | Int - Tanks
Doraville II (BSEVK) Tank 5 - OOS Seal Insp | Item | Open | MEXP | BSEVK00E2301 | Maintenance Framework | 2085509 | Matthews, Clayton | South | 6. Operational | Defined | Tanks | 21571 |  |  | 21570.78 | 24000 | -2429 | Red | 125000 |  | 125000 | -103429 |  |  | 134750 |  |  | 134750 | Phase | 134750 | 21571 |  | 21571 | No | Green | 2023-03-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-04-30 |  |  |  |  | 14000 | 7570.78 | 10000 | 10000 | -2429 | Red | [11 empty] | 5/2/23 Complete 4.5.23 Accrue 14k FHG | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Tank Integrity |  | Georgia | BSEVK - DORAVILLE II TERMINAL |  | 14000 | 7571 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44803 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Doraville II (BSEVK) Tank 6 - OOS Seal Insp | Item | Open | MEXP | BSEVK00E2302 | Maintenance Framework | 2085510 | Matthews, Clayton | South | 6. Operational | Defined | Tanks | 22047 |  |  | 22047.18 | 20000 | 2047 | Red | 125000 |  | 125000 | -102953 |  |  | 135300 |  |  | 135300 | Phase | 135300 | 22047 |  | 22047 | No | Green | 2023-03-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-04-30 |  |  |  |  | 20000 | 2047.18 | 0 | 0 | 2047 | Red | [11 empty] | 5/3/23 CAM Complete 4.5.23 Accrue 15k FHG, 5k CATSI Variance - Project execution is concurrent to Tk 5 savings on mobilization, material and execution. 9/23/22-CES-Reducing budget by 10% for calibration. | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Tank Integrity |  | Georgia | BSEVK - DORAVILLE II TERMINAL |  | 20000 | 2047 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44804 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Doraville II (BSEVK) Tank 9 - OOS API 653 Insp | Item | Open | MCAP | BSEVK00M2301 | Maintenance Framework | 2075763 | Matthews, Clayton | South | 3. Active | Defined | Tanks | 80879 | 325001 |  | 405880 | 400001 | 5879 | Yellow | 430760 |  | 430760 | -24880 |  |  | 257465 |  |  | 257465 | Phase | 257465 | 80879 | 775001 | 855880 | No | Green | 2023-04-01 | 2023-01-18 | 2023-01-18 | 2023-12-30 | 2023-07-31 | [5 empty] | 80879 | 75000 | 75000 | 5879 | Yellow |  |  | 125000 | 150000 | 50000 |  |  |  |  | 1 |  | 5/2/23 CAM Cleaning complate. Inspection blast starting. Inspection scheduled for 5/4/23 Accrue 65879 FHG, accrue 10,000 catsi, accrue 5,000 WV Paint. 4.5.23 Project start date confirmed April 15 compliance date April 20th. 3/21/23-CES-Group meeting today to align on path forward, tank needs to come out of service due to floating roof concerns (high LEL >50%). Notice sent to state. Plan for outage in April and full API 653. 2.16.23 CAM Monitoring this tank for potential pull back to 2023. 2/14/23-CES-Per BECHT RBI completed 8/2/22, tank can be taken out of service in 2024. Updating forecast to CY+1. | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Georgia | BSEVK - DORAVILLE II TERMINAL |  |  | 355879 | 50000 | 1 |  | 450000 | Stine, Carlton | Stine, Carlton |  |  | 1 | 44805 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Fort Lauderdale - Lagoon Cleaning | Item | Open | MEXP | BETQD00E2301 | Maintenance Framework | 2096543 | Johnson, AJ | South | 3. Active | Drawdown | South | 43009 | 1 |  | 43010.34 | 43101 | -91 | Yellow |  |  |  | 43010 |  |  | 43101 |  |  | 43101 | Full | 43101 | 43009 | 1 | 43010 | No | Green | 2023-04-01 | 2023-03-30 | 2023-03-30 | 2023-05-30 | 2023-05-30 | [5 empty] | 43009.34 | 43100 | 43100 | -91 | Yellow |  | Forecasting | [7 empty] | 1 |  |  |  | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | Florida | BETQD - BET FORT LAUDERDALE TERMINAL |  |  | 43009 |  | 1 |  |  | Johnson, AJ | Miller, Michael A. | N/A |  | 1 | 46843 |  | Johnson, AJ | JDE Child | Burnt Orange | 2023-03-27
Fort Lauderdale East Farm Drainage | Item | Open | MCAP | BETQD00M2201 | Maintenance Framework | 1956798 | Campbell, William | South | 3. Active | Defined | Storm Water Management | 2958 |  |  | 2958.3 | 2958 | 0 | Green |  |  |  | 2958 |  |  | 82000 |  |  | 82000 | Full | 82000 | 77958 |  | 77958 | No | Green | 2022-12-01 | 2022-03-22 | 2022-03-22 | 2022-12-30 | 2023-02-28 |  |  | 2850 | 108.3 | 0 | 0 |  |  | 0 | Green | [11 empty] | 5/1/23-Re-accue $75K to Tritan 4/1/23-Re-accrue $75k to Triten 3/1/23-Accrue $75K to Triten 2/1/23-Accrue $75K to Triten 1/1/23- Accrue $75k to Triten 12/1/22-Project to be completed 2nd week of December 11/1/2022 - Scheduled to be completed December 7th 10/3/2022 - Project transferred to DMitchell. Obtaining quotes and project plan. 9/1/2022-Project to be completed in October 8/1/22- Project moved to October due to potential weather delays 6/1/2022-This project was previously with a PM that is no longer with Buckeye. Project recently handed to me and forecast will be moved to July. 4/1/2022 - AFE fully approved. Bid event opened in Coupa. Execution of project to take place during May. 3/1/2022 - AFE routed for approval. 2/1/2022 - AFE development underway with planned approval in February. Project construction targeted for May 2022. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Florida | BETQD - BET FORT LAUDERDALE TERMINAL |  | 2958 | 0 |  |  | 75000 |  | Bonenberger, Mark | Burke, Kevin |  |  | 1 | 37667 |  | Guest, ProSight | Independent | Aqua | 2020-08-11 | Other Programs
George West Mitigate Arc Flash | Item | Open | MCAP | BTXXW00M2001 | Exempt | 1714856 | Brazzil, Cade | South | 3. Active | Drawdown | South |  | 15500 |  | 15500 | 15500 | 0 | Green |  |  |  | 15500 |  |  | 111000 |  |  | 111000 | Full | 111000 | 0 | 15500 | 15500 | No | Green | 2020-07-01 | 2020-05-22 | 2020-05-22 | 2022-03-10 | 2023-08-31 | [15 empty] | 15500 | [5 empty] | 4.3.23 CB - Project Quotes are around $15.5K. Status change to active 3/1/23 Are we operating this or getting rid of it or unmanned? Check with AJ 4.26.22- ML - Project is now belongs to Robert Ashley per Maria DeLeon 6-16-21 - Changed status to ON-HOLD. MC | 2023-05-01 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXXW - George West |  |  | 0 | 15500 |  | -16480 |  | Johnson, AJ | Burke, Kevin |  |  | 1 | 36729 |  | Kabaria, Erika | Independent | Aqua | 2020-05-07
Greensboro I (BSEVP) Tank 5 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | BSEVP00M2301 | Maintenance Framework | 2094129 | Bryant, Ben | South | 3. Active | Defined | Tanks |  | 673772 |  | 673772 | 673772 | 0 | Green | 673772 |  | 673772 | 0 |  |  | 278659 |  |  | 278659 | Phase | 278659 |  | 673772 | 673772 | No | Green | 2023-07-01 | 2023-01-24 | 2023-01-24 | 2023-12-31 | 2023-09-30 | [14 empty] | 177257 | 354515 | 142000 | [6 empty] | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | North Carolina | BSEVP - GREENSBORO I TERMINAL |  |  | 0 | 673772 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44819 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Greensboro I (BSEVP) Tank 1 Out of Service Corrosion Inspection and Refurb | Item | Open | MCAP | BSEVP00M2201 | Maintenance Framework | 2011939 | Bryant, Ben | South | 6. Operational | Drawdown | Tanks | 239501 |  |  | 239501.44 | 238739 | 762 | Yellow | 186000 |  | 186000 | 53501 |  |  | 386000 |  |  | 386000 | Phase | 386000 | 286970 |  | 286970 | No | Green | 2022-11-01 | 2022-08-10 | 2022-08-10 | 2022-12-31 | 2023-03-01 |  |  | 182578.71 | 42712.63 | 13447.94 | 762.16 |  |  | 762 | Red | [11 empty] | 5/1/23 Re Accrue 33K to FHG and 6K to Saybolt. 4/3/23 Re Accrue 33K to FHG and 6K to Saybolt. 3/2/2023 Accrue $6K to Saybolt & $33K to FHG. Tank back in service. Awaiting final invoicing. 2/1/23 Tank has been repaired. Liner is being applied. Accrue 56 to FHG, 28k to W9Y, 30K to Barr None, and 18K to ATP 1/3/23 Repair contractor is working to get unit pricing completed. 12/9/22 Tank has been cleaned and will be inspected the week of December 12th. Repair crew will probably start after holidays. Moved 120K to 2023. 12/1/22 Tank taken out of service on December 5th . Tank will be isolated and cleaned. DJA will be onsite next week. Accrue 5K to W9Y. 11/2/22 Tank will be coming out of service this month. 10/3/22 Tank will be coming out of service Next Month. 9/9/22 Predicting Carryover for 2023. 5.10.22.DLC: Initial Forecast | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | North Carolina | BSEVP - GREENSBORO I TERMINAL |  | 238739 | 762 |  |  | 47468 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 43530 |  | Stine, Carlton | Independent | Aqua | 2022-04-25 | Int - Tanks
Greensboro II - New power feed to additive pump skids | Item | Open | MCAP | BSEVV00M2202 | Maintenance Framework | 2045669 | Corman, Chris | South | 7. Closed | Emergent | Electrical | 5069 |  |  | 5068.65 | 4887 | 182 | Yellow |  |  |  | 5069 |  |  | 30000 |  |  | 30000 | Full | 30000 | 27338 |  | 27338 | No | Green | 2022-12-01 | 2022-11-21 | 2022-11-21 | 2022-12-30 | 2022-12-30 |  |  | 846.22 |  | 4040.6 | 181.83 |  |  | 182 | Red | [11 empty] | 1/3/23- Project complete, ready to close. 12/5/22- Work scheduled for December | 2023-01-03 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | North Carolina | BSEVV - GREENSBORO II TERMINAL |  | 4887 | 182 |  |  | 22269 |  | Ashley, Robert | Johnson, AJ |  |  | 1 | 46224 |  | Johnson, AJ | Independent | Aqua | 2022-11-14 | Other Programs
Greensboro II - Tank 8 Pump B new motor and power feed | Item | Open | MCAP | BSEVV00M2302 | Maintenance Framework | 2094821 | Pitkin, Colton | South | 3. Active | Drawdown | South | 7315 | 20000 |  | 27315 | 27000 | 315 | Yellow |  | 40775 | 40775 | -13460 |  |  | 40775 |  |  | 40775 | Full | 40775 | 7315 | 20000 | 27315 | No | Green | 2023-03-01 | 2023-03-10 | 2023-03-10 | 2023-06-30 | 2023-04-30 |  |  |  |  | 7000 | 315 | 20000 | 20000 | -19685 | Red |  | Contractor/Vendor Issue | 20000 | [8 empty] | 5/3/23 - Re-accruing $7K to Electric Motor Shop. 4-4-23 Pump has been received and accruing $7K to Electric Motor Shop. | 2023-05-03 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | North Carolina | BSEVV - GREENSBORO II TERMINAL |  | 7000 | 20315 |  |  |  |  | Johnson, AJ | Johnson, AJ |  |  | 1 | 46557 |  | Johnson, AJ | Independent | Aqua | 2023-01-30
Greensboro II (BSEVV) Tank 3 - OOS API 653 + Seal Insp & Refurb | Item | Open | MEXP | BSEVV00E2301 | Maintenance Framework | 2085515 | Matthews, Clayton | South | 3. Active | Defined | Tanks |  | 290000 |  | 290000 | 290000 | 0 | Green | 290000 |  | 290000 | 0 |  |  | 191400 |  |  | 191400 | Phase | 191400 |  | 290000 | 290000 | No | Green | 2023-07-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-09-30 | [14 empty] | 60000 | 150000 | 80000 |  |  |  |  | 9/23/22-CES-Reducing budget 10% for calibration. | 2022-09-23 | Landeros, Melisa |  | South | Pipelines and Terminals | Tank Integrity |  | North Carolina | BSEVV - GREENSBORO II TERMINAL |  |  | 0 | 290000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44820 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Greensboro II (BSEVV) Tank 4 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | BSEVV00M2301 | Maintenance Framework | 2075760 | Matthews, Clayton | South | 3. Active | Defined | Tanks | 116219 | 250000 |  | 366219 | 580036 | -213817 | Red | 580072 |  | 580072 | -213853 |  |  | 270862 |  |  | 270862 | Phase | 270862 | 116219 | 250000 | 366219 | No | Green | 2023-04-01 | 2023-01-17 | 2023-01-17 | 2023-12-30 | 2023-06-30 | [5 empty] | 116219 | 123000 | 123000 | -6781 | Yellow |  |  | 150000 | 100000 | [7 empty] | 5/2/23 CAM Cleaning complete. inspection complete, scope development underway. Forecast reduced. Accrue 25,500 GEM, accrue 18519 Rosen, Accrue 15,000 ATP, Accrue 57,200 W9Y. | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | North Carolina | BSEVV - GREENSBORO II TERMINAL |  |  | 366219 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44821 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Greensboro II (BSEVV) Tank 2 Out of Service Corrosion Inspection and Refurb | Item | Open | MCAP | BSEVV00M2201 | Maintenance Framework | 2011940 | Bryant, Ben | South | 6. Operational | Drawdown | Tanks | 28492 |  |  | 28492.42 | -52835 | 81327 | Red | 50000 |  | 50000 | -21508 |  |  | 147000 |  |  | 147000 | Phase | 147000 | 81628 |  | 81628 | No | Green | 2022-12-01 | 2022-08-10 | 2022-08-10 | 2022-12-31 | 2023-02-28 |  |  | 21496.96 | 6694.22 | 301.24 |  | -81327 | -81327 | 81327 | Red | [11 empty] | 3/14/23 Project will be Reclassed by M. Campbell to MEXP upon approval of AFE. 3/2/2023 - Tank work complete and staying IDLE until further notice. Citgo to be notified of the complete cost of $80K 2/1/23 Accrue 16K for Waste Management. Preparing MEXP AFE for flipping these costs 1/3/23 Tank will be Idled. 12/9/22 Tank has been cleaned and the tank floor has been blasted. Tank will be inspected the week of Dec. 12th. This tank will be idled. Will carry over 20K for Waste Management. 12/1/22 Tank will be cleaned and isolated this week. DJA will be onsite next week to conduct API 653 Inspection. 11/2/22 Tank will be coming out of service this month. 10/3/22 Tank will be coming out of service Next month. 9/9/22 Predicting carryover for this project. 5.10.22.DLC: Initial Forecast | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | North Carolina | BSEVV - GREENSBORO II TERMINAL |  | 28492 | 0 |  |  | 53135 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 43531 |  | Stine, Carlton | Independent | Aqua | 2022-04-25 | Int - Tanks
Greensboro II Tank 2 OOS - FLIP TO MEXP | Item | Open | MEXP | BSEVV00E2303 | Maintenance Framework | 2096385 | Bryant, Ben | South | 6. Operational | Defined | Tanks |  |  |  | 0 | 80000 | -80000 | Red | [6 empty] | 80000 |  |  | 80000 | Full | 80000 |  |  |  | No | Green |  | 2023-03-24 | 2023-03-24 | 2023-05-01 | 2023-04-28 | [6 empty] | 80000 | 80000 | -80000 | Red | [13 empty] | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Tank Integrity |  | North Carolina | BSEVV - GREENSBORO II TERMINAL |  |  | 0 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46797 |  | Campbell, Michael | Independent | Aqua | 2023-03-17
Jacksonville - QU907QJ ILI 2023 | Item | Open | MEXP | BETQJ00E2302 | Maintenance Framework | 2096298 | Campbell, William | South | 3. Active | Defined | Assessments |  | 335000 |  | 335000 | 335000 | 0 | Green | 105805 |  | 105805 | 229195 |  |  | 335500 |  |  | 335500 | Full | 335500 |  | 335000 | 335000 | No | Green | 2023-06-01 | 2023-03-26 | 2023-03-26 | 2023-04-30 | 2023-04-30 | [13 empty] | 335000 | [7 empty] | Project will begin 2nd week of June | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Pipeline Integrity |  | Florida | BETQJ - BET JACKSONVILLE TERMINAL |  |  | 335000 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44699 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
Jacksonville (BETQJ) - Secondary containment improvements | Item | Open | MEXP |  | Maintenance Framework |  | Pitkin, Colton | South | 8. Canceled |  | Secondary Containment |  |  |  | 0 | 45000 | -45000 | Red | 45000 |  | 45000 | -45000 | [11 empty] | No | Green |  |  |  |  | 2023-05-31 | [21 empty] | 5/2/2023- no need for additional curbing around the Jacksonville Additive Offloading Area. On April 11th, the topic of containment was discussed by Mark Bonenberger, Gianna Aiezza (PE from Envirospec), Mike Agana, and myself. Gianna has agreed to sign off on a technical amendment to the SPCC plan that addresses the active control measures that will take place during additive offloading. These procedures include constant monitoring of the offload by the driver, the placement of a spill kit (rated for 44 gallons) in the offload area, the placement of drip pans under the belly valve and pump on the trailer, and diversions placed around the two storm drains that could potentially be impacted by a release. | 2023-05-02 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Florida | BETQJ - BET JACKSONVILLE TERMINAL |  |  | 0 |  |  |  |  | Spari, Markella |  |  |  | 1 | 45172 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
Jacksonville disconnect and idle OOS piping to old Barge Dock | Item | Open | MCAP |  | Maintenance Framework |  | Corman, Chris | South | 1. Proposed |  | Facility Integrity |  | 35000 |  | 35000 | 35000 | 0 | Green | 35000 |  | 35000 | 0 | [9 empty] | 35000 | 35000 | No | Green | 2023-06-01 |  |  |  | 2023-04-30 | [13 empty] | 35000 | [11 empty] | South | Pipelines and Terminals | Integrity |  | Florida | BETQJ - BET JACKSONVILLE TERMINAL |  |  | 35000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45643 |  | Administrator, System | Independent | Aqua | 2022-08-30 | Int - Planned Corr & FI
Jacksonville Dock Line Coating Refurbishment | Item | Candidate | MCAP |  | Maintenance Framework |  | Wirfs, Mike | South | 1. Proposed |  | Atmospheric Corrosion |  | 380000 |  | 380000 | 380000 | 0 | Green | 380000 |  | 380000 | 0 | [9 empty] | 380000 | 380000 | No | Green | 2023-08-01 |  |  |  | 2023-05-31 | [15 empty] | 380000 | [9 empty] | South | Pipelines and Terminals | Integrity |  | Florida | BETQJ - BET JACKSONVILLE TERMINAL |  |  | 0 | 380000 |  |  |  | Geib, Rob |  |  |  | 1 | 40497 |  | Guest, ProSight | Independent | Aqua | 2021-07-09 | Int - Planned Corr & FI
Jacksonville Expansion Joint Analysis - MEXP | Item | Open | MEXP | BETQJ00E2209 | Maintenance Framework | 2035960 | Corman, Chris | South | 6. Operational | Drawdown | South | 7465 |  |  | 7464.5 | 2719 | 4746 | Red |  |  |  | 7465 |  |  | 101000 |  |  | 101000 | Full | 101000 | 70688 |  | 70688 | No | Green | 2022-10-01 | 2022-10-03 | 2022-10-03 | 2022-12-30 | 2023-02-28 |  |  | 2046.5 | 158 | 514 | 4746 |  |  | 4746 | Red | [11 empty] | 1/3/23- Risk assessment was analyzed, will install 24/7 hydrocarbon underneath flex joint. 12/1/2022 Risk Assessment was completed. Accrue 27k to HGA 11/1/2022 - Pipe was run in ceasar with as built conditions. Working to modify the current design to eliminate stress problems and remove expansion joint. 10/4/2022 - Pipe was scanned week of 9/19. Working to analyze results. Project brought in from South Region MEXP Drawdown. CC | 2023-01-03 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | Florida | BETQJ - BET JACKSONVILLE TERMINAL |  | 2719 | 4746 |  |  | 63223 |  | Johnson, AJ | Johnson, AJ |  |  | 1 | 45923 |  | Johnson, AJ | Independent | Aqua | 2022-09-27 | Other Programs
Jacksonville Removal of load on Ship Berth Main Platform Access Trestle. | Item | Open | MEXP |  | Project Framework |  | Campbell, William | South | 1. Proposed |  | Marine |  | 500000 |  | 500000 | 500000 | 0 | Green | 500000 |  | 500000 | 0 | [9 empty] | 500000 | 500000 | No | Green | 2023-08-01 |  |  |  | 2023-09-30 | [15 empty] | 250000 | 250000 | [8 empty] | South | Pipelines and Terminals | Station/Terminal |  | Florida | BETQJ - BET JACKSONVILLE TERMINAL |  |  | 0 | 500000 |  |  |  | Spari, Markella |  |  |  | 1 | 41535 |  | Administrator, System | Independent | Aqua | 2021-08-19 | Marine
Jacksonville Terminal (BETQJ) - Site survey to validate SPCC plan calculations and review. | Item | Open | MEXP | BETQJ00E2208 | Maintenance Framework | 2011283 | Burke, Joshua | South | 7. Closed | Defined | Secondary Containment | 874 |  | 0 | 873.5 | 874 | 0 | Green |  |  |  | 874 |  |  | 11000 |  |  | 11000 | Full | 11000 | 8689 | 0 | 8689 | No | Green | 2022-08-01 | 2022-08-03 | 2022-08-03 | 2022-10-30 | 2022-09-30 |  |  | 873.5 | [17 empty] | 0 | 11.1.22 JHB - Work complete, ready for closeout. Contingency unused. 10.3.22 JHB - Diamond Z has issued PE stamped drawings for facility. SPCC group/DZ working on containment design/plan for additive loading station. Accrue remaining $7k to Diamond Z 9.1.22 JHB - Modeling underway, accrue $5k to Diamond Z. 8.24.22 JHB - Excess funding removed from contingency 8.1.22 JHB - AFE routing for approval, Diamond Z to be issued PO for modeling once approved. forecast adjusted to match AFE, excess of $5k placed in contingency. 6.2.22 JHB - Proposal received for modeling existing scan, AFE documents to be generated in coming weeks. 5.3.22 JHB - Diamond Z has reviewed and advised the scan can be used to calculate containment with incremental data collection from Operations. They will prepare a proposal for the modeling in the coming weeks. 5.2.22 JHB - Diamond Z reviewing existing scan and will revise proposal accordingly. 4.28.22 JHB - Pending E&D response. Funds moved to August. 4.4.22 JHB - Pending E&D response on existing survey to be used. 2.25.22 JHB - pricing received for validation survey, currently on hold as E&D may have recent scan that will suffice for volume calcs. 2.2.22 JHB - Requesting proposal for SPCC validations surveys by end of February. | 2022-11-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Station/Terminal |  | Florida | BETQJ - BET JACKSONVILLE TERMINAL |  | 874 | 0 |  |  | 7816 |  | Spari, Markella | Spari, Markella |  |  | 1 | 41556 |  | Administrator, System | Independent | Aqua | 2021-08-19 | Other Programs
Jacksonville Terminal (BETQJ) Tank 7707 - EFR Primary Seal Gap | Item | Open | MEXP | BETQJ00E2301 | Maintenance Framework | 2085579 | Bryant, Ben | South | 3. Active | Defined | Tanks |  | 12000 |  | 12000 | 12000 | 0 | Green | 12000 |  | 12000 | 0 |  |  | 13200 |  |  | 13200 | Phase | 13200 |  | 12000 | 12000 | No | Green | 2023-05-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-05-31 | [12 empty] | 12000 | [10 empty] | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Tank Integrity |  | Florida | BETQJ - BET JACKSONVILLE TERMINAL |  |  | 12000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44827 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Jacksonville VRU Release Prevention | Item | Open | MCAP | BETQJ00M2301 | Maintenance Framework | 2109911 | Pitkin, Colton | South | 3. Active | Drawdown | Vapor Management | 15000 | 63000 |  | 78000 | 60000 | 18000 | Red | 58000 |  | 58000 | 20000 |  |  | 77668 |  |  | 77668 | Full | 77668 | 15000 | 63000 | 78000 | No | Green | 2023-04-01 | 2023-04-05 | 2023-04-05 | 2023-08-30 | 2023-08-30 | [5 empty] | 15000 | 15000 | 15000 | 0 | Green |  |  | 0 | 45000 | 18000 | [6 empty] | 5-3-2023 - Dates locked in June 19th with contractor. | 2023-05-05 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Florida | BETQJ - BET JACKSONVILLE TERMINAL |  |  | 60000 | 18000 |  |  |  | Karl, Marissa | Johnson, AJ |  |  | 1 | 44950 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Other Programs
Knoxville I&II OWS Clean/inspect/repair | Item | Candidate | MEXP |  | Maintenance Framework |  | Matthews, Clayton | South | 1. Proposed |  | South |  | 60000 |  | 60000 | 60000 | 0 | Green | 80000 |  | 80000 | -20000 | [9 empty] | 60000 | 60000 | No | Green | 2023-05-01 |  |  |  | 2023-06-30 | 8 | Yellow |  |  |  |  | 0 | 0 | 0 | Green |  |  | 10000 | 30000 | 20000 | [6 empty] | 4/10/23 CAM AFE In progress. Forecast shifted to May start. | 2023-04-10 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Tennessee | BSEUI - KNOXVILLE I TERMINAL |  |  | 40000 | 20000 |  |  |  | Johnson, AJ |  |  |  | 1 | 45825 |  | Clark, David | Independent | Aqua | 2022-09-12 | Other Programs
Knoxville II Truck Rack Solenoid Repairs | Item | Open | MEXP | BSEUK00E2202 | Maintenance Framework | 2023387 | Leal, Trey (Tony) | South | 7. Closed | Drawdown | Truck Racks | -29 |  |  | -29.15 | -29 | 0 | Green |  |  |  | -29 |  |  | 10000 |  |  | 10000 | Full | 10000 | 6368 |  | 6368 | No | Green | 2022-11-01 | 2022-09-23 | 2022-09-23 | 2022-12-31 | 2023-02-28 |  |  | -29.15 | [18 empty] | 4/3/23 - Project complete. Ready to Close 2/1/23- Tech pulled to Titan Terminal, work to be completed end of month 1/3/23- Solenoids have been partially installed and install should be complete Jan 2023. 12/5/22- Solenoids have arrived and will be installed by tech in December 11/1/2022 - Solenoids should be arriving today, have not received invoice yet 10/3/2022 - Working on getting parts ordered this week, PO is for 6500. Forecasting 3000 in November for tubing and fittings associated with install | 2023-04-03 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | Tennessee | BSEUK - KNOXVILLE II TERMINAL |  | -29 | 0 |  |  | 6398 |  | Younce, Michael | Johnson, AJ |  |  | 1 | 45369 |  | Clark, David | Independent | Aqua | 2022-08-26 | Other Programs
LPG Rail Project @ Buckeye Texas Hub | Item | Open | MCAP | BTXHF00M2216 | Project Framework | 2037831 | Burke, Joshua | South | 4. On-Hold | Unplanned | South | 86113 |  |  | 86112.5 | 85130 | 983 | Yellow |  |  |  | 86113 |  |  | 207000 |  |  | 207000 | Phase | 207000 | 210505 |  | 210505 | No | Green | 2022-11-01 | 2022-10-24 | 2022-10-24 | 2023-05-01 | 2023-07-15 |  |  | 27658.11 | 49205.02 | 8266.53 | 982.84 |  |  | 983 | Red | [11 empty] | 5.3.23 JHB - reaccrue $6k to ESDC. Reclass pending final invoice. 4.3.23 JHB - Accrue $7k to ESDC. Spend is in support of the new BTH Butane Rail Offloading project - will need to be reclassed. 3.1.23 JHB - Project on hold due to increased TIC. Temporary butane rail offloading system likely to proceed in lieu of this project. Accrue $32k to ESDC, $8k to SkyEye. FC removed from March. 2.1.23 JHB - Engineering ongoing, revised TICs indicated significant cost increase. Bid packages on hold pending revised estimates and potential scope modificiations to reduce cost. Accrue $61k to ESDC. Variance due to pause on detailed design scope. 1.4.23 JHB - Detailed engineering continuing, working to determine meter vs. scale approach in early JAN. Bid documents out to vendors for all equipment aside from air operatred valves. Accrue $65k to ESDC. $55k FC added to February to account for total ESDC PO for Detailed engineering - $170k. 12.1.22 JHB - Detailed engineering ongoing. Preliminary PIDs submitted, model & hydraulics underway, single bid for loading platform received. Early design review scheduled for 12/6. Accrue $60k to ESDC. | 2023-05-03 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 85130 | 983 |  |  | 124393 |  | Johnson, AJ | Johnson, AJ |  |  | 1 | 43161 |  | Curry, Michael | Independent | Aqua | 2022-03-11 | Other Programs
Macon (BSEUJ) Tank 2 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | BSEUJ00E2301 | Maintenance Framework | 2085514 | Matthews, Clayton | South | 3. Active | Defined | Tanks |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 |  |  | 11000 |  |  | 11000 | Phase | 11000 |  | 10000 | 10000 | No | Green | 2023-11-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-12-31 | [18 empty] | 10000 |  |  |  |  | Landeros, Melisa |  | South | Pipelines and Terminals | Tank Integrity |  | Georgia | BSEUJ - MACON TERMINAL |  |  | 0 |  | 10000 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44837 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Macon PCW Tank Inspection and repair | Item | Open | MEXP | BSEUJ00E2302 | Maintenance Framework | 2095132 | Corman, Chris | South | 2. Pending AFE |  | Secondary Containment |  | 5000 |  | 5000 | 25000 | -20000 | Red |  |  |  | 5000 | [6 empty] | Interim |  |  | 5000 | 5000 | No | Green | 2023-05-01 | [16 empty] | 5000 | [8 empty] | 5/1/2023 - Tank was cleaned and discovered buckets amounts of rust scale. Also have discovered 3 more holes in the tank. Will most likely look to replace the tank. | 2023-05-01 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Georgia | BSEUJ - MACON TERMINAL |  |  | 5000 |  |  |  |  | Spari, Markella |  |  |  | 1 | 46430 |  | Johnson, AJ | Independent | Aqua | 2023-01-05
Marrero - Dock 3 Repairs and coating | Item | Candidate | MEXP |  | Project Framework |  | Leal, Trey (Tony) | South | 1. Proposed |  | Marine |  | 200000 |  | 200000 | 200000 | 0 | Green | 400000 |  | 400000 | -200000 | [9 empty] | 200000 | 200000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 100000 | 100000 | [5 empty] | 4/3/23 - Scope development underway by program. Shift out to July and August 3/1/2023 - Scope development underway by program 1/29/2023 - Scope development underway by program | 2023-04-03 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Marrero | BMTUA - Marrero Terminal |  |  | 0 | 200000 |  |  |  | Spari, Markella |  |  |  | 1 | 45798 |  | Clark, David | Independent | Aqua | 2022-09-10 | Marine
Marrero - East Dock Repairs and coating | Item | Candidate | MEXP |  | Project Framework |  | Leal, Trey (Tony) | South | 1. Proposed |  | Marine |  | 200000 |  | 200000 | 200000 | 0 | Green | 400000 |  | 400000 | -200000 | [9 empty] | 200000 | 200000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 100000 | 100000 | [5 empty] | 4/3/23 - Scope development underway by program. Shifting forecast to June and July 3/22/23 - Shifted forecast to June. have not heard from program. 3/1/2023 - Scope development underway by program 1/29/2023 - Scope development underway by program | 2023-04-03 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Marrero | BMTUA - Marrero Terminal |  |  | 0 | 200000 |  |  |  | Spari, Markella |  |  |  | 1 | 45799 |  | Clark, David | Independent | Aqua | 2022-09-10 | Marine
Marrero - Install high level tank alarms | Item | Open | MCAP | BMTUA00M2211 | Maintenance Framework | 2023207 | Brazzil, Cade | South | 3. Active | Defined | Instrumentation & Controls | 140 | 217593 |  | 217733 | 220140 | -2407 | Yellow | 220000 |  | 220000 | -2267 |  |  | 218778 |  |  | 218778 | Full | 218778 | 3919 | 217593 | 221512 | No | Green | 2022-10-01 | 2023-04-04 | 2023-04-04 | 2023-12-31 | 2023-09-30 |  |  | 70 |  | 70 |  | 50000 | 50000 | -50000 | Red |  | Forecasting |  | 22593 | 50000 | 72500 | 72500 |  |  |  |  | 5/1/23 TN - Forecasting error/material order lead time 2/28/23 CB - Revising AFE to reduce electrical contractor cost and remove transmitters from purchase. 2/17/23 CB Built AFE and found project is overbudget. Scheduled meeting with team for 2/28/23 at 11:30am 1/27/23 Project cost estimates- Frank is getting quotes - Sid is having a meeting with Emerson to discuss networking and will get their estimates. -Emerson to handle networking and SCADA need there estimate -Electrical contractor to schedule sight walk for wire and conduit runs. 1/23/23 CB_ Reviewed project with Frank and Sid (Michael) to understand project scope. 11/1/2022 - received the first report 10/4/22-- CC working on risk analysis 7/29/2022 - AFE was rejected due to needing a risk analysis. Once I have it I will resubmit. 6/30/2022 - Plan on submitting the AFE in July 6/1/2022 - Waiting on a electrical quote. 3/31/2022 - Waiting on Triad to get a SOW and a quote for a new RIO. 3/1/2022 - Made a trip to scope out the project. Need additional follow up to determine the best path forward. 1/30/2022 - Plan on making a site visit in February | 2023-05-01 | Nguyen, Tong |  | South | Pipelines and Terminals | Operating Infrastructure |  | Marrero | BMTUA - Marrero Terminal |  | 140 | 22593 | 195000 |  | 3779 |  | Forsey, Frank | Burke, Kevin |  |  | 1 | 40303 |  | Guest, ProSight | Independent | Aqua | 2021-06-22 | Other Programs
Marrero - Install TRV's | Item | Open | MCAP | BMTUA00M2208 | Maintenance Framework | 2011968 | Campbell, William | South | 7. Closed | Defined | Valves | 2982 |  |  | 2981.87 | 2982 | 0 | Green |  |  |  | 2982 |  |  | 35000 |  |  | 35000 | Phase | 35000 | 39807 |  | 39807 | No | Green | 2022-10-01 | 2022-08-11 | 2022-08-11 | 2022-09-30 | 2022-12-31 |  |  | 2872.71 | 109.16 | [17 empty] | 2/1/23-Project complete, invoicing complete, close project 1/1/23-Project Complete, invoicing outstanding. Accruals=Eagle-$36K 12/1/22-Project delayed due to paperwork, will be completed week of Dec 5 11/1/22-Project will be completed in November, Move forecast from October to November due to clarifications within the scope. Added 4 TRV's to project 10/1/22-Project to be completed by end of month 9/1/2022-Project to be completed in September 7/29/2022 - AFE first round approved. Work is scheduled for September. 6/30/2022 - Plan on submitting the AFE in July 6/1/2022 - Waiting on additional quotes. 3/1/2022 - Made a trip to scope out the project. Awaiting on quotes. 1/30/2022 - Plan on making a site visit in February | 2023-01-31 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Marrero | BMTUA - Marrero Terminal |  | 2982 | 0 |  |  | 36825 |  | Oey, Alex | Burke, Kevin |  |  | 1 | 41356 |  | Guest, ProSight | Independent | Aqua | 2021-08-09 | Other Programs
Marrero (BMTUA) - 768-769 Motor Replacement | Item | Open | MCAP | BMTUA00M2207 | Maintenance Framework | 2011898 | Campbell, William | South | 3. Active | Defined | Rotating Equipment | 5599 | 30000 |  | 35599.21 | 35241 | 359 | Yellow |  |  |  | 35599 |  |  | 155000 |  |  | 155000 | Full | 155000 | 115644 | 30000 | 145644 | No | Green | 2022-12-01 | 2022-08-10 | 2022-08-10 | 2022-12-31 | 2023-03-31 |  |  | 4181.71 | 158.9 | 900 | 358.6 | 30000 | 30000 | -29641 | Red |  | Supply Chain | 15000 | 15000 | [7 empty] | 5/1/23-Installation this month 4/1/23-Accrue $110K to Shermco 3/1/23-Accrue $110K to Shermco 2/1/23-Accrue $110K to Shermco, move 30K to March in forecast 1/1/23-. Accrue $110K to Shermco, install will be made in Jan by Houma Armature Works. 12/1/22-Motors still scheduled to be received this month. 11/1/22-Motors are scheduled to be received in December and then installed. 10/1/22-Motors ordered but will not be received until December. Project may push completion into January, 2023 9/1/22-Motors to be ordered and installed in November 7/1/2022-Received cost estimate and lead times on pumps. Will get AFE submitted in July. 5/1/2022-Awaiting cost estimate and lead time from Shermco for motors and installation Review to see if these are motors reviewed post Hurricane Ida; need to see if these are cast iron pumps as well. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Marrero | BMTUA - Marrero Terminal |  | 5241 | 30359 |  |  | 110045 |  | Posipanko, Dan | Asiedu, Saka |  |  | 1 | 37975 |  | Guest, ProSight | Independent | Aqua | 2020-08-13 | Other Programs
Marrero (BMTUA) - Facility Insulated Line Refurbishment | Item | Candidate | MCAP |  | Maintenance Framework |  | Leal, Trey (Tony) | South | 1. Proposed |  | Facility Integrity |  | 243000 |  | 243000 | 243000 | 0 | Green | 243000 |  | 243000 | 0 | [9 empty] | 243000 | 243000 | No | Green | 2023-06-01 |  |  |  | 2023-09-30 | [13 empty] | 75000 | 60000 |  | 108000 |  |  |  |  | 4/3/23 - Scope development underway 3/1/2023 - Scope development underway by program 1/29/2023 - Waiting on API 570 report to develop scope. | 2023-04-03 |  |  | South | Pipelines and Terminals | Integrity |  | Marrero | BMTUA - Marrero Terminal |  |  | 75000 | 168000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 37679 |  | Guest, ProSight | Independent | Aqua | 2020-08-11 | Int - Planned Corr & FI
Marrero 20" Line pipe & support recoating between Docks 1 and 3 | Item | Candidate | MCAP |  | Maintenance Framework |  | Leal, Trey (Tony) | South | 1. Proposed |  | Atmospheric Corrosion |  | 125000 |  | 125000 | 125000 | 0 | Green | 125000 |  | 125000 | 0 | [9 empty] | 125000 | 125000 | No | Green | 2023-07-01 |  |  |  | 2023-05-31 | [14 empty] | 63000 | 62000 | [5 empty] | 4/3/23 - Scoping complete. Sourcing additional funding. Shift forecast to May. 3/1/2023 - Adjusted forecast to April | 2023-04-03 |  |  | South | Pipelines and Terminals | Integrity |  | Marrero | BMTUA - Marrero Terminal |  |  | 0 | 125000 |  |  |  | Geib, Rob |  |  |  | 1 | 45400 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Marrero 30" manifold strainer removal | Item | Candidate | MEXP |  | Maintenance Framework |  | Campbell, William | South | 1. Proposed |  | South |  | 175000 |  | 175000 | 175000 | 0 | Green | 175000 |  | 175000 | 0 | [9 empty] | 175000 | 175000 | No | Green | 2023-06-01 |  |  |  | 2023-07-31 | [13 empty] | 50000 | 125000 | [10 empty] | South | Pipelines and Terminals | Station/Terminal |  | Marrero | BMTUA - Marrero Terminal |  |  | 50000 | 125000 |  |  |  | Johnson, AJ |  |  |  | 1 | 44361 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Other Programs
Marrero API 570 Inspection | Item | Open | MEXP | BMTUA00E2212 | Maintenance Framework | 2013813 | Aiken, Elaine | South | 3. Active | Defined | Facility Integrity | 254 | 300000 |  | 300253.79 | 300254 | 0 | Green | 300000 |  | 300000 | 254 |  |  | 230000 |  |  | 230000 | Phase | 230000 | 210436 | 300000 | 510436 | No | Green | 2022-09-01 | 2022-08-29 | 2022-08-29 | 2022-10-28 | 2023-02-28 |  |  | 253.79 | [10 empty] | 50000 | 50000 | 100000 | 100000 |  |  |  |  | 3/1/23 - Switch to corporate project manager - Elaine Aiken. 1/3/23- 2022 Phase of project complete, awaiting final reports. 11/1/2022 - Re-accrue 158k to IAG (received invoice this morning). Re-accrue 23k to Stewart and $7k to Catsi. On site work is complete, IAG is finishing up the report 10/3/2022 - Accrue to IAG, Stewart and Catsi for Sep~ 110k, 23k & 7k. 9/6/2022 - Work to be completed in September & October. Added $300k to 2023 for phase 2. 2022-08-05 - Moved $80k from the Marrero insulated pipe inspection project to this project and reduced that forecast to zero, as all of the piping inspection work at Marrero will be completed under this project in 2022 by the same vendor. 8/1/22- IAG pushed schedule to Sept 6/24/22 - TL - Scheduled site visit with IAG on 7/11 for scope finalizations. AFE will be submitted following site visit. | 2023-03-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | Marrero | BMTUA - Marrero Terminal |  | 254 | 50000 | 250000 |  | 210182 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 41196 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Accel Corr & FI
Marrero API 570 Repairs | Item | Open | MEXP |  | Maintenance Framework |  | Leal, Trey (Tony) | South | 1. Proposed |  | Facility Integrity |  | 200000 |  | 200000 | 200000 | 0 | Green | 200000 |  | 200000 | 0 | [9 empty] | 200000 | 200000 | No | Green | 2023-06-01 |  |  |  | 2023-09-30 | [13 empty] | 50000 | 50000 | 50000 | 50000 |  |  |  |  | 4/3/23 - Scoping underway. Shift may forecast to June. 1/29/2023 - Waiting on API 570 report to develop scope. | 2023-04-03 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Marrero | BMTUA - Marrero Terminal |  |  | 50000 | 150000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 44989 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Marrero Boiler Non-Return valves | Item | Candidate | MEXP |  | Maintenance Framework |  | Corman, Chris | South | 1. Proposed |  | Boilers |  | 28000 |  | 28000 | 28000 | 0 | Green | 28000 |  | 28000 | 0 | [9 empty] | 28000 | 28000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 28000 | [10 empty] | South | Pipelines and Terminals | Station/Terminal |  | Marrero | BMTUA - Marrero Terminal |  |  | 0 | 28000 |  |  |  | Stine, Carlton |  |  |  | 1 | 45233 |  | Guest, ProSight | Independent | Aqua | 2022-08-23 | Other Programs
Marrero Dock 2 to 3 lines over water - removal | Item | Open | MEXP |  | Maintenance Framework |  | Leal, Trey (Tony) | South | 1. Proposed |  | Facility Integrity |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 | [9 empty] | 40000 | 40000 | No | Green | 2023-09-01 |  |  |  | 2023-06-30 | [16 empty] | 40000 |  |  |  |  | 4/3/23 - Scoping underway | 2023-04-03 |  |  | South | Pipelines and Terminals | Station/Terminal | Station/Terminal | Marrero | BMTUA - Marrero Terminal |  |  | 0 | 40000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45659 |  | Administrator, System | Independent |  | 2022-08-30 | Int - Planned Corr & FI
Marrero dock TRV installation | Item | Candidate | MEXP |  | Maintenance Framework |  | Magouirk, Josh | South | 1. Proposed |  | Facility Integrity |  | 35000 |  | 35000 | 35000 | 0 | Green | 35000 |  | 35000 | 0 | [9 empty] | 35000 | 35000 | No | Green | 2023-06-01 |  |  |  | 2023-06-30 | [13 empty] | 35000 | [7 empty] | 4/10/23 - Performed field walk with local OP's. Working on SOW and getting bids | 2023-05-01 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Marrero | BMTUA - Marrero Terminal |  |  | 35000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 44362 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
Marrero Insulated Pipe Inspection | Item | Open | MEXP |  | Maintenance Framework |  | Leal, Trey (Tony) | South | 1. Proposed |  | Facility Integrity |  | 275000 |  | 275000 | 275000 | 0 | Green | 275000 |  | 275000 | 0 | [9 empty] | 925000 | 925000 | No | Green | 2023-06-01 |  |  |  | 2023-09-30 | [13 empty] | 75000 | 75000 | 50000 | 75000 |  |  |  |  | 4/3/23 - Scoping underway 1/29/2023 - Waiting on API 570 report to develop scope. | 2023-04-03 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Marrero | BMTUA - Marrero Terminal |  |  | 75000 | 200000 |  |  | 350000 | Aiken, Elaine |  |  |  | 1 | 44990 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
Marrero MODAD to Sewer/Eng Study | Item | Open | MCAP |  | Maintenance Framework |  | Magouirk, Josh | South | 1. Proposed |  | Storm Water Management |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 | [9 empty] | 40000 | 40000 | No | Green | 2023-05-01 |  |  |  | 2023-06-30 | 8 | Yellow | [10 empty] | 20000 | 20000 | [7 empty] | 4/10/23 - Performed field walk with local OP's. Working on SOW and getting bids | 2023-05-01 |  |  | South | Pipelines and Terminals | Operating Infrastructure |  | Marrero | BMTUA - Marrero Terminal |  |  | 40000 |  |  |  |  | Bonenberger, Mark |  |  |  | 1 | 45564 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
Marrero remove 2 ea. Dead Legs in piping | Item | Open | MEXP | BMTUA00E2302 | Maintenance Framework | 2119773 | Leal, Trey (Tony) | South | 3. Active | Defined | Facility Integrity |  | 40000 |  | 40000 | 40000 | 0 | Green | 25000 | 15000 | 40000 | 0 |  |  | 39160 |  |  | 39160 | Full | 39160 |  | 40000 | 40000 | No | Green | 2023-06-01 | 2023-05-01 | 2023-05-01 | 2023-06-30 | 2023-08-31 | [13 empty] | 40000 | [7 empty] | 5/1/2023- AFE approval received today. Shift forecast to June 2023-04-10 - $15k moved to this project from "Marrero Remove Numerous Dead Legs of Dock Lines (ID: 45666, budget: $100k) 4/3/23 - Procurement underway | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | Marrero | BMTUA - Marrero Terminal |  |  | 40000 |  |  |  |  | Aiken, Elaine | Asiedu, Saka |  |  | 1 | 45661 |  | Administrator, System | Independent | Aqua | 2022-08-30 | Int - Planned Corr & FI
Marrero remove insulation from OOS Dock Lines | Item | Open | MEXP |  | Maintenance Framework |  | Magouirk, Josh | South | 1. Proposed |  | Facility Integrity |  | 20000 |  | 20000 | 20000 | 0 | Green | 20000 |  | 20000 | 0 | [9 empty] | 20000 | 20000 | No | Green | 2023-06-01 |  |  |  | 2023-07-31 | [13 empty] | 10000 | 10000 | [6 empty] | 4/10/23 - Performed field walk with local OP's. Working on SOW and getting bids | 2023-05-01 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Marrero | BMTUA - Marrero Terminal |  |  | 10000 | 10000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 45660 |  | Administrator, System | Independent | Aqua | 2022-08-30 | Int - Planned Corr & FI
Marrero remove numerous dead legs of Dock Lines | Item | Open | MEXP |  | Maintenance Framework |  | Leal, Trey (Tony) | South | 1. Proposed |  | Facility Integrity |  | 85000 |  | 85000 | 85000 | 0 | Green | 100000 |  | 100000 | -15000 | [9 empty] | 85000 | 85000 | No | Green | 2023-08-01 |  |  |  | 2023-10-31 | [15 empty] | 60000 |  | 25000 |  |  |  | 2023-04-10 - $15k of forecast moved to "Marrero Remove 2 ea. Dead Legs in Piping" (ID: 45661). 4/3/23 - Procurement underway | 2023-04-10 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Marrero | BMTUA - Marrero Terminal |  |  | 0 | 60000 | 25000 |  |  | Aiken, Elaine |  |  |  | 1 | 45666 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Int - Planned Corr & FI
Marrero South East yard butterfly manifold valves - 2022 | Item | Candidate | MCAP |  | Maintenance Framework |  | Leal, Trey (Tony) | South | 1. Proposed |  | South |  | 140000 |  | 140000 | 140000 | 0 | Green | 140000 |  | 140000 | 0 | [9 empty] | 140000 | 140000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 100000 | 40000 | [5 empty] | 5/1/2023 - Scope Development underway 4/3/23 - Scope development underway. Getting valve pricing 1/29/2023 - Developing scope | 2023-05-01 |  |  | South | Pipelines and Terminals | Operating Infrastructure |  | Marrero | BMTUA - Marrero Terminal |  |  | 0 | 140000 |  |  |  | Johnson, AJ |  |  |  | 1 | 44358 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Other Programs
Marrero Storm Water Improvements Phase 2023 | Item | Open | MCAP | BMTUA00M2302 | Maintenance Framework | 2084417 | Leal, Trey (Tony) | South | 2. Pending AFE | Defined | Storm Water Management | 35000 | 495000 |  | 530000 | 240000 | 290000 | Red | 600000 | -325000 | 275000 | 255000 |  |  | 529561 |  |  |  | Full | 529561 | 35000 | 495000 | 530000 | No | Green | 2023-04-01 |  |  | 2023-09-01 | 2023-07-31 | [5 empty] | 35000 | 35000 | 35000 | 0 | Green |  |  | 50000 | 195000 | 250000 | [6 empty] | 5/8/2023 - Forecast updated to reflect AFE amount and full project cost 5/1/2023 - Full AFE to be submitted this week. Accrue $35k to Golder. 4/3/23 - Supply chain causing delay in project start-up. 3/2/23 - Submitting Full AFE in March. Adjusted forecast. 1/29/2023 - Finishing up engineering for electrical and piping. We have received bids for the pond construction and are in the evaluation period. | 2023-05-08 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Marrero | BMTUA - Marrero Terminal |  |  | 280000 | 250000 |  |  |  | Bonenberger, Mark | Johnson, AJ |  |  | 1 | 45355 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Other Programs
Marrero Storm Water Improvements Phase 2023 - POND | Item | Open | MCAP | BMTUA00M2303 | Maintenance Framework | 2094934 | Leal, Trey (Tony) | South | 3. Active | Emergent | Storm Water Management | 176029 | 110000 |  | 286028.78 | 315788 | -29759 | Yellow |  | 315000 | 315000 | -28971 |  |  | 314838 |  |  | 314838 | Full | 314838 | 176029 | 110000 | 286029 | No | Green | 2023-03-01 | 2023-03-11 | 2023-03-11 | 2023-06-30 | 2023-06-30 |  |  |  |  | 787.5 | 175241.28 | 175000 | 175000 | 241 | Yellow |  |  | 110000 | [8 empty] | 5/1/2023 - Construction underway. Expected to completed in the second week of may. Accrue $175k to PCM 4/3/23 - Project has been delayed 2 weeks to start on 4/10. Added the $100k originally forecasted for March to April forecast. Contractor delay due to manpower issues. 3/1/2023 - This was split out from the Stormwater Phase 2023 project. AFE has been submitted. Work tentatively scheduled for March and April. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Marrero | BMTUA - Marrero Terminal |  | 788 | 285241 |  |  |  |  | Bonenberger, Mark | Bonenberger, Mark |  |  | 1 | 46643 |  | Campbell, Michael | Independent | Aqua | 2023-02-27
Marrero Terminal (BMTUA) Tank 771 - OOS API 653 Insp | Item | Open | MCAP | BMTUA00M2301 | Maintenance Framework | 2083821 | Cole, Caitlyn | South | 3. Active | Defined | Tanks | 245217 | 210000 |  | 455217.03 | 408104 | 47113 | Red | 477000 |  | 477000 | -21783 |  |  | 227110 |  |  | 227110 | Phase | 227110 | 245217 | 210000 | 455217 | No | Green | 2023-02-01 | 2023-02-08 | 2023-02-08 | 2023-05-30 | 2023-03-31 |  |  |  | 100000 | 108104.41 | 37112.62 | 50000 | 50000 | -12887 | Red | [5 empty] | 50000 | 160000 |  |  |  |  | 5/8/23-CES-Move forecast to Fall. Inspector moving to Opelousas. Resume work upon inspector return. Slop tank (non revenue). 5/3/23 CNC - accrue 74944 for Vertex tank cleaning. Tank was cleaned and inspected. 4/4/23-CES-Accrue $158,000 for Vertex and Environmental Safey. Tank Cleaning Complete. Plan for sandblasting and inspection and mobilization of repairs in April.3/2/23 CNC - tank product was removed in February. A window was then cut for cleaning, which is awaiting chemical analysis. 2/8/2023 CNC- cleaning to take place in February, with major repairs anticipated in March and April 2/2/2023 CNC- project delay due to inability to empty tank due to delay in contractor quotes. Plan to start disposing of product 2/6/2023. 11/23/22-Per Discussion with AJ Johnson, Ben Bryant, and Mark Shook, assigning Caitlyn Cole as PM for this project. | 2023-05-08 | Schultz, Amy |  | South | Pipelines and Terminals | Integrity |  | Marrero | BMTUA - Marrero Terminal |  | 208104 | 37113 | 210000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44846 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Marrero Terminal (BMTUA) Tank 808 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | BMTUA00E2301 | Maintenance Framework | 2085513 | Matthews, Clayton | South | 3. Active | Defined | Tanks |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 |  |  | 11000 |  |  | 11000 | Phase | 11000 |  | 10000 | 10000 | No | Green | 2023-08-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-08-31 | [15 empty] | 10000 | [7 empty] | Landeros, Melisa |  | South | Pipelines and Terminals | Tank Integrity |  | Marrero | BMTUA - Marrero Terminal |  |  | 0 | 10000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44847 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Marrero Terminal (BMTUA) Tank 766 – OOS Corr Insp & Refurb | Item | Open | MCAP | BMTUA00M2202 | Maintenance Framework | 1937302 | Matthews, Clayton | South | 3. Active | Defined | Tanks | 4953 |  | 14748 | 4953.21 | 3714 | 1239 | Red |  |  |  | 4953 |  |  | 176000 |  |  | 176000 | Phase | 176000 | 260907 | 14748 | 275655 | No | Green | 2022-03-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-12-31 |  |  | 1287.22 | 1202.48 | 1224.1 | 1239.41 |  |  | 1239 | Red | [10 empty] | 14748 | 9/2/22 CAM Re- Accrue 57k Hydrochem, 8.2.22 CAM Accrue 7500 Catsi, Accrue 10k Laiche, 3.7k ATP, 50k Hydrochem, 9.5k WM 7.1.22 CAM Accrue 3500 Adler, 3000 DJA, 50,000 Hydrochem, 3500 saybolt, 44K Tarsco, 9500 WM. Re accrue 10,000 Catsi, 6/21/22 CAM Varec to be installed 6/23. Tank RTS anticipated on 6/31 6.1.22 CAM Mechanical work complete. Accrue 50,000 Hydrochem/cleanharbors, accrue 6,000 ATP, Accrue 10,000 Catsi, Accrue 43,000 Tarsco. Ph2 AFE generation to be completed. Forecast adjusted for additional Ph2 work with consideration to vendor issues 5/4/22 CAM working through mechanical repair mobilization with HSSE and vendor 4/3/22 CAM Hydrochem has completed the tank cleaning | 2022-09-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Marrero | BMTUA - Marrero Terminal |  | 3714 | 1239 |  |  | 255954 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41288 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Marrero Terminal (BMTUA) Tank 780 – OOS Corr Insp & Refurb | Item | Open | MCAP | BMTUA00M2204 | Maintenance Framework | 1936938 | Bryant, Ben | South | 7. Closed | Defined | Tanks | 41878 |  |  | 41877.91 | 40023 | 1855 | Yellow |  |  |  | 41878 |  |  | 240000 | 645000 |  | 885000 | Full | 885000 | 825549 |  | 825549 | No | Green | 2022-07-01 | 2021-12-30 | 2021-12-30 | 2022-12-31 | 2022-12-31 |  |  | 23724.89 | 9285.31 | 7013.01 | 1854.7 |  |  | 1855 | Red | [11 empty] | 5/1/23 All invoicing complete. Ready to Close. 4/3/23 Re accrue 7K to Eagle Energy. 3/2/2023 Accrue $7K to Eagle Energy. 2/1/23 Awaiting final invoicing from Waste management. Re-accrue 27K to Insulations Inc. and 7k to Catsi 1/2/23 - Accrue 103K to Tarsco, 27K to Insulations Inc, 7K to Catsi, 25K to Waste Management 12/1/22 Tarsco has completed repairs. Barr None is onsite to put coating on 1 shell course. 11/2/22 Tarsco will be onsite 11/7 to begin repairs to Tank 780. Tank will be post inspected and Strapped. Barr none will be onsite to begin coating of rivets upon completion of repair. 10/3/22 Tarsco is working on their unit Pricing to conduct repairs on Tank 780. Tank has been inspected. 9/1/22 Tank has been isolated and is in the process of being cleaned. Matting has been placed around tank. Accrue 40K to ES&H 8/1/22 Receiving Cleaning quotes for this tank. Expected to start cleaning the week of Aug 8th. Accrue 11K to CATSI. 8K to Insulations Inc. 7/1/22 Tank will begin cleaning after 7/18 when Marrero Tank 778 is returned to service. 6/21/22-CES-Per conversation with PM, anticipate higher tank cleaning costs based on tank 788 6 oil cleaning and repairs. 4/1/22 Project will commence upon the completion of Marrero Tank 778. 3/1/22 Project will commence upon the completion of Marrero Tank 766. 2/1/22 Project will commence upon the completion of Marrero Tank 778. Tank is being moved up due to hurricane season. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | Marrero | BMTUA - Marrero Terminal |  | 40023 | 1855 |  |  | 783671 |  | Stine, Carlton | Jones, Kevin |  |  | 1 | 41290 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Marrero Track Drainage - 2022 | Item | Open | MCAP | BMTUA00M2209 | Maintenance Framework | 2013814 | Campbell, William | South | 7. Closed | Defined | Rail | 13189 |  |  | 13188.91 | 13189 | 0 | Green |  |  |  | 13189 |  |  | 194000 |  |  | 194000 | Full | 194000 | 95647 |  | 95647 | No | Green | 2022-09-01 | 2022-08-29 | 2022-08-29 | 2022-12-31 | 2022-11-01 |  |  | 12706.08 | 482.83 | [17 empty] | 3/1/23-Project complete, invoicing complete, close project 2/1/23-Project complete, invoicing complete. 1/1/23-Project complete, invoicing complete 12/5/2022- Re-Accrue $130k HGA 11/4/2022 Accounting accrued the $130K twice which caused the variance. It will self-correct in November. MC 11/1/22-Project complete. Accruals-HGA=130K 10/1/22-Survey complete, project will be complete by end of October 9/1/2022-Survey to be completed in September, work completed in October 7/1/2022-This project will be combined with platform project to create drainage project at Marrero. | 2023-02-23 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Marrero | BMTUA - Marrero Terminal |  | 13189 | 0 |  |  | 82458 |  | Clark, Dave | Johnson, AJ |  |  | 1 | 41682 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
MBCC - Roof Replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Campbell, William | South | 1. Proposed | Defined | Corporate |  | 70000 |  | 70000 | 70000 | 0 | Green | 70000 |  | 70000 | 0 | [9 empty] | 70000 | 70000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 70000 | [10 empty] | Corporate - Pipes and Terminals | Pipelines and Terminals | Operating Infrastructure | Operating Infrastructure | MT Belvieu CC |  |  |  | 0 | 70000 |  |  |  | Clark, Dave |  |  |  | 1 | 41599 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
MBCC - Generator Repairs | Item | Open | MCAP | 1348322M2201 | Maintenance Framework | 2012610 | Campbell, William | South | 3. Active | Drawdown | South | 4090 |  |  | 4090.13 | 4090 | 0 | Green |  |  |  | 4090 |  |  | 103000 |  |  | 103000 | Full | 103000 | 107171 |  | 107171 | No | Green | 2022-09-01 | 2022-08-18 | 2022-08-18 | 2022-12-31 | 2023-02-28 |  |  | 3914 | 176.13 | 0 | 0 |  |  | 0 | Green | [11 empty] | 5/1/23-re-accrue $103 to Waukesha-Pearce 4/1/23-re-accrue $103 to Waukesha-Pearce. Installation scheduled for April. 3/1/23-Accrue $103 Waukesha-Pearce 2/1/23-Accrue $103K Waukesha-Pearce 1/3/23- Accrue $103K Waukesha-Pearce 12/1/22-Generator ordered with transfer switch, will be received this month or early January 10/1/22-Generator has been ordered, long lead time 9/1/22-Quote received, will order generator this month and install in Dec 22 to Jan 23 depending on lead times 8/22/2022-Project was moved from next year to this year due to availability of MCAP drawdown. AFE has been submitted and approved. Forecast dollars are also moved to December 2022 | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | MT Belvieu CC |  |  | 4090 | 0 |  |  | 103081 |  | Johnson, AJ | Asiedu, Saka |  |  | 1 | 43583 |  | Guest, ProSight | Independent | Aqua | 2022-05-05 | Other Programs
Mont Belvieu Control Center Camera System Upgrade | Item | Candidate | MCAP |  | Maintenance Framework |  | Johnson, AJ | South | 1. Proposed |  | Security & Cameras |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 | [9 empty] | 40000 | 40000 | No | Green | 2023-05-01 |  |  |  | 2023-05-31 | 8 | Yellow | [10 empty] | 40000 | [12 empty] | Corporate - Pipes and Terminals | Pipelines and Terminals | Operating Infrastructure |  | MT Belvieu CC |  |  |  | 40000 |  |  |  |  | Clark, Chris |  |  |  | 1 | 41673 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Montgomery - Truck Rack Stormwater Drainage | Item | Open | MCAP | BETEY00M2201 | Maintenance Framework | 2037806 | Corman, Chris | South | 7. Closed | Defined | Secondary Containment | 536 |  |  | 536 | 536 | 0 | Green |  |  |  | 536 |  |  | 43000 |  |  | 43000 | Full | 43000 | 22536 |  | 22536 | No | Green | 2022-12-01 | 2022-10-24 | 2022-10-24 | 2022-12-31 | 2022-12-31 |  |  | 536 | [18 empty] | 3/2/2023 Project complete - ready to close 1/3/23- Accrue $22k to M&S Contracting. Project complete, awaiting invoicing 12/5/2022- Work scheduled for week of 12/12. 11/1/2022 - Line locating will be scheduled for November. 10/3/2022 - Walkthrough will be this week. 9/1/2022 - AFE is being presented for approval today. 7/26/2022 - AFE was missing SPCC cost. Obtaining quotes. 5.2.22 JHB - Project transferred from D. Mitchel to JHB. Requested Diamond Z review existing scan to determine if data is sufficient to calculate height and spill out of existing curbs at truck racks. Confirmed that truck rack containment should be largest compartment of truck (9200 gal) + 24/25 rain event. | 2023-03-02 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Alabama | BETEY - BET MONTGOMERY |  | 536 | 0 |  |  | 22000 |  | Clark, Dave | Johnson, AJ |  |  | 1 | 41924 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Other Programs
Montgomery Shallow pipe remediation | Item | Candidate | MEXP |  | Maintenance Framework |  | Corman, Chris | South | 1. Proposed |  | South |  | 1 |  | 1 |  | 1 | Red |  |  |  | 1 | [9 empty] | 1 | 1 | No | Green | 2023-12-01 |  |  |  | 2023-12-31 | [19 empty] | 1 |  |  |  | Landeros, Melisa |  | South | Pipelines and Terminals | Station/Terminal | [5 empty] | 0 |  | 1 |  |  | Johnson, AJ | Defee, Daniel |  |  | 1 | 46993 |  | Meitzler, Antoinette | Independent | Aqua | 2023-04-27
Montgomery Terminal (BETEY) Tank 111 - OOS API 653 + Seal Insp & Refurb | Item | Open | MEXP | BETEY00E2301 | Maintenance Framework | 2085512 | Matthews, Clayton | South | 3. Active | Defined | Tanks | 49170 | 195000 |  | 244170 | 245000 | -830 | Yellow | 245000 |  | 245000 | -830 |  |  | 149600 |  |  | 149600 | Phase | 149600 | 49170 | 195000 | 244170 | No | Green | 2023-04-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-06-30 | [5 empty] | 49170 | 50000 | 50000 | -830 | Yellow |  |  | 130000 | 65000 | [7 empty] | 5/2/23 CAM Cleaning Complete. OOS Inspection to start 5/3/23 Accrue 10k ATP, accrue 39,170 FHG | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Tank Integrity |  | Alabama | BETEY - BET MONTGOMERY |  |  | 244170 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44852 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Montgomery Terminal Tank Dike Repair | Item | Open | MEXP | BETEY00E2201 | Maintenance Framework | 2011996 | Corman, Chris | South | 7. Closed | Defined | Secondary Containment | -298 |  |  | -297.5 | -298 | 0 | Green |  |  |  | -298 |  |  | 42000 |  |  | 42000 | Full | 42000 | 21931 |  | 21931 | No | Green | 2022-09-01 | 2022-08-11 | 2022-08-11 | 2022-12-01 | 2022-11-01 |  |  | -297.5 | [18 empty] | 1/3/23- Project complete, all invoices received and ready to close. 12/5/22- Re-Accrue $3k to Diamond Z 11/1/2022 - Accrue $3k to Diamond Z. Writing PO for SPCC amendment in November. 10/3/2022 - Dike construction complete. Engineering is issuing as-builts and will be certified Oct/Nov. 9/1/2022 - Work scheduled to begin Mid September. 8/8/2022 - AFE awaiting approval. 5.2.22 JHB - AFE documents ready for presentation, pending scope definition for newly acquired project "montgomery truck rack containment" to assess synergy. 4.4.22 JHB - SOW clarified with program owner. Construction drawings sent to local contractor for budgetary estimate. Once received, will generate AFE documents & schedule bid walk. | 2023-01-03 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | Alabama | BETEY - BET MONTGOMERY |  | -298 | 0 |  |  | 22229 |  | Spari, Markella |  |  |  | 1 | 41379 |  | Guest, ProSight | Independent | Aqua | 2021-08-11 | Other Programs
Montgomery VCU Refractory Replacement | Item | Candidate | MCAP |  | Exempt |  | Pitkin, Colton | South | 1. Proposed |  | Vapor Management |  | 42000 |  | 42000 | 42000 | 0 | Green | 42000 |  | 42000 | 0 | [9 empty] | 42000 | 42000 | No | Green | 2023-07-01 |  |  |  | 2023-05-31 | [14 empty] | 42000 | [6 empty] | 5//1/2023 - Received quotes for new shroud with refractory. Lead times are expected to be 6 to 8 weeks | 2023-05-01 |  |  | South | Pipelines and Terminals | Operating Infrastructure |  | Alabama | BETEY - BET MONTGOMERY |  |  | 0 | 42000 |  |  |  | Karl, Marissa |  | N/A |  | 1 | 31049 |  | Arnold, Andrew | Independent | Aqua | 2018-08-27 | Other Programs
North Augusta Asphalt Parking lot Repair | Item | Open | MCAP | BETTW00M2301 | Maintenance Framework | 2095598 | Leal, Trey (Tony) | South | 7. Closed | Defined | South | 35936 |  |  | 35935.76 | 43000 | -7064 | Red | 22000 |  | 22000 | 13936 |  |  | 43780 |  |  | 43780 | Full | 43780 | 35936 |  | 35936 | No | Green | 2023-04-01 | 2023-03-18 | 2023-03-18 | 2023-05-31 | 2023-03-31 | [5 empty] | 35935.76 | 43000 | 43000 | -7064 | Red | [11 empty] | 5/1/2023 - Project Complete 4/3/23 - PO has been cut 3/1/2023 - Quotes received. Adjusted forecast out to April 1/29/2023 - Waiting to receive quote. Forecast for March looks good | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | South Carolina | BETTW - BET NORTH AUGUSTA |  |  | 35936 |  |  |  |  | Johnson, AJ | Asiedu, Saka |  |  | 1 | 44427 |  | Guest, ProSight | Independent | Aqua | 2022-08-04 | Other Programs
North Augusta Backflow Preventer | Item | Open | MEXP | BETTW00E2302 | Maintenance Framework | 2095108 | Corman, Chris | South | 7. Closed | Drawdown | Fire Protection | 13950 |  |  | 13950 | 14000 | -50 | Yellow |  | 20000 | 20000 | -6050 |  |  | 20000 |  |  | 20000 | Full | 20000 | 13950 |  | 13950 | No | Green | 2023-04-01 | 2023-03-15 | 2023-03-15 | 2023-07-01 | 2023-07-01 | [5 empty] | 13950 | 14000 | 14000 | -50 | Yellow | [11 empty] | 5/1/2023 - Project is completed 4/4/2023- Project approved, PO's have been issued Work is planned for april. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | South Carolina | BETTW - BET NORTH AUGUSTA |  |  | 13950 |  |  |  |  | Jakubowski, Gregory | Smith, Mark D. | N/A |  | 1 | 46775 |  | Johnson, AJ | JDE Child | Burnt Orange | 2023-03-14
North Charleston - Operations Building Upgrades | Item | Candidate | MCAP |  | Maintenance Framework |  | Campbell, William | South | 1. Proposed |  | South |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 | [9 empty] | 50000 | 50000 | No | Green | 2023-06-01 |  |  |  | 2023-06-30 | [13 empty] | 50000 | [11 empty] | South | Pipelines and Terminals | Operating Infrastructure |  | Southeast Terminals | BETQH - BET NORTH CHARLESTON TERMINAL |  |  | 50000 |  |  |  |  | Johnson, AJ |  |  |  | 1 | 37854 |  | Guest, ProSight | Independent | Aqua | 2020-08-13 | Other Programs
North Charleston Additive Tanks 21 and 22 | Item | Open | MEXP | BETQH00E2301 | Maintenance Framework | 2095595 | Bryant, Ben | South | 3. Active | Defined | South |  | 20000 |  | 20000 | 20000 | 0 | Green | 20000 |  | 20000 | 0 |  |  | 20000 |  |  | 20000 | Full | 20000 |  | 20000 | 20000 | No | Green | 2023-05-01 | 2023-03-18 | 2023-03-18 | 2023-05-30 | 2023-04-30 | [6 empty] | 20000 | 20000 | -20000 | Red |  |  | 20000 | [8 empty] | 5/1/23 Paint crew was slated to be onsite 4/24 but rescheduled to be onsite in May. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | Southeast Terminals | BETQH - BET NORTH CHARLESTON TERMINAL |  |  | 20000 |  |  |  |  | Johnson, AJ | Asiedu, Saka |  |  | 1 | 44382 |  | Guest, ProSight | Independent | Aqua | 2022-08-02 | Other Programs
North Charleston Asphalt Drive Repair | Item | Candidate | MCAP |  | Maintenance Framework |  | Campbell, William | South | 1. Proposed |  | South |  | 85000 |  | 85000 | 85000 | 0 | Green | 85000 |  | 85000 | 0 | [9 empty] | 85000 | 85000 | No | Green | 2023-06-01 |  |  |  | 2023-05-31 | [13 empty] | 85000 | [11 empty] | South | Pipelines and Terminals | Operating Infrastructure |  | Southeast Terminals | BETQH - BET NORTH CHARLESTON TERMINAL |  |  | 85000 |  |  |  |  | Johnson, AJ |  |  |  | 1 | 44481 |  | Guest, ProSight | Independent | Aqua | 2022-08-09 | Other Programs
North Charleston Flame Arrestor Cleaning 2022 | Item | Open | MEXP | BETQH00E2204 | Maintenance Framework | 2037298 | Corman, Chris | South | 7. Closed | Drawdown | South | -42000 |  |  | -42000 | -42000 | 0 | Green |  |  |  | -42000 |  |  | 40000 |  |  | 40000 | Full | 40000 | -499 |  | -499 | No | Green | 2022-11-01 | 2022-10-18 | 2022-10-18 | 2022-12-30 | 2022-12-30 |  |  | -42000 | [18 empty] | 1/3/23- Project complete. 12/5/22- Accrue $17k to Triten Industrial and $25k to J2 Resources 10/18/2022 - Input 40k forecast in November. Project funded from South MEXP drawdown. | 2023-01-03 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | Southeast Terminals | BETQH - BET NORTH CHARLESTON TERMINAL |  | -42000 | 0 |  |  | 41501 |  | Johnson, AJ | Smith, Mark D. | N/A |  | 1 | 46071 |  | Johnson, AJ | JDE Child | Burnt Orange | 2022-10-17 | Other Programs
North Charleston Insulated Pipe Priority 2 Repairs | Item | Open | MEXP |  | Maintenance Framework |  | Campbell, William | South | 1. Proposed |  | Facility Integrity |  | 15000 |  | 15000 | 15000 | 0 | Green | 15000 |  | 15000 | 0 | [9 empty] | 15000 | 15000 | No | Green | 2023-06-01 |  |  |  | 2023-05-31 | [13 empty] | 15000 | [11 empty] | South | Pipelines and Terminals | Station/Terminal |  | Southeast Terminals | BETQH - BET NORTH CHARLESTON TERMINAL |  |  | 15000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45072 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Planned Corr & FI
North Charleston Mooring Dolphin Project 2022 | Item | Open | MCAP | BETQH00M2204 | Project Framework | 2011255 | Campbell, William | South | 7. Closed | Defined | Marine | 425325 |  |  | 425324.9 | 424114 | 1211 | Yellow | 600000 |  | 600000 | -174675 |  |  | 1414000 |  |  | 1414000 | Full | 1414000 | 677556 |  | 677556 | No | Green | 2022-09-01 | 2022-09-15 | 2022-09-15 | 2022-12-31 | 2023-02-28 |  |  | 7849.82 | 389362.59 | 26901.9 | 1210.59 |  |  | 1211 | Red | [11 empty] | 4/1/23-Project complete, invoicing complete. Close project 3/1/23-Project complete, Accrue $600K to Callen Marine. This includes the previous $200K already accrued. 2.14.23.DLC: Reduced forecast by $200k for project actuals...2/1/23-Accrue $200K to Callen Marine 1/1/23- Accrue $200k Callen Marine 12/12/22 - Per PM, advantageous savings from efficient bids significantly lower than budgeted. DC 12/1/22-PO cut to Callen. Materials being ordered and fabrication to begin this month 11/7/2022 Reduced forecast for 2022 to 200k to reflect fabrication costs. CMC 11/1/22-Bid walk complete, Callan Marine will be contractor, should have PO by Nov 7 and will begin ordering supplies. 10/1/22-AFE approved, waiting on bids 9/1/22-AFE submitted, TRC approved. Engineering package to be received this month and bid walk completed 7/20/22-Project was combined and AFE will be submitted for approval on 7/28 6.9.22.DLC: moved to likely month of execution | 2023-04-03 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Southeast Terminals | BETQH - BET NORTH CHARLESTON TERMINAL |  | 424114 | 1211 |  |  | 252231 |  | Spari, Markella | Johnson, AJ |  |  | 1 | 41539 |  | Administrator, System | Independent | Aqua | 2021-08-19 | Marine
North Charleston Phase 1 Insulated Piping Inspection | Item | Open | MEXP |  | Maintenance Framework |  | Campbell, William | South | 1. Proposed |  | Facility Integrity |  | 8000 |  | 8000 | 8000 | 0 | Green | 8000 |  | 8000 | 0 | [9 empty] | 8000 | 8000 | No | Green | 2023-06-01 |  |  |  | 2023-06-30 | [13 empty] | 8000 | [11 empty] | South | Pipelines and Terminals | Station/Terminal |  | Southeast Terminals | BETQH - BET NORTH CHARLESTON TERMINAL |  |  | 8000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 41181 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
North Charleston Rack Canopy | Item | Open | MEXP | BETQH00E2202 | Maintenance Framework | 1990661 | Corman, Chris | South | 7. Closed | Defined | Truck Racks | -5680 |  |  | -5680 | -5680 | 0 | Green |  |  |  | -5680 |  |  | 50000 |  |  | 50000 | Full | 50000 | 20161 |  | 20161 | No | Green | 2022-07-01 | 2022-06-15 | 2022-06-15 | 2022-10-01 | 2023-02-28 |  |  | -5680 | [18 empty] | 5/1/23 - Project is complete. Can be closed 1/3/23- Project on hold. Rack canopy was too expensive and looking for alternative. 12/5/2022 - ReAccrue $15k to Arseal. 11/1/22- ReAccrue $15k to Arseal. 10/3/2022 - Engineering complete. Bidding options for a driver booth. Accrue $15k to Arseal. 9/1/2022 - Accrue $25k to Arseal. Engineering to continue in September. 8/8/22- Laser scan completed in August. Engineering to begin through September. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | Southeast Terminals | BETQH - BET NORTH CHARLESTON TERMINAL |  | -5680 | 0 |  |  | 25841 |  | Younce, Michael | Asiedu, Saka |  |  | 1 | 35229 |  | Bare, Greg | Independent | Aqua | 2019-09-23 | Other Programs
North Charleston Rack Canopy Phase 2 | Item | Open | MCAP | BETQH00M2302 | Maintenance Framework | 2109908 | Pitkin, Colton | South | 3. Active | Drawdown | Truck Racks |  | 100000 |  | 100000 | 90000 | 10000 | Red | 90000 |  | 90000 | 10000 |  |  | 100465 |  |  | 100465 | Full | 100465 |  | 100000 | 100000 | No | Green | 2023-05-01 | 2023-04-04 | 2023-04-04 | 2023-07-15 | 2023-07-31 | [12 empty] | 65000 | 10000 |  | 25000 | [5 empty] | 5/1/2023- Phase 1 engineering done in 2022, Half the work will be done on Phase 2 in 2023. We will need 150K to complete the work in 2024 4/2/2023 - Project approved for a phased out repair. We will repair canopy this year and purchase partial materials for next year's work. forecast updated. 2/2/2023 - Have scoped out project. Will look to budget buying 4 card reader shelters for lanes 1, 2, 4, 8 and repair leaks in overhead structure. | 2023-05-03 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Southeast Terminals | BETQH - BET NORTH CHARLESTON TERMINAL |  |  | 75000 | 25000 |  |  |  | Younce, Michael |  |  |  | 1 | 45265 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Other Programs
North Charleston Repair Garage Building Bathroom | Item | Open | MCAP | BETQH00M2203 | Maintenance Framework | 1971234 | Corman, Chris | South | 4. On-Hold | Defined | South | 153 |  |  | 152.86 | 153 | 0 | Green |  |  |  | 153 |  |  | 53000 |  |  | 53000 | Full | 53000 | 33292 |  | 33292 | No | Green | 2022-06-01 | 2022-04-13 | 2022-04-13 | 2022-05-30 | 2023-01-31 |  |  | 152.86 | [18 empty] | 12/15/2022 - discussed with Mark Smith and he would like to leave this project open to find someone to complete the scope through the 1st quarter of 2023. 11/29.2022 - Many attempts were made to contact the contractor but never a response. I spoke to Mark Smith and told him of the issue and let him know the project would be terminated by the end of November. The lab got built but the windows and bathroom nothing was done. EAC $32,847.96. 11/1/2022 - Contractor was unavailable all month so no work was accomplished. 9/30/2022 - Top Notch completed and fully invoiced. Ninja partially invoiced and paid. Ninja's work was stopped in September due to waiting on a payment. Work to be completed in October. EAC $45,106. 9/1/22- Reaccrue $37k from last month for Top Notch and Ninja. Top Notch work completed. Ninja had scheduling conflicts. Work to be completed.in September. 7/29-2022 - Reaccrue the 6/30 vendors. Accrue Top Notch $2K Accrue Ninja $18K. Re-accrue $17k from Top Notch and Ninja. Project to be completed in August. EAC $44K 6/30/2022 - Accrue Top Notch Heating and Cooling $9k, Accrue Ninja Industrial Contractors $8K. EAC $44K 5/31/2022The work didn't start until the the 25th because of a needed COI. 5/3/2022 - AFE approved. PO going out. Work to start 2nd week of May. 3/31/2022 - AFE in routing for approval. The work will start in April. 3/1/2022 - Getting the last quote. 2/21/2022 - Project delayed getting started due to getting quotes. 1/29/2022 - Made a trip to look over the work. Getting quotes to do the work. Will submit the AFE and start the work in February. | 2023-03-20 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Southeast Terminals | BETQH - BET NORTH CHARLESTON TERMINAL |  | 153 | 0 |  |  | 33139 |  | Johnson, AJ | Asiedu, Saka |  |  | 1 | 35230 |  | Bare, Greg | Independent | Aqua | 2019-09-23 | Other Programs
North Charleston Tank 9305 and 9307 Stairs | Item | Open | MEXP | BETQH00E2302 | Maintenance Framework | 2095594 | Bryant, Ben | South | 3. Active | Defined | Tanks |  | 21000 |  | 21000 | 21000 | 0 | Green | 21000 |  | 21000 | 0 |  |  | 20000 |  |  | 20000 | Full | 20000 |  | 21000 | 21000 | No | Green | 2023-05-01 | 2023-03-18 | 2023-03-18 | 2023-05-30 | 2023-03-31 | [6 empty] | 21000 | 21000 | -21000 | Red |  | Contractor/Vendor Issue | 21000 | [8 empty] | 5/1/23 Paint crew was slated to be onsite 4/24 but rescheduled to be onsite in May. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Tank Integrity |  | Southeast Terminals | BETQH - BET NORTH CHARLESTON TERMINAL |  |  | 21000 |  |  |  |  | Stine, Carlton | Stiles, Mark |  |  | 1 | 44378 |  | Guest, ProSight | Independent | Aqua | 2022-08-02 | Int - Tanks
North Charleston Terminal (BETQH) Tank 9314 – OOS Seal Inspection | Item | Open | MCAP | BETQH00M2201 | Maintenance Framework | 1936940 | Bryant, Ben | South | 6. Operational | Defined | Tanks | 421642 |  |  | 421641.52 | 423637 | -1995 | Yellow |  |  |  | 421642 |  |  | 252000 |  |  | 252000 | Phase | 252000 | 694261 |  | 694261 | No | Green | 2022-10-01 | 2021-12-30 | 2021-12-30 | 2022-12-02 | 2023-03-01 |  |  | 71673.97 | 248187.87 | 55774.96 | 46004.72 | 48000 | 48000 | -1995 | Yellow | [11 empty] | 4/7/23 Accrue 29K to Rosemont. Accrue 8K to Barr none. Awaiting Waste Management Charges. 3/2/2023 - Re-accrue $195K to Hepaco. Tank back in service. Finishing exterior probe work in March. A Phase II AFE will be submitted for this project. 2/1/23 Tank has been repaired, A liner is being put inside. Re accrue 195K to Hepaco. Accrue 50K to spyglass and 20K to Barr None. A Phase II AFE will be submitted for this project. 1/2/23 Accrue 195K to Hepaco. 20K to Barr None. 12/1/22 Awaiting unit pricing for Repairs. Tank will be cable suspended. Allentech has a 5-6 weeks lead time in parts. Accrue 10k to DJA, 20K to Spyglass, 120K to Hepaco. 11/2/22 Tank has been isolated and cleaned. Accrue 90K to Hepaco. 10/3/22 Cleaning contractor will mobilize to site on 10/10/22. Tank will be isolated and cleaned. 9/1/22 Tank Project will kickoff the week of 9/19. 4/1/22 Cleaning Bid has been awarded to HEPACO. | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | Southeast Terminals | BETQH - BET NORTH CHARLESTON TERMINAL |  | 375637 | 46005 |  |  | 272619 |  | Stine, Carlton | Jones, Kevin |  |  | 1 | 41300 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
North Charleston VRU Release Prevention | Item | Open | MCAP | BETQH00M2303 | Maintenance Framework | 2109908 | Pitkin, Colton | South | 3. Active | Drawdown | Vapor Management | 15000 | 65000 |  | 80000 | 80000 | 0 | Green | 58000 |  | 58000 | 22000 |  |  | 80815 |  |  | 80815 | Full | 80815 | 15000 | 65000 | 80000 | No | Green | 2023-04-01 | 2023-04-04 | 2023-04-04 | 2023-07-15 | 2023-07-15 | [5 empty] | 15000 | 15000 | 15000 | 0 | Green |  |  | 65000 | [8 empty] | 5/3/23 Accrue $15K to TPC Industrial 4-4-23 Project moved up to second qtr. per scheduling. Vapor team provided additional funds 23K from other projects within the program that were canceled. | 2023-05-04 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Southeast Terminals | BETQH - BET NORTH CHARLESTON TERMINAL |  |  | 80000 |  |  |  |  | Karl, Marissa | Johnson, AJ |  |  | 1 | 44951 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Other Programs
Opelousas Terminal (BETOP) Tank 102 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | BETOP00M2301 | Maintenance Framework | 2075762 | Matthews, Clayton | South | 3. Active | Defined | Tanks |  | 543747 | 26750 | 543747 | 543747 | 0 | Green | 543747 |  | 543747 | 0 |  |  | 311638 |  |  | 311638 | Phase | 311638 |  | 570497 | 570497 | No | Green | 2023-06-01 | 2023-01-17 | 2023-01-17 | 2023-12-30 | 2023-08-31 | [13 empty] | 72747 | 250000 | 221000 |  |  |  |  | 26750 |  |  | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Opelousas | BETOP - BET OPELOUSAS TERMINAL |  |  | 72747 | 471000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44858 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Opelousas Terminal (BETOP) Tank 101 - API 653 Out of Service Support Project | Item | Open | MCAP | BETOP00M2302 | Maintenance Framework | 2075761 | Matthews, Clayton | South | 3. Active | Defined | Tanks | 75554 | 150000 |  | 225554 | 350000 | -124446 | Red | 400354 |  | 400354 | -174800 |  |  | 296492 |  |  | 296492 | Phase | 296492 | 75554 | 150000 | 225554 | No | Green | 2023-04-01 | 2023-01-17 | 2023-01-17 | 2023-12-30 | 2023-05-31 | [5 empty] | 75554 | 200000 | 200000 | -124446 | Red |  | Buckeye/Customer Schedule | 150000 | [8 empty] | 5/2/23 CAM Accrue 50,554 Don Miller, Accrue 20k Catsi, Accrue 5K ATP Late start on project. 4.13.23 ML - Variance is due to Piping modification determine to take place between 102 and 101. Originally forecasted to take place before 1st tank execution . | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Opelousas | BETOP - BET OPELOUSAS TERMINAL |  |  | 225554 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44908 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
PP862HF BTP AND BTH PIPE SUPPORTS UPGRADES | Item | Open | MCAP | PP862HFM2001 | Maintenance Framework | 1793712 | Garcia, Monica | South | 7. Closed | Defined | South |  |  |  | 0 |  | 0 | Green | [10 empty] | Interim |  | 0 |  | 0 | No | Green | 2020-12-01 |  |  |  | 2023-03-31 | [21 empty] | 1/19/23 MLG: Changed Project Status to Closed and closed work order. 9/13/22 MLG- will resubmit the engineered IFC to contractors for a revised quote for the installation of the concrete pad. 3.17.22.DLC: Project on hold for 2023 consideration. 2/8/22 MLG: The Estimated Operational Date has been changed to reflect 2023 Operational Date. 2/1/22 MLG: Scope of work is in development and the Full AFE will be submitted as soon as the financials have been determined. 1/4/22 MLG-Project scope of work development will occur in January. 12/1/21 MLG: Project work scheduled for 2022. 11/2/21 MLG- No project work for 2021. 2/10/2021 MLG: Project Status changed back to Pending AFE due project financials to be confirmed and closed out. 2/9/2021 MLG: This project has been cancelled; the area greater than the concrete pad dimension requires modification. The 20 acres area will be re-evaluated for modification. | 2023-01-19 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 0 |  |  | -6957 |  | Johnson, AJ |  |  |  | 1 | 39218 |  | Schultz, Amy | Independent | Aqua | 2020-12-22 | Other Programs
PP863HF BTP AND BTH PIPE SUPPORTS UPGRADES | Item | Open | MCAP | PP863HFM2001 | Maintenance Framework | 1783713 | Garcia, Monica | South | 7. Closed | Defined | South |  |  |  | 0 |  | 0 | Green | [10 empty] | Interim |  | -7209 |  | -7209 | No | Green | 2020-12-01 |  |  |  | 2023-03-31 | [21 empty] | 1/19/23 MLG: Changed Project Status to Closed and closed work order. 9/13/22 MLG- will resubmit the engineered IFC to contractors for a revised quote for the installation of the concrete pad. 3.17.22.DLC: Project on hold for 2023 consideration. 2/8/22 MLG: The Estimated Operational Date has been changed to reflect 2023 Operational Date. 2/1/22 MLG: Scope of work is in development and the Full AFE will be submitted as soon as the financials have been determined. 1/4/22 MLG-Project scope of work development will occur in January. 12/1/21 MLG: Project work scheduled for 2022. 11/2/21 MLG- No project work for 2021. 2/10/2021 MLG: Project Status changed back to Pending AFE due project financials to be confirmed and closed out. 2/9/2021 MLG: This project has been cancelled; the area greater than the concrete pad dimension requires modification. The 20 acres area will be re-evaluated for modification. | 2023-01-19 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 0 |  |  | -14009 |  | Johnson, AJ |  |  |  | 1 | 39219 |  | Schultz, Amy | Independent | Aqua | 2020-12-22 | Other Programs
PP865HF BTP AND BTH PIPE SUPPORT MEXP FLIP | Item | Open | MEXP | PP865HFE2201 | Maintenance Framework |  | Garcia, Monica | South | 6. Operational | Unplanned | South | 3015 |  |  | 3014.97 | 3015 | 0 | Green |  |  |  | 3015 |  |  | 7247 |  |  | 7247 | Full | 7247 | 3015 |  | 3015 | No | Green | 2023-01-01 | 2022-12-16 | 2022-12-16 | 2022-12-31 | 2022-12-31 |  |  | 3014.97 | [20 empty] | Landeros, Melisa |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 3015 | 0 |  |  |  |  | Johnson, AJ | Johnson, AJ |  |  | 1 | 46355 |  | Meitzler, Antoinette | Independent | Aqua | 2022-12-13 | Other Programs
PP865HF BTP AND BTH PIPE SUPPORTS UPGRADES | Item | Open | MCAP | PP865HFM2001 | Maintenance Framework | 1783715 | Garcia, Monica | South | 8. Canceled | Defined | South | -7247 |  |  | -7247.43 | -7247 | 0 | Green |  |  |  | -7247 | [6 empty] | Interim |  | 0 |  | 0 | No | Green | 2020-12-01 |  |  |  | 2023-02-02 |  |  | -7247.43 | [18 empty] | 2/1/23 MLG: This project has been canceled and the Total Project Actuals will be reclassed to PP865HFE2201 - PP868HF BTP AND BTH PIPE SUPPORTS MEXP FLIP. 9/13/22 MLG- will resubmit the engineered IFC to contractors for a revised quote for the installation of the concrete pad. 3.17.22.DLC: Project on hold for 2023 consideration. 2/8/22 MLG: The Estimated Operational Date has been changed to reflect 2023 Operational Date. 2/1/22 MLG: Scope of work is in development and the Full AFE will be submitted as soon as the financials have been determined. 1/4/22 MLG-Project scope of work development will occur in January. 12/1/21 MLG: Project work scheduled for 2022. 11/2/21 MLG- No project work for 2021. 2/10/2021 MLG: Project Status changed back to Pending AFE due project financials to be confirmed and closed out. 2/9/2021 MLG: This project has been cancelled; the area greater than the concrete pad dimension requires modification. The 20 acres area will be re-evaluated for modification. | 2023-02-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | -7247 | 0 |  |  | 409 |  | Johnson, AJ |  |  |  | 1 | 39221 |  | Schultz, Amy | Independent | Aqua | 2020-12-22 | Other Programs
PP867HF BTP AND BTH PIPE SUPPORTS MEXP FLIP | Item | Open | MEXP | PP867HFE2201 | Maintenance Framework |  | Garcia, Monica | South | 6. Operational | Unplanned | Secondary Containment |  |  |  | 0 |  | 0 | Green | [6 empty] | 545 |  |  | 545 | Full | 545 |  |  |  | No | Green |  | 2022-12-16 | 2022-12-16 | 2022-12-31 | 2023-02-28 | [21 empty] | 2/1/23 MLG: Project Actuals will be reclassed from PP867HFM2001 - BTXPP PP867HF BTP and BTH Pipe Support Upgrades to this project. | 2023-02-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  |  | 0 |  |  |  |  | Spari, Markella | Johnson, AJ |  |  | 1 | 46394 |  | Meitzler, Antoinette | Independent | Aqua | 2022-12-20 | Other Programs
PP868HF BTP AND BTH PIPE SUPPORT MEXP FLIP | Item | Open | MEXP | PP868HFE2201 | Maintenance Framework |  | Garcia, Monica | South | 6. Operational | Unplanned | South |  |  |  | 0 |  | 0 | Green | [6 empty] | 545 |  |  | 545 | Full | 545 |  |  |  | No | Green |  | 2022-12-16 | 2022-12-16 | 2022-12-31 | 2023-02-28 | [21 empty] | 2/1/23 MLG: Project Actuals will be reclassed from PP868HFM2001 - BTXPP PP868HF BTP and BTH Pipe Support Upgrades to this project. | 2023-02-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  |  | 0 |  |  |  |  | Johnson, AJ | Johnson, AJ |  |  | 1 | 46357 |  | Meitzler, Antoinette | Independent | Aqua | 2022-12-13 | Other Programs
PP868HF BTP AND BTH PIPE SUPPORTS UPGRADES | Item | Open | MCAP | PP868HFM2001 | Maintenance Framework | 1783718 | Garcia, Monica | South | 8. Canceled | Defined | South |  |  |  | 0 |  | 0 | Green | [10 empty] | Interim |  | 0 |  | 0 | No | Green | 2020-12-01 |  |  |  | 2023-03-31 | [21 empty] | 2/1/23 MLG: This project has been canceled and the Total Project Actuals has been reclassed to PP868HFE2201 - PP868HF BTP AND BTH PIPE SUPPORTS MEXP FLIP. 3.17.22.DLC: Project on hold for 2023 consideration. 2/8/22 MLG: The Estimated Operational Date has been changed to reflect 2023 Operational Date. 2/1/22 MLG: Scope of work is in development and the Full AFE will be submitted as soon as the financials have been determined. 1/4/22 MLG-Project scope of work development will occur in January. 12/1/21 MLG: Project work scheduled for 2022. 11/2/21 MLG- No project work for 2021. 2/10/2021 MLG: Project Status changed back to Pending AFE due project financials to be confirmed and closed out. 2/9/2021 MLG: This project has been cancelled; the area greater than the concrete pad dimension requires modification. The 20 acres area will be re-evaluated for modification. | 2023-02-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  |  | 0 |  |  | -217 |  | Johnson, AJ |  |  |  | 1 | 39223 |  | Schultz, Amy | Independent | Aqua | 2020-12-22 | Other Programs
PP999A3 - DIG SHEETS (8) BPL-Other - Due 11-01-21 | Item | Open | MCAP | PP999A3M2201 | Exempt | 2014049 | Garcia, Monica | South | 4. On-Hold | Defined | Pipeline Digs | 10528 | 185000 |  | 195528.09 | 408011 | -212483 | Red |  |  |  | 195528 |  |  | 335000 |  |  | 335000 | Full | 335000 | 150143 | 185000 | 335143 | No | Green | 2022-10-01 | 2022-08-31 | 2022-08-31 | 2021-11-30 | 2023-12-29 |  |  | -2463.5 | 3908.57 | 6566.07 | 2516.95 |  |  | 2517 | Red | [7 empty] | 55000 | 130000 |  |  | 5/1/23 MLG: Project Status has been changed to Hold, the costs of digging in the Superfund site may have to be shifted to 2024. 4/4/23 MLG: Corporate submitted the Excavation Plan to the EPA on 3/30/23 and EPA's response was that it will take over 30 days for a response. Exploring the option to bore a new section of pipe in order to remove the section of line out of the Superfund site. It has been conveyed that a concrete pad will be installed on top of the current section of pipe in the superfund site. 3/1/23 MLG: waiting on EPA approval. 2/2/23 MLG: Held a meeting with Corporate Remediation group was held on January 26th to review the plan for digging in the Super Fund site. Corporate will be submitting the approved plan to the EPA for final approval. We will not be using any water for the Super Fund dig sites. 1/4/23 MLG: Variance due to Corporate has reassigned this project to a 3rd Remediation Project Manager and he wants to hold a meeting prior to submitting the final plan to the EPA, therefore, no digs were performed in December. This meeting is scheduled for January 20th. 12/5/22 MLG: Variance due to EPA has requested information regarding site staging, dimensions of excavation sites (length & width), if we can dig without water, and how much room is needed for equipment. Working on obtaining the information and will submit the information to Environmental so they can submit the answers to EPA. 11/2/22 MLG: variance due to unable to perform additional digs, awaiting invoices. Forecast is for the remaining digs in the Superfund site. Awaiting information and approval from the EPA prior to performing the remaining digs. 9/13/22 MLG-AFE has been approved, moving forward with digs, although, one of the dig sites falls within a Superfund site, Environmental is working Corporate and the EPA regarding this location. 8/2/22 MLG- Forecast shifted by one month; digs are in active bidding process, bids are due 8/5/22. | 2023-05-01 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 8011 | 2517 |  | 185000 | 139615 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40069 |  | Schultz, Amy | Independent | Aqua | 2021-05-11 | Int- Planned Digs
Selma (BSEVS) Tank 41 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | BSEVS00E2301 | Maintenance Framework | 2085516 | Matthews, Clayton | South | 5. Deferred | Defined | Tanks |  | 1 |  | 1 | 1 | 0 | Green | 329796 |  | 329796 | -329795 |  |  | 184250 |  |  | 184250 | Phase | 184250 |  | 1 | 1 | No | Green | 2023-12-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-12-31 | [17 empty] | 0 | 0 | 1 |  | 4.5.23 Project Deferred. | 2023-04-05 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | North Carolina | BSEVS - SELMA TERMINAL |  |  | 0 |  | 1 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44879 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
South Region OGI {FLIR} Camera | Item | Open | MCAP | BTXPP00M2219 | Maintenance Framework | 2022552 | Garcia, Monica | South | 7. Closed | Drawdown | South | 35 | 1 |  | 36 | 36 | 0 | Green |  |  |  | 36 |  |  | 107000 |  | 13000 | 107000 | Full | 120000 | 120059 | 1 | 120060 | No | Green | 2022-09-01 | 2022-09-13 | 2022-09-13 | 2022-12-31 | 2022-11-03 |  |  |  |  | 35 | [14 empty] | 1 |  | 1/19/23 MLG: Changed Project Status to Closed and closed work order. 11/4/22 MLG Variance is due to the Vendor charging an additional $7k for Safety/Sec/Envir & Fire Supp. Also, there is a little over $4k in CWIP. No future forecast and all invoices have been received. 9/6/2022 MLG: This project has been pulled into the 2022 budget year; on 9/6/22 AFE was submitted for routing approval. | 2023-01-19 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 35 | 0 |  | 1 | 120024 |  | Johnson, AJ | Johnson, AJ |  |  | 1 | 45555 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
Spartanburg Dike Drain Valve Installation | Item | Candidate | MCAP |  | Maintenance Framework |  | Campbell, William | South | 1. Proposed |  | Secondary Containment |  | 75000 |  | 75000 | 75000 | 0 | Green | 75000 |  | 75000 | 0 | [9 empty] | 75000 | 75000 | No | Green | 2023-06-01 |  |  |  | 2023-05-31 | [13 empty] | 25000 | 50000 | [10 empty] | South | Pipelines and Terminals | Operating Infrastructure |  | South Carolina | BETNU - BET SPARTANBURG |  |  | 25000 | 50000 |  |  |  | Clark, Dave |  |  |  | 1 | 45824 |  | Clark, David | Independent | Aqua | 2022-09-12 | Other Programs
STXFI - Site Stabilization study to prevent silt and sediment discharge | Item | Open | MEXP |  | Maintenance Framework |  | Burke, Joshua | South | 1. Proposed |  | South |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 | [9 empty] | 100000 | 100000 | No | Green | 2023-06-01 |  |  |  | 2023-07-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 50000 | 0 | 30000 | 20000 |  |  |  |  | 5.3.23 JHB - James Dalton developing AFE documents. Moving May FC to June, work to be completed within 1 month duration. 4.10.23 JHB - 50k moved to Q3 - assuming correction of identified areas and partial area seeding followed by additional identiified work in Q3. 4.3.23 JHB - Proposals received on 4/3 - preparing AFE documents. Adjusting forecast based on anticipated start dates. 3.1.23 JHB - Environmental group provided recommendations - preparing AFE documents. Adjusting forecast based on preliminary schedule. 2.1.23 JHB - Funding intended for STG, not field services. Met with environmental group to discuss scope. Scope options in development. | 2023-05-03 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Corpus Christi | BTXFI - Buckeye Texas Field Services |  |  | 50000 | 50000 |  |  |  | Johnson, AJ |  |  |  | 1 | 45199 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
STXXI – API 570 Inspection | Item | Open | MEXP | STXXI00E2203 | Maintenance Framework | 2002983 | Burke, Joshua | South | 6. Operational | Emergent | Facility Integrity | -3434 |  |  | -3434.18 | -3434 | 0 | Green |  |  |  | -3434 |  |  | 300000 |  |  | 300000 | Interim | 300000 | 303545 |  | 303545 | No | Green | 2022-07-01 | 2022-10-28 | 2022-10-28 | 2022-09-15 | 2022-10-31 |  |  | -3434.18 | [18 empty] | 5.3.23 JHB - Ready to close. 3.1.23 JHB - Drop accrual to Puffer - work postponed and will be picked up by BTPMEC when resumed. Project ready for closeout. 2.2.23 ML Re-Accrue 3k to Puffer 1.4.23 ML - ReAccrue $3k to Puffer and $17k to Sentinel 12.1.22 JHB - Tmin calcs complete. Accrue $5k to Becht, reaccrue $3k to Puffer and $17k to Sentinel 11.1.22 JHB - Becht conducting t-min calc for 36" bends. Moving $5k to November to cover. 10.3.22 JHB - inspections complete, accrue $5k to Becht, $3k to Puffer, $14k to Sentinel 9.2.22 JHB - Visual externals, baseline UTs, and dent inspection complete. Performing TSV survey in September based on findings, and wrapping up documentation for USCG presentation. Accrue $18k to ACTT, $72k to Sentinel. Moving remaining FC To September. Variance due to urgent execution of project prior to AFE entry. Work temporarily coded to opex then recoded to project once AFE in place. 8/11/22 - Reforecasted to Oct/Q4 based upon schedule for approval of AFE and subsequent reclass thereafter. DC 8.3.22.DLC: Allocated unused funds from 2022 Project Ocean Drawdown 8.1.22 JHB - Systemization/Circuitization complete, inspectors performing visual external and UT inspection through August. Specialty NDE to be bid mid-August to meet target completion of early September. EAC approximately $350k pending cost for specialty NDE. Accrue $38k to ACTT $16k to Sentinel. Need to reclass ~$125k and growing from temporary WO. Forecast assumes 120k in 570 inspector costs for August + 40k in RT, and 125k reclass in September + 20k RT. | 2023-05-03 | Landeros, Melisa |  | South | Pipelines and Terminals | South Texas Gateway |  | Corpus Christi | STXXI - Ingleside |  | -3434 | 0 |  |  | 306979 |  | Aiken, Elaine | Asiedu, Saka |  |  | 1 | 44107 |  | Guest, ProSight | Independent | Aqua | 2022-07-12 | Int - Planned Corr & FI
STXXI - DMPA Assessment and Maintenance Plan | Item | Open | MCAP |  | Maintenance Framework |  | Burke, Joshua | South | 1. Proposed |  | Storm Water Management |  | 375000 |  | 375000 | 375000 | 0 | Green | 375000 |  | 375000 | 0 | [9 empty] | 375000 | 375000 | No | Green | 2023-06-01 |  |  |  | 2023-08-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 50000 | 50000 | 150000 | 125000 |  |  |  |  | 5.3.23 JHB - Proposal received, James Dalton preparing AFE documents. FC moved to reflect anticipated start. 4.3.23 JHB - Meeting with HDR held late March - proposal forthcoming. Phase 1 AFE documents to follow. Adjusting forecast based on delayed meeting/proposal. 3.1.23 JHB - HDR scheduling meeting to review proposals and path forward. Adjusting forecast based on preliminary schedule. Variance due to missed forecast. 2.16.23 JHB - FEB forecast inaccurate - will move dollars to April once month closes. 2.1.23 JHB - Scope development meeting held. Engaging HDR to develop proposal for next engineering steps. | 2023-05-03 |  |  | South | Pipelines and Terminals | South Texas Gateway |  | Corpus Christi | STXXI - Ingleside |  |  | 50000 | 325000 |  |  |  | Bonenberger, Mark |  |  |  | 1 | 45198 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
STXXI Boom Reels | Item | Open | MCAP | STXXI00M2204 | Maintenance Framework | 2023840 | Garcia, Monica | South | 3. Active | Emergent | South | 6730 | 100000 |  | 106729.76 | 211543 | -104813 | Red | 60000 |  | 60000 | 46730 |  |  | 103000 |  |  | 103000 | Phase | 103000 | 100346 | 100000 | 200346 | No | Green | 2022-11-01 | 2022-09-28 | 2022-09-28 | 2023-02-17 | 2023-07-31 |  |  | 3553.79 | 1393.62 | 1595.32 | 187.03 |  |  | 187 | Red | [5 empty] | 40000 | 60000 |  |  |  |  | 3/1/23 MLG: Request for quotes and AFE are in development for the construction/installation of the boom reels. 2/2/23 MLG: This project is a phase project. The Full AFE amount of $103k was to purchase the Boom Reels, which have arrived and are in Ingleside. The next phase of this project is to get engineering for the concrete slab and electrical, as well as the construction/installation of the concrete slab and electrical. Each reel is 19'x8' and there is 2 reels. The area is prone to excessive corrosion as well as the deterioration of the ground. A walk down with Operations and the manufacturer of the reels was performed in late January to determine the placement of the reels. 1-4-23 MLG- the Q1 2023 forecast is for installation of concrete and electrical installation. The reels arrived Dec 28th and are staged at STGT. A walk down will be performed in mid-late January for concrete and electrical installation quotes. 11.9.22 AJ Delivery delayed for the Boom Reels ETA December. 9/12/2022: AJ: moved 90k into this years forecast. Project funded from MCAP drawdown | 2023-03-01 | Landeros, Melisa |  | South | Pipelines and Terminals | South Texas Gateway |  | Corpus Christi | STXXI - Ingleside |  | 6543 | 187 | 100000 |  | 93616 |  | Johnson, AJ | Gee, Ryan |  |  | 1 | 45538 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Marine
STXXI Gateway Dredging | Item | Open | MEXP | STXXI00E2102 | Project Framework | 1888592 | Burke, Joshua | South | 7. Closed | Defined | Marine | -4150 |  |  | -4150 | -4150 | 0 | Green |  |  |  | -4150 |  |  | 39000 |  |  | 39000 | Full | 39000 | 7609 |  | 7609 | No | Green | 2021-10-01 | 2021-09-22 | 2021-09-22 | 2022-01-31 | 2022-03-11 |  |  | -4150 | [18 empty] | 3.1.23 JHB - drop accrual, TBS has complete invoicing. Ready to close. 12.1.22 JHB - Reaccrue $4k to TBS. 10.3.22 JHB - re-accrue $8k to TBS. 9.1.22 JHB - dredging completing in September. Re-accure $8k to TBS. 5.2.22 JHB - No change, still working on DMPA assessment. Re-accrue $11.6k 4.4.22 JHB - Still pending path forward on DMPA. Accrue $11.6k to TBS for completion of permitting/sampling. 3.1.22 JHB - Holding off on TBS dredge plans until HDR evaluation of DMPAs/capacity is complete. 2.25.22 JHB - Permit still in review with USACE. 2.1.22 JHB - NWP 16 review in progress, TCEQ WQC received 1/31. Sediment sampling taken in early January and is being processed. 1.3.22 JHB - Permit documents in review. TCEQ WQC request to be submitted week of 1/3. 12.2.21 JHB - Permit application submitted to USACE. Discussing need to evaluate DMPA prior to use with HDR, designer of the DMPAs. 11.1.21 JHB - Permitting support awarded to T Baker Smith. Requested documents prepared and submitted to Buckeye for review & signature. 10/1/21 JHB - Permitting proposals received from 2 vendors. JHB reviewing and issuing PO week of 10/4. | 2023-04-03 | Landeros, Melisa |  | South | Pipelines and Terminals | South Texas Gateway |  | Corpus Christi | STXXI - Ingleside |  | -4150 | 0 |  |  | 4759 |  | Spari, Markella | Martin, David N. |  |  | 1 | 42146 |  | Clark, David | Independent | Aqua | 2021-09-14 | Marine
STXXI Gateway Triennial Atmospheric Inspection | Item | Candidate | MEXP |  | Maintenance Framework |  | Wirfs, Mike | South | 1. Proposed | Defined | Atmospheric Corrosion |  | 56000 |  | 56000 | 56000 | 0 | Green | 56000 |  | 56000 | 0 | [9 empty] | 56000 | 56000 | No | Green | 2023-10-01 |  |  |  | 2023-03-31 | [17 empty] | 56000 |  |  |  | Project was offered up to R Geib to defer to 2024. Project was forecasted into October 2023 to coincide with CP surveys at Gateway. | 2023-05-01 |  |  | South | Pipelines and Terminals | South Texas Gateway |  | Corpus Christi | STXXI - Ingleside |  |  | 0 |  | 56000 |  |  | Geib, Rob |  |  |  | 1 | 40595 |  | Guest, ProSight | Independent | Aqua | 2021-07-21 | Int - Planned Corr & FI
STXXI Install H2S Detectors at Docks | Item | Open | MCAP |  | Maintenance Framework |  | Garcia, Monica | South | 1. Proposed |  | Instrumentation & Controls |  | 15000 |  | 15000 | 15000 | 0 | Green | 15000 |  | 15000 | 0 | [9 empty] | 15000 | 15000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 15000 | [6 empty] | 3/1/23 MLG: walk down tentatively scheduled for mid-March. 2/2/23 MLG: Scope development tentatively scheduled for mid-to late February. | 2023-03-01 |  |  | South | Pipelines and Terminals | South Texas Gateway |  | Corpus Christi | STXXI - Ingleside |  |  | 0 | 15000 |  |  |  | Forsey, Frank |  |  |  | 1 | 45537 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
STXXI Stormwater Stabilization | Item | Open | MCAP | STXXI00M2203 | Maintenance Framework | 2022467 | Burke, Joshua | South | 7. Closed | Defined | Storm Water Management | -5999 |  |  | -5999.12 | -5999 | 0 | Green |  |  |  | -5999 |  |  | 60000 |  |  | 60000 | Full | 60000 | 42181 |  | 42181 | No | Green | 2022-11-01 | 2022-09-12 | 2022-09-12 | 2022-10-31 | 2022-12-31 |  |  | -5999.12 | [18 empty] | 2.2.23 ML Ready to Close 1.4.23 Ml - Accrue 6.5k SR Trident 12.1.22 JHB - SRT mobilized 11/21 & began grading work. Target completion week of 11/28. Accrue $35k to SR Trident. 11.1.22 JHB - 2nd quote received, awarding work and scheduling for November. 10.11.22 JHB - moved forecast from October to November - getting 2nd bid before proceeding with execution. 10.3.22 JHB - AFE approved, entering SSJ for ADK to perform BMP installations/regrading. 9.1.22 JHB - AFE review scheduled for 9/1. $50k moved to October based on current schedule. $10k to December based on trial period of seeding in October followed by additional seeding in December once efficacy confirmed. 8.2.22 JHB - moved funds to September. Waiting on clarification from proposed vendor on cost for regrading before finalizing AFE. 7.12.22 JHB - moved funds to August. Proposal provided for BMP improvements and seeding, pending AFE generation and Operations/Maintenance review before proceeding. 5.2.22 JHB - no update. 4.4.22 JHB - Waiting on significant rain event to determine which BMPs implemented in Q4 2021 were effective and define remaining scope. 2.1.22 JHB - Working to define project scope with target AFE submission of 3/18. Stabilize the site with vegetation and rock to fix the sedimentation problem, what is in place today is temporary solution and fails reasonably quickly | 2023-04-03 | Landeros, Melisa |  | South | Pipelines and Terminals | South Texas Gateway |  | Corpus Christi | STXXI - Ingleside |  | -5999 | 0 |  |  | 48181 |  | Bonenberger, Mark | Johnson, AJ |  |  | 1 | 41929 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Other Programs
Tampa North - North Dolphin - Mooring bit replacement | Item | Open | MCAP |  | Project Framework |  | Campbell, William | South | 1. Proposed |  | Marine |  | 80000 |  | 80000 | 80000 | 0 | Green | 80000 |  | 80000 | 0 | [9 empty] | 80000 | 80000 | No | Green | 2023-06-01 |  |  |  | 2023-05-31 | [13 empty] | 40000 | 40000 | [10 empty] | South | Pipelines and Terminals | Operating Infrastructure |  | Florida | BETQT - BET TAMPA NORTH TERMINAL |  |  | 40000 | 40000 |  |  |  | Spari, Markella |  |  |  | 1 | 41947 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Marine
Tampa North - South Dolphin - Mooring bit replacement | Item | Open | MCAP |  | Project Framework |  | Campbell, William | South | 1. Proposed |  | Marine |  | 80000 |  | 80000 | 80000 | 0 | Green | 80000 |  | 80000 | 0 | [9 empty] | 80000 | 80000 | No | Green | 2023-06-01 |  |  |  | 2023-05-31 | [13 empty] | 40000 | 40000 | [10 empty] | South | Pipelines and Terminals | Operating Infrastructure |  | Florida | BETQT - BET TAMPA NORTH TERMINAL |  |  | 40000 | 40000 |  |  |  | Spari, Markella |  |  |  | 1 | 41948 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Marine
TAMPA NORTH CAMERA UPGRADE | Item | Open | MCAP | BETQT00M2203 | Maintenance Framework | 2002652 | Corman, Chris | South | 7. Closed | Defined | Security & Cameras | 118 |  |  | 118.14 | 118 | 0 | Green |  |  |  | 118 |  |  | 79000 |  |  | 79000 | Full | 79000 | 64588 |  | 64588 | No | Green | 2022-07-01 | 2022-07-11 | 2022-07-11 | 2022-10-30 | 2022-10-30 |  |  | 118.14 | [18 empty] | 12/5/22- Project complete and ready to close. 11/1/2022- Adjustments are still needed at the terminal. Work expected to be completed in November. Reaccrue $43K to Convergint and $3k to Herc Rentals. 10/3/2022 - Accrue $43k to Convergint. Accrue $10k to Knight, $3k to Herc Rentals. Hurricane Ian delayed delivery time. 8/23/2022- Accrue $20k to Convergint for camera material. Work to be completed in September because we had to wait for additional material to arrive. 8/2/22- Cameras received at Convergint, install to begin end of Aug/beginning of Sept | 2022-12-05 | Landeros, Melisa |  | South | Pipelines and Terminals | Operating Infrastructure |  | Florida | BETQT - BET TAMPA NORTH TERMINAL |  | 118 | 0 |  |  | 64469 |  | Clark, Chris | Asiedu, Saka |  |  | 1 | 37867 |  | Guest, ProSight | Independent | Aqua | 2020-08-13 | Other Programs
Tampa North Concrete Replacement 2022 | Item | Open | MCAP | BETQT00M2205 | Maintenance Framework | 2051077 | Campbell, William | South | 7. Closed | Drawdown | South | 155541 |  |  | 155540.82 | 155541 | 0 | Green |  |  |  | 155541 |  |  | 287000 |  |  | 287000 | Full | 287000 | 300541 |  | 300541 | No | Green | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2022-12-31 | 2023-02-01 |  |  | 145006.9 | 10080.31 | 453.61 | [16 empty] | 3/1/23-Project complete, invoicing complete, close project 2/1/23-Project complete, invoicing for security and electrical outstanding 1/4/23- Accrue $145k to Attaway. Project will complete in Jan 2023 | 2023-02-23 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Operating Infrastructure |  | Florida | BETQT - BET TAMPA NORTH TERMINAL |  | 155541 | 0 |  |  | 145000 |  | Johnson, AJ | Burke, Kevin |  |  | 1 | 46267 |  | Guest, ProSight | Independent | Aqua | 2022-11-29 | Other Programs
TAMPA NORTH TERMINAL PCW TANK CLEANING | Item | Candidate | MEXP |  | Exempt |  | Bryant, Ben | South | 4. On-Hold | Defined | South |  | 1 |  | 1 | 1 | 0 | Green |  |  |  | 1 | [9 empty] | 1 | 1 | No | Green | 2023-12-01 |  |  |  | 2023-12-31 | [19 empty] | 1 |  | 4/1/22 on Hold. 3/1/22 On Hold. 2/1/22 On Hold. 1/3/22 Project postponed by facility integrity. 104/21 Facility Integrity is working to verify vendors who can accomplish this project. 5/1/21 Project has been moved to third quarter to better understand scope for this project. 4/1/21 Initial Meeting will take place this month to Evaluate how to clean this tank with stakeholders. | 2022-03-31 |  |  | South | Pipelines and Terminals | Station/Terminal |  | Florida | BETQT - BET TAMPA NORTH TERMINAL |  |  | 0 |  | 1 |  |  | Johnson, AJ |  |  |  | 1 | 37889 |  | Guest, ProSight | Independent | Aqua | 2020-08-13 | Other Programs
Tampa South Generator Repairs | Item | Open | MEXP | BETTK00E2302 | Maintenance Framework | 2095103 | Corman, Chris | South | 3. Active | Drawdown | South |  | 28000 |  | 28000 | 28000 | 0 | Green |  | 28000 | 28000 | 0 |  |  | 28000 |  |  | 28000 | Full | 28000 |  | 28000 | 28000 | No | Green | 2023-06-01 | 2023-03-15 | 2023-03-15 | 2023-06-01 | 2023-06-01 | [13 empty] | 28000 | [9 empty] | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | Florida | BETTK - BET TAMPA |  |  | 28000 |  |  |  |  | Johnson, AJ | Miller, Michael A. | N/A |  | 1 | 46784 |  | Johnson, AJ | JDE Child | Burnt Orange | 2023-03-14
Tampa South Terminal (BETTK) Tank 50 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | BETTK00E2301 | Maintenance Framework | 2085511 | Matthews, Clayton | South | 3. Active | Defined | Tanks |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 |  |  | 11000 |  |  | 11000 | Phase | 11000 |  | 10000 | 10000 | No | Green | 2023-05-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-12-31 | [6 empty] | 10000 | 10000 | -10000 | Red |  | Forecasting | 10000 | [10 empty] | Landeros, Melisa |  | South | Pipelines and Terminals | Tank Integrity |  | Florida | BETTK - BET TAMPA |  |  | 10000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44887 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Tampa South Terminal (BETTK) Tank Maintenance Painting | Item | Open | MEXP | BETTK00E2303 | Maintenance Framework | 2095803 | Bryant, Ben | South | 3. Active | Drawdown | Tanks |  | 40000 |  | 40000 | 40000 | 0 | Green |  |  |  | 40000 |  |  | 40000 |  |  | 40000 | Full | 40000 |  | 40000 | 40000 | No | Green | 2023-05-01 | 2023-03-23 | 2023-03-23 | 2023-05-31 | 2023-05-31 | [12 empty] | 40000 | [10 empty] | Landeros, Melisa |  | South | Pipelines and Terminals | Tank Integrity |  | Florida | BETTK - BET TAMPA |  |  | 40000 |  |  |  |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 46819 |  | Stine, Carlton | JDE Child | Burnt Orange | 2023-03-20
Tampa South VCI Inhibitor Injection for Tank 34, 35, 36 Double Bottoms | Item | Open | MCAP | BETTK00M2205 | Maintenance Framework | 2024023 | Wirfs, Mike | South | 6. Operational | Defined | Atmospheric Corrosion | 11352 |  | 0 | 11352.29 | 10977 | 375 | Yellow |  |  |  | 11352 |  |  | 71000 |  |  | 71000 | Full | 71000 | 75206 | 0 | 75206 | No | Green | 2022-12-01 | 2022-09-30 | 2022-09-30 | 2022-12-31 | 2022-12-31 |  |  | 2426.41 | 210.58 | 8340 | 375.3 |  |  | 375 | Red | [10 empty] | 0 | 5-1-2023 - Project complete, WO closed. 5/1/2023 - Re-accrue $23K to NTIC 4/1/2023 - Re-accrue $23K to NTIC 3/1/2023 ER probes to be installed week of March 6, 2023, Accrual $23K to NTIC 2/1/2023 - Project complete, invoicing approved no posting of actuals. Accrual $23k NTIC. 1/1/2023 - Project Complete. Accrual $23,000 for NTIC. Waiting on final invoicing to close project. 2/1/2022 - Installation rescheduled due to hurricane events. Work scheduled for the week of 12/6/2022. Estimated to take 1 week to complete. 10/31/22 - Installation scheduled for late November September 2022 - AFE written and approved, forecasted $71K in December. August 2021 - Project on hold | 2023-05-05 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | Florida | BETTK - BET TAMPA |  | 10977 | 375 |  |  | 63853 |  | Geib, Rob | Johnson, AJ | N/A |  | 1 | 31486 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Int - Planned Corr & FI
Texas Hub (BTXHF) - Tank 115-01_ OOS Insp & Refurb | Item | Open | MCAP | BTXHF00M2203 | Maintenance Framework | 1937300 | Matthews, Clayton | South | 6. Operational | Defined | Tanks | 44407 |  |  | 44406.7 | 42060 | 2347 | Yellow |  |  |  | 44407 |  |  | 336000 |  |  | 336000 | Phase | 336000 | 422671 |  | 422671 | No | Green | 2022-05-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-10-01 |  |  | 31034.91 | 10550.24 | 474.55 | 2347 |  |  | 2347 | Red | [11 empty] | 5.2.23 ML Re-Accrue 11k WM, 2.3k EquipmentShare 4.5.23 ML Re-Accrue 11k WM 3.3.23 ML Re-Accrue 2.3k EquipmentShare, 11k WM 2.2.23 ML Accrue 2.3k Equip, 78k Tarsco, 11k WM 1/11/23 CAM 30K forecast added to January for Tarsco in service cable installation on 115-1/115-2 1/4/23 CAM Re accrue all prior. Accrue 3,850 Equipment share (rentals) 12/2/22 CAM Accrue 4700 Adlet, Re accrue 48870 Tarsco, Accrue 11k WM 11/2/22 CAM Accrue 15k Adler, re accrue 15k ATP, 4k DJA, re accrue 35300 Hydrochem, Accrue 10.5k knight, accrue 3600 PBI, accrue 5k saybolt, accrue 10k Vapor point 10/2/22 CAM Work complete. Accrue 50k Tarsco, accrue 1500 PBI, accrue 35k hydrochem, accrue 15 ATP. 12k WM 9/2/22 CAM Accrue 20K ATP, Accrue 135 Hydrochem, Accrue 10K DJA. Major scope reduction based on bottom inspection. Forecast adjusted, waiting on unit pricing verification from Tarsco. 8.18.22 CAM Cleaning anticipated for completion on 8.20.22 8.8.22 Cleaning started .6.3.22 No adjustments to project forecast / no accruals to project 4.4.22 Execution based of 50-03 similar service confirmation 3/5/2021 - CAM- AFE was presented to local leadership on 1/7/2021. Forecast amounts were shifted to Q2 start. | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 42060 | 2347 |  |  | 378264 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 37895 |  | Guest, ProSight | Independent | Aqua | 2020-08-13 | Int - Tanks
Texas Hub (BTXHF) - Tank 50-02_ OOS Insp & Refurb | Item | Open | MCAP | BTXHF00M2201 | Maintenance Framework | 1937298 | Matthews, Clayton | South | 7. Closed | Defined | Tanks | 520 |  | 31000 | 519.7 |  | 520 | Red |  |  |  | 520 |  |  | 373000 |  |  | 373000 | Phase | 373000 | 342634 | 31000 | 373634 | No | Green | 2022-02-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-07-31 | [5 empty] | 519.7 |  |  | 520 | Red | [10 empty] | 31000 | 10.10.22 ML Rdy to Close 9/2/22 CAM No changes to project 7.1.22 CAM Project closure underway. Accrue 1500 Adler, 1000 Knight, 1500 Ohmstede 5/4/22 Remaining Contingency updated. All field work complete. Additional internal coating work added. 4.4.22 Scope Reduction from full bottom replacement to bottom repair 3/1/22 CAM Inspection complete. major scope reduction from El Segundo replacement to bottom patching. Forecast updated. Accrue 190k Hydrochem, 12k DJA, 10k Adler, 7500 Waste management. 2/2/22 - Scheduling delays caused the variance in January. CM | 2022-10-10 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  |  | 520 |  |  | 342114 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 37899 |  | Guest, ProSight | Independent | Aqua | 2020-08-13 | Int - Tanks
Texas Hub (BTXHF) 250 Series Tank Overflow Patching | Item | Open | MCAP | BTXHF00M2211 | Maintenance Framework | 2004171 | Matthews, Clayton | South | 7. Closed | Drawdown | Tanks | 321 |  |  | 321.13 | 321 | 0 | Green |  |  |  | 321 |  |  | 199000 |  | 37430 | 236430 | Supplemental | 236430 | 220393 |  | 220393 | No | Green | 2022-07-01 | 2022-07-27 | 2022-07-27 | 2022-12-31 | 2022-09-30 |  |  | 321.13 | [18 empty] | 5.2.23 ML Ready to Close 1/4/23 CAM Re accrue all prior. 12/2/22 CAM Accrue 30K Hydrochem, Accrue 4200 PBI 11/2/22 CAM Accrue 22k ATP, 170k Hydrochem, 8k Ohmstede 10/3/22 CAM Field work completing 10/14. Accrue 15k ATP, Accrue 55k Hydrochem (additional 50k re acrrue) 9/2/22 CAM August underspend. Contractor mobilization delay. New mob date 9/7. Forecast shifted to September/October. Accrue 50k Hydrochem for material fabrication. 8.18.22 CAM Fabrication continuing. PO for installation of patches issued 8.17.22 8.1.22 CAM Accrue 5k ATP, Accrue 25k Hydrochem/Clean Harbors. Late AFE approval. Forecast updated. 6/21/22 CAM Forge bonding approved on 6/17. ETC has been validated, AFE to be submitted ASAP. | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 321 | 0 |  |  | 220072 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 43831 |  | Stine, Carlton | Independent | Aqua | 2022-05-24 | Int - Tanks
Texas Hub (BTXHF) Tank 5003 - OOS Corr + Seal Insp & Refurb | Item | Open | MCAP | BTXHF00M2202 | Exempt | 1937299 | Matthews, Clayton | South | 6. Operational | Defined | Tanks | 2483 |  |  | 2483.43 | 2719 | -236 | Yellow |  |  |  | 2483 |  |  | 373000 |  |  | 373000 | Phase | 373000 | 523275 |  | 523275 | No | Green | 2022-04-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-12-31 |  |  | 0 | 719.15 | 2000 | -235.72 |  |  | -236 | Red | [11 empty] | 5.2.23 ML Re-Accrue 16k PBI, 4.5k to Saybolt 4.5.23 ML Re-Accrue 16k PBI, 4.5k to Saybolt, Accrue 2k WM 3.3.23 ML Re-Accrue 16k PBI, 4.5k to Saybolt 2.2.23 ML Re-Accrue 16k PBI, 4.5k to Saybolt, 19k WM 1/4/23 CAM Re accrue all prior 12/2/22 CAM Re accrue 16k PBI, Re accrue 4535 Saybolt, Accrue 19k WM 11/2/22 CAM Accrue 3k ohmstede, 16k PBI, 4500 saybolt, 26k WM 10/3/22 CAM Re accrue 15k Hydrochem, re accrue 4500 Saybolt, accrue 16 PBI, accrue 3000 Ohmstede, 9k WM 9/2/22 CAM Accrue 2k ATP, Accrue 15k Hydrochem, Accrue 100k Knight, Accrue 4.5k Saybolt 8.6.22 CAM Repair work completed 8.1.22 CAM Accrue 6000 ATP, Accrue 55k Tarsco, Accrue 12k WM, 10k Becht, 140k Hydrochem, 18k Knight Industrial. Re Accrue 18k Knight Ind, Re Accrue 11k DJA, Re Accrue 1140k Hydrochem. Coating work starting 8.2.22 7.1.22 CAM Accrue 18000 American tank, 11,000 DJA, 140,000 Hydrochem, 18000 Knight, 3000 PBI 6/21/22 CAM Waiting for contractor mob due to safety restriction. 6.3.22 CM 55k Change Order for Cleaning Scope / Thermal Oxydizer additional days. Accruals to 130k Hydrochem, 25k ATP 5/4/22 CAM Sim Service not approved. Hydrochem has began tank cleaning. 3.11.22.DLC: Reduced forecast presuming similar service may work out | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXHF - Buckeye Texas Hub |  | 2719 | -236 |  |  | 520791 |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 30424 |  | Guest, ProSight | Independent | Aqua | 2018-08-07 | Int - Tanks
Texas Processing (BTXPP) - Tank 1002 IFR Insp & Refurb | Item | Open | MCAP | BTXPP00M2207 | Maintenance Framework | 1980749 | Matthews, Clayton | South | 6. Operational | Defined | Tanks | 1067 |  |  | 1066.78 | 97 | 970 | Red |  |  |  | 1067 |  |  | 553000 |  |  | 553000 | Full | 553000 | 558837 |  | 558837 | No | Green | 2022-05-01 | 2022-05-27 | 2022-05-27 | 2022-07-29 | 2022-09-30 |  |  | 1404.81 | -7405.19 | 6097 | 970.16 |  |  | 970 | Red | [11 empty] | 5.2.23 ML Ready to Close 4.5.23 ML Re-Accrue 177k WM 3.3.23 CAM accrue 171K WM 2.2.23 ML- Re-Accrue 15k Adler, 165k WM 1/4/23 CAM Re accrue all 12/2/22 CAM Re Accrue 15K Adler, Accrue 20K Tarsco, Re accrue 165K WM 11/8/22 CAM Final invoice from Tarsco in internal mods. PO requested. 11/2/22 CAM re accrue 15000 Adler, re accrue 75000 Hydrochem, re accrue 130k WM 102/22 CAM Accrue 15000 Adler, re accrue 75000 Hydrochem, re accrue 130k WM 9/2/22 CAM Accrue 195k Hydrochem, Re-Accrue 130k WM, Re-Accrue 7.5k Adler Forecast adjustment unknown. EAC driven by engineering and program decision. 8.18.22 CAM Engineering evaluation underway 8.2.22 CAM Accrue 15k ATP., Re Accrue 7500 Adler, Accrue 130k WM, Re Accrue 180k Hydrochem, Engineering evaluation / RCA. 7.1.22 CAM Failure cause evaluation underway. Accrue 15000 American tank, re accrue 7500 adler, re accrue 180k Hydrochem 6/21/22 CAM DirectTank inspection complete. Regional meeting to discuss path forward to be scheduled. 6.3.22 CM Tank Cleaning completed on 6.1.22 Cleaner Mob on 6/9 instead of end of Month Accrual 180k Hydrochem, 40k Three L, 7.5k Adler ,15k ATP | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 97 | 970 |  |  | 557770 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 43379 |  | Clark, David | Independent | Aqua | 2022-04-08 | Int - Tanks
Texas Processing (BTXPP) Tank 1005 IFR Cleaning and Seal Replacement | Item | Open | MCAP | BTXPP00M2215 | Maintenance Framework | 2002884 | Matthews, Clayton | South | 6. Operational | Drawdown | Tanks | 26114 |  |  | 26113.74 | 25114 | 1000 | Yellow |  |  |  | 26114 |  |  | 149000 |  | 75845 | 224845 | Supplemental | 224845 | 224399 |  | 224399 | No | Green | 2022-08-01 | 2022-08-11 | 2022-08-11 | 2022-09-15 | 2022-11-30 |  |  | 10713.69 | 13554.92 | 845.13 | 1000 |  |  | 1000 | Red | [11 empty] | 5/2/23 CAM Project ready to close out 4.5.23 ML Re-Accrue 20K WM, 8k EISCO, Accrue Adler 1K 4.5.23 ML Re-Accrue 20K WM, 8k EISCO 3.3.23 CAM Accrue 20K WM, 8212 Eisco 2.2.23 ML - Re-Accrue 9.5k Select Safety, 20k WM 1/4/23 CAM Re accrue all. Accrue 45k PBI for additional work that was added. Supplemental requirement verified with program. 12/2/22 CAM Accrue 15K Eisco, Re Accrue 4K PBI, Re Accrue 77K Tarsco, Re Accrue 20K WM, Accrue 2k Select Safety 11/2/22 Accrue 5k Adler, 25k PBI, Accrue Re accrue 2k select safety, reaccrue 77k tarsco, reacrue 20k WM. Additional work has been added and forecasted. 10/3/22 CAM Re Accrue 2500 Adler, Re accrue 4k PBI, Re accrue 2k Select Safety, Re accrue 77k Tarsco, Accrue 20k WM 9/2/22 Accrue 77k Tarsco, Acrrue 2k Select Safety, Accrue 10k ATP, Accrue 4k PBI, Accrue 5.5K WM, Accrue 2.5k Adler 8.11.22 CAM Repair work complete 8.9.22 CAM Repair start. Secondary seal replacement, column seals, vent inspections 8.6.22 CAM Cleaning complete 8.3.22 CAM Cleaning Start (PBI) 8.1.22 CAM AFE Submitted. Project planning underway. Cleaning start ASAP. | 2023-05-02 | Landeros, Melisa |  | South | Pipelines and Terminals | Integrity |  | Corpus Christi | BTXPP - Buckeye Texas Processing |  | 25114 | 1000 |  |  | 198285 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44327 |  | Stine, Carlton | Independent | Aqua | 2022-07-29 | Int - Tanks
VM930SH 2021 VMH Facility to Shell Jct ILI | Item | Open | MEXP | VM930SHE2201 | Maintenance Framework | 2022611 | Corman, Chris | South | 6. Operational | Defined | Assessments | 91012 |  |  | 91011.78 | 92000 | -988 | Yellow |  |  |  | 91012 |  |  | 92000 |  |  | 92000 | Full | 92000 | 91012 |  | 91012 | No | Green | 2023-04-01 | 2022-09-14 | 2022-09-14 | 2022-12-05 | 2023-02-28 | [5 empty] | 91011.78 | 92000 | 92000 | -988 | Yellow | [11 empty] | 5/1/23 - Accrue $15K to Eagle Energy, $50K to Rosen,$26K to CCI, 3/2/2023 ILI was pushed to April 2023 1/3/23- ILI was pushed to Feb 2023 12/5/2022- ILI was pushed to Jan 2023 11/1/2022 - ILI was moved to December. Awaiting on final approvals from Shell. 10/3/2022 - Shell is potentially moving ILI run to November. 8/2/22- No product available until late Q4 to run ILI 8/31/2021 - Line will not have product availability until 2022 7/28/2021 - Commissioning expected in October 2021 6/2/2021 - Awaiting shell plant commissioning. Potentially will be in 2022. 4/1/2021 - Project to be transferred to D. Mitchell. 3/2/2021 - Pipeline will most likely not be commissioned this year. Waiting on the construction of a Shell cracker project to be completed in Monaca, PA which feeds this line. 1/14/2021 - Pipeline will not be commissioned until October 2021. In consequence, this forecast has been updated to reflect execution in November 2021. | 2023-05-04 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Pipeline Integrity |  | Liberty | VM930SH - VMH JUNCTION TO SHELL 6 |  |  | 91012 |  |  |  |  | Bartal, Nick | Asiedu, Saka |  |  | 1 | 38236 |  | Schultz, Amy | Independent | Aqua | 2020-08-17 | Int - Assessments
Wilmington - Lubricity Injector replacement | Item | Open | MEXP | BETQM00E2302 | Maintenance Framework | 2095109 | Corman, Chris | South | 3. Active | Drawdown | Truck Racks | 7752 | 20000 |  | 27751.99 | 20000 | 7752 | Red |  |  |  | 27752 |  |  | 20000 |  |  | 20000 | Full | 20000 | 7752 | 20000 | 27752 | No | Green | 2023-04-01 | 2023-03-15 | 2023-03-15 | 2023-06-01 | 2023-06-01 | [5 empty] | 7751.99 |  |  | 7752 | Red |  |  | 20000 | [10 empty] | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | North Carolina | BETQM - BET WILMINGTON TERMINAL |  |  | 27752 |  |  |  |  | Younce, Michael | Smith, Mark D. | N/A |  | 1 | 46771 |  | Johnson, AJ | JDE Child | Burnt Orange | 2023-03-14
Wilmington - Ship Berth - Chicksan Cable Replacement | Item | Open | MCAP |  | Project Framework |  | Magouirk, Josh | South | 1. Proposed |  | Marine |  | 67375 |  | 67375 | 67375 | 0 | Green | 67375 |  | 67375 | 0 | [9 empty] | 67375 | 67375 | No | Green | 2023-08-01 |  |  |  | 2023-08-31 | [15 empty] | 67375 | [9 empty] | South | Pipelines and Terminals | Operating Infrastructure |  | Southeast Terminals | BETQM - BET WILMINGTON TERMINAL |  |  | 0 | 67375 |  |  |  | Spari, Markella |  |  |  | 1 | 41950 |  | Administrator, System | Independent | Aqua | 2021-08-23 | Marine
Wilmington Terminal (BETQM) Tank 8902 - Seal Insp & Refurb | Item | Open | MEXP | BETQM00E2201 | Maintenance Framework | 1936919 | Bryant, Ben | South | 7. Closed | Defined | Tanks | -15713 |  |  | -15713.22 | 20287 | -36000 | Red |  |  |  | -15713 |  |  | 166000 | 331000 |  | 166000 | Phase | 497000 | 29287 |  | 29287 | No | Green | 2022-07-01 | 2021-12-30 | 2021-12-30 | 2022-12-31 | 2022-12-31 |  |  | 472.47 | 17916.19 | 1898.12 | -36000 |  |  | -36000 | Red | [11 empty] | 4/4/23 - Remove accrual for WM. Project complete. 3/2/2023 - Accrue $36K to Waste Management. 2/1/23 Re-Accrue 7K to W9Y. and 36K to Waste Management. 1/2/23 Please accrue 7K to W9Y and 38K to Waste Management. All other costs have been reclassed to BETQM00M2201. MC 12/1/22 Tank floor has been coated by Barr None. Tank has been buttoned up. Re-Accrue 113K to FHG, Accrue 41 K to Barr None, 20K to ATP. 11/1/22 Tank has been repaired. Cables suspension has been added. Tank will be post inspected and strapped. A coating will be added to the floor of the tank. ReAccrue $113k to Streamtech, Accrue $113k to FHG, $30k American Tank Partners 10/10/22 - Additional costs added for repairs Phase 2. DC 10/1/22 Re Accrue 113K to Streamtech Industries. 9/122 Accrue 85K to Streamtech Industries. 8/1/22 Accrue 70K to Streamtech Industries. 7/1/22 Tank will come out of service this month for seal inspection. 4/1/22 Tank Integrity is reviewing the scope for this tank. Tank inspection may be altered. | 2023-04-04 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Tank Integrity |  | Southeast Terminals | BETQM - BET WILMINGTON TERMINAL |  | 20287 | -36000 |  |  | 45000 |  | Stine, Carlton | Jones, Kevin |  |  | 1 | 41351 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Wilmington Terminal Tank 8902 OOS MCAP 2022 PH 2 | Item | Open | MCAP | BETQM00M2201 | Maintenance Framework | 2051324 | Bryant, Ben | South | 7. Closed | Drawdown | Tanks | 17406 |  |  | 17406.08 | 17406 | 0 | Green |  |  |  | 17406 |  |  | 533000 |  |  | 533000 | Full | 533000 | 455736 |  | 455736 | No | Green | 2022-12-01 | 2022-12-03 | 2022-12-03 | 2022-12-31 | 2022-12-30 |  |  | 16656.54 | 749.54 | [17 empty] | 5/1/23 Ready to close. 12/9/22-CES-This project represents a reclass from BETQM00E2201 to this project . | 2023-05-01 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Integrity |  | North Carolina | BETQM - BET WILMINGTON TERMINAL |  | 17406 | 0 |  |  | 438330 |  | Stine, Carlton | Shook, Mark B. |  |  | 1 | 46252 |  | Guest, ProSight | Independent | Aqua | 2022-11-21 | Int - Tanks
Wilmington Truck Rack Solenoid Repairs | Item | Open | MEXP | BETQM00E2203 | Maintenance Framework | 2044299 | Leal, Trey (Tony) | South | 7. Closed | Defined | Truck Racks | 325 |  |  | 325.13 | 325 | 0 | Green |  |  |  | 325 |  |  | 22000 |  |  | 22000 | Full | 22000 | 18820 |  | 18820 | No | Green | 2022-12-01 | 2022-11-07 | 2022-11-07 | 2022-12-31 | 2022-12-31 |  |  | 0 | 0 | 325.13 | [16 empty] | 4/3/23 - Costs have hit. Project ready to close 1/29/2023 - Re-accrue $7k to W9Y 1/3/23- Accrue $7k to W9Y 12/5/22- Solenoids have arrived, coordinating with contractor to try to complete install in December. 11/1/2022 - AFE routed. Solenoids should arrive by December. Reducing forecast from 45k to 22k 10/3/2022 - Received second quote, AFE to be submitted this week, estimating 45k to complete with contractor in December 9/1/2022 TEL - Working with local ops and contractor to line out costs. Targeting AFE 9/8/2022 | 2023-04-03 | Lockwood, Jo Dawn |  | South | Pipelines and Terminals | Station/Terminal |  | North Carolina | BETQM - BET WILMINGTON TERMINAL |  | 325 | 0 |  |  | 18495 |  | Younce, Michael | Asiedu, Saka |  |  | 1 | 45367 |  | Clark, David | Independent | Aqua | 2022-08-26 | Other Programs
Wilmington Verify OOS 6 Oil line is drained and purged | Item | Open | MEXP |  | Maintenance Framework |  | Magouirk, Josh | South | 1. Proposed |  | Facility Integrity |  | 15000 |  | 15000 | 15000 | 0 | Green | 15000 |  | 15000 | 0 | [9 empty] | 15000 | 15000 | No | Green | 2023-06-01 |  |  |  | 2023-04-30 | [13 empty] | 15000 | [11 empty] | South | Pipelines and Terminals | Station/Terminal |  | North Carolina | BETQM - BET WILMINGTON TERMINAL |  |  | 15000 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 45641 |  | Administrator, System | Independent | Aqua | 2022-08-30 | Int - Planned Corr & FI
150-06 RMU Sat. antenna Upgrade | Item | Candidate | MCAP |  | Exempt |  | Logan, Rob | West | 2. Pending AFE |  | Cathodic Protection |  | 12000 |  | 12000 | 12000 | 0 | Green | 12000 |  | 12000 | 0 | [9 empty] | 12000 | 12000 | No | Green | 2023-08-01 |  |  |  | 2023-08-31 | [15 empty] | 12000 | [5 empty] | 5/1/2023 Received quote Pending AFE 4/3/2023 Awaiting quote foe AFE 3/2/2023Pending AFE 2/2/2023 Pending AFE | 2023-05-01 |  |  | West | Pipelines and Terminals | Integrity |  | Michiana | JE150EK - ELKHART JCT TO ELKHART |  |  | 0 | 12000 |  |  |  | Geib, Rob |  |  |  | 1 | 45688 |  | Logan, Rob | Independent | Aqua | 2022-08-29 | Int - Planned Corr & FI
155/156L Grand Calument North Valve Vault Inspection | Item | Open | MEXP | KG155HDE2201 | Maintenance Framework | 2011876 | Logan, Rob | West | 7. Closed | Drawdown | Atmospheric Corrosion | -9027 |  |  | -9026.59 | -9027 | 0 | Green |  |  |  | -9027 |  |  | 19000 |  |  | 19000 | Full | 19000 | -4130 |  | -4130 | No | Green | 2022-10-01 | 2022-08-09 | 2022-08-09 | 2022-10-28 | 2022-10-28 |  |  | -9026.59 | [18 empty] | 1/4/2023 - project was under budget. savings.11/1/2022 - work complete. 10/4/2022 Contacted Andy Schwartz from Midwestern on 10/3/2022 about scheduling he stated he will contact me on 10/4/2022 with firm date for work 9/1/2022 - PO Issued Work scheduled for September | 2023-01-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Michiana | KG155HD - LAKE GEORGE TO HARTSDALE |  | -9027 | 0 |  |  | 4896 |  | Geib, Rob | Gardner, Travis W. | N/A |  | 1 | 44454 |  | Gardner, Travis | JDE Child | Burnt Orange | 2022-08-08 | Other Programs
160L MP 77.59 B- Sleeve Install at F-402.37 | Item | Open | MCAP | AS160HTM2201 | Exempt | 2036061 | Gabriel, Jeff | West | 6. Operational | Emergent | Pipeline Digs | 4787 |  |  | 4786.69 | 4787 | 0 | Green |  |  |  | 4787 |  |  | 39000 |  |  | 39000 | Full | 39000 | 27691 |  | 27691 | No | Green | 2022-11-01 | 2022-11-29 | 2022-11-29 | 2022-11-30 | 2022-12-31 |  |  | 4580.56 | 206.13 | [17 empty] | 1/3/2023- Work Complete all invoices have hit. 12/2/2022- Work Complete need to accrue 22,018 Vance | 2023-01-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Central-Illinois | AS160HT - AUBURN TO HARRISTOWN JCT |  | 4787 | 0 |  |  | 22904 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46242 |  | Gardner, Travis | Independent | Aqua | 2022-11-17 | Int- Planned Digs
180 line Mag installation | Item | Candidate | MCAP |  | Exempt |  | Logan, Rob | West | 2. Pending AFE |  | Cathodic Protection |  | 20000 |  | 20000 | 20000 | 0 | Green | 20000 |  | 20000 | 0 | [9 empty] | 20000 | 20000 | No | Green | 2023-06-01 |  |  |  | 2023-06-30 | [13 empty] | 20000 | [7 empty] | 05/01/2023 Requesting quote from National Pipeline 04/04/2023 Pending AFE 03/02/2023 Pending AFE | 2023-05-01 |  |  | West | Pipelines and Terminals | Integrity |  | St. Louis | WO180XX - WOOD RIVER TO MO S/L |  |  | 20000 |  |  |  |  | Geib, Rob |  |  |  | 1 | 45436 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
2019 L531 MEXP Flips | Item | Open | MEXP | UT534YTE1903 | Exempt | 1619346 | Burns, Richard | West | 7. Closed | Drawdown | Pipeline Digs | 3284 |  |  | 3283.92 | 3284 | 0 | Green |  |  |  | 3284 |  |  | 280000 |  |  | 280000 | Full | 280000 | 312024 |  | 312024 | No | Green | 2020-09-01 | 2019-08-01 | 2019-08-01 | 2019-12-31 | 2019-09-30 |  |  |  |  | 3283.92 | [16 empty] | 9/4/19 - project created to flip costs from capital project to here. | 2019-09-04 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Pipeline Integrity |  | Toledo | UT534YT - TOLEDO STA TO WEST TOLEDO TERM |  | 3284 | 0 |  |  |  |  | Bartal, Nick | Bassani, Joel D. | N/A |  | 1 | 33864 |  | Bassani, Joel | JDE Child | Burnt Orange | 2019-08-01
2022 - DA999A2 - ILI | Item | Open | MEXP | DA999A2E2201 | Exempt | 1945663 | Bost, Jason | West | 6. Operational | Defined | Assessments | 1690 |  |  | 1689.8 | 1690 | 0 | Green |  |  |  | 1690 |  |  | 79830 |  |  | 79830 | Full | 79830 | 444021 |  | 444021 | No | Green | 2022-04-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-10-31 |  |  | 0 | 1689.8 | [17 empty] | 3/1/23 - Variance is from IRIS NDT invoice from work completed on 5/31/22. 1/4/23 - Variance is from Youngs Environmental invoice when removing the temporary traps. 12/5/22 - Traps removed after data analysis group approved successful run. No digs issued from assessment. Accrual is for TDW invoice that was approved in Open Invoice. 11/1/22 - Accrual is for TDW invoice. Integrity confirmed no digs required as a result of this assessment. 10/1/22 - Accrual is for TDW invoice ($10,241) and Holly invoice ($44,697). 9/1/22 - Re-run of MFL tool completed, accrual is for Holly and TDW invoices. Holly invoice includes restoration of cutout dig sites along with tool-run assistance. 8/1/22 - Re-run of MFL tool scheduled 8/2. Accrual is for Holly invoice for roadway restoration at cutout site. 7/5/22 - Accrual is for Holly invoices. Re-run of tool scheduled for 8/2/22. 6/1/22 - Pig became stuck on 5/5/22. Efforts to locate the tool, excavate/cutout span of pipe continued through the week of 5/31. Section of pipe with ILI tool stuck is now going through failure investigation. Tie-ins for replacement pipe completed on 5/31, and refill completed on 6/1/22. 5/3/22 - ILI scheduled for 5/5. 4/2/22 - Airport lines schedule collapsed to run all lines back to back in May 2022. 2/2/22 - No Change 1/3/22 - No Change | 2023-03-02 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Wayne Pipeline | 5DA999A2 - SHELL - DETROIT AIRPORT MANIFO |  | 1690 | 0 |  |  | 442332 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40657 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-23 | Int - Assessments
2022 - DS999A1 - ILI | Item | Open | MEXP | DS999A1E2201 | Exempt | 1945667 | Roman, James | West | 6. Operational | Defined | Assessments | 1994 |  |  | 1994.15 | 1994 | 0 | Green |  |  |  | 1994 |  |  | 76405 |  |  | 76405 | Full | 76405 | 57182 |  | 57182 | No | Green | 2022-07-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-10-05 |  |  | 1994.15 | [18 empty] | 2/1/23 Variance $2k vac truck trailing cost 1/4/23 Variance -$25k $9k accrual for tool vendor had already been paid. Forecasted $16k for contractor in Dec, he came in under budget at $7,400 which will be accrued for Dec. 12/5/22 Variance -$9k. Accrual $9k. Tool Vendor's remaining cost. December forecast to remove and pack traps. 11/1/22 Variance ($3,790) trailing costs 10/3/22 Re-Accruing tool and contractor cost 9/1/22 Variance (-) over forecasted. Tool run complete, and accruing 75% of ILI Vendor's cost along with Degen tracking costs. Nov forecast is remaining 25% of ILI Vendor cost. Project underbudget. 8/2/22 Variance (+) Accrual for trap modifications. 7/5/22 no change 6/2/22 No change 4/2/22 Tool scheduled to run in August. | 2023-04-12 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Toledo | DS999A1 - TOLEDO TO NORCO 8IN REVERSAL |  | 1994 | 0 |  |  | 55188 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40663 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-23 | Int - Assessments
2022 - DT718CO - ILI | Item | Open | MEXP | DT718DME2201 | Exempt | 1945829, 1939970 | Burns, Richard | West | 6. Operational | Defined | Assessments | 65389 |  |  | 65388.58 | 65389 | 0 | Green |  |  |  | 65389 |  |  | 304541 |  |  | 304541 | Full | 304541 | 303231 |  | 303231 | No | Green | 2022-07-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2023-01-31 |  |  | 4503.58 | 0 | 60885 | 0 |  |  | 0 | Green | [11 empty] | 5/1/23 - still no invoice from Rosen; re-acrrued amount. 4/3/23 - variance re-accrue plus new accrual. (Rosen) 3/1/23 - variance re-accrued. (Rosen invoice). 2/1/23 - variance accrued; Rosen invoice came in less than the 75% expected because of $63K of extra reporting requested that will be billed with the final invoice. Rest is from TDW pig sig parts that were backordered ($3194) and P-card charges ($1393). 1/3/23 - Most of variance is accrued for Rosen invoice. Overage is P-card charges more than expected. 12/2/22 - Variance is P-card purchases (D. Farster); ILI run scheduled for 12/6/22, CO to DT. 11/1/22 - Variance is from ILI run not completed due to vendor tool issues and product issues. No set date for rescheduling run but appears it may push to December. Forecasted accordingly. 9/28/22 - variance is because run pushed to week of 10/24/22 due to ILI vendor having tool issues and our scheduling concerns due to Toledo refinery fire. Adjusted forecast accordingly. 9/1/22 - COGNOS report shows $3441 in P-card charges for ILI prep work, but nothing here. 8/31/22 - on track for 9/27 run data. XYZ surveying almost complete. 8/1/22 - variance is p-card purchase (trailer rental for side-by-side for setting AGMs). 7/1/22 - same 6/1/22 - same. 5/2/22 - same 4/20/22 - changed job book required to "no" as they are not required for ILI runs. 4/2/22 - scheduled for September. 2/28/22 - added the WO I created. 2/2/22 - GEO+AMFL+XYZ ILI scheduled for 9/13/22. | 2023-05-09 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Duncansville | DT718DM - DUNCANSVILLE STA-DELMONT |  | 65389 | 0 |  |  | 237842 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40664 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-24 | Int - Assessments
2022 - EC999B2 - Pressure Test | Item | Open | MEXP | EC999B2E2201 | Maintenance Framework | 1945832 | Lloyd, Andrew | West | 7. Closed | Defined | Assessments | 374 |  |  | 373.54 | 374 | 0 | Green |  |  |  | 374 |  |  | 69300 |  |  | 69300 | Full | 69300 | 52544 |  | 52544 | No | Green | 2022-06-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-06-03 |  |  | 373.54 | [18 empty] | 12/19/22 - PO and WO closed - ready to be closed by accounting. 11/16 variance is due to savings, project completed 6/3 10/1 savings from AFE. 9/1 project complete variance is project savings. 8/1 project complete variance is project savings. 7/1 project complete 6/17/22 - signed hydrotest document package handed off to Beth. 6/1 kickoff call held, contractor performing work to fill line and complete hydrotest 5/2 completed field walkdown and awaiting bid. 4/6 no change, will walk down to verify draft hydrotest plan 3/1/22 on track writing hydro procedure to bid out 2/8/22 - just assigned project - working on gathering procedures to bid out. | 2022-12-19 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | EC999B2 - BET TO EAST CHICAGO STATION |  | 374 | 0 |  |  | 52170 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40667 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-23 | Int - Assessments
2022 - EG999B1 - ILI | Item | Open | MEXP | EG999B1E2201 | Maintenance Framework | 1945834 | Lloyd, Andrew | West | 6. Operational | Defined | Assessments | 175083 |  |  | 175083.14 | 170883 | 4200 | Yellow | 8152 |  | 8152 | 166931 |  |  | 53185 |  |  | 53185 | Full | 53185 | 300783 |  | 300783 | No | Green | 2022-09-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2023-01-13 |  |  | 152387.71 | 4878.68 | 5464.75 | 12352 | 8152 | 8152 | 4200 | Red | [11 empty] | 5/1/23 status as prior. need to change status to 80 and close out4/3/23 status as prior 3/31/23 this project was completed, need to change status to 80 and close out POs. 3/20/2023 - need to submit job book and hydrotest documents for temp traps used for ILI run.2/28/2023 variance is due to BP scheduling. Job book submitted, project is complete pending final invoice from Enduro. 2/9/2023 job book documents in sharepoint, awaiting visual pipe inspection form before completing package for shipment to PA. 1/31/2023 variance is due to BP scheduling. Lessons learned meeting completed and future execution plan added to sharepoint. Job book documents in process of submission. 1/13/23 smart tool trapped at Buckeye. 1/2/2023 Variance is due to BP schedule. BP advises suboptimal flow for revised planned date of tool run. Rescheduled all contractors and coordinated with operations/BP for 1/11/23 launch. 12/28 BP scheduler has advised that flow rate potentially may not support planned 1/4/23 run date. Contingency plan is to utilize 1/11/23 as run date in advance of assessment deadline. 12/7/22 variance is due to schedule. BP cannot provide the flow needed for this tool run to occur on 12/14. They have had their gas oil hydrotreater go down last night and tentatively it will not startup to 12/20. We are targeting 1/4/23 for smart tool run with contingency timing being 1/11/23. 11/29 variance is due to schedule. Tool run delayed until 12/14 if flow available from BP. 11/16 traps hung on both sides of canal. BP confirming flow rates for tool run. 11/14 tool run will be rescheduled as flow rates provided by BP are insufficient for a successful tool run. 11/1 variance is due to material delays. Project on track for execution. Walk down scheduled with BP10/3 contractor taking initial measurements 10/5 to be ready for 11/17 install. Discussion with BP to occur on recurring basis until project execution. 9/28 PO issued to contactor, contracting pulling measurements 10/59/2 there areno existing temp. traps to run this tool. Led Roberts, Midwestern, and Manhattan with Cuddy to obtain pricing. FCST reflects cost to build traps. 8/30 field walk scheduled. Traps may be needed for this work. 8/1 PO issued to Expro to provide flare. 7/1 field walk of BP side reveals no obstructions, operations has traps. 6/1 anticipate requiring additional funding for this project due to flare needs, mechanical assistance within BP, and temporary traps. 5/2 obtained quote from Expro for flare services and are booked4/6 on track3/1/2022 propylene tool run on track | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | EG - EAST CHICAGO STA (NORCO) |  | 162731 | 12352 |  |  | 125700 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40669 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-23 | Int - Assessments
2022 - EH999A1 - Pressure Test and Go/No-Go ILI | Item | Open | MEXP | EH999A1E2201 | Maintenance Framework | 1945835 | Lloyd, Andrew | West | 6. Operational | Defined | Assessments | 1189 |  |  | 1188.6 | 735 | 454 | Red |  |  |  | 1189 |  |  | 114000 |  |  | 114000 | Full | 114000 | 83046 |  | 83046 | No | Green | 2022-09-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-09-21 |  |  |  |  | 735 | 453.6 |  |  | 454 | Red | [11 empty] | 5/1 status as prior 3/31/2023 this project was completed last year. Need to change status to 80 and closeout. 11/14 trailing costs anticipated for Actuation Group. 10/1 anticipate savings from AFE estimate. Water haul off in process with environmental. Final painting and backfill to conclude mid october. 9/21 Complete with hydro 9/1 SSSP in for review by safety. Additional walkdown with inspector and contractor and operations has occurred. 8/1 PO issued to shultz for completion of this work. Requests for quotes to other vendors requested. 7/1 field walk with operations completed, shultz anticipated to perform work. 6/1 requested facility P&IDs to modify execution plan for pretzel. 5/2 targeting May/June field walk down 4/6 on track, reviewed with OM 3/1/22 On track writing procedure to have bid out 2/8/22 - just assigned project - working on gathering procedures to bid out. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | EH999A1 - HAMMOND - NORTH PROP GAS |  | 735 | 454 |  |  | 81858 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40671 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-23 | Int - Assessments
2022 - EH999A3 - Pressure Test and Go/No-Go ILI | Item | Open | MEXP | EH999A3E2201 | Maintenance Framework | 1945837 | Lloyd, Andrew | West | 6. Operational | Defined | Assessments | 0 |  |  | -0.4 | 0 | 0 | Green |  |  |  | 0 |  |  | 117150 |  |  | 117150 | Full | 117150 | 116721 |  | 116721 | No | Green | 2022-09-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-09-14 |  |  | -0.4 | 15355 | -15355 | [16 empty] | 5/1 Need to change status to 80 and closeout.4/3/23 variance is due to coupa/vendor issue. Status as prior 3/31/2023 this project was completed last year. Need to change status to 80 and closeout. 1/2/2023 variance is due to savings. Project completed in September. Previously carrying accrual for Brock waiting on COUPA approval. Invoice was submitted and processed for less than expected 12/2 variance is due to timing of invoicing. 11/16 project complete, have reached out to tool vendor for confirmation on report delivery. 10/1 anticipate savings from AFE estimate. Water haul off in process with environmental. Final painting and backfill to conclude mid october. 9/14 hydro complete 9/1 SSSP in for review by safety. Additional walkdown with inspector and contractor and operations has occurred. 8/1 PO issued to shultz for completion of this work. Requests for quotes to other vendors requested. 7/1 field walk with operations completed, shultz anticipated to perform work. 6/1 requested facility P&IDs to modify execution plan for pretzel. 5/2 targeting May/June field walk down 4/6 on track, reviewed with OM 3/1/22 On track writing procedures to have bid event 2/8/22 - just assigned project - working on gathering procedures to bid out. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | EH999A3 - Hammond Main Property to TL Explorer |  | 0 | 0 |  |  | 116721 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40673 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-24 | Int - Assessments
2022 - EU999A2 - Pressure Test | Item | Open | MEXP | EU999A2E2201 | Maintenance Framework | 1945838 | Lloyd, Andrew | West | 7. Closed | Defined | Assessments | 12 |  |  | 11.73 | 0 | 12 | Red |  |  |  | 12 |  |  | 84000 |  |  | 84000 | Full | 84000 | 92673 |  | 92673 | No | Green | 2022-08-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-11-16 |  |  | 0.04 |  |  | 11.69 |  |  | 12 | Red | [11 empty] | 3/10/2023 project complete and ready to be closed by accounting. 1/2/2023 awaiting submittal of contractor invoice for glycol due to weather. 12/20/22 variance is due to weather. Waste management invoice received for WDR. 12/6/22 variance is due to weather. Glycol cost anticipated for this work. 11/17 hydrotesting completed, update note sent to integrity, status changed to operational. Waiting on profile from Karen for GFL haul off of glycol. 11/16 contractor is hydrotesting today. 11/14 contractor has mobilized. Additional costs for glycol anticipated. 11/1 project on track for November execution 10/3 project on track for November execution. 9/1 project remains on track for execution in November. 8/1 PO issued to shultz to perform the hydrotest work. Waiting on vendors to provide quotes for other items. 7/1 scheduled field walk with local asset team for 7/8. 6/1 June field walk to be scheduled 5/2 targeting May/June field walk down 4/6 on track, reviewed with OM 3/1 writing hydrotest procedures for bid event 2/8/22 - just assigned project - working on gathering procedures to bid out. | 2023-03-10 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | EU999A2 - E Chicago B/G to E Chicago Citgo |  | 0 | 12 |  |  | 92662 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40677 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-23 | Int - Assessments
2022 - FG999B1 - Pressure Test | Item | Open | MEXP | FG999B1E2201 | Maintenance Framework | 1945839 | Lloyd, Andrew | West | 7. Closed | Defined | Assessments | 11 |  |  | 10.95 | 11 | 0 | Green |  |  |  | 11 |  |  | 73500 |  |  | 73500 | Full | 73500 | 66417 |  | 66417 | No | Green | 2022-10-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-10-12 |  |  | 10.95 | [18 empty] | 3/10/2023 project is complete and ready to be closed by accounting. 11/2 variance is due to savings from AFE estimate. Project mechanically complete. 10/3 project on track for pressure test 9/1 outage confirmed with third party. 8/1 PO issued to shultz to perform the hydrotest work. Waiting on vendors to provide quotes for other items. 7/1 field walk completed with operations. 6/1 discussed project with Shultz for execution of this project. 5/2 targeting May/June field walk down 4/6 on track, reviewed with OM 3/1/22 writing hydrotest procedures for bid event 2/8/22 - just assigned project - working on gathering procedures to bid out. | 2023-03-10 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Michiana | FG999B1 - Wolverine Gas to BETFG |  | 11 | 0 |  |  | 66406 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40679 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-23 | Int - Assessments
2022 - FG999B2 - Pressure Test | Item | Open | MEXP | FG999B2E2201 | Maintenance Framework | 1945840 | Lloyd, Andrew | West | 7. Closed | Defined | Assessments | 11 |  |  | 10.95 | 11 | 0 | Green |  |  |  | 11 |  |  | 73500 |  |  | 73500 | Full | 73500 | 43167 |  | 43167 | No | Green | 2022-10-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-10-05 |  |  | 10.95 | [18 empty] | 3/10/2023 project complete and ready to be closed by accounting. 11/2 variance is due to savings from AFE estimate. Project mechanically complete. 10/3 project on track for execution. 9/1 outage confirmed with third party. Project on track. 8/1 PO issued to shultz to perform the hydrotest work. Waiting on vendors to provide quotes for other items. 7/1 field walk completed with operations. 6/1 discussed project with Shultz for execution of this project. 5/2 targeting May/June for field walkdown 4/6 on track, initial discussion with ops 3/1/22 writing hydrotest procedures for bid event 2/8/22 - just assigned project - working on gathering procedures to bid out. | 2023-03-10 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Michiana | FG999B2 - Wolerine Oil to BETFG |  | 11 | 0 |  |  | 43156 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40680 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-24 | Int - Assessments
2022 - IC710CP - ILI | Item | Open | MEXP | IC710CPE2201 | Exempt | 1945844 | Roman, James | West | 6. Operational | Defined | Assessments | 1 |  |  | 1.18 | 1 | 0 | Green |  |  |  | 1 |  |  | 105500 |  |  | 105500 | Full | 105500 | 78752 |  | 78752 | No | Green | 2022-10-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-12-31 |  |  | 1.18 | [18 empty] | 2/1/23 No Change 1/4/23 Variance -$45,500. Accrual $24k. Contractor under budget. Some costs hit 820 ILI. Tool run complete. Awaiting integrity to let me know if i can approve ILI vendor invoice. 12-5-22 Variance (-$35,738). Tool rescheduled for 12/13/22 due to project work at Coraopolis. 11/1/22 Variance (-$15k) $15k Accrual. $50k of November forecast is for trap modifications. Do not yet know the cost of tool vendor. Plan to run tool mid November. 10/3/22 Tool run now scheduled for November due to corporate work at Coraopolis facility. Plan to perform XYZ survey in Mid October and trap modifications end of October. 8/2/22 No change 7/5/22 no change 6/2/22 No change 4/2/22 Tool run planned for October. | 2023-02-01 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Coraopolis | IC710CP - CORAOPOLIS JCT TO CORAOPOLIS |  | 1 | 0 |  |  | 78751 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40697 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-23 | Int - Assessments
2022 - IT999A1 - ILI | Item | Open | MEXP | IT999A1E2201 | Exempt | 1945845 | Bost, Jason | West | 6. Operational | Defined | Assessments | -2160 |  |  | -2160 | -2160 | 0 | Green |  |  |  | -2160 |  |  | 77820 |  |  | 77820 | Full | 77820 | 71795 |  | 71795 | No | Green | 2022-04-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-12-31 |  |  | 0 | 0 | -2160 | [16 empty] | 4/3/23 - Received confirmation from TDW that no further charges are expected. PO can be closed. 3/1/23 - Remaining TDW PO amount accrued. 1/31/23 - Accrual is for TDW's final invoice. 1/4/23 - Accrual is for TDW's remaining PO balance. Remaining variance is cost savings, do not expect any other invoices besides TDW's. 12/5/22 - Variance is caused by final invoice from TDW not coming through yet. Moved forecast to December to reflect remaining PO amount. 10/1/22 - Variance is caused by not receiving TDW's final invoice. Forecast adjusted accordingly. 7/5/22 - Variance is caused by a Young's Env invoice. 6/1/22 - ILI completed on 5/3. Accrual is for Holly Invoice. 5/3/22 - ILI scheduled for 5/3. 4/2/22 - Airport lines schedule collapsed to run all lines back to back in May 2022. 2/2/22 - No Change 1/3/22 - No Change | 2023-04-04 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Wayne Pipeline | IT999A1 - DEARBORN TERM TO DETROIT AIRPO |  | -2160 | 0 |  |  | 73955 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40699 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-23 | Int - Assessments
2022 - KG999A2 - Pressure Test | Item | Open | MEXP | KG999A2E2201 | Maintenance Framework | 1945846 | Lloyd, Andrew | West | 6. Operational | Defined | Assessments | 11 |  |  | 10.95 | 11 | 0 | Green |  |  |  | 11 |  |  | 67200 |  |  | 67200 | Full | 67200 | 54540 |  | 54540 | No | Green | 2022-10-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-10-18 |  |  | 2360.95 | 0 | -2350 | [16 empty] | 5/1 Need to change status to 80 and closeout.4/3/23 status as prior 3/31/2023 this project was completed last year. Need to change status to 80 and closeout. 3/1 PO to apache to be reissued to Apache United, only remaining amount. 11/2 variance is due to savings from AFE estimate. Project mechanically complete. 10/20 testing completed 10/17 contractor has mobilized 10/3 project on track for execution by Shultz 9/1 project on track for execution in October 8/1 PO issued to shultz 7/1 completed field walk with operations 6/1 targeting June for field walkdown with operations and contractors 5/2 Targeting May/June for field walkdown 4/6 on track, initial discussion with ops 3/1/22 writing hydrotest procedures for bid event 2/8/22 - just assigned project - working on gathering procedures to bid out. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | KG - LAKE GEORGE STATION |  | 11 | 0 |  |  | 54529 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40700 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-23 | Int - Assessments
2022 - KG999B1 - Pressure Test | Item | Open | MEXP | KG999B1E2201 | Maintenance Framework | 1945848 | Lloyd, Andrew | West | 6. Operational | Defined | Assessments | 3387 |  |  | 3386.94 | 3375 | 12 | Yellow |  |  |  | 3387 |  |  | 143850 |  |  | 143850 | Full | 143850 | 115199 |  | 115199 | No | Green | 2022-11-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2022-12-02 |  |  | 3249 |  | 126.25 | 11.69 |  |  | 12 | Red | [11 empty] | 5/1 Need to change status to 80 and closeout.4/3/23 status as prior 3/31/2023 this project was completed last year. Need to change status to 80 and closeout. 2/1/2023 variance is due to savings from afe estimate. project complete 1/2/2023 variance is due to savings from AFE estimate. Invoicing complete for WM WDR. Job book submitted to sharepoint. Integrity updated on completion 11/28. 12/7/22 variance is due to forecasting. Project mechanically complete. 12/1 water purge complete, refill tomorrow. Haul off of fracs scheduled. 11/30 hydrotest complete, notice sent to integrity 11/29 onsite for purge. Purge success. Contractor filling with water for hydrotest tomorrow 11/30. 11/14 site walk downs with BP success. Roberts has been scheduled for BP training. Pigs received. Linde reminded of obligations. GFL to supply water and vac. Frac tanks and hose discussed. 11/1 project on track for November execution. Walk down with BP scheduled. 10/3 project on track for November execution 9/1 bid walk with selected contractors and operations will occur Friday. 8/1 working to obtain quote from outside contractors. 7/1 completed field walk with operations 6/1 targeting June for field walkdown with operations 5/2 Targeting May/June for field walkdown 4/6 on track, initial discussion with ops 3/1/22 writing hydrotest procedures for bid event 2/8/22 - just assigned project - working on gathering procedures to bid out. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | KG999B1 - CLARK JCT TO BP WHITING |  | 3375 | 12 |  |  | 111812 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40701 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-23 | Int - Assessments
2022 - WD202-204-205WW - ILI - SEAM UTCD | Item | Open | MEXP | WD202DBE2201 | Exempt | 1945856 | Bost, Jason | West | 6. Operational | Defined | Assessments | 64857 |  |  | 64857 | 64857 | 0 | Green | 83812 |  | 83812 | -18955 |  |  | 335250 |  |  | 335250 | Full | 335250 | 269779 |  | 269779 | No | Green | 2022-08-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2023-02-28 |  |  |  | 64857 | 0 | 0 |  |  | 0 | Green |  | Contractor/Vendor Issue | [9 empty] | 5/1/23 - 12 dig anomalies issued by Integrity on 4/24/23. Accrual is final 25% of vendors PO. 4/3/23 - Accrual is 25% NDT Invoice. Run accepted in Nov. 2022. 3/1/23 - 25% NDT PO accrued. Prelim report received, no features met screening criteria. 1/4/23 - Variance is from laggin Holly invoice. 12/5/22 - 75% of vendor invoice has been approved. Final 25% is already reflected in 2023, so remaining variance is likely cost savings.11/1/22 - Variance was shifted into Nov. forecast to reflect project schedule. Assessment completed on 11/1/22. 10/1/22 - Variance is prep for tool run. Assessment rescheduled for 10/31. 9/1/22 - Project delayed due to product scheduling conflict. Forecast adjusted accordingly. 8/1/22 - No Change. 7/5/22 - Assessment planned for late August. 6/1/22 - Assessment planned for 8/23. 5/3/22 - No Change. 4/4/22 - No Change. 3/2/22 - No Change. 2/2/22 - No Change 1/3/22 - No Change | 2023-05-09 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Wayne Pipeline | WD202DB - DETROIT TO DEARBORN-8IN |  | 64857 | 0 |  |  | 204922 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40712 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-23 | Int - Assessments
2022 - WW203WF-2 - ILI | Item | Open | MEXP | WW203WCE2202 | Exempt | 1945859 | Roman, James | West | 6. Operational | Defined | Assessments | 200 |  |  | 200.25 | 200 | 0 | Green |  |  |  | 200 |  |  | 126879 |  |  | 126879 | Full | 126879 | 72995 |  | 72995 | No | Green | 2022-10-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2023-01-30 |  |  | 200 | 0.25 | [17 empty] | 3/1/23 Variance $21k. Re-accrue final invoice. 2/1/23 Variance -$63k, Re-accrual $63k 1/4/23 Variance -$57k. Re-Accrual $63k. Awaiting integrity to let me know if I can approve this invoice. 12/5/22 Variance ($64k). Accrual $63k. 11/1/22 Variance (-123k) Tool run rescheduled for 11/2/22. Revised forecast shows 25% of PO amount. Balance forecasted for Feb 2023. PO amount was less than original forecast. 10/3/22 Tool run scheduled for end of October 9/1/22 no change 7/5/22 no change 6/2/22 Tool run rescheduled for October. 4/2/22 Tool run planned for December. | 2023-04-12 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Wayne Pipeline | WW203WC - WAYNE TO CLARKSTON |  | 200 | 0 |  |  | 72795 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40716 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-23 | Int - Assessments
2022 - WW203WF-3 - ILI | Item | Open | MEXP | WW203WCE2203 | Exempt | 1945860 | Roman, James | West | 6. Operational | Defined | Assessments | 31344 |  |  | 31344 | 31344 | 0 | Green |  |  |  | 31344 |  |  | 102700 |  |  | 102700 | Full | 102700 | 63669 |  | 63669 | No | Green | 2022-10-01 | 2022-01-04 | 2022-01-04 | 2022-12-31 | 2023-03-26 |  |  | 10675 | 20669 | 0 | 0 |  |  | 0 | Green |  | Contractor/Vendor Issue | [9 empty] | 5/1/23 Variance -$21k. Re-accruing Rosen's final invoice. 4/5/23 Variance -$21k. Re-accruing $21k final invoice from Rosen. 3/1/23 Variance $300. Over accrued $300 2/1/23 Variance -$10k, Accrual $10k 1/4/23 No change 12/5/22 Variance (-$32k) Accrual $32k. 11/1/22 Variance (-$102k) Accrual $32,025. PO amount was less than original forecasts. Remaining 25% forecasted for Jan 2023. 10/3/22 Tool run scheduled for end of October. 9/1/22 No change 7/5/22 no change 6/2/22 Tool run rescheduled for October. 4/2/22 Tool run planned for December. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Wayne Pipeline | WW203WC - WAYNE TO CLARKSTON |  | 31344 | 0 |  |  | 32325 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40717 |  | Administrator, System | JDE Child | Burnt Orange | 2021-07-23 | Int - Assessments
2022 RESEAL FRPS 380 TERMINAL PIPING | Item | Open | MEXP | BETHY00E2204 | Maintenance Framework | 1981605 | Brown, Jeff | West | 7. Closed | Drawdown | Atmospheric Corrosion | 81 |  |  | 80.77 | 81 | 0 | Green |  |  |  | 81 |  |  | 26000 |  |  | 26000 | Full | 26000 | 24447 |  | 24447 | No | Green | 2022-08-01 | 2022-05-25 | 2022-05-25 | 2022-12-31 | 2022-09-01 |  |  | 80.77 | [18 empty] | 10/4/2022 - glass mesh late invoice. 8-31-22 PROJECT COMPLETE 8-1-22 AUG IN PROGRESS 7/7/2022 - NO CHANGE IN SCHEDULE. 6/3/2022 - work scheduled for Sept | 2022-10-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  | 81 | 0 |  |  | 24366 |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 43845 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-05-25 | Int - Planned Corr & FI
2022 RESEAL FRPS-LA-AREA 1 | Item | Open | MEXP | BETIL00E2203 | Maintenance Framework | 1981588 | Brown, Jeff | West | 7. Closed | Drawdown | Atmospheric Corrosion | 621 |  |  | 620.7 | 621 | 0 | Green |  |  |  | 621 |  |  | 24370 |  |  | 24370 | Full | 24370 | 23697 |  | 23697 | No | Green | 2022-07-01 | 2022-05-25 | 2022-05-25 | 2022-12-31 | 2022-09-01 |  |  | 620.7 | [18 empty] | 9/1/2022 - work completed ahead of schedule. 8-1-22 Cognos is showing $26,460 is paid. WAITING ON EZ-LINE7-7-22 WORK 90% COMPLETE. 6/2/22 - scheduled for July | 2022-09-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Southern Ohio | BETIL - BET COLUMBUS SOUTH |  | 621 | 0 |  |  | 23077 |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 43840 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-05-25 | Int - Planned Corr & FI
2023 Annual Criteria Digs - WW203WF-1 | Item | Open | MCAP | WW203WCM2301 | Maintenance Framework |  | Roman, James | West | 8. Canceled | Defined | Pipeline Digs |  | 0 |  | 0 | 190000 | -190000 | Red | 190000 |  | 190000 | -190000 |  |  | 221350 |  |  |  | Full | 221350 |  | 0 | 0 | No | Green |  |  |  | 2023-12-31 | 2023-10-31 | [12 empty] | 0 | 0 | [7 empty] | 5/1/23 This project to be cancelled as discussed with Bartal. | 2023-05-02 | Williams, Nikole |  | West | Pipelines and Terminals | Integrity | Integrity | Wayne Pipeline | WW203WC - WAYNE TO CLARKSTON |  |  | 0 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44917 |  | Administrator, System | Independent | Aqua | 2022-08-18 | Int- Planned Digs
2023 Annual Criteria Digs - XB403CL | Item | Open | MCAP | XB403CLM2301 | Maintenance Framework | 2083189 | Cullison, Daniel | West | 6. Operational | Drawdown | Pipeline Digs | 65934 |  |  | 65934.29 | 62866 | 3069 | Yellow | 100000 |  | 100000 | -34066 |  |  | 72059 |  |  | 72059 | Full | 72059 | 65934 |  | 65934 | No | Green | 2023-03-01 | 2023-03-01 | 2023-03-01 | 2023-04-15 | 2023-03-31 |  |  |  |  | 62384.61 | 3549.68 | 481 | 481 | 3069 | Red | [11 empty] | 3/29/23: Project documentation verified and job book submitted via Project Sites. 3/21/23: Work complete and contractor de-mobilized 3/13/23: Degen mobilized 3/7/23: Pre-con meeting held 3/2/23: AFE has been approved; POs requested for Degen, MNT Inspection, and MNT NDT; Set up stakeholder meeting 2/27/23: Quotes have been received from GC, inspection, and NDT contractor. The project has been set up in OPPM, ISN, and a Raken project has been created. An AFE was submitted on 2/23/23. Once the AFE is approved, POs will be submitted. | 2023-04-03 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Indianapolis |  |  | 62385 | 3550 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44923 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int- Planned Digs
2023 AS160PN - ILI | Item | Open | MEXP | AS160HTE2301 | Exempt | 2075690 | Lloyd, Andrew | West | 6. Operational | Defined | Assessments | 15434 | 240752 |  | 256186.37 | 247668 | 8518 | Yellow | 263087 |  | 263087 | -6901 |  |  | 263087 |  |  |  | Full | 263087 | 15434 | 240752 | 256186 | No | Green | 2023-03-01 |  |  | 2023-12-31 | 2023-05-04 |  |  |  |  | 11201.25 | 4233.12 | 7500 | 7500 | -3267 | Red |  |  | 163000 | 26755 |  | 50997 | [5 empty] | 5/1/2023 tool launched at wood river, second entegra crew mobilizing to auburn 5/2. 4/27 gauge pig results verified, on track for tool run 4/14 held additional stakeholders call, launching gauge pig as planned. 4/3 variance is due to contractor availability for mobilization. Project on track for execution, additional stakeholders meetings held with team. CC notified we will launch gauge 4/17 in gas. 3/31/23 project on track for execution, additional stakeholders meetings held with team. CC notified we will launch gauge 4/17 in gas. 3/2/23 This project afe included with program submittal, project is active. Gauge pig 4/19 and smart tool 5/3. In advance will require contractor assistance to pull pig sigs. 1/19/23 wired pig sig lead time too long to replace pre run. Followed up with integrity for new tool vendor information. Planned assessment date is 3/14/23 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Central-Illinois | AS160HT - AUBURN TO HARRISTOWN JCT |  | 11201 | 193988 | 50997 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44670 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 DF999A2 - Pressure Test | Item | Open | MEXP | DF999A2E2301 | Maintenance Framework | 2075735 | Scannell, Adam | West | 3. Active | Defined | Assessments |  | 130000 |  | 130000 | 130000 | 0 | Green | 132000 |  | 132000 | -2000 |  |  | 132000 |  |  | 132000 | Full | 132000 |  | 130000 | 130000 | No | Green | 2023-09-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-09-30 | [16 empty] | 130000 |  |  |  |  | 04/21/23 - Previous test documents including scope have been received. I will schedule a site visit early may to walk through with local pipeliner to develop scope. Rest currently scheduled for September. This project will run in conjunction with the critical bond installation and likely parts of the leak warn installation with Mark Grinder.03/02/23 - Program AFE approved. Started speaking with operations for early planning. Test planned for September. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Eastern Iowa | DF999A2 |  |  | 0 | 130000 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44674 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 Drawdown West Region MCAP | Item | Open | MCAP |  | Maintenance Framework |  | Gardner, Travis | West | 1. Proposed |  | West |  | 656480 |  | 656480 | 554280 | 102200 | Red | 1000000 | -83802 | 916198 | -259718 | [9 empty] | 656480 | 656480 | No | Green | 2023-08-01 |  |  |  | 2023-11-30 | [15 empty] | 140980 | 309300 |  | 206200 |  |  | MCAP 5/9/2023 – Reduced overall increase of $102.2 K. March add drawdown BETND Indianola Bridge Study (22K), Argo Fire Water Hydrant Refurbishments 2023 (198K), and Ferrysburg Terminal Secondary Berm Installation ($145K). Drawdown Reduction for March – Water Hammer Project - BETAI Granger ($23.6K), Ferrysburg Lubricity Flow Meter Replacement ($18.5K), Woodhaven Station Tank 120 Premium Pump Replacement ($23K), XX180ST Strainer Replacement ($22.7K), Griffith Propane Delivery Control Valve & Actuator Replacement ($81K), Council Bluffs New Flash Tester Purchase ($28K), Woodhaven Terminal Fire Suppression Upgrade Phase I ($20K), FLINT STATION UPS REPLACE ($12K), and Council Bluffs - Service Bay HVAC Replacement (17K), East St. Louis Haz-Gas Detectors Replacement ($12K), 316 Discharge Valves Replacement ($6K), Woodhaven Station - Upgrade Oil on Water Detection System ($6K) MCAP 4/9/2023 – Reduced overall reduction of $297K. March add drawdown Huntington North Propane Pump and Motor Replacement (300K). Drawdown Reduction for March – DeWitt Pump Discharge Valve Replacement ($59K), Hartsdale Butane Electrical Distribution Panelboard Replacement ($42K), Hartsdale Terminal Site Lighting Replacement ($21K), Napoleon Terminal Roof Top Unit Replacement ($22.8K), Toledo Station 12"300 Grove Ball Valve Replacement ($29K), Hartsdale Butane Offload Driver Kiosk ($43K), Hartsdale 480V Office Electrical Gear Removal ($17K), East Chicago East Warehouse Roof Refurbishment ($25.6K) MCAP 3/9/2023 – Reduced overall reduction of $61.3K. February add drawdown East Chicago East Truck Rack VAVAC Pressure Transmitter Relocate (35K), East Chicago East Butane Suction Valve Replacement (60K), Kankakee Sample Building Replacement 2020 (25K). Drawdown Reduction for February - Dearborn Terminal Legacy System Electrical Infrastructure Upgrade (120K), Bradley Road Station Camera and Card Reader Replacement ($14K), Ferrysburg Actuator Replacement ($11.3K), Toledo Station 8"600 GROVEBALL VALVE Replacement ($18K), Toledo Station #2 Butane Booster Pump Motor Replacement (18K) MCAP 02/09/2023 – Drawdown Reduction for January - Sugar Creek & Ottumwa 101 Tapping Machine Purchase (16K), Des Moines Terminal HVAC Replacement (16.4K), Canton Fiber VRU comms (31K), Burlington Junction Hazardous Gas Detector Replacement (10.68K), Ferrysburg Pump and Actuator Replacment (28K), Granville Terminal Red Dye System upgrade (15.79K) | 2023-05-08 |  |  | Corporate - Pipes and Terminals | Pipelines and Terminals | Operating Infrastructure | Operating Infrastructure | Corporate | Corporate |  |  | 0 | 450280 | 206200 |  |  | Gardner, Travis |  |  |  | 1 | 45214 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
2023 Drawdown West Region MEXP | Item | Open | MEXP | 1348685E2300 | Maintenance Framework |  | Gardner, Travis | West | 3. Active | Drawdown | West |  | 277650 |  | 277650 | 352250 | -74600 | Red | 500000 | -11000 | 489000 | -211350 |  |  | 500000 |  |  | 500000 | Full | 500000 |  | 277650 | 277650 | No | Green | 2023-06-01 | 2023-01-09 | 2023-01-09 | 2023-12-31 | 2023-11-30 | [13 empty] | 77650 | 100000 |  | 100000 |  |  |  |  | MEXP 05/09/2023 - Reduced overall reduction of $74,600. April add drawdown from WO160BN Henderson Rd Casing Fill (10.4K). Drawdown reduced $85K for the following projects: Sugar Creek - Water Line Repair ($30K), Coraopolis Tank 204 Replace Rotating Element ($20K), PN160AG Manhattan-Monee Rd (CH 6) Pavement Repairs ($35K), CG415GE line investigation ($262K) MEXP 04/09/2023 - Drawdown reduced $63K for the following projects: JJ404JV Nitrogen Purge and Isolate ($18K), Lima Station Unit 5 Replace Seals and Rotating Element ($58K) MEXP 03/09/2023 - Drawdown reduced $63K for the following projects: Detroit Station Unit 5 Multilin 469 Trouble Shooting ($20.1K), Water Hammer Project - BETWF Flint Terminal ($3.6K), Water Hammer Project - BETWD Detroit Terminal ($3.6K), Water Hammer Project - BETON Canton Terminal ($3.6K), Water Hammer Project - BETAD Taylor East($3.6K), Council Bluffs Terminal Tank 6 Gauging Wire Repairs ($11K), Bay City Terminal Prover Actuator Gear Box Repairs (18K) MEXP 2/09/2023 - Drawdown reduced by $15K for 1 emergent project (Des Moines terminal Sewer Line Repair) in January. | 2023-05-08 | Griest, Barbara |  | West | Pipelines and Terminals | Station/Terminal | Station/Terminal | West Region Work Team | Corporate |  |  | 77650 | 200000 |  |  |  | Gardner, Travis | Clark, David |  |  | 1 | 45215 |  | Administrator, System | JDE Parent | Yellow | 2022-08-23 | Other Programs
2023 DS301CG - ILI | Item | Open | MEXP | DC301CGE2301 | Exempt | 2075691 | Bost, Jason | West | 3. Active | Defined | Assessments |  | 162701 |  | 162701 | 162701 | 0 | Green | 164701 |  | 164701 | -2000 |  |  | 164701 |  |  | 164701 | Full | 164701 |  | 162701 | 162701 | No | Green | 2023-08-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-08-31 | [15 empty] | 122026 |  |  | 40675 |  |  | 5/1/23 - No Change. 3/1/23 - No Change. 1/31/23 - Updated forecast to reflect 75% and 25% split. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Toledo | DC301CG - WALBRIDGE/C&O-CYGNET 10&12 |  |  | 0 | 122026 | 40675 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44675 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 DS302CG - ILI | Item | Open | MEXP | DS302CGE2301 | Exempt | 2075694 | Bost, Jason | West | 3. Active | Defined | Assessments |  | 152525 |  | 152525 | 152525 | 0 | Green | 154525 |  | 154525 | -2000 |  |  | 154525 |  |  | 154525 | Full | 154525 |  | 152525 | 152525 | No | Green | 2023-11-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-11-30 | [18 empty] | 114394 | 38131 |  | 5/1/23 - No Change. 3/1/23 - No Change.1/31/23 - Updated forecast to reflect 75% and 25% split. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Toledo | DS302CG - TOLEDO TO CYGNET 10IN SOUTH |  |  | 0 |  | 152525 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44676 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 DS307TO - ILI | Item | Open | MEXP | DS307TOE2301 | Exempt | 2075710 | Bost, Jason | West | 3. Active | Defined | Assessments |  | 117955 |  | 117955 | 117955 | 0 | Green | 119955 |  | 119955 | -2000 |  |  | 119955 |  |  | 119955 | Full | 119955 |  | 117955 | 117955 | No | Green | 2023-11-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-11-30 | [18 empty] | 88466 | 29489 |  | 5/1/23 - No Change. 3/1/23 - No Change.1/31/23 - Updated forecast to reflect 75% and 25% split. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Toledo | DS - TOLEDO STATION |  |  | 0 |  | 117955 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44677 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 EG999A7 - Pressure Test | Item | Open | MEXP | EG999A7E2301 | Maintenance Framework | 2075739 | Lloyd, Andrew | West | 3. Active | Defined | Assessments | 0 | 73000 |  | 73000 | 73000 | 0 | Green | 75000 |  | 75000 | -2000 |  |  | 75000 |  |  | 75000 | Full | 75000 | 0 | 73000 | 73000 | No | Green | 2023-02-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-11-30 |  |  |  | 2000 | -2000 | [11 empty] | 73000 |  |  |  |  | 5/1/2023 integrity has not provided preference on smart tool for this line. Will proceed with hydrotesting using Shultz construction. 4/3 walked down site with contractor and operations, strange to pressure test a line built in 2018 that has traps on both sides. Raised to integrity. 3/31/23 walked down site with contractor and operations, strange to pressure test a line built in 2018 that has traps on both sides. Raised to integrity. 3/2/23 planned assessment is 12/18/23, will move forward for avoidance of glycol costs | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | EG - EAST CHICAGO STA (NORCO) |  | 0 | 0 | 73000 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44678 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 EG999B3 - Pressure Test | Item | Open | MEXP | EG999B3E2301 | Maintenance Framework | 2075740 | Lloyd, Andrew | West | 3. Active | Defined | Assessments | 1098 | 73000 |  | 74097.5 | 74018 | 80 | Yellow | 75000 |  | 75000 | -903 |  |  | 75000 |  |  | 75000 | Full | 75000 | 1098 | 73000 | 74098 | No | Green | 2023-02-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-10-31 |  |  |  | 2000 | -982.5 | 80 |  |  | 80 | Red | [5 empty] | 73000 | [5 empty] | 5/1/2023 integrity has not provided preference on smart tool for this line. Will proceed with hydrotesting using Shultz construction 4/3 walked down site with contractor and operations, strange to pressure test a line built in 2018 that has traps on both sides. Raised to integrity. 3/31/23 walked down line earlier this month with operations and contractor. This line has both receiver and launcher trap. Integrity has been notified. 3/2/23 planned assessment is 9/30/23 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | EG - EAST CHICAGO STA (NORCO) |  | 1018 | 80 | 73000 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44679 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 EG999B4 - Pressure Test | Item | Open | MEXP | EG999B4E2301 | Maintenance Framework | 2075741 | Lloyd, Andrew | West | 3. Active | Defined | Assessments | 0 | 73000 |  | 73000 | 73000 | 0 | Green | 75000 |  | 75000 | -2000 |  |  | 75000 |  |  | 75000 | Full | 75000 | 0 | 73000 | 73000 | No | Green | 2023-02-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-10-31 |  |  |  | 2000 | -2000 | [11 empty] | 73000 |  |  |  |  | 5/1/2023 integrity has not provided preference on smart tool for this line. Will proceed with hydrotesting using Shultz construction 4/3/23 walked down with operations and contractor. This line has traps on both ends and was constructed in 2018. Integrity has been notified so as to updated data. 3/31/2023 walked down with operations and contractor. This line has traps on both ends and was constructed in 2018. Integrity has been notified so as to updated data. 3/2/23 planned assessment is 9/30/23 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | EG - EAST CHICAGO STA (NORCO) |  | 0 | 0 | 73000 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44680 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 EH999A4 - Pressure Test | Item | Open | MEXP | EH999A4E2301 | Maintenance Framework | 2075742 | Lloyd, Andrew | West | 3. Active | Defined | Assessments | 34729 | 157200 |  | 191929.04 | 137621 | 54308 | Red | 135000 |  | 135000 | 56929 |  |  | 135000 |  |  | 135000 | Full | 135000 | 34729 | 157200 | 191929 | Yes | Red | 2023-02-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-03-31 |  |  |  | 2000 | -257.91 | 32986.95 | 32836 | 32836 | 151 | Yellow |  |  | 136000 | 21200 | [7 empty] | 5/1/2023 crew has mobilized to site, dewatering significant, project on track for hydrotest 5/3 and refill by end of week. 4/28/23 kick off held, executing project 5/1. Dewatering in place. 4/14 contacted ROW as there is access issue and also wet conditions that would prevent us from being able to perform this work on schedule. 4/3/23 walked down with operations and contractor earlier this year. Badger will hydrovac in April and dewatering will be placed in late april as well. Operations is ordering materials for this work. Net, project on track for execution in May. 3/31/23 walked down with operations and contractor earlier this year. Badger will hydrovac in April and dewatering will be placed in late april as well. Operations is ordering materials for this work. Net, project on track for execution in May. 3/2/23 project on track for execution. 1/24/23 walked down line with operations and contractor, project on track for execution. Hydrotest work to end 5/5/23 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | EH999A4 - HAMMOND - HAMMOND EAST BADGER |  | 1742 | 190187 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44681 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 HC168HD - ILI | Item | Open | MEXP | HC168HDE2301 | Exempt | 2075711 | Lloyd, Andrew | West | 3. Active | Defined | Assessments | 2227 | 90830 |  | 93056.75 | 93056 | 1 | Yellow | 92830 |  | 92830 | 227 |  |  | 92830 |  |  | 92830 | Full | 92830 | 2227 | 90830 | 93057 | No | Green | 2023-02-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-11-30 |  |  |  | 2000 | -1688.75 | 1915.5 | 1915 | 1915 | 1 | Yellow | [8 empty] | 90830 |  |  | 5/1/23 held call with local operations on special requirements for this tool run. 4/14 survey completed 4/3 schedule change for survey, pushed to April, FCST updated. 3/31/23 schedule change for survey, pushed to April FCST updated. 3/2/23 planned assessment date is 11/14/23 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | HD168HD - ENBRIDGE-GRIFFITH TO HARTSDALE |  | 311 | 1916 |  | 90830 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44684 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 HD167HC - ILI | Item | Open | MEXP | HD167HCE2301 | Exempt | 2075712 | Lloyd, Andrew | West | 3. Active | Defined | Assessments | 2088 | 90830 |  | 92918 | 92918 | 1 | Yellow | 92830 |  | 92830 | 88 |  |  | 92830 |  |  | 92830 | Full | 92830 | 2088 | 90830 | 92918 | No | Green | 2023-02-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-11-30 |  |  |  | 2000 | -1827.5 | 1915.5 | 1915 | 1915 | 1 | Yellow | [8 empty] | 90830 |  |  | 5/1/23 held call with local operations on special requirements for this tool run. 4/14 survey completed 4/3/2023 schedule changed to April for survey, FCST updated. Invoice from contract PM received. 3/31/23 schedule changed to April for survey, FCST updated. 3/2/23 planned assessment date is 11/14/23 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | HD167HC - HARTSDALE TO ENBRIDGE-GRIFFITH |  | 173 | 1916 |  | 90830 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44685 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 KG999A3 - Pressure Test | Item | Open | MEXP | KG999A3E2301 | Maintenance Framework | 2075743 | Lloyd, Andrew | West | 3. Active | Defined | Assessments |  | 75000 |  | 75000 | 75000 | 0 | Green | 75000 |  | 75000 | 0 |  |  | 75000 |  |  | 75000 | Full | 75000 |  | 75000 | 75000 | No | Green | 2023-08-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-11-30 | [15 empty] | 75000 | [5 empty] | 5/1/2023 project on track for execution with Shultz construction. 4/3/23 status as prior 3/31/23 Walked down with operations and contractor previously. Project on track for execution in August. 3/2/23 planned assessment is 11/2/23 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | KG - LAKE GEORGE STATION |  |  | 0 | 75000 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44692 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 LA999A6 - ILI | Item | Open | MEXP | LA999A6E2301 | Exempt | 2075713 | Burns, Richard | West | 3. Active | Defined | Assessments |  | 81502 |  | 81502 | 81502 | 0 | Green | 81502 |  | 81502 | 0 |  |  | 81502 |  |  | 81502 | Full | 81502 |  | 81502 | 81502 | No | Green | 2023-06-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-06-30 | [13 empty] | 81502 | [7 empty] | 5/1/23 - no change. 4/3/23 - no change. ILI run tentatively planned for 6/6/23; deadline is 8/5/23. 3/1/23 - no change. 2/1/23 - No activity yet. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Lima Pipelines | LA999A6 - LIMA TO HUSKY 8IN |  |  | 81502 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44693 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 TU999A1 - Pressure Test | Item | Open | MEXP | TU999A1E2301 | Maintenance Framework | 2075744 | Lloyd, Andrew | West | 3. Active | Defined | Assessments | 173 | 133000 |  | 133172.5 | 133173 | 0 | Green | 133000 |  | 133000 | 173 |  |  | 133000 |  |  | 133000 | Full | 133000 | 173 | 133000 | 133173 | No | Green | 2023-03-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-07-31 |  |  |  |  | 172.5 | [10 empty] | 133000 | [5 empty] | 5/1 walked down with contractor and local operations. Project on track for execution. No issues with 3rd party access. 4/3/23 status as prior 3/31/23 walking down with operations in April. Project on track for execution 3/2/23 multiple line sizes for material list. Discussed with contactor timing and contractor will provide quote. Planned end of hydrotest work is 8/11/23 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Central-Illinois | TU999A1 |  | 173 | 0 | 133000 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44704 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 UR761NB - ILI | Item | Open | MEXP | XX761NBE2301 | Exempt | 2075714 | Lloyd, Andrew | West | 6. Operational | Defined | Assessments | 114376 | 50950 |  | 165325.79 | 173701 | -8376 | Yellow | 163799 |  | 163799 | 1527 |  |  | 163799 |  |  | 163799 | Full | 163799 | 114376 | 50950 | 165326 | No | Green | 2023-03-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-04-04 |  |  |  |  | 29952.31 | 84423.48 | 120799 | 120799 | -36376 | Red |  | Forecasting | 28000 |  | 22950 | [6 empty] | 5/1 variance is due to schedule change for survey work. contractor fabricating drain line 5/8 4/4/23 tool trapped 4/3/23 variance is due to forecast error. Status as prior 3/31/2023 stakeholders calls held, executing 4/3. 3/29/23 - entered Req. for Onstream ILI vendor into JDE. 3/3/23 FCST updated to reflect EWI 4500 cost and TIR 28K cost. 3/2/23 OM advised appropriate asset team contacts for run, will set up on going stakeholder calls to execute tool run. Quote received for tool tracking and line staking. Planned assessment date is 4/3/23 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Sugar Creek | XX761NB - MO S/L TO COUNCIL BLUFFS |  | 29952 | 112423 | 22950 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44707 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 UT534YT - ILI | Item | Open | MEXP | UT534YTE2301 | Exempt | 2075717 | Bost, Jason | West | 3. Active | Defined | Assessments |  | 94850 |  | 94850 | 94850 | 0 | Green | 94850 |  | 94850 | 0 |  |  | 94850 |  |  | 94850 | Full | 94850 |  | 94850 | 94850 | No | Green | 2023-07-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-07-31 | [14 empty] | 71138 |  |  | 23712 |  |  |  | 5/1/23 - No Change. 3/1/23 - No Change.1/31/23 - Updated forecast to reflect 75% and 25% split. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Toledo | UT534YT - TOLEDO STA TO WEST TOLEDO TERM |  |  | 0 | 71138 | 23712 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44716 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 WD202DB, DB204WJ, WJ205WW - ILI | Item | Open | MEXP | WD202DBE2301 | Exempt | 2075718 | Bost, Jason | West | 3. Active | Defined | Assessments | 54643 | 13887 | 10000 | 68529.8 | 64851 | 3679 | Yellow | 137128 |  | 137128 | -68598 |  |  | 137128 |  |  | 137128 | Full | 137128 | 54643 | 23887 | 78530 | No | Green | 2023-03-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-03-31 |  |  |  |  | 51338 | 3304.8 |  |  | 3305 | Red |  | Contractor/Vendor Issue |  |  | 13887 | [5 empty] | 10000 | 5/1/23 - Accrual is for Michael Baker invoice. 4/3/23 - Run completed on 3/21. Accrual is 75% of Onstreams PO along with Michael Bakers invoice for XYZ Survey. 3/1/23 This is Jason Bost's project now. 2/1/23 Tool run scheduled for 3/21/23 | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Wayne Pipeline | WD202DB - DETROIT TO DEARBORN-8IN |  | 51338 | 3305 | 13887 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44730 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 WF208WB - ILI | Item | Open | MEXP | WF208WBE2301 | Exempt | 2075719 | Roman, James | West | 3. Active | Defined | Assessments |  | 164168 |  | 164168 | 164168 | 0 | Green | 164168 |  | 164168 | 0 |  |  | 164168 |  |  | 164168 | Full | 164168 |  | 164168 | 164168 | No | Green | 2023-10-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-10-31 | [17 empty] | 164168 |  |  |  | 5/1/23 no change 3/1/23 Tool run scheduled for October. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Wayne Pipeline | WF208WB - FLINT TO BAY CITY |  |  | 0 |  | 164168 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44732 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 WO160AS - ILI | Item | Open | MEXP | WO160BNE2301 | Exempt | 2075721 | Lloyd, Andrew | West | 6. Operational | Defined | Assessments | 40696 | 164605 |  | 205301.48 | 203044 | 2258 | Yellow | 211327 |  | 211327 | -6026 |  |  | 211327 |  |  | 211327 | Full | 211327 | 40696 | 164605 | 205301 | No | Green | 2023-03-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-05-02 |  |  |  |  | 35438.6 | 5257.88 | 3000 | 3000 | 2258 | Red |  |  | 127072 |  |  | 37533 | [5 empty] | 5/1/2023 tool launched today at Wood River. 4/3/23 status as prior 3/31/2023 variance is due to scheduling from refinery. Gauge tool run will occur 4/17. We will execute tool launch early May in oil, 10K bbl. 3/2/2023 obtaining quote for pig sigs and replacement. Running gauge pig in April. 2/8/2023 PO issued to contractor for work, expecting march mobilization. 2/6/2023 stakeholder meeting held. Planned dates for gauge pig run is 4/17 and tool run 5/1 due to refinery issues. 1/19/23 wired pig sig lead time too long to replace pre run. Followed up with integrity for new tool vendor information. Planned assessment date is 3/12/23 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | St. Louis | WO160BN - WOOD RIVER TO BARNETT |  | 35439 | 132330 | 37533 |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44733 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 WS209WW - Seam ILI | Item | Open | MEXP | WS209WWE2301 | Exempt | 2075723 | Roman, James | West | 3. Active | Defined | Assessments |  | 334262 |  | 334262 | 318250 | 16012 | Yellow | 318250 |  | 318250 | 16012 |  |  | 318250 |  |  | 318250 | Full | 318250 |  | 334262 | 334262 | No | Green | 2023-05-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-06-30 | [12 empty] | 41000 | 221200 |  |  |  | 72062 |  |  |  | 5/1/23 Need to extend traps at WS and WW in May. Forecasting 25% of ILI Vendor cost in October. 75% of ILI cost + tracking cost in June. 3/1/23 Tool run scheduled for June. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Wayne Pipeline | WS209WW - WOODHAVEN TO WAYNE |  |  | 262200 |  | 72062 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44734 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 XF001KZ - Seam ILI | Item | Open | MEXP | XF001KZE2301 | Exempt | 2075726 | Bost, Jason | West | 3. Active | Defined | Assessments |  | 357875 |  | 357875 | 357875 | 0 | Green | 357875 |  | 357875 | 0 |  |  | 357875 |  |  | 357875 | Full | 357875 |  | 357875 | 357875 | No | Green | 2023-09-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-09-30 | [16 empty] | 268406 |  |  | 89469 |  | 5/1/23 - No Change. 4/3/23 - No Change3/1/23 - No Change.1/31/23 - Updated forecast to reflect 75% and 25% split. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Michiana | XF001KZ - GRIFFITH TO KOUTS |  |  | 0 | 268406 | 89469 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44735 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 XF001XB B-sleeve Cutouts | Item | Open | MCAP | XF001KZM2301 | Project Framework | 2112924 | Oldham, David | West | 3. Active | Defined | Pipeline Digs |  | 445001 |  | 445001 |  | 445001 | Red |  | 1000000 | 1000000 | -554999 |  |  | 56755 |  |  | 56755 | Phase | 56755 |  | 445001 | 445001 | No | Green | 2023-05-01 | 2023-04-28 | 2023-04-28 | 2023-12-31 | 1900-12-31 | [12 empty] | 2500 | 12500 | 25000 | 350000 | 55000 |  |  | 1 |  |  |  | Carter, Paige |  | West | Pipelines and Terminals | Integrity |  | Michiana | XF001KZ - GRIFFITH TO KOUTS |  |  | 15000 | 430000 | 1 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46942 |  | Meitzler, Antoinette | Independent | Aqua | 2023-04-13
2023 ZI165LI-1 - ILI | Item | Open | MEXP | ZI165CME2301 | Exempt | 2075728 | Bost, Jason | West | 3. Active | Defined | Assessments |  | 271312 |  | 271312 | 271312 | 0 | Green | 271312 |  | 271312 | 0 |  |  | 271312 |  |  | 271312 | Full | 271312 |  | 271312 | 271312 | No | Green | 2023-07-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-07-31 | [14 empty] | 203484 |  |  | 67828 |  |  |  | 5/1/23 - Asset team started gathering trap dimensions. Roberts to assist with setting AGM's and trap installation in the coming weeks. 4/3/23 - Started planning discussions with asset team. 3/1/23 - No Change.1/31/23 - Updated forecast to reflect 75% and 25% split. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Indianapolis | ZI165CM - ZIONSVILLE TO CARMEL |  |  | 0 | 203484 | 67828 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44737 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 ZI165LI-1 - Seam ILI | Item | Open | MEXP | ZI165CME2302 | Exempt | 2075731 | Bost, Jason | West | 3. Active | Defined | Assessments |  | 551468 |  | 551468 | 551468 | 0 | Green | 551468 |  | 551468 | 0 |  |  | 551468 |  |  | 551468 | Full | 551468 |  | 551468 | 551468 | No | Green | 2023-07-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-07-31 | [14 empty] | 413601 |  |  | 137867 |  |  |  | 5/1/23 - Asset team started gathering trap dimensions. Roberts to assist with setting AGM's and trap installation in the coming weeks. 4/3/23 - Started planning discussions with asset team. 3/1/23 - No Change.1/31/23 - Updated forecast to reflect 75% and 25% split. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Indianapolis | ZI165CM - ZIONSVILLE TO CARMEL |  |  | 0 | 413601 | 137867 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44738 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2023 ZI165LI-2 - ILI | Item | Open | MEXP | ZI165CME2303 | Exempt | 2075733 | Bost, Jason | West | 3. Active | Defined | Assessments |  | 181052 |  | 181052 | 181052 | 0 | Green | 181052 |  | 181052 | 0 |  |  | 181052 |  |  | 181052 | Full | 181052 |  | 181052 | 181052 | No | Green | 2023-07-01 | 2023-01-16 | 2023-01-16 | 2023-12-31 | 2023-07-31 | [14 empty] | 135789 |  |  | 45263 |  |  |  | 5/1/23 - Asset team started gathering trap dimensions. Roberts to assist with setting AGM's and trap installation in the coming weeks. 4/3/23 - Started planning discussions with asset team. 3/1/23 - No Change.1/31/23 - Updated forecast to reflect 75% and 25% split. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Indianapolis | ZI165CM - ZIONSVILLE TO CARMEL |  |  | 0 | 135789 | 45263 |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44739 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Assessments
2024 Tank support project engineering – West District | Item | Candidate | MEXP |  | Maintenance Framework |  | Roth, Aaron | West | 2. Pending AFE |  | Tank Outage |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 | [9 empty] | 100000 | 100000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 50000 | 50000 | [9 empty] | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  |  | 0 | 100000 |  |  |  | Stine, Carlton |  |  |  | 1 | 44416 |  | Guest, ProSight | Independent | Aqua | 2022-08-04 | Int - Tanks
316 CV Actuator Replacement | Item | Open | MCAP | DS00000M2203 | Maintenance Framework | 2013797 | Roknich, Hunter | West | 3. Active | Defined | Valves | 5509 | 21000 |  | 26508.71 | 24996 | 1513 | Yellow | 21000 |  | 21000 | 5509 |  |  | 48000 |  |  | 48000 | Full | 48000 | 29509 | 21000 | 50509 | No | Green | 2022-12-01 | 2022-08-28 | 2022-08-28 | 2022-12-31 | 2023-05-01 |  |  | 912 | 0.36 | 3083.73 | 1512.62 |  |  | 1513 | Red |  |  | 3000 | 18000 | [7 empty] | 5/2/2023 - Install to happen in May 4/4/2023 - Working with local ops to schedule downtime on line. Materials have been delivered. HPC to help with programming actuator. 3/2/2023 - Waiting for updated ship date. Need to order new packing for CV 2/2/2023 - Working with operations to schedule downtime for install 1/4/2023 - Working with operations to schedule downtime for install 12/2/2022 - Working for REXA order 10/3/2022 - Waiting for REXA order 9/1/22 - AFE approved. Materials ordered. 8/2/2022 - reforecasted to 2023 and moved to DD. Analysis complete. Vendor onsite to spec REXA actuator and quote 8/2 3/2/22 - Working with operations to purchase correct valve and actuator. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | DS - TOLEDO STATION |  | 3996 | 22513 |  |  | 24000 |  | Oey, Alex | Gardner, Travis W. |  |  | 1 | 37135 |  | Guest, ProSight | Independent | Aqua | 2020-07-17 | Other Programs
316 Discharge Valves Replacement | Item | Open | MCAP | DS316LRM2301 | Exempt | 2110496 | Hassan, Mohammad | West | 3. Active | Defined | Valves |  | 101000 |  | 101000 | 101000 | 0 | Green | 95000 | 6033 | 101033 | -33 |  |  | 101033 |  |  | 101033 | Full | 101033 |  | 101000 | 101000 | No | Green | 2023-11-01 | 2023-04-10 | 2023-04-10 | 2023-12-15 | 2023-10-31 | [18 empty] | 41000 | 60000 |  | 05-02-2023 - MNH - AFE approved last month. currenly working with supply chain on getting best prices and lead times for the material. Due to 29 week lead time, construction to happen in November/December. Forecast adjusted accordingly. Project EAC at $101K per the AFE. 03-31-2023 - MNH - AFE submitted to the workflow but got delayed due to ORC23B01 - Ohio Refining Co Transition IN emergent project. Due to 30 week lead time, construction to happen in November now. Forecast adjusted accordingly. Project EAC at $101K per the AFE. 02-28-2023 - MNH - Planning on submitting AFE next week. 02-01-2023 - MNH - Will work on submitting AFE this month. 01-24-2023 - MNH - Initial quotes show 30 week lead time for material. Pushing forecast out to reflect that. 01-03-2023 - MNH - Awaiting Quotes from Vendors. 12-1-2022 - MNH - Will start looking at scope of work this month. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | DS316LR - TOLEDO TO LORAIN CO. |  |  | 0 |  | 101000 |  |  | Oey, Alex | Boyer, Keith |  |  | 1 | 33964 |  | Guest, ProSight | Independent | Aqua | 2019-08-12 | Other Programs
760L IM760UGEP24A Exposure Repair | Item | Open | MEXP | IM760UGE2206 | Exempt | 2045723 | Rohr, Travis | West | 6. Operational | Drawdown | Exposed Pipe Evaluation & Remediation | 32896 |  |  | 32895.65 | 32896 | 0 | Green |  |  |  | 32896 |  |  | 49000 |  |  | 49000 | Full | 49000 | 43896 |  | 43896 | No | Green | 2022-12-01 | 2022-11-22 | 2022-11-22 | 2022-12-31 | 2023-01-13 |  |  | 32895.65 | [18 empty] | 5/2/23 Completed. 4/4/23 Completed. 3/2/23 Completed. 2/3/23 - Savings - Work completed last month. No additional billing expected.1/4/23 work started week of Dec 26. Weather stopped work at this location. After talking with Brian Hurley, work is continuing this week. 12/5/22 Work Scheduled this month. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Sugar Creek | IM760UG - MILAN STA TO SUGAR CREEK TERM |  | 32896 | 0 |  |  | 11000 |  | Hurley, Brian | Shook, Mark B. | N/A |  | 1 | 46254 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-11-22 | Int - Planned Exposures
760L MP 32.75 IM760UGEP32B Exposure Repair | Item | Open | MEXP | IM760UGE2202 | Exempt | 2036248 | Rohr, Travis | West | 6. Operational | Drawdown | Exposed Pipe Evaluation & Remediation | -325 |  |  | -324.88 | 3945 | -4270 | Red |  |  |  | -325 |  |  | 20000 |  |  | 20000 | Full | 20000 | 38519 |  | 38519 | No | Green | 2022-11-01 | 2022-10-07 | 2022-10-07 | 2022-12-31 | 2022-11-30 |  |  | -324.88 |  | 4270 | -4270 |  |  | -4270 | Red | [11 empty] | 5/2/23 Completed. 4/4/23 Completed. Found expense from another project billed to this one that will be reclassed back to the correct project. 3/2/23 Completed. 2/3/23 Completed. 1/4/23 Completed. 12/5/22 Work completed, waiting on invoice. 11/1/22 Work scheduled to take place the week of Nov 7. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Sugar Creek | IM760UG - MILAN STA TO SUGAR CREEK TERM |  | 3945 | -4270 |  |  | 38844 |  | Hurley, Brian | Shook, Mark B. | N/A |  | 1 | 46020 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-10-07 | Int - Accel Cutouts
761L MP 53.46 UD761UREP 53A Exposure Repair | Item | Open | MEXP | UD761URE2204 | Exempt | 2036242 | Rohr, Travis | West | 6. Operational | Drawdown | Exposed Pipe Evaluation & Remediation | 22813 |  |  | 22812.75 | 22813 | 0 | Green |  |  |  | 22813 |  |  | 17000 |  |  | 17000 | Full | 17000 | 56375 |  | 56375 | No | Green | 2022-12-01 | 2022-10-07 | 2022-10-07 | 2022-12-31 | 2022-12-31 |  |  | 11710.97 | 11101.78 | [17 empty] | 5/2/23 Completed. 4/4/23 Completed 3/2/23 Completed. Last of the inspector invoicing came in. 2/3/23 Inspector invoicing has come in. not waiting on any other spend. 1/4/23 Waiting on inspector invoicing. Work complete. 12/5/22 Variance was due to weather. Work started on 12/1 and will be backfilled today. 11/1/22 Scheduled for the week of Nov 28 | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Sugar Creek | UD761UR - MUDDY CREEK TO BURLINGTION JCT |  | 22813 | 0 |  |  | 33562 |  | Hurley, Brian | Shook, Mark B. | N/A |  | 1 | 46016 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-10-07 | Int - Accel Cutouts
761L UD761UREP81A Exposure Repair | Item | Open | MEXP | UD761URE2208 | Exempt | 2045744 | Rohr, Travis | West | 7. Closed | Drawdown | Exposed Pipe Evaluation & Remediation | -596 |  |  | -596.3 | -596 | 0 | Green |  |  |  | -596 |  |  | 41000 |  |  | 41000 | Full | 41000 | 14418 |  | 14418 | No | Green | 2022-12-01 | 2022-11-22 | 2022-11-22 | 2022-12-31 | 2022-12-30 |  |  | -596.3 | [18 empty] | 3/2/23 Completed. 2/3/23 Completed. 1/4/23 Work performed week of Dec. 26. Waiting on final cost. Reduction in cost due to dirt availability and not needing rock. 12/5/22 Work is scheduled for this month. waiting on invoice from second contractor. | 2023-03-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Sugar Creek | UD761UR - MUDDY CREEK TO BURLINGTION JCT |  | -596 | 0 |  |  | 15014 |  | Hurley, Brian | Shook, Mark B. | N/A |  | 1 | 46257 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-11-22 | Int - Planned Exposures
761L UG761UDEP31A Exposure Repair | Item | Open | MEXP | UG761UDE2206 | Exempt | 2045742 | Rohr, Travis | West | 7. Closed | Drawdown | Exposed Pipe Evaluation & Remediation | 11149 |  |  | 11149.08 | 11149 | 0 | Green |  |  |  | 11149 |  |  | 24000 |  |  | 24000 | Full | 24000 | 25460 |  | 25460 | No | Green | 2022-12-01 | 2022-11-22 | 2022-11-22 | 2022-12-31 | 2023-01-18 |  |  | 10871.06 | 278.02 | [17 empty] | 3/2/23 Completed. 2/3/23 Work has been completed and invoice was just submitted. Additional cost for gravel. 1/4/23 Started this one week of Dec 19, weather stopped dump trucks from hauling dirt in. 12/5/22 Work is scheduled for this month. | 2023-03-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Sugar Creek | UG761UD - SUGAR CREEK TERM - MUDDY CREEK |  | 11149 | 0 |  |  | 14311 |  | Hurley, Brian | Shook, Mark B. | N/A |  | 1 | 46255 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-11-22 | Int - Planned Exposures
761L UG761UDEP32E Exposure Repair | Item | Open | MEXP | UG761UDE2207 | Exempt | 2045743 | Rohr, Travis | West | 3. Active | Drawdown | Exposed Pipe Evaluation & Remediation |  | 15000 |  | 15000 | 15000 | 0 | Green |  |  |  | 15000 |  |  | 15000 |  |  | 15000 | Full | 15000 |  | 15000 | 15000 | No | Green | 2023-09-01 | 2022-11-22 | 2022-11-22 | 2022-12-31 | 2022-12-31 | [16 empty] | 15000 |  |  |  |  | 5/2/23 Waiting on Brian Hruley for confirmation to move forward with this one. 4/4/23 Waiting on Brian Hurley on confirmation to move forward with this one. 3/2/23 Have spoken with Brian, but still waiting on whether or not to proceed. 2/3/23 Waiting word from Brian hurley to see if we want to do this one. 1/4/23 County requested a surety bond. ROW said it would take at least a month to get. Brian Hurley said to hold off and discuss this month. 12/5/22 Work is scheduled for this month. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Sugar Creek | UG761UD - SUGAR CREEK TERM - MUDDY CREEK |  |  | 0 | 15000 |  |  |  | Hurley, Brian | Shook, Mark B. | N/A |  | 1 | 46256 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-11-22 | Int - Planned Exposures
762L MP 23.64 XX762UCEP23B Exposure Repair | Item | Open | MEXP | XX762UCE2201 | Exempt | 2036236 | Rohr, Travis | West | 6. Operational | Drawdown | Exposed Pipe Evaluation & Remediation | 2148 |  |  | 2148.26 | 1660 | 488 | Red |  |  |  | 2148 |  |  | 19000 |  |  | 19000 | Full | 19000 | 16708 |  | 16708 | No | Green | 2022-11-01 | 2022-10-07 | 2022-10-07 | 2022-12-31 | 2022-11-30 |  |  |  | 1660.26 |  | 488 |  |  | 488 | Red | [11 empty] | 5/2/23 Waiting on ROW Settlement charges to hit. 4/4/23 Waiting on ROW Settlement charges to hit. Work completed. 3/2/23 Completed. Contract ROW expense came in.2/3/23 Completed. 1/4/23 Completed. 12/5/22 Work took place week of Nov 7. No more invoices against this project. 11/1/22 Work scheduled to take place the week of Nov 7. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Sugar Creek | XX762UC - MO S/L TO CRESTON STATION |  | 1660 | 488 |  |  | 14559 |  | Hurley, Brian | Shook, Mark B. | N/A |  | 1 | 46012 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-10-07 | Int - Accel Cutouts
762L UC762OIEP61A Exposure Repair | Item | Open | MEXP | UC762OIE2202 | Exempt | 2045745 | Rohr, Travis | West | 6. Operational | Drawdown | Exposed Pipe Evaluation & Remediation | 9281 |  |  | 9281.34 | 9281 | 0 | Green |  |  |  | 9281 |  |  | 20000 |  |  | 20000 | Full | 20000 | 9281 |  | 9281 | No | Green | 2023-01-01 | 2022-11-22 | 2022-11-22 | 2022-12-31 | 2023-01-06 |  |  | 9281.34 | [18 empty] | 5/2/23 Completed 4/4/23 Completed. 3/2/23 Completed. 2/3/23 Work has been completed and billed. 1/4/23 Weather prevented us from getting dump trucks 1/2 mile off road. 12/5/22 This work is currently scheduled for this month. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Sugar Creek | UC762OI - CRESTION STA TO DES MOINES TER |  | 9281 | 0 |  |  |  |  | Hurley, Brian | Shook, Mark B. | N/A |  | 1 | 46258 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-11-22 | Int - Planned Exposures
Arc Flash Studies - 2023 MEXP - BUCKEYE PIPE LINE CO. , L.P. | Item | Open | MEXP | 1000000E2302 | Exempt | 2096287 | Hassan, Mohammad | West | 3. Active | Defined | Arc Flash | 8000 | 28750 |  | 36750 | 36750 | 0 | Green | 40000 |  | 40000 | -3250 |  |  | 36750 |  |  | 36750 | Full | 36750 | 8000 | 28750 | 36750 | No | Green | 2023-04-01 | 2023-03-24 | 2023-03-24 | 2023-09-30 | 2023-08-31 | [5 empty] | 8000 | 8000 | 8000 | 0 | Green |  |  | 8000 | 12750 | 8000 | [6 empty] | 05-02-2023 - MNH - Site visit done last week at a few sites. On track project EAC at $36750. 04-03-2023 - MNH - AFE has been approved and now working on issuing PO to contractor. Since this was a bundled project with all Arc Flash projects, individual forecasts and costs have been adjusted based on scheduled provided by the contractor. 02-28-2023 - MNH - Still awaiting quote from a 2nd contractor. Planning on submitting AFE in March. 02-01-2023 - MNH - Awaiting quote from a 2nd contractor. Moving forecast out due to delay in receiving contractor quotes. 01-03-2023 - MNH - Received a quote from one contractor and will need another quote before submitting the AFE. 12-1-2022 - MNH - Will start looking at scope of work this month. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  |  | 28750 | 8000 |  |  |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 45787 |  | Clark, David | Independent | Aqua | 2022-09-10 | Other Programs
Arc Flash Studies - 2023 MEXP - BUCKEYE PIPE LINE HOLDINGS LP | Item | Open | MEXP | 1050000E2302 | Exempt | 2096288 | Scannell, Adam | West | 3. Active | Defined | Arc Flash | 20750 | 16000 |  | 36750 | 40000 | -3250 | Yellow | 40000 |  | 40000 | -3250 |  |  | 37502 |  |  | 37502 | Full | 37502 | 20750 | 16000 | 36750 | No | Green | 2023-04-01 | 2023-03-24 | 2023-03-24 | 2023-09-30 | 2023-05-31 | [5 empty] | 20750 | 20000 | 20000 | 750 | Yellow |  |  | 16000 | [8 empty] | 04/21/23 - Arc Flash studies will kick off the week of April 24th (BTTDB) and finish the week of May 1st (DA). 03/30/23 - AFE is approved, PO items are ready to be submitted. Adam is waiting on hearing back from Antoinette regarding individual project numbers to issue the purchase orders. Will verify the schedule for the contractor is still good and will send out to stakeholders. 03/22/23 - AFE submitted to workflow on 03/20/23 02/02/23 - Working on revised quotes with contractor. Expect AFE routing by end of February. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  |  | 36750 |  |  |  |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 45788 |  | Clark, David | Independent | Aqua | 2022-09-10 | Other Programs
Arc Flash Studies - 2023 MEXP - BUCKEYE TERMINALS, LLC | Item | Open | MEXP | 1550000E2305 | Exempt | 2096280 | Hassan, Mohammad | West | 3. Active | Defined | Arc Flash | 16000 | 110000 |  | 126000 | 126250 | -250 | Yellow | 120000 |  | 120000 | 6000 |  |  | 126262 |  |  | 126262 | Full | 126262 | 16000 | 110001 | 126001 | No | Green | 2023-04-01 | 2023-03-24 | 2023-03-24 |  | 2023-08-31 | [5 empty] | 16000 | 15750 | 15750 | 250 | Yellow |  |  | 33000 | 44750 | 11500 | 14750 | 6000 |  |  |  |  | 05-02-2023 - MNH - Site visit done last week at a few sites. On track project EAC at $126K. 04-03-2023 - MNH - AFE has been approved and now working on issuing PO to contractor. Since this was a bundled project with all Arc Flash projects, individual forecasts and costs have been adjusted based on scheduled provided by the contractor. 02-28-2023 - MNH - Still awaiting quote from a 2nd contractor. Planning on submitting AFE in March. 02-01-2023 - MNH - Awaiting quote from a 2nd contractor. Moving forecast out due to delay in receiving contractor quotes. 01-03-2023 - MNH - Received a quote from one contractor and will need another quote before submitting the AFE. 12-1-2022 - MNH - Will start looking at scope of work this month. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  |  | 93750 | 32250 |  |  | 1 | Ashley, Robert | Ashley, Robert |  |  | 1 | 45775 |  | Clark, David | Independent | Aqua | 2022-09-09 | Other Programs
Arc Flash Studies - 2023 MEXP - LAUREL PIPE LINE CO., L. P. | Item | Open | MEXP | 1310000E2302 | Exempt | 2096283 | Scannell, Adam | West | 3. Active | Defined | Arc Flash |  | 35250 |  | 35250 | 30000 | 5250 | Red | 30000 |  | 30000 | 5250 |  |  | 35250 |  |  | 35250 | Full | 35250 |  | 35250 | 35250 | No | Green | 2023-05-01 | 2023-03-24 | 2023-03-24 | 2023-09-30 | 2023-06-30 | [12 empty] | 22500 | 12750 | [7 empty] | 04/21/23 - Arc Flash studies will kick off the week of May 29th (CO and PG) and finish the week of June 12th (DT). 03/30/23 - AFE is approved, PO items are ready to be submitted. Adam is waiting on hearing back from Antoinette regarding individual project numbers to issue the purchase orders. Will verify the schedule for the contractor is still good and will send out to stakeholders. 03/22/23 - AFE submitted to workflow on 03/20/23 02/02/23 - Working on revised quotes with contractor. Expect AFE routing by end of February. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  |  | 35250 |  |  |  |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 45789 |  | Clark, David | Independent | Aqua | 2022-09-10 | Other Programs
Arc Flash Studies - 2023 MEXP - WOOD RIVER PIPE LINES LLC | Item | Open | MEXP | 1200000E2302 | Exempt | 2096282 | Scannell, Adam | West | 3. Active | Defined | Arc Flash |  | 8000 |  | 8000 | 10000 | -2000 | Red | 10000 |  | 10000 | -2000 |  |  | 8000 |  | 2000 | 8000 | Full | 10000 |  | 8000 | 8000 | No | Green | 2023-07-01 | 2023-03-24 | 2023-03-24 | 2023-09-30 | 2023-07-31 | [14 empty] | 8000 | [6 empty] | 04/21/23 - Arc Flash study will be the week of June 26th. 03/30/23 - AFE is approved, PO items are ready to be submitted. Adam is waiting on hearing back from Antoinette regarding individual project numbers to issue the purchase orders. Will verify the schedule for the contractor is still good and will send out to stakeholders. 03/22/23 - AFE submitted to workflow on 03/20/23 02/02/23 - Working on revised quotes with contractor. Expect AFE routing by end of February. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Corporate | Corporate |  |  | 0 | 8000 |  |  |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 45790 |  | Clark, David | Independent | Aqua | 2022-09-10 | Other Programs
Argo Fire Water Hydrant Refurbishments 2023 | Item | Open | MCAP | BETAG00M2304 | Maintenance Framework | 2111876 | Parker, Brian | West | 3. Active | Defined | Fire Protection |  | 251623 |  | 251623 | 450000 | -198377 | Red | 450000 |  | 450000 | -198377 |  |  | 251623 |  |  | 251623 | Full | 251623 |  | 251623 | 251623 | No | Green | 2023-07-01 | 2023-04-19 | 2023-04-19 | 2023-08-31 | 2023-08-31 | [14 empty] | 125812 | 125811 | [5 empty] | 5/8/23 - Remaining funds on this project to be used to install hydrant manifold at East Chicago and Lima North fire alarm project that needs additional funding (GJ); 5/2/23 - just heard from Calumet City Plumbing today that the wrong monitor was quoted. They are sending out a revised quote and I will a CO issued to correct this. Lead time is about 10 weeks so the Jul/Aug timeframe for this work is correct.4/21/23 - removed Dec FCST of 198,377 to get rid of supplemental alert and let Greg and Travis know that the funds are available.4/12/23 - PO for warehouse stock purchase of material was issued to Calumet City Plumbing on Apr 11th.4/4/23 - no word back from stakeholders so I submitted the AFE to the workflow for routing approval today.3/24/23 - emailed SOW and AFE to stakeholders and management for their review. Adjusted FCST and moved to Dec what is available from this budget for other projects.3/7/23 - had a mtg with Calumet Plumbing to walk down the remaining work. Just waiting on two proposals now to assemble this AFE and get material ordered.2/3/23 - will be reaching out to Calumet Plumbing to obtain a "worst case" T&M estimate to refurbish or replace the hydrants/nozzles/butterfly valves in the system. Hope to be able to schedule a site visit sometime in Feb.4/13/22 - there are no extra funds available to complete this project in 2022. Pushing FCST out to 2023.4/5/22 - Calumet Plumbing had the lowest bid for this work. Assembled an AFE so I could get dollars allocated by months to confirm we can get funding for this. Will hold off on AFE submittal until funding has been confirmed. Still waiting on estimate for roll offs from Waste Management but have them estimated at $5,000/ea for qty of 8.2/8/22 - received preliminary bid document from TAS and will send this off to Matt and Greg Jakubowski for review.12/6/21 - moving FCST out to Q1 - I don't expect the completion of the SOW and the bidding process to be completed in time to get an AFE and PO issuedin the month of Dec.10/27/21 - working on scope of work so we can have Supply Chain bid this out - need to talk with GregJakubowski about bidders. | 2023-05-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Argo | BETAG - BET ARGO TERMINAL |  |  | 0 | 251623 |  |  |  | Jakubowski, Gregory | Jakubowski, Greg |  |  | 1 | 42372 |  | Guest, ProSight | Independent | Aqua | 2021-10-27 | Other Programs
Argo Regrade Parking Area | Item | Open | MCAP | BETAG00M2303 | Exempt | 2095130 | Cullison, Daniel | West | 3. Active | Defined | West |  | 84000 |  | 84000 | 84000 | 0 | Green | 84000 |  | 84000 | 0 |  |  | 81796 |  |  | 81796 | Full | 81796 |  | 84000 | 84000 | No | Green | 2023-07-01 | 2023-03-15 | 2023-03-15 | 2023-08-31 | 2023-08-31 | [14 empty] | 42000 | 42000 | [5 empty] | 4/28/23: Third quote procured last week of April. PM will analyze bids and work with Supply Chain to award to a contractor. 3/31/23: Procuring proposal from third contractor as project estimate exceeds $50k. 3/24/23: AFE approved again 3/17/23: AFE approved 3/6/23: AFE submitted 2/27/23: Quotes have been received from two contractors. AFE needs to be finalized and submitted. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Argo | BETAG - BET ARGO TERMINAL |  |  | 0 | 84000 |  |  |  | Gardner, Travis | Gardner, Dale | N/A |  | 1 | 24858 |  | Guest, ProSight | Independent | Aqua | 2017-08-07 | Other Programs
Argo Secondary Containment Improvements | Item | Open | MEXP | BETAG00E2202 | Maintenance Framework | 1970920 | Parker, Brian | West | 3. Active | Defined | Secondary Containment |  | 76000 |  | 76000 | 84983 | -8983 | Red | 120000 |  | 120000 | -44000 |  |  | 1000 | 100000 |  | 101000 | Phase | 101000 | 1017 | 76000 | 77017 | No | Green | 2022-10-01 | 2022-04-08 | 2022-04-08 | 2023-05-31 | 2023-07-31 | [12 empty] | 67000 |  | 9000 | [6 empty] | 5/8/23 - submitted inspector request today and talked with Rodney about spoils. We don't need a roll off for any spoils and this work should be completed in < 5 days. EAC is at 77,000. 4/28/23 - looks like Mills is planning to start this work week of May 15th. 4/7/23 - received SSSP from Mills and sent to Mac for review. I think this project is about 1 week in duration so reducing inspection FCST. Expect this to start no later than May. 4/1/23 - waiting on SSSP from Mills Excavating. Talked with him last week of Mar to obtain status of this plan. 2/28/23 - emailed SSSP and Example to Rodney Mills. 2/3/23 - will work on HASP with Mills in Feb to get HSSE approval so we can start work once the weather breaks. 1/1/23 - no change in status - work pushed out to 2023 due to weather and contractor availability. 11/30/22 - work pushed out to 2023 due to weather and contractor availability. 10/31/22 - PO issued to Mills Excavating on 10/18 - waiting to see if they can get this on their schedule for 2022 and if so, need to get HASP approved and obtain an inspector. 9/29/22 - received a bid from Helmkamp for 57,500 and Mills for 59,750. Waiting on additional proposals - if none are forthcoming will probably award this one to Mills and award 3 other bids to Helmkamp. 9/8/22 - moving this FCST out to 2023 - not 100% sure contractors are available for this work for the remainder of 2022. Will attempt to get work completed in 2022 but planning for worst case scenario since cutoff for 2023 FCST's is near. 9/3/22 - the bid event had issues and nobody from Supply Chain followed up to see how this was progressing. Wasted 1 month on this and starting the bid process over again. I will be reaching out to all bidders the week of Sep 6th to make sure they have everything they need. Still expect to complete this work in Oct. 8/1/22 - Matt requested that we wait until mid-Sep to start this work after they have removed all hydrotest water from the 160L out of tankage. Moving this FCST to Oct timeframe - work could start in mid-Sep. 7/3/22 - will be sending out IFC drawing to management for review via email. Bidding is off the table right now due to contractor availability so just plan on obtaining severalquotes from qualified vendors. 5/31/22 - have IFC drawings in hand - will complete bid document once I have all IFCdrawings in hand and have completed drawing reviews. 5/3/22 -just waiting on IFC drawings from Diamond Z for some other dike projects so we can group these together and go out for bid sometime around late Jun or early Jul. 4/5/22- submitted Phase I AFE for approval routing. | 2023-05-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Argo | BETAG - BET ARGO TERMINAL |  |  | 67000 | 9000 |  | 1017 |  | Spari, Markella | Spari, Markella |  |  | 1 | 41442 |  | Guest, ProSight | Independent | Aqua | 2021-08-13 | Other Programs
Argo Stormwater Flooding FEED | Item | Open | MCAP | BETAG00M2301 | Maintenance Framework | 2093988 | Cullison, Daniel | West | 6. Operational | Defined | Storm Water Management | 27285 |  |  | 27285 | 30000 | -2715 | Yellow | 30000 |  | 30000 | -2715 |  |  | 29887 |  |  | 29887 | Full | 29887 | 27285 |  | 27285 | No | Green | 2023-03-01 | 2023-03-06 | 2023-03-06 | 2023-04-30 | 2023-04-30 |  |  |  |  | 8000 | 19285 | 15000 | 15000 | 4285 | Red | [11 empty] | 4/28/23: -TAS completed study in April -PM compiling presentation to present to Region Leadership 3/29/23: Verifying third option with Buckeye OM and Environmental. TAS to evaluate feasibility. 3/22/23: Alternate solution provided 3/15/23: TAS provided initial solution 3/7/23: Met with TAS and Buckeye Environmental to discuss potential issues with storm water discharge 3/6/2023 Updated forecast to split cost between April and May. TAS's quote estimates a milestone review within 4 weeks of work starting and final deliverable is expected 4 weeks after agreement at milestone review. 2/27/23: A site visit was conducted with TAS Tech Consulting and OM on 2/14/23. A quote was received for the work on 2/21 and an AFE was submitted for this project on 2/24/23. Adjusted forecast from March/April to April. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Argo | BETAG - BET ARGO TERMINAL |  | 8000 | 19285 |  |  |  |  | Bonenberger, Mark | Hoekstra, Matt |  |  | 1 | 45806 |  | Clark, David | Independent | Aqua | 2022-09-12 | Other Programs
Argo Terminal Inlet Valve 30-1 Replacement | Item | Open | MCAP | AG00000M2201 | Maintenance Framework | 2053083 | Parker, Brian | West | 7. Closed | Emergent | Valves | -81158 |  |  | -81158.21 | -81158 | 0 | Green |  |  |  | -81158 |  |  | 95000 |  |  | 95000 | Full | 95000 | 0 |  | 0 | No | Green | 2022-12-01 | 2022-12-22 | 2022-12-22 | 2022-12-21 | 2022-12-20 |  |  | 4459 | 200.66 | -85817.87 | [16 empty] | 5/4/23 - saved Memo to file in both projects and emailed to Joan. Project closed out in JDE and ready to be closed by accounting. 4/1/23 - re-class was completed - just need to add a memo to file for this project that explains why this started out under business unit AG instead of PN160AG. 2/28/23 - approved Midwestern inv in late Feb - ready to close out next month. Need to confirm in OI that the full amount was processed correctly and we don't need line 2 of the PO to Midwestern. 1/30/23 - accrual names are not correct in the Cognos Report - paid GFL and valve invoices - will re-accrue 20,843.05 for Midwestern in Jan. 1/2/23 - var is due to work being completed in Dec after FCST was locked for this emergent project. Accruing the new valve 57,550, mechanical contractor, 20,843.05 and vac truck 2,610 for Dec. 12/22/22 - new valve was installed on Dec 20th. 12/15/22 - created project in OPPM and will route AFE as soon as I have a quote from Midwestern Contractors for installation. Estimate this total cost will be ~ $80,000 posting in Dec. | 2023-05-06 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Argo | AG - ARGO TERMINAL |  | -81158 | 0 |  |  | 81158 |  | Oey, Alex | Koranda, Chad E. |  |  | 1 | 46371 |  | Guest, ProSight | Independent | Aqua | 2022-12-15 | Other Programs
Argo Terminal Manifold Area Painting | Item | Open | MCAP | BETAG00M2302 | Maintenance Framework | 2094242 | Gabriel, Jeff | West | 3. Active | Defined | Facility Painting |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 |  |  | 50382 |  |  | 50382 | Full | 50382 |  | 50000 | 50000 | No | Green | 2023-07-01 | 2023-03-07 | 2023-03-07 | 2023-07-15 | 2023-07-31 | [14 empty] | 50000 | [6 empty] | 5/1/2023- No change 4/3/2023- Project awarded to CPM lowest bid. 3/2/2023- AFE is complete and is being routed for approval | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Argo | BETAG - BET ARGO TERMINAL |  |  | 0 | 50000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44363 |  | Guest, ProSight | Independent | Aqua | 2022-08-01 | Int - Planned Corr & FI
AS160HT 160L Casing VCI Fill - 2021 | Item | Open | MEXP | AS160HTE2201 | Maintenance Framework | 1956056 | Gabriel, Jeff | West | 7. Closed | Drawdown | Cathodic Protection | 8638 |  |  | 8637.64 | 8638 | 0 | Green |  |  |  | 8638 |  |  | 28000 |  |  | 28000 | Full | 28000 | 22629 |  | 22629 | No | Green | 2022-05-01 | 2022-03-15 | 2022-03-15 | 2022-10-04 | 2022-09-30 |  |  | 8637.64 | [18 empty] | 1/3/2023 - waiting for reclass to to move to other project. project.12/5/2022- awaiting reclass. should be applied in November.10/4/2022- Vance spent one day at this location. we discovered the casing was sitting on the line and there was no way to fill the casing . Rob Geib approved a casing removal project. We need to accrue $9,045 The remaining forecast of 18,995 is not needed. 9/1/2022 No change on schedule 8/3/2022 - no change in schedule 7/11/2022 - no change in schedule. 6/1/2022- May actual for end seal materials. Work Scheduled to start in September. Moved forecast 5/1/2022- Need to move forecast to August. Due to the Incident during the 160L dig. Vance would like to wait to continue work in the area 4/4/22-Vance won bid Starting in April | 2023-01-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Central-Illinois | AS160HT - AUBURN TO HARRISTOWN JCT |  | 8638 | 0 |  |  | 13991 |  | Geib, Rob | Geib, Robert |  |  | 1 | 43065 |  | Meitzler, Antoinette | Independent | Aqua | 2022-03-01 | Int - Planned Corr & FI
Bay City Station Meter Replacement | Item | Open | MCAP | WB00000M2201 | Exempt |  | Gardner, Travis | West | 6. Operational | Emergent | Measurement & Quality Control | 2669 |  |  | 2668.63 | 2669 | 0 | Green |  |  |  | 2669 |  |  | 24000 |  |  | 24000 | Full | 24000 | 16299 |  | 16299 | No | Green | 2022-12-01 | 2022-12-09 | 2022-12-09 | 2022-12-31 | 2023-03-03 |  |  | 764.07 | 63.37 | 1841.19 | 0 |  |  | 0 | Green | [11 empty] | 5/3/2023 - accruing cost for vac truck, not sure where operations charged cost too. 4/3/2023 - meter re-installed on 3/2. operational on 3/3. 1/4//2023 - Meter was installed in December but there were issue with the prover so it was removed. accruing cost for meter. 12/14/2022 - emergent project to be completed in Dec | 2023-05-03 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Pipeline | WB - BAY CITY TERMINAL |  | 2669 | 0 |  |  | 13630 |  | Hopkins, Christa | Gardner, Travis W. |  |  | 1 | 46301 |  | Gardner, Travis | Independent | Aqua | 2022-12-05 | Other Programs
Bay City Terminal Prover Actuator Gear Box Repairs | Item | Open | MEXP | WB00000E2301 | Exempt | 2083364 | Gardner, Travis | West | 6. Operational | Drawdown | West | 12340 | 1 |  | 12341 | 1 | 12340 | Red |  |  |  | 12341 |  |  | 18000 |  |  | 18000 | Full | 18000 | 12340 | 1 | 12341 | No | Green | 2023-04-01 | 2023-02-14 | 2023-02-14 | 2023-03-31 | 2023-03-31 | [5 empty] | 12340 |  |  | 12340 | Red | [9 empty] | 1 |  | 5/4/2023 - need to reclass this cost form OPEX. 3/3/2023 - emergent AFE forecast was locked when projewct was setup in OPPM. | 2023-05-03 | Griest, Barbara |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Pipeline | WB - BAY CITY TERMINAL |  |  | 12340 |  | 1 |  |  | Gardner, Travis | Gardner, Travis W. | N/A |  | 1 | 46590 |  | Gardner, Travis | Independent | Aqua | 2023-02-14 | Other Programs
BETAD - HI & HIHI Level Alarms | Item | Candidate | MCAP |  | Exempt |  | Fink, Ryan | West | 2. Pending AFE |  | Instrumentation & Controls |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 | [9 empty] | 40000 | 40000 | No | Green | 2023-08-01 |  |  |  | 2023-06-30 | [15 empty] | 40000 | [5 empty] | 5/2 RRF - Cancelled - funding to go to WS Tank Acutator project. moved fcst to Aug. 4/21/23 - FF - Will remove forecasted values for May/June and release funds for Actuator Upgrade. OPPM entry will then be cancelled. 4/6 RRF - project completed. may need funds for other Detroit area project (BETWS Broadway Tank Valve Actuator Upgrade - Phase 1 FEED - OPPM ID 31591) 3/2 RRF - Done in 2022, will confirm nothing else needed, then return funds. EAC $0 2/13 RRF - May have been completed in 2022, Verify before reducing forecast. EAC $0 2/2 RRF - feb refine scope, March site visit | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETAD - BET TAYLOR EAST TERMINAL |  |  | 0 | 40000 |  |  |  | Forsey, Frank |  |  |  | 1 | 44238 |  | Guest, ProSight | Independent | Aqua | 2022-07-25 | Other Programs
BETAD Dike Access Platforms | Item | Open | MEXP | BETAD00E2302 | Exempt | 2119868 | Roman, James | West | 3. Active | Defined | West |  | 25900 |  | 25900 | 25000 | 900 | Yellow | 28000 |  | 28000 | -2100 |  |  | 25285 |  |  | 25285 | Full | 25285 |  | 53900 | 53900 | Yes | Red | 2023-05-01 | 2023-05-03 | 2023-05-03 | 2023-05-29 | 2023-04-30 | [6 empty] | 0 | 0 | 0 | Green |  |  | 25900 | 0 | [7 empty] | 5/1/23 AFE was submitted 4/24/23. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Terminals | BETAD - BET TAYLOR EAST TERMINAL |  |  | 25900 |  |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 44208 |  | Guest, ProSight | Independent | Aqua | 2022-07-22 | Other Programs
BETAK MAIN POWER BREAKER | Item | Open | MCAP | BETAK00M2207 | Maintenance Framework | 2011270 | Fink, Ryan | West | 7. Closed | Defined | Electrical | 3718 |  |  | 3717.53 | 3718 | 0 | Green |  |  |  | 3718 |  |  | 15000 |  |  | 15000 | Full | 15000 | 3811 |  | 3811 | No | Green | 2022-12-01 | 2022-08-03 | 2022-08-03 | 2022-10-07 | 2023-01-27 |  |  | 4093.44 | 155.55 | -531.46 | [16 empty] | 4/10 RRF - CLosed 4/7 RRF - EAC $4k 3/27 RRF - SPi invoice received $3469. Wait for charges to hit project and close. EAC $4k 3/2 RRF - done pending invoice from SPi and close. EAC $4700. 2/2 RRF - breaker install completed on 1/27. Accrue 4000 to SPI jan. 1/4/23 RRF - waiting on utility for outage, moved install costs to Feb. dropped mat costs, left on local budget. 12/1 RRF - Install dependent on utility outage schedule. Project underspent since we were able to purchase used parts at a lower cost. EAC $7300 10/31 RRF - Install pending utility outage. Plan for mid Nov. Dec material and contingency 9/28 RRF - SPi scheduling with Utility Co, for power outage to install breakers, Planned for October. 9/3 RRF - Moved 3k contingency to Dec, release after work complete. 9/2 RRF - Parts arrived, PO for labor sept. 8/1 RRF - AFE submitted, material order when approved. 7/22 RRF - estimates refreshed, short lead time on parts. AFE to be submitted 7/11 RRF - Scope and estimate July. Moved $ to Sept | 2023-04-10 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | West Shore Terminals | BETAK - BET GRANVILLE |  | 3718 | 0 |  |  | 93 |  | Ashley, Robert | Koranda, Chad E. | N/A |  | 1 | 40479 |  | Guest, ProSight | Independent | Aqua | 2021-07-02 | Other Programs
BETCX EROSION AT FENCE LINE | Item | Open | MCAP | BETCX00M2303 | Exempt | 2109805 | Smith, Kyle | West | 3. Active | Defined | West |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 |  |  | 39984 |  |  | 39984 | Full | 39984 |  | 40000 | 40000 | No | Green | 2023-07-01 | 2023-04-04 | 2023-04-04 | 2023-05-30 | 2023-08-31 | [14 empty] | 20000 | 20000 | [5 empty] | 4/28/23 PO cut to Degen. | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Southern Ohio | BETCX - BET CINCINNATI TERMINAL |  |  | 0 | 40000 |  |  |  | Gardner, Travis | Gardner, Dale |  |  | 1 | 37686 |  | Guest, ProSight | Independent | Aqua | 2020-08-12 | Other Programs
BETEH Tank 50 CP Deep Well Installation | Item | Candidate | MCAP |  | Exempt |  | Logan, Rob | West | 2. Pending AFE |  | Cathodic Protection |  | 35000 |  | 35000 | 35000 | 0 | Green | 35000 |  | 35000 | 0 | [9 empty] | 35000 | 35000 | No | Green | 2023-06-01 |  |  |  | 2023-06-30 | [13 empty] | 35000 | [7 empty] | 05/01/2023 Requesting Quote From National Pipeline 04/03/2023 Seeking second quote per Buckeye policy 3/02/2023 Pending AFE Have received one bid for project to date 2/2/2023 Pending AFE Contractor visited site 1/2023 | 2023-05-01 |  |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  |  | 35000 |  |  |  |  | Geib, Rob |  |  |  | 1 | 45727 |  | Logan, Rob | Independent | Aqua | 2022-08-30 | Int - Planned Corr & FI
BETEU I Rod installation | Item | Open | MCAP | BETEU00M2307 | Exempt |  | Logan, Rob | West | 3. Active | Defined | Atmospheric Corrosion |  | 13689 |  | 13689 | 12000 | 1689 | Red | 10000 | 3689 | 13689 | 0 |  |  | 13689 |  |  | 13689 | Full | 13689 |  | 13689 | 13689 | No | Green | 2023-06-01 | 2023-04-14 | 2023-04-14 | 2023-05-23 | 2023-06-30 | [13 empty] | 12000 | 1689 | [6 empty] | 5/01/2023 Pending PO to CPM Confirmed start date 6/24/2023 due to contractor avai. 04/03/2022 AFE out for Approval 03/02/2023 AFE to be submitted the week of 03/02/2023 | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  |  | 12000 | 1689 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45690 |  | Logan, Rob | Independent | Aqua | 2022-08-29 | Int - Planned Corr & FI
BETEU TK 240 2022 Reclass | Item | Open | MEXP | BETEU00E2209 | Maintenance Framework | 2096643 | Roth, Aaron | West | 3. Active | Drawdown | Tanks | 0 |  |  | 0 | 8460 | -8460 | Red | 290000 |  | 290000 | -290000 |  |  | 290000 |  |  | 290000 | Full | 290000 | 0 |  | 0 | No | Green | 2023-03-01 | 2023-03-31 | 2023-03-31 | 2023-04-01 | 2023-04-01 |  |  |  |  | 8460 | -8460 |  |  | -8460 | Red | [13 empty] | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  | 8460 | -8460 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46811 |  | Meitzler, Antoinette | Independent | Aqua | 2023-03-20
BETGF Cleveland Terminal Canopy Repairs | Item | Candidate | MEXP |  | Maintenance Framework |  | Roknich, Hunter | West | 5. Deferred | Defined | Truck Racks |  |  |  | 0 |  | 0 | Green | 48000 |  | 48000 | -48000 | [9 empty] | 60000 | 60000 | No | Green | 2024-06-01 |  |  |  | 2024-06-30 | [21 empty] | 3/27/2023 - this project has been deferred to 2024 per request from leadership team. | 2023-03-27 |  |  | West | Pipelines and Terminals | Station/Terminal |  | North East Ohio | BETGF - BET CLEVELAND TERMINAL |  |  | 0 |  |  |  | 60000 | Younce, Michael |  |  |  | 1 | 34551 |  | Guest, ProSight | Independent | Aqua | 2019-08-27 | Other Programs
BETHT Bay 1 Concrete STFs Refurbishment | Item | Open | MCAP | BETHT00M2202 | Maintenance Framework | 2023929 | Scannell, Adam | West | 6. Operational | Defined | West | 202 |  |  | 202.11 | 202 | 0 | Green |  |  |  | 202 |  |  | 78000 |  |  | 78000 | Full | 78000 | 36930 |  | 36930 | No | Green | 2022-11-01 | 2022-09-29 | 2022-09-29 | 2022-11-30 | 2022-10-31 |  |  | 152.11 | 50 | [17 empty] | 12/05/22 - Contractor is finishing up this week. 11/02/22 - Contractor changed, and is on site working. Scope was reduced. Variance for October forecast is not used. updated scope and contractor change reduced cost significantly 10/04/22 - AFE approved. Scope review in progress and work ready to start after approval. 07/22/22 - Waiting on bid. AFE to be submitted beginning of August. | 2022-12-07 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Central-Illinois | BETHT - BET HARRISTOWN TERMINAL |  | 202 | 0 |  |  | 36728 |  | Gardner, Travis | Hoekstra, Matt |  |  | 1 | 41632 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
BETHY - Kiosk for Butane Offloading | Item | Candidate | MCAP |  | Maintenance Framework |  | Roknich, Hunter | West | 2. Pending AFE |  | Truck Racks |  | 20000 |  | 20000 | 20000 | 0 | Green | 20000 |  | 20000 | 0 | [9 empty] | 20000 | 20000 | No | Green | 2023-08-01 |  |  |  | 2023-04-30 | [15 empty] | 20000 | [9 empty] | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  |  | 0 | 20000 |  |  |  | Younce, Michael |  |  |  | 1 | 44237 |  | Guest, ProSight | Independent | Aqua | 2022-07-25 | Other Programs
BETHY Dike Drainage | Item | Open | MCAP | BETHY00M2107 | Maintenance Framework | 1915685 | Roknich, Hunter | West | 6. Operational | Unplanned | Secondary Containment | 184 |  |  | 184.3 | 184 | 0 | Green |  |  |  | 184 |  |  | 75000 |  | 30000 | 75000 | Full | 105000 | 108832 |  | 108832 | No | Green | 2021-12-01 | 2021-12-06 | 2021-12-06 | 2021-12-31 | 2022-11-30 |  |  | 184.3 | [18 empty] | 11/2/2022 - Work complete 10/3/2022 - PO issued to Hatzel Buehler. Working on scheduling to finish work 9/2/2022 - Supplemental will be required to complete electrical install. Unexpected conduit corrosion (approx. 235') needs replaced and will exceed AFE threshold. Working with program owner and vendor. Expected project completion early October. 8/2/2022 - Supplemental will be required to complete electrical install. Unexpected conduit corrosion (approx. 235') needs replaced and will exceed AFE threshold. Working with program owner and vendor. Expected project completion late August. 7/5/2022 - Supplemental will be required to complete electrical install. Unexpected conduit corrosion (approx. 235') needs replaced and will exceed AFE threshold. Working with program owner and vendor. Expected project completion late July. 6/2/2022 - Construction was delayed due to contractor availability. Start date 6/6/2022. 5/3/2022 - Construction to be completed in late May 4/4/2022- Insulation and heat tracing connection to be completed in May 3/2/22 - Operations wants the work completed in May. 2/2/22 - Waiting for better weather to complete heat trace and insulation 1/4/2022 - Mechanical work completed and all materials purchased. Variance due to delay in work from unforeseen weather conditions. Dikes are flooded and create a hazardous work area. Will need to wait until flooding has subsided to finish work 12/2/2021 - AFE in approval process. Work to begin as soon as AFE is approved 11/2/2021 - Contractor's have made site visit. Bids to be in by 11/5. AFE to follow. Work to begin 12/1 10/4/2021 - Received pictures regarding project. Working on project scope. | 2022-11-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  | 184 | 0 |  |  | 50586 |  | Clark, Dave | Gardner, Travis W. | N/A |  | 1 | 31561 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Other Programs
BETHY Rectifier Repair | Item | Open | MEXP | BETHY00E2303 | Maintenance Framework | 2095212 | Brown, Jeff | West | 3. Active | Drawdown | Cathodic Protection |  | 15000 |  | 15000 | 15000 | 0 | Green |  |  |  | 15000 |  |  | 15000 |  |  | 15000 | Full | 15000 |  | 15000 | 15000 | No | Green | 2023-07-01 | 2023-03-17 | 2023-03-17 | 2023-12-31 | 2023-12-31 | [14 empty] | 7500 |  |  |  |  | 7500 |  | 5-1-23 Projected Ongoing repairs through-out the year. 4-3-23 PROJECTED ONGOING REPAIRS THROUGH-OUT THE YEAR | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  |  | 0 | 7500 | 7500 |  |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 46806 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-03-17
BETHY TANK DIKE INSTALL CASE END SEALS | Item | Open | MEXP | BETHY00E2201 | Maintenance Framework | 1970002 | Brown, Jeff | West | 7. Closed | Drawdown | Atmospheric Corrosion | 257 |  |  | 257.29 | 257 | 0 | Green |  |  |  | 257 |  |  | 17000 |  |  | 17000 | Full | 17000 | 17164 |  | 17164 | No | Green | 2022-04-01 | 2022-04-01 | 2022-04-01 | 2022-12-31 | 2022-06-02 |  |  | 257.29 | [18 empty] | 7/5/2022 - someone accrued Herbst Electric to this project and then it was reversed out in June. 6/2/22- work completed. ready to close. 5/2/2022 - materials purchased. 4/4/2022 - drawdown project scheduled for July | 2022-07-05 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  | 257 | 0 |  |  | 16907 |  | Geib, Rob | Shook, Mark B. | N/A |  | 1 | 43332 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-04-01 | Int - Planned Corr & FI
BETIT TANK DIKE CASE END SEAL PROJECT | Item | Open | MEXP | BETIT00E2201 | Maintenance Framework | 1970003 | Brown, Jeff | West | 7. Closed | Drawdown | Atmospheric Corrosion | 232 |  |  | 231.81 | 232 | 0 | Green |  |  |  | 232 |  |  | 17000 |  |  | 17000 | Full | 17000 | 16345 |  | 16345 | No | Green | 2022-04-01 | 2022-04-01 | 2022-04-01 | 2022-12-31 | 2022-06-02 |  |  | 231.81 | [18 empty] | 6/2/22- work completed. ready to close. 5/2/2022 - materials purchased. 4/4/2022 - drawdown project scheduled for July | 2022-06-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Wayne Terminals | BETIT - BET DEARBORN |  | 232 | 0 |  |  | 16114 |  | Geib, Rob | Shook, Mark B. | N/A |  | 1 | 43334 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-04-01 | Int - Planned Corr & FI
BETLI Creek Walking Bridges | Item | Open | MCAP | BETLI00M2205 | Maintenance Framework | 2023046 | Roknich, Hunter | West | 6. Operational | Defined | West | 7781 |  |  | 7780.85 | 551 | 7230 | Red |  |  |  | 7781 |  |  | 33000 |  |  | 33000 | Full | 33000 | 37306 |  | 37306 | Yes | Red | 2022-11-01 | 2022-09-19 | 2022-09-19 | 2022-12-31 | 2022-12-31 |  |  | 550.85 | 0 | 0 | 7230 |  |  | 7230 | Red | [11 empty] | 1/4/2023 - Work complete 12/2/2022 - Work scheduled for 12/19. Purchase order has been issued. Fabrication in process. 10/3/2022 - Work scheduled for early November 8/2/2022 - Quote received. Scope in review process. AFE to be submitted after review. Estimated work completion late September/Early october. | 2023-01-04 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Terminals | BETLI - BET LIMA SOUTH TERMINAL |  | 551 | 7230 |  |  | 29525 |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 41208 |  | Guest, ProSight | Independent | Aqua | 2021-08-09 | Other Programs
BETML Roof Repairs MCC Building | Item | Candidate | MCAP |  | Exempt |  | Roknich, Hunter | West | 2. Pending AFE |  | West |  | 28000 |  | 28000 | 28000 | 0 | Green | 28000 |  | 28000 | 0 | [9 empty] | 56000 | 56000 | No | Green | 2023-08-01 |  |  |  | 2023-03-31 | [15 empty] | 28000 | [9 empty] | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETML - BET MARSHALL TERMINAL |  |  | 0 | 28000 |  |  |  | Gardner, Travis |  |  |  | 1 | 44207 |  | Guest, ProSight | Independent | Aqua | 2022-07-22 | Other Programs
BETNB Cathodic Protection Header Cable reroute | Item | Candidate | MEXP |  | Exempt |  | Rohr, Travis | West | 2. Pending AFE |  | Cathodic Protection |  | 20000 |  | 20000 | 20000 | 0 | Green | 20000 |  | 20000 | 0 | [9 empty] | 20000 | 20000 | No | Green | 2023-06-01 |  |  |  | 2023-06-30 | [13 empty] | 20000 | [7 empty] | 5/2/23 Meeting contractor onsite Friday for estimate. 4/4/23 getting second estimate due to cost.3/2/23 Have met with contractor and am waiting for estimate. 2/3/23 Met with local OPS and laid out scope of work and have reached out to contractors for bid. | 2023-05-02 |  |  | West | Pipelines and Terminals | Corrosion |  | Sugar Creek | BETNB - BET COUNCIL BLUFFS |  |  | 20000 |  |  |  |  | Geib, Rob |  |  |  | 1 | 45445 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
BETND - FRP Installations - 2022 | Item | Candidate | MCAP |  | Exempt |  | Gremer, Michael | West | 2. Pending AFE |  | Atmospheric Corrosion |  | 45000 |  | 45000 | 45000 | 0 | Green | 45000 |  | 45000 | 0 | [9 empty] | 45000 | 45000 | No | Green | 2023-09-01 |  |  |  | 2023-10-31 | [16 empty] | 25000 | 20000 |  |  |  | 5/2/23 - PM to set up site visit with contractors. 4/4/23 - PM working on scope of work. 3/2/23 - PM working on scope of work. 2/3/23 - PM working on scope of work. | 2023-05-02 |  |  | West | Pipelines and Terminals | Integrity |  | Coraopolis | ND - INDIANOLA TERMINAL |  |  | 0 | 25000 | 20000 |  |  | Geib, Rob |  |  |  | 1 | 41449 |  | Guest, ProSight | Independent | Aqua | 2021-08-16 | Int - Planned Corr & FI
BETND Indianola Bridge Study | Item | Open | MCAP | BETND00M2302 | Exempt | 2111166 | Roman, James | West | 3. Active | Defined | West | 11000 | 17000 |  | 28000 | 30000 | -2000 | Yellow | 50000 |  | 50000 | -22000 |  |  | 36267 |  |  | 36267 | Full | 36267 | 11000 | 17000 | 28000 | No | Green | 2023-04-01 | 2023-04-17 | 2023-04-17 | 2023-05-31 | 2023-05-31 | [5 empty] | 11000 |  |  | 11000 | Red |  | WorkAhead of Schedule | 17000 | 0 | [7 empty] | 5/2/23 - Variance +$11,000. Started work ahead of schedule. 4/5/23 - Visited site with engineer. Scheduled to get their proposal this week. Will submit AFE and get started. Initial site visit did not show anything critical. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Coraopolis | ND - INDIANOLA TERMINAL |  |  | 28000 |  |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 44244 |  | Guest, ProSight | Independent | Aqua | 2022-07-26 | Other Programs
BETND Indianola Oil/Water separator replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Roknich, Hunter | West | 2. Pending AFE |  | Storm Water Management |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 | [9 empty] | 40000 | 40000 | No | Green | 2023-06-01 |  |  |  | 2023-05-31 | [13 empty] | 20000 | 20000 | [10 empty] | West | Pipelines and Terminals | Operating Infrastructure |  | Coraopolis | ND - INDIANOLA TERMINAL |  |  | 20000 | 20000 |  |  |  | Bonenberger, Mark |  |  |  | 1 | 44214 |  | Guest, ProSight | Independent | Aqua | 2022-07-22 | Other Programs
BETNT pipe painting and I-Rod installation | Item | Open | MEXP | BETNT00E2201 | Maintenance Framework | 2002347 | Smith, Kyle | West | 6. Operational | Defined | Atmospheric Corrosion | -3375 |  |  | -3375.02 | -3375 | 0 | Green |  |  |  | -3375 |  |  | 40000 |  | 12650 | 52650 | Supplemental | 52650 | 56945 |  | 56945 | No | Green | 2022-09-01 | 2022-07-08 | 2022-07-08 | 2022-12-31 | 2022-09-30 |  |  |  |  | -3375.02 | [16 empty] | 10/1/22 Work Completed in Sept. Work Order and PO Closed | 2022-10-24 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Michiana | BETNT - BET NILES WEST TERMINAL |  | -3375 | 0 |  |  | 60320 |  | Geib, Rob | Geib, Robert |  |  | 1 | 38111 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Int - Planned Corr & FI
BETON Canton Accuload to Multiload Upgrades | Item | Open | MCAP | BETON00M2302 | Maintenance Framework | 2109916 | Fink, Ryan | West | 3. Active | Defined | Truck Racks |  | 122000 |  | 122000 | 122000 | 0 | Green | 93000 |  | 93000 | 29000 |  |  | 122708 |  |  | 122708 | Phase | 122708 |  | 122000 | 122000 | No | Green | 2023-07-01 | 2023-04-04 | 2023-04-04 | 2023-08-15 | 2023-06-30 | [14 empty] | 11000 | 62000 | 21000 | 20000 | 4000 | 4000 |  | 4/28 RRF - Wait on updated quote from Triad, moved fcst out 1 mo. EAC $122k 4/6 RRF - AFE approved. EAC $122k 3/10 RRF - Going forward with Design for all 6 lanes, and FCM cab purchase. Ph1 EAC $122k. 3/1 RRF - underbudgeted for full upgrade (6 lanes), reducing to 2 lanes. Material and design 82k Ph1, Install 49k Ph2, Ctgcy 11k. EAC 142k. 2/2 RRF - Triad working on material list for quotes to create AFE ph1 1/23 RRF - orig budget 93k, possible add fiber | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | North East Ohio | BETON - BET CANTON |  |  | 0 | 94000 | 28000 |  |  | Younce, Michael | Younce, Michael |  |  | 1 | 37878 |  | Guest, ProSight | Independent | Aqua | 2020-08-13 | Other Programs
BETON CANTON Detonation Arrestor Installation | Item | Open | MCAP | BETON00M2201 | Maintenance Framework | 1971003 | Roknich, Hunter | West | 3. Active | Defined | Vapor Management | 18188 | 130000 |  | 148188.48 | 140387 | 7801 | Yellow | 130000 |  | 130000 | 18188 |  |  | 74000 |  |  | 74000 | Phase | 74000 | 88728 | 130000 | 218728 | No | Green | 2022-04-01 | 2022-04-12 | 2022-04-12 | 2022-10-31 | 2023-07-31 |  |  | 1714.58 | 70.17 | 8602.74 | 7800.99 |  |  | 7801 | Red |  |  |  |  | 65000 | 65000 | [5 empty] | 5/2/2023 - Design review complete. Changes needing to be made to design. Completing another backpressure analysis with proposed design. Site walk scheduled for 5/3 to determine if there is better design for DA orientation 4/4/2023 - See below 3/2/23 - mrk - moved forecast from may/june, to june/july to accomodate time for bid event. 3/2/2023 - IFR drawings have been received. Will hold design review with stakeholders in coming weeks. 2/2/2023 - IFR drawings have been received. Will hold design review with stakeholders in coming weeks. 1/4/2023 - Engineering IFR drawings still in progress. DA's purchased. 12/2/2022 - Engineering IFR drawings in progress. Receiving bids for all valves and DA's to be purchased CY 10/3/2022 - Vapor drop engineering complete. DA sizing complete. Sending out for bid for DA's. Diamond Z to survey for engineered drawings. 9/2/2022 - Should have Detonation arrestor sizing by 9/9. Waiting on estimate from Diamond Z for survey and engineered drawings. Reforecasted to include engineering and material purchasing CY. Construction to occur CY+1. 8/2/2022 - Prelim engineering in progress 7/5/2022 - Prelim engineering in progress 6/2/2022 - Measurements have been taking for backpressure calculations. Plan to order detonation arrestors late June. 5/3/22 - Preliminary engineering in progress 3/2/22 - Phase I AFE will be submitted in March. Quote received for prelim engineering. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | North East Ohio | BETON - BET CANTON |  | 10387 | 7801 | 130000 |  | 70540 |  | Karl, Marissa | McHugh, Neal |  |  | 1 | 37653 |  | Guest, ProSight | Independent |  | 2020-08-11 | Other Programs
BETON CANTON TERMINAL Tank Gauging Project | Item | Open | MCAP | BETON00M2202 | Maintenance Framework | 2013128 | Fink, Ryan | West | 3. Active | Defined | Instrumentation & Controls | 20032 | 80000 |  | 100031.96 | 97025 | 3007 | Yellow |  |  |  | 100032 |  |  | 85000 |  | 28000 | 85000 | Full | 113000 | 35852 | 80000 | 115852 | No | Green | 2022-10-01 | 2022-08-23 | 2022-08-23 | 2022-10-21 | 2023-05-26 |  |  | 805.27 | 327.03 | 892.38 | 18007.28 | 15000 | 15000 | 3007 | Red |  |  | 55000 | 9000 | 16000 | [6 empty] | 4/28 RRF - in progress, CO for SumpHL $3.7k. Trouble with old JBs. Startup May. EAC $117k 4/6 RRF - in progress, may need CO, still within budget. EAC $113k 3/28 RRF - start work 3/29, EAC $103k 3/23 RRF - Kickoff meeting 3/28. Level Xmtrs arrived. EAC $103k 3/2 RRF - Abbott attended PIC training last week. Confirm then schedule installation. EAC $103k 2/1 RRF - partial equipment delivery, 1/4/2023 RRF - Supp AFE approved, Varec equip accrue $14432 12/9 RRF - ECO requirement communicated to PMO. Submitting project change order to Remedy 12/1 RRF - Change order requested, 11/4 RRF - Abbott missed PIC training, none til 2023, postponing to 2023 11/1 RRF - Abbott PIC training early Nov then start 10/10 RRF - Delayed, sched with contractor 9/30 RRF - PO to Abbott, sched start and PIC training 9/5 RRF - AFE approve, pending additional bids for elec. 8/2 RRF - Estimate received last week, higher than expected, forecast 71k, AFE this week 7/5 RRF - Site visit 7/6 for electrical estimate, AFE to follow 05-19-2022 MNH - moved out one month due to current project workload. 3/25/2022 RRF - moved out one month, pending estimates for AFE | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | North East Ohio | BETON - BET CANTON |  | 2025 | 82007 | 16000 |  | 15820 |  | Forsey, Frank | Gardner, Travis W. |  |  | 1 | 34427 |  | Guest, ProSight | Independent | Aqua | 2019-08-24 | Other Programs
BETOR Lorain Replace Truck Rack Wiring | Item | Open | MCAP | BETOR00M2201 | Maintenance Framework | 2022482 | Fink, Ryan | West | 3. Active | Defined | Instrumentation & Controls | 13540 | 143000 |  | 156540.37 | 156391 | 150 | Yellow | 155000 |  | 155000 | 1540 |  |  | 74000 |  |  | 74000 | Phase | 74000 | 31509 | 143000 | 174509 | No | Green | 2022-11-01 | 2022-09-12 | 2022-09-12 | 2022-08-31 | 2023-08-31 |  |  | 12532.19 | 711.79 | 146.71 | 149.68 |  |  | 150 | Red |  |  |  |  | 10000 | 28000 | 44000 | 55000 | 6000 |  |  | 5/2 RRF - finsih ph2 AFE, EAC $175k 4/7 RRF - EAC $175k 3/2 RRF - sched review and proceed, EAC $175k, 155k 2023. 2/1 RRF - design pending review 1/3/23 RRF - Design in progress, 75% complete. Accrue 12k Dec. Moved $7500 to Jan/Feb 12/1 RRF - Design started, accrue 9k Nov. 11/1 RRF - Eng and Dwgs 10/4 RRF - Approved and engineering started 9/2 RRF - AFE for eng Sept. 8/2 RRF - RFQ for engineering only, will update after review 8/3. 7/21 RRF - revise to PLC upgrade project, phase 1 eng, possibly install fiber. 7/1 RRF - needs engineering, Phase 1 AFE to determine best use of funding, PLC upgrade may eliminate need for most wiring and leave many spares. 6/1 RRF - site visit done, RFQs for AFE. 05-19-2022 - Delay in submitting AFE, Moved June $4K into Julys forecast. 5/3 RRF - site visit sched early may, and AFE 2/23 RRF - moved out 2/2 RRF - init | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | North East Ohio | BETOR - BET LORAIN |  | 13391 | 150 | 82000 | 61000 | 17968 |  | Forsey, Frank | Forehand, Adam |  |  | 1 | 34416 |  | Guest, ProSight | Independent | Aqua | 2019-08-24 | Other Programs
BETST VRU Level Transmitter Replacement | Item | Open | MCAP | BETST00M2203 | Maintenance Framework | 1957590 | Scannell, Adam | West | 6. Operational | Emergent | Vapor Management | 1288 |  |  | 1287.65 | 1288 | 0 | Green |  |  |  | 1288 |  |  | 22000 |  |  | 22000 | Full | 22000 | 18569 |  | 18569 | No | Green | 2022-05-01 | 2022-03-31 | 2022-03-31 | 2022-06-30 | 2022-06-30 |  |  | 0 | 0 | 1287.65 | [16 empty] | 10/14/22 - Work completed on 10/14.Waiting for invoices to close. 10/04/22 - John Zink has received the transmitter. Scheduling replacement for 10/14/22. 09/02/22 - Waiting on confirmation for shipping. Planning to have John Zink tech install as soon as it is received. Target from last discussion with JZ is second week of Sept. 08/02/22 - Waiting on delivery of transmitter. Expected delivery 8/19/22. 07/01/22 - Currently, Rosemount is running way behind on their orders, with the 3051’s running anywhere between 8-12 weeks late. The last update we got from them (a couple of weeks ago) had the current promise date at 8/19. Forecast is due to expected delivery this month before receiving notice of supply chain issues. 06/02/22 - Waiting on transmitter delivery and John Zink Tech schedule for installation. 05/04/22 - Expected delivery of transmitter is late May. Install to be scheduled for early June. 04/04/22 - Emergent project, AFE approved. PO is issued to John Zink and scope reviewed by Chelsea Schumacher. I will follow up on expected delivery/completion this week. Expected 8-10 weeks | 2022-10-19 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | St. Louis | BETST - BET ST LOUIS NORTH TERMINAL |  | 1288 | 0 |  |  | 17281 |  | Karl, Marissa | Decker, Paul |  |  | 1 | 43207 |  | Guest, ProSight | Independent | Aqua | 2022-03-18 | Overhead Update
Bettendorf - Tank 9 Platform Pier Replacements | Item | Open | MCAP | BETDF00M2302 | Exempt | 2110593 | Scott, Cory | West | 3. Active | Defined | West |  | 26000 |  | 26000 | 26000 | 0 | Green | 26000 |  | 26000 | 0 |  |  | 5709 |  |  | 5709 | Phase | 5709 |  | 26000 | 26000 | No | Green | 2023-05-01 | 2023-04-12 | 2023-04-12 | 2023-06-05 | 2023-05-31 | [12 empty] | 4900 |  | 21100 | [6 empty] | 5/2/2023 - Awaiting Engineering and Civil Scope approval. Adjusted construction forecast to July. 4/18/2023 - PO placed for engineering for $4,900.00 3/31/2023 - Adjusted forecast to reflect phase engineering complete in May with construction taking place in June. 3/23/2023 - Site visit took place with TAS Technical to have Detail Drawings produced for Civil Scope Leadership review. 1/23/2023 - Scope approval sent over to senior leadership. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | BETDF - BET BETTENDORF |  |  | 4900 | 21100 |  |  |  | Gardner, Travis | Smith, Todd W. |  |  | 1 | 44001 |  | Guest, ProSight | Independent | Aqua | 2022-06-17 | Other Programs
Bettendorf - Yard Water Hydrant and Frost Free Outdoor Spigot Repairs | Item | Open | MEXP | BETDF00E2204 | Maintenance Framework | 2036089 | Scott, Cory | West | 7. Closed | Drawdown | West | -13 |  |  | -12.56 | -13 | 0 | Green |  |  |  | -13 |  |  | 23000 |  |  | 23000 | Full | 23000 | 20053 |  | 20053 | No | Green | 2022-10-01 | 2022-09-13 | 2022-09-13 | 2022-11-18 | 2022-10-15 |  |  | 265.36 | -277.92 | [17 empty] | 2/2/2023 - Final waste management invoice for removal approved for $2,700.00. Project totals out at $20,052.96 1/10/2023 - Waste management invoice approved for $4,400.00. 12/7/2022 - Ryan and Associates billed for full PO amount. Dumpster being removed on 12/7/2022. Awaiting final waste management invoice. Project will closeout once that arrives. 11/29/2022 - Ryan plans on billing full amount in the next few days. They were going to install bollards when they set the kiosk on 12/9/2022. 11/2/2022 - Dumpster sample sent off. Awaiting billing from Ryan and Associates and Waste Management. 10/26/2022 - Foundation and Bollards installed making this now operational. 10/20/2022 - Hydrant replaced. Planned backfill and concrete repair on 10/28/2022. 10/19/2022 - Line tied to water main. The city plans to shut it off on 10/31/2022. 10/18/2022 - Project Started. Planned completion on 10/19/2022. 10/6/2022 - Dumpster with corn cob ordered. To be delivered on 10/17/2022. 10/4/2022 - PO to be cut to Ryan and Associates. 9/30/2022 - Forecasted 23K put into october. 9/28/2022 - Stakeholder meeting held. | 2023-02-21 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Eastern Iowa | BETDF - BET BETTENDORF |  | -13 | 0 |  |  | 20066 |  | Gardner, Travis | Gardner, Travis W. | N/A |  | 1 | 45832 |  | Gardner, Travis | JDE Child | Burnt Orange | 2022-09-13 | Other Programs
Bettendorf (BETDF) Tank 9 Geodome Taping | Item | Open | MEXP | BETDF00E2301 | Maintenance Framework | 2093990 | Roth, Aaron | West | 3. Active | Defined | Tanks |  | 70000 |  | 70000 | 70000 | 0 | Green | 70000 |  | 70000 | 0 |  |  | 70000 |  |  | 70000 | Full | 70000 |  | 70000 | 70000 | No | Green | 2023-06-01 | 2023-03-06 | 2023-03-06 | 2023-09-01 | 2023-06-30 | [13 empty] | 70000 | [7 empty] | 5.1 - developing schedule. PO in place. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Eastern Iowa | BETDF - BET BETTENDORF |  |  | 70000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44169 |  | Guest, ProSight | Independent | Aqua | 2022-07-18 | Int - Tanks
Bettendorf Deadleg Drain-up & Isolation | Item | Candidate | MEXP |  | Exempt |  | Scott, Cory | West | 5. Deferred |  | Facility Integrity |  |  |  | 0 |  | 0 | Green | 15000 |  | 15000 | -15000 | [9 empty] | 15000 | 15000 | No | Green | 2024-07-01 |  |  |  | 2023-07-31 | [21 empty] | 3/27/2023 - Project deferred till 2024 per Mike Ricke and Travis Gardner with a possible 2023 pull in later in the year. | 2023-03-27 |  |  | West | Pipelines and Terminals | Station/Terminal |  | Eastern Iowa | BETDF - BET BETTENDORF |  |  | 0 |  |  |  | 15000 | Aiken, Elaine |  |  |  | 1 | 45453 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Bettendorf Driver Kiosk Installation 2022 | Item | Open | MCAP | BETDF00M2202 | Maintenance Framework | 2003451 | Scott, Cory | West | 7. Closed | Defined | West | 679 |  |  | 679.1 | 679 | 0 | Green |  |  |  | 679 |  |  | 23000 | 12000 |  | 35000 | Full | 35000 | 32568 |  | 32568 | No | Green | 2022-08-01 | 2022-07-20 | 2022-07-20 | 2022-09-22 | 2022-12-31 |  |  | 679.1 | [18 empty] | 1/9/2023 - Awaiting 1/10/2023 for final processing for project closeout. 12/14/2022 - Final invoice for project posted in JD. The final cost for project is $31787.00 12/13/2022 - Jay Henges sent the invoice for the Kiosk for $16,601. Awaiting the final delivery invoice from arrive logistics and project will be ready for closeout. 12/7/2022 - Kiosk vendor took longer than anticpated to complete Kiosk. Kiosk arrived at terminal on 12/7/2022. Kiosk setting taking place 12/9/2022. 11/29/2022 - Kiosks set to arrive first week of december. Planned installation is 12/9/2022. 11/2/2022 - TAS Technical billed for engineering for $2850.00. 10/18/2022 - Foundation installed. Kiosk will be installed middle of November. 9/28/2022 - Stakeholder meeting. Foundation to be poured on 10/17/2022. 9/2/2022 - Full AFE submitted for 35K. 8/19/2022 - Kiosks are slated to arrive between 11/11/2022 - 11/18/2022. Construction of foundation and bollards will take place in October. 8/16/2022 - Adjusted forecast to reflect engineering, kiosk procurement, installation. 7/27/2022 - PO's cut for the TAS Engineering for 3K and the Kiosk for 19K to Porta King. 7/22/2022 - Forecasted the installation cost into 2023. Total: $37000.00. This cost includes waste management for excavation waste and the contractor installation. 7/21/2022 - Engineering will be billed in August. The kiosk should be ready in October. 7/14/2022 - Submitted Phase 1 AFE for the Kiosk order and Engineering Plan/Layout for 23K. 6/28/2022 - Awaiting Travis response on how to proceed since a large amount of addition scope had to be added for the retaining wall/found installation in the dike. 6/21/2022 - Phase AFE put in for civil drawing and kiosk order. 6/1/2022 - Working on scope for leadership review. Start working with Diamond Z to build prints for civil foundation and retaining wall inside dike. 5/18/2022 - Meeting with Ryan and Associates atTerminal to get estimate. 2/25/2022 - Working with Diamond Z to obtain drawings for Civil Scope of Work. 2/16/2022 - Started preparing scope of work for project. 2/8/2022 - Reached out to Porta King vendor to obtain proposal for kiosk manufacturing. | 2023-01-09 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | BETDF - BET BETTENDORF |  | 679 | 0 |  |  | 31889 |  | Gardner, Travis | Smith, Todd W. | N/A |  | 1 | 21279 |  | Guest, ProSight | Independent | Aqua | 2016-09-09 | Other Programs
Bettendorf Partial Fencing Replacement | Item | Open | MCAP | BETDF00M2301 | Exempt | 2094275 | Scott, Cory | West | 3. Active | Defined | West |  | 23000 |  | 23000 | 20000 | 3000 | Red | 18460 |  | 18460 | 4540 |  |  | 21717 |  |  | 21717 | Full | 21717 |  | 23000 | 23000 | No | Green | 2023-06-01 | 2023-03-08 | 2023-03-08 | 2023-04-14 | 2023-05-26 | [13 empty] | 23000 | [7 empty] | 5/2/2023 - Forecast adjusted to June for construction. It is scheduled to be built in late May. Forecast moved back in case of weather. 4/25/2023 - Recieved 3rd quote from Gullett Fence for 23K with a PIC Trained foreman. PO Placed for Gullett. Stakeholder meeting to be held on 5/5/2023. 4/18/2023 - Recieved second quote from TIMCO for 36K. Will be looking for more options. 3/27/2023 - Stakeholder meeting taking place on April 6th, 2023. Project scheduled for the later part of April. Forecast moved into may just in case the weather delays project into May. 3/21/2023 - PO placed for $18460.00 3/1/2023 - AFE submitted to remedy force 1/26/2023 - Vendor sent back updated quote for $18,641.00 1/25/2023 - Obtaining updated quote from vendor. Once I get pricing I will submit AFE. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | BETDF - BET BETTENDORF |  |  | 23000 |  |  |  |  | Gardner, Travis | Smith, Todd W. |  |  | 1 | 41209 |  | Guest, ProSight | Independent | Aqua | 2021-08-09 | Other Programs
Bettendorf Secondary Containment Improvements | Item | Open | MEXP | BETDF00E2203 | Maintenance Framework | 1970923 | Parker, Brian | West | 3. Active | Defined | Secondary Containment |  | 70000 |  | 70000 | 70000 | 0 | Green | 70000 |  | 70000 | 0 |  |  | 1000 |  |  | 1000 | Phase | 1000 |  | 70000 | 70000 | No | Green | 2023-07-01 | 2022-04-08 | 2022-04-08 | 2022-10-31 | 2023-07-31 | [14 empty] | 35000 | 35000 | [5 empty] | 5/1/23 - bidding end date is May 5th - expect to get bids evaluated and PO's issued in May. 4/10/23 - created bid event in Coupa on Apr 7th. 4/1/23 - have complete list of bidders now by location and will get a Coupa bid event created in Apr for the Phase II construction. BWC is setup now and can bid on this work. 2/28/23 - entered Coupa request to get BWC added as a new vendor so they can bid on this project. Sent emails out to 10 contractors to see which locations they want to bid on for dike work in 2023. I've received 6 responses back to date. Should have bid event created in Coupa in Mar for this project. 2/3/23 - working on getting another contractor setup as a Buckeye approved contractor so they can bid on this work. Plan to get a bid event entered in Feb or Mar so we can start work once the weather breaks. 1/1/23 - no change in status - work pushed out to 2023. Need to conduct a bid event in Q1. 11/30/22 - TIMCO proposal was high - pushing this work out to 2023 and will re-bid this work in Q1 2023. 10/31/22 - still waiting on a proposal from TIMCO - I don't expect this work to be completed until 2023. 9/29/22 - Ryan & Assoc declined to bid, just waiting on a proposal from TIMCO. 9/8/22 - moving this FCST out to 2023 - not 100% sure contractors are available for this work for the remainder of 2022. Will attempt to get work completed in 2022 but planning for worst case scenario since cutoff for 2023 FCST's is near. 9/3/22 - the bid event had issues and nobody from Supply Chain followed up to see how this was progressing. Wasted 1 month on this and starting the bid process over again. I will be reaching out to all bidders the week of Sep 6th to make sure they have everything they need. Still expect to complete this work in Oct/Nov. 8/1/22 - received one comment regarding option 1 for lowering drain pipe. Plan on getting this IFC set out to contractors in early Aug for quotes. 7/3/22 - will be sending out IFC drawing to management for review via email. Bidding is off the table right now due to contractor availabilityso just plan on obtaining several quotesfrom qualified vendors. 5/31/22 - have IFC drawings in hand - will complete bid document once I have all IFC drawings in hand and have completed drawing reviews. 5/3/22 -just waiting on IFC drawings from Diamond Z for some other dike projects so we can group these together and go out for bid sometime around late Jun or early Jul. 4/5/22 - submitted Phase I AFE for approval routing. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Eastern Iowa | BETDF - BET BETTENDORF |  |  | 0 | 70000 |  |  |  | Spari, Markella | Spari, Markella |  |  | 1 | 41443 |  | Guest, ProSight | Independent | Aqua | 2021-08-13 | Other Programs
Bettendorf Tank #3 - Catwalk Pier Replacements | Item | Open | MCAP | BETDF00M2303 | Exempt | 2111187 | Scott, Cory | West | 3. Active | Defined | West |  | 26000 |  | 26000 | 26000 | 0 | Green | 26000 |  | 26000 | 0 |  |  | 5709 |  |  | 5709 | Phase | 5709 |  | 26000 | 26000 | No | Green | 2023-05-01 | 2023-04-17 | 2023-04-17 | 2023-06-05 | 2023-05-31 | [12 empty] | 4900 |  | 21100 | [6 empty] | 5/2/2023 - Awaiting engineering completion and civil scope review. Adjusted forecast to July for construction. 4/18/2023 - PO placed for engineering at $4,900.00 3/30/2023 - Updated forecast to reflect engineering in may and construction in June. 3/23/2023 - Site visit took place with TAS Technical to have Detail Drawings produced for Civil Scope Leadership review. 1/23/2023 - Civil scope sent to senior leadership for review. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | BETDF - BET BETTENDORF |  |  | 4900 | 21100 |  |  |  | Gardner, Travis | Smith, Todd W. |  |  | 1 | 44002 |  | Guest, ProSight | Independent | Aqua | 2022-06-17 | Other Programs
Bettendorf Tank 2 Rack Pump B Power Frame Replacement | Item | Open | MCAP | BETDF00M2101 | Maintenance Framework | 1855306 | Scannell, Adam | West | 6. Operational | Unplanned | Rotating Equipment | 268 |  |  | 267.56 | 268 | 0 | Green |  |  |  | 268 |  |  | 30000 |  |  |  | Full | 30000 | 49113 |  | 49113 | Yes | Red | 2021-10-01 |  |  | 2021-10-31 | 2022-08-31 |  |  | 267.56 | 0 | 0 | 0 |  |  | 0 | Green | [11 empty] | 09/02/22 - Final installations cost was higher due to the need to use a crane service from farther away as well as difficulty getting the drain up and installation complete. 08/25/22 - Pump is installed and operational. 08/02/22 - Rescheduled to 8/16/22. By the time the ISN and vendor issue was complete, the schedule in July was missed. 07/01/22 - Still working on getting a new crane contractor set up to install this pump. ISN verification almost complete. 06/02/22 - Working with contractor on installation dates with new crane company. Previous had a "C" grade and could not be used. 05/04/22 - Work had to be rescheduled due to ISN grade of subcontractor. Setting for the first week of June, the earliest available date for the asset team members. 04/04/22 - Due to personnel limitations in the local asset teams, this work needed to be rescheduled and will be completed by contractors. Obtaining quotes and schedules for completion, late April or first of May expected completion to work with local operations. 03/02/22 - Scheduling installation with contractor. Due to personnel changes the local asset team is not able to perform the install as planned. Added forecast for install in March. 02/02/22 - New motor was received. Scheduling installation with local ops. 01/04/22 - Installation was cancelled by local operations. Rescheduled for January. 12/02/21 - Pump will be installed the week of 12/13/21. 11/02/21 - Pump is ready, motor shipment was delayed. Expected to receive on 11/12/21. Install tentatively scheduled for the week of 11/15/21 10/04/21 - No new updates. Pump delivery expected in October and installation will be complete once received. 09/08/21 - No new updates. Pump delivery expected in October and installation will be complete once received. 08/09/21 - No new updates. Pump delivery expected in October and installation will be complete once received. 07/06/21 - Pump delivery expected in October for installation. 06/03/21 -AFE approved, PO being issued. 18 week lead time expected, with late Oct installation. | 2022-09-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | BETDF - BET BETTENDORF |  | 268 | 0 |  |  | 22581 |  | Posipanko, Dan | Posipanko, Daniel A. | N/A |  | 1 | 31331 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Other Programs
Bettendorf Tank 3 UT Probe Upgrade | Item | Open | MEXP | BETDF00E2206 | Maintenance Framework | 2051832 | Rohr, Travis | West | 7. Closed | Drawdown | Cathodic Protection | 198 |  |  | 198.39 | 198 | 0 | Green |  |  |  | 198 |  |  | 7000 |  |  | 7000 | Full | 7000 | 7198 |  | 7198 | No | Green | 2022-12-01 | 2022-12-09 | 2022-12-09 | 2022-12-31 | 2022-12-31 |  |  | 198.39 | [18 empty] | 3/2/23 Completed. 2/3/23 Completed. 1/4/23 Work was completed week of Dec 12 | 2023-03-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Eastern Iowa | BETDF - BET BETTENDORF |  | 198 | 0 |  |  | 7000 |  | Geib, Rob | Shook, Mark B. | N/A |  | 1 | 46341 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-12-09 | Int - Planned Corr & FI
BETVL Louisville Secondary Containment Upgrades | Item | Open | MCAP | BETVL00M2204 | Maintenance Framework | 1970660 | Parker, Brian | West | 3. Active | Defined | Secondary Containment |  | 157000 |  | 157000 | 157000 | 0 | Green | 157000 |  | 157000 | 0 |  |  | 4000 |  |  | 4000 | Phase | 4000 | 3672 | 157000 | 160672 | No | Green | 2022-05-01 | 2022-04-08 | 2022-04-08 | 2022-10-31 | 2023-07-31 | [14 empty] | 67000 | 90000 | [5 empty] | 5/1/23 - Supply Chain only received one bid from Degen. They are reaching out to the other two bidders to see if this is a no-bid or do they need additional time. 4/10/23 - created bid event in Coupa on Apr 7th. 4/1/23 - have complete list of bidders now by location and will get a Coupa bid event created in Apr for the Phase II construction. 2/28/23 - Sent emails out to 10 contractors to see which locations they want to bid on for dike work in 2023. I've received 6 responses back to date. Should have bid event created in Coupa in Mar for this project. 2/3/23 - need to check with 3 contractors in Feb to confirm they will bid on this project and get a bid event setup in Feb/Mar so we can start work once the weather breaks. 1/1/23 - no change in status - work pushed out to 2023. 11/30/22 - pushing this work out to 2023 and will re-bid this in Q1 2023. 10/31/22 - still waiting on proposals - construction will not start until Q2 2023. 10/1/22 - waiting on proposals from Klump and Degen, this will probably be a 2023 project due to the asphalt work. Might be able to complete the dike work in 2022 - dropping 481 accrual. 9/9/22 - moving this FCST out to 2023 - not 100% sure contractors are available for this work for the remainder of 2022. Will attempt to get work completed in 2022 but planning for worst case scenario since cutoff for 2023 FCST's is near. 9/3/22 - the bid event had issues and nobody from Supply Chain followed up to see how this was progressing. Wasted 1 month on this and starting the bid process over again. I will be reaching out to all bidders the week of Sep 6th to make sure they have everything they need. 9/2/2022 - Bid event in progress. 8/2/2022 - Preliminary engineering complete and Scope/Design sent for management review. Bid event to take place in August/September. 7/5/2022 - Additional preliminary engineering for ethanol offload rack containment in process. 6/2/2022 - Additional preliminary engineering for ethanol offload rack containment in process. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Southern Ohio | BETVL - BET LOUISVILLE |  |  | 0 | 157000 |  | 3672 |  | Clark, Dave | Spari, Markella |  |  | 1 | 41793 |  | Roknich, Hunter | Independent | Aqua | 2021-08-20 | Other Programs
BETWD - Kiosk for Butane Offloading | Item | Candidate | MCAP |  | Maintenance Framework |  | Roknich, Hunter | West | 2. Pending AFE |  | Truck Racks |  | 20000 |  | 20000 | 20000 | 0 | Green | 20000 |  | 20000 | 0 | [9 empty] | 20000 | 20000 | No | Green | 2023-08-01 |  |  |  | 2023-04-30 | [15 empty] | 20000 | [9 empty] | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETWD - DETROIT BET TERMINAL |  |  | 0 | 20000 |  |  |  | Younce, Michael |  |  |  | 1 | 44236 |  | Guest, ProSight | Independent | Aqua | 2022-07-25 | Other Programs
BETWD Tank 9 Pump Upgrade | Item | Open | MCAP | BETWD00M2202 | Maintenance Framework | 1979713 | Fink, Ryan | West | 3. Active | Defined | Rotating Equipment | 141394 | 100000 |  | 241394.02 | 229194 | 12201 | Yellow | 119000 |  | 119000 | 122394 |  |  | 110000 | 396000 |  | 506000 | Full | 506000 | 410136 | 100000 | 510136 | No | Green | 2022-05-01 | 2022-05-04 | 2022-05-04 | 2022-10-31 | 2023-06-30 |  |  | 5540.98 | 1472.19 | 102180.34 | 32200.51 | 25000 | 25000 | 7201 | Red |  |  | 3000 | 76000 | 21000 | [6 empty] | 5/1 RRF - Accrue $4500 to Weld PI for April, EAC $504k 4/7 RRF - Fixed forecast error, EAC $504k 3/30 RRF - March actual $97.5k Tie in done and one pump operational. Change order for additional $32k for starter change and temp electrical. EAC $513k 3/17 RRF - Tie in 3/20-24 w/ old starter. New starters in June. March fcst $63k. (diff 61k placed in Dec). EAC $503k 3/8 RRF - Starters arrived, and do not fit in enclosure. Tie in late March or April. EAC 504k. 3/1 RRF - starters expected late March, install early April. EAC $491k 2/1 RRF - waiting on starters, expected in march 1/3/23 RRF - Accrue 153,844 in Dec22. Concrete and site prep done, Waiting on elec equipment to complete 12/1 RRF - Galvanizing delay pushing tie in to after 12/31, so holding off tie in to wait for starters, tie in planned for March 2023. 11-21-2022 - MNH - Project EAC at $494K. Reducing December forecast. 11/1 RRF - Phase2 approved, rush to finish 10/11 RRF - Relief valves delayed ship to Nov. Project on hold 10/10 RRF - Project stalled due to costs. moved out to Nov/Dec 9/30 RRF - Bids received 269k OVER budget, forecast updated for 2022 mech, 2023 electrical. Phase 2 AFE total $506k pending review to submit. PO# OP-231556 Billed twice, needs fixed 9/12 RRF - moved 25k tie in and 50k starters to 2023 9/4 RRF - Moved starter panels to 2023 incase they get delayed. 9/2 RRF - IFC review done, out for Mech and Elec bid 8/1 RRF - Design review moved to 8/4. Strainers to arrive August, pumps and reliefs, sept Oct. 7/9 RRF - Mat ordered, est ph2; Design review 7/18 6/23 RRF - 20k in June, engineering. 6/1 RRF - design review IFA in June 5/31 RRF - Pumps ordered, drawings in progress 5/3 RRF - AFE phase 1 pending approval since 4/20, moved out forecast 4/6/2022 RRF - site visit 4/7, Phase1 AFE submitted for Engineering, drawings, and long lead items. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETWD - DETROIT BET TERMINAL |  | 109194 | 111201 | 21000 |  | 268742 |  | Posipanko, Dan | Spitz, Nicholas P. | N/A |  | 1 | 31542 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Other Programs
BETWD Tank Dike Access Upgrade | Item | Open | MCAP | BETWD00M2203 | Maintenance Framework | 2044982 | Arch, Stefan | West | 6. Operational | Defined | West | 10550 |  |  | 10550.16 | 10550 | 0 | Green |  |  |  | 10550 |  |  | 166000 |  |  | 166000 | Full | 166000 | 124206 |  | 124206 | No | Green | 2022-12-01 | 2022-11-15 | 2022-11-15 | 2022-12-31 | 2022-12-30 |  |  | 10163.93 | 386.23 | [17 empty] | 4/7/2023 - All invoices have been completed and PO's are closed. WO can be closed. 3/1/2023 - All invoices have been completed and PO's are closed. WO can be closed. 2/1/2023 - Project completed first week of January. No additional forecasting required. All PO's have been closed. 1/3/2022 - Project is 95% complete. Worked throughout December to complete majority in December. Small forecast in January to complete remaining items. The electrical work was completed in December. 12/1/2022 - AFE submitted and approved. PO sent to Holly for work. Planning to begin work next week or following week. Anticipating work will be completed this year. Forecast updated to reflect bulk of work in December. 11/1/2022 - Waiting on one quote, if not received by the end of the week, will submit AFE. No work completed in November. Forecasting pushed out to December. 10/3/2022 - Walked down project on 9/20 with Operations. Developed scope and sent to Leadership team and local Ops. Sent scope to Holly and CCC to quote. Waiting for quotes to come back. Planning to complete in 2022, but put money in 2023 if contractors are not available. 8/25/22 - Working with operations to get 2 more contractors and conduct bid walk. 8/2/2022 - Quote received from Holly construction. Will need to get 2 more quotes to meet supply chain requirements. Estimated construction mid/late October 6/2/2022 - this project is still required . The title didn't match the project scope of work. 4/28/22 - OM stated this work is no longer required. | 2023-04-07 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETWD - DETROIT BET TERMINAL |  | 10550 | 0 |  |  | 113656 |  | Gardner, Travis | Gardner, Travis W. | N/A |  | 1 | 31533 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Other Programs
BETWD-INSTALL FRP COATED UBOLTS | Item | Open | MCAP | BETWD00M2302 | Exempt | 2109888 | Brown, Jeff | West | 3. Active | Defined | Atmospheric Corrosion |  | 97000 |  | 97000 | 97000 | 0 | Green | 97000 |  | 97000 | 0 |  |  | 94629 |  |  | 94629 | Full | 94629 |  | 97000 | 97000 | No | Green | 2023-07-01 | 2023-04-04 | 2023-04-04 | 2022-12-31 | 2023-10-31 | [14 empty] | 13000 |  |  | 84000 |  |  |  | 5-1-23 AFE approved and materials on order. 4-3-23 AFE ROUTING 3-2-23-CONTACTING 22 BID CONTRACTOR FOR THIS WORK7-7-22 NO FUNDS WORK DEFERED 23 | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Wayne Terminals | BETWS - BET WOODDHAVEN TERMINAL |  |  | 0 | 13000 | 84000 |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 41075 |  | Guest, ProSight | Independent | Aqua | 2021-08-06 | Int - Planned Corr & FI
BETWS Broadway Tank Valve Actuator Upgrade - Phase 1 FEED | Item | Open | MCAP | BETWS00M2205 | Maintenance Framework | 1970331 | Fink, Ryan | West | 3. Active | Defined | Valves | 2394 | 174000 |  | 176394 | 124180 | 52214 | Red | 120000 |  | 120000 | 56394 |  |  | 32000 | 174129 |  | 32000 | Full | 206129 | 31717 | 174000 | 205717 | No | Green | 2022-04-01 | 2022-04-04 | 2022-04-04 | 2022-05-31 | 2023-09-30 |  |  | 152.28 | 137.78 | 889.5 | 1214.44 |  |  | 1214 | Red |  |  |  | 10000 | 40000 | 25000 | 52000 | 35000 | 12000 |  |  | 5/3 RRF - Init fcst, 2023 EAC $206k 4/20 RRF - AFE ph2 $174k dike crossing and wiring. ph3 $151k MOV purchase and install. EAC $355k 4/17 RRF - Full EAC $355k, Phase 2 $153k, Phase 3 $172k. Pending approval of additional phases. 4/7 RRF - Estimates exceed budget, revise. EAC $153k 3/2 RRF - sched est and AFE, EAC $153k , 123k 2023 2/1 RRF - ph2 prep 1/4/23 RRF - RFQs out for phase 2 estimate 12/2 RRF - site visit for electrical est 11/2 RRF - sched est site visit 10/3 RRF - need electrical estimate 8/31 RRF - $8532 inv on 8/8, IFR review 8/30, need final site visit to complete dwgs 8/8 RRF - reduced contingency, release $3200. 8/2 RRF - Drawings in progress, minor slip in July, design review Aug. Moved contingency to Dec. 7/11 RRF - In progress, too late to accrue 15k June, moved to July, cont in dec 6/6 RRF - Engineering work starting in June 6/1 RRF - eng 5/3 RRF - engineering in progress 4/11 RRF - Site visit and PO for eng. 3/21/2022 RRF - AFE submitted, $31k | 2023-05-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETWS - BET WOODDHAVEN TERMINAL |  | 1180 | 11214 | 117000 | 47000 | 29323 |  | Oey, Alex | Spitz, Nicholas P. | N/A |  | 1 | 31591 |  | Guest, ProSight | Independent | Aqua | 2018-08-30 | Other Programs
BETWS-INSTALL FRP COATED UBOLTS MCAP 2022 | Item | Open | MCAP | BETWS00M2206 | Maintenance Framework | 2003951 | Brown, Jeff | West | 7. Closed | Defined | Atmospheric Corrosion | 1292 |  |  | 1292.47 | 1292 | 0 | Green |  |  |  | 1292 |  |  | 142000 |  |  | 142000 | Full | 142000 | 134135 |  | 134135 | No | Green | 2022-09-01 | 2022-07-25 | 2022-07-25 | 2022-12-31 | 2022-11-30 |  |  | 1292.47 | [18 empty] | 10-31-22 WORK COMPLETED 10-3 WORK WILL BE COMPLETED OCT 9/1/2022 - WORK TO START 9-6-22 8-1-22 AFE APPROVED-MATERIALS ORDERED | 2022-10-31 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Wayne Terminals | BETWS - BET WOODDHAVEN TERMINAL |  | 1292 | 0 |  |  | 132842 |  | Geib, Rob | Geib, Robert |  |  | 1 | 44172 |  | Meitzler, Antoinette | Independent | Aqua | 2022-07-18 | Int - Planned Corr & FI
BETYH Cuyahoga Replace Roof on Office Building | Item | Open | MCAP | BETYH00M2203 | Maintenance Framework | 1991410 | Roknich, Hunter | West | 4. On-Hold | Defined | West |  | 1 |  | 1 | 1 | 0 | Green |  |  |  | 1 |  |  | 139000 |  |  | 139000 | Full | 139000 |  | 130001 | 130001 | No | Green | 2023-12-01 | 2022-06-23 | 2022-06-23 | 2022-10-31 | 2024-12-31 | [19 empty] | 1 |  | 5/2/2023 - Moved project to "On-Hold" due to there being no 2023 budget. 4/4/2023 - See below. 3/2/2023 - Not in 2023 budget. May possibly get done at end of year with drawdown. 2/2/2023 - Working to find contractor with satisfactory ISN Grade 1/4/2023 - Working to find contractor with satisfactory ISN Grade 12/2/2022 - Moving forecast to CY+1 due to difficulty finding contractor with satisfactory ISNetWorld grading 11/2/2022 - Five Star roofing bid walk scheduled for 11/3 10/3/2022 - Working with Five Star Roofing to try upper management to get ISNet exemption. 9/2/2022 - Change in schedule, forecast, and contractor due to original contractor being put on "do not use" ISNet list. Another bid event was held. Waiting for estimate. 8/2/2022 - Working with West Roofing Systems to develop schedule for work. Estimated construction mid September. 7/5/2022 - AFE approved. Purchase order to be submitted Early July. Preliminary start date mid-September 2/17/22 - Project originally forecasted for March was oversight and not adjusted at the beginning of the year. Project construction to occur late Q2 - early Q3. Possible spends early-mid Q2 once bids are received and half down needed at time of contract. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | North East Ohio | BETYH - BET CUYAHOGA |  |  | 0 |  | 1 |  | 130000 | Gardner, Travis | Gardner, Dale |  |  | 1 | 37787 |  | Guest, ProSight | Independent | Aqua | 2020-08-12 | Other Programs
BETYO Warren Terminal Pole Replacement | Item | Open | MCAP | BETYO00M2201 | Exempt | 2052312 | Gardner, Travis | West | 7. Closed | Emergent | Electrical | 12820 |  |  | 12820.31 | 12820 | 0 | Green |  |  |  | 12820 |  |  | 40000 |  |  | 40000 | Full | 40000 | 38486 |  | 38486 | No | Green | 2022-12-01 | 2022-12-19 | 2022-12-19 | 2022-12-31 | 2022-12-30 |  |  | 12268.24 | 552.07 | [17 empty] | 1/4/2023 - only complete 75% of thew work due to contractor illness. pushed remaining cost into 2023. 12/9/2022 - emergent project planned to be completed in Dec. | 2023-01-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | North East Ohio | BETYO - BET WARREN |  | 12820 | 0 |  |  | 25666 |  | Ashley, Robert |  |  |  | 1 | 46335 |  | Gardner, Travis | Independent | Aqua | 2022-12-08 | Other Programs
BN160AS Rectifier and Pole Replacement MCAP | Item | Open | MCAP | BN160ASM2302 | Maintenance Framework | 2095733 | Gabriel, Jeff | West | 6. Operational | Drawdown | Cathodic Protection | 29475 |  |  | 29474.74 | 24913 | 4562 | Red |  | 24000 | 24000 | 5475 |  |  | 24000 |  |  | 24000 | Full | 24000 | 29475 |  | 29475 | Yes | Red | 2023-03-01 | 2023-03-22 | 2023-03-22 | 2023-07-30 | 2023-03-21 |  |  |  |  | 24912.9 | 4561.84 |  |  | 4562 | Red | [11 empty] | 4/3/2023- Work complete. Would need a supplemental since more Buckeye labor to HT160DQ rectifier pole replacement. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Central-Illinois | BN160AS - BARNETT TO AUBURN |  | 24913 | 4562 |  |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 46714 |  | Meitzler, Antoinette | Independent | Aqua | 2023-03-07
BN160AS Rectifier Pole Replacement | Item | Open | MEXP | BN160ASE2302 | Exempt |  | Gabriel, Jeff | West | 8. Canceled | Defined | Cathodic Protection |  |  |  | 0 |  | 0 | Green | 13500 |  | 13500 | -13500 |  |  | 24000 |  |  |  | Full | 24000 |  |  |  | No | Green |  |  |  | 2023-07-30 | 2023-04-30 | [21 empty] | 4/3/2023- this project needs to be cancelled. changed to MCAP Project BN160ASM2302. 3/2/20223- AFE is complete and is being routed for approval | 2023-04-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Central-Illinois | BN160AS - BARNETT TO AUBURN |  |  | 0 |  |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44166 |  | Guest, ProSight | Independent | Aqua | 2022-07-18 | Int - Planned Corr & FI
BN160ASEP204230 MP 38.62 Exposure Repair | Item | Open | MEXP | BN160ASE2303 | Maintenance Framework | 2094349 | Gabriel, Jeff | West | 3. Active | Drawdown | Exposed Pipe Evaluation & Remediation |  | 39000 |  | 39000 | 39000 | 0 | Green |  |  |  | 39000 |  |  | 39000 |  |  | 39000 | Full | 39000 |  | 39000 | 39000 | No | Green | 2023-08-01 | 2023-03-09 | 2023-03-09 | 2023-06-15 | 2023-06-15 | [15 empty] | 39000 | [5 empty] | 5/1/2023- NO change 4/3/2023- Project awarded to CPM moved forecast to August due to contractor avalibility. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | Central-Illinois | BN160AS - BARNETT TO AUBURN |  |  | 0 | 39000 |  |  |  | Hurley, Brian | Bartal, Nick | N/A |  | 1 | 46721 |  | Hurley, Brian | JDE Child | Burnt Orange | 2023-03-08
Bourbonnais Distributed Ground Bed | Item | Candidate | MCAP |  | Maintenance Framework |  | Scannell, Adam | West | 2. Pending AFE | Defined | Cathodic Protection |  | 45000 |  | 45000 | 45000 | 0 | Green | 45000 |  | 45000 | 0 | [9 empty] | 45000 | 45000 | No | Green | 2023-10-01 |  |  |  | 2023-04-30 | [17 empty] | 45000 |  |  |  | 04/14/23 - New easement with the city is being worked on by ROW. Jeff Gabriel is also looking into utilizing the 163L as a linear anode as an alternate solution. Once he has collected the information needed he will follow up with mw to let me know which route we will be taking. 03/23/23 - Project is currently in ROW for easement aquisition. I will work with Jeff Gabriel to get a design ready to quote once easement is secured. Moving out to October. 03/02/21 - This project is part of the overall West District CP project bid event. Award to contractor planned for end of March. | 2023-04-14 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Argo | KK162XX - KANKAKEE TO IN S/L |  |  | 0 |  | 45000 |  |  | Geib, Rob |  |  |  | 1 | 37876 |  | Guest, ProSight | Independent | Aqua | 2020-08-13 | Int - Planned Corr & FI
Bradley Road Control Valve Replacement | Item | Open | MCAP | YD00000M2201 | Maintenance Framework | 1909813 | Fink, Ryan | West | 6. Operational | Defined | Valves | -997 |  |  | -997.28 | -997 | 0 | Green |  |  |  | -997 |  |  | 71000 |  |  | 71000 | Full | 71000 | 73772 |  | 73772 | No | Green | 2021-12-01 | 2021-12-20 | 2021-12-20 | 2022-04-01 | 2022-06-30 |  |  | -1090.72 | 93.44 | [17 empty] | 5/2 RRF - Need invoice, EAC $74k 4/7 RRF - wait for invoice. Charges hit project but invoice not paid. EAC $74k 3/2 RRF - Final invoice and close, EAC $74k 2/2 RRF - C&K to re-submit invoice 1/4/23 RRF - need to fix C&K invoice then close 12/2 RRF - need to fix C&K invoice then close 11/2 RRF - need to fix C&K invoice then close 10/4 RRF - Fix C&K invoice on PO# C1-231860 9/2 RRF - Re-accrue 7k to LMS, new 3878 Aug accrual to LMS. C&K Invoice stuck. 8/2 RRF - Proving done June, accrue 7k to LMS 7/7 RRF - PCV installed June, Meter proving and close July/Aug 6/3 RRF - Need coupler ($9k) for PCV install. 6/1 RRF - May forecast too high, should have been 37k-11k = 26k. Install in June 5/19 RRF - valve has been delivered, to be installed 6/8; moved 3k of contingency to July. 5/3 RRF - Valve has shipped, in transit, May 9 delivery. May/June install, re-accrue 11363 CCI 4/3 RRF - update for valve ship may 3/1 RRF - dist contingency 2/2 RRF - pending material arrival 1/7 RRF - updated forecast to match AFE, from $84k to $71k. 1/3/2022 RRF - PO w/SS approved 12/29; 30% invoice on PO acceptance, Accrue 11363 Dec. 12/8/2021 RRF - TG submitted AFE, updated forecast | 2023-05-02 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Operating Infrastructure |  | Mantua | YD - BRADLEY ROAD BPLT |  | -997 | 0 |  |  | 63406 |  | Oey, Alex | Spitz, Nicholas P. |  |  | 1 | 42197 |  | Administrator, System | Independent | Aqua | 2021-09-22 | Other Programs
Bradley Road Station Camera and Card Reader Replacement | Item | Open | MCAP | YD00000M2301 | Exempt | 2086009 | Fink, Ryan | West | 3. Active | Drawdown | Security & Cameras |  | 14000 |  | 14000 | 14000 | 0 | Green |  | 14139 | 14139 | -139 |  |  | 14139 |  |  | 14139 | Full | 14139 |  | 14000 | 14000 | No | Green | 2023-06-01 | 2023-02-24 | 2023-02-24 | 2023-06-30 | 2023-08-11 | [13 empty] | 2500 |  | 10000 | 1500 |  |  |  |  | 5/2 RRF - EAC $14k 4/25 RRF - POs submitted for cam/cardread and for new bollards. Hardware to arrive in August, operational date moved to 8/11. Req proj site. EAC $14k. 4/6 RRF - Moved out 1 EAC $14k 3/1 RRF - AFE approved, PO as soon as WO issued. 24 week lead times. EAC $14k 2/14 RRF - AFE review and submit EAC 13k | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Mantua | YD - BRADLEY ROAD BPLT |  |  | 2500 | 11500 |  |  |  | Clark, Chris | Gardner, Travis W. |  |  | 1 | 46589 |  | Gardner, Travis | Independent | Aqua | 2023-02-13 | Other Programs
BTTDB - DOT COATING REPAIR | Item | Candidate | MEXP |  | Exempt |  | Brown, Jeff | West | 2. Pending AFE |  | Atmospheric Corrosion |  | 32000 |  | 32000 | 32000 | 0 | Green | 32000 |  | 32000 | 0 | [9 empty] | 32000 | 32000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 32000 | [6 empty] | 5-1-23 Scoping project.4-3-23 SCOPING 3-2-23 SCOPING PROJECT | 2023-05-01 |  |  | West | Pipelines and Terminals | Corrosion |  | Wayne Pipeline | DB - DEARBORN TERMINAL |  |  | 0 | 32000 |  |  |  | Geib, Rob |  |  |  | 1 | 44440 |  | Guest, ProSight | Independent | Aqua | 2022-08-08 | Int - Planned Corr & FI
Burlington Junction (UR) PLC and HMI replacement | Item | Open | MCAP | UR00000M2201 | Maintenance Framework | 1989965 | Grinder, Mark | West | 3. Active | Defined | Instrumentation & Controls | 46585 | 84000 |  | 130584.74 | 128011 | 2573 | Yellow | 127000 |  | 127000 | 3585 |  |  | 201000 |  |  | 201000 | Phase | 201000 | 142083 | 84000 | 226083 | No | Green | 2022-07-01 | 2022-06-09 | 2022-06-09 | 2022-11-30 | 2023-07-31 |  |  | 15690.18 | 15607.46 | -4286.39 | 19573.49 | 17000 | 17000 | 2573 | Red |  |  | 17000 | 15000 | 52000 | [6 empty] | 4-27-2023 - We are still planning on a July Cutover. 3-23-2023 - This project is now scheduled to be completed in July 2023 due to CC4 schedulers request. 3-01-2023 - This project is now scheduled to be completed in July 2023 due to CC4 schedulers request. 2-01-2023 - This project has completed everything possible until material arrives for installation in May/June 2023. 12-29-2022 - This project has completed everything possible until material arrives for installation in May/June 2023. 11-28-2022 - EN Engineering is performing a FAT test this week and going to finalize/edit the HMI Screens in December and will install once all equipment is received in May 2023. 11-01-2022 - EN Engineering working on Program for PLC/HMI, Control Narrative and RCA database and will spend as much as possible before 2023, the expected spend amounts are forecast through December and remainder has been forecast for May of 2023 . 9-26-2022 - EN Engineering working on Program for PLC/HMI, Control Narrative and RCA database and will spend as much as possible before 2023, the expected spend amounts are forecast through December and remainder has been forecast for May of 2023 . 8-29-2022 - EN Engineering working on Program for PLC/HMI, Control Narrative and RCA database and will spend as much as possible before 2023, the expected spend amounts are forecast through December and remainder has been forecast for May of 2023 . 7-27-2022 EN Engineering working on Program for PLC/HMI, Control Narrative and RCA database and will spend as much as possible before 2023, the expected spend amounts are forecast through December and remainder has been forecast for May of 2023 . 7/1/22 - Moved forecast to 2023 due to material delivery date. 6-29-2022 - PLC, Industrial PC material on order, waiting to receive Final electrical bids in Mid-July. 6/1/22 - need to adjust this FCST to reflect an EAC of 180,000 in 2022. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Sugar Creek | UR - BURLINGTON JCT |  | 27011 | 51573 | 52000 |  | 95498 |  | Forsey, Frank | Smith, Todd W. |  |  | 1 | 37583 |  | Guest, ProSight | Independent | Aqua | 2020-08-10 | Other Programs
Burlington Junction Hazardous Gas Detector Replacement | Item | Open | MCAP | UR00000M2301 | Maintenance Framework | 2083820 | Grinder, Mark | West | 3. Active | Drawdown | Instrumentation & Controls | 7911 | 3000 |  | 10910.65 | 18250 | -7339 | Red |  | 10074 | 10074 | 837 |  |  | 10074 |  |  | 10074 | Full | 10074 | 7911 | 3000 | 10911 | No | Green | 2023-03-01 | 2023-02-06 | 2023-02-06 | 2023-06-30 | 2023-07-31 |  |  |  |  | 7570 | 340.65 |  |  | 341 | Red |  |  |  |  | 3000 | [6 empty] | 4-27-2023 - The material has been received and will be installed when we cut over the new PLC in July. 3-23-2023 - The material has been received and will be installed when we cut over the new PLC in July. 3-01-2023 - The material has been received and will be installed when we cut over the new PLC in July. 2-01-2023 - Submitted and AFE for this project today. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Sugar Creek | UR - BURLINGTON JCT |  | 7570 | 341 | 3000 |  |  |  | Forsey, Frank | Smith, Todd W. |  |  | 1 | 46555 |  | Grinder, Mark T. | Independent | Aqua | 2023-01-27 | Other Programs
Burlington Junction Pump Removal and Blind - Leak Point Eliminations | Item | Open | MEXP | UR00000E2301 | Exempt | 2095670 | Scott, Cory | West | 5. Deferred | Defined | Facility Integrity |  |  |  | 0 |  | 0 | Green | 25000 |  | 25000 | -25000 |  |  | 38885 |  |  | 38885 | Full | 38885 |  | 39000 | 39000 | No | Green | 2024-05-01 | 2023-03-21 | 2023-03-21 | 2023-04-08 | 2023-03-31 | [21 empty] | 3/27/2023 - Project deferred till 2024 or later in 2023 per Travis Gardner and Mike Ricke. 3/21/2023 - Building scope and awaiting work order to produce PO's. Producing PO. 3/9/2023 - Final quotes recieved from contractor (Vance) nde (Acuren) environmental drain up (Prairie Industrial). Submitted AFE. 3/6/2023 - Final site visit with Vance and Associates. 2/28/2023 - Preliminary call for project planning with Buckeye PM's, Contractor, and Technicians. 1/27/2023 - Site visit with Kip Vance to go over project plan for an accurate estimate. | 2023-03-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Sugar Creek | UR - BURLINGTON JCT |  |  | 0 |  |  |  | 39000 | Aiken, Elaine | Smith, Todd W. |  |  | 1 | 44564 |  | Guest, ProSight | Independent | Aqua | 2022-08-12 | Int - Planned Corr & FI
Canton Fiber VRU comms | Item | Open | MCAP | BETON00M2301 | Exempt | 2083823 | Fink, Ryan | West | 6. Operational | Drawdown | Instrumentation & Controls | 21747 | 8500 |  | 30246.74 | 30810 | -564 | Yellow |  | 30951 | 30951 | -704 |  |  | 30951 |  |  | 30951 | Full | 30951 | 21747 | 8500 | 30247 | No | Green | 2023-03-01 | 2023-02-02 | 2023-02-02 | 2023-03-20 | 2023-04-03 |  |  |  |  | 20810.28 | 936.46 | 1000 | 1000 | -64 | Yellow |  |  | 1000 | 5000 | 2500 | [6 empty] | 5/2 RRF - IT Hardware in June, EAC $30k 4/6 RRF - VRU comms up, most cams, IT material May, contingency in June. EAC $31k 3/27 RRF - Fiber done 3/24, tech labor last week of March. IT material in April, EAC $31k 3/1 RRF - begin work mid March, EAC $31k 2/13 RRF - AFE approved, PO out. fcst update 20, 9, 1 . EAC 31k 2/2 RRF - pending AFE approval 1/31 RRF - start work week of 3/1 1/27 RRF - AFE submitted to remedy. Quotes acquired for Fiber and Ethernet cable from office to VRU. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | North East Ohio | BETON - BET CANTON |  | 20810 | 6936 | 2500 |  |  |  | Forsey, Frank | Gardner, Travis W. |  |  | 1 | 46553 |  | Gardner, Travis | Independent | Aqua | 2023-01-27 | Other Programs
Carbon Station Actuator Replacement | Item | Open | MCAP | CN00000M2301 | Exempt | 2094891 | Smith, Kyle | West | 3. Active | Defined | Valves |  | 20775 |  | 20775 | 20775 | 0 | Green | 18000 |  | 18000 | 2775 |  |  | 20775 |  |  | 20775 | Full | 20775 |  | 20775 | 20775 | No | Green | 2023-05-01 | 2023-03-12 | 2023-03-12 | 2023-05-30 | 2023-05-31 | [12 empty] | 20775 | [8 empty] | 4/28/23 Work scheduled second week of May | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Indianapolis | CN - CARBON STATION |  |  | 20775 |  |  |  |  | Oey, Alex | Oey, Alexander |  |  | 1 | 43699 |  | Guest, ProSight | Independent | Aqua | 2022-05-09 | Other Programs
Cedar Rapids Tank 1 Rack Pump Motor Replacement | Item | Open | MCAP | BETAR00M2302 | Exempt | 2084669 | Scott, Cory | West | 3. Active | Defined | Rotating Equipment | 4598 | 3000 |  | 7598 | 7400 | 198 | Yellow | 7000 | 1350 | 8350 | -752 |  |  | 8334 |  |  | 8334 | Full | 8334 | 4598 | 3000 | 7598 | No | Green | 2023-03-01 | 2023-02-14 | 2023-02-14 | 2023-03-31 | 2023-05-31 |  |  |  |  | 4400 | 198 | 0 | 0 | 198 | Red |  |  |  | 3000 | [7 empty] | 5/8/2023 - Coupling date keeps pushing back. Reforecasted into June. 5/2/2023 - Reached out to Superior. Awaiting final install date when technician comes out onsite. 4/18/2023 - Awaiting may installation. 3/21/2023 - Stakeholder meeting held for upcoming project. Motor arrived in June. Coupling not set to arrive until May so I moved back the installation. 2/21/2023 - PO placed for pump motor for $7200. Motor has (5) week lead time. Possible late march install or early April at the latest. 2/3/2023 - AFE submitted for $8400.00. Forecast adjusted. 2/1/2023 - Superior sent updated quote. AFE built. 1/26/2023 - Scope of work built for project. 1/23/2023 - Forecast adjusted to reflect March lead time and April installation. | 2023-05-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | BETAR - BET CEDAR RAPIDS |  | 4400 | 3198 |  |  |  |  | Posipanko, Dan | Smith, Todd W. |  |  | 1 | 45234 |  | Guest, ProSight | Independent | Aqua | 2022-08-23 | Other Programs
Cedar Rapids Terminal (BETAR) Secondary Containment Improvements | Item | Open | MEXP | BETAR00E2203 | Maintenance Framework | 1970924 | Parker, Brian | West | 3. Active | Defined | Secondary Containment |  | 80000 |  | 80000 | 80000 | 0 | Green | 80000 |  | 80000 | 0 |  |  | 1000 |  |  | 1000 | Phase | 1000 |  | 80000 | 80000 | No | Green | 2023-07-01 | 2022-04-08 | 2022-04-08 | 2022-10-31 | 2023-07-31 | [14 empty] | 40000 | 40000 | [5 empty] | 5/1/23 - bidding end date is May 5th - expect to get bids evaluated and PO's issued in May. 4/10/23 - created bid event in Coupa on Apr 7th. 4/1/23 - have complete list of bidders now by location and will get a Coupa bid event created in Apr for the Phase II construction. BWC is setup now and can bid on this work. 2/28/23 - entered Coupa request to get BWC added as a new vendor so they can bid on this project. Sent emails out to 10 contractors to see which locations they want to bid on for dike work in 2023. I've received 6 responses back to date. Should have bid event created in Coupa in Mar for this project. 2/3/23 - working on getting another contractor setup as a Buckeye approved contractor so they can bid on this work. Plan to get a bid event entered in Feb or Mar so we can start work once the weather breaks. 1/1/23 - no change in status - work pushed out to 2023. Need to conduct a bid event in Q1. 11/30/22 - TIMCO proposal was high - pushing this work out to 2023 and will re-bid this work in Q1 2023. 10/31/22 - still waiting on a proposal from TIMCO - I don't expect this work to be completed until 2023. 9/29/22 - Ryan & Assoc declined to bid, just waiting on a proposal from TIMCO. 9/8/22 - moving this FCST out to 2023 - not 100% sure contractors are available for this work for the remainder of 2022. Will attempt to get work completed in 2022 but planning for worst case scenario since cutoff for 2023 FCST's is near. 9/3/22 - the bid event had issues and nobody from Supply Chain followed up to see how this was progressing. Wasted 1 month on this and starting the bid process over again. I will be reaching out to all bidders the week of Sep 6th to make sure they have everything they need. Still expect to complete this work in Oct/Nov. 8/1/22 - emailed IFC drawings on 7/6 and received no feedback. Will get pricing from contractors in Aug and might be able to start work in mid-Sep. Forecasting the work for Oct timeframefor now. 7/3/22 - will be sending out IFC drawing to management for review via email. Bidding is off the table right now due to contractor availability so just plan on obtaining several quotes from qualified vendors. 5/31/22 - have IFC drawings in hand - will complete bid document once I have all IFC drawings in hand and have completed drawing reviews. 5/3/22 - just waiting on IFC drawings from Diamond Z for some other dike projects so we can group these together and go out for bid sometime around late Jun or early Jul. 4/5/22 - submitted Phase I AFE for approval routing. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Eastern Iowa | BETAR - BET CEDAR RAPIDS |  |  | 0 | 80000 |  |  |  | Spari, Markella | Spari, Markella |  |  | 1 | 40766 |  | Guest, ProSight | Independent | Aqua | 2021-07-28 | Other Programs
Cedar Rapids Terminal (BETAR) Tank 6 - OOS API 653 Insp | Item | Open | MCAP | BETAR00M2301 | Maintenance Framework | 2084426 | Roth, Aaron | West | 3. Active | Defined | Tanks | 33809 | 132000 |  | 165809.06 | 186281 | -20472 | Red | 112756 |  | 112756 | 53053 |  |  | 127512 |  |  | 127512 | Phase | 127512 | 33809 | 132000 | 165809 | No | Green | 2023-03-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-09-30 |  |  |  |  | 26281.11 | 7527.95 | 105000 | 105000 | -97472 | Red |  | Contractor/Vendor Issue | 132000 | [8 empty] | 5.1 - Tarsco to start repairs and stair install on 5/8. West Virginia Paint to start 5/15. RTS by end of May. VAR: Tarsco had delays starting due to new stair fab and galvanizing. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Eastern Iowa | BETAR - BET CEDAR RAPIDS |  | 26281 | 139528 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44789 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Cedar Rapids Terminal (BETAR) Tank 2 - OOS Corr Insp & Refurb | Item | Open | MCAP | BETAR00M2102 | Exempt | 1782243 | Roth, Aaron | West | 7. Closed | Defined | Tanks | 7794 |  |  | 7794.12 | 7619 | 175 | Yellow |  |  |  | 7794 |  |  | 208000 |  |  | 208000 | Phase | 208000 | 4068 |  | 4068 | No | Green | 2021-01-01 | 2020-12-02 | 2020-12-02 | 2021-12-31 | 2021-09-30 |  |  |  | 3725.64 | 3893.29 | 175.19 |  |  | 175 | Red | [11 empty] | 12/22/22 - PO and WO closed - ready to be closed by accounting. 9/7/21 - submitted AFE to flip costs to MEXP - reclass will be submitted for Sep business. 8.31.21 - Tank RTS. | 2022-12-22 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Eastern Iowa | BETAR - BET CEDAR RAPIDS |  | 7619 | 175 |  |  | -7451 |  | Stine, Carlton | Bassani, Joel D. | N/A |  | 1 | 30341 |  | Guest, ProSight | Independent | Aqua | 2018-08-06 | Int - Tanks
Cedar Rapids Terminal (BETAR) Tank 2 - OOS Corr Insp & Refurb - flip to MEXP | Item | Open | MEXP | BETAR00E2103 | Exempt | 1887270 | Roth, Aaron | West | 7. Closed | Drawdown | Tanks | -7451 |  |  | -7451.28 | -7451 | 0 | Green |  |  |  | -7451 |  |  | 205000 |  |  | 205000 | Full | 205000 | 178974 |  | 178974 | No | Green | 2021-09-01 | 2021-09-09 | 2021-09-09 | 2021-09-30 | 2021-12-17 |  |  |  | -3725.64 | -3725.64 | [16 empty] | 12/22/22 - PO and WO closed - ready to be closed by accounting. 3.3.22 - complete. Feb var due to dropping an unnecessary accural. | 2022-12-22 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Eastern Iowa | BETAR - BET CEDAR RAPIDS |  | -7451 | 0 |  |  | -7149 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41546 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Int - Tanks
Cedar Rapids Terminal Asphalt Upgrade at Entrance Gate | Item | Open | MCAP | BETAR00M2201 | Exempt | 2043675 | Gardner, Travis | West | 7. Closed | Drawdown | West | -1000 |  |  | -1000 | -1000 | 0 | Green |  |  |  | -1000 |  |  | 27000 |  |  | 27000 | Full | 27000 | 16044 |  | 16044 | No | Green | 2022-11-01 | 2022-11-02 | 2022-11-02 | 2022-12-30 | 2022-11-23 |  |  | -1000 | 0 | [17 empty] | 3/1/2023 - final invoice recieved and ready to close. 2/3/2023 - chasing down invoices. 1/4/2023 - This work was completed in november. waiting for invoices. 11/2/2022 - waiting for Nick to approve AFE so PO's can be cut. | 2023-03-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | BETAR - BET CEDAR RAPIDS |  | -1000 | 0 |  |  | 17044 |  | Gardner, Travis | Spitz, Nicholas P. |  |  | 1 | 46108 |  | Gardner, Travis | Independent | Aqua | 2022-10-21 | Other Programs
Cedar Rapids Terminal Driver Kiosks Replacement | Item | Open | MCAP | BETAR00M2303 | Exempt | 2094859 | Scott, Cory | West | 3. Active | Defined | West |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 |  |  | 46988 |  |  | 46988 | Phase | 46988 |  | 50000 | 50000 | No | Green | 2023-06-01 | 2023-03-10 | 2023-03-10 | 2023-08-20 | 2023-07-31 | [13 empty] | 10000 |  | 15000 | 25000 |  |  |  |  | 5/3/2023 - Moved forecast to fall. Awaiting details to find out if the 48 x 48 XP Kiosk is an option. If so, not concrete would need to be replaced. 4/7/2023 - Electrical investigation took place. 3/10/2023 - AFE submitted for Engineering/Kiosk Order/Electrical investigation. 2/25/2023 - Meet with electrical contractor for quote. They will perform an investigation on conduit runs. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | BETAR - BET CEDAR RAPIDS |  |  | 10000 | 40000 |  |  |  | Gardner, Travis | Smith, Todd W. | N/A |  | 1 | 25793 |  | Guest, ProSight | Independent | Aqua | 2017-09-12 | Other Programs
CG415GE - 2022 Buckeye Criteria Digs | Item | Open | MCAP | CG415BJM2202 | Maintenance Framework | 2003374 | Burns, Richard | West | 7. Closed | Defined | Pipeline Digs | 383 |  |  | 383.38 | 383 | 0 | Green |  |  |  | 383 |  |  | 261000 |  |  | 261000 | Full | 261000 | 243454 |  | 243454 | No | Green | 2022-08-01 | 2022-07-19 | 2022-07-19 | 2022-12-31 | 2022-08-29 |  |  | 383.38 | [18 empty] | 2/1/23 - moved back to closed. 1/17/23 - moved back to operational, since Acct. added in a re-class cost in December, after 1/3/23. 1/3/23 - closed by PM. 12/2/22 - Ready to close. 11/1/22 - variance is Percheron invoices. 10/3/22 - variance is last month accrual vs. actual invoice ($1370), payroll, ($1203) Third party/PPS ($81), p-card ($15), and Percheron ($8076). (9/7/22 - Job book submitted & complete on 9/6/22. Ready to close other than post job evaluation. 9/1/22 - variance is accrued. Overage is from forecasting was conservative; last dig required a 54' B-sleeve adding a week to the schedule. 8/31/22 - all 3 digs completed on 8/29/22. 7/20/22 - digs to start end of July. 7/5/22 - Switched over digs from Ryan Taylor to Rich. He volunteered to take them. | 2023-02-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Toledo | CG415BJ - CYGNET TO BELLEVUE-#1-E |  | 383 | 0 |  |  | 243071 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40993 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
CG415GE - DIG SHEETS (1) DOT-180 - Due 06-25-23 | Item | Open | MCAP | CG415BJM2302 | Maintenance Framework | 2094424 | Burns, Richard | West | 3. Active | Drawdown | Pipeline Digs |  | 115000 |  | 115000 | 60000 | 55000 | Red |  | 66440 | 66440 | 48560 |  |  | 66440 |  |  | 66440 | Full | 66440 |  | 115000 | 115000 | Yes | Red | 2023-05-01 | 2023-04-12 | 2023-04-12 | 2023-06-25 | 2023-06-25 | [12 empty] | 60000 | 55000 | [7 empty] | 5/1/23 - pushed forecast to June as we may not get to it until then. 4/3/23 - AFE submitted on 3/31/23. 3/31/23 - one DOT-180 dig due 6/25/23. Plan to do in May at the latest. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Toledo | CG415BJ - CYGNET TO BELLEVUE-#1-E |  |  | 115000 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46863 |  | Burns, Richard | Independent | Aqua | 2023-03-31
CG415GE - DIG SHEETS (7) | Item | Open | MCAP | CG415BJM2301 | Maintenance Framework | 2094162, 2094306, 2094307, 2094308, 2094309, 2094310, 2094311 | Cullison, Daniel | West | 3. Active | Drawdown | Pipeline Digs | 108554 | 281408 |  | 389961.95 | 421614 | -31652 | Yellow |  | 499068 | 499068 | -109106 |  |  | 499068 |  |  | 499068 | Full | 499068 | 108554 | 281408 | 389962 | No | Green | 2023-04-01 | 2023-04-10 | 2023-04-10 | 2023-08-30 | 2023-08-30 | [5 empty] | 108553.95 |  |  | 108554 | Red |  | WorkAhead of Schedule | 215306 | 66102 | [7 empty] | 5/2/30: The variance is due to the status of the AFE as of last month 3/30/23: AFE submitted 3/27/23: -AFE completed -Confirmed b-sleeve material available at stations 3/24/23: Met with integrity and operations. F-0448662 will be removed from this job and added to integrity cut out program 3/23/23: All sites are staked 3/20/23: Requested quotes from contractors 3/7/23: -documentation sent to OMs and pipeliners -WOs created -Job added to OPPM 3/10/23: digs issued 3/3/23. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Toledo | CG415BJ - CYGNET TO BELLEVUE-#1-E |  |  | 389962 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46756 |  | Burns, Richard | Independent | Aqua | 2023-03-10
CG415GE – Immediate Dig from 2022 GEO+MFL | Item | Open | MCAP | CG415BJM2203 | Maintenance Framework | 2051787 | Bost, Jason | West | 6. Operational | Defined | Pipeline Digs | -4655 |  |  | -4655.44 | -6202 | 1547 | Red |  |  |  | -4655 |  |  | 52933 |  |  | 52933 | Full | 52933 | 47104 |  | 47104 | No | Green | 2022-12-01 | 2023-01-17 | 2023-01-17 | 2022-12-31 | 2022-12-31 |  |  | 22887.77 | -29302.59 | 212.52 | 1546.86 |  |  | 1547 | Red |  | Contractor/Vendor Issue | [9 empty] | 5/1/23 - Variance is from April Reclass ($139), and Percheron invoice ($1408). 4/3/23 - Dig Complete. JDE dig docs uploaded. 3/1/23 - Variance is accrual from January. $30,461 accrued in January to account for reclass that didn't hit project as of 2/1. Reclass is now showing as hitting the project in January. 1/31/23 - Variance is reclass that have not hit the project yet (Degen - $30461). 1/4/23 - Immediate dig issued on 12/2/11.and completed on 1 Integrity initially entered $90k in Dec. forecast. Interim AFE for $75k was submitted on 12/10 and approved on 12/16. Accrual is for Degen and MNT. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Toledo | CG415BJ - CYGNET TO BELLEVUE-#1-E |  | -6202 | 1547 |  |  | 51759 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46347 |  | Guest, ProSight | Independent | Aqua | 2022-12-09 | Int- Planned Digs
CG415GE line investigation | Item | Open | MEXP | GA415GEE2301 | Maintenance Framework | 2095922 | Burns, Richard | West | 3. Active | Emergent | West | 132465 | 130000 |  | 262465.01 |  | 262465 | Red |  |  |  | 262465 | [6 empty] | Interim |  | 132465 | 130000 | 262465 | Yes | Red | 2023-04-01 |  |  |  | 2023-04-30 | [5 empty] | 132465.01 |  |  | 132465 | Red |  | Other | 130000 | [8 empty] | 5/1/23 - variance is because project was just created in April to check 415 line when a natural gas leak was found on the 425. Interim AFE submitted on 4/5/23, approved on 4/10/23. Expect to be there another 2-3 weeks. | 2023-05-01 |  |  | West | Pipelines and Terminals | Station/Terminal |  | Mantua | GA415GE - AURORA TO MANTUA-#1-E |  |  | 262465 |  |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 46882 |  | Burns, Richard | Independent | Aqua | 2023-04-05
Cincinnati - Asphalt Truck rack fall protection - BETCX | Item | Open | MCAP | BETCX00M2302 | Maintenance Framework | 2096401 | Roknich, Hunter | West | 3. Active | Defined | Truck Racks | 30580 | 140000 |  | 170580 | 160000 | 10580 | Yellow | 160000 |  | 160000 | 10580 |  |  | 106363 |  |  | 106363 | Phase | 106363 | 30580 | 140000 | 170580 | No | Green | 2023-04-01 | 2023-03-28 | 2023-03-28 | 2023-10-30 | 2023-05-31 | [5 empty] | 30580 | 20000 | 20000 | 10580 | Red | [6 empty] | 45000 | 95000 |  |  |  | 5/2/2023 - Diamond Z working on structural engineering analysis 4/4/2023 - purchase order issued to Diamond Z for engineering. 10/11/2022 - Quote received on Bullard fall protection for $42k. Discussion with operation on appropriate scope and path forward. 8/2/2022 - reforecasted to 2023 and moved to DD. Quote received for 2 fall protection options and 1 installation quote. All quotes significantly overbudget. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Southern Ohio | BETCX - BET CINCINNATI TERMINAL |  |  | 30580 | 45000 | 95000 |  |  | Younce, Michael | Gardner, Travis W. |  |  | 1 | 41593 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
Cincinnati - Truck Entrance Gate & Exit Gate - BETCX | Item | Open | MCAP | BETCX00M2204 | Exempt | 2023395 | Gardner, Travis | West | 6. Operational | Drawdown | West | 6079 |  |  | 6079.14 | 6079 | 0 | Green |  |  |  | 6079 |  |  | 29000 |  |  | 29000 | Full | 29000 | 26278 |  | 26278 | No | Green | 2022-12-01 | 2022-09-23 | 2022-09-23 | 2022-11-26 | 2022-12-31 |  |  | 5817.36 | 261.78 | [17 empty] | 3/1/2023 - invoice recieved and ready to close. 2/2/2023 - project is now complete. 1/4/2023 - vendor completed 80% of the gate install. waiting on electrical contractor that is scheduled for 1/3. 12/2/2022 - vendor awaiting material. install pushed to Dec. 11/1/2022 - PO wasn't sent to vendor. working on getting this scheduled. 9/22/2022 - emergent project pull ahead 2023 project. | 2023-03-01 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Southern Ohio | BETCX - BET CINCINNATI TERMINAL |  | 6079 | 0 |  |  | 20199 |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 41594 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
Cincinnati Circuit 1, 2, and 3 Phase 2 Insulated Piping Inspection | Item | Open | MEXP | BETCX00E2205 | Exempt | 1980280 | Roknich, Hunter | West | 6. Operational | Defined | Facility Integrity | 0 |  |  | 0 | 0 | 0 | Green |  |  |  | 0 |  |  | 76000 |  |  | 76000 | Phase | 76000 | 53729 |  | 53729 | No | Green | 2022-08-01 | 2022-05-11 | 2022-05-11 | 2022-12-31 | 2022-12-31 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | Green | [11 empty] | 3/2/2023 - Waiting on instruction from Facility Integrity for path forward 2/2/2023 - Waiting on instruction from Facility Integrity for path forward 1/4/2023 - Waiting on instruction from Facility Integrity for path forward 12/2/2022 - Working with Facility Integrity to determine path forward 11/2/2022 - Working with Facility Integrity to determine path forward 10/3/2022 - Inspection complete. Iso drawings given on 10/3. Still need to schedule with WM for asbestos testing 9/2/2022 - Work in progress. Stalled due to need for insulation asbestos testing. 8/2/2022 - Start date early September 7/5/2022- Purchase order issued. Prelim start date 8/1 6/2/2022 - Call week of 6/6 to discuss scheduling with IAG. 5/12/2022 - Current forecast for July. Working with IAG on scheduling. AFE approved. | 2023-03-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Southern Ohio | BETCX - BET CINCINNATI TERMINAL |  | 0 | 0 |  |  | 53729 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 41177 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Accel Corr & FI
Cincinnati Shoreside Erosion and Gangway Foundation | Item | Open | MCAP | BETCX00M2203 | Maintenance Framework | 2023044 | Parker, Brian | West | 3. Active | Defined | Marine | 974 | 315000 |  | 315973.97 | 315885 | 89 | Yellow | 300000 |  | 300000 | 15974 |  |  | 56000 |  |  | 56000 | Phase | 56000 | 35257 | 315000 | 350257 | No | Green | 2022-10-01 | 2022-09-19 | 2022-09-19 | 2023-10-31 | 2023-08-31 |  |  | 711.77 | 85.02 | 88.04 | 89.14 |  |  | 89 | Red |  |  |  |  | 15000 | 150000 | 150000 |  |  |  |  | 4/30/23 - re-accruing 16,493 for TAS in Apr. Will get a final SOW review call scheduled in early May with stakeholders to review before going out to bid. 4/1/23 - re-accruing 16,493 for TAS in Mar. 3/1/23 - Var is due to not getting IFB drawing set issued in Feb. Re-accruing 16,493 for TAS in Feb. After discussion with TAS yesterday, going to have them issue IFB drawing set and circulate with stakeholders one last time before going out to bid. 15,000 in May is for possible geotechnical work. 2/3/23 - re-accruing 16,493 for TAS in Feb. Moved 15,000 out to Apr. Will email the IFR drawing to stakeholders for comments before moving to IFB drawing set. 1/2/23 - accruing 16,493 in Dec for End & Design - will schedule an Eng review in the 2nd full week of Jan. 11/30/22 - reviewed current Eng & Des on Nov 10th with management and program owner. 10/31/22 - too late in the year to get geotech contactors on barges out to the site so this will occur in 2023 - will have most of the design completed in 2022. 9/29/22 - PO issued to TAS on Sep 22nd. 9/3/22 - Eng & Design will be completed in 2022 - 2023 FCST is for construction. 8/2/2022 - Arcadis is looking at the design requirements for Markella 7/8/2022 - Arcadis is looking at the design requirements for Markella | 2023-04-30 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Southern Ohio | BETCX - BET CINCINNATI TERMINAL |  | 885 | 89 | 315000 |  | 34283 |  | Spari, Markella | Gardner, Travis W. |  |  | 1 | 41533 |  | Administrator, System | Independent | Aqua | 2021-08-19 | Marine
Cincinnati Terminal (BETCX) Tank 13 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | BETCX00E2301 | Maintenance Framework | 2084798 | Arch, Stefan | West | 6. Operational | Defined | Tanks | 11630 |  |  | 11630 | 11630 | 0 | Green | 10000 |  | 10000 | 1630 |  |  | 12158 |  |  | 12158 | Full | 12158 | 11630 |  | 11630 | No | Green | 2023-03-01 | 2023-02-08 | 2023-02-08 | 2023-12-31 | 2023-03-10 |  |  |  |  | 11630 | 0 |  |  | 0 | Green | [11 empty] | 4/3/2023 - Up Close seal inspection completed and found the secondary seal needing replaced. Project is complete. No additional funding needed. Seal replacement project approved. 3/1/2023 - Planning to complete on 3/9 by Phillips. Scheduling and Operations are aware. 2/1/2023 - Stakeholder meeting held on 1/26/2023 with scheduling and Operations. Funding routed for the 2023 West Region Up Close seal inspection AFE. Planning to complete work at the beginning of March. Phillips to perform seal inspection. | 2023-04-06 |  |  | West | Pipelines and Terminals | Tank Integrity |  | Southern Ohio | BETCX - BET CINCINNATI TERMINAL |  | 11630 | 0 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44794 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Cincinnati Terminal (BETCX) Tank 15 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | BETCX00E2302 | Maintenance Framework | 2084800 | Arch, Stefan | West | 3. Active | Defined | Tanks |  | 10855 |  | 10855 | 10855 | 0 | Green | 10000 |  | 10000 | 855 |  |  | 12158 |  |  | 12158 | Full | 12158 |  | 10855 | 10855 | No | Green | 2023-07-01 | 2023-02-08 | 2023-02-08 | 2023-12-31 | 2023-08-31 | [14 empty] | 10855 | [6 empty] | 5/1/2023 - No updates, planning to complete in July. 4/3/2023 - No updates, planning to complete in July. 3/1/2023 - Planning to complete in July. No changes made. 2/1/2023 - Stakeholder meeting held on 1/26/2023 with scheduling and Operations. Funding routed for the 2023 West Region Up Close seal inspection AFE. Planning to complete work in July. Phillips to perform seal inspection. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Southern Ohio | BETCX - BET CINCINNATI TERMINAL |  |  | 0 | 10855 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44795 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Cincinnati Terminal (BETCX) Tank 13 Secondary Seal Replacement | Item | Open | MCAP | BETCX00M2301 | Maintenance Framework | 2095580 | Arch, Stefan | West | 6. Operational | Drawdown | Tanks | 43265 |  |  | 43264.5 | 52000 | -8736 | Red |  |  |  | 43265 |  |  | 52221 |  |  | 52221 | Full | 52221 | 43265 | 0 | 43265 | No | Green | 2023-03-01 | 2023-03-17 | 2023-03-17 | 2023-05-26 | 2023-05-26 |  |  |  |  | 9500 | 33764.5 | 42500 | 42500 | -8736 | Red | [11 empty] | 5/1/2023 - Seal replaced on 4/22 by Phillips. Up Close seal inspection form completed by Phillips and uploaded to BEST. No additional forecasting required, project is complete. 4/3/2023 - Project to replace secondary seal on tank 13 due to an in service up close seal inspection. Forecasting was placed in 2024, not 2023. It has been updated. Planning to complete in April. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Southern Ohio | BETCX - BET CINCINNATI TERMINAL |  | 9500 | 33765 |  |  |  | 0 | Stine, Carlton | Stine, Carlton |  |  | 1 | 46785 |  | Arch, Stefan | Independent | Aqua | 2023-03-14
Cincinnati Terminal API 570 Inspection | Item | Open | MEXP | BETCX00E2204 | Exempt | 1980279 | Roknich, Hunter | West | 6. Operational | Defined | Facility Integrity | -1957 |  |  | -1957 | -1957 | 0 | Green |  |  |  | -1957 |  |  | 36000 |  |  | 36000 | Phase | 36000 | 30071 |  | 30071 | No | Green | 2022-08-01 | 2022-05-11 | 2022-05-11 | 2022-12-31 | 2022-09-02 |  |  | 0 | -1957 | [17 empty] | 12/23/22 - PO and WO closed - ready to be closed by accounting. 9/2/2022 - Work completed. Change order in progress due to scope/schedule change. 8/2/2022 - Estimated start mid August 7/5/2022- Purchase order issued. Prelim start date 8/16 6/2/2022 - Call week of 6/6 to discuss scheduling with IAG. 5/12/2022 - Current forecast for June. Working with IAG on scheduling. AFE approved. | 2022-12-23 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Southern Ohio | BETCX - BET CINCINNATI TERMINAL |  | -1957 | 0 |  |  | 32028 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 37490 |  | Administrator, System | Independent | Aqua | 2020-08-05 | Int - Planned Corr & FI
Cincinnati Terminal Asphalt Line Replacement | Item | Open | MCAP | BETCX00M2201 | Maintenance Framework | 1991423 | Roknich, Hunter | West | 6. Operational | Emergent | Pipeline Replacements | 7071 |  |  | 7071.36 | 4694 | 2378 | Red |  |  |  | 7071 |  |  | 1541000 |  | 779000 | 2320000 | Supplemental | 2320000 | 2105217 |  | 2105217 | No | Green | 2022-07-01 | 2022-08-28 | 2022-08-28 | 2022-09-30 | 2022-09-27 |  |  | -29070.04 | 20000 | 13763.62 | 2377.78 |  |  | 2378 | Red | [11 empty] | 2/2/2023 - Overaccrued contractor cost. Ended up being less than expected 1/4/2023 - Variance due to contractor availability for completing insulation installation. Moving forecast to Feb 2023 12/2/2022 - Variance due to contractor availability for completing insulation installation 11/9/2022 - Additional costs in October for Waste Management and shipping. DC 10/10/2022 - Work completed. Line RTS. Variance due to forecast. Change orders made because of scope change and schedule estimate. 9/2/2022 - Variance due to additional contractor costs, waste disposal, and schedule change. Work to be completed by 9/7. September costs to include construction, land repair, waste disposal, inspector, annual pressure test 8/2/2022 - Variance due to additional contractor costs due to site issues due to unforeseen circumstances. Project forecast EAC to be around 950k. Estimated project completion mid/late August. | 2023-02-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Southern Ohio | BETCX - BET CINCINNATI TERMINAL |  | 4694 | 2378 |  |  | 2098145 |  | Oldham, David | Gardner, Travis W. |  |  | 1 | 44041 |  | Gardner, Travis | Independent | Aqua | 2022-06-23 | Int - Planned Corr & FI
Cincinnati Truck Scale BETCX | Item | Open | MCAP | BETCX00M2202 | Maintenance Framework | 2013784 | Roknich, Hunter | West | 4. On-Hold | Defined | Truck Racks | 25988 | 72790 |  | 98777.5 | 83778 | 15000 | Red | 163200 | 40800 | 204000 | -105223 |  |  | 97000 |  | 107000 | 97000 | Supplemental | 204000 | 51616 | 145580 | 197196 | No | Green | 2022-10-01 | 2022-08-29 | 2022-08-29 | 2023-06-30 | 2023-11-30 |  |  | 0 | 24599.9 | 1387.6 | [13 empty] | 57790 | 15000 |  | 5/2/2023 - Moved to "On-Hold" due to long lead time of material. Supplemental AFE in workflow approval process. First scale schedule to be delivered early November. 4/4/2023 - Need to submit supplemental AFE. Both truck scales are on order. One scale to be installed in 2023. One to be installed in 2024 3/2/2023 - ECO approved. Purchase order for second scale entered. 2/2/2023 - Waiting for initial invoicing. Will be submitting ECO and purchasing second scale in Feb. due to lead time. 1/4/2023 - Waiting for initial invoicing 12/2/2022 - Waiting for initial invoicing 11/2/2022 - First purchase order for truck scale has been issued. Accrual for 30% down due at signing 10/3/2022 - Variance due to needing to update vendor in JDE. Purchasing will occur in October. 8/2/2022 - Scale to be purchased Q3. It is 40 week lead time. Install to occur Q1 CY+1 3/2/22 - Have one quote that needs updated. Working with supply chain to find 2 other vendors for bid. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Southern Ohio | BETCX - BET CINCINNATI TERMINAL |  | 25988 | 0 |  | 72790 | 25628 | 72790 | Younce, Michael | Gardner, Travis W. |  |  | 1 | 41591 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
CL999A5-1 - DIG SHEETS (1) DOT-60 - Due 01-20-23 | Item | Open | MCAP | CL999A5M2301 | Maintenance Framework | 2074159 | Burns, Richard | West | 6. Operational | Drawdown | Pipeline Digs | 48085 |  |  | 48085.37 | 47865 | 221 | Yellow |  | 55267 | 55267 | -7182 |  |  | 55267 |  |  | 55267 | Full | 55267 | 48085 |  | 48085 | No | Green | 2023-01-01 | 2023-02-02 | 2023-02-02 | 2023-01-20 | 2023-01-20 |  |  | 45156.43 | 2380.59 | 327.74 | 220.61 |  |  | 221 | Red |  | Other | [9 empty] | 5/1/23 - variance is internal labor. 4/3/23 - variance is internal labor. 3/1/23 - variance is internal labor. 2/22/23 - No supplemental is required. Not sure why this is showing an EAC of $105,156. Project is complete; total Is about $45K as shown in the actuals. Closed remaining PO amounts in JDE. 2/1/23 - Variance is partially accrued. Had issues with WO in JDE new WBS system, could not charge time to it. Rest is dig completed ahead of schedule. 1/30/23 - Dig completed on 1/18/23. 1/6/23 - DOT-60 day dig issued on 11/21/22, due 1/20/23 that slipped through the cracks. Interim AFE submitted 1/3/23, approved today. Expected start date is 1/11/23. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Indianapolis | CL999A5 - CLERMONT TO BET RACEWAY |  | 47865 | 221 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46406 |  | Burns, Richard | Independent | Aqua | 2023-01-04 | Int- Planned Digs
Clermont Station Control Valve Replacement | Item | Open | MCAP | CL00000M2202 | Maintenance Framework | 1980119 | Smith, Kyle | West | 6. Operational | Defined | Valves | -3304 |  |  | -3303.66 | -3304 | 0 | Green |  |  |  | -3304 |  |  | 116000 |  |  | 116000 | Full | 116000 | 93471 |  | 93471 | No | Green | 2022-10-01 | 2022-05-09 | 2022-05-09 | 2022-11-18 | 2022-12-31 |  |  | 2177.44 | -5481.1 | 0 | 0 |  |  | 0 | Green | [11 empty] | 1/1/23 Work Completed, variance is due to Roberts coming in under quote. | 2023-01-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Indianapolis | CL - CLERMONT TERMINAL |  | -3304 | 0 |  |  | 96775 |  | Oey, Alex | Gardner, Dale |  |  | 1 | 2005 |  | Stewart, Richard | Independent | Aqua | 2012-09-15 | Other Programs
Clermont Station Relief Valve Replacement | Item | Open | MCAP | CL00000M2201 | Maintenance Framework | 1945640 | Smith, Kyle | West | 6. Operational | Emergent | Valves | 195 |  |  | 194.76 |  | 195 | Red |  |  |  | 195 |  |  | 48000 |  |  | 48000 | Full | 48000 | 42049 |  | 42049 | No | Green | 2022-03-01 | 2022-02-02 | 2022-02-02 | 2022-05-30 | 2022-10-31 | [5 empty] | 194.76 |  |  | 195 | Red | [11 empty] | 12/1/22 Work completed | 2022-12-01 | Hill, Elizabeth | Parker, Brian | West | Pipelines and Terminals | Operating Infrastructure |  | Indianapolis | CL - CLERMONT TERMINAL |  |  | 195 |  |  | 41854 |  | Oey, Alex | Gardner, Travis W. |  |  | 1 | 42788 |  | Guest, ProSight | Independent |  | 2022-01-25 | Other Programs
Cleveland Terminal (BETGF) Tank C-3 Gauge Repair | Item | Open | MEXP | BETGF00E2202 | Maintenance Framework | 2052881 | Arch, Stefan | West | 3. Active | Emergent | Tanks | 16226 | 12000 |  | 28226 | 28226 | 0 | Green |  |  |  | 28226 |  |  | 26000 |  |  | 26000 | Full | 26000 | 16226 | 12000 | 28226 | No | Green | 2023-03-01 | 2022-12-19 | 2022-12-19 | 2023-01-31 | 2023-04-28 |  |  |  |  | 16226 | 0 | 12000 | 12000 | -12000 | Red |  | Buckeye/Customer Schedule | 12000 | [8 empty] | 5/1/2023 - No work completed in April. due to Phillips availibility. Re-forcasted to May. 4/3/2023 - Phillips was on site to complete the up close seal inspection on 3/13 but did not feel comfortable with the weather conditions on top of the tank. Working with Phillips to reschedule. 3/1/2023 - Planning to complete on 3/13, operations and scheduling on board. An inspector will be on site. No work completed in February. 2/1/2023 - No work completed in January due to product scheduling not matching with Phillips availability. Safe work plan was approved by all necessary parties. Planning to complete beginning of March. 1/3/2023 - Project to repair gauge tape and complete up close seal inspection on tank C-3. AFE approved late December and did not have time to complete in December. Planning to complete in January. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | North East Ohio | BETGF - BET CLEVELAND TERMINAL |  | 16226 | 12000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46350 |  | Perry, Betty | Independent | Aqua | 2022-12-13 | Int - Tanks
Cleveland Terminal FPS Suppression Upgrades | Item | Open | MCAP | BETGF00M2201 | Maintenance Framework | 1971760 | Bost, Jason | West | 3. Active | Defined | Fire Protection | 32426 | 650000 |  | 682426.3 | 678055 | 4371 | Yellow | 650000 |  | 650000 | 32426 |  |  | 145000 |  |  | 145000 | Phase | 145000 | 306330 | 650000 | 956330 | No | Green | 2022-05-01 | 2022-05-02 | 2022-05-02 | 2022-12-31 | 2023-12-31 |  |  | 6873.78 | 11737.06 | 9444.12 | 4371.34 |  |  | 4371 | Red |  | Other | 5000 |  |  |  | 150000 | 300000 | 195000 |  |  | 5/1/23 - Variance is ESDC invoice for engineering assistance during appeals board meeting with the City of Cleveland. 4/3/23 - Variance is ESDC invoice for engineering assistance during discussions with the FD. Appeals meeting pushed back into April. 3/1/23 - Accrual is for ESDC. Meeting with the FD proved to be largely unproductive. Working towards the appeals hearing scheduled for 3/15. 1/31/23 - Accrual is for Foam Tech, ESDC, and Diamond Z. Meeting with the Cleveland FD scheduled for 1/31/23. Board of Appeal meeting scheduled for 3/15/23. 1/4/23 - Stakeholder discussion to review path forward based on recent adjudication letter received by the Cleveland FD. Appeal to letter has bee submitted and proposed meeting with FD expected in January/February. Accrual is for Furey, Foam Tech, and ESDC. 12/15 to 12/5/22 - Material started to be delivered (Foam chambers). Received feedback from the FD on the design of the new system. Stakeholder review scheduled on 12/5 with legal to discuss path forward. 11/1/22 - Consolidated & JCI visited site for scope walkdown. Awaiting bids. Pump, foam, foam chambers ordered on 10/18. 10/1/22 - Bid event in progress, out of 4 contractors included, only 1 accepted the event. Adding more contractors and awaiting their response. Purchasing fire pump, fire dos, foam, and foam tank in 2022. 9/9/2022 - reduced forecast by 482K due uncertainly of permit approvals. 9/1/22 - Engineering and design complete by ESDC. Accrual is for ESDC invoice. Bid event started. 8/1/22 - Drawings complete. Diamond Z to present drawings to the City for permitting. 7/5/22 - Accrual is for ESDC. ESDC continuing to develop drawing for new system. Once drawing is complete, a bid event will take place for mechanical work. 6/1/22 - Scan of facility completed. ESDC is now working on drawings for upgrades. 5/3/22 - Phase 1 AFE approved on 5/2, E&D to begin in May. 4/4/22 - Program Manager met with new Fire Marshal, stakeholders approved moving forward with E&D. Site visit with ESDC to be scheduled in April. 3/2/22 - Scope walk down with program manager, asset team, and PM. Working with ESDC to complete Engineering and Design drawings for bid event. 2/2/22 - No Change 1/3/22 - No Change | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | North East Ohio | BETGF - BET CLEVELAND TERMINAL |  | 28055 | 9371 | 150000 | 495000 | 273904 |  | Jakubowski, Gregory | Jakubowski, Greg |  |  | 1 | 41659 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
CN165ZI Test Station Repairs | Item | Open | MEXP | CN165ZIE2201 | Maintenance Framework | 2014078 | Logan, Rob | West | 7. Closed | Drawdown | Cathodic Protection | 21 |  |  | 21.49 | 21 | 0 | Green |  |  |  | 21 |  |  | 14000 |  |  | 14000 | Full | 14000 | 9463 |  | 9463 | No | Green | 2022-12-01 | 2022-08-31 | 2022-08-31 | 2022-10-31 | 2022-12-31 |  |  | 21.49 | [18 empty] | 03/2023 Project Closed I will contact Barbara to get removed 1/4/2023 - Variance is due to forecast being locked. drawdown project. work completed. Work came in under budet12/5/2022 PO Issued to Roberts awaiting contact from contractor for scheduling 11/1/2022 - work is scheduled for November. 10/4/2022 Awaiting contractor availability 9/1/22 - PO requested on 8/31/22 for Roberts Pipeline | 2023-03-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Indianapolis | CN165ZI - CARBON TO ZIONSVILLE |  | 21 | 0 |  |  | 9442 |  | Geib, Rob | Shook, Mark B. | N/A |  | 1 | 45736 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-08-31 | Int - Planned Corr & FI
Columbus East (BETCE) - Secondary containment improvements | Item | Open | MEXP | BETCE00E2302 | Maintenance Framework | 2111235 | Smith, Kyle | West | 3. Active | Defined | Secondary Containment |  | 48000 |  | 48000 | 48000 | 0 | Green | 48000 |  | 48000 | 0 |  |  | 8000 |  |  | 8000 | Phase | 8000 |  | 48000 | 48000 | No | Green | 2023-05-01 | 2023-04-18 | 2023-04-18 | 2023-07-30 | 2023-05-31 | [6 empty] | 8000 | 8000 | -8000 | Red |  |  | 8000 |  |  | 40000 | [5 empty] | 4/28/23 Cut PO to Diamond Z for engineering | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Southern Ohio | BETCE - BET COLUMBUS EAST TERMINAL |  |  | 8000 | 40000 |  |  |  | Spari, Markella | Spari, Markella |  |  | 1 | 45166 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
Columbus East Terminal (BETCE) Tank 53 OOS Cleaning and Idle | Item | Open | MEXP | BETCE00E2301 | Maintenance Framework | 2076577 | Arch, Stefan | West | 5. Deferred | Defined | Tanks |  |  |  | 0 | 0 | 0 | Green | 12000 |  | 12000 | -12000 |  |  | 13041 |  |  | 13041 | Phase | 13041 |  | 12000 | 12000 | No | Green | 2024-06-01 | 2023-01-20 | 2023-01-20 | 2023-12-31 | 2023-07-31 | [21 empty] | 4/10/2023 - Pushed forecast to 2024 per leadrship request. 4/3/2023 - Discussion with Travis regarding the possible deferral of this project, leaving forecasting in June for now. Operations did not get a chance to look into the tank for the residual product. 3/1/2023 - Stakeholder call held on 2/24. Waiting to confirm product is in the tank with manlift that will be on site for side blending. Planning to complete in June if product is in tank. Tank blinded, air gapped, and sign isntalled. 2/1/2023 - Project to clean and idle tank C-53. Planning to complete in June. Tank is a small pencil tank with residual product. Tank will be blinded. | 2023-04-10 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Southern Ohio | BETCE - BET COLUMBUS EAST TERMINAL |  |  | 0 |  |  |  | 12000 | Stine, Carlton | Stine, Carlton |  |  | 1 | 44906 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Columbus South Tank 4, 7, 9 High Level Alarms | Item | Open | MCAP | BETIL00M2203 | Maintenance Framework | 2003376 | Arch, Stefan | West | 6. Operational | Defined | Instrumentation & Controls | 0 |  |  | 0 | 0 | 0 | Green |  |  |  | 0 |  |  | 113000 |  |  | 113000 | Full | 113000 | 111029 |  | 111029 | No | Green | 2022-07-01 | 2022-07-19 | 2022-07-19 | 2022-12-31 | 2022-12-16 |  |  | 0 | [18 empty] | 5/1/2023 - Waiting on tank 4 and 9 wires to be terminated at the panel by Doug Olds. 4/6/2023 - Waiting on tank 4 and 9 wires to be terminated at the panel by Doug Olds. 3/1/2023 - Waiting on tank 4 and 9 wires to be terminated at the panel by Doug Olds. 2/1/2023 - All tank alarms have been set to correct high levels. Waiting on tank 4 and 9 wires to be terminated in the panel by Doug Olds. 1/3/2022 - Project is complete, waiting for Doug Olds to reset high level alarms on tanks 4 and 9. Small forecast in January for Doug to complete the resetting. 12/1/202 - Tank 1 wiring was discovered to be in poor condition, added to this project. Herbst completed all electrical work in November. Waiting on tech to complete wire transition and high-level setting. Small forecast in December for the tech work. This will be completed in December. 11/1/2022 - Work began in October. Forecast a little lower than anticipated to complete. Took longer to install tank 7 stairs, requiring Herbst to come back on 10/31 to finish install. Forecasting for October includes remaining electrical cost and overhead for installation of magnetrols. 10/3/2022 - Herbst Electric to mobilize to site on 10/3 to begin work. Herbst to run new wire and conduit from the PLC to tanks 4, 7, and 9. Tank 7 conduit will be installed on the new stairs. Small variance in September due to not beginning until October. 9/1/2022 - Planning to complete installation in September and October. Lining up install with the modifications to tank 7 for the new high level alarm. Herbst will install the cables and Consolidated will install the new nozzles. Planning to have all the new wires, nozzles, and Magnetrols installed by the end of October. Forecast for September is begin installation and inspector costs. 8/1/2022 - AFE approved for extra amount on the project. Issued award to Herbst Electric and sent PO. Walking down the project with Herbst on 8/2. Variance in July dueto ordering material quicker than anticipated. Planning to install wiring in late Augustor September. 7/1/2022 - Waiting on quotes back from two additional contractors. Pricingis much higher than budgeted for the whole project. Planning to submit AFE in July.6/1/2022 - Waiting for quotes. Planning to submit AFE in June. 5/2/2022 - Received quotes back from contractors for the work. Quotes came back higher than budget number, planning to develop AFE in May and route for approval. Pushed forecast from June to July. 4/1/2022 - Project walkdown with contractors completed on 3/22. Waiting on quotes to come back. Will submit AFE after. This project goes along the tank 7 stairs. I am also waiting for quotes for the stair replacement so I can figure out the best way to install the new high level alarm on tank 7. Reforecast due to pushing out till tank 7 stairs is designed and installed. . 2/28/2022 - Project walkdown with Ops on 1/31. Developed scope, will send for leadership review in March. Working to develop scope for tank 7 stairs which goes hand in hand with this project. Talked with Mohammad about previous high level installation at BETIL. 1/28/2022 - Walkdown planned for 1/31 with Ops | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Southern Ohio | BETIL - BET COLUMBUS SOUTH |  | 0 | 0 |  |  | 111029 |  | Forsey, Frank | Forehand, Adam | N/A |  | 1 | 31370 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Other Programs
Columbus South Terminal (BETIL) Tank 35 Dome Repairs | Item | Open | MEXP | BETIL00E2205 | Maintenance Framework | 2036082 | Arch, Stefan | West | 7. Closed | Emergent | Tanks | 634 |  |  | 633.55 | 634 | 0 | Green |  |  |  | 634 |  |  | 28000 |  |  | 28000 | Full | 28000 | 25901 |  | 25901 | No | Green | 2022-11-01 | 2022-10-05 | 2022-10-05 | 2022-12-31 | 2022-11-01 |  |  | 633.55 | [18 empty] | 4/3/2023 - PO's closed and WO moved to status 80. Project can be closed. 3/1/2023 - Project is completed. No more forecasting required. All invoices have been approved. WO can be closed. 2/1/2023 - Project is completed. No more forecasting required. All invoices have been approved. 1/3/2022 - Project is completed. No more forecasting required. All invoices have been approved. 12/1/2022 - Project is complete, Phillips installed new bird screen and closed all gaps on the geodome. No additional forecasting required. 11/1/2022 - Phillips arrived on site on 11/1 for installation of the bird screen. Forecasting for November includes dome repairs and inspector cost. Project should be finished by the end of 11/1 week. 10/3/2022 - New project arose from AOEs on tank 35 high level switch. Phillips inspected and provided quote to install bird screen on the edge of the geodome. AFE submitted and waiting for approval. Planning to complete in October or November, waiting on hearing back from Phillip's scheduling. | 2023-04-06 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Southern Ohio | BETIL - BET COLUMBUS SOUTH |  | 634 | 0 |  |  | 25268 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 45935 |  | Gardner, Travis | Independent | Aqua | 2022-09-30 | Int - Tanks
Columbus South Tk-7 Stairs Replaced | Item | Open | MCAP | BETIL00M2201 | Maintenance Framework | 1938068 | Arch, Stefan | West | 7. Closed | Defined | Tanks | 116 |  |  | 115.71 | 116 | 0 | Green |  |  |  | 116 |  |  | 150000 |  |  | 150000 | Phase | 150000 | 153507 |  | 153507 | No | Green | 2022-04-01 | 2022-01-11 | 2022-01-11 | 2022-01-03 | 2022-11-30 |  |  | 115.71 | [18 empty] | 4/6/2023 - All PO's are closed, need to move to status 80 and close out project. 3/1/2023 - Project is complete, no additional forecasting required. Need to close one PO. 2/1/2023 - Project is complete, no additional forecasting required. 1/3/2023 - Project is complete, tank refilled with jet. All invoices are paid. No additional forecasting required. 12/1/2022 - Stairs are installed, tank is RTS. Advanced touched up new stairs on the shell. Variance due to not forecasting painting in November. No additional forecasting required. 11/1/2022 - Stairs completed the week of 10/24. Tank strapped. Waiting for new level alarm wiring to be installed by Herbst this week. Once installed, Doug Olds will test the high-level alarm and it will go back into service. Forecasting for November includes touch up coating, button up, and inspector costs. 10/3/2022 - Allied to clean tank 10/3 through 10/7. Consolidated to be on site 10/10 for stair installation. Tank will be strapped from the gauge pole. Planning to have tank RTS end of October, beginning of November. Small variance in September due to pushing project back a week due to inspector availability. 9/1/2022 - Continued fabrication on the stairs. Planning to take tank OOS end of September and continue in October. Consolidated will be completing mechanical repairs and Allied will be cleaning the tank. Tank will be strapped. Planning to have tank RTS by the end of October. Forecast for September includes beginning the tank OOS and inspector costs. 8/1/2022 - Continued fabrication of the stairs. Planning to take tank OOS in September when marketing has slowed down from summer. 7/1/2022 - Continuing engineering and beginning fabrication on stairs. Small variance due to not forecasting any work in June. Planning to install stairs in September by taking tank OOS. 6/1/2022 - PO issued to Consolidated in May. Accrued costs for material and engineering. Planning to complete in September due to jet needs during August. Discussed timing with scheduling and marketing to take tank OOS for install. 5/2/2022 - Quotes received. Will make decision in beginning of May to cut a PO. Planning to take tank 7 OOS for the installation of a spiral staircase. Forecasting for May includes material, engineering, and preliminary fabrication for the stairs. 4/3/2022 - Walked down project with contractors on 3/22.Waiting to receive quotes back in unit pricing template. Planning to install a spiral staircase on tank with platform at existing door. Bring forecast forward to May for fabrication. 2/28/2022 - Project scope developed and sent to Leadership team. Prefer to install two tier platform to eliminate the need for a confined space entry versus leaving door in place. Tank will need to be taken OOS and cleaned for spiral staircase install. Once scope is approved, will send out to tank contractors for bid. Forecast in July and August for timeframe of project. 2/2/2022 - Walkdown with Ops on 1/31. Planning with level alarm replacement on tank 1/3/2022 - Walkdown with Ops planned for 1/31 | 2023-04-06 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Southern Ohio | BETIL - BET COLUMBUS SOUTH |  | 116 | 0 |  |  | 153391 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41894 |  | Guest, ProSight | Independent | Aqua | 2021-08-22 | Int - Tanks
Columbus South VRU Release Prevention | Item | Open | MCAP | BETIL00M2301 | Maintenance Framework | 2110636 | Scannell, Adam | West | 3. Active | Defined | Vapor Management |  | 61000 |  | 61000 | 61000 | 0 | Green | 61000 |  | 61000 | 0 |  |  | 22048 |  |  | 22048 | Phase | 22048 |  | 61000 | 61000 | No | Green | 2023-07-01 | 2023-03-30 | 2023-03-30 | 2023-07-31 | 2023-07-31 | [14 empty] | 11000 | 50000 | [5 empty] | 05/08/23 - Waiting on quote from contractor to for drain up and installation. Electrical contractor has already walked the job and waiting on estimate. Work should take place in early June when the VRU is down for a carbon change. Valve has been ordered. 4/11/23 - mrk - forecast pushed to july/aug to allow for time to develop engineering drawings. 03/25/23 - Phase I AFE submitted to the workflow. Phase I will cover the engineering for mechanical and electrical. Once design is complete the mechanical and electrical will be bid for installation. | 2023-05-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Southern Ohio | BETIL - BET COLUMBUS SOUTH |  |  | 0 | 61000 |  |  |  | Karl, Marissa |  |  |  | 1 | 44946 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Other Programs
Coraopolis Complex - Secondary Containment Upgrades | Item | Open | MCAP |  | Maintenance Framework |  | Roknich, Hunter | West | 2. Pending AFE |  | Secondary Containment |  | 170000 |  | 170000 | 170000 | 0 | Green | 170000 |  | 170000 | 0 | [9 empty] | 170000 | 170000 | No | Green | 2023-06-01 |  |  |  | 2023-08-31 | [13 empty] | 40000 |  |  |  | 40000 | 90000 | [6 empty] | West | Pipelines and Terminals | Operating Infrastructure |  | Coraopolis | CP - CORAOPOLIS TERMINAL BPL |  |  | 40000 |  | 130000 |  |  | Clark, Dave |  |  |  | 1 | 45160 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
Coraopolis Paving Phase 2 | Item | Open | MCAP | BTTCP00M2301 | Exempt | 2109948 | Roman, James | West | 3. Active | Defined | West |  | 110000 |  | 110000 | 110000 | 0 | Green | 110000 |  | 110000 | 0 |  |  | 36700 |  |  | 36700 | Phase | 36700 |  | 110000 | 110000 | No | Green | 2023-05-01 | 2023-04-04 | 2023-04-04 | 2023-08-31 | 2023-08-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 10000 |  | 0 | 100000 | [5 empty] | 5/1/23 Starting survey and design. 4/5/23 Phase 1 AFE submitted. If no permit required, then only spend $10k in May. If permit required, may spend up to $25k in May. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Coraopolis | BTTCP - CORAOPOLIS BTT TERMINAL |  |  | 10000 | 100000 |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 41738 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Coraopolis RTU OMNI and Blackline PLC upgrade | Item | Open | MCAP | CP00000M2201 | Maintenance Framework | 2036028 | Fink, Ryan | West | 3. Active | Defined | Instrumentation & Controls | 2062 | 103000 |  | 105062.01 | 105438 | -376 | Yellow | 111000 |  | 111000 | -5938 |  |  | 68000 |  |  | 68000 | Phase | 68000 | 14874 | 103000 | 117874 | No | Green | 2022-11-01 | 2022-10-04 | 2022-10-04 | 2022-12-16 | 2023-08-31 |  |  | 1220.55 | 1217.01 | 0 | -375.55 |  |  | -376 | Red |  |  | 2000 | 42000 | 21000 | 27000 | 7000 | 4000 |  |  |  | 5/2 RRF - Ph2 AFE, EAC $118k 4/7 RRF - waiting for parts. EAC$118k 3/2 RRF - panel layout, measurements, EAC $118K 2/1 RRF - reaccrue 11k 1/4/23 RRF - Eng continue, accrue 6490 dec. Updated forecast with OMNI delivery sched for June. 12/1 RRF - Eng in progress, accrue 5k nov 11/2 RRF - Eng & dwgs 9/28 RRF - AFE Ph1 submit, 2022 eng, 2023 install 9/2 RRF - AFE in Sept 8/2 RRF - RFQ'd, pending AFE 7/20 RRF - AFE in August. Will require TWO OMNI flow computers, adding 20k to the project cost. Most expenses will be deferred to 2023 due to material delays. 2022 spend will be approx 17k, remaining in 2023. 7/11 RRF - on site for scope 7/13, omni lead time very long, not likely arrive in 2022. moved most forecast for dec until AFE ready. 05-19-22 - MNH - Delay in submitting AFE and scope is also getting reduced due to another active project. Moving $2K from June to July. 5/3 RRF - Scope and AFE in May | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Coraopolis | CP - CORAOPOLIS TERMINAL BPL |  | 2438 | 43624 | 55000 | 4000 | 12812 |  | Forsey, Frank | Gardner, Travis W. |  |  | 1 | 41787 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Coraopolis Station PLC Recplacment | Item | Open | MCAP | CP00000M2101 | Exempt | 1823873 | Fink, Ryan | West | 3. Active | Defined | Instrumentation & Controls | 2509 | 45500 |  | 48009.38 | 48130 | -120 | Yellow | 48000 |  | 48000 | 9 |  |  | 98000 |  |  | 98000 | Full | 98000 | 59601 | 45500 | 105101 | No | Green | 2021-04-01 | 2021-03-30 | 2021-03-30 | 2021-06-25 | 2023-07-28 |  |  | 544.32 | 644.04 | 941.18 | 379.84 |  |  | 380 | Red |  |  | 4000 | 20000 | 11000 | 10500 | [5 empty] | 5/2 RRF - waiting on CPU, EAC $105k 4/7 RRF - waiting on CPU, EAC $104k 3/2 RRF - Waiting on CPU, EAC $104k 2/1 RRF - Parts delay 1/4/23 RRF - parts delay, start on point assignments and prepare for install in Q2. 12/1 RRF - CPU still delayed, plan for March 11/1 RRF - Material delay, revised forecast, planning for March install 10/4 RRF - Material delay 9/2 RRF - Material delays and 718 project is changing the PLCs that this project is to update. need to update drawings for new changes, and push to 2023, still not enough parts, and conflicts in Nov/Dec. 8/2 RRF - Material delay to Sept 7/11 RRF - Material delay to August 5/3 RRF - Material delay to August 4/11 RRF - Material delayed to August ship. 3/1 RRF - Material delayed, move install to late April 2/2 RRF - Material delay to March 1/3/2022 RRF - waiting on material 12/1 RRF - remaining work pushed to 2022 due to material delays, and availability. Resume in January, install March. 11/2 RRF - updated for actuals 10/10 RRF - Station PLC delayed to January due to parts and tech availability . 10/4 RRF - Planning 11/1 station and booster PLC upgrade, with 3/2022 718 PLC 9/30 RRF - Material ship date updated to 3/2022. 9/2 RRF - Material delays. May have enough for Station/710 PLC install in October, with 718 PLC delayed to early December. 8/2 RRF - Material from Manuf sched for November, vendor expects to locate spares for Sept install. Re accrue dwgs, adjust fcst for delays. 5k june, 5k july accrue. 7/30 RRF - Schedule and forecast update pending Material delivery update on 8/2 7/1 RRF - construction drawings ready, accrue $5k 6/18 RRF - Moved 20k to q4 6/2 RRF - Forecast updated due to delays on other work in area. | 2023-05-02 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Operating Infrastructure |  | Coraopolis | CP - CORAOPOLIS TERMINAL BPL |  | 2130 | 24380 | 21500 |  | 13370 |  | Forsey, Frank | Koehler, Steven M. |  |  | 1 | 37508 |  | Guest, ProSight | Independent | Aqua | 2020-08-05 | Other Programs
Coraopolis Tank 204 Replace Rotating Element | Item | Open | MEXP | BTTCP00E2301 | Maintenance Framework | 2083925, 2083842 | Gardner, Travis | West | 3. Active | Drawdown | Rotating Equipment |  | 1 |  | 1 |  | 1 | Red |  |  |  | 1 |  |  | 20000 |  |  | 20000 | Full | 20000 |  | 1 | 1 | No | Green | 2023-12-01 | 2023-04-26 | 2023-04-26 | 2023-05-12 | 2023-05-12 | [19 empty] | 1 |  | 5/4/2023 - reclass submitted. Anticipate accounting will apply cost in April. | 2023-05-03 | Griest, Barbara |  | West | Pipelines and Terminals | Station/Terminal |  | Coraopolis | BTTCP - CORAOPOLIS BTT TERMINAL |  |  | 0 |  | 1 |  |  | Posipanko, Dan | Gardner, Travis W. | N/A |  | 1 | 46991 |  | Gardner, Travis | JDE Child | Burnt Orange | 2023-04-26
Corapolis Control Valve Actuator Upgrade | Item | Candidate | MCAP |  | Exempt |  | Fink, Ryan | West | 2. Pending AFE |  | Valves |  | 60000 |  | 60000 | 60000 | 0 | Green | 60000 |  | 60000 | 0 | [9 empty] | 180000 | 180000 | No | Green | 2023-08-01 |  |  |  | 2023-10-31 | [15 empty] | 10000 | 40000 | 10000 |  |  |  | 5/2 RRF - EAC 2023 $60k 4/6 RRF - get quotes EAC 2023 $60k 3/2 RRF - Ops Mgr recommended upgrade PA PCV in 2023, ND + spares in 2024. EAC 2023 $60k 2/2 RRF - scope and est | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Coraopolis | GR - GREENSBURG TERMINAL |  |  | 0 | 50000 | 10000 |  | 120000 | Oey, Alex |  | N/A |  | 1 | 26371 |  | Samilo, Gregory | Independent | Aqua | 2017-09-19 | Other Programs
Council Bluffs - Dual Drainage Basins and HDPE Plastic Drain Line Project | Item | Open | MCAP | BETNB00M2302 | Maintenance Framework | 2110757 | Scott, Cory | West | 3. Active | Defined | Storm Water Management |  | 185000 |  | 185000 | 185000 | 0 | Green | 185000 |  | 185000 | 0 |  |  | 18524 |  |  | 18524 | Phase | 18524 |  | 185000 | 185000 | No | Green | 2023-05-01 | 2023-04-15 | 2023-04-15 | 2023-06-26 | 2023-06-30 | [12 empty] | 15000 |  | 170000 | [6 empty] | 5/1/2023 - Engineering process taking place. 4/18/2023 - PO placed for engineering. 4/10/2023 - Pushed back construction 170K to July in case of any delays. 3/23/2023 - Meet with TAS Technical to come up with a engineering plan for project. A plan for a french drain was discussed. This should result in a lower cost than originally proposed. | 2023-05-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Sugar Creek | BETNB - BET COUNCIL BLUFFS |  |  | 15000 | 170000 |  |  |  | Bonenberger, Mark | Smith, Todd W. |  |  | 1 | 44058 |  | Guest, ProSight | Independent | Aqua | 2022-07-01 | Other Programs
Council Bluffs - Front Gate Paving Replacement | Item | Candidate | MCAP |  | Exempt |  | Scott, Cory | West | 2. Pending AFE |  | West |  | 37000 |  | 37000 | 37000 | 0 | Green | 37000 |  | 37000 | 0 | [9 empty] | 37000 | 37000 | No | Green | 2023-07-01 |  |  |  | 2023-06-30 | [14 empty] | 37000 | [6 empty] | 5/1/2023 - Civil scope sent off for review by Senior Leadership. Forecast removed to July. 4/18/2023 - Awaiting answer from marketing to tweak scope for civil review. 4/10/2023 - Scope of work built for leadership review. 3/27/2023 - Meet with Ryan and Associates to have quote produced along with a sketch for civil scope leadership review. | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Sugar Creek | BETNB - BET COUNCIL BLUFFS |  |  | 0 | 37000 |  |  |  | Gardner, Travis |  |  |  | 1 | 45094 |  | Guest, ProSight | Independent | Aqua | 2022-08-18 | Other Programs
Council Bluffs Dike Drainage Phase 2 | Item | Candidate | MCAP |  | Maintenance Framework |  | Stalbaum, Cameron | West | 2. Pending AFE |  | Storm Water Management |  | 300000 |  | 300000 | 300000 | 0 | Green | 300000 |  | 300000 | 0 | [9 empty] | 300000 | 300000 | No | Green | 2023-07-01 |  |  |  | 2023-09-30 | [14 empty] | 100000 | 100000 | 100000 |  |  |  |  | 5/1/23 - No change yet. Waiting on Corys plan sheets for the other project so we can submit for one site walk. 4/3/23 - Working with Cory Scott on this project so we can potentially complete two project at Council Bluffs with the same contractor. Working to define the scope of the phase two work and whether it makes more sense to install the lift pump and piping to the discharge point or to install another dike drain and connect it to the system. | 2023-05-01 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Sugar Creek | BETNB - BET COUNCIL BLUFFS |  |  | 0 | 300000 |  |  |  | Bonenberger, Mark |  |  |  | 1 | 45281 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Other Programs
Council Bluffs Dike Drainage Upgrades Phase 1 | Item | Open | MCAP | BETNB00M2204 | Maintenance Framework | 1956947 | Stalbaum, Cameron | West | 6. Operational | Defined | Secondary Containment | 61757 |  |  | 61756.98 | 59691 | 2066 | Yellow |  |  |  | 61757 |  |  | 10000 | 189000 |  | 199000 | Phase | 199000 | 295393 |  | 295393 | No | Green | 2022-04-01 | 2022-03-24 | 2022-03-24 | 2022-10-30 | 2022-11-30 |  |  | 13189.8 | 595.49 | 45905.92 | 2065.77 |  |  | 2066 | Red | [11 empty] | 5/1/23 - No change for this project. I did have another follow up call on 4/25 with WM on their third party vendor charges. It is unnacceptable to be receiving these charges that were completely unware of. 4/3/23 - WM submitted invoices that were not anticipated. I was under the understanding that the invoices that we received in January would be the final billing amount. The third week in march they submitted these charges. The 45K variance is based on WM. The full 94K variance is based on 70K in WM and 34k in Inspection and Safety Audits. Actual construction costs were completed within the original budget. Additional services are what created the overage. I will submit the Supplemental and the funding will come from the descrease in the phase 2 project that is budgeted for 300K later this year. 2/2/23 - WM submitted invoicing for 7700 in January, however reaccruing the difference as I anticpate they will be billing the full amount. 1/3/23 - Holding Accrual for WM. There are still rolloffs onsite with spoil that EnviroServe has not picked up. Working with WM to get them picked up. 12/2/22 - Timco submitted billing. Holding accrual for Waste Mangement. With the issues that WM had with getting dumpsters out there and then not being able to pick them up. I'm skeptical that this cost will end up coming in over budget. 11/1/22 - Timco Completed the installation on 10/27/22. Covering accruals for Timco Open PO amount. Pugh for Inspection costs and estimated accrual for Waste Management for spoil disposal. 10/3/22 - Timco working on hydro excavation for utility locating. Plan on installing pipe and structures week of 10/3 and completing work week of 10/10. 10/8/31/22 - TIMCO was awarded this project. Materials were sourced in August. Project work is scheduled to start on 9/12 with hydro excavation. 8/2/22 This project is being rebid to Mills Excavating and Timco due to supply chain not finding a A/B grade contractor the first time. Once pricing is received back from both vendors we will make a selection and move forward with a portion of the work. The current accrual is for the additional scope for TAS to review thedrawings and make the necessary amendments from the review performed by Markella & Mark Bonenberger. 7/5/22 - Working with Supply Chain. This project was bid out to 3 vendors and currently we only received bids back from TCCI. Unfortunately TCCI is a Cgrade in ISN so Supply Chain is trying to see if other vendors would be willing to work out in Council Bluffs. 6/1/22 - Waiting for bid packages to come back before proceeding with Phase 2 AFE. 5/2/22 - Variance is for half of TAS po for completing baseline review. Met with Contractors and anticipate having initial bid back by 5/13/22 4/4/2022 -TAS Finishing the design review and plan on meeting two contractors the end of April to walk down the project and get bids. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Sugar Creek | BETNB - BET COUNCIL BLUFFS |  | 59691 | 2066 |  |  | 233636 |  | Clark, Dave | Spari, Markella |  |  | 1 | 34649 |  | Guest, ProSight | Independent | Aqua | 2019-08-28 | Other Programs
Council Bluffs New Flash Tester Purchase | Item | Open | MCAP | BETNB00M2303 | Maintenance Framework | 2110461 | Gardner, Travis | West | 6. Operational | Drawdown | Measurement & Quality Control | 27943 |  |  | 27942.61 | 27000 | 943 | Yellow |  |  |  | 27943 |  |  | 30242 |  |  | 30242 | Full | 30242 | 27943 |  | 27943 | No | Green | 2023-04-01 | 2023-04-18 | 2023-04-18 | 2023-05-31 | 2023-05-31 | [5 empty] | 27942.61 |  |  | 27943 | Red |  | WorkAhead of Schedule | [9 empty] | 5/2/2023 - flasher tester arrived early. ready to close4/18/23 - Submitted requisition for Flash Tester. 4/11/23 - AFE submitted in Remedy Force. | 2023-05-02 | Griest, Barbara | Griest, Barbara | West | Pipelines and Terminals | Operating Infrastructure |  | Sugar Creek | BETNB - BET COUNCIL BLUFFS |  |  | 27943 |  |  |  |  | Hopkins, Christa | Gardner, Travis W. |  |  | 1 | 46919 |  | Griest, Barbara | Independent | Aqua | 2023-04-10
Council Bluffs Tank 8 Premium Substitution | Item | Open | MCAP | BETNB00M2205 | Maintenance Framework | 2002621 | Roth, Aaron | West | 6. Operational | Drawdown | Tank Outage | 45796 |  |  | 45796.3 | 44625 | 1172 | Yellow | 149600 |  | 149600 | -103804 |  |  | 15000 |  |  | 15000 | Phase | 15000 | 60270 |  | 60270 | No | Green | 2022-08-01 | 2022-07-11 | 2022-07-11 | 2022-09-01 | 2023-04-30 |  |  | 27099.82 | 7879.74 | 9645.02 | 1171.72 |  |  | 1172 | Red | [11 empty] | 4.3 - done, tank is returned to service and temporary piping is removed. | 2023-04-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | BETNB - BET COUNCIL BLUFFS |  | 44625 | 1172 |  |  | 14474 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44061 |  | Guest, ProSight | Independent | Aqua | 2022-07-05 | Int - Tanks
Council Bluffs Terminal (BETNB) Tank 12 - OOS API 653 Insp | Item | Open | MCAP | BETNB00M2301 | Maintenance Framework | 2084420 | Roth, Aaron | West | 3. Active | Defined | Tanks | 189475 | 105000 |  | 294475 | 241981 | 52494 | Red | 330153 |  | 330153 | -35678 |  |  | 302188 |  |  | 302188 | Phase | 302188 | 189475 | 105000 | 294475 | No | Green | 2023-03-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-05-31 |  |  |  |  | 64828.39 | 124646.61 | 70000 | 70000 | 54647 | Red |  | WorkAhead of Schedule | 105000 | [8 empty] | 5.1 - liner being installed this week. RTS mid-May. VAR: work ahead of schedule - CFC was able to mobilize the last week of April and complete their scope. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | BETNB - BET COUNCIL BLUFFS |  | 64828 | 229647 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44796 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Council Bluffs Terminal (BETNB) Tank 14 - OOS API 653 + Seal Insp & Refurb | Item | Open | MEXP | BETNB00E2301 | Maintenance Framework | 2051691 | Roth, Aaron | West | 6. Operational | Defined | Tanks | 341787 | 10000 |  | 351786.87 | 360283 | -8496 | Yellow | 295000 |  | 295000 | 56787 |  |  | 223000 |  |  | 223000 | Phase | 223000 | 360538 | 10000 | 370538 | No | Green | 2022-12-01 | 2022-12-07 | 2022-12-07 | 2023-03-20 | 2023-05-31 |  |  | 53620.53 | 286597.26 | 10064.77 | -8495.69 |  |  | -8496 | Red |  |  |  | 10000 | [7 empty] | 4.3 - done | 2023-04-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Sugar Creek | BETNB - BET COUNCIL BLUFFS |  | 350283 | 1504 |  |  | 18751 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44797 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Council Bluffs Terminal (BETNB) Tank 10 - OOS Corr Insp & Refurb | Item | Open | MCAP | BETNB00M2101 | Maintenance Framework | 1782244 | Roth, Aaron | West | 6. Operational | Defined | Tanks | 407 |  | 21330 | 406.9 | 407 | 0 | Green |  |  |  | 407 |  |  | 247000 |  |  | 247000 | Phase | 247000 | 286121 | 21330 | 307451 | No | Green | 2021-01-01 | 2020-12-02 | 2020-12-02 | 2021-12-31 | 2022-10-15 |  |  | 406.9 | [17 empty] | 21330 | 1.3 - done, tank is RTS. VAR due to trailing inspector costs | 2023-01-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | BETNB - BET COUNCIL BLUFFS |  | 407 | 0 |  |  | 263242 |  | Stine, Carlton | Bassani, Joel D. | N/A |  | 1 | 30071 |  | Guest, ProSight | Independent | Aqua | 2018-07-26 | Int - Tanks
Council Bluffs Terminal New Red Dye Platform | Item | Open | MCAP | BETNB00M2206 | Exempt | 2036764 | Gardner, Travis | West | 6. Operational | Drawdown | West | 8321 |  |  | 8321.3 | 8321 | 0 | Green |  |  |  | 8321 |  |  | 22000 |  | 2516 | 22000 | Full | 24516 | 26066 |  | 26066 | No | Green | 2022-12-01 | 2022-10-12 | 2022-10-12 | 2022-12-31 | 2022-12-30 |  |  | 6774.31 | 1546.99 | [17 empty] | 3/1/2023 - Variance is due to PMO or accounting. OPPM actuals don't match cognos actuals again... Actuals for the February should be $1,242, not -16K. 1/4/2023 - platform recieved. Weather too cold to install push install to January. 12/2/022 - drawing approval complete. schedule for december shipment. 11/2/2022 - AFE was approved and PO issued. SafeRack delivery should be around 12/2/2022. | 2023-03-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Sugar Creek | BETNB - BET COUNCIL BLUFFS |  | 8321 | 0 |  |  | 17745 |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 46008 |  | Gardner, Travis | Independent | Aqua | 2022-10-06 | Other Programs
Council Bluffs Terminal Tank 6 Gauging Wire Repairs | Item | Open | MEXP | BETNB00E2303 | Exempt | 2093238 | Gardner, Travis | West | 6. Operational | Drawdown | Electrical | 12748 | 1 |  | 12749.2 | 11001 | 1748 | Red |  | 11000 | 11000 | 1749 |  |  | 11000 |  |  | 11000 | Full | 11000 | 12748 | 1 | 12749 | No | Green | 2023-04-01 | 2023-02-28 | 2023-02-28 | 2023-04-28 | 2023-04-28 | [5 empty] | 12748.2 | 11000 | 11000 | 1748 | Red | [9 empty] | 1 |  | 5/2/2023 - work completed. 4/4/2023 - emergent project working on issuing PO's | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Sugar Creek | BETNB - BET COUNCIL BLUFFS |  |  | 12748 |  | 1 |  |  | Ashley, Robert | Gardner, Travis W. | N/A |  | 1 | 46656 |  | Gardner, Travis | JDE Child | Burnt Orange | 2023-02-28
Cuyahoga load rack canopy fire alarm system replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Henfling, Mike | West | 2. Pending AFE |  | Fire Protection |  | 70000 |  | 70000 | 70000 | 0 | Green | 70000 |  | 70000 | 0 | [9 empty] | 150000 | 150000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 0 | 5000 | 30000 | 35000 |  |  |  |  | 5-2-23 - On-site meeting held 4/18. Notes and initial scope developed, waiting on budgetary quote to decide how to finalize bid specification document. Will open bid event late May or June. 4-4-23 - On-site scoping meeting with Greg J. and Vanguard planned for 4/18. Once scope developed, will bid with Lima North and Lima Station in May. 3-2-23 - No new updates. Plan for scoping site visit in late March. Bid event in April with Lima North and Lima Station. 2-2-23 - Shifted forecast one month. Will need to write scope of work and bid along with Lima North and Lima Station control system at same time. Possible long lead fire control panels. Look to open bid in March 1-3-23 - Left forecast as-is. Will touch base with terminal and CFS (who provided quote) in early 1Q | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | North East Ohio | BETYH - BET CUYAHOGA |  |  | 0 | 70000 |  |  |  | Jakubowski, Gregory |  |  |  | 1 | 45091 |  | Guest, ProSight | Independent | Aqua | 2022-08-18 | Other Programs
Cuyahoga Terminal VRU Vacuum Pump Replacement | Item | Open | MCAP | BETYH00M2204 | Maintenance Framework | 2002639 | Gardner, Travis | West | 7. Closed | Drawdown | Vapor Management | -245 |  |  | -244.86 | -245 | 0 | Green |  |  |  | -245 |  |  | 68000 |  |  | 68000 | Full | 68000 | 60551 |  | 60551 | No | Green | 2022-08-01 | 2022-07-28 | 2022-07-28 | 2022-09-23 | 2022-09-23 |  |  | 0 | -244.86 | [17 empty] | 3/1/2023 - final invoice recieved ready to close. 1/4/2023- waiting for contractor invoice. 12/2/2022 - variance is contingency and savings. 9/9/2022 - Pump was installed on Wednesday, 8/31. Updating status to operational. [Chelsea Schumacher] 9/1/2022 - drawdown project - Variance is due to issue with Inventory pump that was installed. has a knocking noise. This being address by vendor. install cost pushed to November. 8/3/2022 - waiting to hear back from operations on when this work will take place. | 2023-03-08 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | North East Ohio | BETYH - BET CUYAHOGA |  | -245 | 0 |  |  | 60796 |  | Karl, Marissa | Spitz, Nicholas P. |  |  | 1 | 44190 |  | Gardner, Travis | Independent | Aqua | 2022-07-19 | Other Programs
Dayton Catch Basin Replacement | Item | Candidate | MEXP |  | Exempt |  | Smith, Kyle | West | 5. Deferred |  | West |  |  |  | 0 |  | 0 | Green | 26000 |  | 26000 | -26000 | [9 empty] | 52000 | 52000 | No | Green | 2024-09-01 |  |  |  | 2024-09-30 | [21 empty] | 4/5/23 Deferred until 2024 | 2023-04-05 |  |  | West | Pipelines and Terminals | Station/Terminal |  | Southern Ohio | BETDO - DAYTON BET TERMINAL |  |  | 0 |  |  |  | 26000 | Gardner, Travis |  |  |  | 1 | 45226 |  | Guest, ProSight | Independent | Aqua | 2022-08-23 | Other Programs
Dayton Lane 1 Detonation Arrester | Item | Open | MEXP | BETDO00E2302 | Maintenance Framework | 2094411 | Smith, Kyle | West | 3. Active | Defined | Vapor Management |  | 13500 |  | 13500 | 13500 | 0 | Green | 16000 |  | 16000 | -2500 |  |  | 12635 |  | 8865 | 21500 | Full | 21500 |  | 21500 | 21500 | No | Green | 2023-05-01 | 2023-03-09 | 2023-03-09 | 2023-07-30 | 2023-05-31 | [12 empty] | 13500 | [8 empty] | 4/238/23 Cut PO to Degen | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Southern Ohio | BETDO - DAYTON BET TERMINAL |  |  | 13500 |  |  |  |  | Karl, Marissa | Gardner, Travis W. |  |  | 1 | 45225 |  | Guest, ProSight | Independent | Aqua | 2022-08-23 | Other Programs
Dayton Warehouse Roof Repair | Item | Open | MEXP | BETDO00E2301 | Exempt | 2076582 | Smith, Kyle | West | 3. Active | Defined | West |  | 25000 |  | 25000 | 25000 | 0 | Green | 25000 |  | 25000 | 0 |  |  | 27460 |  | 22540 | 27460 | Full | 50000 |  | 50000 | 50000 | No | Green | 2023-06-01 | 2023-01-24 | 2023-01-24 | 2023-04-30 | 2023-04-30 | [13 empty] | 25000 | [7 empty] | 4/28/23 Trying to get vendor reactivated in JDE | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Southern Ohio | BETDO - DAYTON BET TERMINAL |  |  | 25000 |  |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 45227 |  | Guest, ProSight | Independent | Aqua | 2022-08-23 | Other Programs
DE150TO RR Casing Remediation | Item | Open | MEXP | DS150TOE2201 | Maintenance Framework | 2021564 | Brown, Jeff | West | 7. Closed | Defined | Cathodic Protection | 0 |  |  | 0.48 | 0 | 0 | Green |  |  |  | 0 |  |  | 140000 |  |  | 140000 | Full | 140000 | 77643 |  | 77643 | No | Green | 2022-11-01 | 2022-09-02 | 2022-09-02 | 2022-12-31 | 2022-11-30 |  |  | 0.48 | [18 empty] | 1/3/2023 - re-accural for VCP Sales. 12-5 PROJECT COMPLETE, forecast deleted from 2023 no permiting needed. 10-31-22 variance WAITING RR PERMIT move 110K to 2023. 10-3 HOLLY TO WORK IN END OF OCT 8-31-22 AFE SUBMITTED 8/3/2022 - waiting for contractor pricing. 7-7-22 SENDING CONTRACTOR CASING SIZING FOR QUOTE. 3/3/322 - pulled in project not included in original budget | 2023-01-03 | Griest, Barbara |  | West | Pipelines and Terminals | Corrosion |  | Toledo | DE150TO - DELTA TO TOLEDO |  | 0 | 0 |  |  | 77642 |  | Geib, Rob | Geib, Robert |  |  | 1 | 42665 |  | Clark, David | Independent | Aqua | 2022-01-04 | Int - Accel Corr & FI
Dearborn - Mechanical to MultiLoad Upgrade | Item | Open | MCAP | BETIT00M2301 | Maintenance Framework | 2094280 | Hassan, Mohammad | West | 3. Active | Defined | Truck Racks | 33057 | 122900 |  | 155956.56 | 154995 | 961 | Yellow | 190000 |  | 190000 | -34043 |  |  | 155000 |  |  | 155000 | Full | 155000 | 33057 | 122900 | 155957 | No | Green | 2023-03-01 | 2023-03-08 | 2023-03-08 | 2023-07-31 | 2023-07-31 |  |  |  |  | 17495.45 | 15561.11 | 2500 | 2500 | 13061 | Red |  | WorkAhead of Schedule | 23000 | 50000 | 49900 | [6 empty] | 05-02-2023 - MNH - Project procurement underway and some material arrived ahead of schedule. Will have rest of the material receieved in May followed by construction in June & July. Project EAC at $155K. 04-03-2023 - MNH - Project procurement underway. Will have most of the material in May followed by construction in June & July. Project EAC at $155K. 04-03-2023 - MNH - Project procurement underway. Will have most of the material in May followed by construction in June & July. Project EAC at $155K. 03-22-2023 - MNH - Reducing forecast by $35K to fund some of the overage on the lima South Mechanical & Multiload Rack Upgrade (OPPM ID 41800). 02-28-2023 - MNH - Full AFE is complete and routed for approval. Project EAC at $155K. $35K remaining from budget will be used to fund Lima South Mechanical & Multiload Rack Upgrade (OPPM ID 41800). 02-01-2023 - MNH - Will route a phase 1 AFE to start the design & order long lead time PLC material this month. 01-03-2023 - MNH - Scope of work development underway this month. 12-1-2022 - MNH - Will start looking at scope of work this month. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETIT - BET DEARBORN |  | 17495 | 88561 | 49900 |  |  |  | Younce, Michael | Younce, Michael | N/A |  | 1 | 20530 |  | Guest, ProSight | Independent | Aqua | 2016-08-23 | Other Programs
Dearborn (DB) Tank 376 - OOS API 653 Insp | Item | Open | MCAP | DB00000M2301 | Maintenance Framework | 2084433 | Arch, Stefan | West | 3. Active | Defined | Tanks |  | 98504 |  | 98504 | 98504 | 0 | Green | 98504 |  | 98504 | 0 |  |  | 103400 |  |  | 103400 | Phase | 103400 |  | 98504 | 98504 | No | Green | 2023-08-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-12-31 | [15 empty] | 24626 | 49252 | 24626 |  |  |  | 5/1/2023 - Walked down project with Operations and proposed new plan to install piping from relief to Taylor Terminal. Currently working with Nick Spitz on the justification. Planning to take OOS in August still for quick repair. 4/3/2023 - No update, working with Operations on the temporary storage of the tank. Will be holding stakeholder call soon in beg of April. 3/1/2023 - Working with Justin Lamb and Alex Ferrari for temporary relief. Planning to complete in August and September. 2/1/2023 - project to take tank 376 OOS to repair the bottom. Funding approval apart of 2023 West Region MCAP Tank Phase I AFE. Planning to begin in August. Will need frac tanks on site for the temporary outage of the tank. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Wayne Terminals | DB - DEARBORN TERMINAL |  |  | 0 | 73878 | 24626 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44798 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Dearborn Station Replace MOV's | Item | Open | MCAP | DB00000M2201 | Maintenance Framework | 1956779 | Parker, Brian | West | 7. Closed | Defined | Valves | 8419 |  |  | 8418.68 | 8419 | 0 | Green |  |  |  | 8419 |  |  | 65000 |  | 21000 | 86000 | Supplemental | 86000 | 92027 |  | 92027 | No | Green | 2022-08-01 | 2022-03-22 | 2022-03-22 | 2022-11-18 | 2023-02-24 |  |  | 1890.01 | 6247.53 | 281.14 | [16 empty] | 3/31/23 - processed VRS invoice in late Mar. Project ready to be closed out and archived. PO's and WO closed in JDE. 2/28/23 - re-accruing 4,375 for VRS. 2/3/23 - re-accruing 4,375 for VRS and Nick Fawley should have the prover actuator installed the week of Feb 6th. 1/2/23 - Var is due to ~ 10,000 in Buckeye internal labor and FB not being forecast for Dec. Accruing 4,375 for Valve Reconditioning Service - just waiting on their final invoice - still have the prover 4-way actuator to install in Feb. 12/2/22 - work started on Nov 30th and got all new actuators installed except for the prover 4-way valve. Don't expect to get this one installed until Feb 2023. Dec FCST is for Valve Reconditioning Service and O/S Electrical Tech help to get these installed and Feb FCST is for installation of the actuator for the 4-way prover valve. 11/9/22 - Nick Fawley will get a contractor to help him out and take an outage to get all actuators changed out - targeting Nov 30th for a 2-day outage right now. We will be adding the other three actuators to this work for 2022. This will require a supplemental AFE. Should be 12,260 to be issued from inventory.9/28/22 - received the 4-way prover actuator in Sep and tech's started working on this by getting drive nuts to machine shop. Should have these installed in Oct/Nov timeframe.9/1/22 - received 8 actuators in Aug. The last actuator for the 4-way valve should arrive mid-Sep. There were also 3 actuators received for local inventory that need a project approved for them to be installed. Local techs are working on getting the drive nuts machined and getting these installed in Sep/Oct.8/5/22 - 8 actuators totaling 37,214 will ship 8/12, the one prover actuator at 6,237 will ship 9/16, and the 3 remaining actuators for local inventory will ship 8/12. Have installs by local ops FCST for Oct/Nov.7/30/22 - confirming with SPS that actuators will be shipped in Aug to Taylor, MI.7/3/22 - no change to status, expect delivery around mid-Aug for actuators.5/3/22 - last PO for 4-way diverter valve was issued on Apr 14th. Everything is 18 weeks out which should be around mid-Aug.4/5/22 - waiting on final revised quote for the prover 4-way diverter valve. Have PO issuedfor 8 actuators totaling 37,214 thatshould ship around Aug 1st.3/21/22 - received 2nd revision of bid back from Specialty Products and based on this assembled and AFE and submitted for approval. We will be able to replace 9 of 12 actuators and the 3 remaining actuators will be purchased for local warehouse inventory.2/8/22 - have an Excel file assembled that I need to get out to bid for all actuators.1/25/22 - based on actuator lead times for West Toledo project, I'm moving this FCST out to Aug/Sep time frame. Need to enter another project in OPPM for 2023and maybe 2024, once I have bid pricing back forall twelve actuators. | 2023-03-31 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Pipeline | DB - DEARBORN TERMINAL |  | 8419 | 0 |  |  | 83609 |  | Oey, Alex | Gardner, Travis W. |  |  | 1 | 37793 |  | Guest, ProSight | Independent | Aqua | 2020-08-12 | Other Programs
Dearborn Station Replace MOV's 2023 | Item | Candidate | MCAP |  | Exempt |  | Parker, Brian | West | 8. Canceled |  | Valves |  |  |  | 0 |  | 0 | Green | [15 empty] | No | Green |  |  |  |  | 2022-12-01 | [21 empty] | 1/31/2023 - funds used for emergent Wayne Station Replace WS209WW Scraper Bypass Valve. This project will be canceled. 1/3/23 - this budget amount is available since all of this was completed on Dec 1, 2022. | 2023-01-31 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Pipeline | DB - DEARBORN TERMINAL |  |  | 0 |  |  |  |  | Oey, Alex |  |  |  | 1 | 45155 |  | Guest, ProSight | Independent | Aqua | 2022-08-23 | Other Programs
Dearborn Terminal INSTALL FRP COATED UBOLTS | Item | Open | MCAP | BETIT00M2302 | Exempt | 2111851 | Brown, Jeff | West | 3. Active | Defined | Atmospheric Corrosion |  | 120000 |  | 120000 | 120000 | 0 | Green | 120000 |  | 120000 | 0 |  |  | 126374 |  |  | 126374 | Full | 126374 |  | 120000 | 120000 | No | Green | 2023-07-01 | 2023-04-18 | 2023-04-18 | 2022-12-31 | 2023-09-30 | [14 empty] | 20000 | 50000 | 50000 |  |  |  |  | 5-1-23 AFE Approved and material is on order. 4-3-23 AFE ROUTING 3-2-23 CONTACTING 22 BID CONTRACTOR FOR THIS WORK7-7-22 NO FUNDS WORK DEFERED 23 | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | BETIT - BET DEARBORN |  |  | 0 | 120000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 41073 |  | Guest, ProSight | Independent | Aqua | 2021-08-06 | Int - Planned Corr & FI
Dearborn Terminal Kaydon Tank Hi Level Alarms. | Item | Open | MCAP | BETIT00M2202 | Maintenance Framework | 2022623 | Fink, Ryan | West | 7. Closed | Defined | Instrumentation & Controls | 529 |  |  | 529.35 | 529 | 0 | Green |  |  |  | 529 |  |  | 36000 |  |  | 36000 | Full | 36000 | 19037 |  | 19037 | No | Green | 2022-10-01 | 2022-09-14 | 2022-09-14 | 2022-10-28 | 2022-12-31 |  |  | 529.35 | [18 empty] | 2/15 RRF - closed 2/2 RRF - ready to close 1/4/23 RRF - Operational Dec 2022. Close 12/2 RRF - tubing done early, cleanup 10/31 RRF - elec install cancelled. new tubing into air elim. Nov. Elec Demob, tubing install; Dec. material, contingency, and close out. Return $18k from budget. 10/7 RRF - Install cancelled, exploring disconnecting tanks instead of adding level alarms. Moved spends to Dec 9/29 RRF - on track for late Oct install 9/2 RRF - Submit AFE, moved out 1 mo. 8/2 RRF - RFQ'd for current pricing, AFE in August 7/11/2022 RRF - Revising estimates, AFE in August | 2023-02-15 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Pipeline | BETIT - BET DEARBORN |  | 529 | 0 |  |  | 18507 |  | Forsey, Frank | Ransom, Paul |  |  | 1 | 40754 |  | Gardner, Travis | Independent | Aqua | 2021-07-27 | Other Programs
Dearborn Terminal Legacy System Electrical Infrastructure Upgrade | Item | Open | MCAP | BETIT00M2201 | Maintenance Framework | 1956290 | Hassan, Mohammad | West | 3. Active | Drawdown | Electrical | 2481 | 518000 |  | 520480.57 | 519848 | 633 | Yellow | 400000 |  | 400000 | 120481 |  |  | 100000 | 549838 |  | 649838 | Full | 649838 | 133202 | 518000 | 651202 | No | Green | 2022-03-01 | 2022-04-26 | 2022-04-26 | 2022-10-30 | 2023-09-30 |  |  | 600.08 | 613.87 | 633.86 | 632.76 |  |  | 633 | Red |  |  | 100000 | 100000 | 100000 | 100000 | 100000 | 18000 |  |  |  | 05-02-2023 - MNH - Project underway with construction to start this month. Project EAC at 650K. 03-31-2023 - MNH - Phase 2 Full AFE has been approve. Project procurement underway. Project EAC at $650K. 03-31-2023 - MNH - Phase 2 Full AFE has been approve. Project procurement underway. Project EAC at $650K. 03-07-2023 - MNH - Phase 2 Full AFE has been routed for approval. Forecast updated to show project EAC of $650K per the full AFE. 03-01-2023 - MNH - Got all the prices back and will need another $120K to fully fund the project scope. EAC of this project will be at $650K. Forecast still shows the original budget and EAC of $530K. 02-01-2023 - MNH - Running a bid event this month to get quote for submitting Phase II AFE by end of this month. Project EAC at $530K but we may need another $50K to $60K to fully fund this project. 01-03-2023 - MNH - Will work on Phase II scope this month and next followed by submittal of full AFE. Project EAC at $530K but we may need another $50K to fully fund this project. 12-02-2022 - MNH - Work done as planned this month. Phase II work scheduled for 2023. Project EAC at $530K. 11-02-2022 - MNH - Temp rental cables on order to be upgraded this month with permanent cables per the drawings. Project EAC at $530K 10-07-2022 - MNH - Adding $30K to 2022 forecast to get some temp rental cables upgraded with permanent cables per the drawings. Project EAC now at $530K. $30K will come from West Region drawdown. 10-03-2022 - MNH - Design got completed last month. Will now work on getting bids from contractors. Project EAC reduced by Leadership to $500K. 09-01-2022 - MNH - Design should be done this month followed by bid event. Adding estimated construction cost based on 700 foot of new cable tray in 2023 and re-forcasting money from September into November due to design delay. Project EAC $700K. 08-01-2022 - MNH - Design & Engineering are now behind due to ESP's schedule so forecast missed. Reforecasting some money in Q4 now. 07-06-2022 - MNH - Design & Engineering underway andon schedule. 06-01-2022 - MNH - Design & Engineering work to start this month. Adjusting Forecast. 04-29-2022 - MNH - Phase 1 AFE approved and invoice paid for contractor for temporary fix. Will start design & engineering work for permanent fix in May. 04-07-2022 - MNH - Project forecast added including estimated Phase 1 AFE forecast. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETIT - BET DEARBORN |  | 1848 | 200633 | 300000 | 18000 | 130721 |  | Ashley, Robert | Spitz, Nicholas P. |  |  | 1 | 43183 |  | Guest, ProSight | Independent | Aqua | 2022-03-16 | Other Programs
Des Moines (BETOI) - Secondary containment improvements | Item | Candidate | MEXP |  | Maintenance Framework |  | Scott, Cory | West | 2. Pending AFE |  | Secondary Containment |  | 56000 |  | 56000 | 56000 | 0 | Green | 56000 |  | 56000 | 0 | [9 empty] | 56000 | 56000 | No | Green | 2023-06-01 |  |  |  | 2023-07-31 | [13 empty] | 10000 |  |  | 46000 |  |  |  |  | 5/2/2023 - Reached out to Kathy Novak to start the engineering process. Once proposal arrives, I will submit the phase AFE for engineering. 4/18/2023 - Reaching out to Aaron Roth in regards to completed engineering on this project. 3/23/2023 - Meet with TAS technical to discuss multiple options for construction for Engineering and leadership review. | 2023-05-02 |  |  | West | Pipelines and Terminals | Station/Terminal |  | Sugar Creek | BETOI - BET DES MOINES |  |  | 10000 | 46000 |  |  |  | Spari, Markella |  |  |  | 1 | 45168 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
Des Moines Kiosk | Item | Open | MCAP | BETOI00M2202 | Maintenance Framework | 2003598 | Scott, Cory | West | 3. Active | Defined | West | 17399 | 3000 |  | 20398.72 | 21350 | -951 | Yellow |  |  |  | 20399 |  |  | 23000 | 28000 |  | 51000 | Full | 51000 | 47176 | 3000 | 50176 | No | Green | 2022-08-01 | 2022-07-22 | 2022-07-22 | 2022-11-15 | 2023-05-30 |  |  | 118.88 | -2178.62 | 18409.75 | 1048.71 |  |  | 1049 | Red |  |  | 3000 | [8 empty] | 5/8/2023 - Electrical contractor installing power to kiosk. 4/18/2023 - PO placed for electrical component and conduit installation for $2817.00. project should come in around $49,500.00 3/27/2023 - Waste management sample invoice came it at $433.00. Delivery of kiosk invoice came in for $1,200.00. Forecast of $5k is for upcoming conduit work 3/20/2023 - Ryan and Associates installing Kiosk at Des Moines Terminal. Install completed. Electrician to wire up light and heater. They are coming out to give estimate. 3/13/2023 - Recieved invoice from Jay Henges Porta King for the kiosk for 16K. 2/21/2023 - Kiosk expected to be ready 3/3/2023. Ryan and Associates will install in late march. 2/1/2023 - $1500.00 Waste management invoice approved for dumpster removal. 1/9/2023 - PO was placed on 12/14/2023 and manufacturer put this unit into production. Planned arrived of kiosk is middle of March. 12/7/2022 - Kiosk manufacturer pushed back finish date to early to mid 2023. PO wasn't place second Kiosk. $19,000 forecasted into 2023. 11/29/2022 - Kiosks set to arrive first week of december. Pending arrival date Install should be taking place by the end of the first or start of the second week in december around 12/12/2022. Recieved dumpster analytical 11/16/2022 - Recieved first dumpster invoices for $825.00. Awaiting sample to clear for dumpster removal and final billing. 11/15/2022 - Porta king shows delayed delivery till first week of december. 11/2/2022 - TAS Engineering invoice approved for $1550.00 10/31/2022 - Ryan and Associates finished the foundation installation. Dumpster is onsite as well with spoil. 9/28/2022 - Stakeholder meeting held. Civil work to start on 10/24/2022. Kiosk to be installed in mid november. 8/31/2022 - Forecast adjusted to reflect construction of the foundation in October and Kiosk arrival installation in November. 8/16/2022 - Adjusted the forecast to reflect total project. Engineering, Kiosk Procurement, Installation, and Waste Costs.7/23/2022 - PO Placed to Tas Technical for 3K and the kiosk from Porta King for 19K 7/22/2022 - Engineering will be finished an billed in August. The Kiosk will be delivered inOctober. Forecast amounts have been adjusted to reflect this. Forecasted construction installation cost into 2023.2023 Updated Forecast - $20,950.00 7/14/2022 - Phase 1 AFE submitted for the Engineering Plan/Layout Drawing and Kiosk Order (Hazardous Areas Suitable) for 23K. 6/29/2022 - Sent out to contractor for estimate and engineering for estimate. Once Iget the engineering estimate, I will put in a phase AFE. Building out scope for leadership review.3/8/2022 - Site visit for photos. 2/25/2022 - Working with Diamond Z to produce drawings for Civil Scope Of Work. 2/8/2022 - Reached out to Porta Kingvendor to obtain proposal for Kiosk. | 2023-05-09 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Sugar Creek | BETOI - BET DES MOINES |  | 16350 | 4049 |  |  | 29777 |  | Gardner, Travis | Smith, Todd W. | N/A |  | 1 | 26235 |  | Guest, ProSight | Independent | Aqua | 2017-09-15 | Other Programs
Des Moines Remote Site recoat | Item | Open | MCAP | UC762OIM2301 | Exempt | 2085570 | Scott, Cory | West | 6. Operational | Defined | Atmospheric Corrosion | 9282 |  |  | 9282.01 | 10000 | -718 | Yellow | 12001 |  | 12001 | -2719 |  |  | 9882 |  |  | 9882 | Full | 9882 | 9282 |  | 9282 | No | Green | 2023-04-01 | 2023-02-22 | 2023-02-22 | 2023-05-24 | 2023-04-30 | [5 empty] | 9282.01 | 10000 | 10000 | -718 | Yellow | [11 empty] | 5/5/2023 - Cleveland invoice came in at $2,847.71 5/2/2023 - Awaiting final invoice from Cleveland Integrity. 4/20/2023 - Vance and Associates billed $5,282.00 4/18/2023 - Project completed 4/14/2023. Should come in on time and right at budget. 3/30/2023 - Stakeholder meeting held. Project to start 4/17/2023. 3/27/2023 - Inspector request placed. Stake holder meeting to be held on 3/30/2023. 3/20/2023 - PO placed for Vance and Associates for $5,300.00. 1/24/2023 - AFE submitted for 10K. | 2023-05-05 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | UC762OI - CRESTION STA TO DES MOINES TER |  |  | 9282 |  |  |  |  | Geib, Rob | Smith, Todd W. |  |  | 1 | 45448 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Des Moines Tank 11 ethanol support project | Item | Open | MCAP | BETOI00M2201 | Maintenance Framework | 2002622 | Roth, Aaron | West | 3. Active | Drawdown | Tank Outage | 110159 | 60000 |  | 170159.13 | 188959 | -18800 | Yellow | 220000 |  | 220000 | -49841 |  |  | 22000 |  |  | 22000 | Phase | 22000 | 136274 | 60000 | 196274 | No | Green | 2022-08-01 | 2022-07-11 | 2022-07-11 | 2022-09-01 | 2023-07-31 |  |  | 66537.74 | 55250.07 | 7170.89 | -18799.57 |  |  | -18800 | Red |  | Forecasting |  |  | 60000 | [6 empty] | 5.1 - tank work done, ready to be ethanol subsitute for tank 3 project. Clean and use for extra ULSD or GAS storage after tank 3 project. VAR: dropped accrual for inspector time | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | BETOI - BET DES MOINES |  | 128959 | -18800 | 60000 |  | 26115 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44066 |  | Guest, ProSight | Independent | Aqua | 2022-07-05 | Int - Tanks
Des Moines Terminal (BETOI) Tank 1 - OOS API 653 Insp | Item | Open | MCAP | BETOI00M2301 | Maintenance Framework | 2084428 | Roth, Aaron | West | 3. Active | Defined | Tanks |  | 90000 | 192500 | 90000 | 90000 | 0 | Green | 282500 |  | 282500 | -192500 |  |  | 96695 |  |  | 96695 | Phase | 96695 |  | 282500 | 282500 | No | Green | 2023-05-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-08-31 | [12 empty] | 90000 | [7 empty] | 192500 | 5.1 - Square Robot to do robotic inspection tentatively week of 5/22 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | BETOI - BET DES MOINES |  |  | 90000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44799 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Des Moines Terminal (BETOI) Tank 3 - OOS API 653 + Seal Insp & Refurb | Item | Open | MEXP | BETOI00E2301 | Maintenance Framework | 2076572 | Roth, Aaron | West | 3. Active | Defined | Tanks |  | 240000 |  | 240000 | 240000 | 0 | Green | 240000 |  | 240000 | 0 |  |  | 201300 |  |  | 201300 | Phase | 201300 |  | 240000 | 240000 | No | Green | 2023-05-01 | 2023-01-20 | 2023-01-20 | 2023-12-31 | 2023-07-31 | [12 empty] | 40000 | 100000 | 100000 | [6 empty] | 5.1 - HMR isolate/clean May 9, DJA inspect May 15 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Sugar Creek | BETOI - BET DES MOINES |  |  | 140000 | 100000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44800 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Des Moines Terminal (BETOI) Tank 4 - OOS API 653 Insp | Item | Open | MCAP | BETOI00M2302 | Maintenance Framework | 2084429 | Roth, Aaron | West | 3. Active | Defined | Tanks |  | 90000 | 143433 | 90000 | 90000 | 0 | Green | 233433 |  | 233433 | -143433 |  |  | 96695 |  |  | 96695 | Phase | 96695 |  | 233433 | 233433 | No | Green | 2023-05-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-08-31 | [12 empty] | 90000 | [7 empty] | 143433 | 5.1 - Square Robot to do robotic inspection tentatively week of 5/22 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | BETOI - BET DES MOINES |  |  | 90000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44801 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Des Moines Terminal (BETOI) Tank 6 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | BETOI00E2303 | Maintenance Framework | 2084802 | Roth, Aaron | West | 3. Active | Defined | Tanks |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 |  |  | 11200 |  |  | 11200 | Full | 11200 |  | 10000 | 10000 | No | Green | 2023-11-01 | 2023-02-08 | 2023-02-08 | 2023-12-31 | 2023-11-30 | [18 empty] | 10000 |  |  | 5.1 - do in Q4. due date is 11.22.2023 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Sugar Creek | BETOI - BET DES MOINES |  |  | 0 |  | 10000 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44802 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Des Moines Terminal HVAC Replacement | Item | Open | MCAP | BETOI00M2303 | Maintenance Framework | 2076295 | Gardner, Travis | West | 6. Operational | Drawdown | West | 15608 |  |  | 15608.26 | 15608 | 0 | Green |  | 17804 | 17804 | -2196 |  |  | 17804 |  |  | 17804 | Full | 17804 | 15608 |  | 15608 | No | Green | 2023-02-01 | 2023-02-02 | 2023-02-02 | 2023-02-28 | 2023-02-15 |  |  |  | 14936.13 | 672.13 | [16 empty] | 3/1/2023 - work completed and ready to close.2/3/2023 - this work has been completed and will reclass cost in February | 2023-03-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Sugar Creek | BETOI - BET DES MOINES |  | 15608 | 0 |  |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 46559 |  | Gardner, Travis | Independent | Aqua | 2023-01-30 | Other Programs
Des Moines terminal Sewer Line Repair | Item | Open | MEXP | BETOI00E2302 | Exempt | 2052644 | Scott, Cory | West | 6. Operational | Drawdown | West | -7121 |  |  | -7120.86 | -7121 | 0 | Green |  |  |  | -7121 |  |  | 15000 |  |  | 15000 | Full | 15000 | -7121 |  | -7121 | No | Green |  | 2023-01-06 | 2023-01-06 | 2023-02-03 | 2023-02-03 |  |  |  | -5000 | -2120.86 | [16 empty] | 3/7/2023 - Work order updated in JDE from BETOI ops to the job #. Everything should be reclassed to project today. Final pricing should come out to 10K. Monthly Variance Explanation due to project costing $5K lower due to utilizing soil at facility with no dumpster. 2/3/2023 - Ryan and Associates sent invoice for project. It came out to $6,270.50. This is substantially lower than what was factored in. 1/18/2023 - Project completed. Awaiting final invoicing from Ryan and Associates. 1/17/2023 - Ryan and Associates arrived onsite and are starting work. Work planned to be completed 1/18/2023. 1/13/2023 - Stakeholder meeting held. 1/9/2023 - Ryan and Associates plans to dig up and repair sewer line on 1/17/2023. Awaiting site safety plan approval. Scope of work built. Stake holders meeting planned for 1/13/2023. 1/5/2023 - emergent drawdown project enter in OPPM on 1/5/2023 | 2023-03-07 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Sugar Creek | BETOI - BET DES MOINES |  | -7121 | 0 |  |  |  |  | Gardner, Travis | Gardner, Travis W. | N/A |  | 1 | 46438 |  | Gardner, Travis | JDE Child | Burnt Orange | 2023-01-06 | Other Programs
Detroit Engineering to Address Disconnected Fire Mains | Item | Open | MCAP | BETWD00M2301 | Exempt | 2094279 | Henfling, Mike | West | 3. Active | Defined | Fire Protection |  | 22000 |  | 22000 | 22000 | 0 | Green | 15000 | 6960 | 21960 | 40 |  |  | 21960 |  |  | 21960 | Phase | 21960 |  | 22000 | 22000 | No | Green | 2023-05-01 | 2023-03-08 | 2023-03-08 | 2024-12-31 | 2023-07-28 | [6 empty] | 0 | 0 | 0 | Green |  |  | 2000 | 5000 | 10000 | 5000 | [5 empty] | 5/8/23 - If funding here is not all used, ok to use for Lima Fire Alarm upgrades (GJ); 5-2-23 - Local fire hydrants are owned by City of Detroit - ESDC to schedule a flow test (has to be performed by City of Detroit). May not need site visit. Likely will not plan for water lines inside tank farm due to site layout, but may consider other upgrades based on flow test. 4-4-23 - PO issued to ESDC. Looking into whether hydrants are city-owned or Buckeye-owned. If city-owned, need to have City perform flow test. Would coordinate visit upon this plan, site visit tentative for May. Still plan to have engineering completed by July to have budgetary pricing by August. 3-2-23 - AFE in progress. PO to be issued to ESDC upon approval for engineering study. Flow test during April/May (warmer weather). Noted to have engineering completed by July to have budgetary pricing by August. 2-2-23 - Discussed project with site Ops and ESDC. Requested quote from ESDC. Will submit AFE once quote is received. Need to flow test so engineering won't start until warmer weather. Noted to have engineering completed by July to have pricing by August. 1-3-23 - Left forecast as-is. Will likely touch-base with ESDC for design in late January. | 2023-05-08 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETWD - DETROIT BET TERMINAL |  |  | 7000 | 15000 |  |  |  | Jakubowski, Gregory | Jakubowski, Greg |  |  | 1 | 44647 |  | Guest, ProSight | Independent | Aqua | 2022-08-17 | Other Programs
Detroit Station MCC Building Design/Replacement | Item | Candidate | MCAP |  | Exempt |  | Hassan, Mohammad | West | 2. Pending AFE |  | Electrical |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 | [9 empty] | 540000 | 540000 | No | Green | 2023-06-01 |  |  |  | 2023-08-31 | [11 empty] | Contractor/Vendor Issue |  | 15000 | 20000 | 5000 | [5 empty] | 05-02-2023 - MNH - Due to ORC23B01 - Ohio Refining Co Transition Emergent Project & delay from receiving Eatons quote, this project AFE completion is delayed. Moving forecast out a month. 03-29-2023 - MNH - Due to ORC23B01 - Ohio Refining Co Transition Emergent Project, this project AFE completion is delayed. Moving forecast out a month. 02-28-2023 - MNH - Initial site visit conducted last week. Will plan on submitting Phase 1 AFE in a few weeks. March forecast moved out to Q2. 02-01-2023 - MNH - Scope development underway. 01-03-2023 - MNH - Will start looking at scope of work this month. 12-1-2022 - MNH - Will start looking at scope of work next month. | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Pipeline | WD - DETROIT STATION |  |  | 15000 | 25000 |  |  | 500000 | Ashley, Robert |  |  |  | 1 | 45826 |  | Clark, David | Independent | Aqua | 2022-09-12 | Other Programs
Detroit Station Unit 5 Multilin 469 Trouble Shooting | Item | Open | MEXP | WD00000E2301 | Exempt | 2053721 | Gardner, Travis | West | 6. Operational | Drawdown | Electrical | 12450 | 1 |  | 12451.2 | 12451 | 0 | Green |  |  |  | 12451 |  |  | 18000 |  |  | 18000 | Full | 18000 | 12450 | 1 | 12451 | No | Green | 2023-02-01 | 2023-02-14 | 2023-02-14 | 2023-03-03 | 2023-03-03 |  |  |  | 20142.73 | -7692.53 | [14 empty] | 1 |  | 4/4/2023 - March variance in OPPM was -7,693 but Cogonos report shows 0 variance for March. | 2023-04-04 | Griest, Barbara |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Pipeline | WD - DETROIT STATION |  | 12450 | 0 |  | 1 |  |  | Ashley, Robert | Gardner, Travis W. | N/A |  | 1 | 46591 |  | Gardner, Travis | JDE Child | Burnt Orange | 2023-02-14 | Other Programs
DeWitt Pump Discharge Valve Replacement | Item | Open | MCAP | DQ00000M2301 | Exempt | 2075038 | Gardner, Travis | West | 6. Operational | Drawdown | Valves | 60976 |  |  | 60976.42 | 73075 | -12099 | Red |  | 59240 | 59240 | 1736 |  |  | 59240 |  |  | 59240 | Full | 59240 | 60976 |  | 60976 | No | Green | 2023-03-01 | 2023-03-13 | 2023-03-13 | 2023-02-28 | 2023-03-31 |  |  |  |  | 73075.04 | -12098.62 |  |  | -12099 | Red |  | Other | [9 empty] | 5/3/2023 - Variance is accounting applied reclass in March and not April after financials were locked. 4/4/2023 - emergent project, reclass completed. Ready to close | 2023-05-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Central-Illinois | DQ - DEWITT STATION |  | 73075 | -12099 |  |  |  |  | Oey, Alex | Hoekstra, Matt |  |  | 1 | 46719 |  | Gardner, Travis | Independent | Aqua | 2023-03-08
DF999A1 Critical Bond Install | Item | Candidate | MCAP |  | Exempt |  | Scannell, Adam | West | 2. Pending AFE |  | Cathodic Protection |  | 35000 |  | 35000 | 35000 | 0 | Green | 35000 |  | 35000 | 0 | [9 empty] | 35000 | 35000 | No | Green | 2023-09-01 |  |  |  | 2023-09-30 | [16 empty] | 35000 |  |  |  |  | 04/21//23 - Working with Travis Rohr on this. It will be completed during the hydrotest in September. 02-03-2023 - MNH - Moving this in Adam's queue. | 2023-05-02 |  |  | West | Pipelines and Terminals | Integrity |  | Eastern Iowa | DF999A2 |  |  | 0 | 35000 |  |  |  | Geib, Rob |  |  |  | 1 | 41550 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Int - Planned Corr & FI
DM - ATG Transitions and FRP Repairs | Item | Candidate | MCAP |  | Exempt |  | Gremer, Michael | West | 2. Pending AFE |  | Atmospheric Corrosion |  | 25000 |  | 25000 | 25000 | 0 | Green | 25000 |  | 25000 | 0 | [9 empty] | 25000 | 25000 | No | Green | 2023-10-01 |  |  |  | 2023-10-31 | [17 empty] | 25000 |  |  |  | 5/2/23 - PM to set up site visit with contractors. 4/4/23 - PM working on scope of work. 3/2/23 - PM working on scope of work. 2/3/23 - PM working on scope of work. | 2023-05-02 |  |  | West | Pipelines and Terminals | Integrity |  | Coraopolis | DM - DELMONT TERMINAL |  |  | 0 |  | 25000 |  |  | Geib, Rob |  |  |  | 1 | 45336 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Int - Planned Corr & FI
DQ160SI MP 133.60 Ground Bed Replacement | Item | Open | MCAP | DQ160SIM2201 | Exempt | 1946413 | Gabriel, Jeff | West | 6. Operational | Defined | Cathodic Protection | 1355 |  |  | 1355.2 | 1355 | 0 | Green |  |  |  | 1355 |  |  | 38000 |  | 15282 | 53282 | Supplemental | 53282 | 53282 |  | 53282 | No | Green | 2022-02-01 | 2022-02-10 | 2022-02-10 | 2022-10-15 | 2022-12-31 |  |  | 1355.2 | [18 empty] | 1/3/2023-Work complete. Need to Accrue 28,300 12/1/2022- Work complete charges will hit in Dec as forecasted 11/1/2022- PO will be sent out this week. NIS will be completing the work. 10/4/2022- Moved forecast to November. waiting on contractor to be added to JDE to receive Quotes. 9/1/2022 -No Change in Schedule 8/3/2022-Scheduled for October CPM 7/5/2022- contractor availiblity and bid delays. 6/2/2022- Scheduled for June 5/1/2022- Awarded to CPM move forecast to June 4/4/2022- Variance ordered material & Still waiting on Bid Event 3/3-22- Material ordered | 2023-01-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Central-Illinois | DQ160SI - DEWITT TO SIBLEY |  | 1355 | 0 |  |  | 51927 |  | Geib, Rob | Geib, Robert |  |  | 1 | 40843 |  | Guest, ProSight | Independent | Aqua | 2021-07-29 | Other Programs
DS - 344 TEST STATION REPAIRS | Item | Candidate | MEXP |  | Exempt |  | Brown, Jeff | West | 2. Pending AFE |  | Cathodic Protection |  | 20000 |  | 20000 | 20000 | 0 | Green | 20001 |  | 20001 | -1 | [9 empty] | 20000 | 20000 | No | Green | 2023-10-01 |  |  |  | 2023-12-31 | [17 empty] | 20000 |  |  |  | 5-1-23 No change in status. 3-2-23 4th QRTR PROJECT | 2023-05-01 |  |  | West | Pipelines and Terminals | Corrosion |  | Toledo | DS - TOLEDO STATION |  |  | 0 |  | 20000 |  |  | Geib, Rob |  |  |  | 1 | 45288 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Int - Planned Corr & FI
DS301CG - F-0046622, F-0046640 crack like anomalies under B-sleeve | Item | Candidate | MCAP |  | Project Framework |  | Bost, Jason | West | 2. Pending AFE | Emergent | Pipeline Digs |  | 300000 |  | 300000 | 300000 | 0 | Green | 300000 |  | 300000 | 0 | [9 empty] | 300000 | 300000 | No | Green | 2023-08-01 |  |  |  | 2023-09-30 | [15 empty] | 150000 | 150000 |  |  |  |  | 5/1/23 - No change. 4/3/23 - Targeting Q3 to align with other cutouts in the area. 3/1/23 - Reviewing other potential cutouts to complete to minimize downtime. 3/1/23 - turned this project over to Jason Bost. 1/13/23 - forgot to remove the $1 in December which incorrectly triggered the cashflow start date of 12/1/22. Planned for Q3 of 2023. 11/1/22 - pushed to 2023. 4/5/21 - pushed to 2022. 6/4/19 - pushed to 2021. 7/30/18 - discussed pushing to 2019 during last monthly Integrity call. 6/29/18 - no progress yet. 5/1/18 This project will not be started until May/June timeframe. The forecast was simply a placeholder. DLM | 2023-05-02 |  |  | West | Pipelines and Terminals | Integrity |  | Toledo | DS301DL - TOLEDO TO SUN #6-10IN SOUTH |  |  | 0 | 300000 |  |  |  | Bartal, Nick |  | N/A |  | 1 | 25884 | Low Return | Bassani, Joel | Independent | Aqua | 2017-09-13 | Int - Planned Exposures
DS302CG - DIG SHEETS (5) DOT-180 + (7) BPL-Other - Due 03-14-22 | Item | Open | MCAP | DS302CGM2103 | Maintenance Framework | 1889087 1889090 | Bost, Jason | West | 6. Operational | Defined | Pipeline Digs | -402139 | -5500 |  | -407639.21 | -402139 | -5500 | Yellow |  |  |  | -407639 |  |  | 971000 |  |  | 971000 | Full | 971000 | 298946 | -5500 | 293446 | No | Green | 2021-11-01 | 2021-12-07 | 2021-12-07 | 2021-03-14 | 2022-07-05 |  |  | 5000 | 3229 | -410368.21 | [7 empty] | -5500 | [8 empty] | 5.8.23 - $-5,500 forecasted in May due to MEXP flip to DS302CGE2203 (AS) 4/3/23 - Variance is reclass that hit project in March. 3.7.23 - March forecast -$416,013 due to MEXP Flip to DS302CGE2203 (AS) 3/1/23 - Variance is caused by 3 delayed Percheron invoices. 2/14/23 - Submitted Remedy Force ticket to reopen WO's because of three delayed Percheron invoices. (BG) 1/31/23 - Job Book submitted. Variance is MJE02 Sight draft invoice. 12/5/22 - Variance is "MJE02A - Sight Draft" invoice. 11/1/22 - Variance is 2 Percheron Invoices. 9/12/22 - -$542,331 reclassed to DS302CGE2203 (AS) 9/1/22 - Variance is caused by savings from Roberts estimate for final dig. 8/1/22 - Digs complete. Accrual is for Roberts & MNT invoices. 7/11/22 - Variance caused by multiple Roberts invoices in June for work completed in May, Invoices were not included in May's accruals. Additional Black Diamonds needed for final dig causing a larger June variance. 7/5/22 - Digs complete. Forecast is for restoration at multiple sites. Digs to be flipped to Expense due to Black Diamonds being the determined repairs. . 6/1/22 - Remaining digs include 1 like and similar dig and 1 BPL-Other dig. Expected to be completed by end of June. 5/3/22 - Remaining digs include 2 like/similar and 3 BPL-other digs. 4/4/22 - Moved crew from 302 digs to 003L Immediate dig issued on 3/16. Crew is scheduled to mobilize back to the 302L on 4/11. 3/9/22 - Variance is due to reclass to MEXP. 3/2/22 - All DOT digs complete. Will mobilize to the additional similar characteristics digs on 3/21. 2/2/22 - 6 Dig sites complete. Will mobilize to remaining 2 DOT digs prior to moving to similar characteristics digs issued on January 7, 2022. 1/3/22 - 4 dig sites complete. Roberts will continue after immediate digs on the 003L. 12/1/21 - Mobilized on 11/10. First 2 dig sites are complete. | 2023-05-08 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Toledo | DS302CG - TOLEDO TO CYGNET 10IN SOUTH |  | -402139 | -5500 |  |  | 406477 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 42181 |  | Schultz, Amy | Independent | Aqua | 2021-09-17 | Int- Planned Digs
DS302CG - Digs from 2022 UCD ILI | Item | Open | MCAP | DS302CGM2201 | Maintenance Framework | 2035943, 2021920, 2021921, 2021922 | Burns, Richard | West | 3. Active | Defined | Pipeline Digs | -45293 |  |  | -45292.62 | -45412 | 119 | Yellow | 529000 |  | 529000 | -574293 |  |  | 211000 |  |  | 211000 | Phase | 211000 | 25153 |  | 25153 | No | Green | 2022-10-01 | 2022-09-30 | 2022-09-30 | 2022-12-31 | 2023-06-30 |  |  | 78057.11 | 4547.94 | -128016.68 | 119.01 |  |  | 119 | Red | [11 empty] | 5/1/23 - no change. 4.6.23 - Additional -$297 added to March forecast due to MEXP Flip DS302CGE2203 (AS) 4/3/23 - variance is from expense flip. 3.7.23 - March forecast of -$128,635 due to MEXP Flip to DS302CGE2203 (AS) 3/1/23 - variance is Percheron ($704) and PM labor for documentation. 2/1/23 - Variance accrued. Overage is because dig took a little longer than expected due to weather and site conditions. Dig started 1/3, completed 1/11/23. 1/3/23 - Variance is Percheron late invoices ($7040). Rest is payroll. 12/2/22 - Accrued some for Degen getting work down ahead of original schedule; variance is from that. Adjusted forecast to January as crew was moved to more pressing digs; I deleted rest of forecast. Two sites complete, although one of those was just exploratory work for the casing locations. F-34236 is in a casing under I-280 and will be a cutout under a separate project. 11/1/22 - variance is Percheron and labor. 10/3/22 - AFE approved today. Digs expected to start end of October / early November. 9/26/22 - digs transferred to Rich. Adjusted forecasting for the three dig sites that were issued. 9/1/22 - 7 digs at 3 dig sites issued on 8/16. Adjusted forecast to reflect $200k in 2022 with the remaining $529k in 2023. 8/1/22 - No Immediate digs from preliminary report, final report expected for review in August. 6/1/22 - No digs issued from 2022 UCD ILI yet. 3/2/22 - ILI run completed on 2/23/22. No digs issued at this time. 2/2/22 - Digs anticipated to begin in Q2 after ILI run at the end of Q1. 1/3/22 - No Change | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Toledo | DS - TOLEDO STATION |  | -45412 | 119 |  |  | 70446 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 41022 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
DS303WW - DIG SHEETS (1) DOT-180 + (1) BPL-Other - Due 02-20-22 | Item | Open | MCAP | DS303XXM2202 | Maintenance Framework | 2022084/2022085 | Roman, James | West | 6. Operational | Drawdown | Pipeline Digs | 1474 |  | 20000 | 1473.68 | 1150 | 324 | Red |  |  |  | 1474 |  |  | 229000 |  |  | 229000 | Full | 229000 | 194069 | 20000 | 214069 | No | Green | 2022-09-01 | 2022-09-14 | 2022-09-14 | 2022-11-07 | 2022-11-01 |  |  | 250.88 |  | 898.8 | 324 |  |  | 324 | Red | [10 empty] | 20000 | 2/1/23 Variance -$2k. Finished job book without charging. 1/3/23 Variance ($6k) Janx and Percheron charges. 12/5/22 Variance +$4k. BPL Ohio Tax 11/1/22 Variance (-$41,590) Cost savings. Project complete. Need to complete job book. 10/2/22 Variance (+$1,505) site visits. Plan to mobilize to first site 10/10/22 9/1/22 - Visited sites yesterday. Need to determine railroad involvement, then will submit AFE. | 2023-02-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Toledo | DS303XX - TOLEDO TO MICH S/L -WAYNE |  | 1150 | 324 |  |  | 192596 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 45325 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Int- Planned Digs
DS303WW - Temp Upgrade Cutouts | Item | Open | MCAP | DS303XXM2203 | Maintenance Framework | 2023751 | Bost, Jason | West | 6. Operational | Defined | Pipeline Digs | 4285 |  |  | 4285.47 | 4285 | 0 | Green |  |  |  | 4285 |  |  | 531000 |  |  | 531000 | Full | 531000 | 364778 |  | 364778 | No | Green | 2022-10-01 | 2022-10-15 | 2022-10-15 | 2022-12-31 | 2022-12-31 |  |  | 4128.58 | 156.89 | [17 empty] | 1/31/23 - Variance is WM invoice. 1/4/23 - Accrual is for Linde ($51,176) and Youngs ($20,947) invoices. 12/5/22 - Purge, cutouts, refill complete. Accrual is for MNT, Linde, and Youngs invoices. Forecast adjusted in December to reflect cost savings from AFE estimate. 11/1/22 - Purge scheduled for 11/14. Purge from Wayne Station to Ida West valve site (28.03 miles). October variance shifted into November forecast to reflect project schedule. 10/1/22 - Purge planned for 11/14. Mobilize mechanical contractor late Oct. 9/1/22 - Purge planned for October. Scope changed to two cutout sites. 8/1/22 - Targeting late Sept. early Oct. for purge. 6/1/22 - Developing full scope. Immediate digs issued on 5/17. Will work with PM on any additional dig sites that require a cutout and add to scope. 4/4/22 - Working with Pipeline maintenance group with incremental list to develop full scope. 3/2/22 - No Change. 2/2/22 - Cutout anticipated in Q3. | 2023-02-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Toledo | DS303XX - TOLEDO TO MICH S/L -WAYNE |  | 4285 | 0 |  |  | 360492 |  | Bartal, Nick | Guenther, Steve |  |  | 1 | 40720 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Planned Cutouts
DT - Supplemental Anode Groundbed | Item | Open | MCAP | DT00000M2301 | Maintenance Framework |  | Gremer, Michael | West | 2. Pending AFE | Defined | Cathodic Protection |  | 64000 |  | 64000 | 64000 | 0 | Green | 64000 |  | 64000 | 0 |  |  | 63920 |  |  |  | Full | 63920 |  | 64000 | 64000 | No | Green | 2023-06-01 |  |  | 2023-07-31 | 2023-07-31 | [13 empty] | 30000 | 34000 | [6 empty] | 5/2/23 - Forecast revised. AFE will be submitted 5/2. 4/4/23 - PM working on AFE. Forecast moved back due to Anode lead time. 3/2/23 - PM working on scope of work (priority). 2/3/23 - PM working on scope of work. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Duncansville | DT - DUNCANSVILLE STATION |  |  | 30000 | 34000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45317 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Int - Planned Corr & FI
DT718CO - DIG SHEETS (7) Immediate - Due 03-09-23 | Item | Open | MCAP | DM718PGM2301 | Maintenance Framework | 2094331 | Bost, Jason | West | 6. Operational | Drawdown | Pipeline Digs | 654458 | 110000 |  | 764458.04 | 539978 | 224480 | Red |  | 745441 | 745441 | 19017 |  |  | 745441 |  |  | 745441 | Full | 745441 | 654458 | 110000 | 764458 | No | Green | 2023-03-01 | 2023-04-26 | 2023-04-26 | 2023-05-31 | 2023-04-28 |  |  |  |  | 289978.26 | 364479.78 | 200000 | 200000 | 164480 | Red |  | WorkAhead of Schedule | 100000 | 10000 | [7 empty] | 5/1/23 - All digs complete. Restoring last site this week. Integrity issuing MOC's to restore pressure. 4/3/23 - 3 of 6 digs complete. Mobilized to 4th dig on 3/29. Remaining two digs required additional permitting with Wets Penn Power and the PA Turnpike. Permits expected to be in hand within April. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Coraopolis | DM718PG - DELMONT TO PITTSBURGH |  | 289978 | 474480 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46701 |  | Schultz, Amy | Independent | Aqua | 2023-03-06
DT718CO - Temp Repair Cutouts | Item | Open | MCAP | DT718DMM2201 | Maintenance Framework | 1956022 | Roman, James | West | 3. Active | Defined | Pipeline Digs | 105005 | 595000 | 72900 | 700005.4 | 763361 | -63356 | Yellow | 550000 |  | 550000 | 150005 |  |  | 37000 | 891000 |  | 928000 | Full | 928000 | 191507 | 667900 | 859407 | No | Green | 2022-04-01 | 2022-04-07 | 2022-04-07 | 2022-09-09 | 2023-05-26 |  |  | 7790.22 | 22384.75 | -11813.79 | 86644.22 | 150000 | 150000 | -63356 | Red |  | Buckeye/Customer Schedule | 595000 | [7 empty] | 72900 | 5/1/23 Variance -$138,484, Accrual $74k, schedule bumped a week. Worked one week in April instead of two. 4/5/23 Variance -$13k. Forgot to forecast the re-classification of mischarges. 3/1/23 Variance $16k. Reclassifying $20k. Re-accruing $5,600. Scheduling dept wants this cutout to occur in May. Foercast has been revised to reflect ths. 2/1/23 Variance -$3k 1/4/23 Variance $1k. Local labor to plan project. Forecast assumes PG718CO cutout will be on schedule. Same crew plans to mobilize to this project after PG718 is complete. 7/22/2022 - NEB - deferred to 2023 per discussion with local ops, project management, integrity, scheduling, and commercial. 2022 forecast moved to Q1 2023 7/8/22 had mtg with scheduling today. Even if we received DEP permit, we are not able to have the line down due to all current and scheduled down time for the laurel line. Scheduling has requested that we move this cutout to mid Sept. 7/5/22 - Variance - Accrual. Waiting on DEP permit 6/2/22 - Variance - difficulty finding 18" pipe, had planned on purchasing in May. Environmental permit submitted. May need to perform this project after PG718COM2201 due to limited resources this summer. .5/2/22 - RR Permit submitted. Variance -$25k did not order materials yet. HOP not yet started. 4/4/22 - Corporate has added another cutout site. Phase 1 AFE was submitted. Will begin permitting and shoring design in April. May separate into two construction phases. If that's the case, will adjust summer forecast showing two separate cutout events. 3/2/22 No change | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Duncansville | DT718DM - DUNCANSVILLE STA-DELMONT |  | 18361 | 681644 |  |  | 86502 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40721 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Planned Cutouts
DT718DM - Supplemental Magnesium Groundbed | Item | Open | MCAP | DT718DMM2301 | Maintenance Framework |  | Gremer, Michael | West | 2. Pending AFE | Defined | Cathodic Protection |  | 41000 |  | 41000 | 41000 | 0 | Green | 41000 |  | 41000 | 0 |  |  | 41514 |  |  |  | Full | 41514 |  | 41000 | 41000 | No | Green | 2023-05-01 |  |  | 2023-06-30 | 2023-06-30 | [6 empty] | 5000 | 5000 | -5000 | Red |  | Forecasting | 5000 | 36000 | [7 empty] | 5/2/23 - Missed Forecast due to delay in Contractors submitting prices. AFE will be submitted on 5/2. 4/4/23 - PM working on AFE. 3/2/23 - PM working on scope of work (priority). 2/3/23 - PM working on scope of work. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Duncansville | DT718DM - DUNCANSVILLE STA-DELMONT |  |  | 41000 |  |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45331 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Int - Planned Corr & FI
Dubuque Headgate Valve Replacement | Item | Open | MCAP | UB760ARM2203 | Maintenance Framework | 2004172 | Scott, Cory | West | 3. Active | Defined | Valves |  | 18700 |  | 18700 | 18700 | 0 | Green | 20000 |  | 20000 | -1300 |  |  | 23000 |  |  | 23000 | Phase | 23000 | 6155 | 18700 | 24855 | No | Green | 2022-09-01 | 2022-07-27 | 2022-07-27 | 2022-09-18 | 2023-06-30 | [13 empty] | 18700 | [7 empty] | 5/8/2023 - PO placed for prairie industrial for $18,700.00 for a June install. 5/2/2023 - Awaiting capital project purge for install. 3/31/2023 - Awaiting capital project purge for install. 2/28/2023 - Per capital projects, 760 line will be purged in June. Shifted forecast to reflect this installation date. 1/9/2023 - Obtained contractor quote of 18K for installation. Pending capital projects purge of UB760, project date is TBD. 11/1/2022 5K not spent due to not requiring new paint. 9/22/2022 - Forecast updated to 20K for 2023 installation. 9/7/2022 - Forecast adjusted to reflect 5K for Hydrotest in September and 5K for painting in October. 9/2/2022 - Valve passed hydrotest. 7/28/2022 - PO placed for valve to be hydrotested by Prairie Industrial. 7/22/2022 - Forecasted to the fall. Valve hydrotest and possible repair. Awaiting capital projects for installation timeframe. 6/27/2022 - Project is known not to take place in 2022. Proposed budget is moved out to CY+1 forecasted in March 2023. 4/26/2022 - Hydrotest PO requisition called in for $2,963.80. 4/20/2022 - Hydrotest request form received - 9673 4/19/2022 - PO requisitioned for hydrotest of valve. 4/14/2022 - Creating a work order to have valve hydrotested for 2/25/2022 - Awaiting to hear back from major projects to find out if this line will be purged for the exposures so it can be changed out and replaced. | 2023-05-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | UB - DUBUQUE VALVE SITE |  |  | 18700 |  |  | 6155 |  | Oey, Alex | Smith, Todd W. |  |  | 1 | 41874 |  | Guest, ProSight | Independent | Aqua | 2021-08-21 | Other Programs
Duncansville Office Rear step replacement | Item | Open | MEXP | DT00000E2201 | Maintenance Framework | 2051763 | Bost, Jason | West | 6. Operational | Defined | West | 18000 |  |  | 17999.76 | 18000 | 0 | Yellow |  |  |  | 18000 |  |  | 18000 |  |  | 18000 | Full | 18000 | 18000 |  | 18000 | No | Green | 2023-03-01 | 2022-12-15 | 2022-12-15 | 2023-01-31 | 2023-04-28 |  |  |  |  | 18000 | -0.24 |  |  | 0 | Red |  | Contractor/Vendor Issue | [9 empty] | 5/1/23 - Accrual for final installation invoice. 4/3/23 - Accrual is waiting invoice after delivery of stair unit. 3/1/23 - New ship date is 3/7. Message from SafeRack account manager "Sorry for the delay but something changed internally and I was not told what they were doing". 1/31/23 - Erecta steps scheduled for delivery on 2/21. Forecast shifted accordingly. 1/4/23 - Carrying $18k into 2023 due to not receiving the Erecta Steps in 2022. Other costs include Bolt's assistance with install. 12/5/22 - Moving forward with Erecta steps. Asset team reviewing removal of existing steps internally to reduce total cost. 11/1/22 - Project flagged for leadership scope review. Meeting scheduled for 11/3 to discuss a path forward. 10/1/22 - Had to switch contractors due to availability in 2022, working with MCK to complete work in 2022. 9/1/22 - Contractor scheduled for October. 8/1/22 - No Change. 7/5/22 - Scope walkdown with contractor in July. 6/1/22 - No change. 5/3/22 - No Change. 4/4/22 - No Change. 3/2/22 - No Change 2/2/22 - No Change 1/3/22 - No Change | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Station/Terminal |  | Duncansville | DT - DUNCANSVILLE STATION |  | 18000 | 0 |  |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 41667 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Duncansville Surge Relief | Item | Open | MCAP | DT00000M2202 | Maintenance Framework | 2013335 | Henfling, Mike | West | 3. Active | Defined | Transient/Surge Mitigation | 58731 | 331000 | 0 | 389731.02 | 375860 | 13871 | Yellow | 400000 |  | 400000 | -10269 |  |  | 42000 |  |  | 42000 | Phase | 42000 | 75888 | 331000 | 406888 | No | Green | 2022-08-01 | 2022-08-25 | 2022-08-25 | 2023-08-31 | 2023-08-31 |  |  | 2555.41 | 6674.13 | 3630.09 | 45871.39 | 3000 | 3000 | 42871 | Red |  | Supply Chain | 89000 | 100000 | 95000 | 35000 | 10000 | 2000 |  |  | 0 | 5-5-23 - Forecast updated to reflect AFE submittal. July 11th install plan. 5-2-23 - Relief valve arrived two months earlier than expected. Mechanical bids received, PO issued to Bolt. Full AFE to be submitted early May. Install either June or July, pending scheduling. 4-4-23 - Bid event for mechanical work opened in Coupa - bids due 4-18. Once bids received, will submit Full AFE for mechanical work and valves in May. Plan on July/August Installation. 3-2-23 - IFB drawings to be complete in early March. Bid event for mechanical work in late March or April. Relief valve is on order for June delivery. Plan on July/August Installation. New plan to submit Full AFE once bidding is complete. 2-2-23 - IFR drawings completed. Design Review completed 1/27. Plan to submit Phase AFE in February to order long lead relief valve and continue engineering to bid in March/April. Likely 4-month lead relief valve, so July/August construction 1-3-23 - IFR drawing package 95% complete with design review planned for January. Will need to order long-lead relief valve and skid early in 2023. 12-5-22 - IFR drawing package to be complete mid-December for design review in January. 11-2-22 - Missed forecast due to resource availability in October. Still plan to finish and review engineering package to IFB stage prior to year-end. 10-3-22 - Will send drawings for budgetary pricing this week. Still plan to finish and review engineering package to IFB stage prior to year-end. 9-6-22 - Updated 2023 forecast and uploaded estimate 9-1-22 - initial design 95% complete. Will send to contractor for budgetary pricing early September, to update 2023 forecast by end of September. Plan to finish and review engineering package to IFB stage prior to year-end. 8-12-2022 - Added forecast for 2023 and marked Plan-Demand 8-2-22 - Site visit on 7/18 to scan site and begin scoping. Initial conceptual design currently being worked on. Plan to submit AFE and PO for engineering in August. 7-5-22 - Planning to begin engineering in late July / August 6-1-22 - Reduced forecast to match shift of funds to other projects within transient/surge mitigation program. Planning for engineering-only in 2022. 5-4-22 - Reviewed West Region transient program last week - pushed engineering site visits to June/July, and will revisit if construction will still be planned in 2022 or just engineering due to other transient projects in the West Region beingover budget in 2022. 4-4-22 - No new updates. Need to schedule on-site scoping visit in April 3-2-22 - Shifted forecast one month. Scoping visit late March or April. 2-2-22 - Shifted forecast one month. Scoping visit late February or March. High level scoping meeting held 12/2021 | 2023-05-05 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Duncansville | DT - DUNCANSVILLE STATION |  | 12860 | 234871 | 140000 | 2000 | 17157 |  | DiPillo, Evan | Gardner, Travis W. |  |  | 1 | 41731 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
East Chicago (BETEU) TANKS 202 801 AND 806 EFR SEAL INSPECTIONS | Item | Open | MEXP | BETEU00E2303 | Maintenance Framework | 2093287 | Roth, Aaron | West | 6. Operational | Drawdown | Tanks | 32350 |  |  | 32350 | 25000 | 7350 | Red |  |  |  | 32350 |  |  | 25000 |  |  | 25000 | Full | 25000 | 32350 |  | 32350 | No | Green | 2023-04-01 | 2023-03-01 | 2023-03-01 | 2023-06-30 | 2023-05-01 | [5 empty] | 32350 |  |  | 32350 | Red |  | WorkAhead of Schedule | [9 empty] | 5.1 - done | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  |  | 32350 |  |  |  |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 46684 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-03-01
East Chicago East - 2BE (BETEU) Tank 2101 - OOS API 653 Insp | Item | Open | MCAP | BETEU00M2301 | Maintenance Framework | 2051693 | Roth, Aaron | West | 3. Active | Defined | Tanks | 75703 | 236000 |  | 311702.97 | 311000 | 703 | Yellow | 573981 |  | 573981 | -262278 |  |  | 311000 |  |  | 311000 | Phase | 311000 | 75703 | 236000 | 311703 | No | Green | 2023-04-01 | 2022-12-07 | 2022-12-07 | 2023-04-15 | 2023-07-31 | [5 empty] | 75702.97 | 55000 | 55000 | 20703 | Red |  | WorkAhead of Schedule | 35000 | 151000 | 50000 | [6 empty] | 5.1 - tank is being inspected this week. VAR: valves delivered and extra required bottom sampling for customer. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  |  | 261703 | 50000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44807 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
East Chicago East - 2BE (BETEU) Tank 2102 - MEXP Re-Class | Item | Open | MEXP | BETEU00E2304 | Maintenance Framework | 2112057 | Roth, Aaron | West | 3. Active | Drawdown | Tanks |  |  |  | 0 | 111000 | -111000 | Red | [6 empty] | 377996 |  |  | 377996 | Full | 377996 |  |  |  | No | Green |  | 2023-04-21 | 2023-04-21 | 2023-05-01 | 2023-04-21 | [6 empty] | 91000 | 91000 | -91000 | Red | [11 empty] | 5.1.23 - tank RTS, awaiting magnetrol level switch delivery. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  |  | 0 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46907 |  | Roth, Aaron | Independent | Aqua | 2023-04-07
East Chicago East - 2BE (BETEU) Tank 2102 - OOS API 653 Insp | Item | Open | MCAP | BETEU00M2302 | Maintenance Framework | 2053661 | Roth, Aaron | West | 3. Active | Defined | Tanks | 409605 |  |  | 409604.72 | 173770 | 235834 | Red | 576877 |  | 576877 | -167272 |  |  | 311000 |  |  | 311000 | Phase | 311000 | 409605 |  | 409605 | No | Green | 2023-01-01 | 2022-12-24 | 2022-12-24 | 2023-04-15 | 2023-07-31 |  |  | 28894.33 | 112310.52 | 123565.4 | 144834.47 | -91000 | -91000 | 235834 | Red | [11 empty] | 5.1 - done. project to flip to MEXP | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  | 264770 | 144834 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44808 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
East Chicago East - 2BE (BETEU) Tank 240 - OOS API 653 Insp | Item | Open | MCAP | BETEU00M2212 | Maintenance Framework | 2044309 | Roth, Aaron | West | 6. Operational | Defined | Tanks | 202582 |  |  | 202581.91 | 210602 | -8020 | Yellow | 233433 |  | 233433 | -30851 |  |  | 326000 |  |  | 326000 | Phase | 326000 | 277111 |  | 277111 | No | Green | 2022-12-01 | 2022-11-07 | 2022-11-07 | 2022-04-01 | 2023-05-31 |  |  | 187925.02 | -3011.21 | -4312.08 | 21980.18 |  |  | 21980 | Red |  | WorkAhead of Schedule | [9 empty] | 5.1 - done | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  | 180602 | 21980 |  |  | 74529 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44806 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
East Chicago East - 2BE (BETEU) Tank 204 – OOS Corr Insp & Refurb | Item | Open | MCAP | BETEU00M2201 | Maintenance Framework | 1938081 | Roth, Aaron | West | 6. Operational | Defined | Tanks | -26514 |  |  | -26513.94 | -13354 | -13160 | Red |  |  |  | -26514 |  |  | 268000 | 120000 |  | 388000 | Full | 388000 | 383764 |  | 383764 | No | Green | 2022-02-01 | 2022-01-11 | 2022-01-11 | 2022-01-03 | 2022-12-31 |  |  | -15771.82 | 1673.54 | 744.2 | -13159.86 |  |  | -13160 | Red |  | Forecasting | [9 empty] | 2.1 - done. VAR: dropped accrual, not needed. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  | -13354 | -13160 |  |  | 410278 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41256 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
East Chicago East - 2BE (BETEU) Tank 401 - OOS Corr Insp & Refurb | Item | Open | MCAP | BETEU00M2101 | Exempt | 1782245 | Roth, Aaron | West | 7. Closed | Defined | Tanks | 12 |  |  | 11.67 | 12 | 0 | Green |  |  |  | 12 |  |  | 317000 |  |  | 317000 | Phase | 317000 | 401002 |  | 401002 | No | Green | 2021-01-01 | 2020-12-02 | 2020-12-02 | 2021-12-31 | 2021-09-30 |  |  |  | 11.67 | [17 empty] | 12/22/22 - PO and WO closed - ready to be closed by accounting. 9.30.21 - Tank RTS. paint touchup done. | 2022-12-22 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  | 12 | 0 |  |  | 1854 |  | Stine, Carlton | Bassani, Joel D. | N/A |  | 1 | 30358 |  | Guest, ProSight | Independent | Aqua | 2018-08-06 | Int - Tanks
East Chicago East (BETEU) Butane Vessels NFPA Compliance Engineering | Item | Open | MEXP | BETEU00E2302 | Maintenance Framework | 2093986 | Roth, Aaron | West | 6. Operational | Defined | Pressure Vessels | 33000 |  |  | 33000 | 33000 | 0 | Green | 30000 |  | 30000 | 3000 |  |  | 33000 |  |  | 33000 | Full | 33000 | 33000 |  | 33000 | No | Green | 2023-03-01 | 2023-03-06 | 2023-03-06 | 2023-09-20 | 2023-05-01 |  |  |  |  | 11000 | 22000 | 11000 | 11000 | 11000 | Red |  | WorkAhead of Schedule | [9 empty] | 5.1 - TAS finalized the IFR package. to review with ops this month and complete. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  | 11000 | 22000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 45276 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Int - Tanks
East Chicago East (BETEU) Tank 206 Cleaning | Item | Open | MEXP | BETEU00E2201 | Maintenance Framework | 1936951 | Roth, Aaron | West | 7. Closed | Defined | Tanks | 3876 |  |  | 3875.82 | 3876 | 0 | Green |  |  |  | 3876 |  |  | 20000 |  |  | 20000 | Phase | 20000 | 27637 |  | 27637 | No | Green | 2022-04-01 | 2021-12-31 | 2021-12-31 | 2022-12-31 | 2022-09-30 |  |  | 833.34 | 3042.48 | [17 empty] | 12/22/22 - PO and WO closed - ready to be closed by accounting. 6.1.22 - done | 2022-12-22 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  | 3876 | 0 |  |  | 23761 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41258 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
East Chicago East Butane Suction Valve Replacement | Item | Open | MCAP | BETEU00M2207 | Maintenance Framework | 1989626 | Roth, Aaron | West | 5. Deferred | Defined | Valves | 3930 |  |  | 3929.84 | 185 | 3745 | Red | 60000 |  | 60000 | -56070 |  |  | 85000 |  |  | 85000 | Full | 85000 | 23786 | 60000 | 83786 | No | Green | 2022-07-01 | 2022-07-07 | 2022-07-07 | 2022-08-01 | 2024-04-30 |  |  | 91.59 | 93.25 |  | 3745 |  |  | 3745 | Red | [11 empty] | 4.3 - deferred to 2024 since tank 301 is due next year. this will reduce flaring costs. | 2023-04-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  | 185 | 3745 |  |  | 19856 | 60000 | Oey, Alex | Janesy, Ryan |  |  | 1 | 41805 |  | Guest, ProSight | Independent |  | 2021-08-21 | Other Programs
East Chicago East Butane Tanks Remote ESD Valve Activation | Item | Open | MCAP | BETEU00M2208 | Exempt | 1990355 | Grinder, Mark | West | 6. Operational | Defined | Instrumentation & Controls | -3041 |  |  | -3041.37 | -3041 | 0 | Green |  |  |  | -3041 |  |  | 15000 |  | 4000 | 19000 | Full | 19000 | 16790 |  | 16790 | No | Green | 2022-07-01 | 2022-06-13 | 2022-06-13 | 2022-11-29 | 2022-11-01 |  |  | 4432.79 | -7474.16 | [17 empty] | 4-27-2023 - This project has been completed. 3-23--2023 - This project has been completed. 3-01--2023 - This project has been completed. 3-01--2023 - This project has been completed. February actuals wrong per COGNOS report should be -$7,642.61 1-31-2023 - This project has been completed. 12-29-2022 - This project has been completed. 11-28-2022 - This project has been completed. 11-01-2022 - This project was completed on 10/22 working on Equipment tags and as-builts 9-26-2022 - Working on a Control Narrative for this project. and hopefully complete this before December. 8-29-2022 - Submitted the MOC last week and will attempt to get this completed in early December. 7-27-2022- I was just informed that the PLC Equipment is now supposed to be delivered in December 2022, I am changing the forecast to December. 6-29-2022- I was just informed that the PLC Equipment is now supposed to be delivered in December 2022, I am changing the forecast to December. 5-31-2022 - Submitting the AFE this week. 5-24-2022 - AFE is ready to submit. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  | -3041 | 0 |  |  | 19831 |  | Forsey, Frank | Janesy, Ryan |  |  | 1 | 41661 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
East Chicago East DHS - Railroad Gate Camera | Item | Open | MCAP | BETEU00M2308 | Maintenance Framework | 2112630 | Grinder, Mark | West | 3. Active | Defined | Security & Cameras |  | 55000 |  | 55000 | 55000 | 0 | Green | 55000 |  | 55000 | 0 |  |  | 53793 |  |  | 53793 | Full | 53793 |  | 55000 | 55000 | No | Green | 2023-06-01 | 2023-04-25 | 2023-04-25 | 2023-08-31 | 2023-08-31 | [13 empty] | 20000 | 25000 | 10000 | [5 empty] | 4-27-2023 - The AFE has just been approved and PO's are submitted for this project. 3-23-2023 - We have not received all of the quotes for this project. 3-01-2023 - We had a meeting on this last week and will submit an AFE after quotes come back. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  |  | 20000 | 35000 |  |  |  | Clark, Chris | Clark, Chris B |  |  | 1 | 45275 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Other Programs
East Chicago East HVAC duct work on EU front office building | Item | Open | MCAP | BETEU00M2304 | Exempt | 2095042 | Grinder, Mark | West | 3. Active | Defined | West |  | 20000 |  | 20000 | 20000 | 0 | Green | 20000 |  | 20000 | 0 |  |  | 18240 |  |  | 18240 | Full | 18240 |  | 20000 | 20000 | No | Green | 2023-05-01 | 2023-03-14 | 2023-03-14 | 2023-06-30 | 2023-06-30 | [12 empty] | 10000 | 10000 | [7 empty] | 4-27-2023 - PO submitted, Site Safety Plan Approved and will begin work in May. 3-23-2023 - The AFE was submitted and waiting for approval. 3-01-2023 -Getting quotes for AFE submission. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  |  | 20000 |  |  |  |  | Gardner, Travis | Janesy, Ryan |  |  | 1 | 45250 |  | Guest, ProSight | Independent | Aqua | 2022-08-24 | Other Programs
East Chicago East Oneok Communication Link | Item | Closed | MCAP |  | Exempt |  | Grinder, Mark | West | 8. Canceled | Defined | Instrumentation & Controls |  |  |  | 0 |  | 0 | Green | 5000 |  | 5000 | -5000 | [11 empty] | No | Green |  |  |  |  | 2023-01-31 | [21 empty] | 12/29/22 - there is a MEXP project to replace this one. 12/19/22 - there is a MEXP project for this one. 9-26-2022 - I will submit an AFE for this project in early October Oneok says they will be available in November to assist with alarm data transfer and programming. 8-29-2023 - This is still being discussed with Oneok and a path forward should be decided in September. 8-8-2022 - Added 2023 Rollover Forecast of $1 to indicate addition consideration during 2023 budgeting. FF 7-27-2022 - We are still discussing this project with Oneok and another meeting is scheduled. 6-29-2022 - We are still discussing this project with Oneok and another meeting is scheduled. 5-20-2022 - This project is being discussed with Oneok and operations. | 2022-12-29 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  |  | 0 |  |  |  |  | Forsey, Frank |  |  |  | 1 | 41672 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
East Chicago East Oneok Communication Link MEXP | Item | Open | MEXP | BETEU00E2208 | Maintenance Framework | 2036035 | Grinder, Mark | West | 3. Active | Defined | West | -133 | 2000 |  | 1866.87 | 1867 | 0 | Green |  |  |  | 1867 |  |  | 15000 |  |  | 15000 | Full | 15000 | 10916 | 2000 | 12916 | No | Green | 2022-11-01 | 2022-10-04 | 2022-10-04 | 2022-12-31 | 2023-06-30 |  |  | 0 | -133.13 | 0 | 0 |  |  | 0 | Green |  |  |  | 2000 | [7 empty] | 4-27-2023 - Oneok is supposed to have their MOC approved in June. 3-23-2023 - We had another meeting with Oneok and they stated that they would not be ready on their end until June. 3-01-2023 - We had another meeting with Oneok and they stated that they would not be ready on their end until June. 1-31-2023 - This project is waiting for Oneok to complete an MOC on their end so we can cut over the communications to Modbus. 12-29-2022 - This project is completed as far as we can go until Oneok Performs an MOC on their end, Oneok said this will not be approved until next year. 11-28-2022 - This project is completed as far as we can go until Oneok Performs an MOC on their end, Oneok said this will not be approved until next year. 11-01-2022 - The AFE and MOC has been approved but waiting for Oneok to have an approved MOC on their end so I am moving the forecast to December. 9-26-2022 - I will submit an AFE for this project in early October Oneok says they will be available in November to assist with alarm data transfer and programming. 8-29-2023 - This is still being discussed with Oneok and a path forward should be decided in September. 8-8-2022 - Added 2023 Rollover Forecast of $1 to indicate addition consideration during 2023 budgeting. FF 7-27-2022 - We are still discussing this project with Oneok and another meeting is scheduled. 6-29-2022 - We are still discussing this project with Oneok and another meeting is scheduled. 5-20-2022 - This project is being discussed with Oneok and operations | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  | -133 | 2000 |  |  | 11049 |  | Gardner, Travis | Janesy, Ryan |  |  | 1 | 45936 |  | Meitzler, Antoinette | Independent | Aqua | 2022-09-30 | Other Programs
East Chicago East Propylene Pipe Painting | Item | Candidate | MCAP |  | Exempt |  | Logan, Rob | West | 2. Pending AFE |  | Atmospheric Corrosion |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 | [9 empty] | 10000 | 10000 | No | Green | 2023-08-01 |  |  |  | 2023-08-31 | [15 empty] | 10000 | [5 empty] | 05/01/2023 Pending AFE Have contacted CPM for scheduling 04/03/2023 Pending AFE 03/02/2023 AFE Pending | 2023-05-01 |  |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETEQ - BUCKEYE E CHICAGO RAILROAD LLC |  |  | 0 | 10000 |  |  |  | Geib, Rob |  |  |  | 1 | 45708 |  | Logan, Rob | Independent | Aqua | 2022-08-30 | Int - Planned Corr & FI
East Chicago East Seal Coating Dike Roads | Item | Candidate | MEXP |  | Maintenance Framework |  | Parker, Brian | West | 2. Pending AFE |  | Secondary Containment |  | 35000 |  | 35000 | 35000 | 0 | Green | 35000 |  | 35000 | 0 | [9 empty] | 35000 | 35000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 15000 | 20000 | [5 empty] | 5/1/23 - sent email to M+J today asking for an update on the proposal. 4/3/23 - met with M+J to obtain quote for 2023 work and future years work. 2/3/23 - need to call Nick Distasio with M+J to walk down the roadway and obtain some quotes for about 3 different areas. | 2023-05-01 |  |  | West | Pipelines and Terminals | Station/Terminal |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  |  | 0 | 35000 |  |  |  | Spari, Markella |  | N/A |  | 1 | 21101 |  | Guest, ProSight | Independent | Aqua | 2016-09-08 | Other Programs
East Chicago East Spring Check Install for Water Hammer | Item | Open | MCAP | BETEU00M2303 | Maintenance Framework | 2075148 | Parker, Brian | West | 6. Operational | Defined | Truck Racks | 22887 |  |  | 22887.07 | 24698 | -1811 | Yellow | 26000 | 3936 | 29936 | -7049 |  |  | 29936 |  | 3964 | 33900 | Full | 33900 | 22887 |  | 22887 | No | Green | 2023-02-01 | 2023-01-13 | 2023-01-13 | 2023-06-09 | 2023-04-14 |  |  |  | 8654.16 | 389.44 | 13843.47 | 8654 | 8654 | 5189 | Red | [11 empty] | 5/1/23 - Aaron provided a proposal from Manhattan Mechanical for this work. Getting PO issued to contractor today so we can charge this to the correct project. 4/17/23 - work completed on 4/14. Looks like we need to work up specs for additional DFT checks for the 2 Ethanol pumps and the 2 RFG pumps. Just need to process invoices before close out. 4/1/23 - re-accruing 8,654 for Wolseley for Mar. No word on receipt of 2nd DFT spring check valve yet. Expect this to be installed in Apr. 3/29/23 - last update is that DFT should ship 3/31. 3/1/23 - received one DFT check valve on 2/28 so will accrue 8,654 for Feb. Local ops is planning on installing this check next week. Still have the delivery for the 2nd DTF for mid-Apr. 2/3/23 - 12 week lead time for one DFT check valve so no status change until mid-Apr. 1/13/23 - entered req for purchase of DFT Excalibur Silent Check Valves (qty 2). Expect delivery before Apr 14th. 1/9/23 - submitted AFE for approval routing. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  | 9044 | 13843 |  |  |  |  | Younce, Michael | Janesy, Ryan |  |  | 1 | 45248 |  | Guest, ProSight | Independent | Aqua | 2022-08-24 | Other Programs
East Chicago East Sump 2 Repair | Item | Open | MEXP | BETEU00E2206 | Maintenance Framework | 1970620 | Parker, Brian | West | 7. Closed | Defined | West | 1260 |  |  | 1260 | 1260 | 0 | Green |  |  |  | 1260 |  |  | 10000 |  |  | 10000 | Full | 10000 | 33535 |  | 33535 | No | Green | 2022-05-01 | 2022-04-08 | 2022-04-08 | 2022-07-29 | 2022-06-06 |  |  | 930 | 330 | [17 empty] | 4/5/23 - requested archive of this project site. 12/5/22 - var is due to final billing for contaminates found in silt removed from sump. Took a significant amount of time to locate a disposal facility that would accept this material for disposal. This resulted in extended monthly rental charges and a high, final disposal cost. 7/28/22 - have monthly rental of 1,240 for vac box from GFL for July, plus probably another month in Aug for rental, plus waste disposal yet to be invoiced. Aug FCST should be close. 7/2/22 - accruing a 2nd invoice from GFL for 4,638 that was approved on 7/1. PO is closed and WO is closed - ready to close in JDE. 6/6/22 - work is complete and sump is back on-line. GFL cleaned out a lot of sludge, was able to enter the vault and isolate the old Driscoll piping. Need to process final invoices. 5/31/22 - work now planned for Jun 1st or 2nd. Accruing 2,824 for Shultz removal of pump in early May. 5/3/22 - work planned for Jun, weather permitting. Just need to be a little dryer and past the rainy season. 4/5/22 - submitted AFE for approval routing. Planning for Jun work. 2/18/22 - moving this FCST from Apr to Jun - need to work on this when it's dry and not in the rainy season. | 2023-04-05 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  | 1260 | 0 |  |  | 32275 |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 41743 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
East Chicago East Switchrack 1B FCU Cutover | Item | Open | MCAP | BETEU00M2109 | Exempt | 1877719 | Parker, Brian | West | 7. Closed | Unplanned | Instrumentation & Controls | 982 |  |  | 981.73 | 982 | 0 | Green |  |  |  | 982 |  |  | 63000 |  |  | 63000 | Full | 63000 | 47614 |  | 47614 | No | Green | 2021-09-01 | 2021-08-10 | 2021-08-10 | 2021-11-19 | 2022-03-31 |  |  | 21816.23 | -20834.5 | [17 empty] | 5/6/23 - PO and WO closed - ready to be closed in JDE by accounting. 2/28/23 - Var is due to accrual and invoice posting in Jan. Inv was posted in Jan after accrual deadline. Need to confirm everything is good, close out open PO amounts and close the WO in JDE. 2/3/23 - re-accruing RA invoice for 21,816.23. This was re-entered into OI and now has a pay date of 2/8/2023. Cognos is showing (21,816.23) for Jan but OPPM is showing zero for Jan. Seems to be a common issue this month across multiple projects. 1/1/23 - reaccruing RA invoice for 21,816.23. OI is not back up yet so I can't check on the status of this invoice today. 12/2/22 - invoice was cancelled automatically in OI due to 90 days of no activity. Sent an email to Beth to see what she recommends. 11/1/22 - final invoice from RA is in OI but was disputed back to RA - they need to add 1,427.23 to a tax line before this can be approved and paid. Re-accruing this inv for Oct. Sent email to Beth to see if she can send email to Rockwell Automation to correct and re-send. 10/1/22 - final invoice from RA is in OI but was disputed back to RA - they need to add 1,427.23 to a tax line before this can be approved and paid. Re-accruing this inv for Sep. 9/1/22 - final RA invoice for 20,389 did not get loaded into OI before EOM cut off - re-accruing for Aug and it will be processed in early Sep. 7/30/22 - found out that RA is having a 3rd party billing issue with a vendor that will not provide details for an extra 6,000 they are requesting. Asking RA to just invoice for what they have right not then work out the 3rd party billing issue down the road. Re-accruing 20,389 for Jul. 7/2/22 - sent a second email to RA asking for an update on when we can expect to see an invoice for this work. Re-accruing the open PO amount of 20,389 until we receive the final invoice. 6/2/22 - Var is due to dropped 22,360 accrual for Sargent Electric. Re-accruing 20,389 for Rockwell. Cancelled the open PO amount to Sargent. Project is complete except for DWG updates.5/3/22 -re-accruing 20,389 for Rockwell and 22,360 for Sargent Electric. Project is complete except for DWG updates. 4/2/22 - RIO was online 3/24 and cutover was completed the week of 3/28. Have DWG's to update and PLC programs to upload. Sargent has a little bit of cleanup to complete in Apr. Accruing the full open PO amounts for RA and Sargent. 2/28/22 - re-accruing 15,000 for Rockwell and 20,000 for Sargent Electric. Derek is stillwaiting on panel from RA and thinks it will be installed in late Mar. Splitting cost between Mar/Apr due to uncertainty. 2/1/22 - with the current weather situation moving remaining FCST out to Mar - some work could be completed in Feb. 1/3/22 - work should start back up in Jan and hope to get this wrapped up by end of Feb. 12/1/21 - I don't expect much progress during the month of Dec so moving 10,000 of remaining FCST out to Jan/Feb 2022. 11/3/21 - panel work completed from Rockwell - remaining work will be split betweenNov and Dec. 10/4/21 - 40% of Sargent Electric PO has been completed in Sep. Cabinet and Remote Rack is on order per Rockwell Automation update. 9/1/21 - PO's to R-A and Sargent were issued on Aug 30th and 31st. Should have new conduit run vac'd out in Sep and installed. 8/4/21 - submitted AFE to workflow for approval routing. | 2023-05-06 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  | 982 | 0 |  |  | -4524 |  | Forsey, Frank | Jakubowski, Greg |  |  | 1 | 40919 |  | Guest, ProSight | Independent | Aqua | 2021-08-04 | Other Programs
East Chicago East Tank 204 Pump Replacement | Item | Open | MCAP | BETEU00M2203 | Maintenance Framework | 1970632 | Roth, Aaron | West | 6. Operational | Defined | Rotating Equipment | -8270 |  |  | -8269.89 | -8270 | 0 | Green |  |  |  | -8270 |  |  | 58000 | 131060 |  | 189060 | Full | 189060 | 176511 |  | 176511 | No | Green | 2022-04-01 | 2022-04-08 | 2022-04-08 | 2022-10-01 | 2022-12-31 |  |  | 11.69 | -9620.8 | 1339.22 | [16 empty] | 1.3 - work done, JDE tagging and as-builts remain. VAR due to dropping 2 accruals, those POs completed under budget. | 2023-01-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  | -8270 | 0 |  |  | 184781 |  | Posipanko, Dan | Posipanko, Daniel A. |  |  | 1 | 41066 |  | Guest, ProSight | Independent | Aqua | 2021-08-06 | Other Programs
East Chicago East Tank 401 Pump Replacement | Item | Open | MCAP | BETEU00M2106 | Maintenance Framework | 1846640 | Roth, Aaron | West | 7. Closed | Defined | Rotating Equipment | 43 |  |  | 43.18 | 43 | 0 | Green |  |  |  | 43 |  |  | 194000 |  |  | 194000 | Full | 194000 | 186418 |  | 186418 | No | Green | 2021-05-01 | 2021-06-03 | 2021-06-03 | 2021-07-30 | 2021-08-31 |  |  | 43.18 | [18 empty] | 9.30.21 - done. pump commissioned, drawings submitted, tags hung, paint done. | 2021-09-30 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  | 43 | 0 |  |  | -11511 |  | Posipanko, Dan | Posipanko, Daniel A. |  |  | 1 | 40082 |  | Guest, ProSight | Independent | Aqua | 2021-05-11 | Marine
East Chicago East Truck Rack VAVAC Pressure Transmitter Relocate | Item | Candidate | MCAP |  | Maintenance Framework |  | Grinder, Mark | West | 4. On-Hold |  | Vapor Management |  |  |  | 0 |  | 0 | Green | 35000 |  | 35000 | -35000 | [9 empty] | 35000 | 35000 | No | Green | 2024-05-01 |  |  |  | 2023-06-30 | [21 empty] | 4-27-2023 - It has been decided that this project should be moved to 2024 and is now forecast for May, 2024. 4-3-2023 - This project is now back on and holding a meeting to determine where the transmitter will be placed. 3/1/2023 - TWG - this project is no longer required per vapor program and has been canceled. The budgeted money has been moved to the west region drawdown. | 2023-04-27 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  |  | 0 |  |  |  | 35000 | Karl, Marissa |  |  |  | 1 | 45116 |  | Guest, ProSight | Independent | Aqua | 2022-08-19 | Other Programs
East Chicago East Warehouse Roof Refurbishment | Item | Open | MCAP | BETEU00M2305 | Exempt | 2096310 | Parker, Brian | West | 3. Active | Defined | West |  | 50800 |  | 50800 | 50800 | 0 | Green | 30000 | 25565 | 55565 | -4765 |  |  | 55565 |  |  | 55565 | Full | 55565 |  | 50800 | 50800 | No | Green | 2023-08-01 | 2023-03-23 | 2023-03-23 | 2023-04-28 | 2023-08-31 | [15 empty] | 45800 | 5000 |  |  |  |  | 5/1/23 - sent email on 4/26 to confirm that we are still good with a start date at the end of Aug. Just waiting on reply back from Matt Wehrle. 3/31/23 - just heard back today from Ridgeworth that their current schedule has this work starting mid to end of Aug. Adjusted FCST to reflect this update and will check monthly to see if this 2-day job could possibly start earlier than Aug. 3/29/23 - entered Req for Ridgeworth Roofing. 2/28/23 - walking this down with Ridgeworth Roofing to obtain a 2nd quote on Mar 1st. Adjusted the FCST to reflect what I est. is the correct EAC. 2/3/23 - walked down the site with Barney on Jan 19th and requested a revised quote from Gluth Brothers for the full roof at $44,415. Just waiting on a reply back on the warranty period for this system then will send to leadership for their review. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEG - BET EAST CHICAGO TERMINAL |  |  | 0 | 50800 |  |  |  | Gardner, Travis | Janesy, Ryan |  |  | 1 | 45115 |  | Guest, ProSight | Independent | Aqua | 2022-08-19 | Other Programs
East Chicago Station Center Manifold Pump Refurbishment | Item | Open | MCAP | EG00000M2201 | Maintenance Framework | 2036568 | Gardner, Travis | West | 7. Closed | Drawdown | Rotating Equipment | 162 |  |  | 161.66 | 162 | 0 | Green |  |  |  | 162 |  |  | 125000 |  |  | 125000 | Full | 125000 | 101873 |  | 101873 | No | Green | 2022-10-01 | 2022-10-10 | 2022-10-10 | 2022-12-31 | 2022-11-30 |  |  |  | 161.66 | [17 empty] | 11/1/2022 - project complete OPEX reclass submitted. 9/30/2022 - AFE submitted for emergent pump repair that was completed on OPEX. Reclassing cost from OPEX | 2022-11-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | EG - EAST CHICAGO STA (NORCO) |  | 162 | 0 |  |  | 101712 |  | Posipanko, Dan | Spitz, Nicholas P. |  |  | 1 | 45778 |  | Gardner, Travis | Independent | Aqua | 2022-09-09 | Other Programs
East Chicago Transformer Bushing Repair and Refill | Item | Open | MEXP | BETEG00E2203 | Maintenance Framework | 2038403 | Gardner, Travis | West | 7. Closed | Drawdown | Electrical | 16641 |  |  | 16641.3 | 16641 | 0 | Green |  |  |  | 16641 |  |  | 17000 |  |  | 17000 | Full | 17000 | 16641 |  | 16641 | No | Green | 2023-01-01 | 2022-10-31 | 2022-10-31 | 2022-12-16 | 2022-12-31 |  |  | 16641.3 | [18 empty] | 3/24/2023 - work completed in January. closing project. 1/4/2023 - work pushed to Janauary due contractor availiblity.. 12/2/2022- operation has the worlk scheduled for January 10th. 11/2/2022 - emergent project that we are planning to have done in november. | 2023-03-24 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | E. Chicago Terminals | BETEG - BET EAST CHICAGO TERMINAL |  | 16641 | 0 |  |  |  |  | Ashley, Robert | Spitz, Nicholas P. | N/A |  | 1 | 46147 |  | Gardner, Travis | JDE Child | Burnt Orange | 2022-10-31 | Other Programs
East Chicago West - 3BE (BETEG) Tank 108 - OOS Corr Insp & Refurb | Item | Open | MEXP | BETEG00E2101 | Exempt | 1781991 | Roth, Aaron | West | 7. Closed | Defined | Pressure Vessels | 12 |  |  | 11.67 | 12 | 0 | Green |  |  |  | 12 |  |  | 122000 |  |  | 122000 | Phase | 122000 | 12 |  | 12 | No | Green | 2021-01-01 | 2020-12-02 | 2020-12-02 | 2021-12-31 | 2021-05-09 |  |  |  | 11.67 | [17 empty] | 5/9/21 - forecasting re-class to MCAP for June. Move this from May to June since AFE has not been approved and we have not processed final invoicing. 4.3.21 - Tank RTS. paint touchups remain 5.17.21 - IFR repairs included: patching areas of corrosion on deck, replacement of leg actuated vacuum breaker with allentech PV vent | 2021-05-17 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETEG - BET EAST CHICAGO TERMINAL |  | 12 | 0 |  |  |  |  | Stine, Carlton | Bassani, Joel D. | N/A |  | 1 | 30362 |  | Guest, ProSight | Independent | Aqua | 2018-08-06
East Chicago West - 3BE (BETEG) Tank 141 - OOS Corr Insp & Refurb | Item | Open | MEXP | BETEG00E2102 | Exempt | 1781992 | Roth, Aaron | West | 6. Operational | Defined | Pressure Vessels | -6725 |  |  | -6725 | -6725 | 0 | Green |  |  |  | -6725 |  |  | 183000 |  |  | 183000 | Phase | 183000 | 216966 |  | 216966 | No | Green | 2021-01-01 | 2020-12-02 | 2020-12-02 | 2021-12-31 | 2021-12-31 |  |  | -6725 | [18 empty] | 12/22/22 - PO and WO closed - ready to be closed by accounting. 1.3.22 - complete, RTS. | 2022-12-22 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETEG - BET EAST CHICAGO TERMINAL |  | -6725 | 0 |  |  |  |  | Stine, Carlton | Bassani, Joel D. | N/A |  | 1 | 30364 |  | Guest, ProSight | JDE Child | Burnt Orange | 2018-08-06 | Int - Tanks
East Chicago West (BETEG)- Secondary containment improvements | Item | Open | MEXP |  | Maintenance Framework |  | Parker, Brian | West | 2. Pending AFE |  | Secondary Containment |  | 49000 |  | 49000 | 49000 | 0 | Green | 49000 |  | 49000 | 0 | [9 empty] | 49000 | 49000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 10000 | 39000 | [5 empty] | 2/28/23 - discussed this during some emails and a phone call with Diamond Z. Plan is to combine this SOW with the IFC drawing package that was just released by Diamond Z today and just combine the Tank 120-122 dike work and this SOW into this project as a Phase II. | 2023-02-28 |  |  | West | Pipelines and Terminals | Station/Terminal |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  |  | 0 | 49000 |  |  |  | Spari, Markella |  |  |  | 1 | 45169 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
East Chicago West Drum Containment Area | Item | Open | MCAP | BETEG00M2302 | Exempt | 2093964 | Parker, Brian | West | 3. Active | Defined | West | 37401 | 19051 |  | 56451.69 | 55000 | 1452 | Yellow | 20000 |  | 20000 | 36452 |  |  | 63746 |  |  | 63746 | Full | 63746 | 37401 | 19051 | 56452 | No | Green | 2023-03-01 | 2023-03-14 | 2023-03-14 | 2023-06-30 | 2023-07-31 |  |  |  |  | 29000 | 8400.69 | 6000 | 6000 | 2401 | Red |  |  | 9051 |  | 10000 | [6 empty] | 5/8/23 - approved Graybar, TAS, and Mills Excavating invoices in Apr. Est. ship date is now at end of June. 50% charge to P-Card for enclosure should post in May and expect the remaining 50% to post in July. EAC is at 56,000 4/3/23 - concrete work was completed on the 30th. Will accrue 29,000 in Mar for Mills Excavating. Expect the enclosure to be shipped around May 1st. Expect the Mini Power Zone to ship in Apr. EAC is 55,000. 3/28/23 - Mills started excavating and forming up for the concrete pad. 3/1/23 - requested an Interim AFE on Feb 24th so I can get long lead items ordered ASAP. Will submit the full AFE sometime in Mar. Adjusted the EAC to what I expect to spend to project accurate FCST's. 2/3/23 - need to request a quote from Securall for drum building that will hold 12 - 55 gal drums plus the ramp. Will also need to get TAS to create a concrete pad dwg so I can obtain some pricing for this pad. | 2023-05-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEG - BET EAST CHICAGO TERMINAL |  | 29000 | 17452 | 10000 |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 41759 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
East Chicago West EG Robicon VFD Upgrade - Phase I | Item | Open | MCAP | BETEG00M1902 | Exempt | 1583210 | Grinder, Mark | West | 7. Closed | Defined | Electrical | -19400 |  |  | -19400 | -19400 | 0 | Green |  |  |  | -19400 |  |  | 27000 |  |  | 27000 | Phase | 27000 | 0 |  | 0 | No | Green |  | 2019-04-25 | 2019-04-25 | 2019-06-28 | 2019-08-31 |  |  |  |  | -19400 | [16 empty] | 10-04-2019 - The study has been completed and a project has been entered for 2020. 08-01-2019 - The Engineering study is almost complete and will be submitted mid month and a 2020 project will be entered. 7-01-2019 - Waiting for Meade to submit the VFD Engineering Study. 05-01-2019 - Will be writing a PO for the engineering study this month. 4/17/19 - submitted AFE to workflow for approval routing - Phase I FEED for 2019 only with construction planned for 2020. 1/21/2019 - current budget is not sufficient for construction - will be submitting one AFE for Engineering in 2019 with 2020 Construction to follow - plan on utilizing the extra funds in 2019 for other high priority projects as necessary. | 2020-06-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEG - BET EAST CHICAGO TERMINAL |  | -19400 | 0 |  |  |  |  | Ashley, Robert | Parker, Brian K. | N/A |  | 1 | 26279 |  | Guest, ProSight | Independent | Aqua | 2017-09-16
East Chicago West Lab Building HVAC upgrade | Item | Open | MCAP | BETEG00M2301 | Exempt | 2075704 | Parker, Brian | West | 7. Closed | Defined | West | 13242 |  |  | 13242.07 | 13103 | 139 | Yellow | 16000 |  | 16000 | -2758 |  |  | 16176 |  |  |  | Full | 16176 | 13242 |  | 13242 | No | Green | 2023-02-01 |  |  | 2023-04-28 | 2023-02-28 |  |  |  | 10006 | 3096.72 | 139.35 |  |  | 139 | Red | [11 empty] | 5/6/23 - ready to be closed in JDE by accounting. 4/1/23 - processed last invoice from Hayes Mechanical for electrical power modifications. PO and WO closed in JDE. Ready to be closed by accounting. Will move to closed status next month. 2/28/23 - var is due to work completed ahead of schedule. Invoice has been approved and will close out project next month. 2/3/23 - AFE approved and PO issued. Unit is on order and don't expect to see for a month or two. | 2023-05-06 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEG - BET EAST CHICAGO TERMINAL |  | 13103 | 139 |  |  |  |  | Gardner, Travis | Janesy, Ryan |  |  | 1 | 45114 |  | Guest, ProSight | Independent | Aqua | 2022-08-19 | Other Programs
East Chicago West Parking Lot Lightning | Item | Open | MCAP | BETEG00M2205 | Exempt | 2051639 | Gardner, Travis | West | 6. Operational | Emergent | Security & Cameras | 26476 |  |  | 26475.68 | 26476 | 0 | Green |  |  |  | 26476 |  |  | 53000 |  |  | 53000 | Full | 53000 | 48396 |  | 48396 | No | Green | 2022-12-01 | 2022-12-06 | 2022-12-06 | 2023-01-30 | 2023-01-30 |  |  | 883.63 | 24490 | 1102.05 | [16 empty] | 3/1/2023 - work has been completed waiting for invoice. 2/2/2023 - Variance was contractor waiting for materials. project will finish in Feb. running conduit. 1/4/2023 - new pole was set in place. remaining work not done due to cold temps. 12/2/2022 - emergent project. AFE just routed. operations is planning to complete work in December. | 2023-03-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEG - BET EAST CHICAGO TERMINAL |  | 26476 | 0 |  |  | 21920 |  | Clark, Chris |  |  |  | 1 | 46273 |  | Gardner, Travis | Independent | Aqua | 2022-11-30 | Other Programs
East Chicago West Propylene Gas Detector Replacement | Item | Open | MCAP | BETEQ00M2202 | Maintenance Framework | 1980816 | Grinder, Mark | West | 6. Operational | Defined | Instrumentation & Controls | 7987 |  |  | 7986.53 | 7987 | 0 | Green |  |  |  | 7987 |  |  | 71000 |  |  | 71000 | Full | 71000 | 64292 |  | 64292 | No | Green | 2022-09-01 | 2022-05-17 | 2022-05-17 | 2022-09-30 | 2022-11-30 |  |  |  | 7642.61 | 343.92 | [16 empty] | 4-27-2023 - This project has been completed. 3-23--2023 - This project has been completed. 3-01--2023 - This project has been completed. 1-31-2023 - This project has been completed. 12-28-2022 - This project has been completed except installing the tags which just came in last week. 11-28-2022 - This project has been completed, JDE tags are on order and equipment list has been submitted. Meade PO was not used technicians installed all equipment and 4K in Freight and taxes did not hit. 11-01-2022 - This project did not get completed this month due to other priorities, moving the forecast to December. Technician replacing 1 detector to confirm everything is correct and will finish remaining 10 detector installations. 9-26-2022 - Material just received and working on scheduling this work for October completion. 8-29-2022 - Project still planning on an October completion. 7-27-2022 - Project still planning on an October completion. 6-21-2022 - I just received a material lead time and now arriving in September. 5-31-2022 - Updated lead time for material is 10 weeks so I moved the forecast to August, and September. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEQ - BUCKEYE E CHICAGO RAILROAD LLC |  | 7987 | 0 |  |  | 56305 |  | Forsey, Frank | Janesy, Ryan |  |  | 1 | 37344 |  | Guest, ProSight | Independent | Aqua | 2020-07-29 | Other Programs
East Chicago West Propylene Sample Skid Installation | Item | Candidate | MCAP |  | Maintenance Framework |  | Grinder, Mark | West | 4. On-Hold |  | Measurement & Quality Control |  | 21000 |  | 21000 | 21000 | 0 | Green | 21000 |  | 21000 | 0 | [9 empty] | 21000 | 21000 | No | Green | 2023-12-01 |  |  |  | 2023-06-30 | [19 empty] | 21000 |  | 4-27-2023 - This project is on-hold and will probably be cancelled. 3-23-2023 - This project is on-hold and will probably be cancelled. 3-01-2023 - Working with operations to determine if this should be an RCAP project | 2023-04-27 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEQ - BUCKEYE E CHICAGO RAILROAD LLC |  |  | 0 |  | 21000 |  |  | Hopkins, Christa |  |  |  | 1 | 45300 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Other Programs
East Chicago West Shore Manifold Actuator Replacements 2022 | Item | Open | MCAP | BETEU00M2210 | Maintenance Framework | 2011987 | Parker, Brian | West | 7. Closed | Emergent | Valves | 2171 |  |  | 2171.18 | 2171 | 0 | Green |  |  |  | 2171 |  |  | 116000 |  | 29000 | 145000 | Supplemental | 145000 | 143154 |  | 143154 | No | Green | 2022-10-01 | 2022-08-11 | 2022-08-11 | 2022-10-31 | 2022-10-27 |  |  | 2171.18 | 0 | [17 empty] | 2/28/23 - Rockwell invoice approved in Feb. PO's and WO closed - ready to be closed by accounting. 2/3/23 - accruing 2,000.90 in Jan for Rockwell Automation. 1/9/23 - Dec charge of 4,481 is CWIP. 11/28/22 - all PO's closed, need to close out project after JDE Equipment Tags have been updated. 11/1/22 - Nov FCST is inventory issue of 5 actuators. Work was completed on 10/27 and operational. Accruing 6,720 for Actuation Group for Oct. 10/25/22 - starting this work today. Added 2 more actuators to this SOW - getting change orders issued and will get supplemental AFE issued in early Nov. 10/4/22 - expect Vander Werf to get conduit/wiring installed by 10/7 then new actuators can be installed after that. Forecasting inventory issue of 68,700 for Nov due to cycle count in Oct. 9/3/22 - waiting on a quote from Joe Biondo for installation and then work with local ops to get this scheduled. Entered Req. for Vander Werf into JDE. 8/2/22 - submitted AFE for $116,000 total cost for approval routing. 8/1/22 - waiting on proposal from Vander Werf to make modbus wiring changes then I can submit the full AFE. Sep FCST is issuance of 3 actuators to the project with installation in Oct. Might be able to advance this work into Aug/Sep timeframe. 7/19/22 - waiting on proposal from Derek Previs to install modbus out to the manifold. Travis has about $105,000 available to fund this project which should be enough for 3 actuators. Forecasting inventory issue for Aug and installation for Sep based on est. for modbus install at this time. 7/14/22 - Need to move Dec 2023 FCST to Dec 2022 once OPPM has been unlocked in July. | 2023-02-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEU - BET EAST CHICAGO |  | 2171 | 0 |  |  | 140982 |  | Oey, Alex | Gardner, Dale |  |  | 1 | 44154 |  | Guest, ProSight | Independent | Aqua | 2022-07-14 | Other Programs
East Chicago West Tank 106 - Geodome Repairs | Item | Open | MEXP | BETEG00E2201 | Maintenance Framework | 1936954 | Roth, Aaron | West | 3. Active | Defined | Tanks |  | 15000 |  | 15000 | 15000 | 0 | Green |  |  |  | 15000 |  |  | 13000 |  |  | 13000 | Phase | 13000 |  | 15000 | 15000 | No | Green | 2023-06-01 | 2021-12-31 | 2021-12-31 | 2022-12-31 | 2023-06-30 | [13 empty] | 15000 | [7 empty] | 5.1 - fcst june. send someone up for a day T&M | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETEG - BET EAST CHICAGO TERMINAL |  |  | 15000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 40915 |  | Guest, ProSight | Independent | Aqua | 2021-08-03 | Int - Tanks
East Chicago West Tank 120-122 Dike Refurbishment | Item | Open | MEXP | BETEG00E2202 | Maintenance Framework | 1970925 | Parker, Brian | West | 3. Active | Defined | Secondary Containment | 798 | 80000 |  | 80798 | 80798 | 0 | Green | 80000 |  | 80000 | 798 |  |  | 58000 |  |  | 58000 | Phase | 58000 | 52382 | 80000 | 132382 | No | Green | 2022-05-01 | 2022-04-08 | 2022-04-08 | 2022-10-31 | 2023-07-31 |  |  | -2.5 |  | 800.5 | [9 empty] | 40000 | 40000 | [5 empty] | 5/1/23 - had a bid walkdown on Apr 18th with Brieser Construction (Dan Bobzin) and bids should be due May 5th. Plan to evaluate bids and get PO issued in May. 4/10/23 - created bid event in Coupa on Apr 7th. 4/1/23 - have complete list of bidders now by location and will get a Coupa bid event created in Apr for the Phase II construction. 2/28/23 - Sent emails out to 10 contractors to see which locations they want to bid on for dike work in 2023. I've received 6 responses back to date. Should have bid event created in Coupa in Mar for this project since IFC dwg package was just issued. 2/3/23 - waiting on IFB drawing set from Diamond Z. 1/30/23 - processed last invoice from Diamond Z. Just waiting on final IFB drawing set to go out for bid. 1/5/23 - no change in status - work pushed out to 2023 - Diamond Z revision based on review was emailed to stakeholders - need to confirm IFB drawings are current then go out for bid. Accruing 4,200 for Diamond Z 11/30/22 - reviewed dwg's on 11/18 and only had one comment to see about moving the drainage swale to the West of the old tank foundation which could possibly reduce the amount of soil out of this tank dike. Diamond Z is looking into this now. 10/31/22 - no change in status - work pushed out to 2023. Waiting on additional quotes. 10/1/22 - emailed dwg's to Feken, Helmkamp, and Mills - Feken declined, just waiting on replies back from the other two contractors. Reaccruing 22,000 for Diamond Z. 9/8/22 - moving this FCST out to 2023 - not 100% sure contractors are available for this work for the remainder of 2022. 9/1/22 - replied back to Diamond Z on proposal after receiving comments back from local ops - reviewing the details and the SOW - will be re-accruing 33,384 for Aug, expect partial invoice in early Sep. Expect IFR dwg's in late Sep. 7/30/22 - re-accruing 33,384 for Diamond Z - they need more time to find a resolution for this design. 7/2/22 - accruing 33,384 of Jun earned value for Diamond Z - should have final IFR in early Jul. 5/31/22 - accruing 8,000 for Diamond Z in May based on work completed to date. Jun FCST should be remaining costs for Phase I and Phase II. 5/3/22 - issued PO to Diamond Z to scan/survey all tank dikes at the facility to calculate containment volumes and develop a IFR and IFC drawing set to address drainage issues are the two tanks. 4/5/22 - submitted Phase I AFE for approval routing. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | E. Chicago Terminals | BETEG - BET EAST CHICAGO TERMINAL |  | 798 | 0 | 80000 |  | 51584 |  | Spari, Markella | Spari, Markella |  |  | 1 | 37355 |  | Guest, ProSight | Independent | Aqua | 2020-07-29 | Other Programs
East Chicago West Tank Overfill Site Annunciation | Item | Candidate | MCAP |  | Exempt |  | Grinder, Mark | West | 2. Pending AFE |  | Instrumentation & Controls |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 | [9 empty] | 40000 | 40000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 10000 | 10000 | 20000 |  |  |  |  | 4-27-2023 - Waiting for a final quote to submit the AFE. 3-23-2023 - This project has partially been completed during other project work and I will have a scope walk through in the beginning of April. 3-01-2023 - Working on scope of work for quoting. | 2023-04-27 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEG - BET EAST CHICAGO TERMINAL |  |  | 0 | 40000 |  |  |  | Forsey, Frank |  |  |  | 1 | 38141 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
East Chicago West Thermal Relief Upgrades | Item | Candidate | MCAP |  | Maintenance Framework |  | Stalbaum, Cameron | West | 2. Pending AFE |  | Facility Integrity |  | 35000 |  | 35000 | 35000 | 0 | Green | 35000 |  | 35000 | 0 | [9 empty] | 35000 | 35000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 35000 | [6 empty] | 5/1/23 - Have a project walk down with Mike Cuddy on 5/4. Will be reviewing the old quote and getting updated quotes. 4/3/23 - Working on scope. Had a high level meeting with asset team, but need to have another detailed follow up meeting. 12/2/20 - AFE Submitted | 2023-05-01 |  |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETEG - BET EAST CHICAGO TERMINAL |  |  | 0 | 35000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 37338 |  | Guest, ProSight | Independent | Aqua | 2020-07-29 | Int - Planned Corr & FI
East Hammond (BETEH) - Secondary containment improvements | Item | Open | MEXP |  | Maintenance Framework |  | Parker, Brian | West | 2. Pending AFE |  | Secondary Containment |  | 94000 |  | 94000 | 94000 | 0 | Green | 94000 |  | 94000 | 0 | [9 empty] | 94000 | 94000 | No | Green | 2023-08-01 |  |  |  | 2023-09-30 | [15 empty] | 10000 | 84000 |  |  |  |  | 2/28/23 - just waiting for IFC drawing set from Diamond Z for last years work then go out for bid. | 2023-02-28 |  |  | West | Pipelines and Terminals | Station/Terminal |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  |  | 0 | 94000 |  |  |  | Spari, Markella |  |  |  | 1 | 45167 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
East Hammond (BETEZ) Tank D2 and D3 Access Platforms | Item | Candidate | MCAP |  | Exempt |  | Lloyd, Andrew | West | 2. Pending AFE |  | West |  | 44000 |  | 44000 | 44000 | 0 | Green | 44000 |  | 44000 | 0 | [9 empty] | 44000 | 44000 | No | Green | 2023-08-01 |  |  |  | 2023-06-30 | [15 empty] | 22000 | 22000 |  |  |  |  | 5/1/2023 walking this down with operations and Bob at Talon steel on 5/3/2023. 4/14 contacted Bob at Talon steel for site walkdown with operations. 4/3/23 status as prior 3/3/23 local contractor contact received for walkdown and quote purposes. Field verify with Kevin and Ben in field. Will obtain quote so as to submit AFE | 2023-05-01 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  |  | 0 | 44000 |  |  |  | Gardner, Travis |  |  |  | 1 | 43251 |  | Guest, ProSight | Independent | Aqua | 2022-03-24 | Other Programs
East Hammond Dead Leg Piping Removal 2023 | Item | Candidate | MEXP |  | Exempt |  | Lloyd, Andrew | West | 5. Deferred |  | Facility Integrity |  |  |  | 0 |  | 0 | Green | 100000 |  | 100000 | -100000 | [9 empty] | 100000 | 100000 | No | Green | 2024-06-01 |  |  |  | 2024-07-31 | [21 empty] | 4/3/23 status as prior 3/27/23 - moved FCST out to 2024 - this will be deferred to next year per email from Travis Gardner and Mike Ricke. 3/2/23 operations provided timing preference for work and preferred contractor. Will walkdown and obtain quote for afe submittal | 2023-04-10 |  |  | West | Pipelines and Terminals | Station/Terminal |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  |  | 0 |  |  |  | 100000 | Aiken, Elaine |  |  |  | 1 | 40576 |  | Guest, ProSight | Independent | Aqua | 2021-07-17 | Int - Planned Corr & FI
East Hammond North Property HVAC Replacement | Item | Open | MCAP | BETEH00M2303 | Exempt | 2094295 | Grinder, Mark | West | 3. Active | Defined | West |  | 19000 |  | 19000 | 19000 | 0 | Green | 19000 |  | 19000 | 0 |  |  | 18932 |  |  | 18932 | Full | 18932 |  | 19000 | 19000 | No | Green | 2023-10-01 | 2023-03-09 | 2023-03-09 | 2023-06-30 | 2023-11-30 | [17 empty] | 14000 | 5000 |  |  | 4-27-2023 - PO sent to vendor and SSP approved, still forecast for Oct/Nov because of material lead time. 3-23-2023 - PO sent to vendor and SSP approved, still forecast for Oct/Nov because of lead time. 2-28-2023 - AFE submitted, this project has been re-forecast until October/ November because of 28 week material lead time. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  |  | 0 |  | 19000 |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 38193 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
East Hammond Terminal (BETEH) Clean/Idle Tanks D-91 and D-92 | Item | Open | MEXP | BETEH00E2301 | Maintenance Framework | 2076575 | Roth, Aaron | West | 3. Active | Defined | Tanks |  | 80000 |  | 80000 | 80000 | 0 | Green | 80000 |  | 80000 | 0 |  |  | 83600 |  |  | 83600 | Phase | 83600 |  | 80000 | 80000 | No | Green | 2023-05-01 | 2023-01-20 | 2023-01-20 | 2023-12-31 | 2023-05-31 | [12 empty] | 80000 | [8 empty] | 5.1 - install piping to tank 55 week of 5/15. clean and idle both tanks 91/92 week of 5/22. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  |  | 80000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44810 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
East Hammond Terminal (BETEH) Tank D-8F - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | BETEH00E2302 | Maintenance Framework | 2084803 | Roth, Aaron | West | 3. Active | Defined | Tanks |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 |  |  | 11200 |  |  | 11200 | Full | 11200 |  | 10000 | 10000 | No | Green | 2023-07-01 | 2023-02-08 | 2023-02-08 | 2023-12-31 | 2023-07-31 | [14 empty] | 10000 | [6 empty] | 5.1 - due date is 9.12 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  |  | 0 | 10000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44809 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
East Hammond Terminal (BETEH) Tank D-51 - OOS Corr Insp & Refurb | Item | Open | MCAP | BETEH00M2201 | Maintenance Framework | 1938073 | Roknich, Hunter | West | 6. Operational | Defined | Tanks | 4104 |  |  | 4104.24 | 4104 | 0 | Green |  |  |  | 4104 |  |  | 435000 |  |  | 435000 | Phase | 435000 | 705762 |  | 705762 | No | Green | 2022-03-01 | 2022-01-11 | 2022-01-11 | 2022-01-03 | 2022-11-30 |  |  | 3925.13 | 179.11 | [17 empty] | 2/2/2023 COGNOS showing $3,200 for January OPPM showing -20,513. OPPM issue is the cause of the variance 1/9/2023 - Variance due to vendor coming 20k under the purchase order amount. 10/3/2022 - Mechanical work complete. Hydrotest in progress. RTS Mid-October 9/2/2022 - Construction in progress. Estimated construction completion 9/23. Estimated RTS mid October. 8/2/2022 - Civil work prep, lead abatement, and electrical work completed in June. Mechanical construction to begin 8/8. Expected 6-7 weeks for construction. Estimated RTS Mid-October 7/5/2022 - Project variance due to contractor availability. Civil work and lead abatement were supposed to be completed in June, but were delayed due to contractor availability. Civil work scheduled for 7/22, costing 39k. Lead abatement scheduled 7/25, costing approx. 25k. Consolidated to mobilized for el segundo install 8/8. Estimated RTS early October, 6/2/2022 - OOS MOC awaiting approval. Tank to be drained, isolated, and opened by 6/7. Estimated 16 weeks OOS 5/3/2022 - Prelim OOS mid June 4/4/2022 - Prelim OOS mid June. Materials have been purchased. Variance due to a reclass on a valve. 3/2/22 - Prelim OOS in June. March forecast for material purchasing. 10.6.21 - OOS in June. due by 6.27. Major repairs anticipated. | 2023-02-02 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  | 4104 | 0 |  |  | 701657 |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 30365 |  | Guest, ProSight | Independent | Aqua | 2018-08-06 | Int - Tanks
East Hammond Terminal (BETEH) Tank D-52 - OOS Corr Insp & Refurb | Item | Open | MEXP | BETEH00E2001 | Exempt | 1660449 | Roth, Aaron | West | 7. Closed | Defined | Pressure Vessels | 12 |  |  | 11.67 | 12 | 0 | Green |  |  |  | 12 |  |  | 205000 |  |  | 205000 | Phase | 205000 | 161523 |  | 161523 | No | Green | 2020-01-01 | 2019-12-27 | 2019-12-27 | 2020-12-31 | 2021-04-30 |  |  |  | 11.67 | [17 empty] | 4.3.21 - Complete. Tank was RTS on 2.26. Coating touchups and stonework complete. | 2021-04-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  | 12 | 0 |  |  |  |  | Stine, Carlton | Wild, Robert | N/A |  | 1 | 30075 |  | Guest, ProSight | Independent | Aqua | 2018-07-26
East Hammond Terminal (BETEZ) Tank D-3 - OOS Corr + Seal Insp & Refurb | Item | Open | MEXP | BETEZ00E2103 | Maintenance Framework | 1889235 | Roth, Aaron | West | 6. Operational | Emergent | Tanks | 123 |  | 18000 | 122.93 | 123 | 0 | Green |  |  |  | 123 |  | Carryover/Emergent/Drawdown/Reclass | 153000 | 180000 |  | 333000 | Phase | 333000 | 336734 | 18000 | 354734 | No | Green | 2021-10-01 | 2021-09-25 | 2021-09-25 | 2021-12-31 | 2022-02-25 |  |  | 122.93 | [17 empty] | 18000 | 9.1.22 - unforecasted paint touchups | 2022-09-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETEZ - BUCKEYE HAMMOND RAILROAD LLC |  | 123 | 0 |  |  | 234944 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 42239 |  | Meitzler, Antoinette | Independent | Aqua | 2021-09-30 | Int - Tanks
East Hammond Valve Replacement Multi-year 2020 | Item | Open | MCAP | BETEH00M2304 | Exempt | 2120185 | Grinder, Mark | West | 3. Active | Defined | Valves |  | 95000 |  | 95000 | 95000 | 0 | Green | 95000 |  | 95000 | 0 |  |  | 86951 |  |  | 86951 | Phase | 86951 |  | 95000 | 95000 | No | Green | 2023-06-01 | 2023-05-05 | 2023-05-05 | 2023-08-31 | 2023-08-31 | [13 empty] | 60000 | 20000 | 15000 | [5 empty] | 4-27-2023 - The AFE will be submitted tomorrow, Valve has around a 4-week lead time and actuator is in inventory. 3-23-2023 - Still waiting on mechanical quotes before submitting the AFE. 3-01-2023 - Working on Quotes | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  |  | 60000 | 35000 |  |  |  | Oey, Alex | Oey, Alexander | N/A |  | 1 | 31255 |  | Clark, David | Independent | Aqua | 2018-08-28 | Other Programs
East St. Louis Dikewall Assessment | Item | Open | MCAP | ES00000M2201 | Exempt | 1970662 | Parker, Brian | West | 7. Closed | Defined | Secondary Containment | 1328 |  |  | 1327.69 | 1328 | 0 | Green | 25000 |  | 25000 | -23672 |  |  | 12000 | 86000 |  | 98000 | Full | 98000 | 76940 |  | 76940 | No | Green | 2022-07-01 | 2022-04-08 | 2022-04-08 | 2022-10-31 | 2022-12-09 |  |  | 2606 | -3425.31 | 2147 | [16 empty] | 4/1/23 - processed final invoice from Diamond Z in Mar. 3/1/23 - dropping accrual of 2,500 for Envirospec. Can close this on out next month. 1/31/23 - re-accruing 5,258 for Diamond Z and 2,500 for Envirospec. Just waiting on their final invoices. 1/2/23 - Helmkamp inv was paid in Dec, accruing 5,258 for Diamond Z for travel and scanning of completed dike area, 2,500 for Envirospec and 7,620.75 for inspector. Feb FCST is for any additional trailing costs. 12/22/22 - work was completed on Dec 9th and Diamond Z was on-site Dec 19th to scan the area so they can complete the as-builts. 11/29/22 - planning to start work on Dec 5th and duration is 8-10 days. 2023 FCST is for as-builts and update of plans. 11/1/22 - will be getting a PO issued to Helmkamp since they can start this work right after Thanksgiving. Will also get a Phase II AFE submitted and approved. 9/29/22 - received proposal from Helmkamp for 53,200, waiting on a second proposal from TIMCO. 9/9/22 - moving this FCST out to 2023 - not 100% sure contractors are available for this work for the remainder of 2022. Will attempt to get work completed in 2022 but planning for worst case scenario since cutoff for 2023 FCST's is near. 9/3/22 - the bid event had issues and nobody from Supply Chain followed up to see how this was progressing. Wasted 1 month on this and starting the bid process over again. I will be reaching out to all bidders the week of Sep 6th to make sure they have everything they need. 09/02/22 - Variance is from invoice associated with design IFR package to bid repair work. 08/02/22 - IFR drawing package received and out for leadership review. 07/05/22 - Repair plan is in progress and expected in next couple weeks for review. 06/02/22 - Diamond Z is evaluating previous survey for design of repairs/upgrades. 05/04/22 - Previous study will be evaluated for design of dike upgrades. Once evaluation is complete a scope will be put together. 04/11/22 - AFE approved and PO issued to Diamond Z for assessment. 7/10/19- utilizing remaining budget amount for another emergent project (see comments in Financial Notes). 4/18/19 - deferring this project to 2020 since we need to utilize 57,000 of the 65,000 budget on the WO U3 Suction Valve Replacement (OPPM ID 32998). Will change the status from On-Hold to deferred once we allocate the remaining 8,000 shown in the FCST. | 2023-04-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | St. Louis | ES - EAST ST LOUIS (MARATHON ASHLAN) |  | 1328 | 0 |  |  | 75612 |  | Clark, Dave | Spari, Markella | N/A |  | 1 | 30376 |  | Guest, ProSight | Independent | Aqua | 2018-08-06 | Other Programs
East St. Louis Haz-Gas Detectors Replacement | Item | Open | MCAP | ES00000M2302 | Exempt | 2111133 | Scannell, Adam | West | 3. Active | Defined | Instrumentation & Controls |  | 35000 |  | 35000 | 35000 | 0 | Green | 35000 | 12000 | 47000 | -12000 |  |  | 47399 |  |  | 47399 | Full | 47399 |  | 35000 | 35000 | No | Green | 2023-06-01 | 2023-04-17 | 2023-04-17 | 2023-09-30 | 2023-07-31 | [13 empty] | 17000 | 18000 | [6 empty] | 04/21/23 - AFE approved. PO issued to contractor. Scheduling walkthrough with crew discuss scope. Work to install conduit and wiring will be scheduled for May, dependent on asset team preferred schedule. Contractor is ready to start. 03/30/23 - Waiting on last quote for PLC updates to submit the AFE. Electrical work will be scheduled to complete in May if contractor is available. Materials ordered and delivery expected in June. The PLC card has a long lead time and will not arrive until August. The system will be commissioned as soon as the card arrives. 02/02/23 - Materials ordered and delivery expected in June | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | St. Louis | ES - EAST ST LOUIS (MARATHON ASHLAN) |  |  | 17000 | 18000 |  |  |  | Forsey, Frank | Decker, Paul | N/A |  | 1 | 30144 |  | Guest, ProSight | Independent | Aqua | 2018-07-30 | Other Programs
East St. Louis Main Line Motor Refurbishment | Item | Open | MCAP | ES00000M2203 | Exempt | 1980116 | Scannell, Adam | West | 6. Operational | Defined | Rotating Equipment | 5190 |  |  | 5190 | 5000 | 190 | Yellow |  |  |  | 5190 |  |  | 31000 |  | 4084 | 35084 | Full | 35084 | 35897 |  | 35897 | No | Green | 2022-05-01 | 2022-05-09 | 2022-05-09 | 2022-09-30 | 2022-11-30 |  |  |  |  | 5000 | 190 |  |  | 190 | Red | [11 empty] | 12/07/22 - Motor is complete and being held at vendor shop until pump refurbishment is complete. Variance is due to not installing the motor while waiting for pump completion. 11/02/22 - Motor being stored at contractor shop until ready to install with pump. 10/10/22 - Variance is from motor refurb being completed early that forecasted. 10/04/22 - Motor work done and at contractor shop until scheduled for delivery. 09/02/22 - Variance is due to vendor invoicing vs forecasting between this motor removal and the associated pump removal. 08/25/22 - Motor in contractor shop. DCI received, will require additional bearing work. Additional cost will be $6,800 08/02/22 - Customer asked to delay the start until they fixed pump issue. Rescheduled for 08/08/22 07/01/22 - Work was requested to be moved from 06/28 back another month due to issues at refinery. 06/02/22 - Customer has requested we push back the removal of this unit until end of June or early July. 05/12/22 - AFE approved. Removal has been moved back from May until June at the customers request. | 2023-01-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | St. Louis | ES - EAST ST LOUIS (MARATHON ASHLAN) |  | 5000 | 190 |  |  | 30707 |  | Posipanko, Dan | Decker, Paul |  |  | 1 | 40187 |  | Guest, ProSight | Independent | Aqua | 2021-05-27 | Other Programs
East St. Louis Main Line Pump Refurbishment | Item | Open | MCAP | ES00000M2202 | Exempt | 1980181 | Scannell, Adam | West | 6. Operational | Defined | Rotating Equipment | 87048 |  |  | 87048.01 | 81814 | 5234 | Yellow |  |  |  | 87048 |  |  | 42000 |  |  | 42000 | Phase | 42000 | 249205 |  | 249205 | No | Green | 2022-05-01 | 2022-05-10 | 2022-05-10 | 2022-09-30 | 2023-03-10 |  |  | 5531.14 | 322.27 | 75960.13 | 5234.47 |  |  | 5234 | Red | [11 empty] | 04/19/23 - Variance is due to complications on the installation. Had issues with pipe strain and motor mounting holes. Required the motor to be brought back to the shop and several additional days on site for resolving pipe strain issues. 03/23/23 - Installation is complete and pump is returned to service. 03/02/23 - Scheduled for delivery on 03/06/23. Will be completely installed and ready for service by EOB 03/08/23. 02/02/23 - Still on track for delivery the week of 3/06/23. Tentative install date is 3/8 - 3/9 01/04/23 - Pump work is in progress, expected delivery first week of March. 12/07/22 - No new changes to schedule. Expect pump back first week of March. Progress billing will bill 80% in December. 11/02/22 - Pump lead time has not bet reduced yet. Billing will be progressive with 80% in December, remaining amount on delivery. 10/04/22 - Pump DCI just received. 20 week lead time is quoted, working to try and have that expedited. 09/02/22 - Pump has been removed and is in the shop. Variance is due to vendor invoicing vs forecasting between this pump removal and the associated motor removal. 08/02/22 - Customer asked to delay the start until they fixed pump issue. Rescheduled for 08/08/22 07/01/22 - Work was requested to be moved from 06/28 back another month due to issues at refinery. 06/02/22 - Customer has requested we push back the removal of this unit until end of June or early July. 05/12/22 - AFE approved. Removal has been moved back from May until June at the customers request. | 2023-04-19 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | St. Louis | ES - EAST ST LOUIS (MARATHON ASHLAN) |  | 81814 | 5234 |  |  | 162157 |  | Posipanko, Dan | Decker, Paul |  |  | 1 | 40186 |  | Guest, ProSight | Independent | Aqua | 2021-05-27 | Other Programs
EC & Propylene Crash Buttons | Item | Open | MCAP | EC00000M2201 | Maintenance Framework | 1980117 | Fink, Ryan | West | 3. Active | Defined | Instrumentation & Controls | 4164 | 15200 |  | 19363.68 | 19855 | -491 | Yellow |  |  |  | 19364 |  |  | 46000 |  |  | 46000 | Full | 46000 | 24296 | 15200 | 39496 | No | Green | 2022-08-01 | 2022-05-09 | 2022-05-09 | 2022-08-15 | 2023-06-30 |  |  | 1567.29 | 100.23 | 2187.31 | 308.85 | 7000 | 7000 | -6691 | Red |  | Contractor/Vendor Issue | 200 | 7000 | 4000 | 4000 | [5 empty] | 5/1 RRF - Install bumped out to May 31 during EC outage. EAC $40k 4/12 RRF - Panel arrived from rockwell, install late april. EAC $40k 4/6 RRF - PLan to complete end of april, cont in june. EAC $40k 04-03-2023 - MNH - Adjusted April forecast to reflect EAC of $40K per Ryan's comments. 3/8 RRF - EAC $40k 3/1 RRF - april install, EAC $39k 2/2 RRF - on track for april 1/4/23 RRF - updated for april install 12/7 RRF - Rockwell inv dec. updated fcst 12/2 RRF - PLC hardware delay, not parts to install. reforecast. EAC $37,500 11/2 RRF - nov/dec install 10/3 RRF - Material delays will push out to November, Contingency and Inspection moved to Dec, may not use 9/1 RRF - late sept early oct install 8/2 RRF - Material slip, moved to Sept install 7/11 RRF - Install late July, moved out for possible slip or August finish 5/31 RRF - POs issued, waiting for material 5/2 RRF - AFE submitted 3/15/2022 RRF - first review, update fcst to May 4k, June 30k, July 5k. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | EC - EAST CHICAGO STA (BPL) |  | 3855 | 7509 | 8000 |  | 20132 |  | Forsey, Frank | Spitz, Nicholas P. |  |  | 1 | 41515 |  | Guest, ProSight | Independent | Aqua | 2021-08-18 | Other Programs
Effingham Ethanol Containment and Offloading | Item | Open | MCAP | BETEF00M2201 | Maintenance Framework | 2035946 | Scannell, Adam | West | 6. Operational | Defined | Secondary Containment | 57313 |  |  | 57312.98 | 52230 | 5083 | Yellow |  |  |  | 57313 |  |  | 330000 |  |  | 330000 | Full | 330000 | 394374 |  | 394374 | Yes | Red | 2022-10-01 | 2022-10-02 | 2022-10-02 | 2022-11-30 | 2023-01-31 |  |  | 31217.05 | 2013.31 | 0.07 | 24082.55 | 19000 | 19000 | 5083 | Red | [11 empty] | 04/05/23 - Punch list items are complete. Hydrotest was successful and coating topcoat applied. 02/02/23 - Due to multiple issues with civil contractor the 3rd party inspection cost were higher than budgeted for additional time to complete work. Inspector costs are also being audited due to discrepancies in the billing/invoice. 01/04/23 - Drain line and final tie in to be completed. All other work is done. 12/01/22 - Contractor did not install curb as designed, so work is behind schedule for completion. Expect completion in December. 11/02/22 - Work is in progress. Delayed this week due to rebar cages not being delivered. Civil will be complete next week. 10/04/22 - AFE approved. Walkthrough with contractor on 10/04/22. No feedback from leadership design review. Will hold a stakeholder meeting prior to starting work. Expected to start end of October and run into November. 09/02/22 - Bids received and being reviewed. Award will be the week of 09/05/22 and AFE to follow. 07/22/22 - IFB package sent out for leadership review. Bid package submitted to Coupa to open bid event. | 2023-04-07 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | St. Louis | BETEF - BET EFFINGHAM TERMINAL |  | 33230 | 24083 |  |  | 337062 |  | Clark, Dave | Decker, Paul | N/A |  | 1 | 31381 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Other Programs
Effingham Tank 2 Cleaning | Item | Candidate | MEXP |  | Maintenance Framework |  | Roth, Aaron | West | 8. Canceled |  | Tank Outage |  |  |  | 0 |  | 0 | Green | 60000 |  | 60000 | -60000 | [11 empty] | No | Green |  |  |  |  | 2023-05-31 | [21 empty] | 10.28 - clean in June after tank 12 work is complete. 11/29/22-CES-Tank 12 internal inspection has been pushed to 2033. BEST updated. This support project is no longer needed. Removing forecast and cancelling project. | 2022-11-30 |  |  | West | Pipelines and Terminals | Tank Integrity |  | St. Louis | BETEF - BET EFFINGHAM TERMINAL |  |  | 0 |  |  |  |  | Stine, Carlton |  |  |  | 1 | 44072 |  | Guest, ProSight | Independent | Aqua | 2022-07-05 | Int - Tanks
Effingham Terminal (BETEF) Dike Repairs | Item | Open | MEXP | BETEF00E2201 | Maintenance Framework | 1970927 | Parker, Brian | West | 6. Operational | Defined | Secondary Containment | 35032 | 9000 |  | 44032.22 | 44000 | 32 | Yellow | 50000 |  | 50000 | -5968 |  |  | 1000 | 58000 |  | 59000 | Full | 59000 | 38258 | 9000 | 47258 | No | Green | 2022-08-01 | 2022-04-08 | 2022-04-08 | 2022-10-31 | 2023-04-21 | [5 empty] | 35032.22 | 35000 | 35000 | 32 | Yellow |  |  |  | 9000 | [7 empty] | 5/1/23 - accruing 7,500 for O/S inspector for Apr. Waiting on final invoicing. EAC is at 47,258. Jun FCST is for as-builts and SPCC plan update. 4/21/23 - work completed on the 21st. Just processed invoice from Helmkamp on the 22nd. FCST in Jun is for as-builts and SPCC plan update. 4/17/23 - work started on the 17th. 4/7/23 - planning on work starting on Apr 17th, should have PO issued for inspector next week and SSSP has been approved. 4/1/23 - waiting on SSSP from Helmkamp to schedule this work and obtain inspector. 2/28/23 - sent SSSP and example to Helmkamp so I can get this reviewed and approved before any work starts. 2/3/23 - will work to get HASP reviewed and approved this month from Helmkamp so we can start work once weather breaks. 1/1/23 - no change in status - work pushed out to 2023 due to weather and contractor availability. 11/30/22 - pushed this out to 2023. Helmkamp will be working on ES project from Dec 5 - 16 so I don't expect them to start work here until 2023. 10/31/22 - PO issued to Helmkamp on 10/18 - waiting to see if they can get this on their schedule for 2022 and if so, need to get HASP approved. M+J proposal was too high. 9/29/22 - received proposal from Helmkamp for 27,500 and nobody else. Found out M+J will be on-site in mid-Oct for ethanol concrete containment project so send M+J the dwg package and asked them for a proposal to complete this work in Nov. 9/8/22 - moving this FCST out to 2023 - not 100% sure contractors are available for this work for the remainder of 2022. Will attempt to get work completed in 2022 but planning for worst case scenario since cutoff for 2023 FCST's is near. 9/1/22 - Aug var is Pace Analytical and SET Environmental costs to obtain profile of soils where we plan to excavate. Still waiting on bid results, plan to start work in late Sep or early Oct. 8/1/22 - just waiting on final soil sample profiles then will send out IFC drawings to contractors for quotesin Aug. Work could start in Sep. 7/3/22 - will be sending out IFC drawing to management for review via email. Bidding is off the table right now due to contractor availability so just plan on obtaining several quotes from qualified vendors. 5/31/22 - have IFC drawings in hand - will complete bid document once I have all IFCdrawings in hand and have completed drawing reviews. 5/3/22 - just waiting on IFC drawings from Diamond Z for some other dike projects so we can group these together and go out for bid sometime around lateJun or early Jul. 4/5/22 - submitted Phase I AFE for approval routing. | 2023-05-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | St. Louis | BETEF - BET EFFINGHAM TERMINAL |  |  | 44032 |  |  | 3225 |  | Spari, Markella | Spari, Markella |  |  | 1 | 40734 |  | Guest, ProSight | Independent | Aqua | 2021-07-26 | Other Programs
Effingham Terminal (BETEF) Tank E-1 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | BETEF00E2301 | Maintenance Framework | 2084801 | Roth, Aaron | West | 3. Active | Defined | Tanks |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 |  |  | 11200 |  |  | 11200 | Full | 11200 |  | 10000 | 10000 | No | Green | 2023-10-01 | 2023-02-08 | 2023-02-08 | 2023-12-31 | 2023-10-31 | [17 empty] | 10000 |  |  |  | 5.1 - do Q4. due date is 2.6.2024. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | St. Louis | BETEF - BET EFFINGHAM TERMINAL |  |  | 0 |  | 10000 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44812 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Effingham Terminal (BETEF) Tank E-12 - In-Service Aluminum Seal Inspection | Item | Open | MEXP | BETEF00E2302 | Maintenance Framework | 2094894 | Roth, Aaron | West | 3. Active | Defined | Tanks |  | 31000 |  | 31000 | 40000 | -9000 | Red | 240000 |  | 240000 | -209000 |  |  | 20350 |  | 19650 | 40000 | Full | 40000 |  | 31000 | 31000 | No | Green | 2023-05-01 | 2023-03-12 | 2023-03-12 | 2023-07-01 | 2023-08-31 | [12 empty] | 31000 | [8 empty] | 5.1 - AIFR seal inspection tentatively May 31 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | St. Louis | BETEF - BET EFFINGHAM TERMINAL |  |  | 31000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44813 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
EG Center Manifold Pumps Project | Item | Open | MCAP | BETEG00M2203 | Maintenance Framework | 2012008 | Grinder, Mark | West | 3. Active | Defined | Storm Water Management | 1414 | 3000 |  | 4413.96 | 4277 | 137 | Yellow |  |  |  | 4414 |  |  | 40000 |  |  | 40000 | Full | 40000 | 28786 | 3000 | 31786 | No | Green | 2022-09-01 | 2022-08-11 | 2022-08-11 | 2022-12-31 | 2023-06-30 |  |  | 490.77 | 651.34 | 135.11 | 136.74 |  |  | 137 | Red |  |  |  | 3000 | [7 empty] | 4-27-2023 - Still on track to be commissioned in late May or June. 3-23-2023 - This project will be commissioned and completed in May. 3-01-2023 - Radar Gauge commissioning is scheduled to be completed in May. 1-31-2023 - We are trying to schedule this to be completed in March 2023. 12-29-2022 - This project programming and wiring will be completed in December and installation and commissioning of the Radar level transmitter is scheduled for March, Vendor had no openings until next year. 11-28-2022 - This project programming and wiring will be completed in December and installation and commissioning of the Radar level transmitter is scheduled for March, Vendor had no openings until next year. 11-01-2022 - The radar gauge has been received and the panel is being built, we should be on track for a December completion. 9-26-2022 - Called for material lead time update but no response yet, we should still be completing this work in November. 8-29-2022 - The AFE has been approved and material ordered, should arrive before 10-18-2022 and forecast and project completion by the end of November. 7-27-2022 - AFE sent for approval because extra funding needed to complete project and waiting for approval before submitting into the workflow. 6-29-2022 - Meeting is scheduled for July 14th to determine the scope change. 6-03-2022 - Meeting scheduled to review alternative solution to lower project cost. 5-19-2022 - This project is severely underfunded for the scope of work that was selected for this project, We are working on breaking these into two separate projects so we can reduce the cost of each project. Forecast is being moved to September/October. | 2023-05-09 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEG - BET EAST CHICAGO TERMINAL |  | 1277 | 3137 |  |  | 27372 |  | Bonenberger, Mark | Janesy, Ryan |  |  | 1 | 38152 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
EG Rectifier Replacements | Item | Open | MCAP | BETEG00M2202 | Exempt | 2004077 | Logan, Rob | West | 6. Operational | Defined | Cathodic Protection | 7921 |  |  | 7921.38 | 6831 | 1091 | Red |  |  |  | 7921 |  |  | 24000 |  |  | 24000 | Full | 24000 | 25171 |  | 25171 | No | Green | 2022-10-01 | 2022-07-26 | 2022-07-26 | 2022-12-01 | 2023-04-26 |  |  | 864.73 | 1487.96 | 377.95 | 5190.74 |  |  | 5191 | Red |  | WorkAhead of Schedule | [9 empty] | 05/01/2023 Work completed ahead of schedule on 04/26/2023. 04/03/2023 PO issued to Vander Werf Electric for $4055 Awaiting Waste Management to remove old oil filled rectifiers so new ones can be installed The Accural was sent to Barb on 04/03/2023 03/02/2023 PO was never issued. Will check status of PO for installation and get this completed in March. 2/2/2023 Requested PO week of 1/30/2023 Vander Werf Electric for rectifier installations $4,055.00 1/4/2023 Variance is due to vacations and contractor scheduling. Installation quotes recieved awaiting PO. 12/2/2022 - install is scheduled for Dec. 11/2/2022 - accrued rectifier waiting for invoice. 10/4/2022 Rectifiers received awaiting quote from Meade for installation 9/1/22 - Rectifiers due to be delivered 9/29/22 installation in October 8/3/2022 - rectifiers on order. 6/3/22- no update from last month. 2/28/22 on track (RWL) | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETEG - BET EAST CHICAGO TERMINAL |  | 2731 | 5191 |  |  | 17250 |  | Geib, Rob | Geib, Robert |  |  | 1 | 38182 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Int - Accel Corr & FI
EG999A1 Mag anode installation | Item | Candidate | MCAP |  | Exempt |  | Logan, Rob | West | 2. Pending AFE |  | Cathodic Protection |  | 25000 |  | 25000 | 25000 | 0 | Green | 25000 |  | 25000 | 0 | [9 empty] | 25000 | 25000 | No | Green | 2023-06-01 |  |  |  | 2023-06-30 | [13 empty] | 25000 | [7 empty] | 05/01/2023 Awaiting quote from National Pipeline 04/03/2023 AFE Pending 03/02/2023 AFE Pending | 2023-05-02 |  |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | EG999A1 - BP WHITING - E CHIC BET CANAL |  |  | 25000 |  |  |  |  | Geib, Rob |  |  |  | 1 | 45686 |  | Logan, Rob | Independent | Aqua | 2022-08-29 | Int - Planned Corr & FI
El Dorado Surge Relief | Item | Open | MCAP | DG00000M2301 | Maintenance Framework | 2120015 | Henfling, Mike | West | 3. Active | Defined | Transient/Surge Mitigation |  | 480000 |  | 480000 | 480000 | 0 | Green | 480000 |  | 480000 | 0 |  |  | 23417 |  |  | 23417 | Phase | 23417 |  | 480000 | 480000 | No | Green | 2023-05-01 | 2023-05-03 | 2023-05-03 | 2023-12-31 | 2023-12-31 | [12 empty] | 5000 | 5000 | 0 |  |  | 70000 | 200000 | 200000 |  | 5-2-23 - Phase AFE in progress to complete initial engineering/feasibility of installing a small (13' Dia) tank on Buckeye property for surge relief. Engineering site plan to be complete in May with estimate ready by end of June 4-4-23 - Call held 3/27 to review project with stakeholders. Plan to submit Phase AFE for engineering/feasibility of installing a small (13' Dia) tank on Buckeye property for surge relief. Engineering/study in April/May. Plan to discuss late June with BD again to see if option to utilize adjacent facility tank, likely to be purchased by Sunoco, is still on the table and compare to cost estimate/feasbility for 13' Dia tank. 3-28-23 - Pushed most forecast to 4Q per stakeholder call on 3/27 3-3-2-23 - BD confirmed Buckeye is not a finalist to purchase adjacent Zenith facility. Need to schedule a call with stakeholders in March to discuss possible options. No easy solution with not knowing future owner of the site/adjacent land. 2-2-23 - Reached out to BD in January to confirm plans for adjacent Zenith tank farm surge relief option but still need to hear back. 9-1-22 - Zeroed 2022 forecast until new owner of Zenith tank farm is determined. Still planning on a 2023 project. 8-12-22 - Added 2023 Forecast and marked Plan Demand. Note - Zenith site is up for sale (this is still confidential), and until sale is final, we will not know how/where to install surge relief. Engineering on hold in 2022. 8-2-22 - Site visit on 7/18 to scan site and begin scoping. Marketing to confirm with Zenith regarding options to utilize existing tankage. Other options are to build a tank on leased land at El Dorado, or install relief at Duncansville Station which would require a flow rate reduction. 7-5-22 - Planning to begin engineering in late July / August 6-1-22 - Reduced forecast to match shift of funds to other projects within transient/surge mitigation program. Planning for engineering-only in 2022. 5-4-22 - Reviewed West Region transient program last week - pushed engineering site visits to June/July, and will revisit if construction will still be planned in 2022 or just engineering due to other transient projects in the West Region being over budget in 2022. 4-4-22- No new updates. Need to schedule on-site scoping visit in April 3-2-22 - Shifted forecast one month. Scoping visit late March or April. 2-2-22 - Shifted forecast one month. Scoping visit late February or March. High level scoping meeting held 12/2021 | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Duncansville | DG - ELDORADO TERMINAL |  |  | 10000 | 0 | 470000 |  |  | DiPillo, Evan | Gardner, Travis W. |  |  | 1 | 41729 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Eldorado Meter Inlet Valve Operator Replacement | Item | Open | MCAP | DG00000M2201 | Maintenance Framework | 1956649 | Gardner, Travis | West | 3. Active | Drawdown | Valves | 256 | 4000 |  | 4256.08 | 4191 | 65 | Yellow |  |  |  | 4256 |  |  | 17000 |  |  | 17000 | Full | 17000 | 13784 | 4000 | 17784 | No | Green | 2022-10-01 | 2022-03-21 | 2022-03-21 | 2022-08-01 | 2022-12-31 |  |  | 62.4 | 63.53 | 64.67 | 65.48 | 4000 | 4000 | -3935 | Red |  | Buckeye/Customer Schedule | 4000 | [8 empty] | 5/3/2023 - missed March forecast requested tech to install in May. 4/4/2023 - missed March forecast requested tech to install in April. 2/3/2023 - forecast moved to March due to tech request. 1/4/2023 - forecast moved to February due to asset team having other commitments in Dec. 12/2/2022 - holding off installing actuator due to an actuator at Greensburg issue and this would be installed there until the new one is ordered. 11/1/2022 - actuator arrive early. Operations unsure if they can install this year. 10/3/2022 - no operator in September. forecast in November. 9/1/2022 - actuator is scheduled for delivery in September. 8/2/2022 - valve operator is delay until Sept. 7/5/2022- no update from prior month.waiting for actuator to arrive. 6/3/2022 - no update from prior month. 5/2/2022 - no pudate from prior month .4/4/2022 - emergent project 16 to 18 wk lead time. 3/21/22 - emergent project 16 to 18 wk lead time | 2023-05-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Duncansville | DG - ELDORADO TERMINAL |  | 191 | 4065 |  |  | 13528 |  | Oey, Alex | Spitz, Nicholas P. |  |  | 1 | 43056 |  | Gardner, Travis | Independent | Aqua | 2022-03-01 | Other Programs
EU163JU Scraper Trap Launcher Valve Replacement | Item | Open | MCAP | EU163JUM2202 | Maintenance Framework | 2052262 | Parker, Brian | West | 7. Closed | Emergent | Valves | 638 |  |  | 637.72 | 638 | 0 | Green |  |  |  | 638 |  |  | 11000 |  |  | 11000 | Full | 11000 | 7209 |  | 7209 | No | Green | 2022-12-01 | 2022-12-12 | 2022-12-12 | 2022-12-31 | 2022-12-30 |  |  | 249.7 |  | 388.02 | [16 empty] | 1/9/23 - re-class for Dec business has posted. Ready to close out this project. 12/12/22 - submitted re-class request to move 6,571 from JU162EUM2201 to this project. 12/7/22 - just waiting to pay two invoices on other 162L project so I can submit re-class request in Dec. 11/30/22 - this is a re-class of costs - will submit AFE once I have all costs identified that need to be re-classed in Dec. | 2023-01-09 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | EU163JU - E CHICAGO B/G TO HAMMOND J B/G |  | 638 | 0 |  |  | 6571 |  | Oey, Alex | Gardner, Travis W. |  |  | 1 | 46251 |  | Guest, ProSight | Independent | Aqua | 2022-11-21 | Other Programs
Ferrysburg Actuator Replacement | Item | Open | MCAP | BETFG00M2303 | Maintenance Framework | 2093319 | Smith, Kyle | West | 3. Active | Drawdown | West |  | 11254 |  | 11254 | 11254 | 0 | Green |  | 11254 | 11254 | 0 |  |  | 11254 |  |  | 11254 | Full | 11254 |  | 22507 | 22507 | Yes | Red | 2023-06-01 | 2023-03-01 | 2023-03-01 | 2023-04-30 | 2023-06-30 | [13 empty] | 11254 | [7 empty] | 4/28/23 Cut Po for material waiting on delivery | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | BETFG - BET FERRYSBURG TERMINAL |  |  | 11254 |  |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 46587 |  | Smith, C. Kyle | Independent | Aqua | 2023-02-13
Ferrysburg - BETFG - Secondary Containment Upgrades | Item | Open | MCAP | BETFG00M2302 | Maintenance Framework | 2083803 | Parker, Brian | West | 3. Active | Defined | Secondary Containment |  | 110000 |  | 110000 | 110000 | 0 | Green | 110000 |  | 110000 | 0 |  |  | 24082 |  |  | 24082 | Phase | 24082 |  | 110000 | 110000 | No | Green | 2023-07-01 | 2023-02-03 | 2023-02-03 | 2023-08-31 | 2023-09-30 | [14 empty] | 40000 | 50000 | 20000 |  |  |  |  | 5/1/23 - Diamond Z still working on IFR drawing package. 4/4/23 - Diamond Z should be able to get to this sometime in Apr/May timeframe. 2/28/23 - PO issued to Diamond Z on Feb 14th. Will update FCST once I get schedule from Diamond Z. 2/3/23 - Phase I AFE is out for approval - will get Diamond Z a PO once AFE has been approved for IFR and IFC drawing set. Will adjust FCST after bid event has been conducted and bid awarded. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | BETFG - BET FERRYSBURG TERMINAL |  |  | 0 | 110000 |  |  |  | Clark, Dave | Spari, Markella |  |  | 1 | 45161 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
Ferrysburg Lubricity Flow Meter Replacement | Item | Open | MCAP | BETFG00M2304 | Maintenance Framework | 2110592 | Parker, Brian | West | 3. Active | Drawdown | Truck Racks |  | 18516 |  | 18516 | 18516 | 0 | Green |  | 18516 | 18516 | 0 |  |  | 18516 |  |  | 18516 | Full | 18516 |  | 18516 | 18516 | No | Green | 2023-06-01 | 2023-04-12 | 2023-04-12 | 2023-06-30 | 2023-06-30 | [13 empty] | 18516 | [7 empty] | 5/1/23 - no change in status - expect receipt of meter and install in Jun. 4/13/23 - Jun FCST is correct due to meter lead time. Issued PO to Vander Werf today. 4/3/23 - added project to OPPM and submitted AFE to workflow for routing approval. Lead time of meter is 5-6 weeks. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | BETFG - BET FERRYSBURG TERMINAL |  |  | 18516 |  |  |  |  | Younce, Michael | Gardner, Travis W. |  |  | 1 | 46869 |  | Parker, Brian | Independent | Aqua | 2023-04-03
Ferrysburg Pump and Actuator Replacment | Item | Open | MCAP | BETFG00M2301 | Maintenance Framework | 2083815 | Smith, Kyle | West | 6. Operational | Drawdown | West | 19705 |  |  | 19705 | 20589 | -884 | Yellow |  | 28589 | 28589 | -8884 |  |  | 28589 |  |  | 28589 | Full | 28589 | 19705 |  | 19705 | No | Green | 2023-04-01 | 2023-02-02 | 2023-02-02 | 2023-06-30 | 2023-05-01 | [5 empty] | 19705 | 20589 | 20589 | -884 | Yellow | [11 empty] | 4/5/23 PO wrote and work scheduled by local opps | 2023-04-05 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | BETFG - BET FERRYSBURG TERMINAL |  |  | 19705 |  |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 46538 |  | Smith, C. Kyle | Independent | Aqua | 2023-01-25 | Other Programs
Ferrysburg Terminal Secondary Berm Installation | Item | Open | MCAP | BETFG00M2201 | Maintenance Framework | 1970658 | Parker, Brian | West | 6. Operational | Defined | Secondary Containment | -1525 |  |  | -1525.27 | 145108 | -146634 | Red | 145000 |  | 145000 | -146525 |  |  | 23000 |  |  | 23000 | Phase | 23000 | 29359 |  | 29359 | No | Green | 2022-06-01 | 2022-04-08 | 2022-04-08 | 2022-10-31 | 2023-04-28 |  |  | 506.46 | 100.3 | 108.48 | -2240.51 |  |  | -2241 | Red | [11 empty] | 5/8/2023 - move dec 145K forecast to region drawdown.4/30/23 - paid final invoice for Consolidated in Apr. Project ready to be closed out in JDE. PO and WO closed. The FCST amount in December can be used where needed.4/1/23 - just waiting on Consolidated final invoice to be processed - re-accruing 8,591 for Apr. Everything FCST in Dec can be used for other projects.3/1/23 - re-accruing 8,591 for Consolidated in Feb. Trying to complete the install on Mar 9th if everybody's schedule works out.2/3/23 - re-accruing 8,591 for Consolidated in Jan. Just waiting on reply back from Sean on when this install can be scheduled.1/1/23 - accruing 10,800 for Consolidated in Dec. for installation of extended 6" flanged piping to get vapor PRV set higher.11/30/22 - still waiting on a revised estimate and install date to extend the PRV piping.10/31/22 - met with Consolidated at the terminal on 10/7 to review the SOW - expect to see a change order on this PO due to accessibility issues and needing a man lift to get over the piping. Moving this out to Dec since this has not been scheduled yet.9/29/22 - received proposal from Consolidated and got PO issued to them for 10,800 to extend the 6" flanged pipe for the PRV. Estimate this work will be completed in Nov. The additional work in 2023 is to increase the dike capacity based on 2022 survey.9/1/22 - oil stop valve will not work in this location due to proximity to the wetland area and existing grade of the site. We would also have to install electrical to keep this from freezing if we could somehow make this work. There is a budget of 153,000 proposed for 2023 on a new project at this facility based on the Eng & Design completed under this project. Plan it to use this new proposed budget in 2023 and just roll in into this current AFE as a Phase II submittal. Just adding $1 FCST for Dec 2023 to keep visibility.7/30/22 - Diamond Z is still working on the design for the oil stop valve that Env requested to be added.7/2/22 - expect additional costs to modify design for containment for 2022 then remaining costs to hit in Oct for construction - expect costs to be higher than what was budgeted. Will work withprogram owner to prioritize which projects to complete in 2022 and which ones get construction moved to 2023.6/1/22 - site has been scanned just waiting on IFR drawing set to be issued. Drawing should be complete in Jun but splitting FCST between Jun/Jul due to uncertainty.5/3/22 - Issued PO to Diamond Z to survey/scan all dikes to calculate containment volumes and develop IFR and IFC drawing set to installsecondary containment South of VRU.4/5/22 - submitted Phase I AFE for approval routing. | 2023-05-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | BETFG - BET FERRYSBURG TERMINAL |  | 715 | -2241 |  |  | 30884 |  | Clark, Dave | Spari, Markella |  |  | 1 | 41658 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
FLINT STATION UPS REPLACE | Item | Open | MCAP | WF00000M2301 | Exempt | 2119755 | Gardner, Travis | West | 3. Active | Drawdown | Electrical |  | 12000 |  | 12000 |  | 12000 | Red |  |  |  | 12000 |  |  | 13380 |  |  | 13380 | Full | 13380 |  | 12000 | 12000 | No | Green | 2023-06-01 | 2023-05-05 | 2023-05-05 | 2023-08-01 | 2023-08-01 | [13 empty] | 12000 | [7 empty] | 5/4/2023 - emergent UPS failure. | 2023-05-03 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Pipeline | WF - FLINT TERMINAL |  |  | 12000 |  |  |  |  | Ashley, Robert | Gardner, Travis W. |  |  | 1 | 47010 |  | Gardner, Travis | Independent | Aqua | 2023-05-01
Flint Terminal (BETWF) Ethanol offload PLC Upgrade | Item | Open | MCAP | BETWF00M2202 | Maintenance Framework | 1980153 | Hassan, Mohammad | West | 6. Operational | Defined | Instrumentation & Controls | 3849 | 5000 |  | 8848.65 | 9649 | -800 | Yellow | 5000 |  | 5000 | 3849 |  |  | 49000 |  |  | 49000 | Full | 49000 | 28920 | 5000 | 33920 | No | Green | 2022-07-01 | 2022-07-19 | 2022-07-19 | 2022-10-14 | 2022-10-13 |  |  |  |  | 2148.65 | 1700 | 2500 | 2500 | -800 | Red |  | Buckeye/Customer Schedule | 5000 | [8 empty] | 05-02-2023 - MNH - All parts have arrived. Due to Buckeye Tech availability, installation of remaining parts delayed. Project EAC at $34K, but we may have some savings. Moving forecast a bit due to Tech availability. 04-03-2023 - MNH - All parts have arrived. Will work with Tech to get them installed next. Project EAC at $35K, but we may have some savings. Moving forecast a bit due to Tech availability. 03-01-2023 - MNH - Some parts arrived and awaiting the remining parts. Project EAC at $35K. 02-01-2023 - MNH - Same update as last month. Project EAC at $35K. 01-03-2023 - MNH - Same update as last month. Project EAC at $35K now. 12-1-2022 - MNH - Obsolete radios will arrive 4/10/2023. Due to this delay, March $5K forecast moved to April 2023. Project EAC at $34K. 11-02-2022 - MNH - Project commissioned last month and will come under budget. Contingency & Inspection money was not needed. Waiting on replacing obsolete radios in 2023 under punch list items. Project EAC at $34K. Updating 2023 budget to $10K. 10-04-2022 - MNH - Project commissioning still planned for this month. Project EAC at $49K. 09-02-2022 - MNH - PLC is scheduled to arrive by end of this month and will plan project commissioning in October. Adding $5K forecast in 2023 due to long lead time of some obsolete radios that will be upgraded in this project. Project EAC $49K. 08-01-2022 - MNH - Project procurement underway with kick off meeting this week. July variance due to vendor invoicing upfront. August/Sep forecast reduced accordingly. 07-12-2022 - MNH - Updating forecast to $49K to match full AFE. 07-05-2022 - MNH - Received all the quotes but further delay in submitting AFE due to other project workload and emergent project work. Will submit AFE this month. Adjusting forecast. 06-01-2022 - MNH - Received all the quotes but delay in submitting AFE due to other project workload and emergent project work. Will submit AFE this month. Adjusting forecast. 05-03-2022 - MNH - Have received a quote and awaiting another quote. Moving $5K from June in Q3 due to delay in getting an AFE together. 03-31-2022 - MNH - Managing existing workload and emergent projectshave delayed scope start. Moving forecast out a month from baseline. 03-01-2022 - MNH - Will start working on SOW this month. 02-02-2022 - MNH - Will start working on SOW in March. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Pipeline | BETWF - BET FLINT TERMINAL |  | 2149 | 6700 |  |  | 25072 |  | Forsey, Frank | Ransom, Paul |  |  | 1 | 38056 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
Flint Terminal (BETWF) Operations Room Tank Alarm PLC Upgrade | Item | Open | MCAP | BETWF00M2201 | Maintenance Framework | 1980154 | Hassan, Mohammad | West | 6. Operational | Defined | Instrumentation & Controls | 9511 | 2000 |  | 11510.55 | 9580 | 1931 | Red | 9000 |  | 9000 | 2511 |  |  | 10000 |  |  | 10000 | Full | 10000 | 9870 | 2000 | 11870 | Yes | Red | 2022-10-01 | 2022-07-05 | 2022-07-05 | 2023-01-30 | 2023-03-17 |  |  |  |  | 2880 | 6630.55 | 4000 | 4000 | 2631 | Red |  |  | 1000 | 1000 | [7 empty] | 05-02-2023 - MNH - Working on project punch list items now. Project EAC at $9.5K. Some labor charges that shoudl have been reclassed in April are not showing up in OPPM. Accruing those. 04-03-2023 - MNH - Borrowed PLC installed last month. Once the PLC arrives, it will go back to the TCD project. Project EAC at $10K. Will work on project punchlist items next. Some labor charges will be reclassed to project that were on the local WO. 03-01-2023 - MNH - Talked with ARSEAL & we will borrow the needed PLC from TCD project to finish this project and once the PLC arrives, it will go back to the TCD project. Project EAC at $10K. We will try to get this installed next month as forecasted. 02-01-2023 - MNH - PLC is still delayed and vendor has not heard anything from the manufacturer yet. Project EAC at $10K. Moving forecast out a month. 02-01-2023 - MNH - PLC is still delayed and vendor has not heard anything from the manufacturer yet. Project EAC at $10K. Moving forecast out a month. 01-03-2023 - MNH - PLC is still delayed s vendor has not heard anything from the manufacturer yet. Project EAC at $10K. Moving forecast out a month. 12-01-2022 - PLC is delayed into 2023 as vendor has not heard anything from the manufacturer yet. Project EAC at $10K. 11-02-2022 - PLC is delayed into 2023 as vendor has not heard anything from the manufacturer yet. Project EAC at $10K. Moving $1K from December into 2023. 10-04-2022 - PLC most likely will get delayed into 2023 as vendor has not heard anything from the manufacturer yet. Project EAC at $10K. 09-02-2022 - PLC may get delayed into 2023 as vendor has not heard anything from the manufacturer yet. Moving majority of the forecast into 2023 to account for the delay. Project EAC $10K. 08-01-2022 - MNH - Project long lead procurement underway and on track. 06-29-2022 - MNH - AFE routed for approval and needed $3K more than budget that will be sourced from Louisville (BETVL) Load Rack Control PLC Upgrade Project (OPPM ID 38052). 06-01-2022 - MNH - Delay in submitting AFE due to other project workload and emergent project work. Will submit AFE this month. 28 week lead time puts commissioning in December. 05-03-2022 - MNH - Delay in getting an AFE submitted due to other project workload. Will plan on submitting AFE in May. 28 week lead time puts commissioning in December. 04-12-2022 - MNH - Just heard from the vendor that new C70 screen has 28 week lead time. Will need to move forecast to November. 03-31-2022 - MNH - Will submit AFE in April. 03-01-2022 - MNH - Working on SOW but vendor mentioned 20 week lead time for new PLC. Moving forecast to August. 02-02-2022 - MNH - Will start working on SOW in March. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Pipeline | BETWF - BET FLINT TERMINAL |  | 2880 | 8631 |  |  | 359 |  | Forsey, Frank | Forehand, Adam |  |  | 1 | 38041 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
Flint Terminal (BETWF) Tank 3 - OOS API 653 Insp | Item | Open | MCAP | BETWF00M2301 | Maintenance Framework | 2084425 | Arch, Stefan | West | 6. Operational | Defined | Tanks | 259391 | 17000 |  | 276391.04 | 242274 | 34117 | Red | 301580 |  | 301580 | -25189 |  |  | 199086 | 76680 |  | 275766 | Full | 275766 | 259391 | 17000 | 276391 | No | Green | 2023-02-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-05-03 |  |  |  | 14281 | 160992.85 | 84117.19 | 50000 | 50000 | 34117 | Red |  |  | 17000 | [8 empty] | 5/1/2023 - Hatzel and Buehler completed installation of conduit and wire for new high level alarms. Full AFE submitted for approval. Planning to button up on 5/2. MOC will be submitted on 5/1, Mike Ricke approved high level increase. Tank should be RTS week of 5/8. 4/3/2023 - Tank cleaned, inspected, scope developed, and mechanical repairs ongoing. Consolidated to be wrapping the repairs week of 4/3. Once repairs are complete, liner will be touched up, electrical installed, strapped, and buttoned up. Planning to have RTS in late April, beginning of May. Variance due to working ahead of schedule and getting to the mechanical repairs faster than anticipated. 3/1/2023 - Ordered material in February. Beginning cleaning on 3/6, followed by inspection. Planning for mechanical contractor to be on site 3/20. Forecasting for March includes transfer, cleaning, inspection, beginning mechanical repairs, valve procurement, and inspector services. 2/1/2023 - APi 653 project to remove tank 3 from service. Stakeholder call held on 1/11/2023. Funding apart of the 2023 West Region MCAP Tank Phase I AFE. Planning to take OOS at the beginning of March. Forecasting for February is to order equipment and valves. Anticipating minor repairs. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Wayne Terminals | BETWF - BET FLINT TERMINAL |  | 175274 | 101117 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44816 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Flint Terminal (BETWF) Tank 4 - OOS Seal Insp | Item | Open | MEXP | BETWF00E2301 | Maintenance Framework | 2084787 | Arch, Stefan | West | 6. Operational | Defined | Tanks | 6658 |  |  | 6658 | 16000 | -9342 | Red | 128000 |  | 128000 | -121342 |  |  | 22195 |  |  | 22195 | Full | 22195 | 6658 |  | 6658 | No | Green | 2023-04-01 | 2023-02-08 | 2023-02-08 | 2023-12-31 | 2023-04-26 | [5 empty] | 6658 | 16000 | 16000 | -9342 | Red |  | Forecasting | [9 empty] | 5/1/2023 - Seal inspection completed on 4/26 by Phillips. No repairs needed, project is complete. Job performed safely and to the policy. Aluminum safe work plan approved by Travis, Kevin, Mac, and Nick. 4/3/2023 - Project moved forward to April to meet EPA 114 request. Planning to complete while Phillips is on site for the other up close seal inspections at Flint. Working with Phillips on the AIFR up close seal inspection safe work plan. inspection protocol sent to EPA and waiting for their approval. 3/1/2023 - Working with Philips to complete safe work plan. This tank is apart of the EPA section 114 request. Working with Kim T to complete necessary steps. 2/1/2023 - Aluminum in service up close seal inspection. Stakeholder call held on 1/11/2023. Funding approval in the 2023 West Region In service up close seal inspections AFE. Planning to complete in May. Phillips awarded the work. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Wayne Terminals | BETWF - BET FLINT TERMINAL |  |  | 6658 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44817 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Flint Terminal (BETWF) Tank 1 OOS API 653 Insp and Refurb | Item | Open | MCAP | BETWF00M2302 | Maintenance Framework | 2094447 | Arch, Stefan | West | 3. Active | Drawdown | Tanks | 261970 | 212500 |  | 474470.35 | 375143 | 99328 | Red |  | 350000 | 350000 | 124470 |  |  | 246483 |  |  | 246483 | Phase | 246483 | 261970 | 212500 | 474470 | No | Green | 2023-03-01 | 2023-03-21 | 2023-03-21 | 2023-12-31 | 2023-12-31 |  |  |  |  | 110142.76 | 151827.59 | 150000 | 150000 | 1828 | Yellow |  | Engineering or Scope Change | 157500 | 55000 | [7 empty] | 5/1/2023 - Inspection completed on 4/13 and delay with Phillips coming on site. Phillips beginning repairs on 5/2. Planning to complete repairs by the end of May and RTS in early June. Phillips performed seal inspection on 4/26 per EPA requests. Hatzel and Buehler installing wire and conduit. Forecasting for May includes remaining mechanical repairs and inspector costs. Variance due to larger scope than anticipated. 4/3/2023 - Project arose due to finding product on the floating roof. Tank was taken OOS mid March. PO's coded to the local BU but will be re-claased to the project. Planning to have inspection and mechanical repairs completed in April. Forecasting variance in March due to not forecasting before month closed while developing the project. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Wayne Terminals | BETWF - BET FLINT TERMINAL |  | 110143 | 364328 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46733 |  | Arch, Stefan | Independent | Aqua | 2023-03-09
Flint Terminal (BETWF) Tank 1 Water and Floating Roof Inspection | Item | Open | MEXP | BETWF00E2305 | Maintenance Framework | 2093290 | Arch, Stefan | West | 8. Canceled | Drawdown | Tanks | 0 |  |  | 0 | 0 | 0 | Green |  |  |  | 0 |  |  | 12000 |  |  | 12000 | Full | 12000 | 0 |  | 0 | No | Green | 2023-02-01 | 2023-03-01 | 2023-03-01 | 2023-05-26 | 2023-05-26 |  |  |  | 3000 | -3000 | [16 empty] | 4/3/2023 - Product discovered on floating roof, DJA could not enter due to VOC levels. Allied looked at floating roof. and could not vac out through the top of the dome. Small variance on this project due to cost changed to tank 1 653 project. 3/1/2023 - Project developed for investigation of water and possible product on tank 1 roof. Operations working to get the water vacuumed off the floating roof. | 2023-04-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Wayne Terminals | BETWF - BET FLINT TERMINAL |  | 0 | 0 |  |  |  |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 46687 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-03-01
Flint Terminal (BETWF) Tank 10 Up Close Seal Inspection | Item | Open | MEXP | BETWF00E2303 | Maintenance Framework | 2093288 | Arch, Stefan | West | 6. Operational | Drawdown | Tanks | 13317 |  |  | 13317 | 15000 | -1683 | Red |  |  |  | 13317 |  |  | 15000 |  |  | 15000 | Full | 15000 | 13317 |  | 13317 | No | Green | 2023-04-01 | 2023-03-01 | 2023-03-01 | 2023-06-30 | 2023-04-26 | [5 empty] | 13317 | 15000 | 15000 | -1683 | Red | [11 empty] | 5/1/2023 - Seal inspection completed on 4/26 by Phillips. No repairs needed to the seals. Inspection was completed safely and to policy. No additional forecasting required. Safe work plan approved by Travis, Nick, Kevin, and Mac. 4/3/2023 - Inspection protocol sent to the EPA, waiting on approval from the EPA. Working with Phillips for the AIFR safe work plan. Planning to complete in late April. 3/1/2023 - Drawdown project added for EPA 114 notification. Working with air compliance and Phillips to complete inspection protocol. Planning to complete late April/early May. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Wayne Terminals | BETWF - BET FLINT TERMINAL |  |  | 13317 |  |  |  |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 46685 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-03-01
Flint Terminal API 570 Inspection | Item | Open | MEXP | BETWF00E2201 | Maintenance Framework | 1980276 | Roknich, Hunter | West | 6. Operational | Defined | Facility Integrity | -1565 |  |  | -1565 | -1565 | 0 | Green |  |  |  | -1565 |  |  | 25000 |  |  | 25000 | Phase | 25000 | 13902 |  | 13902 | No | Green | 2022-07-01 | 2022-05-11 | 2022-05-11 | 2022-12-31 | 2022-09-30 |  |  | 0 | -1565 | [17 empty] | 12/23/22 - PO and WO closed - ready to be closed by accounting. 9/2/2022 - Work complete 8/2/2022 - Inspection completed 7/5/2022- Purchase order issued. Prelim start date 7/23 6/2/2022 - Call week of 6/6 to discuss scheduling with IAG. 5/12/2022 - Current forecast for June. Working with IAG on scheduling. AFE approved. | 2022-12-23 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Pipeline | BETWF - BET FLINT TERMINAL |  | -1565 | 0 |  |  | 15467 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 37491 |  | Administrator, System | Independent | Aqua | 2020-08-05 | Int - Planned Corr & FI
Fostoria Station (BETFS) Tank 6001 Dome Repair | Item | Open | MEXP | BETFS00E2301 | Maintenance Framework | 2076584 | Arch, Stefan | West | 6. Operational | Drawdown | Tanks | 13626 |  |  | 13626 | 13626 | 0 | Green |  |  |  | 13626 |  |  | 22000 |  |  | 22000 | Full | 22000 | 13626 |  | 13626 | No | Green | 2023-02-01 | 2023-01-23 | 2023-01-23 | 2023-03-31 | 2023-03-15 |  |  |  | 7600 | 6026 | 0 |  |  | 0 | Green | [11 empty] | 4/6/2023 - Waiting on one invoice from Consolidated and then project can be moved to status 80 and closed. 4/3/2023 - Project is complete, waiting on one invoice from Consolidated for the work but it is accrued. No additional forecasting required. 3/1/2023 - Consolidated inspected and fabricated new panel for the geodome. Planning to install in March. 2/1/2023 - Project to repair the dome on tank 6001, it was damaged during a winter storm. Consolidated on site 2/1 to inspect the damage and quote. Planning to complete in February/March. | 2023-04-06 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Toledo | BETFS - BET FOSTORIA |  | 13626 | 0 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46496 |  | Meitzler, Antoinette | Independent | Aqua | 2023-01-19 | Int - Tanks
GA - FRP Installations | Item | Candidate | MCAP |  | Exempt |  | Gremer, Michael | West | 2. Pending AFE |  | Atmospheric Corrosion |  | 55000 |  | 55000 | 55000 | 0 | Green | 55000 |  | 55000 | 0 | [9 empty] | 55000 | 55000 | No | Green | 2023-07-01 |  |  |  | 2023-06-30 | [14 empty] | 30000 | 25000 | [5 empty] | 5/2/23 - PM to set up site visit with contractors. 4/4/23 - Forecast moved back to align with other proposed projects. PM working on scope. 3/2/23 - PM working on scope of work (priority). 2/3/23 - PM working on scope of work. | 2023-05-02 |  |  | West | Pipelines and Terminals | Integrity |  | Mantua | GA - AURORA TERMINAL |  |  | 0 | 55000 |  |  |  | Geib, Rob |  |  |  | 1 | 41450 |  | Guest, ProSight | Independent | Aqua | 2021-08-16 | Int - Planned Corr & FI
GA425GE - Shorted Casing Remediation - Main St. | Item | Candidate | MEXP |  | Maintenance Framework |  | Gremer, Michael | West | 2. Pending AFE |  | Cathodic Protection |  | 162000 |  | 162000 | 162000 | 0 | Green | 162000 |  | 162000 | 0 | [9 empty] | 162000 | 162000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 132000 | 30000 | [5 empty] | 5/2/23 - Bid documents sent to 4 contractors. Waiting on prices. 4/4/23 - PM working on scope of work. 3/2/23 - PM working on scope of work. 2/3/23 - PM working on scope of work. | 2023-05-02 |  |  | West | Pipelines and Terminals | Corrosion |  | Mantua | GA425GE - AURORA TO MANTUA-#2-E |  |  | 0 | 162000 |  |  |  | Geib, Rob |  |  |  | 1 | 45306 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Int - Planned Corr & FI
GC425GK - FDM-05 Boston Rd. Groundbed Replacement | Item | Open | MCAP | GC425GKM2202 | Exempt | 1990683 | Gremer, Michael | West | 6. Operational | Defined | Cathodic Protection | 1463 |  |  | 1463.24 | 1463 | 0 | Green |  |  |  | 1463 |  |  | 33000 |  |  | 33000 | Full | 33000 | 32489 |  | 32489 | No | Green | 2022-07-01 | 2022-06-16 | 2022-06-16 | 2022-09-30 | 2022-10-31 |  |  |  | 680.2 | 783.04 | [16 empty] | 4/4/23 - Contract ROW agent trying to negotiate settlement with land owner. 3/2/23 - Unexpected Charge from contract ROW agent. 11/01/22 - Work Completed. 10/04/22 - Weather issues Contractor delayed due to weather and OQ expirations. Work being done this week. Accrue $9,000 for Corrpro and $14,742 for LSC. 09/01/22 - Materials delivered. Scheduled for September install. 08/02/22 - Expected material delivery in July. Waiting on materials. Forecast revised. 07/07/22 - AFE approved on 6/16. Materials ordered on 6/23. PO issued to contractor on 6/28. Forecast revised. 06/03/22 - AFE submitted on 5/31. Waiting on approval. Forecast changed to reflect adjusted budget. 04/05/22 - Forecast moved back due to delay in Bid event. 03/03/22 - Forecast moved to May due to delay in Bid event. | 2023-04-04 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Mantua | GC425GK - WAKEMAN - BRECKSVILLE-#2-E |  | 1463 | 0 |  |  | 31025 |  | Geib, Rob | Geib, Robert |  |  | 1 | 41399 |  | Guest, ProSight | Independent | Aqua | 2021-08-12 | Other Programs
GC425GK - Shorted Casing Remediation - Ridge Rd. | Item | Candidate | MEXP |  | Maintenance Framework |  | Gremer, Michael | West | 2. Pending AFE |  | Cathodic Protection |  | 155000 |  | 155000 | 155000 | 0 | Green | 155000 |  | 155000 | 0 | [9 empty] | 155000 | 155000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 125000 | 30000 | [5 empty] | 5/2/23 - Bid documents sent to 4 contractors. Waiting on prices. 4/4/23 - PM working on scope of work. 3/2/23 - PM working on scope of work. 2/3/23 - PM working on scope of work. | 2023-05-02 |  |  | West | Pipelines and Terminals | Corrosion |  | Mantua | GC425GK - WAKEMAN - BRECKSVILLE-#2-E |  |  | 0 | 155000 |  |  |  | Geib, Rob |  |  |  | 1 | 45311 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Int - Planned Corr & FI
GE - Supplemental Groundbed Installation - 2022 | Item | Open | MCAP | GE00000M2202 | Exempt | 1990681 | Gremer, Michael | West | 6. Operational | Defined | Cathodic Protection | 324 |  |  | 324 | 324 | 0 | Green |  |  |  | 324 |  |  | 58000 |  |  | 58000 | Full | 58000 | 55903 |  | 55903 | No | Green | 2022-07-01 | 2022-06-16 | 2022-06-16 | 2022-09-30 | 2022-12-31 |  |  | 324 | [18 empty] | 01/04/23 - Work completed. 12/05/22 - New Contractor procured. Groundbed work completed. Rectifier installation to be completed in December. Accrue $35000 for NPS, $2820 for JA Electronics, $2000 for Pugh. Re-accrue $7500 for Bass. 11/01/22 - Forecast Missed. Contractor delayed to 12/5 due to coordination with sub-contractors. PM to get another contractor to do work in Nov. Accrue $7,500 for materials. 10/04/22 - Weather issues Forecast revised due to delays with contractor schedule. Work to start week of 10/10. Accrue $36,300 for Bass Engineering. 09/01/22 - Mesa starting in Sept. 08/02/22 - Forecast revised based upon Contractor's schedule. 7/7/22 - AFE approved on 6/16. Materials ordered on 6/23. PO issued to contractor on 6/28. Forecast revised. 6/3/22 - AFE submitted on 5/31. Waiting on approval. 5/2/22 - Revised forecast due to delayed bid event. 3/3/22 - Revised forecast. | 2023-01-04 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Mantua | GE - MANTUA STATION |  | 324 | 0 |  |  | 55579 |  | Geib, Rob | Geib, Robert |  |  | 1 | 41451 |  | Guest, ProSight | Independent | Aqua | 2021-08-16 | Other Programs
GE520NI - 2022 Buckeye Criteria Digs | Item | Open | MCAP | GE521ZCM2201 | Maintenance Framework | 2002799 | Burns, Richard | West | 7. Closed | Defined | Pipeline Digs | 403 |  |  | 402.86 | 182 | 221 | Red |  |  |  | 403 |  |  | 84000 |  |  | 84000 | Full | 84000 | 55804 |  | 55804 | No | Green | 2022-10-01 | 2022-07-15 | 2022-07-15 | 2022-12-31 | 2022-10-10 |  |  | 182.25 |  |  | 220.61 |  |  | 221 | Red | [11 empty] | 3/28/23 - Ready to close. Job book submitted today. 1/3/23 - variance is Percheron late invoices. 11/1/22 - most of variance is accrued; waiting on Degen invoice. rest is cost savings. 10/28/22 - repair completed on 10/6/22. 10/3/22 - dig started today. 8/31/22 - variance is because crew was pulled off here to complete more critical digs. Pushed forecast to October. 8/12/22 - this will get pushed until later in the year - crew will move to DOT-60 digs on the 211 for Jason Bost's project; those have a deadline in 9/23/22. Forecasting was closed or I would've pushed to September or later. 8/1/22 - no change. 7/20/22 - dig expected to be completed in August. 7/5/22 - Switched over dig from Ryan Taylor to Rich. He volunteered to take it. | 2023-03-28 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Mantua | GE521ZC - MANTUA TO COLUMBIANA |  | 182 | 221 |  |  | 55401 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 40994 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
GE521ZC - Shorted Casing Remediation - New Rd. | Item | Candidate | MEXP |  | Maintenance Framework |  | Gremer, Michael | West | 2. Pending AFE |  | Cathodic Protection |  | 155000 |  | 155000 | 155000 | 0 | Green | 155000 |  | 155000 | 0 | [9 empty] | 155000 | 155000 | No | Green | 2023-08-01 |  |  |  | 2023-09-30 | [15 empty] | 125000 | 30000 |  |  |  |  | 5/2/23 - Bid documents sent to 4 contractors. Waiting on prices. 4/4/23 - PM working on scope of work. 3/2/23 - PM working on scope of work. 2/3/23 - PM working on scope of work. | 2023-05-02 |  |  | West | Pipelines and Terminals | Corrosion |  | Mantua | GE521ZC - MANTUA TO COLUMBIANA |  |  | 0 | 155000 |  |  |  | Geib, Rob |  |  |  | 1 | 45312 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Int - Planned Corr & FI
GE521ZC (12in) - DIG SHEETS (7) | Item | Open | MCAP | GE521ZCM2101 | Exempt | 1837942, 1837943, 1837944, 1837945, 1837946 | Burns, Richard | West | 7. Closed | Drawdown | Pipeline Digs | -81 |  |  | -81 | -81 | 0 | Green |  |  |  | -81 |  |  | 465000 |  |  | 465000 | Full | 465000 | 158373 |  | 158373 | No | Green | 2021-06-01 | 2021-05-18 | 2021-05-18 | 2021-10-19 | 2021-06-17 |  |  |  | -81 | [17 empty] | 9/7/22 - Closed by PM. 8/16/22 - Job book submitted; ready to close. 7/1/21 - All digs completed on 6/17/21, ahead of schedule. 6/1/21 - digs started on 5/25/21. 5/5/21 - 7 anomalies / 5 dig sites issued on 4/22/21. Three due on 6/21/19, rest due on 10/19/21. | 2022-09-07 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Mantua | GE521ZC - MANTUA TO COLUMBIANA |  | -81 | 0 |  |  | 81 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 39872 |  | Schultz, Amy | Independent | Aqua | 2021-04-30 | Int- Planned Digs
GE52ZC - AC Mitigation Design Study | Item | Open | MEXP | GE521ZCE2301 | Exempt |  | Gremer, Michael | West | 2. Pending AFE | Defined | Cathodic Protection |  | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 |  |  | 29887 |  |  |  | Full | 29887 |  | 30000 | 30000 | No | Green | 2023-06-01 |  |  | 2023-07-31 | 2023-07-31 | [13 empty] | 15000 | 15000 | [6 empty] | 5/2/23 - AFE will be submitted on 5/2. 4/4/23 - PM working on AFE. 3/2/23 - PM working on scope of work. 2/3/23 - PM working on scope of work. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Corrosion |  | Mantua | GE521ZC - MANTUA TO COLUMBIANA |  |  | 15000 | 15000 |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45329 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Int - Planned Corr & FI
GR - FRP REPAIRS AND INSTALLATIONS | Item | Candidate | MCAP |  | Exempt |  | Gremer, Michael | West | 2. Pending AFE |  | Atmospheric Corrosion |  | 25000 |  | 25000 | 25000 | 0 | Green | 25000 |  | 25000 | 0 | [9 empty] | 25000 | 25000 | No | Green | 2023-10-01 |  |  |  | 2023-10-31 | [17 empty] | 25000 |  |  |  | 5/2/23 - PM to set up site visit with contractors. 4/4/23 - PM working on scope of work. 3/2/23 - PM working on scope of work. 2/3/23 - PM working on scope of work. | 2023-05-02 |  |  | West | Pipelines and Terminals | Integrity |  | Coraopolis | GR - GREENSBURG TERMINAL |  |  | 0 |  | 25000 |  |  | Geib, Rob |  |  |  | 1 | 45335 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Int - Planned Corr & FI
Granger (BETAI) Tank 7 - OOS COrr Insp & Refurb (MEXP) | Item | Open | MEXP | BETAI00E1903 | Exempt | 1549551 | Clark, Dave | West | 7. Closed | Emergent | Pressure Vessels | 5537 |  |  | 5536.7 | 5537 | 0 | Green |  |  |  | 5537 |  |  | 256000 |  |  | 256000 | Full | 256000 | 249329 |  | 249329 | No | Green | 2020-01-01 | 2019-12-01 | 2019-12-01 | 2019-12-31 | 2020-01-31 |  |  |  |  | 5536.7 | [16 empty] | 2/3/20 - DONE, waiting on invoices | 2020-02-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Michiana | BETAI - BET GRANGER |  | 5537 | 0 |  |  |  |  | Stine, Carlton | Baldwin, T. Andy |  |  | 1 | 35488 |  | Guest, ProSight | Independent | Aqua | 2019-11-06
Granger Tank 3 Surge Relief Piping Modification | Item | Open | MCAP | BETAI00M2204 | Maintenance Framework | 2002625 | Roth, Aaron | West | 3. Active | Drawdown | Tank Outage | 237 | 42000 |  | 42236.66 | 134376 | -92139 | Red | 134200 |  | 134200 | -91963 |  |  | 13000 | 208765 |  | 13000 | Phase | 221765 | 12739 | 42000 | 54739 | No | Green | 2022-08-01 | 2022-07-11 | 2022-07-11 | 2022-09-01 | 2023-05-31 |  |  | 57.67 | 58.71 | 59.77 | 60.51 |  |  | 61 | Red |  |  | 42000 | [8 empty] | 5.1 - install piping week of 5/22. start OOS 5/29. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Michiana | BETAI - BET GRANGER |  | 176 | 42061 |  |  | 12502 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44070 |  | Guest, ProSight | Independent | Aqua | 2022-07-05 | Int - Tanks
Granger Terminal (BETAI) Tank 3 - OOS API 653 Insp | Item | Open | MCAP | BETAI00M2301 | Maintenance Framework | 2084378 | Roth, Aaron | West | 3. Active | Defined | Tanks | 314 | 371785 |  | 372099.14 | 372099 | 0 | Green | 371785 |  | 371785 | 314 |  |  | 307230 |  |  | 307230 | Phase | 307230 | 314 | 371785 | 372099 | No | Green | 2023-03-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-09-30 |  |  |  |  | 314.14 | [9 empty] | 92946 | 185893 | 92946 |  |  |  |  | 5.1 - install piping week of 5/22. start OOS 5/29. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Michiana | BETAI - BET GRANGER |  | 314 | 0 | 371785 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44818 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Granger Terminal (BETAI) Tank 2 - OOS Corr + Seal Insp & Refurb | Item | Open | MCAP | BETAI00M2201 | Maintenance Framework | 1938074 | Roth, Aaron | West | 3. Active | Defined | Tanks | 73485 | 20000 | 0 | 93485.14 | 86661 | 6824 | Yellow | 15000 |  | 15000 | 78485 |  |  | 400000 | 545000 |  | 945000 | Full | 945000 | 963233 | 20000 | 983233 | No | Green | 2022-04-01 | 2022-01-11 | 2022-01-11 | 2022-01-03 | 2023-07-31 |  |  | 18443.85 | 7819.57 | 40397.91 | 6823.81 |  |  | 6824 | Red |  |  |  |  | 20000 | [5 empty] | 0 | 5.1 - tank is RTS. paint touchups remain, fcsting July VAR: unforecasted change order | 2023-05-01 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Michiana | BETAI - BET GRANGER |  | 66661 | 6824 | 20000 |  | 889748 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41267 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Granger Terminal (BETAI) Tank 2 Support Project | Item | Open | MCAP | BETAI00M2202 | Maintenance Framework | 1917366 | Roth, Aaron | West | 6. Operational | Defined | Tank Outage | 561 | 0 |  | 560.61 | 561 | 0 | Green |  |  |  | 561 |  |  | 50000 |  |  | 50000 | Full | 50000 | 39522 | 0 | 39522 | No | Green | 2022-02-01 | 2022-01-10 | 2022-01-10 | 2022-07-01 | 2023-04-01 |  |  | 179.72 | 182.96 | 197.93 | [7 empty] | 0 | [8 empty] | 4.3 - dropping forecast. done | 2023-04-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Michiana | BETAI - BET GRANGER |  | 561 | 0 |  |  | 38962 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41268 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Granger Terminal (BETAI) Tank 7 - OOS Corr Insp & Refurb | Item | Open | MCAP | BETAI00M1901 | Exempt | 1549551 | Clark, Dave | West | 7. Closed | Defined | Tanks | -5537 |  |  | -5536.7 | -5537 | 0 | Green |  |  |  | -5537 |  |  | 212000 |  |  | 212000 | Phase | 212000 | 0 |  | 0 | No | Green | 2020-01-01 | 2019-01-08 | 2019-01-08 | 2019-12-31 | 2020-01-31 |  |  |  |  | -5536.7 | [16 empty] | 2/3/20 - Reclass complete - okay to close | 2020-02-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Michiana | BETAI - BET GRANGER |  | -5537 | 0 |  |  |  |  | Stine, Carlton | Shook, Mark B. | N/A |  | 1 | 29312 |  | Guest, ProSight | Independent | Aqua | 2018-06-11
GRANGER VRU KNOCK OUT TANK PUMP REPLACEMENT | Item | Open | MCAP | BETAI00M2205 | Maintenance Framework | 2012604 | Parker, Brian | West | 3. Active | Drawdown | Vapor Management | 20555 | 4000 |  | 24554.7 | 21566 | 2989 | Red |  |  |  | 24555 |  |  | 28000 |  |  | 28000 | Phase | 28000 | 20555 | 4000 | 24555 | No | Green | 2023-03-01 | 2022-08-18 | 2022-08-18 | 2023-04-30 | 2023-05-31 |  |  |  |  | 17565.6 | 2989.1 | 4000 | 4000 | -1011 | Red |  |  | 4000 | [8 empty] | 5/1/23 - was notified in late Apr that we have a tentative date of May 25th to install this new pump & motor. 3/31/23 - sent email to Joe to get this scheduled with 8 hr outage and informed Phil that this pump/motor has arrived. Expect this to be installed in Apr. 3/30/23 - received pump/motor today and receipted in JDE. 3/3/23 - no change to status - Professional Pump is now showing a ship date of 3/13. 2/3/23 - revised ship date is now 3/9. 1/3/23 - no change in status - ship date of pump/motor is 2/17. 11/30/22 - Professional Pump is now showing a ship date of 2/17/2023 for this pump and motor. 10/31/22 - PO issued on Vander Werf on 10/18 and to Professional Pump on 10/24. Both total 20,374. 10/21/22 - created Req to purchase pump/motor - expect delivery around 12/19 or sooner. 10/12/22 - decision was made to go back to the original SOW and replace the pump/motor. Entered Coupa request to get pump vendor re-activated so we can get a PO issued. Lead time is 6-8 weeks. 10/10/22 just received proposal from Consolidated today for 87,200 for this work - adjusted the 2023 FCST amount based on this proposal after putting everything into AFE template. 9/29/22 - met with Consolidated at the site on 9/26 and waiting on quote to complete this revised SOW. Moving this work out to 2023 since Consolidated is busy and can't get to this in 2022. Estimating the cost for 2023 to complete all work at $50,000. 9/3/22 - had a call with all stakeholders and going to modify the SOW to remove the buried knock out tank and just install piping to create a drip leg with a high level switch in the drip leg. Will schedule a time to meet with a contractor on-site in Sep. Adjusted FCST to what I think it will cost to make modifications and abandon the buried tank in place. 8/11/22 - submitting AFE for routing approval. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | BETAI - BET GRANGER |  | 17566 | 6989 |  |  |  |  | Karl, Marissa | Baldwin, T. Andy |  |  | 1 | 44402 |  | Guest, ProSight | Independent | Aqua | 2022-08-03 | Other Programs
Granville Terminal (BETAK) Tank 4 Seal Repairs | Item | Open | MEXP | BETAK00E2301 | Maintenance Framework | 2094420 | Roth, Aaron | West | 6. Operational | Drawdown | Tanks | 55000 |  |  | 55000 | 45000 | 10000 | Red |  |  |  | 55000 |  |  | 50000 |  |  | 50000 | Full | 50000 | 55000 |  | 55000 | No | Green | 2023-04-01 | 2023-03-31 | 2023-03-31 | 2023-05-26 | 2023-05-26 | [5 empty] | 55000 | 45000 | 45000 | 10000 | Red |  | Engineering or Scope Change | [9 empty] | 5.1 - done. VAR: scope changed from repair to replace, additional mob was required | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | West Shore Terminals | BETAK - BET GRANVILLE |  |  | 55000 |  |  |  |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 46751 |  | Stine, Carlton | JDE Child | Burnt Orange | 2023-03-10
Granville Terminal Accuload III Upgrade Project | Item | Candidate | MCAP |  | Maintenance Framework |  | Grinder, Mark | West | 2. Pending AFE |  | Truck Racks |  | 225000 |  | 225000 | 225000 | 0 | Green | 225000 |  | 225000 | 0 | [9 empty] | 550000 | 550000 | No | Green | 2023-07-01 |  |  |  | 2024-12-31 | [14 empty] | 50000 | 50000 | 50000 | 50000 | 25000 |  |  | 4-27-2023 - Working on submitting the AFE for this but was requested to see if we could add E-85 Blending on Bay 4 for Conoco Phillips, working on getting all of the quotes for this option. 4-3-2023 - Working on a Phase I AFE for Engineering and material purchases in 2023 and installation will be executed in 2024. 3-23-2023 - Waiting to see if this project can get proper funding, this was budgeted for less than half of what the actual EAC costs will be. Budgeted 225K and estimated cost will be approximately 575K. 3-01-2023 - Waiting for scope of work quote from Triad for competitive bidding and Phase I AFE. | 2023-04-27 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | West Shore Terminals | BETAK - BET GRANVILLE |  |  | 0 | 150000 | 75000 |  | 325000 | Younce, Michael |  |  |  | 1 | 41830 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Granville Terminal Deep Well Replacement | Item | Open | MCAP | BETAK00M2208 | Maintenance Framework | 2023405 | Gabriel, Jeff | West | 6. Operational | Drawdown | Cathodic Protection | 2339 |  |  | 2339.34 | 2339 | 0 | Green |  |  |  | 2339 |  |  | 67000 |  |  | 67000 | Full | 67000 | 73176 |  | 73176 | No | Green | 2022-10-01 | 2022-09-23 | 2022-09-23 | 2022-12-15 | 2022-12-31 |  |  | 2238.6 | 100.74 | [17 empty] | 1/3/2023- Work complete need to accrue 55,644 12/2/2022- work is Scheduled for 12/6 11/1/2022 - PO will be issued this week NIS is completing the wort. 10/1/2022- Material ordered NIS will be completing the work | 2023-01-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | West Shore Terminals | BETAK - BET GRANVILLE |  | 2339 | 0 |  |  | 70836 |  | Geib, Rob | Geib, Robert |  |  | 1 | 45878 |  | Gardner, Travis | Independent | Aqua | 2022-09-20 | Int - Planned Corr & FI
Granville Terminal Fire Suppression System Monitor | Item | Open | MCAP | BETAK00M2202 | Exempt | 1956937 | Stalbaum, Cameron | West | 3. Active | Defined | Fire Protection | 528 |  |  | 528.01 | 382 | 146 | Red |  |  |  | 528 |  |  | 25000 |  | 4379 | 29379 | Full | 29379 | 30685 |  | 30685 | No | Green | 2022-06-01 | 2022-03-24 | 2022-03-24 | 2022-07-30 | 2023-01-31 |  |  | 96.77 | 141.52 | 143.96 | 145.76 |  |  | 146 | Red | [11 empty] | 5/1/23 - Trying to schedule an onsite meeting with Vanguard to walk down the install. The project manage for vanguard just left the company, so trying to get the replacement up to speed and figure out what they need to do in order to finish the installation. 4/3/23 - Vanguard has the panel completed and has scheduled the install for late April. Follow up meeting scheduled for 4/6. 1/3/23 - Holding Accrual for Vanguard. Spoke with Josh Ritter, they are going to bill this work out for 2022 however the install will happen in January due to the city of Milwaukee holding the permit. 12/1/22 - Milwaukee City Fire Engineer permit issuer has indicated that all permits are put on hold until after the first of the year. Vanguard has built the panel and everything is waiting to be hooked up once the city issues the permit. We will hold the accrual for the installation portion of the work which is expected to be pushed through after the first of the year. 11/1/22 - Still waiting on the City inspection. Vanguard indicated that this was supposed to be on schedule for 11/4. Holding accrual for the final billing of the panel install. 10/3/22 - Waiting on the City to complete inspection so Vanguard can install the panel. Panel is completed just waiting on the installation. 9/5/22 - Still waiting on permit issuance from city of Milwaukee. Additional accrual is for the change order for having the drawings PE stamped for the permit issuance. 8/2/22 - Variance is due to permit issues with the city of Milwaukee. It was not originally anticipated that we would need a permit review to update the fire alarm system. After review with the city they are requiring it. The variance is for the full amount of the material purchase minus the installation cost from Vanguard. 7/5/22 - Vanguard is scheduled to install the new monitor system on 7/19-7/20. MOC is being initiated on 7/5. 6/1/22 - Vanguard has completed partial board upgrades in theirshop. 5/5/22 - Vanguard has new board on order per 5/5 update they anticipate a ship date of mid June due to. 5/2/22 Waiting to hear back on the exact delivery date. 4/4/22 - Vanguard has ordered the new mother board and pending arrival work to be scheduled once material arrives. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | West Shore Terminals | BETAK - BET GRANVILLE |  | 382 | 146 |  |  | 30157 |  | Jakubowski, Gregory | Koranda, Chad E. |  |  | 1 | 41490 |  | Guest, ProSight | Independent | Aqua | 2021-08-18 | Other Programs
Granville Terminal Manifold Delivery Valve Replacement | Item | Open | MCAP | BETAK00M2301 | Exempt | 2074861 | Stalbaum, Cameron | West | 3. Active | Defined | Valves | 98911 | -27290 |  | 71620.91 | 45261 | 26360 | Red |  |  |  | 71621 |  |  | 50197 |  |  | 50197 | Full | 50197 | 98911 | -27290 | 71621 | Yes | Red | 2023-01-01 | 2023-01-10 | 2023-01-10 | 2023-05-15 | 2023-04-28 |  |  | 28468 | 1281.06 | 511.79 | 68650.06 |  |  | 68650 | Red |  | Other | 15000 | -42290 | [7 empty] | 5/1/23 - Variance is due material receipt on wrong project and needs reclassed. Valve was received. Working with operations to set up time to completed the drain up and change out of the valve. This is more than likely going to happen the last week of May. Additionally - This project is not in supplemental. The charges for a seperate project were some how accidentally coded to this project. A negative cost was forecasted in June to account for the reclass that will be submittted for the error 4/3/23 - Valve was received, just needs to be receipted so billing can come through. 3/1/23 - Valves were received, accrual is for this material that hasnt been billed yet. Forecast is for installation of valve, which is scheduled in conjunction with proposed Demarcation work. 2/2/23 - Accrual is for Valve that has been purchased. Install still scheduled for when we perform the demarcation project. 1/24/23 - Pushed the valve install out to April. This will be getting completed during a scheduled outage at Granville. 1/3/23 - This variance is due to the having to resubmit the AFE on the new AFE template since I had costs for this project split between December and January for the install. PMO wanted this resubmitted and I had forgotten about it due to the timing of the Leak Detection testing and then Vacation late in the month. 12/2/22 - Submitted AFE for the purchase of the manifold valve and adapter plate. 1/3/22 | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | West Shore Terminals | BETAK - BET GRANVILLE |  | 30261 | 41360 |  |  |  |  | Oey, Alex | Koranda, Chad E. |  |  | 1 | 46282 |  | Guest, ProSight | Independent | Aqua | 2022-12-01 | Other Programs
Granville Terminal Red Dye System upgrade | Item | Open | MCAP | BETAK00M2302 | Maintenance Framework | 2083822 | Stalbaum, Cameron | West | 3. Active | Defined | Truck Racks | 44193 | 8500 |  | 52693.05 | 52693 | 0 | Green | 35000 | 15787 | 50787 | 1906 |  |  | 50787 |  |  | 50787 | Full | 50787 | 44193 | 8500 | 52693 | No | Green | 2023-02-01 | 2023-02-03 | 2023-02-03 | 2023-07-30 | 2023-07-31 |  |  |  | 42290 | 1903.05 | 0 |  |  | 0 | Green |  |  | 8500 | [8 empty] | 5/1/23 - Material was received. The cost for this project double posted to the Granville Terminal Valve Replacement. This is scheduled for installation with the terminal guys for mid may. 4/3/23 - Still holding accrual for red dye skid. Should be delivered next week. 3/1/223 - Accrual is for red dye materials that were ordered from ASI. Remaining 8500 forecast is for Asset team to install additive system once all final parts are received. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | West Shore Terminals | BETAK - BET GRANVILLE |  | 44193 | 8500 |  |  |  |  | Younce, Michael | Koranda, Chad E. |  |  | 1 | 44487 |  | Guest, ProSight | Independent | Aqua | 2022-08-09 | Other Programs
Greensburg Rear Sidewalk | Item | Open | MEXP | BETGM00E2201 | Exempt | 2036130 | Roknich, Hunter | West | 6. Operational | Defined | West | 21 |  |  | 21.15 | 21 | 0 | Green |  |  |  | 21 |  |  | 26000 |  |  | 26000 | Full | 26000 | 23369 |  | 23369 | No | Green | 2022-12-01 | 2022-10-06 | 2022-10-06 | 2022-11-30 | 2022-12-31 |  |  | 21.15 | [18 empty] | 1/4/2023 - Work Complete 12/2/2022 - Project scheduled to begin 12/7/2022 11/2/2022 - Working with JR Hall to get scheduled. 10/11/2022 - JR Hall quote for $21.5k. Scope to be reviewed by management. Work to begin early November. 8/2/2022 - Bid walk being held 8/9 | 2023-01-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Duncansville | BETGM - BET GREENSBURG |  | 21 | 0 |  |  | 23348 |  | Gardner, Travis | Roberts, Shawn C. |  |  | 1 | 41676 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Greensburg Terminal Ethanol Offload Pump Replacement | Item | Open | MCAP | BETGM00M2301 | Maintenance Framework | 2095658 | Henfling, Mike | West | 3. Active | Defined | Rotating Equipment | 12445 | 78000 |  | 90445 | 90000 | 445 | Yellow | 90000 |  | 90000 | 445 |  |  | 68007 |  |  | 68007 | Phase | 68007 | 12445 | 78000 | 90445 | No | Green | 2023-03-01 | 2023-03-21 | 2023-03-21 | 2023-10-01 | 2023-08-31 |  |  |  |  | 8000 | 4445 | 5000 | 5000 | -555 | Red |  |  | 6000 | 5000 | 25000 | 5000 | 33000 | 4000 |  |  |  | 5-2-23 - Engineering in progress, to be complete mid-May. Design review early June, bidding late June. Install in August/September. 4-4-23 - Final pump quotes reviewed with Nate Frey, new pump is on order from Furey for July delivery. Engineering site visit held 3/30. IFR drawings to be complete by end of April. Design review planned for May, bidding in May/June. Install in August/September. 3-2-23 - one pump quote received, waiting on a second quote. Will then select and order pump in March for likely June delivery. Once pump selected, will visit site for engineering survey. AFE to be submitted in early March utilizing first pump quote. 2-2-23 - Discussed project with Ops and Nate Frey. Working with DXP to specify pump (Roto-Prime vs. self-priming ANSI). Hope to purchase pump in February/March. Engineering visit in late February or early March pending pump decision. AFE in March once pump decided. 1-3-23 - will need to purchase long-lead Gorman-Rupp pump. Engineering visit possibly in February | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Duncansville | BETGM - BET GREENSBURG |  | 8000 | 15445 | 63000 | 4000 |  |  | Posipanko, Dan | Gardner, Travis W. |  |  | 1 | 45899 |  | Clark, David | Independent | Aqua | 2022-09-22 | Other Programs
Griffith Delivery Propane Strainer Replacement | Item | Open | MCAP | XF00000M2203 | Maintenance Framework | 2046296 | Parker, Brian | West | 7. Closed | Emergent | West | 10549 |  |  | 10548.61 | 10133 | 416 | Yellow |  |  |  | 10549 |  |  | 41000 |  |  | 41000 | Full | 41000 | 29302 |  | 29302 | No | Green | 2022-12-01 | 2022-11-29 | 2022-11-29 | 2023-02-28 | 2023-03-16 |  |  | 799.21 | 89.74 | 9243.69 | 415.97 |  |  | 416 | Red | [11 empty] | 5/6/23 - project ready to be closed in JDE by accounting. 4/1/23 - var is due to local ops getting this installed earlier than expected. Job Book documents are complete. WO and PO closed - ready to close in JDE. Sent email to archive this project. 3/16/23 - new strainer was installed on Mar 16th. Need to request hydrotest number and complete hydrotest documents. 3/1/23 - no change to status - leaving FCST in Apr for the installation. 2/3/23 - after discussion with John Rangel, looks like we can only complete this change out when the ambient temp is in the 40's, so leaving the FCST for Apr right now for the install. 1/2/23 - should have new strainer installed in Jan once local ops has this scheduled but leaving FCST in Feb for now until everybody is back from the holidays. 11/30/22 - waiting for a reply back from local ops to see if they work the install into their schedule for Dec 2022. 11/21/22 - submitted AFE to workflow for approval routing. | 2023-05-06 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | XF - GRIFFITH STATION |  | 10133 | 416 |  |  | 18753 |  | Gardner, Travis | Baldwin, T. Andy |  |  | 1 | 44403 |  | Guest, ProSight | Independent | Aqua | 2022-08-03 | Other Programs
Griffith Propane Delivery Control Valve & Actuator Replacement | Item | Open | MCAP | XF00000M2301 | Maintenance Framework | 2112027 | Parker, Brian | West | 3. Active | Drawdown | Valves | 55282 | 25000 |  | 80281.93 |  | 80282 | Red |  | 102887 | 102887 | -22605 |  |  | 102887 |  |  | 102887 | Full | 102887 | 55282 | 25000 | 80282 | No | Green | 2023-04-01 | 2023-04-21 | 2023-04-21 | 2023-06-30 | 2023-06-30 | [5 empty] | 55281.93 |  |  | 55282 | Red |  | WorkAhead of Schedule | 12500 | 12500 | [7 empty] | 4/29/23 - valve and actuator issued from inventory - Pioneer Industrial is working on getting valve and actuator mated together then local ops will install - Vander Werf will complete the electrical for the new control box. All work should be completed in Apr. EAC is at 80,150. 4/25/23 - AFE approved on 4/21 and req's created on 4/24 for Vander Werf and Pioneer Industrial. Valve in process of getting transported from ZI to EH today. Getting inventory items issued to project in Apr and should have this installed sometime in May. 4/17/23 - created project in OPPM and routing AFE for approval. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | XF - GRIFFITH STATION |  |  | 80282 |  |  |  |  | Oey, Alex | Gardner, Travis W. |  |  | 1 | 46951 |  | Guest, ProSight | Independent | Aqua | 2023-04-17
Hammond 160L VFD 10 year PM | Item | Open | MEXP | BETEH00E2304 | Exempt | 2094276 | Grinder, Mark | West | 3. Active | Defined | Electrical | 14317 | 20000 |  | 34316.51 | 35000 | -683 | Yellow | 35000 |  | 35000 | -683 |  |  | 32076 |  |  | 32076 | Full | 32076 | 14317 | 20000 | 34317 | No | Green | 2023-04-01 | 2023-03-08 | 2023-03-08 | 2023-07-31 | 2023-07-31 | [5 empty] | 14316.51 |  |  | 14317 | Red |  | WorkAhead of Schedule |  |  | 20000 | [6 empty] | 4-27-2023 - This has been scheduled with Rockwell for completion in July. 3-23-2023 - AFE approved and PO was sent, will get this scheduled with Rockwell for completion in July. 2-28-2023 - Project AFE in the approval workflow. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  |  | 14317 | 20000 |  |  |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 45458 |  | Clark, David | Independent | Aqua | 2022-08-26 | Other Programs
Hammond Electrical Infrastructure Upgrade Engineering Study | Item | Open | MEXP | BETEH00E2303 | Exempt | 2084405 | Grinder, Mark | West | 3. Active | Defined | Electrical |  | 14500 |  | 14500 | 14500 | 0 | Green | 30000 |  | 30000 | -15500 |  |  | 14410 |  |  | 14410 | Full | 14410 |  | 14500 | 14500 | No | Green | 2023-05-01 | 2023-02-02 | 2023-02-02 | 2023-04-01 | 2023-05-31 | [12 empty] | 14500 | [8 empty] | 4-27-2023 - This was not completed early but will be completed in May.as forecast. 3-23-2023 - This should be completed in Mid April. 3-01-2023 - The PO was submitted and should be completed a little early. 2-02-2023 - The AFE for this project in in the approval process, PO's will be written once budgets are loaded. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  |  | 14500 |  |  |  |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 45110 |  | Guest, ProSight | Independent | Aqua | 2022-08-19 | Other Programs
Hammond HMI Upgrade | Item | Open | MCAP | BETEH00M2205 | Exempt | 1989959 | Fink, Ryan | West | 6. Operational | Defined | Instrumentation & Controls | 2570 | 2713 |  | 5283.19 | 5570 | -287 | Yellow |  |  |  | 5283 |  |  | 70000 |  | 9000 | 70000 | Supplemental | 79000 | 76389 | 2713 | 79102 | No | Green | 2022-06-01 | 2022-06-09 | 2022-06-09 | 2022-07-22 | 2022-12-31 |  |  | 1312.06 | 1048.05 | 210.08 | [9 empty] | 2713 | [6 empty] | 5/2 RRF - Spare HMI to arrive in July, EAC$79k 4/6 RRF - Supplemental submitted, PC ordered, EAC$79k 3/31 RRF - no PC yet.. EAC $79k 3/2 RRF - HMI to be upgraded, and keep current as spare. PC to ship in March. EAC $79k 2/1 RRF - pause on spare HMI, hardware only march. update with lead time after order 1/4/23 RRF - operational, spare HMI Jan. 12/1 RRF - install week of 12/5, 3k in Jan for spare hardware. 11/1 RRF - licenses rec'd, install nov/dec 10/3 RRF - Coupled with PLC upgrade, on track for Nov 8/31 RRF - PCs arrived, setup in progress. November checkout 8/2 RRF - material delayed to Aug, need to verify shipping 7/11 RRF - on track 6/1 RRF - Material from PLC project delayed to August, Install moved to September 5/31/2022 RRF - project moved to I&C program, AFE submitted at $70k -3/8/22: This project is cancelled because operations (under Ryan Fink) has a project in place to handle this upgrade.. These funds will be repurposed to cover SD activities. LK | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  | 2570 | 0 | 2713 |  | 73819 |  | Forsey, Frank | Gardner, Travis W. |  |  | 1 | 37880 |  | Guest, ProSight | Independent | Aqua | 2020-08-13 | IT
Hammond PLC Migration | Item | Open | MCAP | EH00000M2201 | Maintenance Framework | 1956017 | Fink, Ryan | West | 6. Operational | Defined | Instrumentation & Controls | 19989 | 18000 |  | 37989.04 | 37406 | 584 | Yellow |  |  |  | 37989 |  |  | 206000 |  | 34000 | 206000 | Supplemental | 240000 | 223217 | 18000 | 241217 | No | Green | 2022-04-01 | 2022-03-14 | 2022-03-14 | 2022-07-22 | 2022-12-31 |  |  | 3040.61 | 6760.21 | 6604.7 | 3583.52 | 7000 | 7000 | -3416 | Red |  | Contractor/Vendor Issue | 4000 | 11000 | 3000 | [6 empty] | 5/2 RRF - Asbuilts and cleanup in progress, EAC $241k 4/6 RRF - Supplemental submitted, EAC $241k 3/31 RRF - IT equipment from closed Fiber project has just arrived. charged to this project, EAC $241k 3/30 RRF - EAC $238k 3/8 RRF - EAC $238 Submit supplemental 3/1 RRF - dwgs, and closeout EAC $231k 2/1 RRF - Rockwell dwgs open for feb/mar then close 1/4/23 RRF - operational, punch list remains. $25k open on rockwell for feb, . 12/8 RRF - checkout in progress, removed contingency from Dec forecast. 12/1 RRF - Cutover week of 12/5 11/1 RRF - Install moved to Nov/Dec for downtime 10/4 RRF - Accrue 26931 to Rockwell, install in progress. Nov checkout 9/1 RRF - Accrual was an ERROR, -40712.52 July Accrual should have been 9200. Aug Accrual 6609 for Rockwell 8/2 RRF - install prep continues, small slip. Accrue 9200 to Rockwell 7/5 RRF - install prep in progress 6/9 RRF - update from status meeting. Material and eng to be billed in August. Added O/S labor 6/2 RRF - Material delivery delayed to August, Install moved to September. 5/31 RRF - material may not have arrived in May 5/3 RRF - on track 4/11 RRF - Material ordered 3/7 RRF - updated with quotes 3/1/2022 RRF - updated pre AFE; Budget 107 | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | EH - HAMMOND TERM ( WOOD RIVER) |  | 16406 | 18584 | 3000 |  | 203228 |  | Forsey, Frank | Spitz, Nicholas P. |  |  | 1 | 38099 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
Hammond Rail Cameras Installation | Item | Open | MCAP | BETEZ00M2201 | Maintenance Framework | 2011274 | Grinder, Mark | West | 3. Active | Defined | Security & Cameras | 24927 |  |  | 24926.94 | 23338 | 1589 | Yellow |  |  |  | 24927 |  |  | 106000 |  |  | 106000 | Full | 106000 | 116474 |  | 116474 | No | Green | 2022-08-01 | 2022-08-03 | 2022-08-03 | 2022-12-31 | 2023-06-30 |  |  | 616.98 | -2199.12 | 24920.32 | 1588.76 |  |  | 1589 | Red | [11 empty] | 4-27-2023 - Still waiting on network switches to complete around June unless material shows up sooner. 3-23-2023 - Still waiting on network switches to complete around June unless material shows up sooner. 3-01-2023 - We are still waiting for network switches to complete. 1-31-2023 - This project is waiting for Network Switches to be delivered in June for completion. 12-29-2022 - This project has encountered a delay on the Rail cameras due to unmanaged switches, we have new switches on order but have not been notified on the delivery date yet, we are having Convergent program all of these cameras so we can have everything installed and ready to put online. 11-28-2022 - This project has encountered a delay on the Rail cameras due to unmanaged switches, we have new switches on order but have not been notified on the delivery date yet, we are having Convergent program all of these cameras so we can have everything installed and ready to put online. 11-01-2022 - We are in need of a network switch and supposed to have it by the end of the month and checkout should be in December. 9-26-2022 - All material received, Electrical contractor is working on conduit and wiring. 8-29-2022 - Some camera material in stock and remaining material on order, scheduled to arrive in mid-September starting the electrical work in September and commissioning in October. 7-27-2022 - AFE sent for approval because extra funding needed to complete project and waiting for approval before submitting into the workflow. 6-29-2022 - Scheduling a meeting with IT, discussion is about unmanaged network switches are worst at this site than any other Buckeye site. 6-21-2-22 - Moved the July forecast to August, waiting on final quotes before submitting AFE and waiting on our IT group to verify the existing Network can support the extra traffic. 5-31-2022 - We are performing project scope and walkthrough tomorrow at Hammond and AFE will be submitted once quotes are received. 5-02-2022 - Scheduling a project walkthrough/SOW this month. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEZ - BUCKEYE HAMMOND RAILROAD LLC |  | 23338 | 1589 |  |  | 91547 |  | Clark, Chris | Clark, Chris B | N/A |  | 1 | 29543 |  | Hamilton, Richard | Independent | Aqua | 2018-06-14 | Other Programs
Hammond Terminal (BETEH) -Site survey to validate SPCC plan calculations and review. | Item | Open | MEXP | BETEH00E2203 | Exempt | 1955402 | Roth, Aaron | West | 6. Operational | Defined | Secondary Containment | -3 |  |  | -2.5 | -923 | 920 | Red |  |  |  | -3 |  |  | 25000 |  | 19315 | 52790 | Supplemental | 52790 | 49448 |  | 49448 | No | Green | 2022-04-01 | 2022-03-07 | 2022-03-07 | 2022-08-01 | 2023-01-31 |  |  | -47.5 | -1795 | 920 | 920 |  |  | 920 | Red | [11 empty] | 3.1 - survey done, items identified for repair on separate project | 2023-02-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  | -923 | 920 |  |  | 49451 |  | Spari, Markella | Spari, Markella |  |  | 1 | 41558 |  | Administrator, System | Independent | Aqua | 2021-08-19 | Other Programs
Hammond Terminal (BETEH) Tank 8F Dike Drainage Improvements | Item | Open | MCAP | BETEH00M2202 | Maintenance Framework | 1970659 | Parker, Brian | West | 3. Active | Defined | Secondary Containment | 1030 | 100000 |  | 101030.2 | 100927 | 103 | Yellow | 100000 |  | 100000 | 1030 |  |  | 24000 |  |  | 24000 | Phase | 24000 | 21746 | 100000 | 121746 | No | Green | 2022-06-01 | 2022-04-08 | 2022-04-08 | 2022-10-31 | 2023-07-31 |  |  | 260.63 | 87.81 | 578.44 | 103.32 |  |  | 103 | Red |  |  |  |  | 40000 | 60000 | [5 empty] | 5/1/23 - need to schedule one more review with local ops this week and then get a Coupa bid event created after IFC's are created. 4/1/23 - processed last invoice from Diamond Z. Have all bidder details now (who wants to bid on what) and will get a Coupa bid event entered in Apr for this project. 2/28/23 - Re-accruing 2,105 for Diamond Z. Sent emails out to 10 contractors to see which locations they want to bid on for dike work in 2023. I've received 6 responses back to date. Should have bid event created in Coupa in Mar for this project. 2/28/23 - just waiting on IFC drawing package from Diamond Z. 1/31/23 - re-accruing 2,105 for Diamond Z and waiting on updated drawing. 1/5/23 - no change in status - waiting on updated dwg from Diamond Z then go out for bid. Accruing 3,600 for Diamond Z. 11/30/22 - had a call with management and local ops on Nov 18th to review drawing. Looking to install an overflow culvert from the containment pond to the North of the property but need to obtain product pipe depth first. Local ops and Diamond Z have the elevations and are looking to see if this is a viable option. 10/31/22 - no change in status - waiting on quotes from contractors for this 2023 construction project. 9/29/22 - emailed dwg's to Feken, Helmkamp, and Mills - Feken declined, just waiting on replies back from the other two contractors. Re-accruing 10,000 for Diamond Z. 9/8/22 - moving this FCST out to 2023 - not 100% sure contractors are available for this work for the remainder of 2022. 9/1/22 - just received DWG package on 8/31 from Diamond Z - reviewing the details and the SOW - will be re-accruing 14,636.50 for Aug, expect partial invoice in early Sep. Provided comments on proposal layout and expect IFR dwg's sometime in Sep. New pump/motor has 15 week lead time so putting this FCST in Feb 2023 plus cost to install/commission. Remaining FCST for Q4 is a best guess right now until I can obtain some quotes. 7/30/22 - re-accruing 14,635.50 for Diamond Z - they need more time to resolve the design issues at Hammond so issuance of IFR has moved to Aug. 7/2/22 - accruing 7,958 for Diamond Z and should have IFR drawing package by end of Jul. 6/1/22 - site has been scanned just waiting on IFR drawing set to be issued. Drawing should be complete in Jun butsplitting FCST between Jun/Jul due to uncertainty. 5/3/22 - issued PO to Diamond Z to develop IFR and IRC drawing set to address drainage issues around this tank. 4/5/22 - submitted Phase I AFE for approval routing. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  | 927 | 103 | 100000 |  | 20716 |  | Clark, Dave | Spari, Markella |  |  | 1 | 40757 |  | Guest, ProSight | Independent | Aqua | 2021-07-27 | Other Programs
Hammond Transmix Pipe Mods | Item | Open | MCAP | BETEH00M2206 | Maintenance Framework | 2002624 | Roth, Aaron | West | 3. Active | Drawdown | Tank Outage | 972 | 100000 |  | 100971.84 | 175158 | -74186 | Red | 175000 |  | 175000 | -74028 |  |  | 11000 | 107671 |  | 11000 | Phase | 118671 | 12208 | 100000 | 112208 | No | Green | 2022-08-01 | 2022-07-11 | 2022-07-11 | 2022-09-01 | 2023-05-31 |  |  | 51.83 | 52.77 | 53.71 | 813.53 |  |  | 814 | Red |  |  | 100000 | [8 empty] | 5.1 - install piping to tank 55 week of 5/15. clean and idle both tanks 91/92 week of 5/22. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETEH - BET HAMMOND TERMINAL |  | 158 | 100814 |  |  | 11236 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44069 |  | Guest, ProSight | Independent | Aqua | 2022-07-05 | Int - Tanks
Harper Station - Pump Motor Upgrade | Item | Open | MCAP | HH00000M2201 | Maintenance Framework | 2043604 | Scott, Cory | West | 6. Operational | Drawdown | Rotating Equipment | 11964 |  |  | 11964.14 | 11964 | 0 | Green |  |  |  | 11964 |  |  | 34000 |  |  | 34000 | Phase | 34000 | 32128 |  | 32128 | No | Green | 2022-12-01 | 2022-11-01 | 2022-11-01 | 2022-12-30 | 2023-01-31 |  |  | 11524.87 | 439.27 | [17 empty] | 2/20/2023 - Final project completed for $31,689.00. 2/15/2023 - Final invoice approved for Illinois electric. 2/2/2023 - Invoice recieved from Illinois Electric. Project totals at 31k. 1/18/2023 - Pump motor #2 reinstalled. Project completed. Awaiting final billing. 1/5/2023 - Reinstallation planned to take place on 1/18/2023. 12/27/2022 - Contractor plans to have motor repaired and reinstalled the second week of January. 12/14/2022 - Received vendor inspection results. An additional $3,600.00 is needed to finish the repair. Change order being completed and sent in to adjust the PO. 12/8/2022 - Contractor removed pump motor an took to shop for repair. 12/7/2022 - Contractor unable to remove pump motor till 12/8/2022. They might be able to complete before year end. If not, it should be installed first part of January. 11/18/2022 - Pump to be removed early december and reinstalled late december, early january. 11/2/2022 - PO to be placed for Illinois Electric for 25K. Stakeholder meeting planned to be held on 11/17/2022. | 2023-02-20 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | HH - HARPER STATION |  | 11964 | 0 |  |  | 20164 |  | Posipanko, Dan | Gardner, Travis W. |  |  | 1 | 46120 |  | Gardner, Travis | Independent | Aqua | 2022-10-26 | Other Programs
Harper Station Headgate Valve Replacement | Item | Open | MCAP | HH760OTM2202 | Maintenance Framework | 2011198 | Scott, Cory | West | 7. Closed | Defined | Valves | 189 |  |  | 189.06 | 189 | 0 | Green |  |  |  | 189 |  |  | 13000 | 19000 |  | 32000 | Full | 32000 | 31495 |  | 31495 | No | Green | 2022-09-01 | 2022-08-02 | 2022-08-02 | 2022-09-17 | 2022-10-15 |  |  | 189.06 | [18 empty] | 12/27/2022 - Project closeout. 12/16/2022 - WOM sent valve invoice. Project completed at $31,862.00 10/5/2022 - Prairie Industrial invoiced 17K. Valve invoice should arrive in mid november. 9/30/2022 - Project completed. 9/22/2022 - Project installation planned for end of month. 9/6/2022 - Stakeholders meeting taking place. 8/23/2022 - Full AFE submitted for project. 8/19/2022 - Prairie Industrial sent me an estimate for $13,200.00 8/2/2022 - PO placed for this valve for 11K. 7/22/2022 - Phase 1 AFE submitted to order ball valve. Due to a long lead time the current ball valve in stock at the Sugar Creek will be used and reclassed to the project. The other valve that is being order will be placed back into the warehouse under operations. 7/21/2022 - Forecasted into 2023 between February and March. 6/27/2022 - Still not sure if we are going to spend this or not. 6/3/2022 - Planned purge work taking place in August/September. Valve will be replaced during this purge. 4/14/2022 - Planned inventory form to be submitted to order valve to put in stock. Quote request from Worldwide Oilfield Machine valve co. 2/2/2022 - Awaiting corporate project for finalized purge dates. | 2022-12-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | HH760OT - HARPER STA TO OTTUMWA STA |  | 189 | 0 |  |  | 31306 |  | Oey, Alex | Smith, Todd W. |  |  | 1 | 41875 |  | Guest, ProSight | Independent | Aqua | 2021-08-21 | Other Programs
Harper Station Roof Painting | Item | Open | MEXP | HH00000E2301 | Exempt |  | Scott, Cory | West | 5. Deferred | Defined | West |  |  |  | 0 |  | 0 | Green | 26000 |  | 26000 | -26000 |  |  | 21725 |  |  |  | Full | 21725 |  | 26000 | 26000 | No | Green | 2024-05-01 |  |  | 2023-05-04 | 2024-05-31 | [21 empty] | 3/27/2023 - Project deferred until 2024 or later in 2023 per Mike Ricke and Travis Gardner. 3/20/2023 - Built AFE and submitted to remedyforce along with the estimate from Allen Blasting and Coating. Adjusted original forecast from 26K to 22K. 3/16/2023 - Recieved quote from Allen Blasting and Coating for 20K. 3/8/2023 - Site visit made with contractor. Awaiting quote next week. I told them to additional pricing for second smaller building. Should keep cost down from having to go back in the future. Bumped forecast to May due to being able to do it earlier than originally forecasted. | 2023-03-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Eastern Iowa | HH - HARPER STATION |  |  | 0 |  |  |  | 26000 | Gardner, Travis | Smith, Todd W. |  |  | 1 | 37666 |  | Guest, ProSight | Independent | Aqua | 2020-08-11 | Other Programs
Harper Station Sump Replacement | Item | Open | MCAP | HH00000M2202 | Maintenance Framework | 2052891 | Scott, Cory | West | 3. Active |  | West | 10443 | 3800 |  | 14242.65 | 13969 | 274 | Yellow |  |  |  | 14243 |  |  | 19000 |  |  | 19000 | Phase | 19000 | 15693 | 3800 | 19493 | No | Green | 2022-12-01 | 2022-12-19 | 2022-12-19 | 2023-09-30 | 2023-09-29 |  |  | 199.5 | 4875 | 5094.38 | 273.77 |  |  | 274 | Red |  |  |  |  | 3800 | [6 empty] | 5/2/2023 - Awaiting IFB set. IFR has been approved by Todd and myself to move forward with design. Drawings will be sent to senior leadership was made. 4/18/2023 - Awaiting drawings from TAS. 3/31/2023 - TAS working on design for sump pump project. 2/3/23 - TAS is working on design for new double-walled sump. This is an unplanned and emergent project that will probably have to be funded from MCAP drawdown. 1/2/23 - processed 1st invoice for TAS in Dec. Have an on-site mtg scheduled for the 19th. 12/8/22 - routing Phase I AFE for approval for Eng & Des. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | HH - HARPER STATION |  | 10169 | 274 | 3800 |  | 5250 |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 46329 |  | Guest, ProSight | Independent | Aqua | 2022-12-08 | Other Programs
Harristown (BETHT) Butane Pump #1 seal | Item | Open | MCAP | BETHT00M2205 | Exempt | 2052426 | Gardner, Travis | West | 8. Canceled | Emergent | Rotating Equipment |  |  |  | 0 |  | 0 | Green | [6 empty] | 9000 |  |  | 9000 | Full | 9000 |  |  |  | No | Green |  | 2022-12-20 | 2022-12-20 | 2022-12-31 | 2022-12-23 | [21 empty] | 2/2/2023 - Project is canceled seals are no longer leaking. 1/4/2023 - emergent project in December that was for a leaking butane pump seal. Seal stopped leaking and forecast moved to January if seal starts leaking again. | 2023-02-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Central-Illinois | BETHT - BET HARRISTOWN TERMINAL |  |  | 0 |  |  |  |  | Posipanko, Dan | Skelly, Mark L. |  |  | 1 | 46381 |  | Gardner, Travis | Independent | Aqua | 2022-12-15 | Other Programs
Harristown (BETHT) Mainline butane pump power | Item | Open | MCAP | BETHT00M2204 | Exempt | 2021593 | Gardner, Travis | West | 6. Operational | Emergent | Electrical | 1805 |  |  | 1805.16 | 1805 | 0 | Green |  |  |  | 1805 |  |  | 55000 |  |  | 55000 | Full | 55000 | 46317 |  | 46317 | No | Green | 2022-12-01 | 2022-12-20 | 2022-12-20 | 2022-12-31 | 2023-02-22 |  |  | 1805.16 | 0 | 0 | [16 empty] | 3/1/2023 - remaining work was completed. 1/4/2023 - variance is forecast was locked. emergent AFE created in December. | 2023-03-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Central-Illinois | BETHT - BET HARRISTOWN TERMINAL |  | 1805 | 0 |  |  | 44511 |  | Ashley, Robert |  |  |  | 1 | 46372 |  | Gardner, Travis | Independent | Aqua | 2022-12-15 | Other Programs
Harristown API Strainer Installation | Item | Open | MCAP | HT00000M2201 | Maintenance Framework | 2046271 | Parker, Brian | West | 7. Closed | Emergent | West | 18913 |  |  | 18913.43 | 18914 | 0 | Yellow | 73000 |  | 73000 | -54087 |  |  | 67000 |  |  | 67000 | Full | 67000 | 71722 |  | 71722 | No | Green | 2022-12-01 | 2022-11-29 | 2022-11-29 | 2023-02-28 | 2022-12-21 |  |  | 7089.75 | 4361.39 | 757.53 | 6704.76 | 6705 | 6705 | 0 | Yellow | [11 empty] | 5/6/23 - have one more charge to update P&ID's by TAS since Drafting does not have the bandwidth. Should be completed very soon. Ready to be closed in JDE by accounting. 5/1/23 - P-Card charge should post to this project for Apr business. I will move it out to May if it has not posted after accruals have been updated in OPPM. Local ops installed the access platform in Apr. Project ready to be closed once P-Card charge has posted. 3/31/23 - processed Consolidated inv in Mar. Will have a charge of 6,704.76 on P-Card from Motion Industries for new access platform that was drop shipped at terminal on 3/31. 2/28/23 - re-accruing 14,440 for Consolidated and sent Tony an email about the invoice. Also sent another email to SafeRack about the platform quote. Actuals in OPPM are not correct. 1/31/23 - re-accruing 14,440 for Consilidated. Moving Erectastep platform costs out to May. 1/2/23 - accruing 14,400 for Consolidated and remaining FCST in Mar is for purchase and installation of Erectastep access platform and stairs. 12/22/22 - strainer was installed and operational on Dec 15th. Still need to spec and order new access platform and stairs which should be completed in Q1 2023. 12/12/22 - install of strainer scheduled for 12/15 and should only take 1 day. Entered Req for Consolidated to install. Need to obtain quote from Erectastep or another vendor for access platform. 11/29/22 - should have quote soon for installation of this strainer plus all concrete work to get started on this one. The platform and access stairs will be installed in 2023 due to lead time. 11/21/22 - submitted AFE to workflow for approval routing. | 2023-05-06 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Central-Illinois | HT - HARRISTOWN TERMINAL |  | 12209 | 6705 |  |  | 52809 |  | Gardner, Travis | Hoekstra, Matt |  |  | 1 | 44393 |  | Guest, ProSight | Independent | Aqua | 2022-08-03 | Other Programs
Harristown Terminal Sulfur Analyzer Replacement | Item | Open | MCAP | BETHT00M2203 | Maintenance Framework | 2045791 | Parker, Brian | West | 7. Closed | Drawdown | Measurement & Quality Control | 109 |  |  | 109.17 | 109 | 0 | Green |  |  |  | 109 |  |  | 89000 |  |  | 89000 | Full | 89000 | 78577 |  | 78577 | No | Green | 2022-11-01 | 2022-11-23 | 2022-11-23 | 2022-12-31 | 2022-11-29 |  |  | 109.17 | [18 empty] | 1/9/23 - last charge of 2,872.61 in Dec is for CWIP. 12/14/22 - PO and WO closed - ready to be closed by accounting. 12/7/22 - var is due to receiving the new Sindie unit on Nov 29th instead of in Dec as originally estimated by vendor. 11/29/22 - AFE is approved - sent email to supply chain to change account coding of the PO to this project. Sindie unit was received at the terminal on Nov 29th. 11/18/22 - AFE is out for approval - will re-code the local opex PO to this project once AFE has been approved. | 2023-01-09 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Central-Illinois | BETHT - BET HARRISTOWN TERMINAL |  | 109 | 0 |  |  | 78468 |  | Hopkins, Christa | Hoekstra, Matt |  |  | 1 | 46238 |  | Guest, ProSight | Independent | Aqua | 2022-11-17 | Other Programs
Hartsdale 480V Office Electrical Gear Removal | Item | Open | MCAP | HD00000M2304 | Maintenance Framework | 2096278 | Grinder, Mark | West | 3. Active | Defined | Electrical |  | 35000 |  | 35000 | 35000 | 0 | Green | 35000 | 16586 | 51586 | -16586 |  |  | 51586 |  |  | 51586 | Full | 51586 |  | 35000 | 35000 | No | Green | 2023-05-01 | 2023-03-23 | 2023-03-23 | 2023-08-31 | 2023-08-31 | [12 empty] | 5000 | 10000 | 15000 | 5000 | [5 empty] | 4-27-2023 - PO sent out and waiting for materials. 3-23-2023 - The AFE is now in the approval phase. 3-01-2023 - Working on an AFE for this, I just received the final quote yesterday. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | HD - HARTSDALE |  |  | 15000 | 20000 |  |  |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 41494 |  | Guest, ProSight | Independent | Aqua | 2021-08-18 | Other Programs
Hartsdale Butane Electrical Distribution Panelboard Replacement | Item | Open | MCAP | HD00000M2303 | Maintenance Framework | 2096289 | Parker, Brian | West | 3. Active | Drawdown | Electrical |  | 32000 |  | 32000 | 32000 | 0 | Green |  | 41966 | 41966 | -9966 |  |  | 41966 |  |  | 41966 | Full | 41966 |  | 32000 | 32000 | No | Green | 2023-07-01 | 2023-03-23 | 2023-03-23 | 2023-06-30 | 2023-07-31 | [14 empty] | 32000 | [6 empty] | 5/1/23 - no change in status - material to ship in early July. 4/7/23 - EAC is now at 32,000. 3/30/23 - PO's issued to Meade and Graybar. Material lead time for panelboard is 12-14 weeks so looking at sometime around July 6th for shipment from Graybar. 3/18/23 - created project in OPPM and routing full AFE for approval for this emergent project. Project will be funded from West Region Drawdown per Travis Gardner. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | HD - HARTSDALE |  |  | 0 | 32000 |  |  |  | Ashley, Robert | Aiken, Elaine |  |  | 1 | 46808 |  | Parker, Brian | Independent | Aqua | 2023-03-18
Hartsdale Butane Offload Driver Kiosk | Item | Open | MCAP | HD00000M2302 | Maintenance Framework | 2094149 | Parker, Brian | West | 3. Active | Defined | Truck Racks | 12386 | 25000 |  | 37385.63 | 38000 | -614 | Yellow | 30000 | 43140 | 73140 | -35754 |  |  | 73140 |  |  | 73140 | Full | 73140 | 12386 | 25000 | 37386 | No | Green | 2023-04-01 | 2023-03-24 | 2023-03-24 | 2023-06-30 | 2023-08-31 | [5 empty] | 12385.63 | 12000 | 12000 | 386 | Yellow |  |  |  | 11000 | 11000 | 3000 | [5 empty] | 4/30/23 - new pad was set in Apr. New electrical panel will ship on 6/22/23 so would expect electrical work to be completed in Jul. Kiosk should ship on 5/26/23 but FCST'ing this for Jun. Aug FCST is for as-builts. EAC is at 37,356. 4/7/23 - issued PO to Mills Excavating. Should be all set and just approved kiosk dwg. Don't expect Meade to complete any work until after the new distribution panelboard and transformer have been installed - sometime in Jul. Est. ship date of kiosk is May 26th. Rodney plans to get new pad installed week of Apr 10th. EAC is at 38,000. 3/28/23 - PO's issued to Porta-King and Meade. Waiting on revised quote from Mills. Don't expect delivery of kiosk until July timeframe. EAC is 48,000 3/17/23 - submitted Full AFE to workflow for approval routing. Entered Req's for Porta-King, Meade, and Mills Excavating. Kiosk has 3-4 month lead time. 3/1/23 - requested an Interim AFE on Feb 24th so I can get long lead items ordered ASAP. Will submit the full AFE sometime in Mar, adjusted the EAC to what I expect to spend for this project. 2/4/23 - need to get a drawing created for the new concrete pad for the kiosk. Requested a modification on this quote to reduce the kiosk size to 5' x 4'. Will get with TAS to create a drawing since it looks like we need to move the bollard that has the ESD button. Also need to replace the Class 1, Div 2 rated panelboard with a new panelboard and a new transformer rated for haz locations. Also need to obtain a quote from Meade to all electrical work. FCST is the current estimated EAC until I can obtain some more definitive quotes. Moving the 43,000 budget from the Mt Auburn Install New Trap Door (OPPM ID 34378) to this project to fund budget overages. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | HD - HARTSDALE |  |  | 23386 | 14000 |  |  |  | Younce, Michael | Younce, Michael |  |  | 1 | 45245 |  | Guest, ProSight | Independent | Aqua | 2022-08-24 | Other Programs
Hartsdale Camera System Installation | Item | Open | MCAP | BETHD00M2302 | Maintenance Framework | 2095068 | Grinder, Mark | West | 3. Active | Defined | Security & Cameras | 3435 | 45000 |  | 48435.15 | 45000 | 3435 | Yellow | 45000 |  | 45000 | 3435 |  |  | 4428 |  |  | 4428 | Phase | 4428 | 3435 | 45000 | 48435 | No | Green | 2023-04-01 | 2023-03-15 | 2023-03-15 | 2023-09-30 | 2023-09-30 | [5 empty] | 3435.15 |  |  | 3435 | Red |  |  |  | 10000 | 15000 | 15000 | 5000 |  |  |  |  | 4-27-2023 - PO's are being sent out for approval for approval, will start electrical work as soon as contractor is available. 3-23-2023 - Phae I AFE Approved and Switches ordered, still waiting for camera quotes. 3-01-2023 - Site meeting was held last week and quotes are due in three weeks, submitting a phase 1 AFE for network switch ordering. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | HD - HARTSDALE |  |  | 13435 | 35000 |  |  |  | Clark, Chris | Clark, Chris B | N/A |  | 1 | 31407 |  | Clark, David | Independent | Aqua | 2018-08-29 | Other Programs
Hartsdale Cathodic Protection Upgrade | Item | Open | MCAP | HD00000M2202 | Maintenance Framework | 2013042 | Logan, Rob | West | 6. Operational | Emergent | Cathodic Protection | 1028 |  |  | 1027.58 | 1028 | 0 | Green |  |  |  | 1028 |  |  | 165000 |  | 19000 | 184000 | Supplemental | 184000 | 182562 |  | 182562 | No | Green | 2022-10-01 | 2022-09-01 | 2022-09-01 | 2022-10-31 | 2022-12-31 |  |  | 1027.58 | [18 empty] | 04/03/2023 Awaiting supplemental approval 03/02/2023 Project over budget/ Contingency by $2,398 due do internal labor cost 1/4/2023 - work completed. 12/5/2022 Variance is for local asset team time on project. Rectifier installation scheduled for Thursday 12/8/2022 11/1/2022 - work started early. 90% completed. 9/27/2022 Start date 10/17/2022 9/1/2022 - Waiting on AFE approval. ordering rectifiers to determine start date. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | HD - HARTSDALE |  | 1028 | 0 |  |  | 181535 |  | Geib, Rob | Geib, Robert |  |  | 1 | 45126 |  | Gardner, Travis | Independent | Aqua | 2022-08-22 | Int - Planned Corr & FI
Hartsdale Station Baseline Facility Assessment | Item | Open | MEXP | BETHD00E2202 | Exempt | 1980272 | Parker, Brian | West | 7. Closed | Defined | Facility Integrity | -2622 |  |  | -2622.27 | -2622 | 0 | Green |  |  |  | -2622 |  |  | 36000 |  |  | 36000 | Phase | 36000 | 6982 |  | 6982 | No | Green | 2022-12-01 | 2022-05-11 | 2022-05-11 | 2022-12-31 | 2022-12-30 |  |  | -2622.27 | [18 empty] | 1/31/23 - sent email to LSC to confirm the invoice processed on 1/21 is the final invoice and I can cancel the remaining open PO amount. 1/2/23 - work completed in Dec. Accruing 9,604.60 for Lake Superior Consulting in Dec. 11/30/22 - no change in status, work should be completed in Dec. 11/8/22 - received proposal from program owner and will get req entered into JDE for work - adjusted FCST. 10/31/22 - no change in status - waiting on reply from program owner regarding the SOW and who is completing this work. 9/29/22 - no change in status - waiting on reply from program owner regarding the SOW and who is completing this work. 9/3/22 - no change in status - waiting on reply from program owner regarding the SOW and who is completing this work. 8/1/22 - no change in status from last month. 7/3/22 - no success in obtaining a SOW or estimate from Facility Integrity - last update I had via email was they were looking at utilizing a contract PM that Dave Clark has been using to walk down all marine sites to complete the facility assessments. No word on the outcome of that meeting that was schedule for Jun 1st. Moving this FCST out to Q3 until more details are forthcoming. 5/31/22 - attempting to get details on SOW so we can get a PO issued. 5/12/22 - AFE was just approved on May 11th - will be getting PO issued soon and getting work scheduled. 4/5/22 - Hunter will be submitting this one under one Parent AFE that covers 9 individual API 570 and Facility Integrity projects. 2/8/22 - just waiting on guidance from facility integrity group on the path forward. | 2023-01-31 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | E. Chicago Terminals | BETHD - BET HARTSDALE TERMINAL |  | -2622 | 0 |  |  | 9605 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 41200 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
Hartsdale Station Sulfur Analyzer Replacement - 2022 | Item | Open | MCAP | HD00000M2203 | Exempt | 2052353 | Gardner, Travis | West | 6. Operational | Emergent | Measurement & Quality Control | 2547 |  |  | 2546.99 | 2547 | 0 | Green |  |  |  | 2547 |  |  | 83000 |  |  | 83000 | Full | 83000 | 63047 |  | 63047 | No | Green | 2022-12-01 | 2022-12-19 | 2022-12-19 | 2022-12-31 | 2022-12-30 |  |  | 2437.31 | 109.68 | [17 empty] | 1/4/2023 - material recieved. variance was due to forecast being locked. | 2023-01-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | HD - HARTSDALE |  | 2547 | 0 |  |  | 60500 |  | Hopkins, Christa |  |  |  | 1 | 46360 |  | Gardner, Travis | Independent | Aqua | 2022-12-14 | Other Programs
Hartsdale Surge Relief Conversion for Tank 1612 to 1613 | Item | Open | MCAP | HD00000M2301 | Maintenance Framework | 2085620 | Parker, Brian | West | 6. Operational | Defined | Facility Integrity | 119121 |  |  | 119120.63 | 117360 | 1761 | Yellow | 84000 |  | 84000 | 35121 |  |  | 135979 |  |  | 135979 | Full | 135979 | 119121 |  | 119121 | No | Green | 2023-02-01 | 2023-03-01 | 2023-03-01 | 2023-06-30 | 2023-03-28 |  |  |  | 61385.41 | 46974.09 | 10761.13 | 9000 | 9000 | 1761 | Red | [11 empty] | 5/1/23 - looks like all invoices have been paid. Working on Job Book now. As-builts were submitted on Apr 6th to Eng & Design. JDE Equipment Tags were submitted on Apr 10th. 4/7/23 - accruing 62,250 for Shultz and 2,460 for GFL. 3/28/23 - piping mod's were completed and lines were refilled today. Need to have local ops create an MOC WO# to switch from TK 1612 to TK 1613. 2/28/23 - var is due to receiving new GTS valves, pipe, and fittings ahead of schedule and Shultz starting work early. Targeting end of month to complete this work. 2/24/23 - requested an Interim AFE on Feb 24th so I can get long lead items ordered ASAP. Already submitted the full AFE also. 2/23/23 - GTS valves and pipe/fittings have been ordered under OPEX for HD. Will re-code PO's once AFE has been approved (AFE was routed on 2/22). Also created Req. in JDE for Shultz work today coded to HD. Targeting to get the new piping and valves installed on 3/27. 2/3/23 - Andrew is getting a quote from Shultz for this work, have a quote for new GTS valves in hand. | 2023-05-06 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | HD - HARTSDALE |  | 108360 | 10761 |  |  |  |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 45354 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Hartsdale Terminal (BETHD) Tank 1620 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | BETHD00E2303 | Maintenance Framework | 2084804 | Roth, Aaron | West | 3. Active | Defined | Tanks |  | 10000 |  | 10000 | 10000 | 0 | Green | 10000 |  | 10000 | 0 |  |  | 11200 |  |  | 11200 | Phase | 11200 |  | 10000 | 10000 | No | Green | 2023-08-01 | 2023-02-17 | 2023-02-17 | 2023-12-31 | 2023-08-31 | [15 empty] | 10000 | [5 empty] | 5.1 - due date is 9.29.2023 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETHD - BET HARTSDALE TERMINAL |  |  | 0 | 10000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44822 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Hartsdale Terminal (BETHD) Tank 1621 - OOS Seal Insp | Item | Open | MEXP | BETHD00E2301 | Maintenance Framework | 2084789 | Roth, Aaron | West | 3. Active | Defined | Tanks |  | 29000 |  | 29000 | 156000 | -127000 | Red | 156000 |  | 156000 | -127000 |  |  | 20428 |  |  | 20428 | Phase | 20428 |  | 29000 | 29000 | No | Green | 2023-06-01 | 2023-02-08 | 2023-02-08 | 2023-12-31 | 2023-09-30 | [13 empty] | 29000 | [7 empty] | 5.1 - do in-service inspection june 1st | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETHD - BET HARTSDALE TERMINAL |  |  | 29000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44823 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Hartsdale Terminal (BETHD) Tank 1622 - OOS Seal Insp | Item | Open | MEXP | BETHD00E2302 | Maintenance Framework | 2084791 | Roth, Aaron | West | 3. Active | Defined | Tanks |  | 28000 |  | 28000 | 56000 | -28000 | Red | 156000 |  | 156000 | -128000 |  |  | 20428 |  |  | 20428 | Phase | 20428 |  | 28000 | 28000 | No | Green | 2023-06-01 | 2023-02-08 | 2023-02-08 | 2023-12-31 | 2023-08-31 | [13 empty] | 28000 | [7 empty] | 5.1 - do in-service inspection june 1st | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETHD - BET HARTSDALE TERMINAL |  |  | 28000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44824 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Hartsdale Terminal (BETHD) Tank 1623 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | BETHD00M2301 | Maintenance Framework | 2084366 | Roth, Aaron | West | 3. Active | Defined | Tanks |  | 907813 |  | 907813 | 907813 | 0 | Green | 947813 |  | 947813 | -40000 |  |  | 760001 |  |  | 760001 | Phase | 760001 |  | 907813 | 907813 | No | Green | 2023-08-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-09-30 | [15 empty] | 260000 | 500000 | 147813 |  |  |  | 5.1 - start in Aug | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETHD - BET HARTSDALE TERMINAL |  |  | 0 | 760000 | 147813 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44825 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Hartsdale Terminal (BETHD) Tank 1611 - OOS Corr Insp & Refurb | Item | Open | MEXP | BETHD00E2101 | Exempt | 1781993 | Roth, Aaron | West | 7. Closed | Defined | Pressure Vessels | 12 |  |  | 11.67 | 12 | 0 | Green |  |  |  | 12 |  |  | 183000 |  |  | 183000 | Phase | 183000 | -7936 |  | -7936 | No | Green | 2021-01-01 | 2020-12-02 | 2020-12-02 | 2021-12-31 | 2021-06-30 |  |  |  | 11.67 | [17 empty] | 6/2/21 - moving re-class to July due to observed AFE approval duration. 5/9/21 - forecasting re-class to MCAP for June. 4/8/21 - forecasting re-class to MCAP for June 4.3.21 - Repairs to begin 4/12. expected RTS at the end of April. Due: 7/5/2021. | 2021-06-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETHD - BET HARTSDALE TERMINAL |  | 12 | 0 |  |  |  |  | Stine, Carlton | Bassani, Joel D. | N/A |  | 1 | 30371 |  | Guest, ProSight | Independent | Aqua | 2018-08-06
Hartsdale Terminal (BETHD) Tank 1612 – OOS Corr Insp & Refurb | Item | Open | MCAP | BETHD00M2201 | Maintenance Framework | 1938071 | Roknich, Hunter | West | 6. Operational | Defined | Tanks | 3688 |  | 140000 | 3687.81 | 2853 | 834 | Red |  |  |  | 3688 |  |  | 489000 |  |  | 489000 | Phase | 489000 | 613692 | 140000 | 753692 | No | Green | 2022-03-01 | 2022-01-11 | 2022-01-11 | 2022-01-03 | 2022-10-03 |  |  | 1200.58 | 213.64 | 1439.27 | 834.32 |  |  | 834 | Red | [10 empty] | 140000 | 10/10/2022 - Variance due to $6k missed on forecasting for containment work, as well as waste disposal and inspector costs 8/2/2022 - All tank construction complete. Button up to be complete by 8/5. First refill RTS 8/8. 7/5/2022 - Consolidated mobilizing 7/5. Estimated 3 weeks for Mechanical repairs. Coating and inspections to occur after. Estimated RTS 8/2 6/2/2022 - Tank OOS, isolated, cleaned, sandblasted. DJA onsite for inspection, Estimated RTS early July. 5/3/2022 - Project delayed 1 week due to procedural change MOC to utilize TK1613 as temporary surge relief tank while 1612 is OOS. Forecast in May for cleaning (50k), DJA inspection (11k), pipe modification (21k), and onsite inspector (15k). 4/4/2022 - Prelim OOS 5/9. Material purchasing complete. Variance due to price increase on material 3/2/22 - Prelim OOS date 5/9. March forecast for material purchasing. 10.6.21 - BP wants May OOS. | 2022-10-10 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETHD - BET HARTSDALE TERMINAL |  | 2853 | 834 |  |  | 610004 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41271 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Hartsdale Terminal (BETHD) Tank 1614 - OOS Corr Insp & Refurb | Item | Open | MEXP | BETHD00E2102 | Exempt | 1781994 | Roth, Aaron | West | 7. Closed | Defined | Pressure Vessels | 35 |  |  | 35.01 | 35 | 0 | Green |  |  |  | 35 |  |  | 231000 |  |  | 231000 | Phase | 231000 | -3374 |  | -3374 | No | Green | 2021-01-01 | 2020-12-02 | 2020-12-02 | 2021-12-31 | 2021-06-30 |  |  |  | 35.01 | [17 empty] | 6/18/21 - submitted Re-Class request to move 248,949.03 to the MCAP project. 6.1.21 - Tank RTS. external touchups remain | 2021-06-18 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | E. Chicago Terminals | BETHD - BET HARTSDALE TERMINAL |  | 35 | 0 |  |  |  |  | Stine, Carlton | Bassani, Joel D. | N/A |  | 1 | 30369 |  | Guest, ProSight | Independent | Aqua | 2018-08-06
Hartsdale Terminal (BETHD) Tank 1615 – OOS Corr Insp & Refurb | Item | Open | MCAP | BETHD00M2202 | Maintenance Framework | 1938079 | Roknich, Hunter | West | 6. Operational | Defined | Tanks | 1890 |  | 50000 | 1890 | 1890 | 0 | Green |  |  |  | 1890 |  |  | 285000 |  |  | 285000 | Phase | 285000 | 249525 | 50000 | 299525 | No | Green | 2022-02-01 | 2022-01-11 | 2022-01-11 | 2022-01-03 | 2022-06-10 |  |  | 1890 | [17 empty] | 50000 | 10/10/2022 - Dike grading complete. Reason for variance. 9/2/2022 - Project complete. Miscellaneous invoices for WDR's, late invoicing 8/2/2022 - Exterior paint touch-ups complete 6/2/2022 - Project complete. RTS MOC approved. Waiting for BP first batch in tank. 5/3/2022 - Tank buttoned up, RTS MOC to be submitted by 5/6. BP wants first batch 5/20. Variance due to a change order from cleaning contractor (9k), and missed forecast schedule. 4/4/2022 - DJA report completed and minor repairs are needed. Consolidated to mobilize 4/18 and should be 1 week worth of work. DJA inspection and Saybolt strapping to follow in April. Tank RTS by 4/31. 3/2/22 - Tank has been stripped to 1.65'. The remaining product will go to TK 1614. OOS will begin 3/14 with Inserv cleaning. Materials have been purchased. DJA inspection to begin 3/24. Minor repairs expected. Variance due to change in material. 2/2/22 - Tank prelim OOS scheduled for 3/7/22. 10.6.21 - candidate for robotic inspection, if not BP wants March OOS | 2022-10-11 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | BETHD - BET HARTSDALE TERMINAL |  | 1890 | 0 |  |  | 247635 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41272 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Hartsdale Terminal Site Lighting Replacement | Item | Open | MCAP | BETHD00M2303 | Exempt | 2094866 | Gardner, Travis | West | 3. Active | Drawdown | West |  | 18000 |  | 18000 | 18000 | 0 | Green |  | 20429 | 20429 | -2429 |  |  | 20429 |  |  | 20429 | Full | 20429 |  | 18000 | 18000 | No | Green | 2023-07-01 | 2023-03-17 | 2023-03-17 | 2023-05-31 | 2023-05-31 | [6 empty] | 18000 | 18000 | -18000 | Red |  | Contractor/Vendor Issue |  |  | 18000 | [6 empty] | 4/20/2023 - moved forecast to July. new light material is on back order. 4/4/2023 - emergent project PO issued to Meade. | 2023-04-20 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | BETHD - BET HARTSDALE TERMINAL |  |  | 0 | 18000 |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 46762 |  | Gardner, Travis | Independent | Aqua | 2023-03-13
HC Junction Communication Cabinet Upgrade | Item | Candidate | MCAP |  | Exempt |  | Grinder, Mark | West | 2. Pending AFE |  | Instrumentation & Controls |  | 8000 |  | 8000 | 8000 | 0 | Green | 8000 |  | 8000 | 0 | [9 empty] | 8000 | 8000 | No | Green | 2023-09-01 |  |  |  | 2023-09-30 | [16 empty] | 8000 |  |  |  |  | 4-27-2023 - Still waiting for an updated quote for this and will submit the AFE sometime in May. 3-23-2023 - AFE not submitted yet, I just received the quote for installation and will work on the AFE in the beginning of Mayl. 3-01-2023 - I will be submitting the AFE for this next week. | 2023-04-27 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | HC - HARTSDALE JCT TO ENBRIDGE |  |  | 0 | 8000 |  |  |  | Forsey, Frank |  |  |  | 1 | 41497 |  | Guest, ProSight | Independent | Aqua | 2021-08-18 | Other Programs
HD156KG - 2021 GEO+AMFL ILI | Item | Open | MEXP | HD156KGE2101 | Exempt | 1784270 | Smith, Kyle | West | 7. Closed | Defined | Assessments | -45560 |  |  | -45560 | -45560 | 0 | Green |  |  |  | -45560 |  |  | 85314 |  |  | 85314 | Full | 85314 | 163013 |  | 163013 | No | Green | 2021-02-01 | 2020-12-29 | 2020-12-29 | 2021-12-31 | 2021-05-20 |  |  | -45560 | [18 empty] | 2/3/2023 - Variance is J. Williamson accrual reversal. Accrual is no longer needed. 12/23/22 - PO and WO closed - ready to be closed by accounting. 6/1/21 Work has been completed | 2023-02-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | E. Chicago Terminals | HD156KG - HARTSDALE TO LAKE GEORGE |  | -45560 | 0 |  |  | -45560 |  | Bartal, Nick | Bassani, Joel D. |  |  | 1 | 37022 |  | Administrator, System | JDE Child | Burnt Orange | 2020-07-13 | Int - Assessments
HH760IM - Digs from 2022 GEO+MFL ILI | Item | Open | MCAP | HH760OTM2201 | Maintenance Framework | 1989884 | Scott, Cory | West | 7. Closed | Defined | Pipeline Digs | 100 |  |  | 100 | 100 | 0 | Green |  |  |  | 100 |  |  | 539000 |  | 78000 | 617000 | Supplemental | 617000 | 629781 |  | 629781 | No | Green | 2022-06-01 | 2022-06-24 | 2022-06-24 | 2022-08-01 | 2022-09-30 |  |  |  |  | 100 | [16 empty] | 1/23/2023 - Project closed. 1/3/2023 - $12,681.00 variance due to right of way charges. 12/6/22 - Negative $145 in December due to Flip to HH760OTM2201 (AS) 10/19/2022 - Engineering Change Order approved by Carl Ostach eliminating supplemental. 10/10/2022 - (2) Additional digs were added to the scope from Milan to Sugar Creek resulting in additional cost. 9/15/2022 - Job Book completed and approved per Joan Felchock. 9/12/22 - _$16,588 related to Flip HH760TE2202 (AS) 8/31/2022 - Final dig site data turned into JDE upload. 8/24/2022 - Final change order sent to Timco. 8/18/2022 - Final Timco Invoices approved. 8/11/2022 - Final reports sent for line restoration. 8/10/2022 - P-0300981 completed. 8/3/2022 - P-0373639 completed. 7/31/2022 - P-0482578 completed. 7/20/2022 - P-0161005A & P-0161005B & P-0161006 Complete. Final dig will start on 7/28/2022 and be completed around 7/31/2022. 7/16/2022 - P-0143447 Complete 7/13/2022 - P-0125143A & B Complete 6/27/2022 - P-0068537 and P-0071511 complete. 6/25/2022 - P-0065766 and P-0065767 complete. 6/20/2022 - P-0005641 complete. 6/17/2022 - Project excavation started. 6/16/2022 - Project Precon and kickoff meeting. Project clearing started. 6/14/2022 - Contractor finished OQ's. Once calls have been submitted. Contractor will mobilize on 6/15/2022. Contractor will kickoff project on 6/16/2022. 6/13/2022 - Pending inspector availability, project planned to start 6/15/2022. Contractor will produce schedule. AFE fully submitted into remedyforce. Sleeve material arrived onsite. 6/10/2022 - PO's for sleeve material put in 12", 13" totaled = $16.313.90. The 9" oversleeve totaled = $3912.40. HGA PO approved for $45,576.16. Acuren PO approved for $105,228.00 6/8/2022 - Chaining digs. Working on estimates. 6/7/2022 - Chaining out digs for contractor estimates. 6/6/2022 - Contractor took PIC training in Tulsa. Interim AFE to open up project submitted. 6/2/2022 - Working on scope, afe, and obtaining quotes 5/26/22 -Digs issued by integrity. 4/1122 - No change; digs not yet issued. | 2023-01-23 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Eastern Iowa | HH760OT - HARPER STA TO OTTUMWA STA |  | 100 | 0 |  |  | 629681 |  | Bartal, Nick | Smith, Todd W. |  |  | 1 | 41013 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
HT160DQ Rectifier Pole Replacement | Item | Open | MCAP | HT160DQM2302 | Exempt | 2096481 | Gabriel, Jeff | West | 6. Operational | Defined | Cathodic Protection | 26061 |  |  | 26060.88 | 27924 | -1863 | Yellow | 13500 |  | 13500 | 12561 |  |  | 56845 |  |  | 56845 | Full | 56845 | 26061 |  | 26061 | No | Green | 2023-03-01 | 2023-03-22 | 2023-03-22 | 2023-07-30 | 2023-04-30 |  |  |  |  | 3924.3 | 22136.58 | 24000 | 24000 | -1863 | Yellow |  | Forecasting | [9 empty] | 5/1/2023 approved amount was above the AFE I submitted. need to look into this. 4/3/2023- Work complete. ahead of Schedule. 3/2/2023- AFE is complete and is being routed for approval | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Central-Illinois | HT160DQ - HARRISTOWN JCT TO DEWITT |  | 3924 | 22137 |  |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44167 |  | Guest, ProSight | Independent | Aqua | 2022-07-18 | Int - Planned Corr & FI
Huntington BDL PLC and HMI Replacement Phase 1 | Item | Open | MCAP | BDLHN00M2201 | Maintenance Framework | 1939420 | Fink, Ryan | West | 3. Active | Defined | Instrumentation & Controls | 4178 | 82000 |  | 86178.1 | 85991 | 187 | Yellow | 89000 |  | 89000 | -2822 |  |  | 57000 |  |  | 57000 | Phase | 57000 | 44385 | 82000 | 126385 | No | Green | 2022-02-01 | 2022-01-24 | 2022-01-24 | 2022-06-30 | 2023-10-20 |  |  | 39027.61 | -35865.97 | 829.35 | 187.11 |  |  | 187 | Red | [5 empty] | 12000 | 24000 | 46000 |  |  |  | 5/2 RRF - Need to finish ph2 AFE, EAC $126k 4/7 RRF - EAC $126k 3/2 RRF - Site visit last week, preparing ph2 AFE, EAC $126k 2/2 RRF - PHase 2 AFE in feb, site visit mid feb 2-1-23 Invoice from Unlimited Technology (37,795) posted to wrong project reclass submitted. 01-04-2023 - Meeting with ARSEAL next week. 12/2 RRF - review HMI and Yoko 11/1 RRF - HMI updates 10/4 RRF - RFQ Estimate to add Yokogawa 9/12 RRF - Engineering 80%, need decisions on HMI to move forward. Should Yokogawa PLC be included in this new one? 9/2 RRF - will update by 9/8. Not quite right, needs some work., moved remainder to 2023 8/2 RRF - HMI PC arrived, HMI programming in progress. Moved contingency to Dec. 7/11 RRF - locating material, pending update 6/9 RRF - update for phase 2. will move additional funds from XB00000M2201 6/2 RRF - Material hold 5/3 RRF - in progress 4/11 RRF - I/O list done, material to be ordered 3/1 RRF - update with material delivery times 2/4 RRF - PC arrive July, adjust fcst. and op date. 2/2 RRF - PC request from IT, forecast full budget 1/12 RRF init | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Huntington | BDLHN - HUNTINGTON - BDL |  | 3991 | 187 | 36000 | 46000 | 40207 |  | Forsey, Frank | Wernsman, Jason T. |  |  | 1 | 34030 |  | Guest, ProSight | Independent | Aqua | 2019-08-15 | Other Programs
Huntington BDL Security Video System Installation | Item | Open | MCAP | BDLHN00M2202 | Maintenance Framework | 1957432 | Smith, Kyle | West | 6. Operational | Defined | Security & Cameras | 1750 |  |  | 1749.72 | 1750 | 0 | Green |  |  |  | 1750 |  |  | 45000 |  | 8749 | 53749 | Supplemental | 53749 | 53569 |  | 53569 | No | Green | 2022-10-01 | 2022-03-29 | 2022-03-29 | 2022-06-30 | 2022-12-31 |  |  | 1929.72 | -180 | [17 empty] | 1/1/23 Work Completed | 2023-01-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Huntington | BDLHN - HUNTINGTON - BDL |  | 1750 | 0 |  |  | 51820 |  | Clark, Chris | Clark, Chris B | N/A |  | 1 | 31392 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Other Programs
Huntington North Propane Pump and Motor Replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Smith, Kyle | West | 5. Deferred |  | West |  |  |  | 0 |  | 0 | Green | 300000 |  | 300000 | -300000 | [9 empty] | 300000 | 300000 | No | Green | 2024-07-01 |  |  |  | 2024-12-31 | [21 empty] | 4/5/23 Deferred until 2024 | 2023-04-05 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Huntington | BDLHN - HUNTINGTON - BDL |  |  | 0 |  |  |  | 300000 | Gardner, Travis |  |  |  | 1 | 45747 |  | Gardner, Travis | Independent | Aqua | 2022-09-02 | Other Programs
Huntington Sample Building Refurbishment | Item | Candidate | MCAP |  | Exempt |  | Smith, Kyle | West | 2. Pending AFE |  | West |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 | [9 empty] | 50000 | 50000 | No | Green | 2023-10-01 |  |  |  | 2023-07-31 | [17 empty] | 50000 |  |  |  | 4/28/23 Stakeholders call complete. Waiting on updates from Travis where to go with this project. | 2023-04-28 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Huntington | XB - HUNTINGTON STATION |  |  | 0 |  | 50000 |  |  | Gardner, Travis |  |  |  | 1 | 37511 |  | Guest, ProSight | Independent | Aqua | 2020-08-06 | Other Programs
Huntington South Propane Pump and Motor Replacement | Item | Open | MCAP | BDLHN00M2104 | Maintenance Framework | 1909898 | Smith, Kyle | West | 6. Operational | Unplanned | Rotating Equipment | 205 | -24798 |  | -24593.05 | -34186 | 9593 | Red |  |  |  | -24593 |  |  | 180000 |  | 227000 | 407000 | Supplemental | 825000 | 847797 | -24798 | 822999 | No | Green | 2021-11-01 | 2021-11-18 | 2021-11-18 | 2021-12-31 | 2022-10-31 |  |  | 611.98 | -10000 | 0 | 9592.97 |  |  | 9593 | Red |  |  |  | -24798 | [7 empty] | 5/2/23 Sahmbaugh was contacted about billing in Feb. They said all billing was done. Open PO was discussed and they said they had all billing in. We dropped PO and now they sent another bill for open PO. It is owed but bad communication from their end. 2/27/23 - June forecast for reclass of motor to inventory 12/1/22 Work has been completed and just cleaning up billing | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Huntington | BDLHN - HUNTINGTON - BDL |  | -9388 | -15205 |  |  | 717964 |  | Posipanko, Dan | Wernsman, Jason T. |  |  | 1 | 42401 |  | Guest, ProSight | Independent | Aqua | 2021-11-02 | Other Programs
Huntington Station (XB) -Site survey to validate SPCC plan calculations and review. | Item | Open | MEXP | XB00000E2202 | Exempt | 1955407 | Roth, Aaron | West | 7. Closed | Defined | Secondary Containment | 2610 |  |  | 2609.5 | 2610 | 0 | Green |  |  |  | 2610 |  |  | 13000 |  |  | 13000 | Full | 13000 | 11025 |  | 11025 | No | Green | 2022-03-01 | 2022-03-07 | 2022-03-07 | 2022-08-01 | 2022-03-30 |  |  | 2609.5 | [18 empty] | 12/22/22 - PO and WO closed - ready to be closed by accounting. 3.31.22 - done, awaiting invoices | 2022-12-22 |  |  | West | Pipelines and Terminals | Station/Terminal |  | Huntington | XB - HUNTINGTON STATION |  | 2610 | 0 |  |  | 8416 |  | Spari, Markella | Spari, Markella |  |  | 1 | 41560 |  | Administrator, System | Independent | Aqua | 2021-08-19 | Other Programs
Huntington Station Concrete Replacement | Item | Open | MCAP |  | Exempt |  | Smith, Kyle | West | 2. Pending AFE | Defined | West |  | 70000 |  | 70000 | 70000 | 0 | Green | 70000 |  | 70000 | 0 |  |  | 34260 |  |  |  | Full | 34260 |  | 70000 | 70000 | No | Green | 2023-08-01 |  |  | 2023-08-30 | 2023-05-31 | [15 empty] | 70000 | [5 empty] | 4/28/23 Bid event complete waiting on blacktop quotes to compare requested by Mike R. | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Huntington | XB - HUNTINGTON STATION |  |  | 0 | 70000 |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 42474 |  | Guest, ProSight | Independent | Aqua | 2021-11-18 | Other Programs
Huntington Station DRA Skid Containment Upgrade | Item | Open | MCAP | XB00000M2301 | Maintenance Framework | 2096559 | Smith, Kyle | West | 3. Active | Defined | Secondary Containment |  | 54000 |  | 54000 | 54000 | 0 | Green | 54000 |  | 54000 | 0 |  |  | 19703 |  |  | 19703 | Phase | 19703 |  | 54000 | 54000 | No | Green | 2023-05-01 | 2023-03-30 | 2023-03-30 | 2023-07-30 | 2023-08-31 | [12 empty] | 5000 |  | 40000 | 9000 | [5 empty] | 4/28/23 Waiting on final engineering | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Huntington | XB - HUNTINGTON STATION |  |  | 5000 | 49000 |  |  |  | Clark, Dave | Spari, Markella |  |  | 1 | 43167 |  | Gardner, Travis | Independent | Aqua | 2022-03-14 | Other Programs
Huntington Station PLC and HMI Upgrade | Item | Open | MCAP | XB00000M2201 | Maintenance Framework | 1946227 | Fink, Ryan | West | 3. Active | Defined | Instrumentation & Controls | 1228 | 171000 |  | 172227.72 | 172104 | 124 | Yellow | 172000 |  | 172000 | 228 |  |  | 46000 |  |  | 46000 | Phase | 46000 | 26144 | 171000 | 197144 | No | Green | 2022-02-01 | 2022-02-07 | 2022-02-07 | 2022-05-01 | 2023-08-31 |  |  | 489.24 | 118.76 | 495.52 | 124.2 |  |  | 124 | Red |  |  |  |  | 3000 | 6000 | 151000 | 11000 |  |  |  | 5/2 RRF - need to finish ph2 AFE, EAC $197k 4/7 RRF - EAC $197k 3/2 RRF - preparing ph2 AFE, EAC $197k 172k 2023 2/2 RRF - ph2 AFE feb, site visit mid feb 01/04/2023 - MNH - Getting with ARSEAL to get quotes. 12/2 RRF - create AFE 11/2 RRF - ph2 afe 10/4 RRF - create phase 2 AFE 9/1 RRF - nothing new 8/2 RRF - moved $148K to drawdown and added to 2023 forecast. and design work progressing, slip 1 month 7/11 RRF - dwg and design done, charges to date 21766 moved to project in June ; need material list to RFQ mat. Material not likely available in 2022. moved that to Dec for now. 6/9 RRF - update for current status 5/3 RRF - material list received 4/29, pending rfq, on track 4/11 RRF - pending parts list for phase 2 3/1/2022 RRF - ok | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Huntington | XB - HUNTINGTON STATION |  | 1104 | 124 | 160000 | 11000 | 24916 |  | Forsey, Frank | Wernsman, Jason T. |  |  | 1 | 34867 |  | Guest, ProSight | Independent | Aqua | 2019-08-30 | Other Programs
Huntington Station Switchgear AC Roof Top Replacement | Item | Open | MCAP | XB00000M2204 | Maintenance Framework | 2036560 | Smith, Kyle | West | 6. Operational | Drawdown | West | 38832 | 2000 |  | 40831.99 | 45627 | -4795 | Red | 45000 |  | 45000 | -4168 |  |  | 80000 |  |  | 80000 | Full | 80000 | 72776 | 2000 | 74776 | No | Green | 2022-11-01 | 2022-10-10 | 2022-10-10 | 2023-05-15 | 2023-04-30 |  |  | 153.73 | 159.4 | 314.08 | 38204.78 |  |  | 38205 | Red |  | WorkAhead of Schedule | 2000 | [8 empty] | 4/26/23 Work is completed. 4/5/23 Stakeholder call complete and all plans approved work scheduled this month. 3/3/23- Stakeholders call sit for 3/6/23 3/1/2023 - unit order and invoice received install is scheduled for 2023. 11/2/2022 - vendor should be invoicing 50% on award in November. 10/3/2022 - this is an emergent project. HVAC 16 week lead time. vendor terms 50% on award, remaining on completion in 2023 | 2023-04-26 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Huntington | XB - HUNTINGTON STATION |  | 627 | 40205 |  |  | 33944 |  | Gardner, Travis | Spitz, Nicholas P. |  |  | 1 | 45931 |  | Gardner, Travis | Independent | Aqua | 2022-09-29 | Other Programs
Huntington Station Tank Probes 2020 | Item | Open | MCAP | XB00000M2101 | Exempt | 1838242 | Smith, Kyle | West | 6. Operational | Unplanned | Tanks | 672 |  |  | 671.9 | 672 | 0 | Green |  |  |  | 672 |  |  | 40000 |  | 14000 | 65000 | Supplemental | 65000 | 63326 |  | 63326 | No | Green | 2021-05-01 | 2021-04-23 | 2021-04-23 | 2021-05-30 | 2022-11-30 |  |  |  |  | 671.9 | [16 empty] | 12/1/22 Tech has parts and says job is completed as far as he can until they can get the time to install the boards. No additional cost to hit this project. | 2022-12-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Huntington | XB - HUNTINGTON STATION |  | 672 | 0 |  |  | 9527 |  | Stine, Carlton | Clark, David |  |  | 1 | 24281 |  | Administrator, System | Independent | Aqua | 2017-07-21 | Int - Tanks
IC822CP - 2021 GEO+AMFL ILI | Item | Open | MEXP | IC822CPE2101 | Exempt | 1801895 | Bost, Jason | West | 6. Operational | Defined | Assessments | 289 | 7999 |  | 8287.5 | 8288 | 0 | Green | 18893 |  | 18893 | -10606 |  |  | 75567 |  |  | 75567 | Full | 75567 | 25169 | 7999 | 33168 | No | Green | 2022-11-01 | 2021-01-28 | 2021-01-28 | 2021-12-31 | 2023-02-23 |  |  | 0 | 0 | 288.5 | [7 empty] | 7998 | [6 empty] | 1 |  | 4/3/23 - Run accepted. Remaining PO balance forecasted accordingly. 3/1/23 - Accrual is 75% TDW's PO. Delay in approval of tool run caused by deviation required to accept 96% sensor coverage rather than the standard 97% coverage. Deviation approved by all necessary parties on 2/23. 1/31/23 - Accrual is for 75% TDW invoice. TDW awaiting approval from Buckeye Integrity. 1/4/23 - Accrual is for TDW's 75% invoice. 12/5/22 - Assessment completed on 11/15. Accrual is 75% of TDW's PO. Final 25% is already reflected in 2023, so remaining variance is likely cost savings. 11/1/22 - Assessment scheduled 11/15. 11/1/21 - no change. 9/1/21 - Delayed to 2022 due to L820 return to service timing pushing out. -7/1/21 - Run date changed to 9/14 due to no product moving on the line until Sept.6/2/21 - Run scheduled for late June/early July, but may change based on discussion with John Williamson. 10/29/20 - Recommissioning is delayed until Q2 2021 due to needing to address land slip locations prior to bringing back in service. ILI will not be able to be run until recommissioning is complete. | 2023-04-04 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Pipeline Integrity |  | Coraopolis | IC822CP - CORAOPOLIS JCT TO CORAOPOLIS |  | 289 | 7998 |  | 1 | 24880 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 37023 |  | Administrator, System | Child (Major Project) | Olive | 2020-07-13 | Int - Assessments
IM760UG - Digs From 2022 Tool Run | Item | Open | MCAP | IM760UGM2303 | Maintenance Framework | 2076516 | Scott, Cory | West | 6. Operational | Defined | Pipeline Digs | 89906 | 4000 |  | 93905.61 | 86034 | 7872 | Yellow |  |  |  | 93906 |  |  | 85474 |  |  | 85474 | Full | 85474 | 89906 | 4000 | 93906 | No | Green | 2023-03-01 | 2023-01-26 | 2023-01-26 | 2023-03-11 | 2023-03-17 |  |  |  |  | 86034.04 | 3871.57 |  |  | 3872 | Red |  |  | 4000 | [8 empty] | 5/8/2023 - Forecasted $4000 for damages and right of way agent cost. 4/18/2023 - Final invoice for Acuren approved. Project final cost around 86K. 4/10/2023 - Job book completed and approved. 3/21/2023 - Change orders produced due to higher cost than anticipated. Final cost should land close to 87K-90K. 3/3/2023 - Project completion and demobilization. Expected final cost expected to come under budget. Project should total 82K. 2/28/2023 - First dig planned to be completed by March 1st. Second should be completed by end of first week. 2/23/2023 - Crew started working on dig # F-038022. 2/2/2023 - Stakeholder meeting held. 1/30/2023 - OQ job # setup in ISNetworld. PO's placed. Work orders setup. 1/28/2023 - AFE fully approved. 1/25/2023 - Site Safety Plan Approved by Buckeye HSSE. 1/17/2023 - AFE submitted. | 2023-05-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | IM760UG - MILAN STA TO SUGAR CREEK TERM |  | 86034 | 7872 |  |  |  |  | Bartal, Nick | Smith, Todd W. |  |  | 1 | 46461 |  | Guest, ProSight | Independent | Aqua | 2023-01-13 | Int- Planned Digs
IM760UG 7 Mile Hill Remote Recoat | Item | Open | MEXP | IM760UGE2301 | Exempt | 2085559 | Scott, Cory | West | 6. Operational |  | Atmospheric Corrosion | 8234 |  |  | 8234.08 | 8500 | -266 | Yellow | 7001 | 1350 | 8351 | -117 |  |  | 8177 |  |  | 8177 | Full | 8177 | 8234 |  | 8234 | No | Green | 2023-04-01 | 2023-02-22 | 2023-02-22 | 2023-05-05 | 2023-04-30 | [5 empty] | 8234.08 | 8500 | 8500 | -266 | Yellow | [11 empty] | 5/5/2023 - Cleveland invoice came in at $2,847.71 5/2/2023 - Awaiting final invoice from Cleveland Integrity. 4/12/2023 - Project completed. Final invoicing will come in right a budget amount. 3/30/2023 - Stakeholder meeting held. Projects to start 4/11/2023. 3/27/2023 - Inspector request placed. Stakeholder meeting is to take place 3/30/2023. 3/20/2023 - PO placed to Vance and Associates for 4K. 1/23/2023 - Built project AFE. Adjusted forecast to $8500.00. AFE submitted. | 2023-05-05 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Sugar Creek | IM760UG - MILAN STA TO SUGAR CREEK TERM |  |  | 8234 |  |  |  |  | Geib, Rob | Smith, Todd W. |  |  | 1 | 45452 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
IM760UG Scraper Trap Replacement Phase 1 | Item | Open | MCAP | IM760UGM2202 | Maintenance Framework | 1971974 | Scott, Cory | West | 3. Active | Defined | ILI Modifications | 12864 | 160000 |  | 172863.98 | 171939 | 925 | Yellow |  | 183000 | 183000 | -10136 |  |  | 78000 | 248000 |  | 326000 | Full | 326000 | 194867 | 160000 | 354867 | No | Green | 2022-07-01 | 2022-04-21 | 2022-04-21 | 2022-07-29 | 2023-10-31 |  |  | 5395.61 | 5388.18 | 1155.07 | 925.12 |  |  | 925 | Red | [6 empty] | 160000 |  |  |  |  | 5/2/2023 - August/September installation. 4/18/2023 - August/September installation. 2/22/2023 - Adjusted forecast to reflect paying for half a purge, final installation, and waste management. $160,000.00 for completion.2/15/2023 - Acuren NDE invoice approved for 4270.001/9/2023 - Trap fab/hydro/paint completed. January delivery to Sugar Creek. Awaiting planned purge or submission of new purge plan pending capital projects. 12/14/2022 - Timco fabrication completed. The billed $116,800.00.12/2/2022 - PO cut to Acuren for NDE of trap on 12/5/2022. Hydro testing and painting will follow immediately after. 11/05/2022 - Timco recieved all the pipe and fittings.9/28/2022 - PO placed to Timco. Timco plans to have the fabrication and testing completed before the end of 2022. 9/13/2022 - Timco awarded bid for 194K. Phase 2 AFE submitted. 9/5/2022 - Final bids from bid event being submitted by contractors. 8/19/2022 - Engineering, valve procurement, and contractor fabrication taking place in 2022. 60K put into CY+1 for installation. The trap will be installed during a purge taking place for capital projects in 2023. 8/12/2022 - Diamond Z billed 11K for engineering design. 8/11/2022 - Scraper trap drawings recieved. Bid process beginning. 8/5/2022 - PO placed to Prairie Industrial for the hand dig investigation to complete final engineering. 6/24/2022 - Diamond Z sent the design back stating that the Buckeye standards have changed. I plan on having a conversation between Brian/Todd to discuss the route of design to address this change in order to move forward. 5/31/22 - Final updates being discussed on drawings produced by Diamond Z. Once drawing package is complete, project scope will go out for bid. 5/9/22 - NEB added 8k contingency from overall program variance. 4/23/2022 - PO for Ranger Ball Valves sent to Specialty Products for $33,902.72. Lead time of (12) weeks. 4/22/22 - PO for scan and engineering sent to Diamond Z for $22,860.004/21/22 - Phase 1 AFE approved and PO's for the Valves and Engineering requisitioned.4/8/22 - NEB added $15k contingency from overall program variance. 4/6/2022 - Moving forecast out to August to receive valves, fittings, and materials. Moved work installation costs to September. 4/4/2022 - Submitting PhaseAFE for Valves, Engineering, and miscellaneous fittings. 4/1/2022 - Pull measurements and make sketch to be sent to Diamond Z for updated engineered drawings. 3/25/2022 - Received quotes from vendors and builtphase 1 AFE to be reviewed and submitted to remedyforce. 3/22/2022 - Sent valve data sheets to vendors to have quote produced. 3/8/2022 - Started working on Scope Of Work for this project.3/7/2022 - Requested engineering drawings from Buckeye Engineering and Design to markup for DiamondZ toproduce a new set of drawings. | 2023-05-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | IM760UG - MILAN STA TO SUGAR CREEK TERM |  | 11939 | 925 | 160000 |  | 182003 |  | Bartal, Nick | Smith, Todd W. | N/A |  | 1 | 26316 |  | Guest, ProSight | Independent | Aqua | 2017-09-17 | Other Programs
Indianapolis terminal - new video system | Item | Candidate | MCAP |  | Maintenance Framework |  | Fink, Ryan | West | 2. Pending AFE |  | Security & Cameras |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 | [9 empty] | 40000 | 40000 | No | Green | 2023-07-01 |  |  |  | 2023-10-31 | [14 empty] | 5000 | 11000 | 18000 | 2000 | 4000 |  |  | 4/28 RRF - reduced scope to 1 cam, re-RFQ EAC $40k 4/6 RRF - estimates exceed budget, revising scope to fit budget, and RFQ again. EAC $40k 3/1 RRF - RFQ out to vendors, EAC 40k 2/2 RRF - site visit 2/22 | 2023-04-28 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Indianapolis | BETID - BET INDIANAPOLIS TERMINAL |  |  | 0 | 34000 | 6000 |  |  | Clark, Chris |  |  |  | 1 | 40814 |  | Guest, ProSight | Independent | Aqua | 2021-07-28 | Other Programs
Indianola Surge Relief Modification | Item | Open | MCAP | ND00000M2201 | Maintenance Framework | 2021971 | Henfling, Mike | West | 7. Closed | Defined | Transient/Surge Mitigation | 2203 |  | 0 | 2202.67 | 2203 | 0 | Green |  |  |  | 2203 |  |  | 106000 |  |  | 106000 | Full | 106000 | 73073 | 0 | 73073 | No | Green | 2022-09-01 | 2022-09-07 | 2022-09-07 | 2022-12-31 | 2022-12-21 |  |  | 993.67 | 1209 | [16 empty] | 0 | 4-4-23 - Project Ready for Close 3-2-23 - Project Ready for Close 2-2-23 - Job book completed in January, awaiting two final invoices then will close project. 1-3-23 - Piping installed 12/20 and is operational. Final invoices and job book to be completed in January. 12-5-22 - Piping fully fabricated and tested. Scheduled install of 11/15 postponed due to Site Operations availability and other projects going on at the same time. Looking to schedule the one-day install in December but will likely push to January due to contractor availability. 11-2-22 - Twinseal and Brodie valves arrived in October. PO in place to XL for mechanical work, scheduled install 11/15. Pre-construction meeting planned for 11/3. 10-3-22 - Twinseal and Brodie valves on order for October delivery. Awaiting quote for piping work from mechanical contractor - PO to be issued in October for November installation. Actual install date TBD. 9-1-22 - AFE in queue, was not approved prior to 9/1 so missed forecast and can't accrue so initial engineering/PM costs. 6 week lead time Brodie valve to be ordered early September for full piping install in November. 8-2-22 - Site visit on 7/19 to scan site and begin scoping. Initial design complete and out to contractor for budgetary pricing. AFE and PO for engineering in August. 7-5-22 - Planning to begin engineering in late July / August 6-1-22 - Reduced forecast to match shift of funds to other projects within transient/surge mitigation program. Planning for engineering-only in 2022. 5-4-22 - Reviewed West Region transient program last week - pushed engineering site visits to June/July, and will revisit if construction will still be planned in 2022 or just engineering due to other transient projects in the West Region being over budget in 2022. 4-4-22 - No new updates. Need to schedule on-site scoping visit in April 3-2-22 - Shifted forecast one month. Scoping visit late March or April. 2-2-22 - Shifted forecast one month. Scopingvisit late February or March. High level scoping meetingheld 12/2021 | 2023-04-04 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Coraopolis | ND - INDIANOLA TERMINAL |  | 2203 | 0 |  |  | 70870 |  | DiPillo, Evan | Gardner, Travis W. |  |  | 1 | 41588 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
Indianola Terminal (BETND) Facility Painting | Item | Open | MCAP | BETND00M2202 | Maintenance Framework | 1972638 | Arch, Stefan | West | 6. Operational | Defined | Facility Painting | -2366 |  |  | -2366.42 | -2366 | 0 | Green |  |  |  | -2366 |  |  | 339000 |  |  | 339000 | Full | 339000 | 368405 |  | 368405 | No | Green | 2022-05-01 | 2022-04-28 | 2022-04-28 | 2022-12-31 | 2022-09-30 |  |  | 133.58 | 0 | -2500 | [16 empty] | 3/1/2023 - Project is complete, all PO's are closed. Waiting on one invoice from Waste Management for the paint chips and blast grit. Roll off was picked up and taken for disposal. 2/1/2023 - Project is complete, all PO's are closed. Waiting on one invoice from Waste Management for the paint chips and blast grit. 1/3/2023 - Project is complete. Waiting on one invoice from waste management for sand blast grit disposal. It is accrued. 12/1/2022 - Change order approved, no additional cost required on the project. Waiting on invoice from waste management. 11/1/2022 - Project completed in October. Change order required for additional FRP and u bolt installation. Variance for that reason. No additional forecast needed for the project. Project is complete. 10/3/2022 - Barr-None completed project on 9/30. Walked down the project on 9/27 for final walkthrough. Verified all FRP's were installed and all pipe was painted. DFT measurements were taken throughout the project and will be handed over from inspector. Change order needed for additional FRP's and u bolt replacement, it is included in September accruals. Variance in September due to Barr-None taking an extra week longer than they told me. Project is complete, no additional forecasting is needed. 9/1/2022 - Barr-None continuing pressure washing, FRP installation, and coating. Approximately 90% completed. Hoping for better progress in August, but Barr-None kept moving people around and working on tank 1201. Planning to be completed in September. 8/1/2022 - Barr-None continued pressure washing, painting, and install FRP's at Indianola. Approximately 80% complete. Barr-None swapped out crew at the end of July for the second time. Planning to have this project wrapped up in August. 7/1/2022 - Barr-None on site to complete painting. Areas 1,2, and 5 have 2 coatings completed. Area 7 is pressure washed. Continuing progress in July and pushing to be approximately 90% completed by theend of July. Variance in June due to not completing as much as anticipated. Forecasting in June covers pressure washing, painting and inspector services. 6/1/2022 - AFE approved and PO approved for Barr-None. Barr-None will mobilize on 6/6 to begin the work. FRP's will be installed as coating sections are completed. Forecasting for June include Barr None for 4 weeks, inspector costs, and CWIP charges. 5/2/2022 - Reviewed quotes and awarded to Barr-None. AFE submitted for $339,000, approved for the entire facility. Planning to begin late June/early July timeframe.The work will take 6-7 weeks. Forecasting in May includes material ordering. 4/3/2022 - Walked down project early March with contractors. Received bids back from contractors on 4/1. Will review and award contract. Planning to begin project in June when weather is warm.3/2/2022 - Walkdown and scope developed. Scope call held on 2/24. Scope broken into seven areas. Will need to involve supply chain to the complete | 2023-03-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Coraopolis | ND - INDIANOLA TERMINAL |  | -2366 | 0 |  |  | 370772 |  | Geib, Rob | Geib, Robert |  |  | 1 | 37775 |  | Guest, ProSight | Independent | Aqua | 2020-08-12 | Int - Planned Corr & FI
Indianola Terminal (BETND) Tank 201 (008A) - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | BETND00M2301 | Maintenance Framework | 2084374 | Arch, Stefan | West | 5. Deferred | Defined | Tanks |  |  |  | 0 |  | 0 | Green | 634537 |  | 634537 | -634537 |  |  | 591090 |  |  | 591090 | Phase | 591090 |  | 635000 | 635000 | No | Green | 2024-06-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2024-12-31 | [21 empty] | 1/30/23-CES-Project is being deferred due to the need to find funding within the tank program for urgent IFR needs in South Texas. Earliest compliance date for this tank is in 2024. Tank was budgeted in 2023 to make shell repairs and regain fill height in the tank. Tank will be required to be externally inspected at shortened intervals in accordance with 653 until repairs are made. | 2023-01-30 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Coraopolis | ND - INDIANOLA TERMINAL |  |  | 0 |  |  |  | 635000 | Stine, Carlton | Stine, Carlton |  |  | 1 | 44826 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Indianola Terminal (BETND) Tank 1201 (003A) – OOS Corr Insp & Refurb | Item | Open | MCAP | BETND00M2201 | Maintenance Framework | 1938055 | Arch, Stefan | West | 6. Operational | Defined | Tanks | 4902 |  |  | 4902.18 | 4691 | 211 | Yellow |  |  |  | 4902 |  |  | 531000 | 225000 |  | 756000 | Full | 756000 | 735898 |  | 735898 | No | Green | 2022-01-01 | 2022-01-11 | 2022-01-11 | 2022-01-03 | 2022-07-19 |  |  | 0 | 0 | 4691.08 | 211.1 |  |  | 211 | Red | [11 empty] | 4/7/2023 - Last invoice came through from Waste Management. All PO's and MOC's are closed. 3/1/2023 - Project is complete, waiting on one invoice from Waste Management and to close one PO. 2/1/2023 - Project is complete, waiting on one invoice from Waste Management and to close one PO. 1/3/2022 - Project is complete, waiting on one invoice from waste management, it is accrued. 11/1/2022 - Project is complete. Received Varec transmitter that was ordered in February. Waiting on waste management for one invoice for earth spoil disposal but cost is accrued. No forecast needed. 10/3/2022 - Tank painting completed in September. Variance in September due to forgetting to forecast the fire pipe install. Waiting on the Varec 2920 to come in but found a spare. Project is complete. 9/1/2022 - Tank is currently being painted. Painting should be completed mid September. 8/1/2022 - Tank buttoned up on 7/20. Waiting on instrumentation to be installed. Small variance in July due to spending less than anticipated. Planning to pain the tank in August. 7/1/2022 - Mechanical repairs completed beginning of June. Variance in June due to change order rom Phillips for additional time to remove the VOC's/lels from under the existing bottom. Waiting on foam chambers to come in to button up tank and RTS. Phillips will complete the foam chamber install. Forecasting for July includes button up, RTS activities, CWIP, and inspector services. 6/1/2022 - Mechanical repairs will be completed 6/3. Phillips will need to come back for the installation of 4 new foam chambers. the tank will be strapped and post mod inspection completed. Forecasting for June includes strapping, post mod inspection, CWIP, and inspector services. Waiting for foam chambers to come in for installation, mid-end of month. 5/2/2022 - Scope includes replacing 22 bottom plates, verifying plumbness of columns, adding sand, and implementation of Buckeye repair considerations. Will cut a hole in the roof and lower in the plates. Forecasting for May includes 60% of themechanical repairs and inspector costs. Planning to have mechanical repairs completed in June. 4/3/2022 - Jumper line installed the week of 3/21. Began cleaning end of 3/21 week and finished on 4/1. DJAon site for inspection 3/31 and 4/1, will complete the week of 4/4. Preliminary inspection found creases and bulges in the floor. Anticipating major scope. Forecasting in April is for inspector, DJA inspection, beginning mechanical repairs, mobilization, and material.2/28/2022 - Planning to install associated jumper 3/21 and 3/22. Tank will be isolated, drained, and cleaned after jumper install. Tank 803 will be used as temporary ULSD storage. Anticipating major repairs on the tank based on previous inspection reports. 1/28/1993 - Anticipating a larger scope. Associated support projectto install jumper line. Planning to take tank OOS in March. | 2023-04-07 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Coraopolis | ND - INDIANOLA TERMINAL |  | 4691 | 211 |  |  | 730996 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41273 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Indianola VRU Carbon Replacement | Item | Open | MCAP | BETND00M2203 | Maintenance Framework | 2004192 | Roknich, Hunter | West | 6. Operational | Drawdown | Vapor Management | -26124 |  |  | -26123.88 | -26492 | 368 | Yellow |  |  |  | -26124 |  |  | 184000 |  |  | 184000 | Full | 184000 | 169073 |  | 169073 | No | Green | 2022-10-01 | 2022-08-25 | 2022-08-25 | 2022-11-11 | 2022-11-30 |  |  | -34681.26 | 0.92 | 8188 | 368.46 |  |  | 368 | Red | [11 empty] | 2/3/2023 - Reclass posted causing variance in accruals 12/2/2022 - Waiting for final invoicing and reclasses. Variance due to an error in accrual last month of $41,880. 11/2/2022 - Variance due to a reclass of $41880 to the wrong project. This will hit next month. 10/10/22 - variance due to missed forecast. Work scheduled for week of 10/17 9/27/22 - Still working to reduce the LEL in V2 to safely complete the work. Working thought the plan with the regional team and ops. This project will be completed in 2022. 9/9/2022 - Field replacement scheduled the week of Sept. 19th. The carbon is getting relocated from Columbus South. | 2023-02-03 | Schultz, Amy |  | West | Pipelines and Terminals | Operating Infrastructure |  | Coraopolis | ND - INDIANOLA TERMINAL |  | -26492 | 368 |  |  | 195197 |  | Karl, Marissa | Spitz, Nicholas P. |  |  | 1 | 44583 |  | Gardner, Travis | Independent | Aqua | 2022-08-12 | Other Programs
Interference Testing 331/344/380 | Item | Open | MEXP | DS302CGE2202 | Maintenance Framework | 1946431 | Brown, Jeff | West | 7. Closed | Drawdown | Cathodic Protection | 0 |  |  | -0.01 | 0 | 0 | Green |  |  |  | 0 |  |  | 10000 |  |  | 10000 | Full | 10000 | 10000 |  | 10000 | No | Green | 2022-11-01 | 2022-02-10 | 2022-02-10 | 2022-12-31 | 2022-11-30 |  |  | -0.01 | [18 empty] | 12-5-22 JOB COMPLETED 10-31-22 TO BE COMPLETED NOV-DEC 10/4/2022 - work scheduled in October. 9/1/2022 - still scheduled for Oct. 7/7/2022 - no change to schedule. 6/3/2022 - work scheduled for October 4/5/2022 - work scheduled for October. | 2022-12-05 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Toledo | DS302CG - TOLEDO TO CYGNET 10IN SOUTH |  | 0 | 0 |  |  | 10000 |  | Geib, Rob | Shook, Mark B. | N/A |  | 1 | 42904 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-02-10 | Int - Planned Corr & FI
JJ404JV Nitrogen Purge and Isolate | Item | Open | MEXP | JJ404JVE2301 | Maintenance Framework | 2096478 | Smith, Kyle | West | 6. Operational | Defined | West | 48607 |  |  | 48606.85 | 72000 | -23393 | Red | 54000 |  | 54000 | -5393 |  |  | 67141 |  |  | 67141 | Full | 67141 | 48607 |  | 48607 | No | Green | 2023-04-01 | 2023-03-29 | 2023-03-29 | 2023-04-18 | 2023-04-30 | [5 empty] | 48606.85 | 72000 | 72000 | -23393 | Red |  | Savings from AFE Estimate | [9 empty] | 4/28/23 Work is completed | 2023-04-28 |  |  | West | Pipelines and Terminals | Station/Terminal |  | Indianapolis | JJ404JV - JOLIETVLLE JCT-JOLIETVILLE |  |  | 48607 |  |  |  |  | Gardner, Travis |  |  |  | 1 | 39584 |  | Guest, ProSight | Independent |  | 2021-03-17 | Other Programs
Kankakee Accuload Preset Upgrade Project | Item | Candidate | MCAP |  | Maintenance Framework |  | Grinder, Mark | West | 4. On-Hold |  | Truck Racks |  |  |  | 0 |  | 0 | Green | 190000 |  | 190000 | -190000 | [9 empty] | 400000 | 400000 | No | Green | 2024-07-01 |  |  |  | 2024-12-31 | [21 empty] | 4-27-2023 - This project will be deferred until 2024 and some of the funds will be used for the Granville Multioad Uprade Project. 4-3-2023 - This project will be deferred until 2024 and some of the funds will be used for the Granville Multioad Uprade Project. 3-23-2023 - This project is on hold, this project is underfunded as well and waiting to see if this is being cancelled or not. 3-01-2023 - Waiting for Triad to submit a quote so I can write a phase I AFE. | 2023-04-27 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Argo | KK163OA - KANKAKEE TO MAROA |  |  | 0 |  |  |  | 400000 | Younce, Michael |  |  |  | 1 | 41569 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
Kankakee Drain Pipe Replacement | Item | Open | MEXP | BETKK00E2205 | Maintenance Framework | 1970930 | Parker, Brian | West | 7. Closed | Defined | Secondary Containment | -245 |  |  | -244.5 | -245 | 0 | Green |  |  |  | -245 |  |  | 1000 | 19000 | 5022 | 25022 | Full | 25022 | 25022 |  | 25022 | No | Green | 2022-10-01 | 2022-04-08 | 2022-04-08 | 2022-10-31 | 2022-11-30 |  |  | -244.5 | 0 | 0 | 0 |  |  | 0 | Green | [11 empty] | 4/30/23 - final invoice from Envirospec was processed in Apr - ready to be closed out in JDE. 4/3/23 - re-accruing 3,000 for Envirospec for Mar and just coded and approved the invoice in OI today. 2/28/23 - re-accruing 3,000 for Envirospec for Feb. 1/31/23 - re-accruing 3,000 for Envirospec for Jan. Paid Diamond Z invoice in Jan. 1/5/23 - processed Keldorn invoice - accruing 3,000 for Diamond Z and 3,000 for Envirospec. PO and WO closed - ready to be closed by accounting at end of Jan. 12/2/22 - work was completed in Nov. Just need to process invoice then I can close out this project. 10/31/22 - expect to have the pipe in hand in about 2 weeks then will get the work scheduled. Moving this FCST out to Dec just in case we run into a supply chain delay. 9/29/22 - PO issued to Feken on Sep 16th for 17,500 to complete this work. They might complete this work in Oct but not 100% sure. 9/3/22 - the bid event had issues and nobody from Supply Chain followed up to see how this was progressing. Wasted 1 month on this and starting the bid process over again. I will be reaching out to all bidders the week of Sep 6th to make sure they have everything they need. Still expect to complete this work in Oct/Nov. 8/1/22 - had one comment back when IFC drawings were sent out for review. Plan on getting this out to contractors in Aug and get some pricing back to start work in Sep. 7/3/22 - will be sending out IFC drawing to management for review via email. Bidding is off the table right now due to contractor availability so just plan on obtaining several quotes from qualified vendors. 5/31/22 - have IFC drawings in hand - will complete bid document once I have all IFC drawings in hand and have completed drawing reviews. 5/3/22 - just waiting on IFC drawings from Diamond Z for some other dike projects so we can group these together and go out for bid sometime around late Jun or early Jul. 4/5/22 - submitted Phase I AFE for approval routing. | 2023-04-30 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Argo | BETKK - BET KANKAKEE TERMINAL |  | -245 | 0 |  |  | 25267 |  | Spari, Markella | Spari, Markella |  |  | 1 | 41488 |  | Guest, ProSight | Independent | Aqua | 2021-08-17 | Other Programs
Kankakee Sample Building Replacement 2020 | Item | Candidate | MCAP |  | Exempt |  | Parker, Brian | West | 5. Deferred |  | West |  | 1 |  | 1 | 1 | 0 | Green | 25000 |  | 25000 | -24999 | [9 empty] | 25001 | 25001 | No | Green | 2023-12-01 |  |  |  | 2023-10-31 | [19 empty] | 1 |  | 3/7/23 - removing FCST for 2023 and it has been moved to the West Region MCAP Drawdown Program for Travis Gardner's request. 2/13/23 - moving FCST out to Q4 based on conversation with OM. Just in a holding pattern right now since management is evaluating the upcoming pig dig costs vs the revenue the terminal and pipeline generate. | 2023-03-07 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Argo | BETKK - BET KANKAKEE TERMINAL |  |  | 0 |  | 1 |  | 25000 | Gardner, Travis |  | N/A |  | 1 | 20969 |  | Guest, ProSight | Independent | Aqua | 2016-09-02 | Other Programs
Kankakee Terminal (BETKK) Tank 153 - EFR Primary Seal Gap | Item | Open | MEXP | BETKK00E2301 | Maintenance Framework | 2084796 | Roth, Aaron | West | 6. Operational | Defined | Tanks | 13000 |  |  | 13000 | 13000 | 0 | Green | 12000 |  | 12000 | 1000 |  |  | 13440 |  |  | 13440 | Full | 13440 | 13000 |  | 13000 | No | Green | 2023-04-01 | 2023-02-08 | 2023-02-08 | 2023-12-31 | 2023-07-31 | [5 empty] | 13000 | 13000 | 13000 | 0 | Green | [11 empty] | 5.1 - done | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Argo | BETKK - BET KANKAKEE TERMINAL |  |  | 13000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44828 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Kankakee Terminal (BETKK) Tank 151 – OOS Corr Insp & Refurb | Item | Open | MCAP | BETKK00M2201 | Maintenance Framework | 1938080 | Roth, Aaron | West | 6. Operational | Defined | Tanks | 2353 |  | 13000 | 2353.34 | 2353 | 0 | Green |  |  |  | 2353 |  |  | 275000 |  |  | 275000 | Phase | 275000 | 340265 | 13000 | 353265 | No | Green | 2022-04-01 | 2022-01-11 | 2022-01-11 | 2022-01-03 | 2022-10-28 |  |  |  | 2252 | 101.34 | [15 empty] | 13000 | 10.31 - done | 2022-10-31 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Argo | BETKK - BET KANKAKEE TERMINAL |  | 2353 | 0 |  |  | 337912 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41276 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Kankakee Terminal (BETKK) Tank 152 Support Project | Item | Open | MEXP | BETKK00E2201 | Maintenance Framework | 1937989 | Roth, Aaron | West | 6. Operational | Defined | Tank Outage | 16271 |  |  | 16270.54 | 16271 | 0 | Green |  |  |  | 16271 |  |  | 98000 |  |  | 98000 | Phase | 98000 | 132148 |  | 132148 | No | Green | 2022-02-01 | 2022-01-11 | 2022-01-11 | 2022-09-26 | 2022-11-18 |  |  | 353.55 | 15905.35 | 11.64 | [16 empty] | 10.31 - done | 2022-10-31 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Argo | BETKK - BET KANKAKEE TERMINAL |  | 16271 | 0 |  |  | 115878 |  | Stine, Carlton | Stanisich, Carla D. |  |  | 1 | 41277 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Kankakee Terminal Security Video System Upgrade | Item | Open | MCAP | BETKK00M2203 | Maintenance Framework | 2023931 | Fink, Ryan | West | 6. Operational | Defined | Security & Cameras | 18862 | 2000 |  | 20862.05 | 20697 | 165 | Yellow | 1000 |  | 1000 | 19862 |  |  | 82000 |  |  | 82000 | Full | 82000 | 69535 | 2000 | 71535 | No | Green | 2022-10-01 | 2022-09-29 | 2022-09-29 | 2022-11-11 | 2023-03-31 |  |  | 711.18 | 9993.02 | 993.22 | 7164.63 | 2000 | 2000 | 5165 | Red |  |  | 500 | 1500 | [7 empty] | 4/28 RRF - Convergint NVR commissioning done, Accrue $6583. Intercom pending test (Buckeye internal) Contingency moved to June, and close. EAC $72k 4/6 RRF - Convergint delay on installing licenses. move forecast out due to unknown return date. EAC $71k 4-3-2023 - MNH - Added $8K in May to reflect EAC of $71K per Ryan's comments from March. 3/1 RRF - Convergint had license problem, delay commissioning to March. Accrue 7185 for parts. EAC $71k. 2/2 RRF - Convergint delayed, install now 2/6 1/4/23 RRF - NVR install Jan, Intercom in Q1 and close 12/2 RRF - Intercom added 11/29 RRF - Cameras installed, Pending NVR install in Jan due to material delay. $11k for intercom in March if not done early. 10/31 RRF - started work, stalled due to no cameras 9/30 RRF - AFE approved, POs submitted 9/28 RRF - Elec contractor confirmed finish in 2022, AFE submitted, forecast updated for 2022 completion. 3k cont and 2k allocation not forecast. 9/23 RRF - AFE submitted, forecast worst case for 2023 install. 9/2 RRF - Delay in response for electrical quotes, none received to date, have now asked other vendors, and estimate is in progress. Have cam quote, cams 1 day lead, NVR 8 week. 8/2 RRF - Pending quotes for AFE, moved out 1 month 7/11 RRF - AFE to be ready in July 6/22/2022 RRF - Initial draft AFE estimate | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Argo | BETKK - BET KANKAKEE TERMINAL |  | 11697 | 9165 |  |  | 50673 |  | Clark, Chris | Hoekstra, Matt | N/A |  | 1 | 31391 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Other Programs
Kankakee VRU Vacuum pump replacement | Item | Open | MCAP | BETKK00M2301 | Exempt | 2074272 | Gardner, Travis | West | 6. Operational | Emergent | Vapor Management | 17642 |  |  | 17642.49 | 17642 | 0 | Green |  | 19518 | 19518 | -1876 |  |  | 19518 |  |  | 19518 | Full | 19518 | 17642 |  | 17642 | No | Green | 2023-02-01 | 2023-02-09 | 2023-02-09 | 2023-02-28 | 2023-02-28 |  |  |  | 17000 | 642.49 | [16 empty] | 3/1/2023 - work completed and reclass submitted on 3/1. 2/2/2023 - emergent Vacuum pump replacement | 2023-03-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Argo | BETKK - BET KANKAKEE TERMINAL |  | 17642 | 0 |  |  |  |  | Karl, Marissa | Hoekstra, Matt |  |  | 1 | 46573 |  | Gardner, Travis | Independent | Aqua | 2023-02-02 | Other Programs
Kouts Switch Gear Engineering Study | Item | Open | MEXP | KZ00000E2301 | Exempt | 2084406 | Grinder, Mark | West | 6. Operational | Defined | Electrical | 13100 |  |  | 13100 | 13100 | 0 | Green | 10000 |  | 10000 | 3100 |  |  | 14850 |  |  | 14850 | Full | 14850 | 13100 |  | 13100 | No | Green | 2023-03-01 | 2023-02-02 | 2023-02-02 | 2023-06-30 | 2023-03-31 |  |  |  |  | 13100 | 0 |  |  | 0 | Green | [11 empty] | 4-27-2023 - This project has been completed. 3-23-2023 - Should be completed in March 3-01-2023 - Should be completed in March 2-02-2023 - The AFE for this project in in the approval process, PO's will be written once budgets are loaded. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Michiana | KZ - KOUTS |  | 13100 | 0 |  |  |  |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 45243 |  | Guest, ProSight | Independent | Aqua | 2022-08-24 | Other Programs
Kouts Valve Site Easement and Road | Item | Open | MCAP | KZ001LKM2101 | Exempt | 1855222 | Smith, Kyle | West | 7. Closed | Defined | West | 3161 |  |  | 3161.13 | 3161 | 0 | Green |  |  |  | 3161 |  |  | 114000 |  |  | 114000 | Full | 114000 | 122963 |  | 122963 | No | Green | 2021-09-01 | 2021-05-28 | 2021-05-28 | 2021-07-30 | 2021-10-31 |  |  | 3025 | 136.13 | [17 empty] | 12/23/22 - PO and WO closed - ready to be closed by accounting. 3/2/22 - forecasted in Janaury issed accrual. 1-3-22 Work completed | 2022-12-23 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | KZ001LK - KOUTS TO LAKETON |  | 3161 | 0 |  |  | 30636 |  | Gardner, Travis |  |  |  | 1 | 37527 |  | Guest, ProSight | Independent | Aqua | 2020-08-06 | Other Programs
KZ001LK Aldine Block Valve EFRD Installation | Item | Open | MCAP | KZ001LKM2203 | Maintenance Framework | 1980744 | Parker, Brian | West | 6. Operational | Defined | Valves | 27259 | 8000 |  | 35258.95 | 31101 | 4158 | Red |  |  |  | 35259 |  |  | 62000 | 149000 |  | 211000 | Phase | 211000 | 160426 | 8000 | 168426 | No | Green | 2022-05-01 | 2022-05-16 | 2022-05-16 | 2022-12-31 | 2023-04-13 |  |  | 7582.86 | 12117.63 | 3400.64 | 4157.82 |  |  | 4158 | Red |  |  |  | 8000 | [7 empty] | 4/29/23 - paid RA and Vander Werf Electric invoices in Apr. Waiting on as-builts from RA - Jun FCST is for networking hardware (still waiting on costs to post) and completing as-builts. EAC is at 168,273. 4/14/23 - operational on Apr 13th - still waiting on networking hardware charges to post (have them FCST for Jun). 3/31/23 - Re-accruing 5,000 for Rockwell and 6,900 for Vander Werf. Looks like Steve has the valve commissioning scheduled for Apr 13th. Moving 8,000 FCST for comms equipment cost out to Jun. 2/28/23 - re-accruing 7,500 for Rockwell and accruing 6,900 for Vander Werf Electric. Last update I had is that Steve was needing wiring connections for actuator and Joe was going to provide these. After actuator is wired, need to schedule pipeline downtown to set limits and check operation locally and back to SCADA. Also waiting on details of cost for communications equipment. Have 8,000+ FCST for this but this could take months to see this post. 2/3/23 - paid Vander Werf invoice in Jan, re-accruing 20,000 for Rockwell. Processed CO for Vander Werf to install Dairyland isolator. Looks like we will also be installing 4G primary with VSAT backup. Shifting some costs out a little longer since I currently do not have an install date for communications equipment. 1/5/23 - Re-accrual of 30,000 for Vander Werf Electric and accruing 20,000 for Rockwell Automation - just waiting for NIPSCO to schedule electrical install and delivery of delayed SS Enclosure for PLC. 11/28/22 - Metro Fence is done and Vander Werf is probably 80% complete so will accrue that for Nov. Electrical inspection by NIPSCO was completed on the 14th and Vander Werf will be back after the Holidays to finish up their work after NIPSCO completes their portion of the new power service to the meter. Delay in the PLC enclosure from RA will push the remaining work out into 2023. Need to PO issued for Dairyland Isolator installation this month for Jan/Feb install. 11/1/22 -Work delayed to 11/7 due to lead time of concrete. Sight draft of 12,000 posted in Oct and paid 2 invoices to RA totaling 8,634.23 10/10/22 - var is due to missing new easement payment - mtg with landowner was pushed out to Aug 29th. Work will not start until Oct 31st at request of landowner. Actuator should be received in the 2nd half of Oct and Vander Werf should be completed in mid-Nov. Expect RA work to be completed in Dec andactuator to be installed in Nov and commissioned in Dec. New fence will be installed just as soon as electrical main feed and rack has been installed. Accruing 3,072.19 for Rockwell Automation. 9/1/22 - paid TAS invoice in Aug, Turfbrothers invoice in Aug, and paid for PLC material from RA in Aug. Dropping accrual for TAS. Have Phase II AFE ready to go with an estimated cost of 30,000 for NIPSCO and 15,000 for new easement. Just waiting for Sole Source to be approved for Vander Werf then their PO will be issued for the electrical work. Also had call in Aug to discuss comm's back to SCADA. Delivery of new actuator is 2nd half of Oct. Currently waiting on ROW agreement with landowner to expand the fencing. Need to get PO issued for 3rd Party Insp for 3 weeks. 8/1/22 - re-accruing 9,375 for TAS,expect this total cost to go down but waiting on final, additional easement costs plus electrical contractor costs before making adjustments. 7/2/22 - accruing 9,375 for TAS. Turfbrothers should get the area cleaned up in Jul. Working on plan/profile view of expanded site so we can get new easement negotiated. 5/31/22 -accruing 25% of PO to TAS for May. Should receive actuator around late Oct. Working on legal drawing for additional easement acquisition to expand fencing. 5/16/22 - Phase I AFE approved, will get PO's issued to TAS and Actuation Group. 5/3/22 - I have TAS proposal for Eng & Design, just waiting on quote for new actuator from Actuation Group so I can submit Phase I AFE,hopefully in May. 4/5/22 - have meeting scheduled on-site for Apr 18 to get started on ROW easement and fencing requirements for new footprint. Will probably submit a Phase I AFE after the meeting to get started on procuring long lead items and start Eng & Design. 2/18/22 - moved Apr FCST to May for Eng & Design. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | KZ001LK - KOUTS TO LAKETON |  | 23101 | 12158 |  |  | 133167 |  | Oey, Alex | Baldwin, T. Andy |  |  | 1 | 37395 |  | Guest, ProSight | Independent | Aqua | 2020-07-31 | Other Programs
LA - L331 TEST STATION REPAIRS | Item | Open | MEXP | LA00000E2302 | Exempt | 2094186 | Brown, Jeff | West | 6. Operational | Defined | Cathodic Protection | 29127 |  |  | 29127 | 30000 | -873 | Yellow | 30000 |  | 30000 | -873 |  |  | 30583 |  |  | 30583 | Full | 30583 | 29127 |  | 29127 | No | Green | 2023-03-01 | 2023-03-07 | 2023-03-07 | 2023-06-30 | 2023-05-01 |  |  |  |  | 15000 | 14127 | 15000 | 15000 | -873 | Yellow |  | Savings from AFE Estimate | [9 empty] | 5-1-23 Project Complete. All invoices have been received and processed in ADP. 4-3-23 PROJECT 50% COMPLETE 3-2-23 AFE IS IN ROUTING | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Corrosion |  | Lima Pipelines | LA - LIMA STATION |  | 15000 | 14127 |  |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45286 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Int - Planned Corr & FI
LA402XB - Digs from 2022 UCD ILI | Item | Open | MCAP | LA402XXM2201 | Exempt | 2052298, 2051861, 2051862, 2051863, 2051864, 2051865 | Burns, Richard | West | 3. Active | Defined | Pipeline Digs | 694248 | 150000 |  | 844247.72 | 756505 | 87742 | Red |  | 775127 | 775127 | 69121 |  |  | 400381 | 774746 |  | 1175127 | Full | 1175127 | 694799 | 150000 | 844799 | No | Green | 2022-12-01 | 2023-01-19 | 2023-01-19 | 2023-06-04 | 2023-05-26 |  |  | 158991.6 | 147715.41 | 169798.39 | 217742.32 | 160000 | 160000 | 57742 | Red |  | WorkAhead of Schedule | 150000 | [8 empty] | 5/1/23 - variance is from getting an extra dig completed by another crew waiting to go to another project. 4/3/23 - variance accrued. Integrity cancelled 12 digs. Adjusted forecast accordingly. 3/8/23 - adjusted March forecast because of other dig projects schedule changes. 3/7/23 - added forecast for May and June. 3/1/23 - variance accrued. Adjusted March forecast down so crew can go work on 211 immediate dig. 2/1/23 - variance accrued. 1/3/23 - 7 Immediate digs and 24 BPL Other digs (25 dig sites) issued. Started today. Forecasted accordingly. Variance is internal labor. 11/1/22 - no change 9/28/22 - no digs issues yet. Pushed forecast to Q2 2023. 9/1/22 - no digs issued yet. Pushed forecast out. 8/1/22 - still no digs issued. 7/1/22 - no digs issued yet. 2/2/22 - no digs issued yet; expected after the June ILI runs. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Lima Pipelines | LA402XX - LIMA-IND S/L/HUNTINGTON W |  | 476505 | 367742 |  |  | 552 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 41024 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
LA402XX - DEFIANCE TRAIL RECTIFIER REPLACEMENT | Item | Candidate | MCAP |  | Exempt |  | Brown, Jeff | West | 2. Pending AFE |  | Cathodic Protection |  | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 | [9 empty] | 30000 | 30000 | No | Green | 2023-11-01 |  |  |  | 2023-06-30 | [18 empty] | 30000 |  |  | 5-1-23 No change in status. 3-2-23 HOLDING ONTO THIS PRJECT YET | 2023-05-01 |  |  | West | Pipelines and Terminals | Integrity |  | Lima Pipelines | LA402XX - LIMA-IND S/L/HUNTINGTON W |  |  | 0 |  | 30000 |  |  | Geib, Rob |  |  |  | 1 | 45282 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Int - Planned Corr & FI
LA402XX DEFIANCE TRAIL RECTIFIER REPLACEMENT | Item | Open | MCAP | LA402XXM2301 | Exempt | 2085667 | Brown, Jeff | West | 3. Active | Defined | Cathodic Protection |  | 13000 |  | 13000 | 13000 | 0 | Green | 11000 |  | 11000 | 2000 |  |  | 14910 |  |  | 14910 | Full | 14910 |  | 13000 | 13000 | No | Green | 2023-05-01 | 2023-02-21 | 2023-02-21 | 2023-12-31 | 2023-05-31 | [6 empty] | 5000 | 5000 | -5000 | Red |  | Contractor/Vendor Issue | 5000 | 8000 | [7 empty] | 5-1-23 Confirmed ship date of May 12, 2023. Readjusted forecast for delivery. 4-3-23 RECTIFIER ORDERED MATERIAL WAS PLANNED FOR MARCH BUT DUE TO EXTENDED LEAD TIME, FORECASTING NEEDS MOVED TO APRIL. 3-2-23 AFE APPROVED-ORDER RECTIFIER-02-03-23 - MNH - AFE is routed | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Lima Pipelines | LA402XX - LIMA-IND S/L/HUNTINGTON W |  |  | 13000 |  |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45364 |  | Gardner, Travis | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Lake George Electrical Building HVAC Upgrades | Item | Open | MCAP | KG00000M2301 | Exempt | 2075759 | Parker, Brian | West | 7. Closed | Defined | West | 16087 |  |  | 16086.73 | 16087 | 0 | Green | 20000 |  | 20000 | -3913 |  |  | 20059 |  | 15941 | 36000 | Full | 36000 | 16087 |  | 16087 | No | Green | 2023-02-01 | 2023-01-17 | 2023-01-17 | 2023-04-28 | 2023-02-28 |  |  |  | 15394 | 692.73 | [16 empty] | 5/6/23 - ready to be closed out in JDE by accounting. 2/28/23 - var is due to work being completed in Feb ahead of schedule. Will close out next month. 2/3/23 - PO issued to Hayes Mechanical for 13,339 on Jan 20th. | 2023-05-06 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | E. Chicago Terminals | KG - LAKE GEORGE STATION |  | 16087 | 0 |  |  |  |  | Gardner, Travis | Janesy, Ryan |  |  | 1 | 45113 |  | Guest, ProSight | Independent | Aqua | 2022-08-19 | Other Programs
Leak Detection - Clermont 2023 | Item | Candidate | MCAP |  | Maintenance Framework |  | Smith, Kyle | West | 2. Pending AFE |  | Leak Detection |  | 500000 |  | 500000 | 500000 | 0 | Green | 500000 |  | 500000 | 0 | [9 empty] | 500000 | 500000 | No | Green | 2023-07-01 |  |  |  | 2023-09-30 | [14 empty] | 200000 | 150000 | 150000 |  |  |  |  | 4/28/23 Completting bids to submit AFE | 2023-04-28 |  |  | West | Pipelines and Terminals | Integrity |  | Indianapolis | CL - CLERMONT TERMINAL |  |  | 0 | 500000 |  |  |  | Guenther, Steve |  |  |  | 1 | 38952 |  | Guest, ProSight | Independent | Aqua | 2020-10-29 | Leak Detection
Leak Detection - DB999TJ-TJ999A2 Dearborn to Total Junction to Shell | Item | Candidate | MCAP |  | Maintenance Framework |  | Hassan, Mohammad | West | 2. Pending AFE |  | Leak Detection |  | 380000 |  | 380000 | 380000 | 0 | Green | 380000 |  | 380000 | 0 | [9 empty] | 380000 | 380000 | No | Green | 2023-06-01 |  |  |  | 2023-09-30 | [13 empty] | 30000 | 30000 | 100000 | 120000 | 100000 |  |  |  | 05-02-2023 - MNH - Due to ORC23B01 - Ohio Refining Co Transition Emergent Project, this project AFE completion is delayed. Moving forecast out a month. 03-29-2023 - MNH - Due to ORC23B01 - Ohio Refining Co Transition Emergent Project, this project AFE completion is delayed. Moving forecast out a month. 02-28-2023 - MNH - Will plan a site visit in March followed by submitting Phase 1 AFE. 02-01-2023 - MNH - Scope development underway. 01-03-2023 - MNH - Will start looking at scope of work this month. 12-1-2022 - MNH - Will start looking at scope of work next month. | 2023-05-02 |  |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | TJ - TOTAL JCT |  |  | 30000 | 250000 | 100000 |  |  | Guenther, Steve |  | N/A |  | 1 | 27313 |  | Guest, ProSight | Independent | Aqua | 2017-12-19 | Leak Detection
Leak Detection - DG999A1 - Eldorado to PPC | Item | Open | MCAP | DG999A1M2101 | Maintenance Framework | 1878587 | Hassan, Mohammad | West | 3. Active | Defined | Leak Detection | 54691 | 39300 | 0 | 93990.56 | 97344 | -3354 | Yellow | 70000 |  | 70000 | 23991 |  |  | 89000 | 173000 |  | 362000 | Full | 362000 | 358094 | 39300 | 397394 | No | Green | 2021-08-01 | 2021-08-30 | 2021-08-30 | 2022-10-31 | 2023-06-30 |  |  | 13821.24 | 24452.49 | 5070.38 | 11346.45 |  |  | 11346 | Red |  | WorkAhead of Schedule | 3300 | 20000 | 16000 | [5 empty] | 0 | 05-02-2023 - MNH - Some work done ahead of schedule and working on supplemental AFE & ECO next. Plan on completing it this week. Supplemental AFE to be around $431K. 04-20-2023 - MNH - Working on supplemental AFE & ECO next. Plan on completing it during week of May 1st. Supplemental AFE to be around $431K. 04-01-2023 - MNH - Onsite SCADA checkout was done in February, but more work is needed including piping changes that were not in original scope are needed to accommodate LHT requests. Also, local Tech labor was double what was budgeted in the AFE so AFE contingency is used up. We will finalize additional design & costs and work on the changes next. Once that is done, leakwarn testing can begin. Project EAC now at 398K, but a supplemental AFE will be needed to fully complete the additional scope and get the final EAC. 03-01-2023 - MNH - Onsite SCADA checkout was done last month, but more work is needed including piping changes that were not in original scope are needed to accommodate LHT requests. Also, local Tech labor was double what was budgeted in the AFE so AFE contingency is used up. We will finalize additional design & costs and work on the changes next. Once that is done, leakwarn testing can begin. Project EAC now at 398K, but a supplemental AFE may be needed to fully complete the additional scope. 02-01-2023 - MNH - More work done last month and onsite checkout with SCADA scheduled for this month. Some piping changes are needed to accomodate LHT requests. We will finalize that design and work on the changes next. Once that is done, leakwarn testing can begin. Project EAC still at 362K. 01-03-2023 - MNH - Some checkout work done last month. Will continue working with Tech & SCADA to get the rest of PLC checked out this quarter following by leakwarn testing. Project EAC still at $362K. Reducing 2023 forecast to account for more spends in December. 12-01-2022 - MNH - Planning on point to point checkout (round 1) this month.Project EAC still at $362K. 11-01-2022 - MNH - Construction started last month slightly ahead of schedule and will continue this month. Project EAC at $362K. 10-04-2022 - MNH - Still waiting on electrical contractor to give us start date based on some material pending. Project EAC at $362K. 09-22-2022- MNH - Moving some money from November into 2023 as contractor unsure about delivery dates of some material. 09-12-2022 - MNH - Project EAC at $362K per Phase 3 AFE. 09-01-2022 - MNH - We received two bids and will now plan on getting Full AFE completed next week. PLC parts have not been received still. so moving some forecast from September into October to account for delays. Full project EAC around $358K. Also adding some money in 2023 for possible commissioning delays. 08-02-2022 - MNH - A few revision delayedcompletion of Electrical design so will work with supply chain this month to get electrical work bid out. Mechanical work is still 50% done and other will be done this month. Project behind schedule so adjusting rest of forecast. Full project EAC around $358K. PLC parts delayed till end of Sep. 07-05-2022 - MNH - Electrical design is complete and will work with supply chain next to get electrical work bid out. Material delays caused June forecast to be missed by $5K. Mechanical work is 50% doneand other will be done this month. Project behind schedule so adjusting rest of forecast. Full project EAC around $358K. 06-01-2022 - MNH - Electrical design underway and planning on completing mechanical pipe modifications this month. Full project EAC around $358K. 04-29-2022 - MNH - Phase II AFE approved this month and electrical design underway. Will plan on procuring some more material in May followed by Mechanical work. Full phase EAC around $358K. 04-04-2022 - MNH - Delay in Actuators will cause the forecast to move out another month but we aremaking good progress with electrical design completion but will need to route another Phased AFE to keep electrical design going. 03-02-2022 - MNH - Further delay has been anticipated for PLC parts. New ship date 9/1. Unless we use parts from Toledo Leakwarn projects, this project will be delayed into Q4 of 2022. Moving $75K in Q4 from Q2. Project EAC now at $350K due to added scope needed at Eldorado Terminal. 01-27-2022 - MNH - Delay in PLC cabinet due to PLC parts long lead times and need to install actuators on a few valves which have 16 week lead time.This will cause project electrical work to shift by three months.We will still try to complete the mechanical work in March. Project Phase II AFE to be submitted next month. Project Budget still at $320K. 01-04-2022 - MNH - Working with supply chain this month to get quotes from contractors. Meter has been received, PLC cabinet to be completed this month. Some items do have long lead times still. Project Phase II AFE to be submitted by end of this month or early next. Project Budget still at $320K. 12-02-2021 - MNH - Project mechanical & electrical design complete. Getting quotes next. 11-02-2021 - MNH - Project mechanical design almostcomplete. Electrical design underway. 10-05-2021 - MNH - Meter has been ordered and PT's & TT's to be ordered next. Due to resource limitations Sep was underspent and $30K from Q4 2021 moved to Q3 of 2022. 09-02-2021 - MNH - Phase 1 approved and design underway. Due to delay in getting new PLC components, commissioning work will most likely go into 2022. Also we may need to upgrade the back pressure CV at PPC which has a long lead time thatwill push this project into2022. $220K moved into 2022 Q1 & Q2. 08-02-2021 - MNH - Project just handed over to me, initial design complete and Phase 1 should be submitted this month. September forecast moved into Q4. 7/2/21 AFE to be submitted shortly. Materials to be ordered in summer for early Fall construction. Reduced forecast by $100k based on modified scope, 6/2/21 AFE to be submitted shortly. Materials tobe ordered in summer for early Fall construction. | 2023-05-02 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Duncansville | DG999A1 - ELDORADO TO PPC |  | 43344 | 34646 | 16000 |  | 250466 |  | Guenther, Steve | Guenther, Steve | N/A |  | 1 | 27307 |  | Guest, ProSight | Independent | Aqua | 2017-12-19 | Leak Detection
Leak Detection - DS999A1 DS to Buckeye Junction CS Reversal | Item | Open | MCAP | DS999A1M2101 | Maintenance Framework | 1703468 | Hassan, Mohammad | West | 3. Active | Defined | Leak Detection | 6331 | 4750 |  | 11080.81 | 10679 | 402 | Yellow | 3500 |  | 3500 | 7581 |  |  | 18000 | 22000 |  | 40000 | Full | 40000 | 36811 | 4750 | 41561 | No | Green | 2021-06-01 | 2021-06-08 | 2021-06-08 | 2021-10-15 | 2023-06-30 |  |  | 140.36 | 143.14 | 5645.71 | 401.6 |  |  | 402 | Red |  |  | 4000 | 750 | [7 empty] | 05-02-2023 - MNH - All work on schedule. Project EAC still at $41K now. 04-03-2023 - MNH - All service quotes under TO999A1M2101 now received. Project EAC still at $41K now. 03-01-2023 - MNH - Further delay due to ARSEAL & Tech availability so design still 90% complete. All but one service quote under TO999A1M2101 received. Project EAC still at $40K. 02-01-2023 - MNH - 90% of design is complete and service qoutes under TO999A1M2101 received. Project EAC still at $40K. 01-03-2023 - MNH - Full design work to be completed this month along with TO999A1M2101 project. Project EAC still at $40K. 12-01-2022 - MNH - Some design work got completed and some to continue this month. Project EAC still at $40K. 11-03-2022 - MNH - Project Design for this project & TO999A1M2101 project is underway but behind schedule from the vendor. Project EAC at $40K. Moving $6K into 2023. 10-04-2022 - MNH - Project Design for TO999A1M2101 project is underway now. Project EAC at $40K. 09-01-2022 - MNH - Project Design for TO999A1M2101 project is behind due to contractor schedule & resource shortage. Moving forecast out a month. Adding some forecast into 2023 to account for possible delays. 08-02-2022 - MNH - Project Design for TO999A1M2101 project is behind due to contractor schedule & resource shortage. Moving forecast out a month. 07-05-2022 - MNH - Project Design is underway that will be completed with the TO999A1M2101 project. 06-01-2022 - MNH - Final AFE approved last month and design is underway that will be completed with the TO999A1M2101 project. 04-29-2022 - MNH - Planning on submitting Phase II AFE in May. 04-04-2022 - MNH - We finally got a response from Delta Terminal owner and are resuming with the project. Some engineering work completed ahead of schedule. 03-02-2022 - MNH - Moving project forecast out two month as this project is dependent on TO999A1M2101 project which is having delays due to no response from Delta Terminal owner. 01-27-2022 - MNH - Project mechanical design to be completed by end of this month. Electrical design to follow. EAC at $40K. Phase II planned to be submitted next month. 01-04-2022 - MNH - Further delay in project design completion due to engineering contractors availability. Design now to be completed this month. 12-02-2021 - MNH - Delay inproject design completion due to engineering contractors availability. Design to be completed this month. 11-02-2021 - MNH- Project design to be completed this month. 10-05-2021 - MNH - Due to PLC parts delay and this projects dependency on TO999A1, project commissioning is moved into Q1 & Q2 of next year. 09-02-2021 - MNH - Project design underway but behind. Delay in PLC parts may push this project into 2022, but will know that in a month. August missed forecast moved into September. 08-02-2021 - MNH - Project engineering & design underway but behind due to dependency on TO999A1 project. September forecast moved intoOctober & November. 07-01-2021 - MNH - Project engineering & design underway. 06-02-2021 - MNH - Phase 1 AFE to be submitted this week or next. 05-04-2021 - MNH - Scope/AFE development to be completed this month. 04-01-2021 - MNH - Scope/AFE development to start later this month or early May. 02-01-2021 - MNH - Forecast pushed out 3 months per Program Manager's direction. | 2023-05-02 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Toledo | DS999A1 - TOLEDO TO NORCO 8IN REVERSAL |  | 5929 | 5152 |  |  | 18767 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 37760 |  | Guest, ProSight | Independent | Aqua | 2020-08-12 | Leak Detection
Leak Detection - DS999A4 DS to MAC | Item | Open | MCAP | DS999A4M2101 | Maintenance Framework | 1703476 | Hassan, Mohammad | West | 4. On-Hold | Defined | Leak Detection | 869 | 11900 |  | 12768.73 | 12769 | 0 | Green | 11000 |  | 11000 | 1769 |  |  | 75000 | 301000 |  | 376000 | Full | 376000 | 364116 | 11900 | 376016 | No | Green | 2021-07-01 | 2021-07-21 | 2021-07-21 | 2022-06-30 | 2023-06-30 |  |  | 270.48 | 598.25 | 0 | 0 |  |  | 0 | Green |  |  |  |  | 6900 | 5000 | [5 empty] | 05-02-2023 - MNH - Project still on hold due to refinery shutdown. Project EAC still at $376K. Moving forecast out a month. 04-03-2023 - MNH - Project still on hold due to refinery shutdown. Project EAC still at $376K. Moving forecast out a month. 03-01-2023 - MNH - Project still on hold due to refinery shutdown. Project EAC still at $376K. Moving forecast out a month. 02-01-2023 - MNH - Project on hold due to refinery shutdown. Project EAC still at $376K. 01-15-2023 - MNH - Putting project on hold due to refinery shutdown. 01-03-2023 - MNH - Cable tray work complete at DS as scheduled, but due to refinary shutdown final commissioning to be delayed until Q2 of 2023. Moving forecast out a month. Project EAC at $376K. 12-01-2022 - MNH - Cable tray work underway at DS as scheduled, but due to refinary shutdown final commissioning to be delayed until 2023. Adding $5K from december into April 2023. Project EAC at $376K. 11-03-2022 - MNH - Completed some PLC checkout at Marathon ahead of scheduled. Cable tray work at DS end of the line to start this month. Project EAC still at $376K. 10-03-2022 - MNH - Some material was received last month ahead of schedule and some to arrive this week. Planning on PLC checkout at Marathon this month. Project EAC still at $376K. Cable tray work delayed until November. 09-13-2022 - MNH - Putting project on hold until we receive final PLC components. Project EAC at $376K.09-01-2022 - MNH - We are now at a stand still until we get PLC parts. Also cable tray material for work on this project at DS got delayed till end of October. Moving forecast out a month and adding some money in 2023 for possible commissioning delays.08-02-2022 - MNH - Electrical & Civil work underway and more got done than expected. Final commissioning still dependent on PLC parts to arrive in September or October. Adjusting some forecast based on current project schedule.07-05-2022 - MNH - Electrical & Civil work behind schedule due to contractor delays so June forecast missed by $15K. Final commissioning still dependent on PLC parts to arrive in September. Adjusted some forecast based on current project schedule.06-01-2022 - MNH - Mechanical work complete and ahead of schedule, and will now plan is to completing electrical/civil work over next two months. Final commissioning still dependent on PLC parts to arrive in September. Adjusted some forecast based on current project schedule.04-29-2022 - MNH - Moving $68K from November to forecast for DS999TOM2101 project as it would need more money.04-04-2022 - MNH - Phase II AFE approved at $376K. Total project budget is actually $444K so $68K being moved to Q4 that can be used by another leak detection project. Also PLC parts are delayed till September which will cause commissioning to go into Q4. Moving $30K in October to accommodate that. Electrical design is complete.03-02-2022 - MNH - Phase II AFE submitted but readiness review identified additional scope. New AFE to be submitted this month and should be around $353K. Total project budget is actually $444K.01-27-2022 - MNH - Phase II AFE tobe submitted by Feb 15th. Current project budget is $459K but Phase II AFE should be well under this budget.01-04-2022 - MNH - Phase II AFE to be summited this month. Meter has been received. Current project budget is $459K but Phase II AFE should be well under this budget.12-02-2021- MNH - Delay in delivery of meter and erroneous accrual last month caused missed forecast. PT & TT have been received, working on submitting Phase II AFE next. Current project budget is $459K.11-02-2021 - MNH - PT & TT ordered. Electrical design underway to be completed this month. Phase II AFE to be submitted this month.10-05-2021 - MNH - Mechanical Design is complete and Meter ordered. PT & TT to be ordered next. Phase II AFE to be submitted next.09-02-2021 - MNH - Design& Engineering underway. Delay is automation components may push some of the 2021 forecast into 2022.08-02-2021 - MNH - Phase 1 AFE approved and design & engineering underway but a little behind.07-01-2021 - MNH - Phase 1 AFE to be submitted this week.06-15-2021 - MNH -Moved some cost from August to September.06-02-2021 - MNH - Phase 1 AFE development underway and should be summited this month.04-01-2021 - MNH - Scope/AFE development to start in May.04-01-2021 - MNH - Scope/AFE development to start in May.02-01-2021 - MNH - Forecast pushed out 3 months per Program Manager's direction and for now Q4 forecast for construction activity moved to Q2 of 2022 due to winter weather. | 2023-05-02 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Toledo | DS999A4 - TOLEDO TO SEAMAN TO MARATHON |  | 869 | 0 | 11900 |  | 278682 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 37768 |  | Guest, ProSight | Independent | Aqua | 2020-08-13 | Leak Detection
Leak Detection - DS999A5 - BP Swamp Dock | Item | Open | MCAP | DS999A5M2101 | Exempt | 1703474 | Hassan, Mohammad | West | 4. On-Hold | Unplanned | Leak Detection | 627 | 500 |  | 1127 | 952 | 175 | Red |  |  |  | 1127 |  |  | 34000 | 73000 |  | 107000 | Full | 107000 | 106515 | 500 | 107015 | No | Green | 2021-04-01 | 2021-04-13 | 2021-04-13 | 2021-11-15 | 2023-06-30 |  |  | 452 | 0 | 0 | 175 |  |  | 175 | Red |  |  | 500 | [8 empty] | 05-02-2023 - MNH - Project still on hold due to refinery shutdown that is preventing further leakwarn testing. Project EAC at $107K. 04-03-2023 - MNH - Project still on hold due to refinery shutdown that is preventing further leakwarn testing. Project EAC at $107K. 03-01-2023 - MNH - Project still on hold due to refinery shutdown that is preventing further leakwarn testing. Project EAC at $107K. 02-01-2023 - MNH - Project on hold due to refinery shutdown that is preventing further leakwarn testing. Project EAC still at $107K. 01-15-2023 - MNH - Putting project on hold due to refinery shutdown. 01-03-2023 - MNH - Due to Toledo refinery Shutdown & limited scheduled pipeline moves, testing with Ops & Leak detection is taking more time and this will continue into late Q1 or early Q2 of 2023. Project EAC at $107K. 12-01-2022 - MNH - Due to Toledo refinery Shutdown & limited scheduled pipeline moves, testing with Ops & Leak detection is taking more time and this will go into 2023. Moving December forecast of $1500 to Q1 2023. Project EAC at $107K now. 11-03-2022 - MNH - Due to Toledo refinery Shutdown & limited scheduled pipeline moves, testing with Ops & Leak detection is taking more time. Will continue to make progress over next few months. 10-03-2022 - MNH - Due to Toledo refinery Shutdown & limited scheduled pipeline moves, testing with Ops & Leak detection is taking more time. Will continue to make progress over next few months. 09-01-2022 - MNH - Due to limited scheduled pipeline moves, testing with Ops & Leak detection is taking more time. Will continue to make progress over next few months. 08-02-2022 - MNH - Due to limited limited scheduled pipeline moves, testing with Ops & Leak detection taking more time. Will continue to make progress over next few months. July variance due to reclass of charges from DS00000M2003. 07-06-2022 - MNH - SCADA group still working with local Ops in order to test each lineupthis month. Couldn't do much last month due to other projects that kept operations busy. 06-01-2022 - MNH - SCADA group working withlocal Ops in order to test each lineup this month. 04-29-2022 - MNH - No updates. SCADA/Leakwarn continues to run the model in thebackground. 04-04-2022 - MNH - SCADA/Leakwarn testing for each lineup is challenging due to pipeline usage and certain operational moves.Operational date moved to May 31st. 03-22-2022 - MNH - SCADA/Leakwarn testing for each lineup is challenging due to pipeline usage. Operational date moved to April 29th. 01-27-2022 - MNH - SCADA/Leakwarn testing for each lineup is challenging due to pipeline usage. Operational date move to march 31st and March forecast moved into Q2. 01-04-2022 - MNH - Project under SCADA testing now over next few weeks followed by moving into production at CC. New EAC at $100K due to cost savings. 12-02-2021 - MNH - Delay in getting CO to vendor due to ISN grade issue as well as material delivery delay and SCADA configuration delay will cause November underspent and will get thefinal commission of this project into January. EAC at $105.5K. 11-02-2021 - MNH - Project commissioning with SCADA happened last month and rest to be completed this month and next. $7500 in chargesdidn't get coded properly and will be reclassed to this project. Added missed October forecast in December. 10-04-2021 - MNH - Project Phase II approved and commissioning planned for this month and next. 09-02-2021 - MNH - Phase II AFE to be submitted this week. Forecast adjusted to reflect actual progress. $107K that was deferred from TO999A2 moved to Dec. 08-01-2021 - MNH - Project engineering is almost complete and waiting on automation proposal before submitting Phase II AFE this month. 07-01-2021 - MNH - Project engineering behind and will continue into this month. 06-01-2021 - MNH -Project engineering underway on track to be completed by end of this month. 05-03-2021 - MNH - Phase 1 AFE approved and project engineering underway. 04-01-2021 - MNH - Phase I Scope/AFE development for engineering & someprocurement underway and should be submitted soon. Phase II for complete project execution to be submitted later in Q2. TO999A2 project has been excluded and will not use the forecast that is currently in Q4. | 2023-05-02 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Toledo | DS - TOLEDO STATION |  | 452 | 675 |  |  | 19355 |  | Guenther, Steve | Bishop, Rick | N/A |  | 1 | 30161 |  | Guest, ProSight | Independent | Aqua | 2018-07-30 | Leak Detection
Leak Detection - DS999A6 - Toledo to BP 4 BP 10" | Item | Open | MCAP | DS999A6M2101 | Exempt | 1703477 | Hassan, Mohammad | West | 4. On-Hold | Defined | Leak Detection | 1597 | 18500 |  | 20097.27 | 30557 | -10460 | Red | 5000 |  | 5000 | 15097 |  |  | 40000 | 245000 |  | 285000 | Full | 285000 | 266591 | 18500 | 285091 | No | Green | 2021-04-01 | 2021-04-19 | 2021-04-19 | 2021-09-01 | 2023-07-28 |  |  | 339 | 1218.27 | 0 | 40 |  |  | 40 | Red |  |  |  | 12000 | 6500 | [6 empty] | 05-02-2023 - MNH - Final PLC commissining is complete. Now will work with leak detection team on testing the model. Project EAC now at $285K now. Also, refinery shutdown will affect leakwarn testing. Moving forecast out a month due to this delay. We may also not use some of contingency. 04-03-2023 - MNH - All parts are now here and we will complete project commissioning followed by leak detection testing. Project EAC still at $296K. Also, refinery shutdown will affect leakwarn testing. Moving forecast out a month due to delay in receiving PLC parts. 03-01-2023 - MNH - Some parts still remaining that should be receive this month now. ARSEAL also ordered wrong parts. Once we receive all parts, we will complete project commissioning followed by leak detection testing. Project EAC still at $296K. Moving forecast out a month due to delay in receiving PLC parts. Also, refinery shutdown will affect leakwarn testing. 02-01-2023 - MNH - Expecting PLC parts to arrive this month now. Once received we will complete project commissioning followed by leak detection testing. Project EAC still at $296K. Moving forecast out a month due to delay in receiving PLC parts. 01-03-2023 - MNH - Still waiting on some PLC parts to arrive so January work will most likely be moved into February 2023. Project will stay on hold until we get all the remaining PLC parts followed by final project commissioning. Project EAC still at $296K. Moving forecast out a month. Adding $7K from Q1 into Q2 of 2023. 12-01-2022 - MNH - Still waiting on some PLC parts to arrive so December work will most likely be moved into 2023. Project will stay on hold until we get all the remaining PLC parts followed by final project commissioning. Project EAC still at $296K. Moving forecast out a month. Adding $7K from December into March 2023. 11-03-2022 - MNH - Some PLC parts will arrive this month. Project will stay on hold until we get all the remaining PLC parts followed by final projectcommissioning. Project EAC still at $296K. Moving forecast out a month. Added $19K to 2023. 10-04-2022 - MNH - Still waiting on PLC parts and no date provided from the vendor. Project will stay on hold until we get the remaining PLC parts followed by final project commissioning. Moving forecast out a month. Project EAC still at $296K. 09-01-2022 - MNH - Project on hold until we get the remaining PLC parts this month or October followed by final project commissioning. Reducing Sep forecast by $10K & moving it into Q4 to account of material delays. Project EAC still at $296K. Adding some money in 2023 for possible commissioning delays. 08-02-2022 - MNH - Project on hold until we get the remaining PLC parts in September or October followed by final project commissioning. Due to higher than expected WM costs July actuals are higher than forecast and Project EAC now at $296K. Moving forecast out a bit due to furtherdelay on PLC parts. 07-06-2022 - MNH - Project on hold until we get the remaining PLC parts in September following by final project commissioning. Project EAC at $285K now. 06-01-2022 - MNH - Project on hold until we get the remaining PLC parts in September following by final project commissioning. 05-10-2022 - MNH - Putting project on hold as now we are waiting for PLC parts to arrive in September before we can complete this project. 05-04-2022 - MNH - Electrical work ahead of schedule. We are now waiting on PLC material to arrive later this year beforefinal commissioning can happen. Moving $10K from June into September. 04-04-2022 - MNH - Planning on starting electrical this month. Final commissioning will be delayed as PLC material is delayed till September. Moving $30K in September to accommodate that. 03-02-2022 - MNH - Mechanical work done in February and ahead of schedule. March/April/May Forecast reduced to reflect the extra spends in February. EAC at $290K due to extra purging work. 01-27-2022 - MNH - Mechanical fabrication complete and ahead of schedule. Planning on mechanical install in February. EAC at $285K. 01-04-2022 - MNH - Mechanical fabrication underway and ahead of schedule, meter received. Jan forecast reduced by $9K. Planning on mechanical work in February/March. EAC at $285K.. 12-02-2021 - MNH - Mechanical PO issued last monthand procurement underway, but a wrong accrual of $15K (whichshould be on another leak detection project) and delay in meter delivery is showing actuals to be underspent. Project EAC at $285K. 11-02-2021 - MNH - Minimum mechanical bid is above $50K so need to go through bidding it out through supply chain.This will likely push mechanical work into 2022. Moving $57K forecast into 2022 Q2. 10-27-2021 - MNH - Phase 2 AFE approved. Getting 2nd bid to avoid sole source will add some delay. Moved $35K into 2022. 10-15-2021 - MNH - Added $56K to the 2022 forecast to account for Phase 2 AFE cost of $285K.OPPMID 37764 budget/EAC will be reduced by $56K. 10-05-2021 - MNH - Project mechanical design is complete and bid from mechanical contractor back. Will work on PHASE II AFE next to get mechanical install and ordering material. 09-02-2021 - MNH - project mechanical design almost complete but automation material will cause delay. $20K from September moved into Q1 of 2022. 08-02-2021- MNH - Project engineering and design underway but behind. Pipe modifications are needed to add clamp-on meter which caused additional delay. Also material delay will push the forecast into Q4 and into Q2 of 2022 for commissioning. 07-01-2021 - MNH - Project engineering and design underway. 06-15-2021 - MNH - Moved $100k of forecast from 3rd Q to 4th Q as design may take bit longer and to give alittle more time for procurement delays. 06-01-2021 - MNH - Project engineering underway on track to be completed by end of this month. 05-03-2021 - MNH - Project design & engineering underway. 04-01-2021 - MNH - Phase I Scope/AFE development for engineering & some procurement underway and should be submitted soon. Phase II for complete project execution to be submitted later in Q2. | 2023-05-02 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Toledo | DS999A6 - TOLEDO TO BP OIL 10IN |  | 1557 | 12040 | 6500 |  | 177079 |  | Guenther, Steve | Bishop, Rick | N/A |  | 1 | 27308 |  | Guest, ProSight | Independent | Aqua | 2017-12-19 | Leak Detection
Leak Detection - DS999A7+A9 -Toledo to TX BP-1 & BP-2 | Item | Open | MCAP | DS999A7M2101 | Maintenance Framework | 1703467 | Hassan, Mohammad | West | 4. On-Hold | Unplanned | Leak Detection | 0 | 2500 |  | 2500 | 2500 | 0 | Green |  |  |  | 2500 |  |  | 32000 | 64000 |  | 96000 | Full | 96000 | 94329 | 2500 | 96829 | No | Green | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2021-08-31 | 2023-07-28 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | Green |  |  |  |  | 500 | 2000 | [5 empty] | 05-02-2023 - MNH - Project still on hold due to refinery shutdown that is preventing further leakwarn testing. Project EAC at $97K. Forecast moved out a month. 04-03-2023 - MNH - Project still on hold due to refinery shutdown that is preventing further leakwarn testing. Project EAC at $97K. Forecast moved out a month. 03-01-2023 - MNH - Project still on hold due to refinery shutdown that is preventing further leakwarn testing. Project EAC at $97K. Forecast moved out a month. 02-01-2023 - MNH - Project on hold due to refinery shutdown that is preventing further leakwarn testing. Project EAC at $97K. 01-15-2023 - MNH - Putting project on hold due to refinery shutdown. 01-03-2023 - MNH - Due to Toledo refinery Shutdown & limited scheduled pipeline moves, testing with Ops & Leak detection is taking more time and this will continue into late Q1 or early Q2 of 2023. Project EAC at $97K now. 12-01-2022 - MNH - Due to Toledo refinery Shutdown & limited scheduled pipeline moves, testing with Ops & Leak detection is taking more time and this will go into 2023. Moving December forecast of $1000 to Q1 2023. Project EAC at $96K now. 11-03-2022 - MNH - Due to Toledo refinery Shutdown & limited scheduled pipeline moves, testing with Ops & Leak detection is taking more time. Will continue to make progress over next few months. Oct missed forecast moved out a month. 10-04-2022 - MNH - Due to Toledo refinery Shutdown & limited scheduled pipeline moves, testing with Ops & Leak detection is taking more time. Will continue to make progress over next few months. Sep missed forecast moved out a month. 09-02-2022 - MNH - Due to limited scheduled pipeline moves, testing with Ops & Leak detection is taking more time. Will continue to make progress over next few months. 08-02-2022 - MNH - Due to limited limited scheduled pipeline moves, testing with Ops & Leak detection taking more time. Will continue to make progress over next few months.07-06-2022 - MNH - Due to Ops availability we are still planning on testing valve lineups with Ops & SCADA this month. 06-01-2022 - MNH - Same update as lastmonth plus working with Ops & SCADA to test all valve lineups this month. 05-04-2022 - MNH - We are making some PLC updates this month in order to continue to validate SCADA/Leakwarn testing for each lineup. We will try to move everything into CC by June/July. 04-04-2022 - MNH - SCADA/Leakwarn testing for each lineup ischallenging due to pipeline usage and certain operational moves. Operational date moved to May 31st. 03-22-2022 - MNH - SCADA/Leakwarn testing for each lineup is challenging due to pipeline usage. Operational date moved to April 29th and forecast adjusted accordingly. 01-27-2022 - MNH - SCADA/Leakwarn testing for each lineup is challenging due to pipeline usage. Operational date move to march 31st and February forecast moved into Q2.150L segment work still pending for total completion of this project. Project EAC at $95K. 01-04-2022 - MNH - Project under SCADA testing now over next few weeks followed by moving into production at CC. 150L segment work still pending for total completion of this project. 12-02-2021 - MNH - Project under SCADA development, but we found 150L segment from DS to TO not in any scope. This will add another leakwarn project and may cause delay in completion of thisproject. 11-02-2021 - MNH - Project commissioning getting delayed due to 300# & HDD projects taking most of Toledo's resources. Moving $12K into Q1 of 2022. November and December forecast adjusted as well. 10-04-2021 - MNH - Project commissioning being planned for this month and next. 09-02-2021 - MNH - Project underway but behind schedule due to other leakwarn project work load at the same location. Forecast moved into 4th Q. 08-02-2021 - MNH - Project Phase II ready with readiness review workflow under approval. Project automation design & procurement work underway. 07-14-2021 - MNH - Missed adding a $10K accrual for DiamondZ for the month of June. Since OPPM is locked now, I will add the $10K to Q3 once its unlocked. EAC to remain at $96K.. 07-01-2021 - MNH -Project design & engineering close to complete and Phase II AFE completion underway. 06-02-2021 - MNH - There was delay in submitting the Phase 1 AFE and its under approval. As soon as it is approved, design and engineering will begin. 05-04-2021 - MNH - AFE to be submitted by end of next week. 04-01-2021 - MNH - Scope/AFE development underway and should be submitted later this month. 02-01-2021 - MNH - Forecast pushed out 3 months per Program Manager's direction. | 2023-05-02 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Toledo | DS999A7 - TOLEDO TO BP INLAND TK FARM 16 |  | 0 | 0 | 2500 |  | 11194 |  | Guenther, Steve | Guenther, Steve | N/A |  | 1 | 27312 |  | Guest, ProSight | Independent | Aqua | 2017-12-19 | Leak Detection
Leak Detection - DS999A8 - Toledo to Inland BP-3 - 10" | Item | Open | MCAP | DS999A8M2101 | Maintenance Framework | 1703470 | Hassan, Mohammad | West | 4. On-Hold | Defined | Leak Detection | 482 | 5000 |  | 5482.35 | 7482 | -2000 | Red | 5000 |  | 5000 | 482 |  |  | 30000 | 196000 |  | 226000 | Full | 226000 | 233119 | 5000 | 238119 | No | Green | 2021-08-01 | 2021-08-19 | 2021-08-19 | 2022-05-27 | 2023-07-28 |  |  | 237.35 | 202.5 | 42.5 | 0 |  |  | 0 | Green |  |  |  | 5000 | [7 empty] | 05-02-2023 - MNH - Final PLC commissioning is complete. Now will work with leak detection team on testing the model. Project EAC now at $238K now. Also, refinery shutdown will affect leakwarn testing. Moving forecast out a month due to this delay. 04-03-2023 - MNH - All parts are now here and we will complete project commissioning followed by leak detection testing. Project EAC still at $240K. Also, refinery shutdown will affect leakwarn testing. 03-01-2023 - MNH - Some parts still remaining that should be receive this month now. ARSEAL also ordered wrong parts. Once we receive all parts, we will complete project commissioning followed by leak detection testing. Project EAC still at $240. Moving forecast out a month due to delay in receiving PLC parts. Also, refinery shutdown will affect leakwarn testing. 02-01-2023 - MNH - Expecting PLC parts to arrive this month now. Once received we will complete project commissioning followed by leak detection testing. Project EAC still at $240K. 01-03-2023 - MNH - Some PLC parts arrived in December but waiting on some remaining PLC parts to arrive so remaining work will most likely be moved into Q2 of 2023. Project will stay on hold until we get all the remaining PLC parts followed by final project commissioning. Project EAC still at $240K. Adding $8K from Q1 into Q2 of 2023 and reducing Q1 forecast by $6K. 12-01-2022 - MNH - Still waiting on some PLC parts to arrive so December work will most likely be moved into 2023. Project will stay on hold until we get all the remaining PLC parts followed by final project commissioning. Project EAC still at $240K. Moving forecast out a month. Adding $3K from December into March 2023. 11-03-2022 - MNH - Some PLC parts will arrive this month. Project will stay on hold until we get all the remaining PLC parts followed by final project commissioning. Project EAC still at $240K. Moving forecast out a month. Added $6K to 2023. 10-04-2022 - MNH - Still waitingon PLC parts and no date provided from the vendor. Project will stay on hold until we get the remaining PLC parts followed by final project commissioning. Moving forecast out a month. Project EAC still at $240K. 09-01-2022 - MNH - Project on hold until we get the remaining PLC parts this month or October followed by final project commissioning. Reducing Sep forecast by $3K & moving it into Q4 to account of material delays. Project EAC still at $240K and adding some money in 2023 for possible commissioning delays. 08-02-2022 - MNH - Project on hold until we get the remaining PLC parts in September or October followed by final project commissioning. Due to higher than expected WM costs July actuals above forecast and Project EAC now at $240K. Moving forecast out a bit due to further delay on PLC parts. 07-06-2022 - MNH - Some progress was made on the automation side last month but project on hold until we get the remaining PLC parts in September following by final project commissioning. Project EAC still at $236K. 06-01-2022 - MNH - Project on hold until we get the remaining PLC parts in September following by final project commissioning. 05-10-2022 - MNH - Putting project on hold as now we are waiting for PLC parts to arrive in September before we can complete this project. 05-04-2022 - MNH - Electrical work ahead of schedule. We are now waiting on PLC material to arrive later this year before final commissioning can happen. Moving $3K from May into September. 04-04-2022 - MNH - Planning on starting electrical this month. Final commissioning will be delayed as PLC material is delayed till September. Moving $23K in September to accommodate that. 03-02-2022 -MNH - Mechanical work done in February and ahead of schedule. March/April/June forecast reduced to reflect the extra spends in February. EAC now at $236K due to extra purging cost. 02-02-2022 - MNH - Mechanical fabrication complete and ahead of schedule. Planning on mechanical install in February. EAC at $226K.. 01-04-2022 - MNH - Mechanical fabrication underway and ahead of schedule, meter received. Planning on mechanical work in March. EAC at $226K. 12-02-2021 - MNH - Meter delivery got delayed into December so November underspent. Adding $16K into December. 11-15-2021 - MNH - Adding $129,000 to forecast per the Phase II AFE which will be sourced from DS999TOM2101 (OPPM ID 37764) project. EAC to be at $226,000. 11-02-2021 - MNH - Project design is complete and mechanical bidding to happen next followed by submitting Phase II AFE. EAC being estimated at $205K at this time. Mechanical work will happen in 2022. 10-05-2021 - MNH - Meter has been ordered and PT & TT to be ordered next. Due to not idling this line as decided in the initial budget development, project EAC willbe around $180K but will be finalize once Phase II AFE is submitted next. 09-02-2021 - MNH - Phase 1 approved and design is underway. We will plan the pipe modifications this year with electrical & commissioning work done in 2022. 08-02-2021 - MNH - Phase 1 scope changed from original assumptions. Modified Phase 1 to be submitted this month. August forecast pushed into September. 07-01-2021 - MNH - Phase 1 AFE development underway andshould be submitted soon. 06-02-2021 - MNH - Scope/AFE development didn't get started last month and should begin this month. 05-04-2021 - MNH - Scope/AFE development to begin this month. 04-01-2021 - MNH - Scope/AFE development to begin next month. 02-01-2021 - MNH - Forecast pushed out 3 months per Program Manager's direction. | 2023-05-02 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Toledo | DS999A8 - TOLEDO TO BP INLAND 10IN |  | 482 | 5000 |  |  | 183309 |  | Guenther, Steve | Guenther, Steve | N/A |  | 1 | 25478 |  | Guest, ProSight | Independent | Aqua | 2017-09-01 | Leak Detection
Leak Detection - DS999B1, DS999B2, DS999B3 | Item | Open | MCAP | DS999TOM2101 | Exempt | 1703475 | Hassan, Mohammad | West | 3. Active | Defined | Leak Detection | 64081 | 20500 |  | 84580.54 | 80563 | 4018 | Yellow | 48000 |  | 48000 | 36581 |  |  | 165000 | 250000 |  | 622000 | Full | 622000 | 608590 | 20500 | 629090 | No | Green | 2021-05-01 | 2021-05-03 | 2021-05-03 | 2022-06-30 | 2023-06-30 |  |  | 37669.12 | 7948.98 | 6644.72 | 11817.72 | 8300 | 8300 | 3518 | Red |  |  | 3000 | 17000 | 500 | [6 empty] | 05-02-2023 - MNH - Leakwarn configuration and testing to continue now for few months. Some electrical punch list items to be completed when weather is warmer. Project EAC now at $629K due to $3K interest charges each month. 04-03-2023 - MNH - Leakwarn configuration and testing to continue now for few months. Some electrical punch list items to be completed when weather is warmer. Project EAC still at $622K. 03-01-2023 - MNH - Leakwarn configuratoin and testing to continue now for few months. Some electrical punch list items to be completed when weather is warmer. Project EAC still at $622K. 02-01-2023 - MNH - Cable tray work is complete and first round of SCADA checkout is done. Leakwarn configuratoin and test to continue now for several months. Project EAC still at $622K. 01-02-2023 - MNH - Cable tray work is complete and will now work with SCADA, ARSEAL & Techs to do commissioning followed by Leakwarn Testing. Project EAC still at $622K. 12-01-2022 - MNH - Cable tray work is underway and will continue into this month. Project EAC still at $622K. Moving some of Q1 2023 forecast out into Q2 due to refinery shutdown. 11-09-2022 - MNH - Due to refinery shutdown, commissioning these lines will take longer so moving some more money into 2023. Project EAC still at $622K. 11-03-2022 - MNH - Cable tray work to start this month. Project EAC still at $622K. 10-03-2022 - MNH - Tank farm end construction work ahead of schedule. Cable tray work still delayed until November/December. Project EAC still at $622K. 08-31-2022 - MNH - Notified by contractor that cable tray will not be delivered until Oct 28th. This will push some construction work from October into November and possible delay of commissioning into January of 2023. Adding $48K in 2023 to account for the possible delay.08-23-2022 - MNH - Adding forecast in Q4 to account for the new project EAC of $622K based on the final AFE being submitted this week.08-02-2022 - MNH - July variance due to reclass. Electric cabinet mostly done. Awaiting a competing quote from electrical contractor. Delay in receiving new cable tray will push the work out till October. New project EAC at $599K now. $68K from the budget of DS999A4M2101 project is in the December forecast. 07-05-2022 - MNH - Electrical cabinet under fabrication but delay with supply chain bidding & anticipated material delays will push someof forecast into Q4 from Q3.$68K from the budget of DS999A4M2101 project is in the December forecast.06-01-2022 - MNH - Mechanical work is complete and electrical cabinet under fabrication. Project ahead of schedule. June forecast reduced.05-03-2022 - MNH - Will plan on starting mechanical this month followed by electrical work.04-29-2022 - MNH - Moving $68K from the budget of DS999A4M2101 project to this project.04-04-2022 - MNH - Will plan on submitting another Phased AFE (Phase II) to get mechanical work schedule and completed. Electrical work willbe delayed due to other leak detection projects workload. Forecast pushed out a month. Full project EAC still at $550K.03-02-2022 - MNH - Phase II AFE is ready and should be $550K. Dueto PLC material further lead time delays of 20 weeks, project final commissioning won't happen until August. Project automation design is ahead of schedule.Project EAC now at $550K.02-02-2022 - MNH - Phase II AFE to be submitted this month. Budget for this project still at $505K.01-04-2022 - MNH - Meters have been received last month. Project Phase II AFE development underway this month. Budget for this project still at $505K.12-02-2021 - MNH - Meter delivery delay caused November forecast to be missed. Meters to be delivered in December so adding forecast.11-15-2021 - MNH - Reducing budget by $129,000 to support DS999A8M2101 project. New budget for this project is $505,000.11-02-2021 - MNH - Instrumentation was ordered on 10-8 with 2 week lead time, but is taking longer so Octoberis underspent. November forecast increased by 11K.10-25-2021 - MNH - Reducing budget by $56,000 to support DS999A6M2101 project. Budget reduced from $690,000 to $634,000.10-05-2021 - MNH - Mechanical design complete and got bid from mechanical contractor. PO for meter is cut.09-02-2021 - MNH - Mechanical design still not fully complete due to contractor handling multiple short line work at the same location. Once design is complete, we will acquire metering equipment this year with install and commissioning in2022. Q4 forecast adjusted to reflect the delay in design completion.08-02-2021 - MNH - Project on track with design to be completed by end of this month. Automation design to begin soon. Original scope will reduce due to less piping modifications.07-01-2021 - MNH - Project on track with design underway.06-16-2021 - MNH - Move $50K from Q3 to Q4 in order to account for any procurement delays.06-02-2021 - MNH - Project engineering underway on track to be completed by next month.05-03-2021 - MNH - Phase 1 AFE inroute and should be approved any day.04-01-2021 - MNH - Phase I Scope/AFE development for engineering & some procurement underway and should be submitted soon. Phase II for complete project execution to be submitted in late Q2 or early Q3.02-01-2021 - MNH - Forecast pushed out 3 months per Program Manager's direction and Q3 forecast for construction activity moved to Q2 of 2022 due to winter weather. | 2023-05-02 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Toledo | DS999TO - TOLEDO BPL TO TOLEDO NORCO |  | 52263 | 31818 | 500 |  | 365341 |  | Guenther, Steve | Bishop, Rick |  |  | 1 | 37764 |  | Guest, ProSight | Independent | Aqua | 2020-08-12 | Leak Detection
Leak Detection - DS999TO - Toledo to NORCO Slop 6" | Item | Open | MCAP | DS999TOM2102 | Maintenance Framework | 1703469 | Hassan, Mohammad | West | 3. Active | Unplanned | Leak Detection | 2144 | 14000 |  | 16144.05 | 16391 | -247 | Yellow |  |  |  | 16144 |  |  | 19000 | 50000 |  | 69000 | Full | 69000 | 45050 | 14000 | 59050 | No | Green | 2021-06-01 | 2021-06-23 | 2021-06-23 | 2021-08-31 | 2023-06-30 |  |  | 764.22 | 418.28 | 208.82 | 752.73 |  |  | 753 | Red |  |  |  | 14000 | [7 empty] | 05-02-2023 - MNH - We go more leak alarm so back on the drawing board. Working with program manager for next steps. We did check the alarm with SCADA last month. Project EAC still at $59K. Forecast moved out a month due to issues in getting alarms configured. 04-01-2023 - MNH - PLC leak alarms are monitoring better now. ARSEAL working with SCADA & Orin to get alarm points to CC & leak detection teams. Project EAC still at $59K. Forecast moved out a month due to delay in getting alarm to CC. 03-01-2023 - MNH - PLC leak alarms are monitoring better now. Will now work with SCADA & Leak detection group to get the alarm over to CC. Project EAC still at $59K. 02-01-2023 - MNH - Worked with Ops and made some adjustments to set point. Will now monitor the line to see if PLC model detects leaks properly now. This will continue for another month followed by leakwarn implementation. Prject EAC still at $59K. 01-03-2023 - MNH - Will work with Ops group to implement an option next. Project EAC still at $59K. 12-01-2022 - MNH - Still working with Hydraulics team and DiamondZ to come up with a solution. Project EAC still at $59K. 11-03-2022 - MNH - Testing determined that thermal pressure variations on this line will give false alarms so now will work with Hydraulics team to come up with a different approach to monitor leak detection on this line. not fully favorable. Moving money into 2023 to account for other leak detection method needed for this line if current PLC testing does not give us successful results over next month or so. 09-27-2022 - MNH - Testing continues but not fully favorable. Moving money into 2023 to account for other leak detection method needed for this line if current PLC testing does not give us successful results over next month or so. 09-02-2022 - MNH - PLC program changes were done in August and now we need to test the program for 4 week followed by moving to leak detection for testing into SCADA environment. Project may come under budget if this test is successful. September forecast moved to Q4 as a place holder. 08-02-2022 - MNH - PLC program changes underway as part of some action items. Next step is to move leak detection for testing to SCADA test environment. Project may come under budget if this test is successful. 07-06-2022 - MNH - Discussions & analysis with CC & Leak detection team brought up more action items before this line can move to CC. We will work with program owners to get additional guidance on resolution of those action items. Moving July forecast to August. 06-01-2022 - MNH - Will try to move this line to CC by end of this month. Ifthat is successful, the remaining forecast on the project won't be needed. 05-04-2022 - MNH - Will now work with CC for monitoring leak detection on this line. All of June forecast may not be used if this monitoring at CC is successful. 04-04-2022 - MNH - Same issues as last months notes. April forecast now moved to May as a backup if we need toinstall PPA solution 03-02-2022 - MNH - Leak detection monitoring underway at the PLC level but not looking promising as the pipe doesn't hold pressure over 1 hour window and loses 20 psi over 1 hour from initial pressure of 35 psi. We made further tweak to the program to see if we get better results before moving monitoring to SCADA/CC. March forecast now moved to April as a backup if we need to install PPA solution 02-02-2022 - MNH - Cost savings on project so forecast reduced by $10K. Leak detection monitoring underway at the PLC level and will continue this and next month before moving to SCADA/CC. March forecast is as a backup if we need to install PPA solution. 01-04-2022 - MNH - Cost savings on project so forecast reduced by $10K. Leak detection monitoring underwayat the PLC level and will continue this and next month before moving to SCADA/CC. March forecast is as a backup if we need to install PPA solution. 12-02-2021 - MNH - new BPCV was installed successfully and leak detection monitoring at PLC level to start this month. If that fails, we mayhave to go to PPA solution. Adding forecast into Q1 of 2022 if we need PPA solution otherwise project will come under budget. 11-02-2021 - MNH - Phase II to be submitted this week or next with new BPCV installation on Nov 17th with leak detection implementation by end of December. 10-05-2021 - MNH - Phase II AFE submission underway for installation of the new BPCV in November followed by leak detection implementation in December. 09-02-2021 - MNH - A new BPCV will be ordered and installed in Oct or Nov followed by Leak detection implementation on this short line. 08-02-2021 - MNH - Nochange from previous update from 7/29. 07-29-2021 - MNH - We did some initial testing for continuous pressure monitoring which revealed issues with the back pressure control valve at TO. This will push the implementation into 4th quarter until the back pressure CV issue is resolved. 07-01-2021- MNH - Project engineering & design and programming underway but a little behind. 06-02-2021 - MNH - Phase 1 AFE should be submitted by this week or next. 05-04-2021 - MNH - Scope/AFE development to begin this month. 04-01-2021 - MNH - Scope/AFE development to begin next month. 02-01-2021 - MNH - Forecast pushed out 3 months per Program Manager's direction. | 2023-05-02 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Toledo | DS999TO - TOLEDO BPL TO TOLEDO NORCO |  | 1391 | 14753 |  |  | 5075 |  | Guenther, Steve | Guenther, Steve | N/A |  | 1 | 30163 |  | Guest, ProSight | Independent | Aqua | 2018-07-30 | Leak Detection
Leak Detection - EC999B1 - Clark Jct. to East Chicago Station | Item | Open | MCAP | EC999B1M2201 | Maintenance Framework | 2022499 | Stalbaum, Cameron | West | 3. Active | Defined | Leak Detection | 4930 | 20000 |  | 24929.91 | 24607 | 323 | Yellow |  |  |  | 24930 |  |  | 75000 |  |  | 75000 | Full | 75000 | 44208 | 20000 | 64208 | No | Green | 2022-10-01 | 2022-09-12 | 2022-09-12 | 2022-12-30 | 2023-11-30 |  |  | 921.74 | 1162.48 | 2522.67 | 323.02 |  |  | 323 | Red |  |  | 5000 | 10000 | 5000 | [6 empty] | 5/1/23 - Forecast for May is for Meade to electrical for box instllation. Installs could be delayed pending when Vanmok will ship the boxes. 3/31/23 - Forecast is updated to reflect the receipt of the vanmok boxes as well as Meade costs for electrical installation and actual wiring of the Vanmok equipment. Project slated to be completed by end of June. 1/3/23 - Still Accruing for Vanmok. There invoices are being held up in Open invoice because they were not submitted correctly in USD and were entered in CAD. 12/2/22 - Accruing for vanmok boxes 11/1/22 - Holding accrual for Vanmok Boxes that have been ordered for this project. Will have to reclass costs from the Overall engineering project as the AFE was not approved when the ordering was submitted. 10/3/22 - Vanmok Boxes are on order for this project. Working with Vanmok to get final details on operating peramiters. 9/5/22 - Writing AFE to purchase material. Drawings were received on 8/23. Scheduling reviews with complex to verify all necessary modifications. AFE will be submitted week end 9/9. 3/2/22 - After having calls with leak warn group as well as district leadership. Im reducing the forecast for these projects in 2022 to only cover a material purchase cost. With engineering proposed to be completed the last week of May I'm not confident that we will be able to secure material and install the solution. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | EC999B1 - CLARK JCT TO E CHICAGO STATION |  | 4607 | 15323 | 5000 |  | 39278 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 38942 |  | Guest, ProSight | Independent | Aqua | 2020-10-29 | Leak Detection
Leak Detection - EG999A1 - BP Whiting to East Chicago BET (Canal Line) | Item | Open | MCAP | EG999A1M2201 | Maintenance Framework | 2037535 | Stalbaum, Cameron | West | 3. Active | Defined | Leak Detection | 8848 | 40000 |  | 48847.87 | 48679 | 169 | Yellow | 120500 |  | 120500 | -71652 |  |  | 94000 |  |  | 94000 | Phase | 94000 | 35522 | 40000 | 75522 | No | Green | 2022-10-01 | 2022-10-21 | 2022-10-21 | 2023-05-30 | 2023-08-31 |  |  | 7848.1 | 665.07 | 165.96 | 168.74 |  |  | 169 | Red |  |  | 10000 | 15000 | 15000 | [6 empty] | 5/1/23 - Forecast is for Meade for installation of electrical equipment and box installs in the future. 3/31/23 - Forecast has been updated to reflect the receipt of the vanmok box and Meade for installation and electrical work inside of BP. Working issuing MEADE PO for them to start the pre electrical work inside of BP. Overall forecast was reduced for PPA solution. 2/2/23 - This was for completing the installation of the pressure transmitters. 1/3/23 - Holding Accrual for Vanmok due to invoicing error. 12/2/22 - Reforecasted vanmok amount for December. This is the reason for the variance. As there has been an issue with BP getting back with me on whether or not we can installed solar on their side of the line. 11/1/22 - Vanmok equipment has been ordered. Waiting to hear back from BP Engineer on location where we can install solar vanmok. 10/3/22 - Working on AFE submission. Plan on having it submitted week of 10/3. 9/5/22 - Writing AFE to purchase material. BP is working on a project with Dan Ownby to make piping modifications to this line on their property and to be able to install the strap on meter at the Action Corner site. This project will be installed in 2023. 3/2/22 - After having calls with leak warn group as well as district leadership. Im reducing the forecast for these projects in 2022 to only cover a material purchase cost. With engineering proposed to be completed the last week of May I'm not confident that we will be able to secure material and install the solution. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | EG999A1 - BP WHITING - E CHIC BET CANAL |  | 8679 | 25169 | 15000 |  | 26674 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 38943 |  | Guest, ProSight | Independent | Aqua | 2020-10-29 | Leak Detection
Leak Detection - EG999A5 - East Chicago Station to East Chicago Jct. 6-Inch Line | Item | Candidate | MCAP |  | Maintenance Framework |  | Stalbaum, Cameron | West | 8. Canceled |  | Leak Detection |  | 0 |  | 0 | 0 | 0 | Green | 100000 |  | 100000 | -100000 | [9 empty] | 0 | 0 | No | Green |  |  |  |  | 2023-07-31 | [6 empty] | 0 | 0 | 0 | Green |  |  |  |  | 0 | [10 empty] | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | EG999A5 - East Chicago - East Chicago Jct. |  |  | 0 | 0 |  |  |  | Guenther, Steve |  |  |  | 1 | 38944 |  | Guest, ProSight | Independent | Aqua | 2020-10-29 | Leak Detection
Leak Detection - EG999A6 | Item | Open | MCAP | EG999A6M2201 | Maintenance Framework | 2023214 | Grinder, Mark | West | 3. Active | Defined | Leak Detection | 12726 | 300000 |  | 312726.49 | 312653 | 73 | Yellow | 100000 |  | 100000 | 212726 |  |  | 60000 |  |  | 60000 | Phase | 60000 | 56571 | 300000 | 356571 | No | Green | 2022-11-01 | 2022-09-20 | 2022-09-20 | 2023-08-01 | 2023-09-29 |  |  | 11995.86 | 522.57 | 134.69 | 73.37 |  |  | 73 | Red |  |  |  | 75000 | 75000 | 75000 | 75000 |  |  |  |  | 4-27-2023 - Waiting for Quotes for mechanical work and submit a phase II AFE. 3-23-2023 - Working on Quotes for mechanical work and submit a phase II AFE. 3-01-2023 - Working on Quotes for mechanical work and submit a phase II AFE. 2-01-2023 - The Meters and transmitters have been received and fabrication will start in April 2023 and installation will begin in July 2023. 12-29-2022 - The Meters and transmitters have been received and fabrication will start in April 2023 and installation will begin in July 2023. 11-28-2022 - The Meters and transmitters have been ordered and should arrive in late December, fabrication will start in April 2023 and installation will begin in July 2023. 11-01-2022 - Material will be ordered this week and waiting for a quote from Rockwell for the panel build. 9-30-2022 - The AFE has been approved and waiting for quotes to order material. 9-02-2022 - A determination will be made for this line section this month after reviewing drawings.. 8-08-2022 I am forecasting 65K for November if a PPA solar solution is considered if not we will purchase strap-on metering and install electrical for this line section and complete the installation in 2023. 7-27-2022 - Still working on Engineering and supposed to receive IFR drawing August 8th and IFB August 20th. 6-29-2022 - Still working on Engineering and supposed to receive IFR drawing August 8th and IFB August 20th. 5-31-2022 - This leak warn project is still undergoing engineering for project scope. 4-07-2022 - Moved the Forecast to October and November since the engineering has not been performed on this line section. 3-01-2022 - Moved the Forecast to October and November since the engineering has not been performed on this line section. 9-01-2021 - Working on a Phase 1 AFE to get material ordered and electrical work completed 8-01-2021 - Waiting for Allied Engineering to decide if we are using PPA or Strap-on metering for leak warn on this short line. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | EG999A6 - E Chicago (W) to E Chicago (E) 12 in. Line |  | 12653 | 75073 | 225000 |  | 43845 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 38687 |  | Administrator, System | Independent | Aqua | 2020-10-01 | Leak Detection
Leak Detection - EG999B1 - BP Whiting to East Chicago (West) Propylene Tanks | Item | Open | MCAP | EG999B1M2001 | Exempt | 1776282 | Grinder, Mark | West | 6. Operational | Defined | Leak Detection | -2886 |  |  | -2886 | -2886 | 0 | Green |  |  |  | -2886 |  |  | 110000 |  |  | 110000 | Full | 110000 | 76174 |  | 76174 | No | Green | 2020-12-01 | 2020-11-18 | 2020-11-18 | 2020-12-31 | 2022-12-31 |  |  | -2886 | 0 | 0 | 0 |  |  | 0 | Green | [11 empty] | 4-27-2023 - This project has been completed. 3-23-2023 - This project has been completed. 3-01-2023 - Working on a procedure for operations and SCADA leak warn. 2-01-2023 - This project has been completed. 12-29-2022 - This project has been completed. 11-28-2022 - This has been completed. 11-01-2022 - This is being tested this week or next, since propylene has been down from BP the last two weeks 9-26-2022 - This did not get completed this month, majority of the work has been performed but SCADA commissioning did not get completed, this will be completed in October. 8-29-2022 - This is still expected to be completed in September. 7-27-2022 - This will be completed in September. 6-29-2022 - Another meeting is scheduled for July 12th to discuss the trending analysis for leak warn, Once the leak warn group is confidant of the data and ensure we will not experience false alarms we can execute the project. 5-31-2022 - We are having a meeting June 16th to discuss the path forward for this project, moved the forecast to August. 5-02-2022 - This has been postponed until June so the leak warn group can evaluate the collected data on Propylene Rail Loading. 4-02-2022 - This project needs to be postponed, the leakwarn group would like more time to determine how to calculate data when loading is active at the propylene rail. 3-01-2022 - This project will be completed next month due to contractor availability, forecasting 35K April Spend. 2-01-2022 - Still on track to be completed in March. 1-04-2022 - This project is scheduled to complete in March this year. 12-01-2021 - This project is being moved to first quarter of 2022, minimal local support and availability due to holidays and vacation time. 11-01-2021 - This project is being moved to first quarter of 2022 due to meter proving in November, minimal local support and availability due to holidays and vacation time. 10-01-2021- The PSSR will be completed in October, Scada Checkout will be conducted in November after meters are proved, the EG999B2 project completion will be performed at the same time.Forecast 35K spend in November. 9-01-2021 - Moving the forecast to October, will complete the PHA/PSSR this month. 8-01-2021 - The forecast was moved to September and a PHA will be performed in September also. 7-01-2021 - This will still be completedwhen the EG to EU project is completed. The PHA has been postponed until August. 6-02-2021 - This will still be completed when the EG to EU project is completed. The PHA has been postponed until June. 5-03-2021 - This will be completed when The EG/EU leak warn project gets completed, all completed except the SCADA checkout. 4-01-2021 - Working on installing the PLC point I/O and Control Valve automation. 3-01-2021 - Power has been connected and will complete the SCADA checkout when performing the checkout during the EG to EU SCADA checkout. 2-03-2021 - The MOC has been approved for this project and waiting for BP to allow us to have poweron the PLC so we can power up and test back to SCADA, I will update the notes when this will occur. 1-04-2021 - The EG side hazardous gas conduit has been ran, the Gas detectors should arrive today and BP side conduit will be completed this week, meeting Thursday to define alarm response and actions. 11-24-2020 - PO's were written and approved and this project is scheduled to be completed in December. 11-09-2020 - AnAFE will be submitted this week, we discussed a solution last Friday that will meet PHMSA Reg's for short line leak warn detection.10/29/20 - moved 2020 funding to this project to reflect the correct line number that will be receiving leak detection in Dec 2020. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | EG - EAST CHICAGO STA (NORCO) |  | -2886 | 0 |  |  | 17222 |  | Guenther, Steve | Burdett, Jesse |  |  | 1 | 38951 |  | Guest, ProSight | Independent | Aqua | 2020-10-29 | Leak Detection
Leak Detection - EG999B2 - East Chicago (EG) to Propylene Rail (EU) | Item | Open | MCAP | EG999B2M2001 | Exempt | 1776283 | Grinder, Mark | West | 6. Operational | Unplanned | Leak Detection | 2819 |  |  | 2818.88 | 2819 | 0 | Green |  |  |  | 2819 |  |  | 15000 |  |  | 15000 | Full | 15000 | 19781 |  | 19781 | Yes | Red | 2020-12-01 | 2020-11-18 | 2020-11-18 | 2020-12-31 | 2022-10-31 |  |  | 278.42 | 2162.6 | 377.86 | [16 empty] | 4-27-2023 - This project has been completed. 3-23-2023 - This project has been completed. 3-01-2023 - This project has been completed. 2-01-2023 -This has been completed and we are monitoring this for alarms before this gets turned over in March to SCADA to avoid false alarms. 12-29-2022 - This has been completed and we are monitoring this for alarms before this gets turned over in March to SCADA to avoid false alarms, 11-28-2022 - This has been completed and we are monitoring this for alarms before this gets turned over to SCADA to avoid false alarms. 11-01-2022 - This is being tested this week or next, since propylene has been down from BP the last two weeks 9-26-2022 - This did not get completed this month, majority of the work has been performed but SCADA commissioning did not get completed, this will be completed in October. 8-29-2022 - Project completion is scheduled for September 19 through the 23rd. 7-27-2022 - Scheduled for September 19 through the 23rd. 6-29-2022 - Another meeting is scheduled for July 12th to discuss the trending analysis for leak warn, Once the leak warn group is confidant of the data and ensure we will not experience false alarms we can execute the project. 5-31-2022 - We are having a meeting June 16th to discuss the path forward for this project, moved the forecast to August. 5-02-2022 - This has been postponed until June so the leak warn group can evaluate the collected data on Propylene Rail Loading. 4-02-2022 - This project needs to be postponed, the leakwarn group would like more time to determine how to calculate data when loading is active at the propylene rail. 3-01-2022 - this will be completed next month, forecasting 12K in April Due to contractor availability. 2-01-2022 - Scheduled for March completion. 1-04-2022 - This project is forecast for March 2022, this will be completed with the EG999B2 Leak Warn Project. 12-01-2021 - ProjectForecast for March 2022. 11-01-2021 - This project is being deferred until March 2022, Meter proving not scheduled until Mid-November and localsupport will not be available. 10-01-2021 - This project PSSR will be conducted in October, the asset team is repairing the prover valves and areproving the meters in Mid-October, the Scada Leak Warn should be completed in November. 9-01-2021 - Moving the forecast to October we will have the PHA/PSSR in September and complete in October. 8-01-2021 - We will be performing a PHA and PSSR in August and plan on completing the project in September. 7-01-2021 - This project PHA was delayed due to a potential BP off spec butane project thatmay happen. 6-02-2021 - The PHA was postponed until June due to other priorities at the complex, we will have the PHA in June. 5-03-2021 - We are having the PHA for this project May 6th and a PSSR will follow. 4-01-2021 - The MOC has been approved and working on PLC installation and Produce Consume message with Triadfor Rail load start and stop along with re-pressurization routine. This will be completed by the end of the month. 3-02-2021 - Working on the MOC for this project and discussing the Master Metering and repressure with Leak warn group, I will have another meeting before project kickoff. 2-03-2021 - This is still on track to be completed by the end of the first quarter. 1-04-2020 - Material received but due to contractor availability this has been scheduled to complete in the first quarter of 2021. The PLC has been installed and only programming remaining for the automation of the control valve differential pressure according to the saturation chart, re-pressure line with PLC routine for leakwarn integrity check and SCADA alarm programming. 11-24-2020 - Material has been ordered and this project is scheduled to be completed in December. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | EG - EAST CHICAGO STA (NORCO) |  | 2819 | 0 |  |  | 13303 |  | Guenther, Steve | Bishop, Rick |  |  | 1 | 39003 |  | Guest, ProSight | Independent | Aqua | 2020-11-11 | Leak Detection
Leak Detection - EG999KG - Lake George to East Chicago Line | Item | Open | MCAP | EG999KGM2201 | Maintenance Framework | 2023215 | Grinder, Mark | West | 3. Active | Defined | Leak Detection | 20615 | 55000 |  | 75614.62 | 75462 | 152 | Yellow | 100000 |  | 100000 | -24385 |  |  | 65000 |  |  | 65000 | Phase | 65000 | 32024 | 55000 | 87024 | No | Green | 2022-11-01 | 2022-09-21 | 2022-09-21 | 2023-08-01 | 2023-09-30 |  |  | 18365.33 | 1948.55 | 148.61 | 152.13 |  |  | 152 | Red |  |  | 5000 | 15000 | 25000 | 10000 | [5 empty] | 4-27-2023 - Should have the electrical installation completed early, targeting June completion. 3-23-2023 - Should have the electrical installation completed early, targeting June completion. 3-01-2023 - Working on the quote for Electrical installation. 2-01-2023 - All material has been received and working on electrical in the next month or two. 12-29-2022 - Partial material has been received and installed, still waiting for the Vanmok Gateway and PLC it has been held up at customs. 11-28-2022 - Waiting for material to be received and trying to complete this early. 11-01-2022 - Material has been ordered for this project. 9-30-2022 - The AFE has been approved and waiting for quotes to order material. 9-02-2022 - A determination will be made on this line section this month. 8-8-2022 - The PPA solution is not going to work for this line since there are Three manifolds between the beginning and end of this section, one of the tie-ins to the manifold on the KG side is buried. Moving the forecast to August of 2023 so we can have engineering determine the best solution for rupture protection. 7-29-2022 - This project is still undergoing Engineering IFR drawings should be received August 8th and IFB August 20th. 6-29-2022 - This project is still undergoing Engineering IFR drawings should be received in August. 5-31-2022 - This leak warn project is still undergoing engineering for project scope. 4-07-2022 - Moved the Forecast to October and November since the engineering has not been performed on this line section. 3-01-2022 - Moved the Forecast to October and November since the engineering has not been performed on this line section. 9-01-2021 - Working on a Phase 1 AFE to get material ordered and electrical work completed 8-01-2021 - Waiting for Allied Engineering on design package for pressure point analysis or Strap-on Metering solution for this short line project. 4/13/21 - basedon most recent DNV Phase II analysis of lines - the EG999KG line falls into the Excepted category if weutilize 1) PPA and 2) Frequent patrol and Public awareness program. 4-08-2021 - Moved forecast from July to December. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | EG999KG - LAKE GEORGE TO E CHICAGO BET |  | 20462 | 20152 | 35000 |  | 11409 |  | Guenther, Steve | Guenther, Steve | N/A |  | 1 | 27309 |  | Guest, ProSight | Independent | Aqua | 2017-12-19 | Leak Detection
Leak Detection - EH999A1 - Hammond Main to North (Gas) | Item | Open | MCAP | EH999A1M2101 | Maintenance Framework | 1901883 | Grinder, Mark | West | 3. Active | Unplanned | Leak Detection | -3771 |  |  | -3771.13 | -4332 | 561 | Red |  |  |  | -3771 |  |  | 60000 |  |  | 60000 | Phase | 60000 | 95248 |  | 95248 | No | Green | 2021-11-01 | 2021-10-12 | 2021-10-12 | 2021-12-31 | 2023-06-30 |  |  | 799.88 | 611.39 | -5743.13 | 560.73 |  |  | 561 | Red | [11 empty] | 4-27-2023 - Working on a procedure for operations and SCADA leak warn. 4.6.23 - -$6,381 March forecast due to MEXP Flip EH999A1E2301 (AS) 3-23-2023 - Working on a procedure for operations and SCADA leak warn. 3-01-2023 - Working on a procedure for operations and SCADA leak warn. 2-01-2023 - Antenna was replaced and alarms come in appropriately, SCADA monitoring for false alarms and working with Leak warn group on response and action criteria for operations and control center. 12-29-2022 - This project is still waiting to test the new PLC response, this will be tested in the first week of January. 11-28-2022 - The PLC has been tested but has a latency issue so we had to order a new antenna which was just received and will install it this week. we will retest to see if the response is acceptable. 11-01-2022 - The vanmok PLC has just been received and will be commissioned this month and tested back to SCADA, the data will not be activated from SCADA until after it is determined that nuisance alarms are not being generated for approximately 4 weeks. 9-26-2022 - We are scheduled to tie-in the Vanmok PLC to SCADA this month, the data will not be activated from SCADA until after it is determined that nuisance alarms are not being generated for approximately 4 weeks. 8-29-2022 - We are scheduled to tie-in the Vanmok PLC to SCADA this month, the data will not be activated from SCADA until after it is determined that nuisance alarms are not being generated for approximately 4 weeks. 8-29-2022 - We are scheduled to tie-in the Vanmok PLC to SCADA this month, the data will not be activated from SCADA until after it is determined that nuisance alarms are not being generated for approximately 4 weeks. 7-27-2022 - The final round of testing has been completed this afternoon and will be discussing the path forward on the short line leak warn PPA solution for the company this Friday. 6-29-2022 - We are scheduled to perform testing again starting July 25th, the transmitters have all been re-scaledto 0 - 300 psi. 6-02-2022 - The leak warn group would like to dofurther testing in July, we are going to rescale the transmitters from 0 -800 PSI to 0 - 300 PSI and gather a couple weeks of data before testing again. 5-31-2022 - We have tested the leak warn for EH999A1line section and the leak warn group is discussing further testing on the other EH line sections. 5-02-2022 - The PPA testing is scheduled for the week of May 9th, the leak warn group and engineering are currently working on a detailed testing procedure that can be used for testing this pilot system. Forecast 30K spend in May 4-1-2022 Forecast moved to May not enough data collected to commission this line section. 3-01-2022 - Moving forecast of $6K to April, Vanmok will be onsite March 7th to upload new firware on the Vanmok Gateways, testing should be performed in the second week of April. 2-01-2022 - PPA leak warn system is online and values being recorded, collecting data until March and still waiting for a SCADA solution. 1-03-2022 - We have commissioned the Vanmok PPA gateways and will be collecting data for the next three months, we are also working on a solution to get this data back to SCADA for leak warn purposes. 12-17-2021 - We will complete the commissioning on all 4 Vanmok Gateways at Hammond today for all 4 leak detection projects, working with IT and SCADA to determine the best way to get these devices routed into SCADA. I am accruing $26,000 for December and forecasting $6000 for March 2022 for physical testing and tuning. 12-01-2021 - Pressure Transmitters were received and planning on installing next week. Vanmok will set up each Unit controllermid December. 11-01-2021 - Pressure Transmitters ordered and lead time is 5 weeks, we will perform the installation in the beginning of December. 10-01-2021 - Working on Phase 1 AFE's for Leak warn Project 9-01-2021 - Working on a Phase 1 AFE to get material ordered and electrical work completed 8-01-2021 - Waiting for Allied Engineering on design package for pressure point analysis for this short line project. 7-01-2021 - Scheduled to meet with contractor to determine scope in Mid-July | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | EH999A1 - HAMMOND - NORTH PROP GAS |  | -4332 | 561 |  |  | 66536 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 38688 |  | Administrator, System | Independent | Aqua | 2020-10-01 | Leak Detection
Leak Detection - EH999A2 - Hammond Main to North (Oil) | Item | Open | MCAP | EH999A2M2101 | Maintenance Framework | 1901882 | Grinder, Mark | West | 3. Active | Unplanned | Leak Detection | 1143 |  |  | 1142.68 | 851 | 292 | Red |  |  |  | 1143 |  |  | 60000 |  |  | 60000 | Phase | 60000 | 61507 |  | 61507 | No | Green | 2021-11-01 | 2021-10-12 | 2021-10-12 | 2021-12-31 | 2023-06-30 |  |  | 278.45 | 283.48 | 288.57 | 292.18 |  |  | 292 | Red | [11 empty] | 4-27-2023 - Working on a procedure for operations and SCADA leak warn. 3-23-2023 - Working on a procedure for operations and SCADA leak warn. 3-01-2023 - Working on a procedure for operations and SCADA leak warn. 2-01-2023 - Antenna was replaced and alarms come in appropriately, SCADA monitoring for false alarms and working with Leak warn group on response and action criteria for operations and control center. 12-29-2022 - This project is still waiting to test the new PLC response, this will be tested in the first week of January. 11-28-2022 - The PLC has been tested but has a latency issue so we had to order a new antenna which was just received and will install it this week. we will retest to see if the response is acceptable. 11-01-2022 - The vanmok PLC has just been received and will be commissioned this month and tested back to SCADA, the data will not be activated from SCADA until after it is determined that nuisance alarms are not being generated for approximately 4 weeks. 9-26-2022 - We are scheduled to tie-in the Vanmok PLC to SCADA this month, the data will not be activated from SCADA until after it is determined that nuisance alarms are not being generated for approximately 4 weeks. 8-29-2022 - We are scheduled to tie-in the Vanmok PLC to SCADA this month, the data will not be activated from SCADA until after it is determined that nuisance alarms are not being generated for approximately 4 weeks. 8-15-2022 - Need to forecast 14K spend in October for the UPS install into the West Shore Building on Hammond North Property. 7-27-2022 - The final round of testing has been completed this afternoon and will be discussing the path forward on the short line leak warn PPA solution for the company this Friday. 6-29-2022 - We are scheduled to perform testing again starting July 25th, the transmitters have all been re-scaled to 0 - 300 psi. 6-02-2022 - The leak warn group would like to do furthertesting in July, we are going to rescale the transmitters from 0 - 800 PSIto 0 - 300 PSI and gather a couple weeks of data before testing again.5-31-2022 - We have tested the leak warn for EH999A1line section and the leak warn group is discussing further testing on the other EH line sections. 5-02-2022 - Depending on the PPA testing results for the EH999A1 short line, we will possibly not spend any further money testing the EH999A2, A3 and A4 short lines. 4-1-2022 Forecast moved to May not enough data collected to commission this line section. 3-01-2022 - Moving forecast of $6K to April, Vanmok will be onsite March 7th to upload new firware on the Vanmok Gateways, testing should be performed in the second week of April. 2-01-2022 - PPAleak warn system is online and values being recorded, collecting data until March and still waiting for a SCADA solution. 1-03-2022 - We have commissioned the Vanmok PPA gateways and will be collecting data for the next three months, we are also working on a solution to get this data back to SCADA for leak warn purposes. 12-17-2021 - We will complete the commissioning on all 4 Vanmok Gateways at Hammond today for all 4 leak detection projects, working with IT and SCADA to determine the best way to get these devices routed into SCADA. I am accruing $28,000 for December and forecasting $6000 for March 2022 for physical testing and tuning. 12-01-2021 - Pressure Transmitters were received and planningon installing next week. Vanmok will set up each Unit controller mid December. 11-01-2021 - Pressure Transmitters ordered and lead time is 5 weeks, we will perform the installation in the beginning of December. 10-01-2021 - Working on Phase 1 AFE's for Leak warn Project. 9-01-2021 - Working on a Phase 1 AFE to get material ordered and electrical work completed 8-01-2021 - Waiting for Allied Engineering on design package for pressure point analysis for this short line project. 7-01-2021 - Scheduled to meet with contractor to determine scope in Mid-July | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | EH999A2 - HAMMOND - NORTH PROP OIL |  | 851 | 292 |  |  | 24173 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 38689 |  | Administrator, System | Independent | Aqua | 2020-10-01 | Leak Detection
Leak Detection - EU999A1 - East Chicago B/G to East Chicago Norco 10-Inch 2022 | Item | Open | MCAP | EU999A1M2201 | Maintenance Framework | 2023217 | Grinder, Mark | West | 3. Active | Defined | Leak Detection | 20899 | 15000 |  | 35899.11 | 35461 | 438 | Yellow | 100000 |  | 100000 | -64101 |  |  | 52000 |  |  | 52000 | Phase | 52000 | 104797 | 15000 | 119797 | No | Green | 2022-11-01 | 2022-09-21 | 2022-09-21 | 2022-08-01 | 2023-07-31 |  |  | 18635.45 | 481.36 | -8655.76 | 10438.06 | 10000 | 10000 | 438 | Yellow |  |  | 15000 | [8 empty] | 4-27-2023 - This should be completed in May. 3-23-2023 - Working on the installation schedule. 3-01-2023 - Working on quotes for this project. 2-01-2023 - Material has finally been received and transmitters installed, electrical work will begin in the next month or two. 01-04-2023 - The Vanmok Gateways and PLC has been lost in Customs, I have to re-order them. We are still going to meet the original forecast. 11-28-2022 - All material has been ordered and supposed to arrive in late November early December, we are trying to complete this project early. 11-01-2022 - The material has been ordered for this project 9-26-2022 - The AFE was just approved and waiting for updated quotes to procure material. 9-02-2022 - A determination will be made on this line section this month. 8-08-2022 - I am forecasting 60K for November 2022 and the remaining amount for September 2023, If the PPA solution is suitable for this line section than the 2023 forecast will be dropped. We are getting quotes for power at the Citgo Junction and not sure what the lead time will be for installation. 7-27-2022 - Moving forecast to September, waiting on quotes for electrical that needs to be installed. 6-29-2022 - Working on quotes for electrical that needs to be installed. 5-31-2022 - This leak warn project is still undergoing engineering for project scope. 4-07-2022 - Moved the Forecast to August, October and November since the engineering has not been performed on this line section. 3-01-2022 - Moved the Forecast to August, October and November since the engineering has not been performed on this line section. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | EU999A1 - E CHICAGO B/G TO E CHICAGO NOR |  | 10461 | 25438 |  |  | 83898 |  | Guenther, Steve | Guenther, Steve | N/A |  | 1 | 27315 |  | Guest, ProSight | Independent | Aqua | 2017-12-19 | Leak Detection
Leak Detection - EU999A2 - 6-Inch East Chicago (B/G) to East Chicago (CITGO) | Item | Open | MCAP | EU999A2M2201 | Maintenance Framework | 2022627 | Stalbaum, Cameron | West | 3. Active | Defined | Leak Detection | 35633 | 65000 |  | 100633.03 | 98028 | 2605 | Yellow | 163000 |  | 163000 | -62367 |  |  | 213000 |  |  | 213000 | Phase | 213000 | 106587 | 65000 | 171587 | No | Green | 2022-10-01 | 2022-09-14 | 2022-09-14 | 2023-05-30 | 2023-08-31 |  |  | 30985.13 | 1786.1 | 256.42 | 2605.38 |  |  | 2605 | Red |  |  |  | 20000 | 20000 |  |  |  |  | 25000 |  | 5/1/23 - Still holding accrual for Meade. They did submit an invoice that hasnt hit for 24K, so accrual covers that invoice along with remaining work that should be invoiced as well. 20K forecast is for boxes to be installed. 3/31/23 - Still holding accrual for Meade for the H structure. Forecast was updated to reflect receipt of vanmok boxes and Meade for installation in June/July. Transformer costs were pushed out to end of the year. 3/1/23 - Accrual is for Meade for the material for the electrical installation at Citgo JCT. They installed the H support structure in Feb. Just waiting on them to bill the labor and material for the installation. 2/2/23 - Accrual is for Meade material. They billed a portion of it this past month, but did not bill all of it. Actuals that posted were for transmitters that I anticipated coming later in the year and the portion of the material that Meade billed. Forecast has been adjusted for future spend. This project will be way under budget. 1/3/23 - Still holding accrual for Meade for material purchase for power supply of 58K. 12/2/22 - Accruing for vanmok and also accruing for poles and cabinets that Meade has on order. 11/1/22 - Vanmok equipment ordered. Working on transformer with MEADE. 50K in November is for vanmok equipment as well as MEADE for material purchase. 10/3/22 - Vanmok Boxes are on order for this line. Working on setting parameters with vanmok for this line section. 9/5/22 - Writing AFE to purchase material. Drawings were received on 8/23. Scheduling reviews with complex to verify all necessary modifications. This project will require bringing in a power drop from NIPSCO and a step down transformer. Anticipate the power supply work to be done in 2023, but will install as much of the PPA equipment in 2022 as possible. Will do final commissioning in 2023. 3/2/22 - After having calls with leak warn group as well as district leadership. Im reducing theforecast for these projects in 2022 to only cover a material purchase cost. With engineering proposed to be completed the last week of May I'm not confident that we will be able to secure material and install the solution. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | EU999A2 - E CHICAGO B/G TO E CHIC CITGO |  | 33028 | 22605 | 20000 | 25000 | 70954 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 38946 |  | Guest, ProSight | Independent | Aqua | 2020-10-29 | Leak Detection
Leak Detection - KG999A2 - Clark Jct. to Lake George | Item | Candidate | MCAP |  | Maintenance Framework |  | Stalbaum, Cameron | West | 4. On-Hold | Defined | Leak Detection |  | 138000 |  | 138000 | 138000 | 0 | Green | 138000 |  | 138000 | 0 | [9 empty] | 138000 | 138000 | No | Green | 2023-12-01 |  |  |  | 2023-08-31 | [19 empty] | 138000 |  | 5/1/23 - No change. 4/3/23 - Waiting on final determination if we have to install PPA on this line section since it is under 50FT. This project could be a potential savings if we can eliminate it from the program. 9/5/22 - This line section has not been identified on the Leak Detection list and engineering is not aware of this line. I have pushed the forecast for this project out into 2023 pending a deeper dive into this line section. 3/2/22 - After having calls with leak warn group as well as district leadership. Im reducing the forecast for these projects in 2022 to only cover a material purchase cost. With engineering proposed to be completed the last week of May I'm not confident that we will be able to secure material and install the solution. | 2023-05-01 |  |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | KG - LAKE GEORGE STATION |  |  | 0 |  | 138000 |  |  | Guenther, Steve |  |  |  | 1 | 38947 |  | Guest, ProSight | Independent | Aqua | 2020-10-29 | Leak Detection
Leak Detection - KG999B1 - Clark Jct. to BP Whiting | Item | Open | MCAP | KG999B1M2201 | Maintenance Framework | 2035948 | Stalbaum, Cameron | West | 3. Active | Defined | Leak Detection | 17666 | 29500 |  | 47166.22 | 46282 | 884 | Yellow | 100000 |  | 100000 | -52834 |  |  | 61000 |  |  | 61000 | Phase | 61000 | 34488 | 29500 | 63988 | No | Green | 2022-10-01 | 2022-10-03 | 2022-10-03 | 2023-08-01 | 2023-07-31 |  |  | 12948.4 | 707.43 | 3126.34 | 884.05 | 10000 | 10000 | -9116 | Red |  | Contractor/Vendor Issue | 15000 | 10000 | 4500 | [6 empty] | 5/1/23 - 10K for April was for Meade. They did not end up securing the necessary material. This is being pushed to May and June. 3/31/23 - Forecast has been updated based on quote that was received from Meade. Meade is planned to start electrical work in April and Finish installation inside BP in May. 4500 in July is for the subscription fee for Vanmok 2/2/23 - This was for the order of pressure transmitters for the leak detection installations. This order came in sooner than originally anticipated. 1/3/23 - This variance is for Shultz installing hot taps and getting ready folr Vanmok installs. 12/2/22 - Holding Accrual for Vanmok Boxes, After review the accrual was dropped to 8000 as we did not have to purchase a second vanmok box. 11/1/22 - Vanmok equipment ordered equipment purchase was only 15K. Variance is for material quote coming in under what was originally anticipated. Waiting on call back from BP Engineering on location for Vanmok equipment. 10/3/22 - Vanmok boxes are on order. Trying to set up meeting with BP OMD engineer to findout where we can install the box on BP property. 9/5/22 - Writing AFE to purchase material. Drawings were received on 8/23. Scheduling reviews with complex to verify all necessary modifications. 3/2/22 - After having calls with leak warn group as well as district leadership. Im reducing the forecast for these projects in 2022 to only cover a material purchase cost. With engineering proposed to be completed the last week of May I'm not confident that we will be able to secure material and install the solution. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | KG999B1 - CLARK JCT TO BP WHITING |  | 16782 | 25884 | 4500 |  | 16822 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 38948 |  | Guest, ProSight | Independent | Aqua | 2020-10-29 | Leak Detection
Leak Detection - KG999EG - Lake George to East Chicago BET (GAS) | Item | Open | MCAP | KG999EGM2201 | Maintenance Framework | 2037529 | Stalbaum, Cameron | West | 3. Active | Defined | Leak Detection | -8416 | 35000 |  | 26584.26 | 26383 | 201 | Yellow | 27500 |  | 27500 | -916 |  |  | 75000 |  |  | 75000 | Phase | 75000 | 17554 | 35000 | 52554 | No | Green | 2022-10-01 | 2022-10-21 | 2022-10-21 | 2023-05-05 | 2023-08-31 |  |  | -14596.68 | 179.26 | 800.5 | 5201.18 | 5000 | 5000 | 201 | Yellow |  |  | 10000 | 10000 |  | 15000 | [5 empty] | 5/1/23 - Meade has indicated they secured the necessary materials for the installation. This is what the accrual is for. Forecast is for Meade installing necessary electrical equipment for the installations. 3/31/23 - Updated forecast to reflect Meade electrical installation. 5k in april is for material ordering and installations in late may early june. 2/2/23 - I went ahead and dropped the accrual for vanmok. In early January Mark and I were able to couple this line with another vanmok install and thus we will not need the extra box that this cost would have covered. The box that was purchased for this will be reallocated. Future forecast is for the installation of the single box and having Meade hook them up with Mark's lines. 1/3/23 - Still Accruing for Vanmok. There invoices are being held up in Open invoice because they were not submitted correctly in USD and were entered in CAD.12/2/22 - Waiting on Vanmok to issue invoice for boxes. 11/1/22 - Vanmok boxes are on order. The variance is because vanmok quote came back lower than what was originally anticipated. 10/3/22 - Working on AFE submission. Plan on having it submitted week of 10/3.9/29/22 - Submitting phase 1 afe to cover the cost of the hot taps. We will be reducing down next years budget as Mark and I will be splitting costs on this line between the gas and the oil lines. 9/5/22 - Writing Phase 1 AFE to purchase material. Drawings were just received on 8/23. Working with Complex to review drawings and make final changes. 3/2/22 - After having calls with leak warn group as well as district leadership. Im reducing the forecast for these projects in 2022 to only cover a material purchase cost. With engineering proposed to be completed the last week of May I'm not confident that we will be able to secure material and install the solution. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | KG999EG - LK GEORGE TO E CHIC BET (GAS) |  | -13617 | 25201 | 15000 |  | 25969 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 38949 |  | Guest, ProSight | Independent | Aqua | 2020-10-29 | Leak Detection
Leak Detection - TO999A1 - Zenith, Delta, Sunoco ETP | Item | Open | MCAP | TO999A1M2101 | Maintenance Framework | 1703472 | Hassan, Mohammad | West | 3. Active | Defined | Leak Detection | 74550 | 260000 |  | 334550.19 | 331290 | 3260 | Yellow | 332000 |  | 332000 | 2550 |  |  | 50000 | 258000 |  | 308000 | Phase | 308000 | 336002 | 260000 | 596002 | No | Green | 2021-06-01 | 2021-06-22 | 2021-06-22 | 2021-11-15 | 2023-08-18 |  |  | 3755.13 | 9866.57 | 33168.55 | 27759.94 | 5000 | 5000 | 22760 | Red |  | WorkAhead of Schedule | 5000 | 46000 | 150000 | 59000 | [5 empty] | 05-02-2023 - MNH - Some work done ahead of schedule at Zenith. Final Phase 3 AFE to be at $662K and will be submitted this month and got delayed due to other projects workload. Project EAC should be $662K now. OPPM numbers still show original $332K budget for 2023 with original EAC of $593K. Forecast adjusted. 04-03-2023 - MNH - All quotes now received. Final AFE to be at $662K and we will need another $69K to get all the scope completed on this project. Will work with program owner next to secure funding followed by routing final Phase 3 AFE later this month. Project EAC should be $662K now. OPPM numbers still show original $332K budget for 2023 with original EAC of $593K. 03-01-2023 - MNH - All but one quote received per design and we will need another $37K to get all the scope completed on this project. Will work with program owner next to secure funding followed by routing final Phase 3 AFE later this quarter. Project EAC should be $630K now. OPPM numbers still show original $332K budget for 2023 with original EAC of $593K. 02-01-2023 - MNH - Quote received per design and we will need another $32K to get all the scope completed on this project. Will work with program owner next to secure funding followed by routing final Phase 3 AFE later this quarter. Project EAC should be $625K now. OPPM numbers still show orignal $332K budget for 2023. 01-03-2023 - MNH - All design should be complete this month. Cable tray work at DS end of the line is complete. Full project EAC still at $593K. 2023 budget is at $332K. 12-02-2022 - MNH - Contractor completed some drawings but a bit behind. Cable tray work at DS end of the line started as planned last month. Full project EAC now at $593K. 2023 budget is at $332K. 11-03-2022 - MNH - Contractor is behind on some E&D work. Cable tray work at DS end of the line to start this month. Full project EAC still at $600K. 2023 budget is at $332K. 10-04-2022 - MNH - Contractor is planning on completing E&Dwork by mid October. Delay in receiving cable tray until end of October will keep construction from starting until November. Full project EAC still at $600K. 2023 budget is at $332K. 09-02-2022 - MNH - Contractor is behind but planning on completing E&D work by mid October. Further delay in receiving cable tray until end of October now will push forecast out. Full project EAC still around $600K. 2022 forecast reduced by $70K. 2023 budget now $332K. 08-02-2022 - MNH - July variance due to reclass but contractor is behind on E&D work due to other work load and resource shortage. Delay in receiving cable tray until end of Sep will push forecast out. Full project EAC now around$600K. 2022 forecast still reflects the original budget of $338K. Adding $262K in 2023 for executing the rest of this project. 07-05-2022 - MNH - Phase II (Phased) AFE submitted on the 6th and got approved on 20th of June. This delay along with delay in receiving material caused June forecast to be missed. Also adjusting the rest of the forecast to reflectmaterial delays and project delays due to resource shortage. Full project EAC now around $560K. Forecast still reflects the original budget of $338K. Some of June forecast moved into Q4. 06-01-2022 - MNH - Delay in submitting Phased AFE due to other project workload and emergent projects. Will plan on submitting this week for ordering long lead time items and completing some electrical work. Full project EAC now around $600K. Forecast still reflects the original budget of $338K. Some of June forecast moved into Q4. 05-04-2022 - MNH - Delay in submitting Phased AFE due to other project workload. Will plan on submitting this month for ordering long lead time items. Full project EAC nowaround $600K. Forecast still reflects the original budget of $338K. May Forecast moved into July. 04-04-2022 - MNH - Same update as last month plus planning on routing anotherPhase AFE to start ordering long lead time items in April now. Full project EAC still around $550K. Forecast still reflects the original budget of $338K. 03-02-2022 - MNH - Further delay in PLC material and lack of resources will now push this project out another two months. Also, we are waiting response from delta terminal owner which is adding to the delay. Planning on routing another Phase AFE to start ordering long lead time items in March. Project AFE may be around $550K now. Forecast still reflects the original budget of $338K. 02-02-2022 -MNH - January underspent by $6K compared to forecast due to vendor delay in getting PLC & Instrumentation material. 2022 forecast has been adjusted accordingly. New EAC now at $502,000, but will be finalized once Phase II AFE is completed. Forecast still reflects the original budget of $338K. 01-04-2022 - MNH - December underspent by $20K compared to forecast due to vendor delay in cabinet completion as well as project delay due to resources that are busy with other leak detection projects. 2022 forecast has been adjusted accordingly. New EAC now at $496,000, but will be finalized once Phase II AFE is completed. Forecast still reflects the original budget of $338K. 12-02-2021 - MNH - Meter delivery delay and delay from engineering firmcaused November to be underspent. Project EAC will be above budget as scope complexity for this project has increased. Estimate EAC now at $458,000, but will be finalized once Phase II AFE is completed. 11-02-2021 - MNH - Slight material delay and delay from engineering firm caused October to be underspent. Project EAC still at budget of $338K but will be finalized once Phase II AFE is completed. 10-04-2021 - MNH - Meters have been ordered and will order PT's & TT's next. We are underway for completing power design at Delta Terminal. Some MOV's needed at Zenith Terminal. Dueto resource limitations Sep was underspent and now we will be doing most of the construction in 2022. 09-02-2021 - MNH - It was determined that Delta Terminal will need a new power drop from Toledo Edison which will cause delay inimplementing leak detection on this line. Moving $178K from November in Q1 of 2022 to accommodate this work. We will continue to work on completing design & procurement to keep this project moving. 08-02-2021 - MNH - Project engineering & design underway but behind due to additional scope complexities. July under spent money to be moved into August. 07-01-2021 - MNH - Projectdesign &engineering underway. 06-02-2021 - MNH - Phase 1 AFE should be submitted by this week or next. 04-01-2021 - MNH - Phase I Scope/AFE development for engineering & some procurement underway and should be submitted next month. Phase II for complete project execution to be submitted in Q3. | 2023-05-02 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Toledo | TO999A1 - TOLEDO TO C/S LINE (NORCO) |  | 46790 | 78760 | 209000 |  | 176278 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 37761 |  | Guest, ProSight | Independent | Aqua | 2020-08-12 | Leak Detection
Leak Detection - TU999A1 - Mid America Pipe Line Co. Metering Station to Tuscola Terminal | Item | Candidate | MCAP |  | Maintenance Framework |  | Scannell, Adam | West | 2. Pending AFE |  | Leak Detection |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 | [9 empty] | 50000 | 50000 | No | Green | 2023-09-01 |  |  |  | 2023-09-30 | [16 empty] | 50000 |  |  |  |  | 04/21/23 - Enterprise is planning to install a Red Lion data station for Buckeye to tie into. Information for costs have been reveived and conversations with Buckeye's network team started to determine our scope and internal equipment needs. Once received, AFE will be submitted for orders to be made. 02/02/23 - Initial stakeholder meetings have been held to kick off scope discussions. Setting up a meeting with Enterprise to discuss Buckeye needs and get approvals started. | 2023-05-02 |  |  | West | Pipelines and Terminals | Integrity |  | Central-Illinois | TU999A1 |  |  | 0 | 50000 |  |  |  | Guenther, Steve |  |  |  | 1 | 38950 |  | Guest, ProSight | Independent | Aqua | 2020-10-29 | Leak Detection
Leak Detection - XF999A1 - Griffth to BP Caverns | Item | Open | MCAP | XF999A1M2201 | Maintenance Framework | 2037532 | Stalbaum, Cameron | West | 3. Active | Defined | Leak Detection | 13237 | 40000 |  | 53236.62 | 53088 | 149 | Yellow | 210000 |  | 210000 | -156763 |  |  | 73000 |  |  | 73000 | Phase | 73000 | 31384 | 40000 | 71384 | No | Green | 2022-10-01 | 2022-10-21 | 2022-10-21 | 2023-05-30 | 2023-09-30 |  |  | 10862.16 | 548.51 | 1676.85 | 149.1 |  |  | 149 | Red | [6 empty] | 40000 |  |  |  |  | 5/1/23 - No change. Still working with Petro Gas to get PPA solution approved to install equipment on their side of the line. They are pushing back on the reasoning to install equipment on their side of the line. 3/31/23 - No Change here. Forecast has been updated to reflect installation later this year. Currently working with Petrgo Gas on drawing/installation approval. 2/1/23 - This variance was for the purchase of the vanmok. Vanmok with the 1 year subscripton came back in 10K higher. 1/3/23 - Still Accruing for Vanmok. There invoices are being held up in Open invoice because they were not submitted correctly in USD and were entered in CAD.12/2/22 - Holding accrual for Vanmok 11/1/22 - Vanmok Equpment ordered. Variance is for the difference in anticipated quote from what was actually quoted. 10/3/22 - After talking with leak detection group we are going to go ahead and purchase PPA equipment for this project. With the limited room to install a meter and being on petrogas property we do not believe we will have room to make the necessary piping modifications. Forecast was reduced to only purchasing the PPA equipment this year. 9/29/22 - Reduced forecast to 20,000. This would only cover the purchase of the Vanmok Boxes. This application is still being discussed with the leak warn group as major piping modifications are needed if we have to utilize a meter as well as approval from Petro Gas. 9/5/22 - Writing phase 1 to purchase material for this project. Installation cost are being pushed to 2023, as Leak Detection engineering and Petro Gas need to finalize the necessary modification in order to proceed forward. 3/2/22 - After having calls with leak warn group as well as district leadership. Im reducing the forecast for these projects in 2022 to only cover a material purchase cost. With engineering proposed to be completed the last week of May I'm not confident that we will be able to secure material and install the solution. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Michiana | XF999A1 - GRIFFITH TO BPCAVERNS |  | 13088 | 149 | 40000 |  | 18148 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 38940 |  | Guest, ProSight | Independent | Aqua | 2020-10-29 | Leak Detection
Leak Detection-DF999A2 | Item | Open | MCAP | DF999A2M2201 | Maintenance Framework | 2023218 | Grinder, Mark | West | 3. Active | Defined | Leak Detection | 4191 | 152500 |  | 156690.52 | 156691 | 0 | Green | 152500 |  | 152500 | 4191 |  |  | 101000 |  |  | 101000 | Phase | 101000 | 79691 | 152500 | 232191 | No | Green | 2022-10-01 | 2022-09-21 | 2022-09-21 | 2022-12-31 | 2023-11-30 |  |  | 4037.11 | 153.41 | 0 | 0 |  |  | 0 | Green | [5 empty] | 32500 | 60000 | 30000 | 30000 |  |  | 4-27-2023 -This project is still being discussed if this is considered DOT or not, still have an Actuator that was ordered and should be shipped around June. 3-23-2023 - This project is still being discussed if this is considered DOT or not, still have an Actuator that was ordered and should be shipped around June. 3-01-2023 - This project is still being discussed if this is considered DOT or not, still have an Actuator that was ordered and should be shipped around June. 1-31-2023 - This project has all material except for the Valve that is supposed to be delivered in August, and still waiting on decision since US Oil has a New Regulatory compliance director and they are stating that their equipment is not under DOT requirements. 12-29-2022 - This project is on hold, US Oil has a New Regulatory compliance director and they are stating that their equipment is not under DOT requirements. 11-28-2022 - Material has been ordered and should arrive in late December, the installation will happen sometime in 2023 depending on the negotiations with US Oil.11-01-2022 - The material was ordered for this and a site visit revealed that we need to use PPA for the US Oil East side of this line.9-30-2022 - The AFE was approved and waiting for Pipe thickness before metering material can be ordered and waiting for a quote for the transmitters.9-02-2022 - leaving $75K forecast for November Moving $162.5K to May 2023 We are now in negotiations with US Oil allowing Buckeye to maintain the Bettendorf line section for leak warn purposes..8-29-2022 - leaving $100K forecast for November Moving $137.5K to May 2023 We are now in negotiations with US Oil allowing Buckeye to maintain the Bettendorf line section for leak warn purposes..8-4-2022 - leaving $100K forecast for November Moving $137.5K to May 2023 We are now in negotiations with US Oil allowing Buckeye to maintain the Bettendorf line section for leak warn purposes..7-27-2022 - This project is still under review with US Oil and the Leak Warn Group.6-29-2022 - This project is still under review with US Oil and the Leak Warn Group.5-31-2022 - The Buckeye legal team is discussing the leak warn project with US Oil and Magellan. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Eastern Iowa | DF999A2 |  | 4191 | 0 | 92500 | 60000 | 75501 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 41408 |  | Administrator, System | Independent | Aqua | 2021-08-13 | Leak Detection
Leak Detection-EH999A3 | Item | Open | MCAP | EH999A3M2101 | Maintenance Framework | 1901893 | Grinder, Mark | West | 3. Active | Unplanned | Leak Detection | 688 |  |  | 687.62 | 512 | 176 | Red |  |  |  | 688 |  |  | 60000 |  |  | 60000 | Phase | 60000 | 37012 |  | 37012 | No | Green | 2021-11-01 | 2021-10-12 | 2021-10-12 |  | 2023-06-30 |  |  | 167.56 | 170.59 | 173.65 | 175.82 |  |  | 176 | Red | [11 empty] | 4-27-2023 - Working on a procedure for operations and SCADA leak warn. 3-23-2023 - Working on a procedure for operations and SCADA leak warn. 3-01-2023 - Working on a procedure for operations and SCADA leak warn. 2-01-2023 - Antenna was replaced and alarms come in appropriately, SCADA monitoring for false alarms and working with Leak warn group on response and action criteria for operations and control center. 12-29-2022 - This project is still waiting to test the new PLC response, this will be tested in the first week of January. 11-28-2022 - The PLC has been tested but has a latency issue so we had to order a new antenna which was just received and will install it this week. we will retest to see if the response is acceptable. 11-01-2022 - variance is for vanmok reclass was submitted for October. The vanmok PLC has just been received and will be commissioned this month and tested back to SCADA, the data will not be activated from SCADA until after it is determined that nuisance alarms are not being generated for approximately 4 weeks 9-26-2022 - We are scheduled to tie-in the Vanmok PLC to SCADA this month, the data will not be activated from SCADA until after it is determined that nuisance alarms are not being generated for approximately 4 weeks. 8-29-2022 - We are scheduled to tie-in the Vanmok PLC to SCADA this month, the data will not be activated from SCADA until after it is determined that nuisance alarms are not being generated for approximately 4 weeks. 7-27-2022 - The final round of testing has been completed this afternoon and will be discussing the path forward on the short line leak warn PPA solution for the company this Friday.6-29-2022 - We are scheduled to perform testing again starting July 25th, the transmitters have all been re-scaled to 0 - 300 psi.6-02-2022 - The leak warn group would like to do further testing in July, we are going to rescale the transmitters from 0 - 800 PSI to 0 - 300 PSI and gather a couple weeks of data before testing again.5-31-2022 - We have tested the leak warn for EH999A1line section and the leak warn group is discussing further testing on the other EH line sections.5-02-2022 - Depending on the PPA testingresults for the EH999A1 short line, we will possibly not spend any further money testing the EH999A2, A3 and A4 short lines.4-01-2022 - We are planning on testing this Line section at the end of April.3-01-2022 - Moving forecast of $6K to April, Vanmok will be onsite March 7th to upload new firware on the Vanmok Gateways, testing should be performed in the second week of April.2-01-2022 - PPA leak warn system is online and values being recorded, collecting data until March and still waiting for a SCADA solution.1-03-2022 - We have commissioned the Vanmok PPA gateways and will be collecting data for the next three months, we are also working on a solution to get this data back to SCADA for leak warn purposes. 12-17-2021 - We will complete the commissioning on all 4 Vanmok Gateways at Hammond today for all 4 leak detection projects, working with IT and SCADA to determine the best way to get these devices routed into SCADA. I am accruing $28,000 for December and forecasting $6000 for March 2022 for physical testing and tuning.12-01-2021 - Pressure Transmitters were received and planning on installing next week. Vanmok will set up each Unit controller mid December. 11-01-2021 - Pressure Transmitters ordered and lead time is 5 weeks, we will perform the installation in the beginning of December.10-01-2021 - Working on Phase 1 AFE's for Leak warn Project. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | EH999A3 - Hammond Main Property to TL Explorer |  | 512 | 176 |  |  | 4558 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 41410 |  | Administrator, System | Independent | Aqua | 2021-08-13 | Leak Detection
Leak Detection-EH999A4 | Item | Open | MCAP | EH999A4M2101 | Maintenance Framework | 1901891 | Grinder, Mark | West | 3. Active | Unplanned | Leak Detection | 3008 |  |  | 3008.36 | 2838 | 171 | Yellow |  |  |  | 3008 |  |  | 66000 |  |  | 66000 | Phase | 66000 | 35904 |  | 35904 | No | Green | 2021-11-01 | 2021-10-12 | 2021-10-12 | 2021-12-31 | 2023-06-30 |  |  | 151.74 | 1221.36 | 1464.69 | 170.57 |  |  | 171 | Red | [11 empty] | 4-27-2023 - Working on a procedure for operations and SCADA leak warn. 3-23-2023 - Working on a procedure for operations and SCADA leak warn. 3-01-2023 - Working on a procedure for operations and SCADA leak warn. 2-01-2023 - Antenna was replaced and alarms come in appropriately, SCADA monitoring for false alarms and working with Leak warn group on response and action criteria for operations and control center. 12-29-2022 - This project is still waiting to test the new PLC response, this will be tested in the first week of January. 11-28-2022 - The PLC has been tested but has a latency issue so we had to order a new antenna which was just received and will install it this week. we will retest to see if the response is acceptable. 11-01-2022 - The vanmok PLC has just been received and will be commissioned this month and tested back to SCADA, the data will not be activated from SCADA until after it is determined that nuisance alarms are not being generated for approximately 4 weeks. 9-26-2022 - We are scheduled to tie-in the Vanmok PLC to SCADA this month, the data will not be activated from SCADA until after it is determined that nuisance alarms are not being generated for approximately 4 weeks. 8-29-2022 - We are scheduled to tie-in the Vanmok PLC to SCADA this month, the data will not be activated from SCADA until after it is determined that nuisance alarms are not being generated for approximately 4 weeks. 7-27-2022 - The final round of testing has been completed this afternoon and will be discussing the path forward on the short line leak warn PPA solution for the company this Friday. 6-29-2022 - We are scheduled to perform testing again starting July 25th, the transmitters have all been re-scaled to 0 - 300 psi. 6-02-2022 - The leak warn group would like to do further testing in July, we are going to rescale the transmitters from 0 - 800 PSI to 0 - 300 PSI and gather a couple weeks of data before testing again. 5-31-2022 - We have tested the leak warn for EH999A1line section and the leak warn group is discussing further testing on the other EH line sections. 5-02-2022 - Depending on the PPA testing results for the EH999A1 short line, we will possibly not spend any further money testing the EH999A2, A3 and A4 short lines. 4-01-2022 - We are planning on testing this Line section at the end of April. 3-01-2022 - Moving forecast of $6K to April, Vanmok will be onsite March 7th to upload new firware on the Vanmok Gateways, testingshould be performed in the second week of April. 2-01-2022 - PPA leak warn system is online and values being recorded, collecting data until March and still waiting for a SCADA solution. 1-03-2022- We have commissioned the Vanmok PPA gateways and will be collecting data for the next three months, we are also working on a solution to get this data back to SCADA for leak warn purposes. 12-17-2021 - We will complete the commissioning on all 4 Vanmok Gateways at Hammond today for all 4 leak detection projects, working with IT and SCADA to determine the best way to get these devices routed into SCADA. I am accruing $28,000 for December and forecasting $6000 for March 2022 for physical testing and tuning. 12-01-2021 - Pressure Transmitters were received and planning on installing next week. Vanmok will set up each Unit controller mid December. 11-01-2021 - Pressure Transmitters ordered andlead time is 5 weeks, we will perform the installation in the beginning of December. 10-01-2021 - Working on Phase 1 AFE's for Leak warn Project. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | E. Chicago Terminals | EH999A4 - HAMMOND - HAMMOND EAST BADGER |  | 2838 | 171 |  |  | -3332 |  | Guenther, Steve | Guenther, Steve |  |  | 1 | 41411 |  | Administrator, System | Independent |  | 2021-08-14 | Leak Detection
LI165LA Hydraulic and Control Study | Item | Candidate | MEXP |  | Exempt |  | Parker, Brian | West | 2. Pending AFE |  | West |  | 45000 |  | 45000 | 45000 | 0 | Green | 30000 |  | 30000 | 15000 | [9 empty] | 45000 | 45000 | No | Green | 2023-07-01 |  |  |  | 2023-10-31 | [14 empty] | 15000 | 15000 |  | 15000 |  |  |  | 2/3/23 - walked this down with local ops on Jan 24th and looking over drawings now. Sounds like we need to get the new REXA installed on the 501 control valve first before going to the next step. | 2023-02-03 |  |  | West | Pipelines and Terminals | Station/Terminal |  | Lima Pipelines | LA999A6 - LIMA TO HUSKY 8IN |  |  | 0 | 30000 | 15000 |  |  | Gardner, Travis |  |  |  | 1 | 44600 |  | Guest, ProSight | Independent | Aqua | 2022-08-15 | Other Programs
Lima North Stair Replacement Phase 1 - STF | Item | Open | MCAP | BETLM00M2201 | Maintenance Framework | 2044313 | Roknich, Hunter | West | 3. Active | Defined | West | 15577 | 50000 |  | 65576.89 | 50825 | 14752 | Red | 50000 |  | 50000 | 15577 |  |  | 42000 |  |  | 42000 | Phase | 42000 | 49301 | 50000 | 99301 | No | Green | 2022-11-01 | 2022-11-08 | 2022-11-08 | 2022-12-31 | 2023-08-31 |  |  | 640.32 | 90.84 | 93.78 | 14751.95 |  |  | 14752 | Red | [5 empty] | 50000 | [5 empty] | 5/2/2023 - Scope review in process. Final install May/June. 4/4/2023 - Final install moved into April/May. 3/2/32023 - Final work for phase 1 being completed in March 2/2/2023 - Work 90% complete. Waiting for better weather to finish 1/4/2023 - Work 90% complete. Will finish in January 12/2/2022 - Working on fabrication. Installation scheduled to begin 12/19 11/2/2022 - AFE approval in progress. Work expected mid/late November. 10/11/2022 - Work quoted by Degen Excavating for $35k. Scope to be reviewed by management. AFE to be submitted in next week. Work to occur early November. 8/2/2022 - Waiting for quote to be completed | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Terminals | BETLM - BET MA NORTH TERMINAL |  | 825 | 14752 | 50000 |  | 33724 |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 41783 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Lima North Terminal Fire Foam Control System Upgrade | Item | Candidate | MCAP |  | Maintenance Framework |  | Henfling, Mike | West | 2. Pending AFE |  | Fire Protection |  | 70000 |  | 70000 | 70000 | 0 | Green | 70000 |  | 70000 | 0 | [9 empty] | 130000 | 130000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 | 0 | 5000 | 30000 | 35000 |  |  |  |  | 5-2-23 - On-site meeting held 4/19. Notes and initial scope developed, waiting on budgetary quote to decide how to finalize bid specification document. Will open bid event late May or June. Could potentially require additional funds in 2023 to complete and/or a phased approach over two years. 4-4-23 - On-site scoping meeting with Greg J. and Vanguard planned for 4/19. Once scope developed, will bid with Cuyahoga and Lima Station in May. 3-2-23 - No new updates. Plan for scoping site visit in late March. Bid event in April with Cuyahoga and Lima Station. Left forecast as-is. 2-2-23 - Discussed project with Ops and Greg J. in January. Plan to complete a site visit in March and put together a scope for bid event with Cuyahoga and Lima Station. Left forecast as-is. 1-3-23 - Left forecast as-is. | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Terminals | BETLM - BET MA NORTH TERMINAL |  |  | 0 | 70000 |  |  |  | Jakubowski, Gregory |  |  |  | 1 | 45378 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Other Programs
Lima North Vapor Piping Upgrade | Item | Open | MCAP |  | Maintenance Framework |  | Roknich, Hunter | West | 2. Pending AFE |  | Vapor Management |  | 56000 |  | 56000 | 56000 | 0 | Green | 56000 |  | 56000 | 0 | [9 empty] | 56000 | 56000 | No | Green | 2023-09-01 |  |  |  | 2023-11-30 | [16 empty] | 10000 |  | 46000 | [6 empty] | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Terminals | BETLM - BET MA NORTH TERMINAL |  |  | 0 | 10000 | 46000 |  |  | Karl, Marissa |  |  |  | 1 | 44942 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Other Programs
Lima South Mechanical & Multiload Rack Upgrade | Item | Open | MCAP | BETLI00M2204 | Maintenance Framework | 1955624 | Hassan, Mohammad | West | 3. Active | Defined | Truck Racks | 46726 | 185000 |  | 231726.01 | 231331 | 395 | Yellow | 115000 |  | 115000 | 116726 |  |  | 66000 | 224000 |  | 290000 | Full | 290000 | 105406 | 185000 | 290406 | No | Green | 2022-09-01 | 2022-09-09 | 2022-09-09 | 2023-06-30 | 2023-06-30 |  |  | 1620.69 | 516.74 | 9193.32 | 35395.26 | 24000 | 24000 | 11395 | Red |  | WorkAhead of Schedule | 90000 | 85000 | 10000 | [6 empty] | 05-02-2023 - MNH - All material received and construction to being later this month as planned. EAC at $290K. 04-20-2023 - MNH - All PO's issued and work underway as planned. EAC at $290K. 04-03-2023 - MNH - AFE completed and under approval. Project EAC based on AFE is at $290K. Forecast have been updated to show total project EAC. 03-01-2023 - MNH - Electrical pre-bid meeting scheduled for next week followed by full AFE submission. Will work with REM to get more funding or decision to phase this project if there is no funding. Project EAC now around $283K if funding is approved. Forecast still shows $173K EAC. 02-01-2023 - MNH - Working with REM to get more funding or decision to phase this project if there is no funding. Project EAC around $273K if funding is approved. Forecast still shows $173K EAC. 01-30-2023 - MNH - Got mechanical prices back and they are much higher than expected. Project EAC to be at $275K. Will work with program manager or REM to get funding approved next. 01-03-2023 - MNH - IFB drawings are done. Will work on doing bid walk this month. Project EAC at $173K, but we may need more money to get this project done. estimating $218K for final EAC. Will work with Program Manager for more funding once Phase 2 is ready in Q1 of 2023. 12-02-2022 - MNH - IFR drawings done. Will work on getting IFB drawings for getting quotes for 2023 work. Project EAC still at $168K, but we may need more money to get this project done. estimating $220K for final EAC. Will work with Program Manager for more funding once Phase 2 is ready in Q1 of 2023. 11-01-2022 - MNH - Design work started but is delayed due to Buckeyes internal drawings request process. November forecast reduced by $10K and moved into December. Project EAC still at $168K. 10-04-2022 - MNH - Phase 1 approved last month and PO issued to one of the contractors. Will start design work this month. Current project EAC at $168K 09-02-2022 - MNH - Delay in getting Phase 1 submitted so planning on getting it completed next week. Pushing forecast out a bit due to this delay and increasing 2023 forecast. 08-01-2022 - MNH - Finally received quote from ESPbut it was much higher than anticipated at $38,500 and now will need to get another quote since its above $30K. If we do design this year, we can doprocurement & construction in 2023 and more funding would be needed. Adding $100K in 2023 as a placeholder. Will plan on submitting Phase 1 by end of August. 07-21-2022 - MNH - Finally received quote from ESP but it was much higher than anticipated at $38,500 and now will need to getanother quote since its above $30K. If we do design this year, we can do procurement & construction in 2023 and more funding would be needed. Adding $100K in 2023 as a placeholder. Will plan on submitting Phase 1 by end of August. 06-27-2022 - MNH - Reducing budget by $32K to fund Taylor Terminal Truck Rack MultiLoad Upgrade Phase 2 (OPPM ID 41737). Phase 1 submittal delayed due to ESP quote delays. 06-01-2022 - MNH - Have received some pricing but still waiting on quotes for completing design. Will submit a Phase 1 AFE this month to complete design & order material. 05-03-2022 - MNH - Delay in getting information from Tech & vendor so SOW development to continue this month. Moving forecast out a month. 04-01-2022 - MNH - Initial site visit completed last month. SOW development to be completed this month. 03-01-2022 - MNH - Will start working on SOW in this month. Forecast moved to Q3 and adjusted based to anticipated long lead timeson material. 02-02-2022 - MNH - Will start working on SOW in March. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Terminals | BETLI - BET LIMA SOUTH TERMINAL |  | 11331 | 210395 | 10000 |  | 58680 |  | Younce, Michael | Carnes, John L. |  |  | 1 | 41800 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Lima South NGL Offload Pump Upgrade | Item | Open | MCAP | BETLI00M2302 | Maintenance Framework | 2112690 | Parker, Brian | West | 3. Active | Defined | Pipeline Digs |  | 34000 |  | 34000 | 34000 | 0 | Green | 34000 |  | 34000 | 0 |  |  | 37545 |  |  | 37545 | Full | 37545 |  | 34000 | 34000 | No | Green | 2023-06-01 | 2023-04-26 | 2023-04-26 | 2023-08-31 | 2023-08-31 | [13 empty] | 12500 | 12500 | 9000 | [5 empty] | 5/1/23 - PO's issued to Furey Filter & Pump and Degen for this work. Sent email to local ops on 4/27 asking them to select a week that they would like to schedule this work. 4/10/23 - sent email to local techs and OM to review AFE before submitting to management for review. 3/20/23 - sent email to Degen (Jeff) requesting a quote to get this pump/motor skid installed along with piping modifications. Already have a quote from Furey to align and commission this pump/motor skid. 2/3/23 - Jack suggested that we look at a Blackmere SGL Pump that is specifically designed for NGL and Propane. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Lima Terminals | BETLI - BET LIMA SOUTH TERMINAL |  |  | 12500 | 21500 |  |  |  | Bartal, Nick | Carnes, John L. |  |  | 1 | 34319 |  | Guest, ProSight | Independent | Aqua | 2019-08-22 | Other Programs
Lima South Terminal - Outfall 004 Stormwater Drainage Control | Item | Open | MCAP | BETLI00M2103 | Maintenance Framework | 1868987 | Roknich, Hunter | West | 6. Operational | Defined | Storm Water Management | 21167 |  |  | 21167.26 | 14129 | 7038 | Red |  |  |  | 21167 |  |  | 31000 |  |  | 31000 | Phase | 31000 | 94135 |  | 94135 | No | Green | 2021-07-01 | 2021-07-18 | 2021-07-18 | 2021-10-30 | 2023-04-07 |  |  | 3835.1 | 9496.8 | 797.36 | 7038 |  |  | 7038 | Red | [11 empty] | 3/2/2023 - Final electrical tie-ins being completed 3/3/2023. 2/2/2023 - Need to complete electrical connections to MOV 1/4/2023 - Need to complete electrical connections to MOV in January (9k variance in December) 12/2/2022 - Construction scheduled to begin 12/19 11/2/2022 - Scope sent to UM for review. Scheduled for late November mobilization. 10/3/2022 - Work scheduled to be completed early November (same time as BETLI Creek Walking Bridges) 9/2/2022 - Electrical quote received. SOW review still needed. Estimated completion mid October. 8/2/2022 - Waiting for electrical quote. Received construction quote. Estimated install moved to September/October. 7/5/2022 - Waiting for electrical quote. Estimated install in August 6/2/2022 - Quote received for installation. Estimated install in August. 5/3/2022 - Stakeholder review complete. Bid event was delayed. Will be onsite 5/4/2022 for bid walk. Expected construction start in August. 4/4/2022 - Holding Bid Event 4/6/22 3/2/22 - Working on RFP for bid event in April. Engineering complete. Valve and actuator have not shipped yet. 2/2/22 - Construction to begin mid/late Q2 1/4/2022 - Variance due to valve and actuator purchase 12/2/2021 - Variance due to difficulty getting vendor approved for sluice gate valve. Pushing engineering and valve purchasing to December forecast and construction to CY+1 Q2 due to long lead time (20 weeks) on valve 11/2/2021 - Valve to be purchased as soon as vendor is registered in COUPA. This is a long lead item (20 weeks). All support work will be completed by end Q4. $20k forecasted in CY+1 Q2 for valve installation and electrical work. 10/4/2021 - Awaiting Engineering Design. Expect to push interim AFE through for purchasing valve since it has long lead time 9/2/2021 - Working with Diamond Z on prelim engineering. Construction prelim scheduled for 10/2021 8/3/2021 - Diamond Z has surveyed and is working on preliminary engineering 7/2/2021 - AFE in approval process. DiamondZ Engineering to survey week of 7/5. Design to follow | 2023-03-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Terminals | BETLI - BET LIMA SOUTH TERMINAL |  | 14129 | 7038 |  |  | 26930 |  | Bonenberger, Mark | Votta, Joseph T. |  |  | 1 | 34049 |  | Guest, ProSight | Independent | Aqua | 2019-08-15 | Other Programs
Lima South Terminal (BETLI) Tank 110 Handrail Installation | Item | Open | MEXP | BETLI00E2301 | Maintenance Framework | 2095102 | Arch, Stefan | West | 6. Operational | Drawdown | Tanks | 8000 | 4500 |  | 12500 | 12501 | -1 | Yellow |  |  |  | 12500 |  |  | 15000 |  |  | 15000 | Full | 15000 | 8000 | 4500 | 12500 | No | Green | 2023-03-01 | 2023-03-16 | 2023-03-16 | 2023-05-31 | 2023-05-03 |  |  |  |  | 4000 | 4000 | 4000 | 4000 | 0 | Green |  |  | 4500 | [8 empty] | 5/1/2023 - Consolidated to install stairs on 5/2 and 5/3. Drawings reviewed and approved. No additional updates. 4/3/2023 - Project to complete installation of a handrail on the inside of tank 110 stairs. Continuing fabrication in April and installation in May. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Lima Terminals | BETLI - BET LIMA SOUTH TERMINAL |  | 4000 | 8500 |  |  |  |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 46769 |  | Stine, Carlton | JDE Child | Burnt Orange | 2023-03-14
Lima South Terminal (BETLI) Tank 110 Stair Handrail Installation | Item | Open | MCAP | BETLI00M2301 | Maintenance Framework |  | Arch, Stefan | West | 8. Canceled | Drawdown | Tanks |  | 0 |  | 0 | 0 | 0 | Green |  | 14563 | 14563 | -14563 |  |  | 14563 |  |  |  | Full | 14563 |  | 0 | 0 | No | Green |  |  |  | 2023-06-30 | 2023-10-27 | [12 empty] | 0 | [8 empty] | 4/3/2023 - Duplicate project and needs to be cancelled. | 2023-04-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Lima Terminals | BETLI - BET LIMA SOUTH TERMINAL |  |  | 0 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46720 |  | Arch, Stefan | Independent | Aqua | 2023-03-08
Lima South Terminal Transmix Offload | Item | Open | MCAP | BETLI00M2206 | Maintenance Framework | 2023246 | Henfling, Mike | West | 3. Active | Emergent | West | 53475 | 100000 |  | 153475.03 | 140042 | 13433 | Yellow | 140000 |  | 140000 | 13475 |  |  | 83000 |  |  | 83000 | Phase | 83000 | 114936 | 100000 | 214936 | No | Green | 2022-09-01 | 2022-09-21 | 2022-09-21 | 2022-09-01 | 2023-07-31 |  |  | 40505.62 | -13913.05 | 20449.54 | 6432.92 | 7000 | 7000 | -567 | Yellow |  |  | 12000 | 68000 | 15000 | 5000 | [5 empty] | 5-2-23 - Mech bids received, PO issued to Degen. Quote requested for electrical. Plan to submit full AFE in May. June/July installation, after load rack project. 4-4-23 - Foundations poured late March. All went in per plan - no changes to piping routing needed. Plan to obtain formal mechanical and electrical bids in April for June install. Need to wait until after meter proving on 5/19 -23 - Plan to pour foundation in March. Once foundation poured, will bid mechanical and electrical. Mechanical and electrical installation planned for late Spring. Once formal bids are in, will submit Full AFE. 3-10-23 - Reclass of Pump costs hit in January instead of February, hence $25k variance. 3-2-23 - Plan to pour foundation in March. Once foundation poured, will bid mechanical and electrical. Mechanical and electrical installation planned for late Spring. 2-2-23 - PO to Degen to be submitted today for pump foundation, planned for early March (or February if weather window found). Pump has been delivered. Electrical scope finalized. Want to bid mechanical after pump foundation is installed in March. Strainer and meter to be delivered in February. Mechanical and electrical installation planned for late Spring. 1-3-23 - IFB drawings completed. Pump foundation bid received and will discuss with site ops on timing (updated forecast to March). Pump components have been delivered and full pump assembly to be completed in January. Strainer and meter on order for 1Q 2023. Mechanical and electrical installation planned for 2Q. 12-5-22 - Design review completed 11/17/22. Drawings to be updated to Issue for Bid. Will not be able to install pump foundation in 2022. Pump components to be delivered to distributor mid-December, but full pump assembly to be delivered in January. Valves to be delivered in December. Strainer and meter on order for 1Q 2023. Mechanical and electrical installation planned for 2023. 11-2-22 - Missed forecast as reclass hit for September business rather than October. Engineering mostly complete, design review to be planned for mid-November. Concrete pump pad to be poured in December. Pump to be delivered in December. Mechanical and electrical installation planned for 2023. 10-3-22 - $10k to be re-classed to this project from LA00000M2202 in October. Pump still on order for December delivery. Mechanical and electrical installation planned for 2023. Engineering in October so-as to install concrete pump pad in November 2022. 9/12/2022 - moved cost from Lima Station project to this project since work is now at Lima South. Lima Station Transmix project will be canceled. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Terminals | BETLI - BET LIMA SOUTH TERMINAL |  | 47042 | 86433 | 20000 |  | 61461 |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 44497 |  | Gardner, Travis | Independent | Aqua | 2022-08-10 | Other Programs
Lima South TMS E-Room A/C Replacement | Item | Candidate | MCAP |  | Exempt | 2094430 | Burns, Richard | West | 2. Pending AFE |  | West |  | 12000 |  | 12000 | 12000 | 0 | Green | 12000 |  | 12000 | 0 | [9 empty] | 12000 | 12000 | No | Green | 2023-08-01 |  |  |  | 2023-08-31 | [15 empty] | 12000 | [5 empty] | 5/1/23 - received quotes on 4/20/23. 4/3/23 - Meeting with two contractors tomorrow to get pricing for mini-split system. 3/1/23 - nothing yet. | 2023-05-01 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Terminals | LI - LIMA SOUTH TERMINAL |  |  | 0 | 12000 |  |  |  | Gardner, Travis |  | N/A |  | 1 | 19735 |  | Guest, ProSight | Independent | Aqua | 2016-07-25 | Other Programs
Lima Station (LA) Replace Unit 3 Cabling | Item | Open | MCAP | LA00000M2205 | Maintenance Framework | 1955620 | Hassan, Mohammad | West | 6. Operational | Defined | Electrical | -116 |  |  | -116.47 | -116 | 0 | Green |  |  |  | -116 |  |  | 123000 |  |  | 123000 | Full | 123000 | 127867 |  | 127867 | No | Green | 2022-08-01 | 2022-08-25 | 2022-08-25 | 2023-04-30 | 2022-11-02 |  |  | 171.53 | -288 | 0 | 0 |  |  | 0 | Green | [11 empty] | 05-02-2023 - MNH - Will work on project closeout this month. 04-03-2023 - MNH - Will work on project closeout this month. 03-01-2023 - MNH - Will work on project closeout now. 02-01-2023 - MNH - Working on closeout items and still awaiting final invoice submital in OpenInvoice form vendor. Project EAC at $128K now. 01-03-2023 - MNH - Working closeout items and awaiting final invoice. Project EAC at $126K now. 12-01-2022 - MNH - Project is commissioned and working on punch list and closeout items now and awaiting final invoices. Project EAC now at $128K due to savings in inspection cost. 11-01-2022 - MNH - Cable was installed last month but had a failure. New cable being installed this week. Project EAC updated to $132K due to extra cost for testing and inspection. 2023 forecast of $58K moved into 2022. 10-04-2022- MNH - Material has been received ahead of schedule. Will plan on getting the cable installed this month. Project EAC still at $123K. 09-02-2022- MNH - AFE approved on 8/25. Will work with supply chain to run bid event next followed by selecting contractor and awarding work. If cable is received in time, this work could be completed in 2022. Current project EAC at $123,000. 08-17-2022 - MNH - Updating 2023 forecast to reflect the additional funding needed to get this project completed. If cable is received in time, this work could be completed in 2022. Current project EAC at $123,000. 08-01-2022 - MNH - Working on running bid event this week through supply chain followed by project AFE submittal late August to early September. 07-21-2022 - MNH - This project will need at least $110K to complete. We can buy the cable this year and plan on install in 2023. If cable comes early, we may be able to install this year but would need more funding. Adding $45K to 2023 Q2. 07-06-2022 - MNH - Delay in submitting Phase 1 due to other project workload. Phase 1 AFE to be submitted this month. Adjusted forecast.06-01-2022 - MNH - Have received some prices and this project would need more funding. We can buy the cable with 8 to 10 week lead time now and figure out a plan for installation later.Phase 1 AFE to be submitted this month. 05-03-2022 - MNH - Delay in submitting the AFE due to other project workload. Will plan on submittingPhase 1 this month now. Keeping forecast as is. 04-01-2022 - MNH - Will be submitting phase 1 AFEto order cable this month due to long lead time. Current quotes came in higher than budget of this project. 03-07-2022 - MNH - Just received quote from contractor and wire is showing16 week lead time. Moving project forecast out based on this new information. 03-01-2022 - MNH - Working with contractor on getting scope finalized and quote. Concerns were brought up regarding existing trays integrity soscope may increase to properly support the cable. 02-02-2022 - MNH - Will start working on SOW this month. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Pipelines | LA - LIMA STATION |  | -116 | 0 |  |  | 127984 |  | Ashley, Robert | Gardner, Travis W. |  |  | 1 | 38021 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
Lima Station (LA) Tank 401 - OOS API 653 Insp | Item | Open | MCAP | LA00000M2301 | Maintenance Framework | 2084431 | Arch, Stefan | West | 5. Deferred | Defined | Tanks |  |  |  | 0 |  | 0 | Green | 309261 |  | 309261 | -309261 |  |  | 272606 |  |  | 272606 | Phase | 272606 |  |  |  | No | Green |  | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2024-12-31 | [21 empty] | 1/30/23-CES-This project is being cancelled due to the need to find funding for South Texas IFRs. Tank is not due until 2025 and was included in the 2023 budget at the request of commercial. Removing forecast and changing status to deferred. | 2023-01-30 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Lima Pipelines | LA - LIMA STATION |  |  | 0 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44829 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Lima Station (LA) Tank 406 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | LA00000M2302 | Maintenance Framework | 2084369 | Arch, Stefan | West | 3. Active | Defined | Tanks | 14610 | 175000 |  | 189609.58 | 188736 | 873 | Yellow | 801177 |  | 801177 | -611567 |  |  | 412696 |  |  | 412696 | Phase | 412696 | 14610 | 825000 | 839610 | No | Green | 2023-03-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-12-31 |  |  |  |  | 13736.41 | 873.17 | 0 | 0 | 873 | Red | [8 empty] | 75000 | 100000 |  | 5/1/2023 - No updates, planning to take OOS beginning of November. Large scope anticipated. 4/1/2023 - Ordered material in March. Received word from Tank Integrity and Dave Clark on pushing this out till the end of the year to save on MCAP. Re-forecasted the project to November and December. Anticipating major scope due to fiberglass reinforced liner and patching completed at last OOS project. 3/1/2023 - Equipment was not ordered due to WO being issued on 2/23. Re-forecasted that amount and pushed back the project a month. Carlton and Dave stated this project may get pushed back to December due to tank program funding. Waiting on an answer from them, planned to begin early March but did not receive an answer. 2/1/2023 - Project to take tank OOS for API 653 internal inspection. Stakeholder call held on 1/18/2023. Planning to begin in early March. Funding is apart of the 2023 West Region MCAP tank Phase I AFE. Anticipating major repairs due to past inspection reports. February forecast to order equipment. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Lima Pipelines | LA - LIMA STATION |  | 13736 | 873 |  | 175000 |  | 650000 | Stine, Carlton | Stine, Carlton |  |  | 1 | 44830 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Lima Station 003 CV Actuator Replacement | Item | Candidate | MCAP |  | Exempt |  | Parker, Brian | West | 2. Pending AFE |  | Valves |  | 88000 |  | 88000 | 88000 | 0 | Green | 68000 |  | 68000 | 20000 | [9 empty] | 88000 | 88000 | No | Green | 2023-07-01 |  |  |  | 2023-09-29 | [14 empty] | 20000 | 39000 | 29000 |  |  |  |  | 2/24/23 - adding $20,000 to FCST since we need to install a new Daniel control valve when we install the new REXA actuator and moving this out to Q3 based on comments from local ops and not being able to obtain downtime. | 2023-02-24 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Pipelines | LA - LIMA STATION |  |  | 0 | 88000 |  |  |  | Oey, Alex |  |  |  | 1 | 44405 |  | Guest, ProSight | Independent | Aqua | 2022-08-04 | Other Programs
Lima Station 306 Line ANSI class 300 upgrades | Item | Open | MCAP | LA00000M2107 | Project Framework | 1900706 | Henfling, Mike | West | 6. Operational | Defined | Transient/Surge Mitigation | 34573 |  | 0 | 34573.37 | 33640 | 933 | Yellow |  |  |  | 34573 |  |  | 57000 | 442000 |  | 2090000 | Full | 2090000 | 2165683 | 0 | 2165683 | No | Green | 2021-11-01 | 2021-10-12 | 2021-10-12 | 2021-12-31 | 2022-09-23 |  |  | 3519.7 | 9383.39 | 20737.11 | 933.17 |  |  | 933 | Red | [10 empty] | 0 | 5-2-23 - Project ready for close. 4-4-23 - Job book Complete. Micro Motion densitometers delivered and invoiced. Project ready for close next month, want to wait until Reg Compliance confirms OQ issue response before closing project. 3-2-23 - Job book 90% complete. Micro Motion densitometers have shipped for March delivery. 2-2-23 - Job book to be completed in February. Micro Motion densitometers delayed to 3-3-22 ship date due to materials shortage. 1-3-23 - Supplemental AFE may be needed if not waived by PMO group due to overages on CWIP ($4k), safety auditors ($36k), and Ohio Use tax ($50k). Waiting a response from Ben Clark prior to any supplemental AFE submittal. Job book to be completed in January. Plan to prepare drawings for PH II work next year in December. Micro Motion densitometers delayed to 3-3-22 ship date due to materials shortage. 12-5-22 - Change order from contractor finalized and will be invoiced in December. As-builts and JDE completed. Job book to be completed in December or January. Plan to prepare drawings for PH II work next year in December. Micro Motion densitometers delayed to 3-3-22 ship date due to materials shortage. 11-2-22 - Punchlist and painting completed in October. Negotiating final change order with Bolt for outage work. As-builts/JDE/job book in November and December. Plan to prepare drawings for PH II work next year in November/December. Micro Motion densitometers delayed to 12-15-22 ship date. 10-3-22 - Outage work completed on 9/23, station was back up and running. Outage lasted 12.5 days rather than 8 days, but overall went well with no safety issues. Remaining punchlist work in October and engineering in November/December to complete as-builts and prepare drawings for PH II work next year. Micro Motion densitometers delayed to 12-15-22 ship date. 9-1-22 - missed forecast due to valve shipment delay from factory, remaining valves to ship 9/9 just prior to outage. Piping has been fully fabricated and final pressure test of pipe held9/1. 8-day outage on schedule for 9/12 thru 9/20. 8-2-22 - Piping fabrication in progress. Hydroexcavation complete for underground verifications - a few changes are required due to differences foundunderground, awaiting final change order cost from Bolt. Assume total change order with twonew valve needed is ~$80k out of contingency. 8-day outage still planned for 9/12 thru 9/20. Valves and meters to be delivered in mid- August. 7-5-22 - TRC completed and Full AFE approval in progress. Piping fabrication has commenced in the Bolt's shop. Hydro-excavation to begin 7/11 to verify underground piping and continue shop fabrication. 8-day outage still planned for 9/12 thru 9/20. Valves and meters to be delivered in early August. 6-1-22 - Contractor selected (Bolt Construction). Valve bid completed 6/1. TRC planned for 6/6/22. Construction start 6/20, with 3-4 weeks of on-site prep, 8-10 weeks of shop fabrication, and then 3-5 weeks of field install. 8-day large station outage tentatively planned for 9/12 thru 9/20. Forecast updated to match AFE request. 5-4-22 - Contractor bid event to close 5/12, and will have better understanding of total cost once bids arrive and decide if completing project in one or two phases. Valve bid event planned to open in May. Construction still tentative for Q3. 4-4-22 - Design Review completed 3/15. Long lead items (meters and strainers) have been ordered. Contractor and valve bid events planned to open in April, with construction still tentative for Q3. Upon receipt of contractor bids, may decide to phase project over two years. 3-2-22 - Design Review planned for 3/15. Construction still tentative for Q3. Will have two long lead items - (2) 6" turbine meters, likely Phase I AFE coming late March to order materials. 2-2-22 - Engineering 75% complete. Drawings should be ready for design review mid-February. 12/1/21 - engineering not all completed in November, about half done. Will complete in Dec. 10/20/21 - Engineering work started this week. 10/4/21 -Completed walk through on 9/28/21. Waiting on engineering proposal. 8/3/21 - still waiting on others for input. 7/2/21 - had call discussing details. Waiting on Hydraulics group and local team to itemize what lines and systems downstream of ANSI 600 meter run are affected by any pressure surges. 4/4/21 - no change; still need clarification for details of project. 9/4/19 - still waiting for clarification on the details of this project. 7/2/19 - I reached out to Zack O'Farrell-Huber and Alex Ferrari. This inbound meter piping is already ANSI 600. Not sure why this project is in existence. There are 2 valves downstream of the meter run at the manifold that are ANSI 150 and could potentially be over pressurized. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Pipelines | LA - LIMA STATION |  | 33640 | 933 |  |  | 2078302 |  | DiPillo, Evan | Gardner, Travis W. | N/A |  | 1 | 31345 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Other Programs
Lima Station 306 Line ANSI Class 300 Upgrades PH II | Item | Open | MCAP | LA00000M2305 | Project Framework | 2095083 | Henfling, Mike | West | 3. Active | Defined | Transient/Surge Mitigation | 27408 | 703000 |  | 730408.4 | 728900 | 1508 | Yellow | 731001 |  | 731001 | -593 |  |  | 42173 |  |  | 42173 | Phase | 42173 | 27408 | 703000 | 730408 | No | Green | 2023-03-01 | 2023-03-15 | 2023-03-15 | 2023-11-01 | 2023-12-01 |  |  |  |  | 12900 | 14508.4 | 10000 | 10000 | 4508 | Red |  |  | 9000 | 10000 | 75000 | 150000 | 240000 | 200000 | 13000 | 6000 |  | 5-2-23 - Engineering ongoing. Model review with Ops and Engineering group approved. Drawings to be completed mid-May, bid to open late May or early June. Full AFE in June, July start fabrication for Fall construction. 4-4-23 - Phase AFE approved. Design Review held 3/22; modified design to eliminate most tie-in welds and likely reduce outage time from 10 days to 2-3 days. Likely better luck finding outage time in Fall for project to be installed. Drawings to be modified in April, bidding in May, Full AFE in June, July start fabrication for Fall construction. 3-2-23 - AFE now planned for March for engineering and valves. Design review tentative for late March. Project timing still up in the air. 2-2-23 - Plan to submit phase AFE in February for engineering and valves. Will complete IFR drawings late February and hold a design review in early March. Will work with marketing/scheduling as to project timing - currently supply constraints that may push outage work to 2024. 1-3-23 - Plan to complete drawings by February. Will order long-lead twinseal valves early. Scheduling requested not to do work until Q3. Will require an approximate one week outage. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Pipelines | LA - LIMA STATION |  | 12900 | 33508 | 465000 | 219000 |  |  | DiPillo, Evan | Gardner, Travis W. |  |  | 1 | 43838 |  | Henfling, Mike | Independent |  | 2022-05-27 | Other Programs
Lima Station 501 CV Actuator Replacement | Item | Candidate | MCAP |  | Exempt |  | Parker, Brian | West | 2. Pending AFE |  | Valves |  | 67000 |  | 67000 | 67000 | 0 | Green | 67000 |  | 67000 | 0 | [9 empty] | 67000 | 67000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 38000 | 29000 | [5 empty] | 2/24/23 - moving this out to Q3 based on recent site visit with local ops. | 2023-02-24 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Pipelines | LA - LIMA STATION |  |  | 0 | 67000 |  |  |  | Oey, Alex |  |  |  | 1 | 44407 |  | Guest, ProSight | Independent | Aqua | 2022-08-04 | Other Programs
LIMA STATION ADD 6 CHANNEL RMU-3 FOR ANODE MONITORING | Item | Open | MCAP | LA00000M2303 | Exempt | 2085716 | Brown, Jeff | West | 6. Operational | Defined | Cathodic Protection | 6033 |  | 4476 | 6032.92 | 6176 | -143 | Yellow | 5500 |  | 5500 | 533 |  |  | 6175 |  |  | 6175 | Full | 6175 | 6033 | 4476 | 10509 | Yes | Red | 2023-03-01 | 2023-02-22 | 2023-02-22 | 2023-10-31 | 2023-04-30 |  |  |  |  | 3176 | 2856.92 | 3000 | 3000 | -143 | Yellow | [10 empty] | 4476 | 5-1-23 Project complete. Accrual is for material invoice not received from Watson Muter. 4-3-23 SCHEDULED TO BE INSTALLED APRIL - ACCRUAL IS FOR WATSON MUTER INVOICE. 3-2-23 AFE APPROVED-ORDER RMU-2-03-23 - MNH - AFE is routed | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Lima Pipelines | LA - LIMA STATION |  | 3176 | 2857 |  |  |  |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 25588 |  | Guest, ProSight | Independent | Aqua | 2017-09-07 | Int - Planned Corr & FI
Lima Station Control Valve Actuator Upgrades Phase 1 | Item | Open | MCAP | LA00000M2203 | Maintenance Framework | 1980126 | Parker, Brian | West | 4. On-Hold | Defined | Valves | 356 | 20400 |  | 20755.89 | 20756 | 0 | Green |  |  |  | 20756 |  |  | 61000 |  |  | 61000 | Phase | 61000 | 41317 | 20400 | 61717 | No | Green | 2022-09-01 | 2022-05-09 | 2022-05-09 | 2022-11-18 | 2023-09-29 |  |  | 235.46 |  | 120.43 | [11 empty] | 20400 |  |  |  |  | 2/28/23 - moving this project to On-Hold since there will be no activity for several months and I don't want to incur 1,000 in CWIP charges during no activity. 2/3/23 - during site visit with local ops on 1/24, it looks like we need to move the installs of the REXA actuators for the 306 and 003 out to Aug/Sep due to product availability issues (can't get the downtime). 1/3/23 - no change to status - need to schedule the install with local ops in Jan. This project is for the 306L REXA install on the existing Brodie valve that was recently rebuilt. 11/30/22 - at request of local ops, moving this install out to 2023 due to current workload and now being short one tech. 11/9/22 - REXA actuator received - scheduling a tentative date of 12/13 and 12/14 to install this at Lima. Entered Req into JDE on Nov 9th. 9/29/22 - var is due to REXA actuator shipping prior to Oct. Will work with local ops and vendor to get the installation scheduled. Forecasting that work for Nov right now until I get can something scheduled. 9/3/22 - requested update from Eastern Controls to confirm that new actuator is still scheduled for delivery in Oct. 8/1/22 - no change to status - expect delivery around end of Sep or first of Oct. 5/31/22 - PO issued on May 13th - expect delivery around end of Sep or first of Oct. 5/10/22 - entered Req into JDE for purchase of REXA actuator and entered Sole Source justification. 5/3/22 - submitted AFE to workflow on May 3rd - lead time due to quick connect cables at actuator end is 20 weeks so moving receipt of material to Oct with installation in Nov. 4/10/22 - with a 12 week lead time on REXA adjusting the FCST to what I expect will be receipt of actuators then installation to follow. 4/5/22 - REXA is working up the quotes for the two valves at Lima. Expect to see something in Apr then I can get an AFE routed for approval. Lead time is 12-14 weeks for REXA actuators. 2/1/22 - going to bid out a group of 4 REXA actuators to purchase for warehouse stock plus lead time of 12 weeks puts receipt of actuators around Jun with installation in Jul/Aug. | 2023-02-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Pipelines | LA - LIMA STATION |  | 356 | 0 | 20400 |  | 40961 |  | Oey, Alex | Gardner, Travis W. | N/A |  | 1 | 25443 |  | Guest, ProSight | Independent | Aqua | 2017-08-31 | Other Programs
Lima Station Fire Suppression System Controls Upgrade | Item | Candidate | MCAP |  | Maintenance Framework |  | Henfling, Mike | West | 2. Pending AFE |  | Fire Protection |  | 70000 |  | 70000 | 70000 | 0 | Green | 70000 |  | 70000 | 0 | [9 empty] | 130000 | 130000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [12 empty] | 0 | 0 | 5000 | 30000 | 35000 |  |  |  |  | 5-2-23 - On-site meeting held 4/19. Notes and initial scope developed, waiting on budgetary quote to decide how to finalize bid specification document. Plan to remove Halon system but potentially keep FM-200 system. Will open bid event late May or June. Could potentially require additional funds in 2023 to complete and/or a phased approach over two years. 4-4-23 - On-site scoping meeting with Greg J. and Vanguard planned for 4/19. Once scope developed, will bid with Lima North and Cuyahoga in May. 3-2-23 - No new updates. Plan for scoping site visit in late March. Bid event in April with Cuyahoga and Lima North. Left forecast as-is. 2-2-23 - Discussed project with Ops and Greg J. in January. Plan to complete a site visit in March and put together a scope for bid event with Cuyahoga and Lima North. Left forecast as-is. 1-3-23 - Left forecast as-is. | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Pipelines | LA - LIMA STATION |  |  | 0 | 70000 |  |  |  | Jakubowski, Gregory |  |  |  | 1 | 45379 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Other Programs
Lima Station Leak Detection - 2023 | Item | Candidate | MCAP |  | Maintenance Framework |  | Hassan, Mohammad | West | 2. Pending AFE |  | Leak Detection |  | 380000 |  | 380000 | 380000 | 0 | Green | 380000 |  | 380000 | 0 | [9 empty] | 380000 | 380000 | No | Green | 2023-06-01 |  |  |  | 2023-09-30 | [13 empty] | 50000 | 100000 | 150000 | 80000 |  |  |  |  | 05-02-2023 - MNH - Will work on submitting AFE this month. June Forecast reduced and added to Q3. 03-31-2023 - MNH - Site visit complete, SOW & AFE development underway next month. 02-28-2023 - MNH - Will plan a site visit next week. 02-01-2023 - MNH - Will start looking at scope of work this month. 01-03-2023 - MNH - Will start looking at scope of work next month. 12-1-2022 - MNH - Will start looking at scope of work in Q1 2023. | 2023-05-02 |  |  | West | Pipelines and Terminals | Integrity |  | Lima Pipelines | LA999A3 - LIMA TO SHELL (10IN/16IN) |  |  | 50000 | 330000 |  |  |  | Guenther, Steve |  | N/A |  | 1 | 25479 |  | Guest, ProSight | Independent | Aqua | 2017-09-01 | Leak Detection
Lima Station PLC Device & Hardware Additions | Item | Open | MCAP | LA00000M2206 | Maintenance Framework | 2013331 | Hassan, Mohammad | West | 6. Operational | Emergent | Instrumentation & Controls | 2999 | 300 |  | 3299.15 | 3299 | 0 | Green |  |  |  | 3299 |  |  | 23000 |  |  | 23000 | Full | 23000 | 22689 | 300 | 22989 | No | Green | 2022-09-01 | 2022-08-25 | 2022-08-25 | 2022-10-07 | 2022-12-31 |  |  | 2870 | 129.15 | [9 empty] | 300 | [7 empty] | 05-02-2023 - MNH - This project is complete now. Under punch list items, scaling change needs to be implemented which will be handled between Operations & ARSEAL once a station shutdown can be coordinated. Will keep MOC open for Operations to coordinate this downti 04-03-2023 - MNH - This project is complete now. Under punch list items, scaling change needs to be implemented which will be handled between Operations & ARSEAL once a station shutdown can be coordinated. Will keep MOC open for Operations to coordinate this downtime. 03-01-2023 - MNH - This project is complete now. Under punch list items, scaling change needs to be implemented which will be handled between Operations & ARSEAL once a station shutdown can be coordinated. Will keep MOC open for Operations to coordinate this downtime. 02-01-2023 - MNH - This project is complete now. Under punch list items, scaling change needs to be implemented which will be handled between Operations & ARSEAL once a station shutdown can be coordinated. Will keep MOC open for Operations to coordinate this downtime. 01-03-2023 - MNH - Remaining punch list items to be completed next month due to Vendor & Buckeye Tech schedule issues. Project EAC at $23K still. 12-01-2022 - MNH - Remaining punch list items to be completed this month or Jan due to Vendor & Buckeye Tech schedule issues. Project EAC at $23K. Moving $4K in Q1 of 2023. 11-02-2022 - MNH - Remaining punch list items to be completed this month or early next month if Eng drawings request takes longer than expected. Project EAC at $23K. 10-03-2022 - MNH - Majority of the work got completed last month ahead of schedule. Some remaining & punch list items to be completed this and next month. 09-02-2022 - MNH - AFE approved on 8/25 and PO cut to contractor on 8/29. Will plan on getting this work done in October & November. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Pipelines | LA - LIMA STATION |  | 2999 | 300 |  |  | 19690 |  | Forsey, Frank |  |  |  | 1 | 45090 |  | Guest, ProSight | Independent | Aqua | 2022-08-18 | Other Programs
Lima Station Sample Building Foundation Repair | Item | Candidate | MEXP |  | Exempt |  | Henfling, Mike | West | 5. Deferred |  | West |  | 0 |  | 0 | 0 | 0 | Green | 20000 |  | 20000 | -20000 | [9 empty] | 44000 | 44000 | No | Green | 2024-06-01 |  |  |  | 2024-07-31 | [13 empty] | 0 | [7 empty] | 5-2-23 - Project Deferred, no new updates 4-4-23 - Project has been deferred to 2024. Zeroed forecast. Met with contractor in March - notes have been uploaded to OPPM for 2024 project. 3-2-23 - Plan to meet contractor in March/April during next site visit to review project 2-2-23 - Reviewed project with Ops in January. Left forecast as-is. 1-3-23 - Left forecast as-is. | 2023-05-02 |  |  | West | Pipelines and Terminals | Station/Terminal |  | Lima Pipelines | LA - LIMA STATION |  |  | 0 |  |  |  | 20000 | Gardner, Travis |  |  |  | 1 | 45381 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Other Programs
Lima Station Tank 408 Booster Pump Foundation Restoration | Item | Open | MCAP | LA00000M2304 | Maintenance Framework | 2094825 | Roknich, Hunter | West | 3. Active | Defined | Rotating Equipment | 25000 | 104500 |  | 129500 | 117000 | 12500 | Red | 113000 |  | 113000 | 16500 |  |  | 45307 |  |  | 45307 | Phase | 45307 | 25000 | 104500 | 129500 | No | Green | 2023-04-01 | 2023-03-10 | 2023-03-10 | 2023-06-30 | 2023-07-31 | [5 empty] | 25000 | 12500 | 12500 | 12500 | Red |  |  | 12500 |  | 92000 | [6 empty] | 5/2/2023 - See below 4/4/2023 - Diamond Z Engineering working on drawing package. 10/11/2022 - Pump on order for inventory stock. getting work quoted for CY+1 8/3/2021 - Site visit for scope development week of 8/9 7/2/2021 - Site visit to be made for scope development mid-July | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Pipelines | LA - LIMA STATION |  |  | 37500 | 92000 |  |  |  | Posipanko, Dan | Gardner, Travis W. |  |  | 1 | 34444 |  | Guest, ProSight | Independent | Aqua | 2019-08-26 | Other Programs
Lima Station Tank Booster Pump Starters Upgrade | Item | Open | MCAP | LA00000M2201 | Maintenance Framework | 1955716 | Fink, Ryan | West | 3. Active | Defined | Electrical | 47880 | 44000 |  | 91879.85 | 91843 | 36 | Yellow |  |  |  | 91880 |  | CY Budget Estimate Incorrect | 100000 |  |  | 100000 | Full | 100000 | 51852 | 44000 | 95852 | No | Green | 2022-03-01 | 2022-03-11 | 2022-03-11 | 2022-06-03 | 2023-06-30 |  |  | 44623.11 | 1923.08 | 797.2 | 536.46 | 500 | 500 | 36 | Yellow |  |  | 1000 | 29000 | 4000 | 10000 | [5 empty] | 4/28 RRF - TBD install 6/2 or 6/14, EAC $96k 4/6 RRF - TBD install 6/2, EAC $96k 3/24 RRF - Install TBD 6/2, contingency in August. EAC $96k 3/2 RRF - Plan for April Install, EAC $93k 2/2 RRF starters delivered., install prep 1/17 RRF - starters delivered. 1/13 RRF - shipped 1/11. 01/04/2023 RRF - Still delay on material - No updates since december. 12/2 RRF - Still delay on material 11/2 RRF - Material delay to 2023 10-20-2022 - MNH - Added 2023 forecast based on last note entry from Ryan. 10/3 RRF - Material Delay to unknown date, no time to install in 2022, move to 2023. 2023 forecast Jan 0, Feb 49k, Mar 1k, Apr 30k, May 3k, June 13k (Contingency,Allocation,Interest) 9/2 RRF - Material delay to 10/14, moved out sched. Will miss full outage sched on 9/12. Plan for Nov install. 8/2 RRF - Material moved to 8/24 ship, install 9/12, moved contingency to dec 7/11 RRF - material delay again, moved out 1 mo. 6/14 RRF - Material ship delay to 7/18, install AFTER 8/1 5/31 RRF - Install TBD July 5/20 RRF - Material delay from 5/1 to 6/24 ship date. push out 2 month. 5/3 RRF - on track 4/4 RRF - material to arrive in May 3/8 RRF - forecast 4 starters AFE 3/8 RRF - forecast for 8 starters, based on quotes, full afe 3/1 RRF - Forecast for 8 starters, pending labor estimates. EAC 141k. Budget 108k. | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Pipelines | LA - LIMA STATION |  | 47343 | 30536 | 14000 |  | 3972 |  | Ashley, Robert | Carnes, John L. |  |  | 1 | 34446 |  | Guest, ProSight | Independent | Aqua | 2019-08-26 | Other Programs
Lima Station Transmix Offload | Item | Open | MCAP | LA00000M2202 | Maintenance Framework | 1970410 | Henfling, Mike | West | 8. Canceled | Defined | West | -129 |  |  | -129.05 | -129 | 0 | Green |  |  |  | -129 |  |  | 82000 |  |  | 82000 | Phase | 82000 | 0 |  | 0 | No | Green | 2022-04-01 | 2022-04-06 | 2022-04-06 | 2022-09-01 | 2022-12-31 |  |  | -129.05 | [18 empty] | 2/3/2023 - variance is pump was ordered on original project and will need reclassed to BETLI project. forecasted reclass in February. 11-2-22 - Plan to cancel project. New project located at Lima South Terminal BETLI00M2206. $129.05 of CWIP and Interest charged in September, does this need reclassed?10-3-22 - Reclass costs to BETLI00M2206 in October and zero forecast. Project then to be cancelled.9-1-22 - Reduced forecast due to pump delivery. Pump on order for December delivery. Mechanical and electrical installation planned for 2023. Exploratory hydroexcavation completed 9-1 to determine location for pump pad. Engineering in Sept. and October. 2022 construction planned to be pump pad only in October. 8-2-22 - Working on pump design and plan to get pump on order in August. Overall plan to hydro excavate and install pump pad in September while awaiting pump delivery. Construction planned for October/November pending pump delivery. Still may eventually cancel this project and create new project for BETLI location. $4.1k to be re-classified to another project in July did not hit cost report yet as of 8/1/22. Reduced overall forecast due to shift in design from 6/22 visit and 7/5 email confirmation from Ops leadership.7-5-22 - Site visit held 6-22 to review Lima South Terminal (BETLI) as a possible option for transmix offload from Lima Station (LA), to avoid environmental issues and save cost vs. install at LA. BETLI work is feasible, and looks to be moving forward. Will need engineering and pump design completed in July and August. May eventually cancel this project and create new project for BETLI location. Will work through those details in July. Updated forecast to show engineering in July and August. Kept remaining forecast but pushed. $4.1k to be re-classified to another project in July.6-1-22 - stakeholder review held mid-May to agree upon a location for the pump skid (inside the dike). Still working through environmental issues with theplan forward, as further issues arose after stakeholder call. Pushed forecast another month.5-4-22 - Site visit late Aprilto review newlocation for pump skid per stakeholder review call mid-April. Plan to hold another stakeholder review with new location early May. Once agreed-upon, will order long lead pump skid. Construction planned for early Fall due to 12-week lead time of pump skids.Pushed forecast due to re-design/new location of pump skid.4-4-22 - Phase AFE submitted late March to allow for ordering of long-lead pump skid and to complete engineering. Site visit held in March and stakeholder call to review conceptual design planned for April. Construction planned for late summer.3-2-22 -Spread out initial engineering/materials phase of forecasts. Site visit planned 3/15. Engineering early Q2 and construction Q3 or early Q42-2-22 - No change to forecast. Engineering early Q2 and construction Q3 or early Q4 | 2023-02-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Pipelines | LA - LIMA STATION |  | -129 | 0 |  |  | 129 |  | Gardner, Travis | Carnes, John L. | N/A |  | 1 | 31250 |  | Guest, ProSight | Independent | Aqua | 2018-08-28 | Other Programs
Lima Station Unit 5 Replace Seals and Rotating Element | Item | Open | MEXP | LA00000E2303 | Exempt | 2084337, 2109750 | Gardner, Travis | West | 3. Active | Drawdown | Rotating Equipment |  | 58000 |  | 58000 | 58000 | 0 | Green |  |  |  | 58000 |  |  | 58000 |  |  | 58000 | Full | 58000 |  | 58000 | 58000 | No | Green | 2023-06-01 | 2023-04-03 | 2023-04-03 | 2023-06-02 | 2023-06-02 | [13 empty] | 58000 | [7 empty] | 5/3/2023 - scheduling for June. 4/4/2023 - emergent project working on issuing PO's | 2023-05-03 | Griest, Barbara |  | West | Pipelines and Terminals | Station/Terminal |  | Lima Pipelines | LA - LIMA STATION |  |  | 58000 |  |  |  |  | Posipanko, Dan | Gardner, Dale |  |  | 1 | 46844 |  | Gardner, Travis | JDE Child | Burnt Orange | 2023-03-27
Line 160 – Cal Sag Bridge | Item | Open | MCAP | PN160AGM1801 | Maintenance Framework | 1475006 | Stalbaum, Cameron | West | 7. Closed | Defined | Exposure Remediation | -9880 |  |  | -9880.34 | -9880 | 0 | Green |  |  |  | -9880 |  |  | 93000 | 548000 |  | 641000 | Phase | 641000 | 644822 |  | 644822 | No | Green | 2022-03-01 | 2018-11-01 | 2018-11-01 | 2018-07-01 | 2022-10-15 |  |  | 119.66 | -10000 | [17 empty] | 1/3/23 -This variance is for a WM invoice that came in late. 12/2/22 - Variance is for the 42K change order for Michels. This was to cover the down time for the corrosion inspections that were found while painting the span. Since we were under the total project amount I did not submit additional funding request to cover each of the instances where additional corrosion chains were found. 11/1/22 - Holding accrual for Pugh for the remainded of the inspection. 10/3/22 - Project is completed. The variance is for completing more work in August than originally anticipated. We are approximately 52K underbudget right now. However, working through some change orders with Michels currently. There is approximately 25K that could be forthcoming. 9/5/22 - Variance is for Michels getting mobilized a week ahead of schedule. Forecast covers 333K for Michels to finish their contract as well as inspection and disposal. 8/2/22 - 10K variance is for a bond permit the city required. Michels anticipates on mobilizing to the site the last week of August, after Granville Demarcation Tie Ins are completed. This will push the majority of the work into september. 7/5/22 - Michels has requested this project to start in August once they are completed with the Granville Hydro Test and Demarcation work. 6/1/22 - Waiting on 3 permit approvals before starting work. Michels is working on Site Safety Plan and tentative kickoff meeting for June 20th. 5/2/22 - Working on permitting. Project was awarded to Michels. 4/4/22 - Variance is for TAS starting permitting work. I'm working on trying to pull this project forward so we do not have to deal with pipe sweating. 3/2/22 - Working with supply chain on bid event. Anticipate having contractor pricing back a the end of March.2/17/21 - Project changed to pending, we anticipate this project will go in 20216/18/20 - FCST $1 in Dec to keep this one in the queue so that it can be properly FCST for 2021.1/8/20 - Cameron working to findoutinformation on this project. Currently unknown where we stand with this project.7/1/19 received painting bids. Working with Geeding to obtain pricing on the barge for river work6/3/19 Will hold paint walk/event this month. Plan to use mechanical contractor from integrity dig work for obtaining permits for barge5/1/19 Working to obtain painting pricing and schedule for painting activities4/1/19 will meet with supply to discuss contracting strategy for this project3/4/19 Kick-off meeting this month. Will identify timing and contractors2/1/19 Will schedule kick-off meeting for repairs this month1/2/19 Will work towards closing this month12/3/18 Project is complete11/2/18 Awaiting inspection report10/2/18 Inspection is complete awaiting report from Midwestern on findings. 9/24/18 During the inspection corrosion was identified and assessed for repair. The assessment determined that B sleeve repair was required. It was installed. Cost updated to reflect9/4/18 Work to be completed this month8/1/18 Waiting for permits to be secured to execute work from barge7/2/18 Will issue PO to Midwestern for work, and hold stakeholder meeting.6/4/18 AFE being routed5/1/18 Received proposal and submitted AFE4/3/18 Waiting on proposal from Midwestern for work3/2/18 Will reach out to contractorwho previously executed work and get started on a proposal for inspectionProject deferred beyond 2017.2018 forecast represents FEEDwork.Constructiontargeted for 2019 | 2023-01-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Argo | PN160AG - PEOTONE TO ARGO |  | -9880 | 0 |  |  | 562012 |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 21867 |  | Administrator, System | Independent | Aqua | 2016-10-24 | Int - Accel Exposures
Lorain HVAC replacement | Item | Candidate | MCAP |  | Exempt | 2094433 | Burns, Richard | West | 2. Pending AFE |  | West |  | 26000 |  | 26000 | 26000 | 0 | Green | 26000 |  | 26000 | 0 | [9 empty] | 26000 | 26000 | No | Green | 2023-10-01 |  |  |  | 2023-10-31 | [17 empty] | 26000 |  |  |  | 5/1/23 - no change. 4/3/23 - getting recommendations / pricing from local contractors. 3/1/23 - nothing yet. | 2023-05-01 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | North East Ohio | BETOR - BET LORAIN |  |  | 0 |  | 26000 |  |  | Gardner, Travis |  |  |  | 1 | 41768 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Lorain Terminal (BETOR) Tank 8 - OOS API 653 Insp | Item | Open | MCAP | BETOR00M2302 | Maintenance Framework | 2084432 | Arch, Stefan | West | 3. Active | Defined | Tanks | 9794 | 185000 |  | 194794.18 | 209372 | -14578 | Yellow | 264477 |  | 264477 | -69683 |  |  | 239157 |  |  | 239157 | Phase | 239157 | 9794 | 185000 | 194794 | No | Green | 2023-03-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-08-31 |  |  |  |  | 9372.42 | 421.76 | 7500 | 7500 | -7078 | Red |  |  | 35000 | 120000 | 30000 | [6 empty] | 5/1/2023 - Planning to clean and inspect at the end of May. Jumper line being fabricated now and will be completed within two weeks. No spend in April due to not ordering valves. it is re-forecasted to May as well as cleaning, inspector services, and inspection. 4/3/2023 - Product in tank 7 is currently being transferred to tank 1. Once product is transferred, tank 7 will come OOS for modifications for temporary Ethanol, tank 8 will come OOS. Planning to begin work in late April/early June. 3/1/2023 - Planning to begin in April. Sent support project for scope review, waiting for management approval. Anticipating minor repairs to tank 8. 2/1/2023 - Project to take tank 8 OOS for an API 653. Project walked down on 1/6/2023. Support project to install jumpers and install liner in tank 7 for temporary Ethanol storage required. Anticipating minor repairs. Planning to begin in April. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | North East Ohio | BETOR - BET LORAIN |  | 9372 | 155422 | 30000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44835 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Lorain Terminal (BETOR) Tank 8 OOS Support Project | Item | Open | MCAP | BETOR00M2301 | Maintenance Framework | 2051689 | Arch, Stefan | West | 3. Active | Defined | Tank Outage | 184631 | 113000 |  | 297630.58 | 309615 | -11985 | Yellow | 190000 |  | 190000 | 107631 |  |  | 31000 | 339000 |  | 370000 | Phase | 370000 | 192641 | 113000 | 305641 | No | Green | 2022-12-01 | 2022-12-07 | 2022-12-07 | 2023-08-01 | 2023-07-31 |  |  | 12662.82 | 1882.02 | 70.31 | 170015.43 | 160000 | 160000 | 10015 | Yellow |  |  | 88000 |  | 25000 | [6 empty] | 5/1/2023 - Tank 7 was cleaned and liner installed. Up Close seal inspection completed on 4/23 by DJA and found no repairs needed. Currently fabricating pipe and will be installed in two weeks by Bolt. Once installed, tank 7 will be ready for Ethanol service. Forecasting for May includes remaining piping cost and inspector services. 4/3/2023 - Sent out project to bidders and walked down. Received bid packages back on 3/24. Went with Bolt but waiting on Supply Chain to send the LOI and get me the bid package for the materials. Variance in March due to lag with supply chain. Planning to fabricate piping and install early May for tank 8 outage. Currently tank 7 is being drawn down for cleaning, seal inspection, and installation of a liner. Full AFE submitted on 3/27. 3/1/2023 - IFC drawings received and reviewed with Diamond Z and Operations. Scope developed and sent to management for review. Planning to go to bid in the coming week. Fabrication to begin in March once awarded. Tank 8 will be cleaned and liner installed in April. Phase II AFE will be submitted once quotes are received for the mechanical portion. Variance in February due to me missing forecasting the engineering and design. 2/1/2023 - Diamond Z is currently engineering and designing the jumper lines. Once design is accepted, will go to bid for jumper line install. A Phase II AFE will be submitted once estimates are realized. Planning to complete installation by the beginning of April. 1/3/2023 - Project began in 2022 for facility scanning, walkdown, and preliminary drawing. Planning to complete engineering in January or early February. Forecast readjusted to reflect bidding, fabrication, and install. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | North East Ohio | BETOR - BET LORAIN |  | 14615 | 258015 | 25000 |  | 8011 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44565 |  | Guest, ProSight | Independent | Aqua | 2022-08-12 | Int - Tanks
Louisville (BETVL) Load Rack Control PLC Upgrade | Item | Open | MCAP | BETVL00M2301 | Maintenance Framework | 2052435 | Hassan, Mohammad | West | 3. Active | Defined | Instrumentation & Controls | 28489 | 62000 |  | 90489.09 | 90029 | 460 | Yellow | 90000 |  | 90000 | 489 |  |  | 48000 |  |  | 48000 | Phase | 48000 | 28489 | 62000 | 90489 | No | Green | 2023-01-01 | 2022-12-15 | 2022-12-15 | 2023-07-31 | 2023-07-31 |  |  | 19937.78 | 850.95 | 7240.7 | 459.66 |  |  | 460 | Red |  |  | 2000 | 15000 | 30000 | 15000 | [5 empty] | 05-02-2023 - MNH - We are getting IFB drawings and scope completed to get bids next from electrical contractors. Tentative plan is to have PLC commissioned by end of June. Project EAC still at $90K but will be finalized based on Phase 2 AFE. 04-20-2023 - MNH - Delay from Local Tech to verify drawings. Current plan is to have this done in June, but most likely get pushed to July. Adjusting forecast. EAC still at $90K. 03-31-2023 - MNH - Project review drawings are ready but will need to be verified by local Tech which is talking longer. Once IFB set is done, we will get prices from electrical contractors followed by submitting Phase II final AFE. Project EAC at still at $90K. 03-01-2023 - MNH - Project design underway and most of material received. Once design is done, we will get prices from electrical contractors. Project EAC at still at $90K. 02-01-2023 - MNH - PO for design and material issued. Project kick-off call with stakeholders scheduled for this month. Project EAC at still at $90K. 01-03-2023 - MNH - Phase 1 AFE got approved last month. Will cut PO to contractor this month to get design started and procurement done. Project EAC at $90K. 12-1-2022 - MNH - Will start looking at scope of work & phase 1 AFE this month. 11-01-2022 - MNH - No updates from last month. If there is some time, Phase 1 AFE to be routed by end of this month. 10-04-2022 - MNH - No updates from last month. If there is some time, Phase 1 AFE to be routed by end of this month. 09-02-2022 - MNH - No updates from last month. If there is some time, Phase 1 AFE to be routed by end of next month. 08-01-2022 - TWG pushed work to 2023 money moved to DD. MNH - Received updated quote from vendor. Will plan on submitting Phase 1 AFE this month and get design & procurement started. Will adjust forecast and move money in 2023 etc. once lead times are confirmed. 07-27-2022 - MNH - Reducing the budget by $8K to fund Napoleon Terminal (BETNP) Rackpump PLC Upgrade (OPPM ID 38062). 07-21-2022 - MNH - Per discussion with program owner, this project may push into 2023 due to long lead times of material and current project work load. Will adjust forecast and move money in 2023 etc. once lead times are confirmed. 06-29-2022 - MNH - Reducing the budget by $3K to fund Flint Terminal (BETWF) Ops Rm Tank Alarm PLC Upgrade (OPPM ID 38041). AFE for this project has beendelayed and some work on this project may move to 2023. Updated budget is $68K for now. 06-01-2022 - MNH - Delay in submitting AFE due to other project workload and emergent project work. Will submit AFE this month. Adjusting forecast. 05-03-2022 - MNH - Have received some quotes from vendors. Will plan on submitting AFE this month. Moved June forecast into Q3. 04-01-2022 - MNH - Will start working on SOW this month. 03-01-2022 - MNH - Will start working on SOW in April. Forecast pushed back a month. 02-02-2022 - MNH - Will start working on SOW in March. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Southern Ohio | BETVL - BET LOUISVILLE |  | 28029 | 17460 | 45000 |  |  |  | Forsey, Frank | Carnes, John L. |  |  | 1 | 38052 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
Louisville Dock Mooring Cell Repair | Item | Candidate | MEXP |  | Maintenance Framework |  | Parker, Brian | West | 2. Pending AFE | Defined | Marine |  | 90000 |  | 90000 | 90000 | 0 | Green | 90000 |  | 90000 | 0 | [9 empty] | 90000 | 90000 | No | Green | 2023-08-01 |  |  |  | 2023-09-30 | [15 empty] | 35000 | 55000 |  |  |  |  | 9/3/22 - this work will be executed in 2023 when other refurbishments are implemented and rolled into a larger SOW. Cancelling this project for 2022 due to the cost to mobilize a barge and complete this work is cost prohibitive. 7/6/22 - 5-year dock inspection is scheduled for July 12 - 13 and this will be looked at during the inspection. 5/31/22 - this will be looked at during 5-year inspection of the marine dock. 4/5/22 - quote came back at 45,000 (15,000 of this cost is mobilization). Angela Mirandi is aware of this cost and I would anticipate that this project will probably get pushed out to a future year and adjust the budget if funding is tight in 2022. Moving this FCST out to Sep. 2/10/22 - send email to Steve Hawthorne with Southern Marine Construction to update proposal/quote and get on his schedule for 2022. | 2022-09-03 |  |  | West | Pipelines and Terminals | Station/Terminal |  | Southern Ohio | BETVL - BET LOUISVILLE |  |  | 0 | 90000 |  |  |  | Spari, Markella |  |  |  | 1 | 38015 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Marine
Louisville Load Rack Cracks In Concrete | Item | Open | MEXP | BETVL00E2201 | Maintenance Framework | 1955607 | Parker, Brian | West | 7. Closed | Defined | Truck Racks | 41 |  |  | 41.27 | 41 | 0 | Green |  |  |  | 41 |  |  | 10000 |  |  | 10000 | Full | 10000 | 4880 |  | 4880 | No | Green | 2022-10-01 | 2022-03-10 | 2022-03-10 | 2022-06-30 | 2022-11-09 |  |  | 41.27 | [18 empty] | 12/14/22 - just approved last invoice on the 9th, PO and WO closed - ready to closed by accounting. 12/2/22 - accruing 2400 based on previously billed amount for completing Bay 1 and sent email to contractor requesting invoice. Ready to close after processing this invoice. 11/18/22 - Bay 2 sealing of cracks was completed on Nov 9th. 11/7/22 - var is due to only being able to fill cracks in Bay 1 in Oct.. Bay 2 work is scheduled for Nov 9th. Accruing 5,345 for contractor in Oct. 9/29/22 - sent email to everybody on Sep 28th to confirm outage for week of Oct 17th for Bay 1 (West) and week of Oct 24th for Bay 2 (East) to fill the cracks. 2-part epoxy requires 48 hrs for curing so looking at 2.5-3 days for each bay. 9/3/22 - received revised quote from East & Westbrook to fill the cracks in both bays. Had a call with local ops to review all projects at Louisville and they are good with the plan and notification requirements. Work should be completed no later than Oct. 8/1/22 - need to hold off on filling cracks in concrete under the rack until we saw cut and clear the drain blockage on the West bay. Moving this out to Oct. 7/3/22 - East & Westbrook was finally reactivated week of Jun 27th - need to hold off on scheduling this work since we now need sawcut concrete under West rack to clear drain line obstruction. We can seal cracks once we have this emergent work completed. Moving FCST out to Sep. 5/31/22 - no change in status from the first of May - no word yet on reactivation of vendor. 5/3/22 - still waiting on getting East & Westbrook reactivated as a vendor in JDE. I'm sending the details to Tammy to see if she can help with this since it's been 1 month plus trying to get this vendor reactivated. Moving FCST out to Jul. 4/5/22 - supply chain is working to get East & Westbrook reactivated as a vendor in JDE. Once this occurs I can get a PO issued and get this scheduled with local ops. 3/7/22 - submitted AFE to workflow for approval routing. Budget was 14,000 plan to use about 7,500 to complete this work and have about 2,500 in contingency. | 2022-12-14 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Southern Ohio | BETVL - BET LOUISVILLE |  | 41 | 0 |  |  | 4838 |  | Younce, Michael | Gardner, Travis W. |  |  | 1 | 41892 |  | Guest, ProSight | Independent | Aqua | 2021-08-22 | Other Programs
Louisville Rack Control Valve Repairs 2022 | Item | Open | MEXP | BETVL00E2207 | Maintenance Framework | 2012438 | Parker, Brian | West | 3. Active | Emergent | Truck Racks | 17806 | 25000 |  | 42805.53 | 46519 | -3714 | Yellow | 29000 |  | 29000 | 13806 |  |  | 17000 | 67000 |  | 84000 | Full | 84000 | 48513 | 25000 | 73513 | No | Green | 2022-10-01 | 2022-08-16 | 2022-08-16 | 2022-12-31 | 2023-06-30 |  |  | 0 | 2419.17 | 18199.86 | -2813.5 | 17900 | 17900 | -20714 | Red |  | Buckeye/Customer Schedule | 17000 | 8000 | [7 empty] | 4/30/23 - Var is due to local ops busy with other work and not getting the 210 valves shipped back to Franklen Equipment until late Apr. Approved final Spade invoice for 6,833.02 in late Apr. Should have 4 repaired 210 valves around mid-May with install in late May or early June - working to obtain a quote from Degen for the installs. EAC is at 75,345. 3/31/23 - accruing 9,900 for Spade for work completed on Mar 7th. Jason is getting two 210 valves ready to ship back to Franklen today so expect them back in about 2 weeks. Should get last set of 210 valves swapped out in Apr and last refurbished valves invoiced in May. 3/9/23 - swapped out two more 210 valves on Mar 7th so this next set should ship out on next week to Franklen for another 1-2 week turnaround. Bay 1, Arm 15 PBOB and Bay 2, Arm 25 PBOB were changed out on Mar 7th. 2/28/23 - two rebuilt 210 valves will be shipping this week to the terminal and local ops will get these installed week of Mar 6th with assistance from Spade. 2/7/23 - var is due to local ops not using Spade for 2 swap outs on Jan 19th and not getting the old valves turned around with Franklen. Bay 2, 21 Conv. Gas and 22 Conv, Gas were swapped out on Jan 19th. Local ops will ship the 2 valves to Franklen for rebuild. Moving FCST out to Mar timeframe. Re-accruing Spade cost for Jan. 1/2/23 - var is due to local ops not being available to change out another set of valves in Dec due to other terminal project workload. Still waiting on an invoice from Spade that should be ~ 7,500. 11/28/22 - var is due to only completing one set of install/repair in Nov. Should have two repaired 210 valves back at Louisville around the 1st of Dec then need to schedule Spade for installation. Only expect to get one set changed out in Dec then two more sets in Q1 2023. 10/29/22 - first two 210 valves were swapped out on 10/27 - sending the old valves back to Franklen for repair. Bay 2, 21 ULSD and 23 ULSD were swappped out in Oct.Will accrue 7,500 for Spade in Oct. 10/21/22 - entered Req to rebuild 8 - 210 valves. 10/5/22 - the 2 new 210 valves should have shipped on 9/30 to Louisville. Entered Req. for Spade to change out 2 control valves during 4 mobilizations. 9/3/22 - PO issued to Franklen Equipment for 2 new 210 Valves on Aug 17th - lead time is 8-10 weeks which is last week in Oct. Going to plan for some delays in getting all valves swapped out in 2022 so moving some of this FCST out into Jan 2023. 8/5/22 - Phase I AFE was submitted on 8/4 to get 2 new 210 valves purchased. | 2023-04-30 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Southern Ohio | BETVL - BET LOUISVILLE |  | 20619 | 22187 |  |  | 30707 |  | Younce, Michael | Younce, Michael |  |  | 1 | 44404 |  | Guest, ProSight | Independent | Aqua | 2022-08-03 | Other Programs
Louisville Replace Accuload III With Multiload | Item | Open | MCAP | BETVL00M2302 | Maintenance Framework | 2093981 | Parker, Brian | West | 3. Active | Defined | Truck Racks | 93051 | 51361 |  | 144412.15 | 101639 | 42773 | Red | 140000 |  | 140000 | 4412 |  |  | 109441 |  |  | 109441 | Phase | 109441 | 93051 | 51361 | 144412 | No | Green | 2023-03-01 | 2023-03-06 | 2023-03-06 | 2023-06-30 | 2023-09-29 |  |  |  |  | 88638.81 | 4412.34 |  |  | 4412 | Red |  |  | 13000 |  |  |  | 38361 |  |  |  |  | 5/1/23 - walked this down with Doug Olds, local ops, and Jason McEnaney (United Electric) on 4/27. Expect to have a proposal by 5/12 then will assemble full AFE to see if we can fund the construction in 2023 or push this off to 2024. United Electric would have a hard time starting this work in Q2 or early Q3 so finding a qualified electrical contractor to complete this in 2023 could be a major issue that would push this out to 2024. 4/21/23 - just received dwg package today from Triad - need to schedule a site walkdown with local electrical contractor, Doug Olds, and local ops. 3/31/23 - Var. is due to Multiload material shipping quicker than expected. Terminal has received the 2 Multiload and Triad has received all of the FCMII Modules mid-March. Just waiting on drawings from Triad so we can walk down the electrical work with a contractor and obtain a proposal for this work. Triad should have IFR drawings in about 3 weeks. 2/28/23 - submitted Phase I AFE for approval based on estimated costs for TopTech material and quote from Triad. 2/3/23 - just waiting on a Eng & Des proposal from Prajj with Triad so I can submit a Phase I AFE. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Southern Ohio | BETVL - BET LOUISVILLE |  | 88639 | 17412 | 38361 |  |  |  | Younce, Michael | Potter, Eric |  |  | 1 | 41879 |  | Guest, ProSight | Independent | Aqua | 2021-08-21 | Other Programs
Louisville Shoreside Erosion | Item | Open | MCAP | BETVL00M2205 | Maintenance Framework | 2023039 | Parker, Brian | West | 3. Active | Defined | Marine | 1201 | 650060 |  | 651261.27 | 651148 | 113 | Yellow | 630000 |  | 630000 | 21261 |  |  | 70000 |  |  | 70000 | Phase | 70000 | 43831 | 650060 | 693891 | No | Green | 2022-10-01 | 2022-09-19 | 2022-09-19 | 2023-09-30 | 2023-09-30 |  |  | 868.19 | 108.06 | 111.81 | 113.21 |  |  | 113 | Red |  |  |  |  | 20060 | 200000 | 230000 | 200000 |  |  |  | 4/30/23 - received permit details and it did not have the depth of the pilings listed. Setting up a call in early May to review the path forward with stakeholders. 4/1/23 - re-accruing 20,000 for TAS. Received BP transition files so need to review these and try to locate a permit #. 2/28/23 - Var is due to incorrect FCST for geotechnical work in Feb. Re-accruing 20,000 in Feb for TAS. USACE requires a permit number to locate drawings. Looking through drawings to see if I can locate a permit number reference. Attempting to determine the length of the bends via NDE if we can't locate original drawings. No details in drawings provided by Eng & Design from Adept. 20,060 FCST for Jun is for possible geotechnical work (this is actually in the six figure range so this will probably be dropped). 1/31/23 - re-accruing 20,000 in Jan. Travis has Christopher Ruppen with GSI going to make a site visit within the next 2 weeks to get a recommendation on the erosion project. 1/2/23 - accruing 20,000 in Dec for End & Design - will schedule an Eng review in the 2nd full week of Jan. 11/30/22 - reviewed current Eng & Des on Nov 10th with management and program owner. 10/31/22 - too late in the year to get geotech contactors on barges out to the site so this will occur in 2023 - will have most of the design completed in 2022. 9/29/22 - PO issued to TAS on Sep 22nd. 9/3/22 - Eng & Design will be completed in 2022 with construction to follow in 2023. 7/6/22 - Arcadis looked at the site on Jun 14th, took measurements and created sketches for civil engineer to evaluate and develop a SOW. 5/31/22 - Arcadis will take a look at this issue sometime around mid-Jun - trying to get a date set for June 14th. 5/3/22 - planning to look at this when Lloyd Eng is out for the dock inspection in Jun/Jul timeframe. 4/1/22 - currently have this scheduled to meet on-site Apr 20th if the river levels are normal. Moving the FCST out to Jul/Aug for now. 2/10/22- contacted Owen Parker with Lloyd Engineering and waiting on a reply back regarding schedule to meet on-site. | 2023-04-30 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Southern Ohio | BETVL - BET LOUISVILLE |  | 1088 | 113 | 450060 | 200000 | 42630 |  | Spari, Markella | Gardner, Travis W. |  |  | 1 | 37758 |  | Guest, ProSight | Independent | Aqua | 2020-08-12 | Marine
Louisville Terminal (BETVL) Tank 107 – OOS Corr Insp & Refurb | Item | Open | MCAP | BETVL00M2201 | Maintenance Framework | 1938056 | Arch, Stefan | West | 6. Operational | Defined | Tanks | 339 |  |  | 339.27 | 339 | 0 | Green |  |  |  | 339 |  |  | 253000 |  |  | 253000 | Phase | 253000 | 271923 |  | 271923 | No | Green | 2022-02-01 | 2022-01-11 | 2022-01-11 | 2022-01-03 | 2022-09-26 |  |  | 339.27 | 0 | 0 | 0 |  |  | 0 | Green | [11 empty] | 4/7/2023- Waiting on one invoice before closing project. 2/1/2023 - Project is complete, waiting for one invoice from Waste Management. No additional forecasting required. 2/1/2023 - Project is complete, waiting for one invoice from Allied and one from Waste Management. No additional forecasting required. 1/3/2023 - Project is complete, working through one invoice from Allied and waiting on one invoice from Waste Management. No additional forecasting required. 11/1/2022 - Tank project completed at the end of September. Variance in October due to not forecasting inspector cost for transfer work and waste management disposal. 10/3/2022 - Tank mechanical repairs completed on 9/9. Liner visual inspected and touch ups completed with holiday test. All indications repaired. Tank buttoned up on 9/27. Ethanol currently being transferred from tank 103 to 107. Pump calls will be changed back to 107 after the roof is floating. Small variance was due to working ahead of schedule. Small forecast in October for CWIP. 9/1/2022 - Tank inspected on 8/18. Minor scope with majority of implementation of Buckeye Repair Considerations. FHG mobilized to site on 8/31 and will be completed by the end of the week of 9/12. Advanced will then inspect floor and complete touch ups. Forecasting for September includes remaining mechanical repairs, liner touch up, strapping, inspector services, and post modification inspection. Planning to have tank RTS by the beginning of October. Variance in August due to working ahead for getting FHG on site. 8/1/2022 - Jumpers will be completed 8/2 and then begin transferring product from tank 103 to 105 and 107 to 103. Planning to have tank OOS late week of 8/8 or beginning week of 8/15. Inspection will be completed by 8/22. Forecast in August includes cleaning, inspection, inspector costs, and beginning mechanical repairs. Forecast shifted to September for majority of mechanical repairs, liner touch up, and RTS activities.Variance in July due to not getting to transferring in July.7/1/2022 - Planning to take OOS late July or early June. No changes. 6/1/2022 - Compliance date is 8/22. Planning to take OOS end of July. Associated piping project with two jumpers needed. Please see notes on tank 107 support project notes. No updates. 5/2/2022 - Compliance date is 8/22. Planning to take OOS end of July. Associated piping project with two jumpers needed. Please see notes on tank 107support project notes. 4/3/2022 - Compliance date is 8/22. Planning to take OOS end of July. Associated piping project with two jumpers needed. Please see notes on tank 107 support project notes. 3/1/2022 - Ordered valves, equipment, and Magnetrols in February. Forecasting for July through September for OOS. Developed scope for associated piping project, see tank 107 support project notes. 1/28/2022 - Conducting walkdown on 2/1. Planning to take OOS in July. | 2023-04-07 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Southern Ohio | BETVL - BET LOUISVILLE |  | 339 | 0 |  |  | 271584 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41280 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Louisville Terminal (BETVL) Tank 107 OOS Support Project | Item | Open | MEXP | BETVL00E2204 | Maintenance Framework | 1981022 | Arch, Stefan | West | 6. Operational | Defined | Tank Outage | -122265 |  |  | -122264.88 | -122265 | 0 | Green |  |  |  | -122265 |  |  | 135000 |  |  | 135000 | Phase | 135000 | -122265 |  | -122265 | No | Green | 2022-05-01 | 2022-05-19 | 2022-05-19 | 2022-12-31 | 2022-08-09 |  |  | -122264.88 | [18 empty] | 5/1/2023 - Double reclass amount still needs corrected in OPPM. Project is complete. 4/7/2023 - Double reclass amount still needs corrected in OPPM. Project is complete. 3/1/2023 - Reclass complete to MCAP project, no additional funding required. Cognos report is showing net zero, January variance in OPPM is incorrect. 2/1/2023 - Reclass complete to MCAP project, no additional funding required. Cognos report is showing net zero, variance in OPPM is incorrect. 1/3/2023 - Reclassed $126,767.11 on 12/20/2022 to MCAP project. No additional forecasting or invoice required on this project. 12/1/2022 - Expense project flipped to MCAP. These costs will be reclassed to the MCAP project. 11/1/2022 - Tank 103 project rolled into this project. Completed cleaning of tank 103, seal inspection, and mechanical repairs. Blistering found throughout the liner. Project will be changed to MCAP. Project set up from approved AFE. Project will be complete in November. 10/1/2022 - Tank 107 project is complete and currently transferring Ethanol from tank 103 to 107. Tank 103 will be cleaned, seal inspected, strapped, and RTS. Planning to have tank 103 RTS by the end of October. 9/1/2022 - Jumpers completed the week of 8/1. Planning to take tank 103 OOS for cleaning and inspect seals once tank 107 is RTS. Tank 103 work should be completed by the end of October. Forecast removed for September, no work should be completed until tank 107 is back in service. 8/1/2022 - Jumpers will be completed on 8/2, all went well. Begin transferring gasoline and Ethanol on 8/3. Small forecast in August for additional time to install the jumpers. Pushed out cleaning and inspection forecast to September due to timing of taking tank 107 OOS. 7/1/2022 - Spade currently fabricating jumpers. Planning to install the week of 7/25. Pump incorrect information was given to me when designing the project but will work. Small variance in June due to completing fabrication earlier than anticipated. Forecasting in July includes installation of the jumpers and inspector cost. 6/1/2022 - AFE submitted and approved. Project quotes received back fromvendors. Awarded Spade for the work. Variance in May due to Spade fabrication and ordering valves. Planning to install jumpers in July and follow with tank107 OOS. Tank 103 will becleaned at the tail end of the project for product change back to gasoline and seal inspection. The project will need tobe flipped from MEXP to MCAP due to the jumpers being permanent. 5/2/2022 - Piping project walked down with contractors on 4/28. Will receive bids back on 5/6 in Coupa. Once bids are back, will develop AFE for submittal. Confirmed with scheduling that we can use tank 103 as temporary Ethanol service during the outage of tank 107. Tank 103 has a liner. Will need to perform a seal inspection on tank 103 once Ethanol is removed. Forecasting pushed to June due to lag on bids. 4/3/2022 - Associatedproject to install jumper. Scope send to leadership team. Going to send to Supply chain for bid event. Planning to install in late June/early July timeframe. Will need to clean tank 3 after tank 107 project is complete. 3/1/2022 - Associated piping project to install two jumpers for Ethanol offload and rack. Planning to use tank 103 for temporary Ethanol storage during tank 107 outage. Scope has been developed and sent to Leadership Team. Planning to begin project in April/May. 1/28/2022 - Conducting walkdown on 2/1 to develop scope. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Southern Ohio | BETVL - BET LOUISVILLE |  | -122265 | 0 |  |  | 0 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41281 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Louisville Terminal (BETVL) Tank 107 OOS Support Project MCAP FLIP | Item | Open | MCAP | BETVL00M2206 | Maintenance Framework | 2038131 | Arch, Stefan | West | 6. Operational | Defined | Tanks | 22029 |  |  | 22029.06 | 17271 | 4758 | Red |  |  |  | 22029 |  |  | 341000 |  |  | 341000 | Full | 341000 | 327393 |  | 327393 | No | Green | 2022-10-01 | 2022-10-29 | 2022-10-29 | 2022-12-31 | 2022-11-28 |  |  | 16026.84 | 1243.63 | 0.65 | 4757.94 |  |  | 4758 | Red | [11 empty] | 5/12023 -. Project is complete. Small spend due to late Waste Management invoices. 4/72023 -. Project is complete, all work is operations, waiting for invoice from Waste Mangement then I will close it out. 3/1/2023 - Waiting to approve once invoice on a PO line that was incidental closed. Project is complete, all work is operations. 2/1/2023 - Project is complete. Waiting on two invoices from Consolidated and Hepaco. Reclass was completed. Variance due to additional project costs that weren't accrued. 1/3/2023 - Tank 103 is RTS. No additional funding required for this project. Waiting on multiple invoices from contractors. During the change in PO from MEXP to MCAP, the PO's seemed to disappear from JDE. Working with Spencer to get the PO's found. Large variance caused by the MEXP charges hitting MCAP project. 12/1/2022 - Project flipped to MCAP, all accruals will go on this project for November and the existing on the MEXP will be reclassed. Consolidated completed minor work to floating roof. WVP completed replacement of the liner. Tank was buttoned up on 11/29. Waiting to receive product and set high level alarms. 11/1/2022 - Budget switch from tank 107 support project. This includes tank 103 cleaning, inspection, mechanical repairs, liner replacement, and RTS activities. Planning to reclass all actuals from the expense project to this project. Large variance in October due to putting accruals switching to the new project. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Southern Ohio | BETVL - BET LOUISVILLE |  | 17271 | 4758 |  |  | 305364 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46106 |  | Meitzler, Antoinette | Independent | Aqua | 2022-10-21 | Int - Tanks
Louisville Terminal Concrete Drive Replacement | Item | Open | MCAP | BETVL00M2203 | Maintenance Framework | 1956200 | Parker, Brian | West | 3. Active | Defined | West | 201 | 65000 |  | 65200.59 | 65149 | 51 | Yellow |  |  |  | 65201 |  |  | 75000 |  |  | 75000 | Full | 75000 | 10797 | 65000 | 75797 | No | Green | 2022-05-01 | 2022-03-15 | 2022-03-15 | 2022-07-29 | 2023-07-31 |  |  | 48.88 | 49.76 | 50.66 | 51.29 |  |  | 51 | Red |  |  |  |  | 30000 | 35000 | [5 empty] | 5/1/23 - walked this down with local ops on 4/27 and identified three sections that are priorities for 2023. Need to have East & Westbrook update their proposal from 2022 then get a PO issued for this work. 4/1/23 - need to review the scope of work with new OM and new terminal operator before proceeding with Coupa bid event for unit pricing. 3/1/23 - no change to status. Concentrating on other projects right now then will go a bid based on 12'x12' section of concrete to replace along with 2' shoulder install on opposite side of concrete replacement. Will just shoot for a unit pricing structure to compare costs between what I think will be 3 contractors. 2/3/23 - need to circle back to Klump and Spade in Feb to see if they are interested in bidding on this work. 1/1/23 - no change to status - work pushed out to 2023. 11/30/22 - no change to status - work pushed out to 2023. 10/31/22 - received one proposal from East & Westbrook and still waiting on other proposals from Klump and Spade. Expect this work to be completed in 2023. 9/29/22 - have final revision on dwg set and will send it out to three contractors for some pricing. Moving FCST out to 2023 for now since I'm not sure if contractors are available to completed this in 2022 - will attempt to get it completed in late Oct/early Nov. 9/1/22 - TAS invoice paid in Aug. Have final dwg set and emailed to local ops yesterday to have them prioritize what they want to address in 2022. Plan to get East & Westbrook scheduled to start this work in early Oct. 7/30/22 - received IFR drawing and emailed for management review. Re-accruing 5,000 for TAS. 7/3/22 - still working on design to install temporary entrance while replacing the concrete at the automated facility gate. Can not take extended downtime for concrete work so working a temporary bypass. Accruing 5,000 for TAS for work completed in Jun. 5/31/22 - No accrual for May since two invoices for Eng & Des work was paid. Shouldwrap up in Jun and have a plan/profile view of what needs to be replaced to facilitate a bid event in late Jun or early Jul. 5/3/22 - issued PO to TAS to develop plan/profile view of areas that need to be replaced - will use this to go bid the work. Moving FCST out to Aug. 4/5/22 - need to call a couple of engineering firms local to the area and obtain proposals for LIDAR scanning of existing entrance to get a long term plan/design developed. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Southern Ohio | BETVL - BET LOUISVILLE |  | 149 | 51 | 65000 |  | 10596 |  | Gardner, Travis | Gardner, Travis W. | N/A |  | 1 | 31554 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Other Programs
Louisville Terminal Pipeline Manifold Painting | Item | Open | MCAP | BETVL00M2304 | Maintenance Framework |  | Smith, Kyle | West | 2. Pending AFE | Defined | Facility Painting |  | 60000 |  | 60000 | 60000 | 0 | Green | 60000 |  | 60000 | 0 |  |  | 59942 |  |  |  | Full | 59942 |  | 60000 | 60000 | No | Green | 2023-08-01 |  |  | 2023-08-30 | 2023-08-31 | [15 empty] | 60000 | [5 empty] | 4/28/23 Site walk through next week May 5th | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Southern Ohio | BETVL - BET LOUISVILLE |  |  | 0 | 60000 |  |  |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 31557 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Int - Planned Corr & FI
Louisville VRU Release Prevention | Item | Open | MCAP | BETVL00M2303 | Maintenance Framework | 2096566 | Scannell, Adam | West | 3. Active | Defined | Vapor Management |  | 58000 |  | 58000 | 58000 | 0 | Green | 58000 |  | 58000 | 0 |  |  | 22048 |  |  | 22048 | Phase | 22048 |  | 58000 | 58000 | No | Green | 2023-07-01 | 2023-03-30 | 2023-03-30 | 2023-07-31 | 2023-07-31 | [14 empty] | 11000 | 47000 | [5 empty] | 05/08/23 - Site visit with contractor is planned for May 30th to get estimate for spool modifications and installation. Planning for August installation. 4/11/23 - mrk - forecast pushed to july/aug to allow for time to develop engineering drawings. Engineering anticipated completion in July. 03/25/23 - Phase I AFE submitted to the workflow. Phase I will cover the engineering for mechanical and electrical. Once design is complete the mechanical and electrical will be bid for installation. | 2023-05-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Southern Ohio | BETVL - BET LOUISVILLE |  |  | 0 | 58000 |  |  |  | Karl, Marissa |  |  |  | 1 | 44952 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Other Programs
Luther Shield Pump Station A/C replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Fink, Ryan | West | 2. Pending AFE |  | West |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 | [9 empty] | 50000 | 50000 | No | Green | 2023-10-01 |  |  |  | 2023-11-30 | [17 empty] | 30000 | 20000 |  |  | 5/2 RRF - More scope options needed, EAC $92k 4/6 RRF - more estimates, try to fit budget, EAC $92k 3/1 RRF - Detailed scope to Purchasing, EAC $92k 2/2 RRF - preparing to get more quotes, will need site visits, moved forecast out 1/23 RRF - Updated quote has significant cost increase. 30wk lead/ 1/6/23 RRF - Near 1 year lead time. Requested revised quote. 12k depo on PO? Orig budget 50k | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Duncansville | LS - SHIELD'S PUMP STATION |  |  | 0 |  | 50000 |  |  | Gardner, Travis |  |  |  | 1 | 44323 |  | Guest, ProSight | Independent | Aqua | 2022-07-29 | Other Programs
Mantua area ATG Coating Transitions/FRP Installs | Item | Candidate | MCAP |  | Exempt |  | Gremer, Michael | West | 2. Pending AFE | Defined | Atmospheric Corrosion |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 | [9 empty] | 50000 | 50000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 50000 | [6 empty] | 5/2/23 - PM to set up site visit with contractors. 4/4/23 - PM working on scope of work. 3/2/23 - PM working on scope of work. 2/3/23 - PM working on scope of work. 6/16/2022 - project deferred to 2023. funds used for Bourbon A Distributed Ground Bed. 05/15/2019 Project deferred to 2020. Funding shifted to Mogadore Station (OD) FRP Installations OPPM 25267 | 2023-05-02 |  |  | West | Pipelines and Terminals | Integrity |  | Mantua | GE - MANTUA STATION |  |  | 0 | 50000 |  |  |  | Geib, Rob |  | N/A |  | 1 | 31337 |  | Guest, ProSight | Independent | Aqua | 2018-08-29 | Int - Planned Corr & FI
Mantua Office building hvac unit replacement | Item | Open | MCAP | GE00000M2203 | Maintenance Framework | 2051185 | Burns, Richard | West | 7. Closed | Emergent | West | 378 |  |  | 378.27 | 378 | 0 | Green | 13000 |  | 13000 | -12622 |  |  | 11000 |  |  | 11000 | Full | 11000 | 10336 |  | 10336 | No | Green | 2022-12-01 | 2022-12-08 | 2022-12-08 | 2022-12-31 | 2022-12-16 |  |  | 378.37 | -0.1 | [17 empty] | 3/1/23 - PO closed, WO at 80. ready to close. 2/1/23 - variance accrued. Still waiting on Jackson Comfort invoice. 1/3/23 - HVAC unit installed; accrued cost for Jackson Comfort. 12/5/22 - Project being pulled into 2022. Existing unit failed last week, setting off CO alarms. Unit will be replaced this week and costs will be re-classed to this project. AFE submitted on 12/3/22. Removed May 2023 forecasting. | 2023-03-08 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Mantua | GE - MANTUA STATION |  | 378 | 0 |  |  | 9957 |  | Gardner, Travis | Spitz, Nicholas P. |  |  | 1 | 44447 |  | Guest, ProSight | Independent | Aqua | 2022-08-08 | Other Programs
Mantua Oil Water Seperator Upgrade | Item | Open | MCAP | GE00000M2201 | Maintenance Framework | 1971013 | Arch, Stefan | West | 6. Operational | Defined | Storm Water Management | 9633 | 8000 |  | 17632.53 | 16077 | 1555 | Yellow |  |  |  | 17633 |  |  | 40000 |  |  | 40000 | Full | 40000 | 20300 | 8000 | 28300 | No | Green | 2022-04-01 | 2022-04-12 | 2022-04-12 | 2022-09-30 | 2023-04-07 |  |  | -855.16 | 932.33 | 0 | 9555.36 | 6500 | 6500 | 3055 | Red |  |  |  | 8000 | [7 empty] | 5/1/2023 - A/G tanks cleaned by Allied. Small forecast in June to paint the tanks and piping, while also getting as-builts completed. Separator is now functioning as intended. 4/6/2023 - New high level sensor delivered and Colton to install week of 4/3. Colton did install a sensor that he had on hand at the shop and separator was working well. Forecast for May is to clean the A/G tanks. 3/1/2023 - Ordered new level sensor and waiting for delivery to install. Techs troubleshoot the electrical. The separator should be functional once installed. 2/1/2023 - Local tech went to install new level sensor, but the sensor is not long enough. Tech sent back the sensor for correct length. Planning to install when we get it back. The O/WS separator should be functional after level sensor install. 1/3/2023 - No work completed in December. Working with techs to get this work completed. Re-forcasted into January and February to complete the work. 12/1/2022 - No work completed in November. Talked with new tech this week to discuss the project. Planning to complete by the end of the year. 11/1/2022 - Waiting for parts to come in. Trying to work with techs to get the separator diagnosed, asked multiple times. Planning to diagnose in November and get the unit back running again. 10/3/2022 - Waiting for components (5-7 weeks) to come in for the separator. I have been asking techs to troubleshoot while we wait on the components, but has not been completed. Variance in September due to the lead time of the components. Hopefully will arrive in October and complete installation. 9/1/2022 - Ordered components for the O/WS separator and waiting for them to come in for installation. Colton Slaugbaugh to look into the electrical components for diagnosis. Pump motor has been installed. Forecasting for September is for diagnosis and ordering parts. 8/1/2022 - Continued diagnosing the electrical components. Will have a better idea in August on what needs replaced. Forecast shifted in September and October. 7/1/2022 - No work was completed on the O/WS during June. Working with Colton to have him troubleshoot the electrical. Forecasting for July includes troubleshooting the electrical and ordering parts. 6/1/2022 - Continue to work with operations on timing and when they can troubleshoot the O/WS separator. Working with Colton Slaugbaugh. Planning to hit the majority of the work in July/August/September. 5/2/2022 - AFE developed and approved. Planning to order electrical parts and pump motor in May. This will be an ongoing project with local techs to get the O/W separator functional. Forecasting spread out over July/August/September. 4/3/2022 - Scope developed and sent to leadership team. Planning to submit AFE in beginning ofMay. 3/1/2022 - Planning to walkdown project with Ops the week of 3/7. Preliminary scope identifies pump refurbishment, wire installation, and high level indicator needed | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Mantua | GE - MANTUA STATION |  | 77 | 17555 |  |  | 10668 |  | Bonenberger, Mark | Ricke, Michael |  |  | 1 | 34407 |  | Guest, ProSight | Independent | Aqua | 2019-08-24 | Other Programs
Mantua Station (GE) Tank 508 - OOS API 653 + Seal Insp & Refurb | Item | Open | MEXP | GE00000E2301 | Maintenance Framework | 2076573 | Arch, Stefan | West | 3. Active | Defined | Tanks | 25686 | 253000 |  | 278686.13 | 273321 | 5365 | Yellow | 273000 |  | 273000 | 5686 |  |  | 199100 |  |  | 199100 | Phase | 199100 | 25686 | 253000 | 278686 | No | Green | 2023-01-01 | 2023-01-20 | 2023-01-20 | 2023-12-31 | 2023-12-31 |  |  | 9303 | 0 | 1017.7 | 15365.43 | 10000 | 10000 | 5365 | Red | [5 empty] | 73000 | 120000 | 60000 |  |  |  | 5/312023 - Re-forecasted project to August OOS timeframe and still planning for minimal repairs. Ordered material in April and pulled lead sampling. 4/3/2023 - Walked down the project with Phillips in March for preliminary scope. Anticipating minor repairs since the tank is in great condition. No additional updates. 3/1/2023 - No spend completed in February due to not ordering parts. Re forecasting amount in March. Planning to begin project in June/July. 2/1/2023 - Project to take tank 508 OOS for inspection and repairs. Stakeholder call held on 1/20/2023. AFE has been approved. Planning to begin in June. Small variance in January due to ordering parts. February forecasting to continue ordering parts. 9/23/22-CES-Tank had new bottom 10 years ago, anticipating minor repairs. Reducing mechanical repair budget. Anticipating MEXP. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Mantua | GE - MANTUA STATION |  | 10321 | 15365 | 193000 | 60000 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44843 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Mantua Station (GE) Tank A-06 Cleaning and Idle | Item | Open | MEXP | GE00000E2302 | Maintenance Framework | 2076578 | Arch, Stefan | West | 5. Deferred | Defined | Tanks |  |  |  | 0 | 0 | 0 | Green | 10000 |  | 10000 | -10000 |  |  | 11275 |  |  | 11275 | Phase | 11275 |  | 10000 | 10000 | No | Green | 2024-08-01 | 2023-01-20 | 2023-01-20 | 2023-12-31 | 2023-05-31 | [21 empty] | 4/10/2023 - deferred forecast to 2024 per leadership request. 4/3/2023 - Discussion with Travis regarding the possible deferral of this project, leaving forecasting in August for now. 3/1/2023 - Forecasting moved to Q3 during tank 508 outage. No additional updates. 2/1/2023 - Project to take tank OOS and idle. Planning to complete in May during tank 508 project. planning to remove valves and blind tank. | 2023-04-10 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Mantua | GE - MANTUA STATION |  |  | 0 |  |  |  | 10000 | Stine, Carlton | Stine, Carlton |  |  | 1 | 44907 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Marshall Terminal VCU Replacement | Item | Open | MCAP | BETML00M2301 | Maintenance Framework |  | Scannell, Adam | West | 2. Pending AFE | Emergent | Vapor Management |  | 39261 |  | 39261 | 39261 | 0 | Green |  | 39261 | 39261 | 0 |  |  | 39261 |  |  |  | Phase | 39261 |  | 39261 | 39261 | No | Green | 2023-05-01 |  |  | 2023-12-31 | 2023-12-31 | [12 empty] | 15000 | 16900 | 7361 | [6 empty] | 03/30/23 - This project is on hold. Recent mechanical work seems to have addressed the issue with the existing VCU stack emissions. Once evaluated we will determine if this project is necessary. 03/22/23 - Forecast in April/May is for the design portion of the project. The forecast for estimated full cost will be updated based off bids resulting from the engineering package. | 2023-04-05 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETML - BET MARSHALL TERMINAL |  |  | 31900 | 7361 |  |  |  | Karl, Marissa | Gardner, Travis W. |  |  | 1 | 46826 |  | Scannell, Adam | Independent | Aqua | 2023-03-22
Marshall Terminal West Lane Concrete Repairs | Item | Candidate | MCAP |  | Exempt |  | Bost, Jason | West | 2. Pending AFE |  | West |  | 65000 |  | 65000 | 65000 | 0 | Green | 65000 |  | 65000 | 0 | [9 empty] | 130000 | 130000 | No | Green | 2023-07-01 |  |  |  | 2023-06-30 | [14 empty] | 10000 | 55000 | [5 empty] | 5/1/23 - Site visit scheduled late May.4/3/23 - No Change. 3/1/23 - Scheduling scope walkdown in March. 1/31/23 - The West lane under the load rack is in very poor condition. The concrete is cracked, heaved in spots and also holds water in areas and is a STF hazard. Scheduling scope visit early March. | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETML - BET MARSHALL TERMINAL |  |  | 0 | 65000 |  |  |  | Gardner, Travis |  |  |  | 1 | 44191 |  | Guest, ProSight | Independent | Aqua | 2022-07-19 | Other Programs
Midland driveway paving | Item | Candidate | MEXP |  | Exempt |  | Roman, James | West | 2. Pending AFE |  | West |  | 122000 |  | 122000 | 125000 | -3000 | Yellow | 100000 |  | 100000 | 22000 | [9 empty] | 122000 | 122000 | No | Green | 2023-05-01 |  |  |  | 2023-06-30 | 8 | Yellow | [10 empty] | 2000 | 0 |  | 120000 | [5 empty] | 5/2/23 Submitting phase 1 AFE to assemble bid pkg. 4/5/23 Visited site, will need State permit, I will submit Phase 1 AFE for that. Adjacent owner pledged $20k. | 2023-05-02 |  |  | West | Pipelines and Terminals | Station/Terminal |  | Coraopolis | BETIP - MIDLAND LPG |  |  | 2000 | 120000 |  |  |  | Gardner, Travis |  |  |  | 1 | 44219 |  | Guest, ProSight | Independent | Aqua | 2022-07-22 | Other Programs
MIDLAND LPG IDLE FACILITY - 2023 | Item | Open | MEXP | BETIP00E2301 | Maintenance Framework |  | Arch, Stefan | West | 2. Pending AFE | Unplanned | West |  | 650000 |  | 650000 | 650000 | 0 | Green |  |  |  | 650000 |  |  | 664962 |  |  |  | Full | 664962 |  | 650000 | 650000 | No | Green | 2023-06-01 |  |  | 2023-08-30 | 2023-06-30 | [13 empty] | 150000 | 250000 | 250000 | [5 empty] | 5/1/2023 - Submitted AFE on 5/1. Planning to begin flaring beginning of June, followed by Flaring. Re-forecasted project to start in beginning of June and complete in August. 4/3/2023 - Open flare rejected by the state and went back to contractor to discuss enclosed flare. ExPro gave me a quote for enclosed flare and Marissa Karl is working through using the PVCU. Hoping to have an answer in the coming week and submit an AFE. 3/1/2023 - Working through a few nitrogen quotes and will submit an AFE within 1.5 weeks. Planning to begin flaring and purging at the beginning of April. Spoke with Dave Clark and Travis, project moved to MEXP for the flaring and purging. 2/1/2023 - Flaring and purging is confirmed. Getting last quote from TransTech to flare and purge the system. EQT does not plan to pay for the mechanical repairs. Mike Curry is currently working on finding a new customer that would be willing to pay for the modifications. Planning to begin flaring in April. Moved forecasting from 2024 back into April and May. 1/3/2023 - Discussed project with Mike Curry in December. Waiting to hear back from EQT if project will be approved. 12/1/2022 - No update, waiting on word from Mike Curry for project status. 11/1/2022 - Estimate developed and sent to Mike Ricke for review with Mike Curry. Waiting on word to submit Phase I AFE for material. Forecast shifted to November to begin Engineering. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Coraopolis | BETIP - MIDLAND LPG |  |  | 150000 | 500000 |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 45394 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Other Programs
Milan FRP and painting | Item | Open | MCAP | IM00000M2301 | Exempt | 2110756 | Scott, Cory | West | 6. Operational | Defined | Atmospheric Corrosion | 29000 |  |  | 29000 | 22000 | 7000 | Red | 22001 |  | 22001 | 6999 |  |  | 28965 |  |  | 28965 | Full | 28965 | 29000 |  | 29000 | No | Green | 2023-04-01 | 2023-04-15 | 2023-04-15 | 2023-04-28 | 2023-08-31 | [5 empty] | 29000 |  |  | 29000 | Red | [11 empty] | 5/5/2023 - Recieved Cleveland invoice for $4,554.00. Project should complete around 25K. 5/4/2023 - Awaiting final billing. Recieved $20,032.10 from Vance and Associates. Awaiting final bill from Cleveland Integrity. 5/1/2023 - Project finished 4/27/2023. 4/24/2023 - Project kickoff. Project planned completion on 4/28/2023. 4/21/2023 - Stakeholder meeting held. Project to start on 4/24/2023. PO's are in, site safety plan approved. 4/19/2023 - ISNetworld OQ's put in for Vance and Associates. 4/18/2023 - Stakeholder meeting being held on 4/21/2023. Inspector request placed. PO placed for Vance and Associates. Forecast updated to reflect approved AFE. 4/5/2023 - Estimate recieved. AFE put in for 29K. 3/27/2023 - Site visit with Vance and Associates to put estimate and scope together. | 2023-05-05 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | IM - MILAN STATION |  |  | 29000 |  |  |  |  | Geib, Rob | Smith, Todd W. |  |  | 1 | 45451 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Milan Station (IM) Tank 1 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | IM00000M2201 | Maintenance Framework | 2044304 | Roth, Aaron | West | 6. Operational | Defined | Tanks | 55135 |  |  | 55134.61 | 39575 | 15560 | Red | 395195 |  | 395195 | -340060 |  |  | 383000 |  |  | 383000 | Phase | 383000 | 196970 |  | 196970 | No | Green | 2022-11-01 | 2022-11-07 | 2022-11-07 | 2023-04-01 | 2023-08-31 |  |  | 31081.97 | 12078.24 | -3585.6 | 15560 |  |  | 15560 | Red | [11 empty] | 4.3 - done | 2023-04-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | IM - MILAN STATION |  | 39575 | 15560 |  |  | 141835 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44850 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Milan Station (IM) Tank 2 - OOS API 653 + Seal Insp & Refurb | Item | Open | MCAP | IM00000M2202 | Maintenance Framework | 2044307 | Roth, Aaron | West | 6. Operational | Defined | Tanks | 76827 |  | 0 | 76827.27 | 66327 | 10500 | Red | 467423 |  | 467423 | -390596 |  |  | 384000 |  |  | 384000 | Phase | 384000 | 186080 | 0 | 186080 | No | Green | 2022-11-01 | 2022-11-07 | 2022-11-07 | 2022-04-01 | 2023-08-31 |  |  | 67148.57 | 3997.41 | -4818.71 | 10500 |  |  | 10500 | Red |  | Forecasting | [8 empty] | 0 | 5.1 - done. VAR: unforecasted Waste Management invoice | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | IM - MILAN STATION |  | 66327 | 10500 |  |  | 109252 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44851 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Milan Station IM Pull In Tanks 1 & 2 2022 Reclass | Item | Open | MEXP | IM00000E2202 | Maintenance Framework | 2096642 | Roth, Aaron | West | 3. Active | Drawdown | Tanks |  |  |  | 0 |  | 0 | Green | 366000 |  | 366000 | -366000 |  |  | 366000 |  |  | 366000 | Full | 366000 |  |  |  | No | Green |  | 2023-03-31 | 2023-03-31 | 2023-04-01 | 2023-04-01 | [23 empty] | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Sugar Creek | IM - MILAN STATION |  |  | 0 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 46810 |  | Meitzler, Antoinette | Independent | Aqua | 2023-03-20
Mt Auburn Install New Trap Doors | Item | Candidate | MCAP |  | Exempt |  | Parker, Brian | West | 8. Canceled |  | Facility Integrity |  |  |  | 0 |  | 0 | Green | 43000 |  | 43000 | -43000 | [11 empty] | No | Green |  |  |  |  | 2022-07-01 | [21 empty] | 2/4/23 - Ryan Taylor will cover the purchase and installation of these two flanged closures on his project. This budget amount will be utilized for the Hartsdale Butane Offload Driver Kiosk (OPPM ID 45245) since the scope has changed and we are exceeding the budget. 12/9/22 - due to the delay in getting the new AFE template issued, this FCST will probably shift out another month since the lead time for the new closures is 9 weeks. | 2023-02-04 |  |  | West | Pipelines and Terminals | Integrity |  | Central-Illinois | AS - AUBURN STATION |  |  | 0 |  |  |  |  | Aiken, Elaine |  |  |  | 1 | 34378 |  | Guest, ProSight | Independent | Aqua | 2019-08-23 | Int - Planned Corr & FI
Muncie Security Cameras Installation | Item | Open | MCAP | BETMN00M2201 | Maintenance Framework | 1957331 | Smith, Kyle | West | 6. Operational | Defined | Security & Cameras | 3559 |  |  | 3559.04 | 3559 | 0 | Green |  |  |  | 3559 |  |  | 45000 |  |  | 45000 | Full | 45000 | 43983 |  | 43983 | No | Green | 2022-05-01 | 2022-03-28 | 2022-03-28 | 2022-06-30 | 2022-12-31 |  |  | 3244.73 | 314.31 | 0 | 0 |  |  | 0 | Green | [11 empty] | 1//1/23 Work has stalled because of UT getting cameras in and didn't have Windows installed. Suppose to be done shortly | 2023-01-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Huntington | BETMN - BET MUNCIE TERMINAL |  | 3559 | 0 |  |  | 40424 |  | Clark, Chris | Clark, Chris B |  |  | 1 | 24308 |  | Administrator, System | Independent | Aqua | 2017-07-21 | Other Programs
Muncie Terminal - BETMN - Secondary containment upgrades | Item | Open | MCAP | BETMN00M2301 | Maintenance Framework | 2083837 | Parker, Brian | West | 3. Active | Defined | Secondary Containment | 1418 | 103000 |  | 104417.5 | 103000 | 1418 | Yellow | 103000 |  | 103000 | 1418 |  |  | 28212 |  |  | 28212 | Phase | 28212 | 1418 | 103000 | 104418 | No | Green | 2023-04-01 | 2023-02-02 | 2023-02-02 | 2023-08-31 | 2023-09-29 | [5 empty] | 1417.5 |  |  | 1418 | Red | [5 empty] | 45000 | 58000 |  |  |  |  | 5/1/23 - Diamond Z is still working on IFR drawing package. 4/4/23 - Diamond Z should be able to get to this sometime in Apr/May timeframe. 3/1/23 - PO issued to Diamond Z on Feb 14th to provide IFR and IFC set for dike repairs identified in 2022. 2/3/23 - Phase I AFE is out for approval - will get Diamond Z a PO once AFE has been approved for IFR and IFC drawing set. Will adjust FCST after bid event has been conducted and bid awarded. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Huntington | BETMN - BET MUNCIE TERMINAL |  |  | 1418 | 103000 |  |  |  | Clark, Dave | Spari, Markella |  |  | 1 | 45159 |  | Administrator, System | Independent | Aqua | 2022-08-23 | Other Programs
Napoleon Terminal - new video system | Item | Open | MCAP | BETNP00M2202 | Maintenance Framework | 1970408 | Hassan, Mohammad | West | 6. Operational | Defined | Security & Cameras | 2550 |  |  | 2550.18 | 2550 | 0 | Green |  |  |  | 2550 |  |  | 65000 |  |  | 65000 | Full | 65000 | 68449 |  | 68449 | No | Green | 2022-07-01 | 2022-06-30 | 2022-06-30 | 2022-09-30 | 2022-12-31 |  |  | 2128.69 | 218.43 | 203.06 | [16 empty] | 05-02-2023 - MNH - Working on project closeout items now. 04-03-2023 - MNH - Working on project closeout items now. Final EAC at $68.5K. 03-01-2023 - MNH - Working on project closeout items now. EAC at $69K. 02-01-2023 - MNH - Everything has been commissioned and installed now and this project is operational. Will work on project punch list/closeout items next. Project EAC at $69K still. 01-03-2023 - MNH - Working this month with Techs/IT & Convergint to get everything including extra camera commissioned & installed. Project EAC at $69K. 12-02-2022 - MNH - Network switch arrived yesterday ahead of schedule. Will now work with Techs/IT & Convergint to get everything including extra camera commissioned & installed. Due to Techs schedule commissioning may still happen in 2023. Project EAC at $69K. 11-02-2022 - MNH - We were able to get all camera installed but 4 are left to be commissioned pending network Switch arrival and one extra to be installed this month or next. Estimate for switch is April of 2023. Moving $4K in 2023 Q2 to pay for switch and final commissioning. Project EAC now at $69K. 10-03-2022 - MNH - We were able to get some construction work done ahead of schedule last month. Will plan on doing majority of remaining construction this month. Still waiting on network switches for final commissioning later this year. Project EAC at $65K. 09-01-2022 - MNH - Most of the material has been received but now waiting on network switches from IT group which is estimated at 2 months out. We will try to get construction work started next month in order to keep making progress but Sep forecast has to move to November. 08-01-2022 - MNH - Project procurement underway but no definitive delivery date received from vendor. Adjusting forecast to account for material delays and moving some money into Q4. 07-06-2022 - MNH - AFE approved & PO cut to the vendor. Project procurement to happen next. Adjusting some forecast. 06-01-2022 - MNH - Still waiting on updated quote from vendor which now delayed submitting of AFE. Will plan to submit AFE this month now. MovingJuly Forecast into August. 05-03-2022 - MNH - Have received quotes from vendors. Will plan on submitting AFE this month. 04-01-2022 - MNH - Will start working on SOW this month. 03-01-2022 - MNH - Will start working on SOW in April. 02-02-2022 - MNH -Will start working on SOW in April. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETNP - BET NAPOLEON |  | 2550 | 0 |  |  | 65898 |  | Clark, Chris | Clark, Chris B |  |  | 1 | 40813 |  | Guest, ProSight | Independent | Aqua | 2021-07-28 | Other Programs
Napoleon Terminal (BETNP) Rack pump PLC Upgrade | Item | Open | MCAP | BETNP00M2203 | Maintenance Framework | 2011202 | Hassan, Mohammad | West | 6. Operational | Defined | Instrumentation & Controls | 375 |  |  | 375.44 | 375 | 0 | Green |  |  |  | 375 |  |  | 78000 |  |  | 78000 | Full | 78000 | 56820 |  | 56820 | No | Green | 2022-08-01 | 2022-08-02 | 2022-08-02 | 2022-11-18 | 2022-10-26 |  |  | 375.44 | [18 empty] | 05-02-2023 - MNH - Project closeout underway but delayed to other high priority items. 04-03-2023 - MNH - Project closeout underway but delayed to other high priority items. 03-01-2023 - MNH - Project closeout underway. 02-01-2023 - MNH - Project punch list items are complete and project closeout underway now. Project EAC at $56K now. 01-03-2023 - MNH - Project punch list item work underway this month due to Tech on vacation. Project EAC now at $58K. Some labor charges might hit this month. 12-02-2022 - MNH - Project punch list item work underway this month. Project EAC now at $59K as less than planned internal labor was used. 11-02-2022 - MNH - Project commissioned last week. Will work on project closeout and punch list items this month. Project should come under budget as electrical contractor & inspection was not used. Project EAC now at $62K. 10-04-2022 - MNH - Project underway and ahead of schedule and construction & commissioning planned for October 24th week. Project EAC at $77K now. 09-01-2022 - MNH - Project underway and material on order. Construction & commissioning planned for October 24th week. 07-27-2022 - MNH - AFE routed for approval and needed $8K more than budget that will be sourced from Louisville (BETVL) Load Rack Control PLC Upgrade Project (OPPM ID 38052). 07-21-2022 - MNH - Will have AFE submitted next week and get this project started. Based on lead times of material, this may get pushed in 2023, but will know about that next week. 07-06-2022 - MNH - Delay in submitting AFE due to other project workload. Now planning on submitting AFE by end of this month. Adjusting forecast. 06-01-2022 - MNH - Planning on submitting AFE by end of this month. 05-03-2022 - MNH - Have received quotes from vendors. Will plan on submitting AFE next month. Moving forecast out a month. 04-01-2022 - MNH - Managing existing workload and emergent projects have delayed scope start. Moving forecast out a month from baseline. 03-01-2022 - MNH - Will start working on SOW this month. 02-02-2022 - MNH - Will start working on SOW in March. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETNP - BET NAPOLEON |  | 375 | 0 |  |  | 56445 |  | Forsey, Frank | Ransom, Paul |  |  | 1 | 38062 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
Napoleon Terminal (BETNP) Tank 3– OOS Corr Insp & Refurb | Item | Open | MCAP | BETNP00M2201 | Maintenance Framework | 1938057 | Arch, Stefan | West | 7. Closed | Defined | Tanks | 264 |  |  | 264.1 | 264 | 0 | Green |  |  |  | 264 |  |  | 239000 | 447000 |  | 686000 | Full | 686000 | 634156 |  | 634156 | No | Green | 2022-01-01 | 2022-01-11 | 2022-01-11 | 2022-01-03 | 2022-09-23 |  |  | 264.1 | [18 empty] | 3/9/2023 - Closed Tulsa Inspection PO, updated WO Status to 80 in JDE (BG). 3/1/2023 - Project is complete, need to close one PO. 2/1/2023 - Project is complete, need to close one PO. 1/3/2023 - Project is complete, all invoices have been approved. 11/1/2022 - Project completed. Trailing costs hit in October. No additional forecast required. Will submit full AFE in November for approval. 10/3/2022 - Liner replaced. Hydrotest exemption approved by Tank Integrity, Regional Engineering Manager, and Regional Vice President. Tank buttoned up on 9/23. Small forecast in October for CWIP. Project is complete, waiting for transfer into tank. 9/1/2022 - Mechanical repairs completed the week of 8/8. Consolidated had quality problems that required gouging out welds and rewelding. Advanced completed the liner install on the new sketch sheets on 8/19, but the bottom sheet liner could not pass a holiday test and could not be repaired. Planning to complete the remaining liner install the week of 9/5. Once liner is installed, the tank will RTS. Waiting on hydrotest exemption from Hagen Engineering, the fitness for service is fine. Planning to have tank RTS the week of 9/12. 8/1/2022 - Mechanical repairs ongoing and should be completed end of 8/1 week. Small change order to Consolidated for sand installation and extra NDE for the hydrotest exemption. Planning to have Advanced on site, 8/8 to complete the liner install, touch up, and holiday test. Hagen Engineering completing the hydrotest exemption. Planning to have tank RTS end of August. Variance in July due to completing more work than anticipated. 7/1/2022 - Tank scope developed and leadership reviewed. Replacing all 28 sketch sheets and implementing Buckeye Repair Considerations. Consolidated mobilized on site 6/29 and began gouging out welds. Napoleon does not have a hydrotest discharge permit and we can only draw from the fire hydrant at night. Hydrotest exemption was approved on 6/29. Forecasting in July includes mechanical repairs, inspector costs, and strapping.Variance in June because work completed faster than anticipated. 6/1/2022 - Tank taken OOS on 6/23 and cleaning finished on 6/27, DJA on site 5/31 to perform 653 inspection. Scope will be sent once preliminary report is received. Tank has a thick film liner and bottom showing soil side indications. DJA report called out tank critical zone failing. Panning to replace all sketch sheets. Updated forecasting for extensive mechanical repairs, hydrotest, and liner install. I believe this will be a medium scope. Forecasting for June includes beginning mechanical repairs and inspector costs. 5/2/2022 - Held call on 5/3 with operations. Scheduling to take tank OOS on 5/23. Forecasting in May includes cleaning and inspector costs for one week. June forecasting includes inspection, mechanical repairs, and inspector costs. 4/3/2022 - Compliance date is 6/13/2022. Planning to take tank OOS in late May. Working with Mohammad to determine if PLC can handle Varec 2920 install. Anticipating minor repairs. Small variance in March for no spend. Forecasting in May in line with spend. 3/1/2022 - Variance in February due to not ordering equipment. the current PLC set up for tank gauging requires outside engineering review to determine if it can handle a Varec 2920 in Modbus communication. Working with Mohammad and Triad on the PLC changes needed. Planning to take tank OOS in May. 1/28/2022 - Held stakeholder call on 1/25. Planning to take late May. | 2023-03-09 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Wayne Terminals | BETNP - BET NAPOLEON |  | 264 | 0 |  |  | 633892 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41294 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Napoleon Terminal (BETNP) Tank 5 Stair Installation | Item | Candidate | MCAP |  | Maintenance Framework |  | Arch, Stefan | West | 2. Pending AFE |  | Tanks |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 | [9 empty] | 100000 | 100000 | No | Green | 2023-06-01 |  |  |  | 2023-08-31 | [13 empty] | 25000 | 35000 | 40000 | [5 empty] | 5/1/2023 - Working with Consolidated on design of new stairs. Planning to submit Phase I AFE for engineering and Phase II for the mechanical works. The stairs will run from the top of dike wall to the top of the tank. 4/3/2023 - Developed preliminary scope and sent it to Consolidated for thoughts on drawing and plan. No additional updates, forecasting and schedule stayed the same. 3/1/2023 - Walked down project with Operations on 2/22. Developing scope and planning to send to management for review. Planning for summer install. 2/1/2023 - Project to install stairs on the breakout tank. Preliminary scope includes adding a set of stairs without taking the tank OOS. Need to get on site and walk down the tanks. Planning to complete in summer. | 2023-05-01 |  |  | West | Pipelines and Terminals | Integrity |  | Wayne Terminals | BETNP - BET NAPOLEON |  |  | 25000 | 75000 |  |  |  | Stine, Carlton |  |  |  | 1 | 45101 |  | Guest, ProSight | Independent | Aqua | 2022-08-19 | Int - Tanks
Napoleon Terminal Roof Top Unit Replacement | Item | Open | MCAP | BETNP00M2301 | Maintenance Framework | 2096360 | Gardner, Travis | West | 3. Active | Drawdown | West |  | 22800 |  | 22800 | 22800 | 0 | Green |  |  |  | 22800 |  |  | 24673 |  |  | 24673 | Full | 24673 |  | 22800 | 22800 | No | Green | 2023-06-01 | 2023-04-04 | 2023-04-04 | 2023-05-03 | 2023-05-03 | [13 empty] | 22800 | [7 empty] | 5/2/2023 Delivery of unit is moved to June. 4/4/2023 - emergent HVAC failure forecasted in May due to lead time. | 2023-05-02 | Griest, Barbara | Griest, Barbara | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETNP - BET NAPOLEON |  |  | 22800 |  |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 46852 |  | Griest, Barbara | Independent | Aqua | 2023-03-29
ND710ICEP471368 Pine Creek Bryant Rd. Exposure Remediation | Item | Open | MCAP | ND710ICM2301 | Project Framework | 2094873 | Roman, James | West | 3. Active | Defined | Exposure Remediation | 24622 | 1660000 |  | 1684622.19 | 1700000 | -15378 | Yellow |  |  |  | 1684622 |  |  | 130551 |  |  | 130551 | Phase | 130551 | 24622 | 1660000 | 1684622 | No | Green | 2023-04-01 | 2023-03-10 | 2023-03-10 | 2023-11-17 | 2023-09-30 | [5 empty] | 24622.19 | 30000 | 30000 | -5378 | Red |  | Other | 5000 | 5000 |  |  | 50000 | 500000 | 500000 | 600000 |  | 5/1/23 Variance -$5,500. Holding off on submitting permit until after June 1 pre app mtg with DEP. Will adjust June forecast after said mtg. 3/1/23 Submitting Phase 1 AFE this week. Get started on wetland delienation. 1/31/23 - Had initial mtg with engineer. Getting proposal for a Phase 1 AFE to include conceptual designs and permitting. Permitting path to be determined by construction approach yet to be determined. Anticipate minimum 6 month time period to obtain permits. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Coraopolis | ND710IC - INDIANOLA ST TO CORAOPOLIS JCT |  |  | 34622 | 50000 | 1600000 |  |  | Hurley, Brian | Shook, Mark B. |  |  | 1 | 46433 |  | Guest, ProSight | Independent | Aqua | 2023-01-05 | Int - Planned Exposures
Niles Main Terminal (BETNM) Truck Rack Fire Suppression | Item | Open | MCAP | BETNM00M2301 | Maintenance Framework | 2112688 | Smith, Kyle | West | 3. Active | Defined | Fire Protection |  | 11500 |  | 11500 | 50000 | -38500 | Red | 50000 |  | 50000 | -38500 |  |  | 11467 |  |  | 11467 | Phase | 11467 |  | 11500 | 11500 | No | Green | 2023-06-01 | 2023-04-26 | 2023-04-26 | 2023-07-30 | 2023-07-31 | [13 empty] | 11500 | [7 empty] | 5/8/23 Will only do engineering this year. May need funds for Lima North fire alarm (GJ); 4/28/23 Cutting PO for engineering | 2023-05-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | BETNM - BET NILES TERMINAL |  |  | 11500 |  |  |  |  | Jakubowski, Gregory | Jakubowski, Greg |  |  | 1 | 41654 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Niles North Tank gauging feedback into TMS 2020 Phase 1 | Item | Open | MCAP | BETNM00M2202 | Maintenance Framework | 1957587 | Parker, Brian | West | 7. Closed | Defined | Instrumentation & Controls | 1592 |  |  | 1591.91 | 1592 | 0 | Green |  |  |  | 1592 |  |  | 95000 |  |  | 95000 | Full | 95000 | 99031 |  | 99031 | No | Green | 2022-04-01 | 2022-03-31 | 2022-03-31 | 2022-07-29 | 2022-09-19 |  |  | 1591.91 | [18 empty] | 4/5/23 - requested archive of Project Site. 1/1/22 - final invoice to Triad paid in Dec, project can be closed out by accounting. Triad will be getting updated drawings to drafting. 11/30/22 - re-accruing 6,426.96 for Triad until invoice has been paid. 11/1/22 - re-accruing 6,426.96 for Triad until invoice has been paid. 9/29/22 - Triad completed their programming earlier than expected in mid-Sep. The 2 Varec 2500 ATG's arrived today. Just waiting on Triad's final invoice so accruing that open PO amount for Sep. 9/1/22 - completed everything we could right now until Triad can get on-site. Added 3,000 to Nov FCST for local ops final work. 8/16/22 - Triad is 8 weeks out before they can get on-site to complete the programming. Moved their cost out to Oct and moved the 2 Varec's out to Nov - long delivery delay on Varec's. 7/30/22 - Network Group will allow use of the existing network switches from Main Office to Butane Blending Bldg due to 12 month lead time of new network switches. Re-accruing 10,000 for Vander Werf. Should have PO issued to Triad in Aug since we have a final resolution with communication path. Also expect the 2 Varec tank gauges in Aug 7/11/22 - moving FCST out to Aug/Sep - waiting to hear back on lead time for managed network switch. This could move out into Q4. 7/2/22 - re-accruing 10,000 for Vander Werf in Jun. Still waiting on Varec gauge heads to arrive. Splitting remaining cost between Jul and Aug. 5/31/22 - accruing 10,000 for Van Der Werf in May. Still waiting on the two Varec gauge heads to arrive. Van Der Werf should complete their work in Jun. 5/19/22 - delay in getting approval from network group on data transmission to local HMI from PL PLC is pushing the programming back to Jul. 5/9/22 - received the 6th GSI transmitter on May 6th. 5/2/22 - received 5 of the 6 GSI transmitters earlier than expected in Apr. Vander Werf also completed about 2/3's of the electrical work (20,000) in Aprwhich will be accrued. 4/1/22 - 44,000 FCSTfor May is 33,300 for O/S and remaining cost is for 2 - 2500 ATG and 6 - GSI level transmitters, and 6 - Reotemp Dual-Mode thermometers. Remaining FCST in Jun is for Triad programming and local ops costs to commission. | 2023-04-05 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | BETNM - BET NILES TERMINAL |  | 1592 | 0 |  |  | 97439 |  | Forsey, Frank | Gardner, Travis W. |  |  | 1 | 24311 |  | Administrator, System | Independent | Aqua | 2017-07-21 | Other Programs
Niles South Idle Containment Tank | Item | Open | MEXP | BETNM00E2201 | Maintenance Framework | 1957353 | Smith, Kyle | West | 6. Operational | Defined | West | 3375 |  |  | 3375.02 | 3375 | 0 | Green |  |  |  | 3375 |  |  | 18000 |  |  | 18000 | Full | 18000 | 10803 |  | 10803 | No | Green | 2022-09-01 | 2022-03-28 | 2022-03-28 | 2022-06-30 | 2022-09-30 |  |  |  |  | 3375.02 | [16 empty] | 10/1/22 Work Completed in Sept | 2022-10-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Michiana | BETNM - BET NILES TERMINAL |  | 3375 | 0 |  |  | 7428 |  | Gardner, Travis | Baldwin, T. Andy |  |  | 1 | 37988 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
Niles Terminal (BETNM) Tank N-50 - OOS Corr + Seal Insp & Refurb | Item | Open | MCAP | BETNM00M2201 | Maintenance Framework | 1938085 | Roth, Aaron | West | 6. Operational | Defined | Tanks | 208 |  |  | 208.3 | 208 | 0 | Green |  |  |  | 208 |  |  | 197000 |  |  | 197000 | Phase | 197000 | 249814 |  | 249814 | No | Green | 2022-01-01 | 2022-01-11 | 2022-01-11 | 2022-01-03 | 2022-05-27 |  |  | 208.3 | [18 empty] | 9.1.22 - DONE - VAR due to unforecasted change order from tank cleaner. | 2022-09-01 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Michiana | BETNM - BET NILES TERMINAL |  | 208 | 0 |  |  | 249606 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41299 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Niles Terminal Asphalt Repair | Item | Candidate | MEXP |  | Exempt |  | Smith, Kyle | West | 5. Deferred |  | West |  |  |  | 0 |  | 0 | Green | 49190 |  | 49190 | -49190 | [9 empty] | 58000 | 58000 | No | Green | 2024-07-01 |  |  |  | 2023-07-31 | [21 empty] | 4/28/23 Waiting on Degens quote | 2023-04-28 |  |  | West | Pipelines and Terminals | Station/Terminal |  | Michiana | BETNM - BET NILES TERMINAL |  |  | 0 |  |  |  | 58000 | Gardner, Travis |  |  |  | 1 | 44433 |  | Guest, ProSight | Independent | Aqua | 2022-08-05 | Other Programs
Niles Terminal Baseline Facility Assessment | Item | Open | MEXP | BETNM00E2203 | Exempt | 1980271 | Smith, Kyle | West | 6. Operational | Defined | Facility Integrity | -1447 |  |  | -1446.86 | -1447 | 0 | Green |  |  |  | -1447 |  |  | 36000 |  |  | 36000 | Phase | 36000 | 11353 |  | 11353 | No | Green | 2022-12-01 | 2022-05-11 | 2022-05-11 | 2022-12-31 | 2022-12-31 |  |  | -1011.86 | -435 | [17 empty] | 1/1/23 - received proposal from program owner and will get req entered into JDE for work - adjusted FCST. 11/1/22 Waiting on scope of work and scheduling from Corporate | 2023-01-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Michiana | BETNM - BET NILES TERMINAL |  | -1447 | 0 |  |  | 12800 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 41199 |  | Administrator, System | Independent |  | 2021-08-10 | Int - Planned Corr & FI
Niles Terminal Dike Repairs | Item | Open | MEXP | BETNM00E2202 | Maintenance Framework | 1970933 | Parker, Brian | West | 6. Operational | Defined | Secondary Containment | 38944 | 9000 |  | 47944.03 | 60000 | -12056 | Red | 80000 |  | 80000 | -32056 |  |  | 1000 | 64000 |  | 65000 | Phase | 65000 | 38944 | 9000 | 47944 | No | Green | 2023-04-01 | 2022-04-08 | 2022-04-08 | 2022-10-31 | 2023-04-24 | [5 empty] | 38944.03 |  |  | 38944 | Red |  |  |  | 9000 | [7 empty] | 5/1/23 - work completed ahead of schedule on Apr 24th - need to accrue 30,900 for Job Site Servies and 8,000 for CASTI in Apr. Have 9,000 in Jun for as-builts and SSSP plan updates. Diamond Z will be onsite May 9th to complete as-builts. 4/19/23 - JSS started work on Apr 18th. 4/10/23 - JSS would like to start on the 17th at Niles - just entered an Inspector request. 4/1/23 - SSSP has been approved by Rob O'Neill. Just waiting for Tom Holderman with JSS to schedule this work. Informed him that I need 2 week notice so I can get an inspector scheduled. They also completed a site visit in May to look over both Niles projects. 3/1/23 - reached out to Tom Holdeman w/Job Site Services to request the completed SSSP so we are ready to go once the weather breaks. Should have this to sometime this week. 2/3/23 - will work on SSSP approval in Feb/Mar so we can start work once the weather breaks. 1/3/23 - no change to status - work will start once weather breaks - still need to get SSSP and get this approved. 11/30/22 - work pushed out to 2023 due to weather and contractor availability. 10/31/22 - PO issued to Job Site Services on 10/18 - waiting to see if they can get this on their schedule for 2022 and if so, need to get HASP approved and get inspector scheduled. 9/29/22 - only received a bid from Job Site Services for 30,900. Waiting on a proposal from Klump Excavating. 9/8/22 - moving this FCST out to 2023 - not 100% sure contractors are available for this work for the remainder of 2022. Will attempt to get work completed in 2022 but planning for worst case scenario since cutoff for 2023 FCST's is near. 9/3/22 - the bid event had issues and nobody from Supply Chain followed up to see how this was progressing. Wasted 1 month on this and starting the bid process over again. I will be reaching out to all bidders the week of Sep 6th to make sure they have everything they need. Still expect to complete this work in Oct/Nov. 8/1/22 -emailed IFC drawings on 7/7 and received no feedback. Will get pricing from contractors in Aug and might be able to start workin mid-Sep. Forecasting the work for Oct timeframe for now. 7/3/22 - will be sending out IFC drawingto management for review via email. Bidding is off the table right now due to contractor availability so just plan on obtaining several quotes from qualified vendors. 5/31/22 - have IFC drawings in hand - will complete bid document once I have all IFC drawings in hand and have completed drawing reviews. 5/3/22 - just waiting on IFC drawings from Diamond Z for some other dike projects so we can group these together and go out for bid sometime around late Jun or early Jul. 4/5/22 - submitted Phase I AFE for approval routing. | 2023-05-05 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Michiana | BETNM - BET NILES TERMINAL |  |  | 47944 |  |  |  |  | Spari, Markella | Spari, Markella |  |  | 1 | 40564 |  | Guest, ProSight | Independent | Aqua | 2021-07-16 | Other Programs
Niles West (BETNT) - Secondary containment dike wall upgrades | Item | Open | MCAP | BETNT00M2203 | Maintenance Framework | 1970661 | Parker, Brian | West | 8. Canceled | Defined | Secondary Containment |  |  |  | 0 |  | 0 | Green | [6 empty] | 5000 | 68000 |  | 5000 | Phase | 73000 | 0 |  | 0 | No | Green | 2022-06-01 | 2022-04-08 | 2022-04-08 | 2022-10-31 | 2022-06-01 | [21 empty] | 10/31/22 - this project will be cancelled. Work is not Capital and was moved to an Expense project. 9/29/22 - only received a bid from Job Site Services for 38,400. Waiting on a proposal from Klump Excavating. 9/8/22 - moving this FCST out to 2023 - not 100% sure contractors are available for this work for the remainder of 2022. Will attempt to get work completed in 2022 but planning for worst case scenario since cutoff for 2023 FCST's is near. 9/3/22 - the bid event had issues and nobody from Supply Chain followed up to see how this was progressing. Wasted 1 month on this and starting the bid process over again. I will be reaching out to all bidders the week of Sep 6th to make sure they have everything they need. Still expect to complete this work in Oct. 8/1/22 - emailed IFC drawings on 7/7 and received feedback that Travis that everything looks good. Will get pricing from contractors in Aug and might be able to start work in mid-Sep. 7/2/22 - don't expect any additional invoices from Diamond Z if SOW remains the same - need to schedule call with management to review SOW and get some quotes from vendors. 5/31/22 - have IFC drawings in hand - will complete bid document once I have all IFC drawings in hand and have completed drawing reviews. 5/3/22 - just waiting on IFC drawings from Diamond Z then will bid this work out with other Dike projects to be completed around Aug or Sep. 4/1/22 - have a proposal from Diamond Z to generate IFC drawings - will be submitting this under a Phase I Parent AFE in Apr so we can go out for bid sometime in May. Moving FCST out to Jul. | 2022-10-31 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | BETNT - BET NILES WEST TERMINAL |  |  | 0 |  |  | 0 |  | Clark, Dave | Spari, Markella |  |  | 1 | 41755 |  | Spari, Markella | Independent | Aqua | 2021-08-20 | Other Programs
Niles West Load Rack Fire Suppression Extension | Item | Open | MCAP | BETNT00M2202 | Maintenance Framework | 1955718 | Smith, Kyle | West | 6. Operational | Defined | Fire Protection | 2414 |  |  | 2414.35 | 2414 | 0 | Green |  |  |  | 2414 |  |  | 60000 |  |  | 60000 | Full | 60000 | 61227 |  | 61227 | No | Green | 2022-05-01 | 2022-03-11 | 2022-03-11 | 2022-05-30 | 2022-12-31 |  |  | 0 | 2314.45 | 99.9 | [16 empty] | 1/1/23 Work Completed | 2023-01-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | BETNT - BET NILES WEST TERMINAL |  | 2414 | 0 |  |  | 58813 |  | Jakubowski, Gregory | Baldwin, T. Andy |  |  | 1 | 40732 |  | Guest, ProSight | Independent | Aqua | 2021-07-26 | Other Programs
Niles West Secondary Containment Dike Wall Upgrades MEXP | Item | Open | MEXP | BETNT00E2202 | Maintenance Framework | 2037888 | Parker, Brian | West | 6. Operational | Defined | Secondary Containment | 44427 | 9000 |  | 53427 | 61000 | -7573 | Red |  |  |  | 53427 |  |  | 66000 |  |  | 66000 | Full | 66000 | 46002 | 9000 | 55002 | No | Green | 2022-10-01 | 2022-10-25 | 2022-10-25 | 2023-05-31 | 2023-04-19 | [5 empty] | 44427 |  |  | 44427 | Red |  |  |  | 9000 | [7 empty] | 5/1/23 - work completed at BETNT on 4/19. Need to accrue 38,400 for Job Site Services and 6,000 for CATSI. Jun FCST of 9,000 is for as-builts and SPCC plan updates. Diamond Z will be onsite May 9th to complete as-builts. 4/17/23 - work started today at BETNT. 4/10/23 - JSS would like to start on the 17th at Niles - just entered an Inspector request. 4/1/23 - SSSP has been approved by Rob O'Neill. Just waiting for Tom Holderman with JSS to schedule this work. Informed him that I need 2 week notice so I can get an inspector scheduled. They also completed a site visit in May to look over both Niles projects. 3/1/23 - reached out to Tom Holdeman w/Job Site Services to request the completed SSSP so we are ready to go once the weather breaks. Should have this to sometime this week. 2/3/23 - will work on SSSP approval in Feb/Mar so we can start work once the weather breaks. 1/3/23 - no change to status - work will start once weather breaks - still need to get SSSP and get this approved. 11/30/22 - work pushed out to 2023 due to weather and contractor availability. 10/31/22 - PO issued to Job Site Services on 10/18 - waiting to see if they can get this on their schedule for 2022 and if so, need to get HASP approved and get inspector scheduled. 10/20/22 - routed MEXP AFE for approval - this is replacing the MCAP project that out for approval - SOW does not meet capitalization criteria. 9/29/22 - only received a bid from Job Site Services for 38,400. Waiting on a proposal from Klump Excavating. 9/8/22 - moving this FCST out to 2023 - not 100% sure contractors are available for this work for the remainder of 2022. Will attempt to get work completed in 2022 but planning for worst case scenario since cutoff for 2023 FCST's is near. 9/3/22 - the bid event had issues and nobody from Supply Chain followed up to see how this was progressing. Wasted 1 month on this and starting the bid process over again. I will be reaching out to all bidders the week of Sep 6th to make sure they have everything they need. Still expect to complete this work in Oct. 8/1/22 - emailedIFC drawings on 7/7 and received feedback that Travisthat everything looks good. Will getpricing from contractors in Aug and mightbe able to start work in mid-Sep. 7/2/22 - don't expect any additional invoices from Diamond Z if SOW remains the same - need to schedule call with management to review SOW and get some quotes from vendors. 5/31/22 - have IFC drawings in hand - will complete bid document once I have all IFC drawings in hand and have completed drawing reviews. 5/3/22- just waiting on IFC drawings from Diamond Z then will bid this work out with other Dike projects to be completed around Aug or Sep. 4/1/22 - have a proposal from Diamond Zto generate IFC drawings - will be submitting this under a Phase I Parent AFE in Apr so we can go out for bid sometime in May. Moving FCST out to Jul. | 2023-05-05 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Michiana | BETNT - BET NILES WEST TERMINAL |  |  | 53427 |  |  | 1575 |  | Spari, Markella | Spari, Markella |  |  | 1 | 46093 |  | Guest, ProSight | Independent | Aqua | 2022-10-20 | Other Programs
Niles West Security Camera System Upgrade | Item | Candidate | MCAP |  | Maintenance Framework |  | Fink, Ryan | West | 2. Pending AFE |  | Security & Cameras |  | 70000 |  | 70000 | 50000 | 20000 | Red | 50000 |  | 50000 | 20000 | [9 empty] | 70000 | 70000 | No | Green | 2023-07-01 |  |  |  | 2023-09-29 | [14 empty] | 5000 | 17000 | 35000 | 13000 |  |  |  | 4/28 RRF - 20k moved from other projects, AFE in May, EAC $70k 4/6 RRF - estimates exceed budget, revising scope to fit budget, and RFQ again. EAC $50k 3/1 RRF - RFQ out to vendors EAC 50k 2/2 RRF - Site visit 2/21 | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | BETNT - BET NILES WEST TERMINAL |  |  | 0 | 57000 | 13000 |  |  | Clark, Chris |  |  |  | 1 | 24317 |  | Administrator, System | Independent | Aqua | 2017-07-21 | Other Programs
Niles West Truck Rack Preset Upgrade | Item | Open | MCAP | BETNT00M2204 | Maintenance Framework | 2013798 | Fink, Ryan | West | 6. Operational | Defined | Truck Racks | 4188 |  |  | 4188.19 | 3682 | 506 | Red |  |  |  | 4188 |  |  | 77000 |  |  | 77000 | Full | 77000 | 62590 |  | 62590 | No | Green | 2022-09-01 | 2022-08-28 | 2022-08-28 | 2022-10-07 | 2022-12-31 |  |  | 1149.51 | 2423.84 | 109.07 | 505.77 |  |  | 506 | Red | [11 empty] | 5/2 RRF - Review documentation and close EAC $62k 4/7 RRF - Close. EAC $62k 3/1 RRF - prepare to close 2/1 RRF - updated, operational, closeout 1/23 RRF - Proving invoiced lower than expected, $1707. 1/4/23 RRF - Install complete, meter xmtr damaged, added 4k to costs. Accrue 11609 to Franklin for proving and meter repairs. 12/1 RRF - Install in progress, accrue 2500 nov 11/9 RRF - Nov/Dec install, reclass Triad PO to BETNT00R2201 10/31 RRF - Oct actual $1121, Material arrived, scheduling with Cetane proj for install. 9/30 RRF - Sept actual 29.2k, eng and panel fab in progress. 9/20 RRF - Sept spends $28k, PO to Triad. ML and FCM arrived, shipping to Triad. Dropped inspection from fcst, to be covered by RCAP. Moved Triad to Dec, will be moved to RCAP. 9/2 RRF - AFE approved, POs out to vendors 8/2 RRF - pending receipt of quotes, to submit AFE. Moved out one month. 7/11/2022 RRF - Site visit for estimate 7/14. AFE to follow | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | BETNT - BET NILES WEST TERMINAL |  | 3682 | 506 |  |  | 58402 |  | Younce, Michael | Baldwin, T. Andy |  |  | 1 | 41833 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Novi Station Prover Valve Rebuild | Item | Open | MCAP | WN00000M2201 | Maintenance Framework | 2023818 | Burns, Richard | West | 3. Active | Drawdown | Valves | 431 | 40000 |  | 40431.42 | 40152 | 280 | Yellow |  |  |  | 40431 |  |  | 60000 |  |  | 60000 | Full | 60000 | 11245 | 40000 | 51245 | No | Green | 2022-11-01 | 2022-11-17 | 2022-11-17 | 2022-12-31 | 2022-12-30 |  |  | 49.07 | 50.78 | 51.69 | 279.88 |  |  | 280 | Red |  |  |  | 40000 | [7 empty] | 5/1/23 - same 4/3/23 - firmer estimate received and PO was issued. 3/1/23 - no change. 2/1/23 - Pushed forecast out. Soft goods valve parts are 14-16 delivery. Valve will require more extensive rebuild than originally expected, waiting on quote. Supplemental may be required. 1/3/23 - variance is because of vendor issues with the valve type and parts / supply chain issues. Should be done in January but forecast pushed to February. 12/2/22 - Project recently approved; variance is from reclass of charges (Holly and Macomb invoices) from the local budget. Forecasted remaining costs to rebuild valve and reinstall. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Pipeline | WN - NOVI TERMINAL |  | 152 | 40280 |  |  | 10814 |  | Oey, Alex | Gardner, Dale |  |  | 1 | 46217 |  | Gardner, Travis | Independent | Aqua | 2022-11-10 | Other Programs
OD531YO - DIG SHEETS (9) | Item | Open | MCAP | OD531YOM2202 | Maintenance Framework | 2037421, 2037422, 2037423, 2037424, 2037425, 2037426, 2037427 | Burns, Richard | West | 3. Active | Drawdown | Pipeline Digs | 194662 | -25666 |  | 168995.54 | 253993 | -84998 | Red |  |  |  | 168996 |  |  | 519000 |  |  | 519000 | Full | 519000 | 297830 | -25666 | 272164 | No | Green | 2022-12-01 | 2022-12-03 | 2022-12-03 | 2023-04-18 | 2023-12-15 |  |  | 17534.73 | 88441.39 | 78016.93 | 10668.49 |  |  | 10668 | Red |  | Other | -95666 | [6 empty] | 70000 |  | 5.8.23 - $-95,666 forecast in May due to MEXP Flip to OD531YOE2301 (AS) 5/1/23 - variance is PPS invoice for documentation. 4.6.23 - added -$72,600 to March for MEXP Flip OD531YOE2301 (AS) 4/3/23 - variance is from under-accrual and last dig. Extreme wet weather made access difficult and required extra equipment (dozer, 2nd hoe) to access dig site. 3/8/23 - high water conditions at lake dig caused this dig to be delayed. Will complete it at the end of the year when lake level is lowered. Changed forecast accordingly. 3/7/23 - changed forecast to complete last dig in March. Permits for 211 digs fell through so they will stay on these. 3/1/23 - variance is from work completed ahead of schedule. Accrued some for contractor and inspection. Two digs left. One dig may push until April due to water levels in the reservoir and the proximity of the dig to that. Also adjusted March forecast so crew can go work on 211 immediate dig. 2/1/23 - Variance is from under accruing last month ($7243), and Percheron ($2365). Actual here does not match COGNOS ($13,155 vs $9608).. Adjusted forecast based on contractor's schedule with other dig projects that have become more pressing than these. 1/3/23 - variance is from an extra dig being completed. Accrued $15K (Degen), $5581 (MNT) for that dig. Adjusted forecast based on new schedule. 12/2/22 - Two DOT-60 digs to start 12/5/22. 11/20/22 - AFE submitted. Two DOT-60 digs to be done in December. Rest in 2023. 11/1/22 - digs issued on 10/20/22. | 2023-05-08 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Mantua | OD531YO - MOGADORE STA TO YOUNGSTOWN TER |  | 183993 | -84998 |  | 70000 | 103168 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 46105 |  | Guest, ProSight | Independent | Aqua | 2022-10-20 | Int- Planned Digs
OD531YO DEF/MFL 2019 DOT 180 + BPL Other Digs | Item | Open | MCAP | OD531YOM1901 | Exempt | 1566991, 1581572, 1581573, 1581574 | Burns, Richard | West | 7. Closed | Drawdown | Pipeline Digs | -3284 |  |  | -3283.92 | -3284 | 0 | Green |  |  |  | -3284 |  |  | 311000 |  |  | 311000 | Full | 311000 | 0 |  | 0 | No | Green | 2020-03-01 | 2019-05-07 | 2019-05-07 | 2019-06-05 | 2019-06-21 |  |  |  |  | -3283.92 | [16 empty] | 7/31/19 - job book submitted. 7/2/19 - all digs completed 6/21/19. 6/4/19 - digs started on 5/16/19. DOT 180 dig (F-183500) repair completed on 5/22/19. | 2019-08-02 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Mantua | OD531YO - MOGADORE STA TO YOUNGSTOWN TER |  | -3284 | 0 |  |  |  |  | Bartal, Nick | Bassani, Joel D. |  |  | 1 | 33222 |  | Kabaria, Erika | Independent | Aqua | 2019-05-01
Ottumwa Ethanol - Biodiesel - Additive Offload Containment Installation 2018 | Item | Open | MCAP | BETOT00M2202 | Maintenance Framework |  | Scott, Cory | West | 3. Active | Defined | Secondary Containment | 387 | 120000 |  | 120387.08 | 120288 | 99 | Yellow | 120000 |  | 120000 | 387 |  |  | 22000 |  |  | 22000 | Phase | 22000 | 20835 | 120000 | 140835 | No | Green | 2022-08-01 | 2022-06-28 | 2022-06-28 | 2022-07-25 | 2023-06-30 |  |  | 94.32 | 96.02 | 97.76 | 98.98 |  |  | 99 | Red | [6 empty] | 120000 |  |  |  |  | 5/8/2023 - Working with engineering 4/18/2023 - Ryan and Associates sent quote for containment. Need to work with Engineering for updated scope approval. 1/9/2023 - Planning out new design for upper management approval. 10/11/2022 - remaining work in 2023. 6/29/2022 - PO placed for TAS Technical for $19,450.00 6/20/2022 - Meeting with TAS. Project planned to be designed for driveway extension and containment. 5/31/2022 - Working with Diamond Z to develop drawings for a containment across drive. 5/9/2022 - Phase AFE submitted to remedyforce for TAS Technical engineering and design. 4/16/2022 - Proposal has been received from TAS for $19,450 for the engineering and design of full project. 4/14/2022 - It has been determined that it will be a hazard to install this containment pad without extending driveway for safe backing up. The new plan is to use this funding for engineering and design of a containment along with a driveway extension. 3/14/2022 - Started working on Scope of Work and sent drawing to a contractor to work up an estimate for this project. | 2023-05-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | BETOT - BET OTTUMWA |  | 288 | 99 | 120000 |  | 20448 |  | Clark, Dave | Smith, Todd W. |  |  | 1 | 24322 |  | Administrator, System | Independent | Aqua | 2017-07-21 | Other Programs
Ottumwa Outfall Valve Platforms | Item | Candidate | MCAP |  | Maintenance Framework |  | Scott, Cory | West | 2. Pending AFE |  | Secondary Containment |  | 31000 |  | 31000 | 31000 | 0 | Green | 31000 |  | 31000 | 0 | [9 empty] | 31000 | 31000 | No | Green | 2023-08-01 |  |  |  | 2023-06-30 | [15 empty] | 16000 | 15000 |  |  |  |  | 4/18/2023 - Ryan and Associates produced quote for project installation. Civil scope still required. 3/31/2023 - Ryan and Associates looking at project to get ideas for execution. | 2023-04-18 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | BETOT - BET OTTUMWA |  |  | 0 | 31000 |  |  |  | Clark, Dave |  |  |  | 1 | 41888 |  | Guest, ProSight | Independent | Aqua | 2021-08-21 | Other Programs
Ottumwa Pipeline MCC Power Feed Upgrade | Item | Open | MCAP | BETOT00M2205 | Maintenance Framework | 2011329 | Grinder, Mark | West | 6. Operational | Defined | Electrical | 1303 |  |  | 1303.04 | 1303 | 0 | Green |  |  |  | 1303 |  |  | 63000 |  |  | 63000 | Full | 63000 | 52026 |  | 52026 | No | Green | 2022-10-01 | 2022-08-04 | 2022-08-04 | 2022-12-31 | 2022-12-30 |  |  | 1303.04 | 0 | 0 | 0 |  |  | 0 | Green | [11 empty] | 4-27-2023 - This project has been completed. 3-23--2023 - This project has been completed. 3-01--2023 - This project has been completed. 1-31-2023 - This project has been completed. 12-29-2022 - This project was completed in December. 11-28-2022 - Material received and project scheduled to start December 12th. 11-01-2022 - Material received and project scheduled to start December 12th. 9-26-2022 - Material on order and should be received Mid October and project completion should happen in November/December. 8-29-2022 - The AFE was approved and waiting for a second quote because cost was over 30K. 7-27-2022 - AFE sent for approval because extra funding needed to complete project and waiting for approval before submitting into the workflow. Forecasting this for October because of the amount of work at the facility in September 6-29-2022 - I have moved this forecast to September, I have not received the quote for this work yet. 5-31-2022 - Performed a site visit this month and waiting for quote for AFE submittal. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | BETOT - BET OTTUMWA |  | 1303 | 0 |  |  | 50723 |  | Ashley, Robert | Smith, Todd W. |  |  | 1 | 34995 |  | Guest, ProSight | Independent | Aqua | 2019-08-30 | Other Programs
Ottumwa Secondary Containment Improvements | Item | Open | MEXP | BETOT00E2202 | Maintenance Framework | 1970943 | Parker, Brian | West | 3. Active | Defined | Secondary Containment | 47 | 85000 |  | 85047.25 | 85047 | 0 | Green | 85000 |  | 85000 | 47 |  |  | 1000 |  |  | 1000 | Phase | 1000 | 652 | 85000 | 85652 | No | Green | 2022-10-01 | 2022-04-08 | 2022-04-08 | 2022-10-31 | 2023-07-31 |  |  | 47.25 | [11 empty] | 25000 | 60000 | [5 empty] | 5/1/23 - bidding end date is May 5th - expect to get bids evaluated and PO's issued in May. 4/10/23 - created bid event in Coupa on Apr 7th. 4/1/23 - have complete list of bidders now by location and will get a Coupa bid event created in Apr for the Phase II construction. BWC is setup now and can bid on this work. 2/28/23 - entered Coupa request to get BWC added as a new vendor so they can bid on this project. Sent emails out to 10 contractors to see which locations they want to bid on for dike work in 2023. I've received 6 responses back to date. Should have bid event created in Coupe in Mar for this project. 2/3/23 - working on getting another contractor setup as a Buckeye approved contractor so they can bid on this work. Plan to get a bid event entered in Feb or Mar so we can start work once the weather breaks. 1/3/23 - no change in status - work pushed out to 2023. Need to conduct a bid event in Q1. 11/30/22 - TIMCO proposal was high - pushing this work out to 2023 and will re-bid this work in Q1 2023. 10/31/22 - still waiting on a proposal from TIMCO - I don't expect this work to be completed until 2023. 9/29/22 - Ryan & Assoc declined to bid, just waiting on a proposal from TIMCO. 9/8/22 - moving this FCST out to 2023 - not 100% sure contractors are available for this work for the remainder of 2022. Will attempt to get work completed in 2022 but planning for worst case scenario since cutoff for 2023 FCST's is near. 9/3/22 - the bid event had issues and nobody from Supply Chain followed up to see how this was progressing. Wasted 1 month on this and starting the bid process over again. I will be reaching out to all bidders the week of Sep 6th to make sure they have everything they need. Still expect to complete this work in Oct/Nov 8/1/22 - emailed IFC drawings on 7/6 and received no feedback. Will get pricing from contractors in Aug and might be able to start work in mid-Sep. Forecasting the work for Sep/Oct timeframe for now. 7/3/22 - will be sending out IFC drawing to management for review via email. Bidding is off the table right now due to contractor availability so just plan on obtaining several quotes from qualified vendors. 5/31/22 - have IFC drawings in hand - will complete bid document once I have all IFC drawings in hand and have completed drawing reviews. 5/3/22 - just waiting on IFC drawings from Diamond Z for some other dike projects so we can group these together and go out for bid sometime around late Jun or early Jul. 4/5/22 - submitted Phase I AFE for approval routing. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Eastern Iowa | BETOT - BET OTTUMWA |  | 47 | 0 | 85000 |  | 605 |  | Spari, Markella | Spari, Markella |  |  | 1 | 41441 |  | Guest, ProSight | Independent | Aqua | 2021-08-13 | Other Programs
Ottumwa Tank 4 Ringwall Repairs | Item | Candidate | MEXP |  | Maintenance Framework |  | Roth, Aaron | West | 5. Deferred |  | Tanks |  |  |  | 0 |  | 0 | Green | 60000 |  | 60000 | -60000 | [9 empty] | 60000 | 60000 | No | Green | 2024-07-01 |  |  |  | 2024-07-31 | [21 empty] | 4.3 - project funding pushed to 2024. | 2023-04-03 |  |  | West | Pipelines and Terminals | Tank Integrity |  | Eastern Iowa | BETOT - BET OTTUMWA |  |  | 0 |  |  |  | 60000 | Stine, Carlton |  | N/A |  | 1 | 29831 |  | Guest, ProSight | Independent | Aqua | 2018-07-06 | Int - Tanks
Ottumwa VCU Refractory Replacement | Item | Open | MCAP | BETOT00M2301 | Maintenance Framework | 2121570 | Scott, Cory | West | 3. Active | Defined | Vapor Management |  | 110000 |  | 110000 | 110000 | 0 | Green | 110000 |  | 110000 | 0 |  |  | 109733 |  |  | 109733 | Full | 109733 |  | 110000 | 110000 | No | Green | 2023-06-01 | 2023-05-09 | 2023-05-09 | 2023-07-15 | 2023-05-31 | [13 empty] | 30000 | 80000 | [6 empty] | 5/9/2023 - AFE fully approved. PO placed for Cimarron to order materials. 5/2/2023 - Submitting AFE request. 4/19/2023 - Build scope for bid event. Send to supply chain along with (2) estimates which were already procured. 4/18/2023 - (2) Quotes have been procured. A bid event will be held for this project once scope is built. I plan to build scope soon. | 2023-05-09 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Eastern Iowa | BETOT - BET OTTUMWA |  |  | 30000 | 80000 |  |  |  | Karl, Marissa | Smith, Todd W. |  |  | 1 | 41753 |  | Schumacher, Chelsea | Independent | Aqua | 2021-08-20 | Other Programs
Peotone Station PLC5 Conversion | Item | Open | MCAP | PN00000M2201 | Maintenance Framework | 1979721 | Grinder, Mark | West | 3. Active | Defined | Instrumentation & Controls | 3015 | 20000 |  | 23015.32 | 22317 | 698 | Yellow | 20000 |  | 20000 | 3015 |  |  | 172000 |  |  | 172000 | Full | 172000 | 146967 | 20000 | 166967 | No | Green | 2022-06-01 | 2022-05-04 | 2022-05-04 | 2022-09-30 | 2023-06-30 |  |  | 660.9 | 952.86 | 703.41 | 698.15 |  |  | 698 | Red |  |  |  | 20000 | [7 empty] | 4-27-2023 - Wood River is still on scheduling June 12th through the 16th outage so we are tentatively scheduled for this week with scheduling.group. 3-23-2023 - Wood River is supposed to have a scheduled 5-day outage in late May early June and this will determine the cutover, we are tentatively scheduled for May but need scheduling group to confirm. 3-01-2023 - All material has been delivered and working on downtime schedule for cutover. 2-01-2023 - This project is still waiting for Analog cards and should arrive this month, 12-29-2022 - This project was supposed to be executed in the Beginning of October but was informed that the pipeline scheduled outage has changed and we are still missing a Prosoft card and a 13-slot rack. We are completing all of the PLC and HMI programming, Control Narrative and Drawings this year and we will schedule the installation in early 2023 when all material is received. 11-28-2022 - This project was supposed to be executed in the Beginning of October but was informed that the pipeline scheduled outage has changed and we are still missing a Prosoft card and a 13 slot rack. We are completing all of the PLC and HMI programming, Control Narrative and Drawings this year and we will schedule the installation in early 2023 when all material is received. 11-01-2022 - This project was supposed to be executed in the Beginning of October but was informed that the pipeline scheduled outage has changed and we are still missing a Prosoft card and a 13 slot rack. We are completing all of the PLC and HMI programming, Control Narrative and Drawings this year and we will schedule the installation in early 2023 when all material is received. 9-26-2022 - This project was supposed to be executed in the Beginning of October but was informed that the pipeline scheduled outage has changed and we are still missing a Prosoft card and a 13 slot rack. We are completing all of the PLC and HMI programming, Control Narrative andDrawings this year and we will schedule the installation in early 2023 when all material is received. 8-29-2022 - The fiber work is completed and planning on completing most of the PLC cut-over during the October 3rd through the 8th Wood River outage thetotally complete the project once the Analog cards are shipped in 2023. 7-27-2022 - Fiber has been received and waiting for a lift plan from contractor so we can install 2 utility poles, runand terminate the fiber. Rockwell material is supposed to be received in September for a October completion. I am forecasting 20K for May of 2023 because the PLC Analog modules are not being delivered until March of 2023. 6-29-2022 - The Fiber is being delivered Thursday 6-30-2022 and working on an installation Schedule. 5-31-2022 - The Fiber is supposed to be delivered at the end of June and will try to schedule installation as soon as it arrives. 5-02-2022 - AFEsubmitted but not fully approved, planning on September completion. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Argo | PN - PEOTONE STATION |  | 2317 | 20698 |  |  | 143951 |  | Forsey, Frank | Hoekstra, Matt | N/A |  | 1 | 25720 |  | Guest, ProSight | Independent | Aqua | 2017-09-08 | Other Programs
Peotone Terminal (BETPN) Tank P-70 Gauge Repair | Item | Open | MEXP | BETPN00E2301 | Maintenance Framework | 2096452 | Roth, Aaron | West | 6. Operational | Drawdown | Tanks | 13000 |  |  | 13000 | 15000 | -2000 | Red |  |  |  | 13000 |  |  | 15000 |  |  | 15000 | Full | 15000 | 13000 |  | 13000 | No | Green | 2023-04-01 | 2023-03-29 | 2023-03-29 | 2023-05-31 | 2023-05-31 | [5 empty] | 13000 | 15000 | 15000 | -2000 | Red | [11 empty] | 5.1 - done | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Argo | BETPN - BET PEOTONE TERMINAL |  |  | 13000 |  |  |  |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 46835 |  | Stine, Carlton | JDE Child | Burnt Orange | 2023-03-23
PG718CO B-SLEEVE CUTOUT | Item | Open | MCAP | PG718COM2201 | Maintenance Framework | 1970536 | Roman, James | West | 6. Operational | Defined | Pipeline Digs | 1850205 | 70000 |  | 1920205.24 | 1829947 | 90258 | Yellow | 1200000 |  | 1200000 | 720205 |  |  | 215000 | 1416000 | 598000 | 1631000 | Full | 2229000 | 2123029 | 70000 | 2193029 | No | Green | 2022-04-01 | 2022-04-07 | 2022-04-07 |  | 2023-03-31 |  |  | 526949.62 | 521127.42 | 711869.72 | 90258.48 | 70000 | 70000 | 20258 | Red |  | Other | 70000 | [8 empty] | 5/1/23 Variance -$712,916, Accrual $701,140, Still need to restore asphalt. 4/5/23 Approved budget should be $2,229,000. Variance -$514k. Accrual $767k.. Cutout is finished, need to repair county road in April. 3/1/23 Variance -$286k. Accrue $370,963. Underestimated disposal costs for spoils. Will submit ECO and supplement for scope increase and unforseen site issues. 2/1/23 Variance $-25k. 1/4/23 Variance $3k. Local charges as we ramp up for construction. 12/5/22 No change. 11/1/22 Variance (-$173k) Accrual for $174k. Plan to mobilize January 9, 2023. 10/3/22 Variance (-) Accrual. Schedule remains for Q1 2023 9/1/22 Variance (-) Accrual. 8/25/2022 - Project pushed to 2023 to address overall MCAP budget. Remaining forecast moved to Q1 2023. 8/3/22 I have pushed the schedule a month. See below. In addition we are working from a verbal confirmation from railroad, I still have nothing in writing. 8/2/22 Just received notice from railroad that flaggers are not available to start until 8/29/22. Will need to make decision whether or not to push purge into October. I estimate needing 3 weeks for excavation. An 8/29/22 start date only provides 2 weeks for excavation. Will make decision prior to this forecast being due and will adjust forecast if necessary. 8/1/22 Variance (+), spent more on materials than originally estimated. Hopefully receive railroad permit by end of this week. Scheduling dept requested that we do purge week of 9/12/22. In order to meet this date, we'll need to begin excavating by 8/22/22. 7/5/22 Variance + Missed an accrual. Waiting on Railroad Permit and Railroad Flagger Schedule. Will move some forecast $$ later into Q2. 6/2/22 HOP submitted, some material purchased. Hope to have RR permit and flaggers scheduled by late July. 5/3/22 Assembling environmental permit, ordering some fittings and pigs in May. Currently scoping the work, forescast is for placeholders at this time. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity | Integrity | Coraopolis | PG718CO - PITTSBURGH TO CORAOPOLIS |  | 1759947 | 160258 |  |  | 272824 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 43308 |  | Meitzler, Antoinette | Independent | Aqua | 2022-03-31 | Int - Accel Cutouts
Pittsburgh Terminal (BETRN) Tank 5 - OOS Corr Insp & Refurb | Item | Open | MCAP | BETRN00M2101 | Exempt | 1783671 | Henfling, Mike | West | 7. Closed | Unplanned | Tanks | 14678 |  |  | 14678.38 | 14678 | 0 | Green |  |  |  | 14678 |  |  | 246000 | 143000 | 43000 | 432000 | Supplemental | 432000 | 450168 |  | 450168 | No | Green | 2021-01-01 | 2020-12-15 | 2020-12-15 | 2021-12-31 | 2021-11-22 |  |  | 14046.3 | 632.08 | [17 empty] | 2/23/2023 - variance for unpaid invoice from 2022. 4-4-22 - Supplemental AFE approved, project ready to close. 3-2-22 - Project is complete. Supplemental AFE to be submitted very soon to address AFE overage. One final invoice for $1k forthcoming. 2-2-22 - Project is complete. Supplemental AFE to be submitted early February to address AFE overage 1-5-22-Project complete, awaiting final invoices. | 2023-02-03 | Pastorius, Bonnie | Gardner, Travis | West | Pipelines and Terminals | Integrity |  | Coraopolis | BETRN - BET PITTSBURGH |  | 14678 | 0 |  |  | 5168 |  | Stine, Carlton | Bassani, Joel D. | N/A |  | 1 | 30393 |  | Guest, ProSight | Independent | Aqua | 2018-08-07 | Int - Tanks
Pittsburgh Terminal Kiosk Replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Roknich, Hunter | West | 2. Pending AFE |  | Truck Racks |  | 20002 |  | 20002 | 20002 | 0 | Green | 20000 |  | 20000 | 2 | [9 empty] | 20002 | 20002 | No | Green | 2023-11-01 |  |  |  | 2023-09-30 | [18 empty] | 20000 | 2 |  | Kiosk replacement to be completed under side-blending project per OM. 20k available. | 2023-02-24 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Coraopolis | BETRN - BET PITTSBURGH |  |  | 0 |  | 20002 |  |  | Younce, Michael |  |  |  | 1 | 41680 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
PN160AG Inlet Valve 30-1 Replacement Re-Class | Item | Open | MCAP | PN160AGM2203 | Maintenance Framework | 2095196 | Parker, Brian | West | 7. Closed | Emergent | Valves | 89680 |  |  | 89679.67 | 85818 | 3862 | Yellow |  |  |  | 89680 |  |  | 86000 |  |  | 86000 | Full | 86000 | 89680 |  | 89680 | No | Green | 2023-03-01 | 2023-03-20 | 2023-03-20 | 2023-03-24 | 2023-03-24 |  |  |  |  | 85817.87 | 3861.8 |  |  | 3862 | Red | [11 empty] | 5/6/23 - added memo to file for original project and this project. Project ready to be closed by accounting in JDE. Job Book completed and PO/WO closed. 4/1/23 - re-class was completed - just need to add a memo to file for this project that explains why this started out under business unit AG instead of PN160AG. 3/17/23 - submitted re-class AFE for approval routing, received Project # and WO # and submitted re-class request. This should post for Mar business. | 2023-05-06 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Argo | PN160AG - PEOTONE TO ARGO |  | 85818 | 3862 |  |  |  |  | Oey, Alex | Koranda, Chad E. |  |  | 1 | 46795 |  | Parker, Brian | Independent | Aqua | 2023-03-17
PN160AG Manhattan-Monee Rd (CH 6) Pavement Repairs | Item | Open | MEXP | PN160AGE2301 | Maintenance Framework | 2111954 | Stalbaum, Cameron | West | 1. Proposed | Drawdown | West |  | 35000 |  | 35000 |  | 35000 | Red |  |  |  | 35000 |  |  | 35000 |  |  | 35000 | Full | 35000 |  | 35000 | 35000 | No | Green | 2023-06-01 | 2023-04-20 | 2023-04-20 | 2023-07-28 | 2023-07-28 | [13 empty] | 35000 | [7 empty] | 5/1/23 - M&J is working on the traffic control plan. Hope to get this work completed here in May. | 2023-05-02 |  |  | West | Pipelines and Terminals | Station/Terminal |  | Argo | PN160AG - PEOTONE TO ARGO |  |  | 35000 |  |  |  |  | Gardner, Travis | Gardner, Travis W. | N/A |  | 1 | 46967 |  | Gardner, Travis | JDE Child | Burnt Orange | 2023-04-20
PN160EH - DIG SHEETS (10) | Item | Open | MCAP | XX160EHM2202 | Maintenance Framework | 2037467, 2037468, 2037469, 2037470, 2037471, 2037472 | Burns, Richard | West | 6. Operational | Defined | Pipeline Digs | 170031 |  |  | 170031.05 | 169437 | 594 | Yellow |  |  |  | 170031 |  |  | 422000 |  |  | 422000 | Full | 422000 | 380699 |  | 380699 | No | Green | 2022-11-01 | 2022-10-27 | 2022-10-27 | 2023-03-26 | 2022-12-31 |  |  | 62152.6 | 101283.79 | 6000.61 | 594.05 |  |  | 594 | Red |  | Other | [9 empty] | 5/1/23 - variance is PPS invoice for documentation. 4/3/23 - variance is SET Env. inv ($230) and internal labor for data documentation. 3/1/23 - variance is overspend due to missed forecast. Last dig required matting, additional time, etc. Also, GFL clean-up charges for earlier EH dig with leaking abandoned line ($19,184). All digs are complete. 2/1/23 - Variance is from starting work ahead of schedule. Accrued Degen cost for first dig. Adjusted Feb. forecast accordingly. 1/31/23 - Remaining 2 digs started in January, ahead of schedule. 1/3/23 - variance from completing an extra dig inside Hammond Station ahead of schedule. Plus, Percheron ($2576). Two digs left to complete. 12/2/22 - variance is accrued. Two digs remaining; 4 are complete. 12/1/9/22-pushed December forecast to February due to scheduling of construction crew with other digs. 11/1/22 - Two DOT-60 digs to start 11/7/22 and are due by 11/26/22. Other four dig sites due 3/26/23. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Michiana | XX160EH - IL S/L TO HAMMOND |  | 169437 | 594 |  |  | 210668 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 45929 |  | Schultz, Amy | Independent | Aqua | 2022-09-29 | Int- Planned Digs
PN160EH - DIG SHEETS (4) Immediate - Due 06-02-22 | Item | Open | MCAP | XX160EHM2201 | Maintenance Framework | 1981674, 1981675, 1981676, 1981677 | Burns, Richard | West | 6. Operational | Drawdown | Pipeline Digs | 3258 |  |  | 3258.06 | 3258 | 0 | Green |  |  |  | 3258 |  |  | 445000 |  |  | 445000 | Full | 445000 | 339492 |  | 339492 | No | Green | 2022-06-01 | 2022-06-30 | 2022-06-30 | 2022-07-01 | 2022-07-07 |  |  | 3117.76 | 140.3 | [17 empty] | 4/3/23 - ready to close. 2/1/23 - variance is MRC invoice finally hit after 6+ months. 1/3/23 - variance is from re-accrual from MRC & M&J Industrial; I'm giving up as I don't think there are any more costs. 12/2/22 - variance reaccrued. 11/1/22 - Variance is from over-accruing. Re-accrued for MRC and second part of M&J. Job book submitted. 0/3/22 - variance is re-accrued. 9/1/22 - variance is re-accrued. Overage is Shaw invoice and payroll. 8/1/22 - Accrual is for piping work at PN; variance is cost savings (Degen, Shaw invoices less than expected), and piping contractor for PN pipe modifications work came in higher than expected. Total was slight overspend. 7/7/21 - Peotone piping completed, changing it back to normal operations. 6/21/22 - digs finished today way ahead of schedule; variance is because of that. Forecast for next month is piping changes at PN. 6/1/22 - Four DOT-5 digs issued on 5/25/22. Interim AFE submitted on 5/27. Plan to start work on 6/6/22. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Michiana | XX160EH - IL S/L TO HAMMOND |  | 3258 | 0 |  |  | 336234 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 43860 |  | Gardner, Travis | Independent | Aqua | 2022-05-27 | Int- Planned Digs
Raceway Asphalt Replacement 2020 | Item | Candidate | MCAP |  | Exempt |  | Smith, Kyle | West | 2. Pending AFE |  | West |  | 40000 |  | 40000 | 40000 | 0 | Green | 40000 |  | 40000 | 0 | [9 empty] | 40000 | 40000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 40000 | [6 empty] | 4/28/23 Still trying to find vendors to complete. Working with Degen | 2023-04-28 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Indianapolis | BETRA - BET RACEWAY TERMINAL |  |  | 0 | 40000 |  |  |  | Gardner, Travis |  | N/A |  | 1 | 20491 |  | Guest, ProSight | Independent | Aqua | 2016-08-19 | Other Programs
Raceway Pump Containment Install | Item | Open | MCAP | BETRA00M2301 | Exempt | 2076596 | Smith, Kyle | West | 3. Active | Defined | West |  | 12699 |  | 12699 | 12699 | 0 | Green | 9000 |  | 9000 | 3699 |  |  | 12699 |  |  | 12699 | Full | 12699 |  | 12699 | 12699 | No | Green | 2023-06-01 | 2023-01-24 | 2023-01-24 | 2023-04-30 | 2023-03-31 | [13 empty] | 12699 | [7 empty] | 4/28/23 Working on new bids to complete dike around pump | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Indianapolis | BETRA - BET RACEWAY TERMINAL |  |  | 12699 |  |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 42944 |  | Guest, ProSight | Independent | Aqua | 2022-02-14 | Other Programs
Raceway Tank 203 Ethanol Substitution and Pipe Mods | Item | Open | MCAP | BETRA00M2201 | Maintenance Framework | 2002626 | Roth, Aaron | West | 3. Active | Drawdown | Tank Outage | 275 | 200000 |  | 200275.01 | 370208 | -169933 | Red | 370000 |  | 370000 | -169725 |  |  | 13000 | 36381 |  | 13000 | Phase | 49381 | 14040 | 200000 | 214040 | No | Green | 2022-08-01 | 2022-07-11 | 2022-07-11 | 2022-09-01 | 2023-05-31 |  |  | 63.5 | 64.64 | 80.17 | 66.7 |  |  | 67 | Red |  |  |  |  | 190000 |  |  | 10000 |  |  |  | 5.1 - install piping to tank 203 week of July 3. isolate & clean 202 week of July 10 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Indianapolis | BETRA - BET RACEWAY TERMINAL |  | 208 | 67 | 190000 | 10000 | 13765 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44071 |  | Guest, ProSight | Independent | Aqua | 2022-07-05 | Int - Tanks
Raceway Terminal (BETRA) Tank 202 - OOS API 653 + Seal Insp & Refurb | Item | Open | MEXP | BETRA00E2301 | Maintenance Framework | 2075934 | Roth, Aaron | West | 3. Active | Defined | Tanks | 19012 | 285000 |  | 304011.52 | 286425 | 17587 | Yellow | 285000 |  | 285000 | 19012 |  |  | 234300 |  |  | 234300 | Phase | 234300 | 19012 | 285000 | 304012 | No | Green | 2023-03-01 | 2023-01-20 | 2023-01-20 | 2023-12-31 | 2023-12-31 |  |  |  |  | 1425 | 17586.52 |  |  | 17587 | Red |  | WorkAhead of Schedule |  |  | 75000 | 155000 | 55000 |  |  |  |  | 5.1 - isolate & clean 202 week of July 10 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Indianapolis | BETRA - BET RACEWAY TERMINAL |  | 1425 | 17587 | 285000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44870 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Raceway Terminal (BETRA) Tank 203 - OOS API 653 + Seal Insp & Refurb | Item | Open | MEXP | BETRA00E2302 | Maintenance Framework | 2075933 | Roth, Aaron | West | 3. Active | Defined | Tanks | 30792 | 360000 |  | 390792.46 | 390792 | 0 | Green | 390000 |  | 390000 | 792 |  |  | 283690 |  |  | 283690 | Phase | 283690 | 30792 | 360000 | 390792 | No | Green | 2023-03-01 | 2023-01-20 | 2023-01-20 | 2023-12-31 | 2023-12-31 |  |  |  |  | 30792.46 | [9 empty] | 50000 |  | 75000 | 75000 | 125000 | 35000 |  | 5.1 - Substitute for 202 OOS. Clean 2x. Complete 653 while OOS. VAR: valves came in early | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Indianapolis | BETRA - BET RACEWAY TERMINAL |  | 30792 | 0 | 125000 | 235000 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44871 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Raceway Terminal (BETRA) Tank 403 - Jet Cleaning Inspection | Item | Open | MEXP | BETRA00E2303 | Maintenance Framework | 2076576 | Roth, Aaron | West | 6. Operational | Defined | Tanks | 92709 |  | 145000 | 92709.22 | 77920 | 14790 | Red | 203000 |  | 203000 | -110291 |  |  | 66000 |  |  | 66000 | Phase | 66000 | 92709 | 145000 | 237709 | No | Green | 2023-02-01 | 2023-01-20 | 2023-01-20 | 2023-12-31 | 2023-12-31 |  |  |  | 173.58 | 77746.09 | 14789.55 |  |  | 14790 | Red |  | Forecasting | [8 empty] | 145000 | 4.3 - done | 2023-04-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Indianapolis | BETRA - BET RACEWAY TERMINAL |  | 77920 | 14790 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44872 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Raceway Terminal Legacy 480VAC Electrical Upgrade | Item | Candidate | MCAP |  | Maintenance Framework |  | Hassan, Mohammad | West | 2. Pending AFE |  | Electrical |  | 100000 |  | 100000 | 100000 | 0 | Green | 100000 |  | 100000 | 0 | [9 empty] | 100000 | 100000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 50000 | 50000 | [5 empty] | 05-02-2023 - MNH - AFE development got delayed due to other project workload. Will work on submitting AFE this month. Project EAC still at $100K with forecast moved out a month. 03-31-2023 - MNH - AFE development got delayed due to other project workload. Will work on submitting AFE next month. Project EAC still at $100K with forecast moved out a month. 02-24-2023 - MNH - Met with Asset team and contractors last week. Utility company has 12 weeks lead time before they can start so moving project forecast out a month. EAC at $100K. 02-01-2023 - MNH - Scope development underway and site visit with contractors planned for this month. 01-03-2023 - MNH - Will start looking at scope of this month. 12-1-2022 - MNH - Will start looking at scope of work next month. | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Indianapolis | BETRA - BET RACEWAY TERMINAL |  |  | 0 | 100000 |  |  |  | Ashley, Robert | Wernsman, Jason T. |  |  | 1 | 45698 |  | Clark, David | Independent | Aqua | 2022-08-29 | Other Programs
RD401CB Control Valve and Operator Upgrade | Item | Open | MCAP | RD401CBM2201 | Maintenance Framework | 1980127 | Roknich, Hunter | West | 3. Active | Defined | Valves | 1148 | 15000 |  | 16148.2 | 15854 | 294 | Yellow |  |  |  | 16148 |  |  | 113000 |  |  | 113000 | Full | 113000 | 61834 | 15000 | 76834 | No | Green | 2022-10-01 | 2022-05-09 | 2022-05-09 | 2022-11-18 | 2023-09-30 |  |  | 279.39 | 284.98 | 290.1 | 293.73 |  |  | 294 | Red | [7 empty] | 15000 |  |  |  | 5/2/2023 - See below 3/31/2023 - See below 2/2/2023 - Operations wants to wait to install CV and actuator until relocation project in September. 1/4/2023 - Working with operations to schedule install. 12/2/2022 - Moving to Q1 CY+1 per operations request due to limited manpower to install valve. 11/2/2022 - Valve and actuator received. Working with REXA tech and operations to schedule install. Expecting early December time frame 10/3/2022 - Valve and actuator estimated ship mid/late October. Install in November. 9/2/2022 - Waiting for valve and actuator. 8/2/2022 - Estimated ship date October 7/5/2022 - Will schedule install when we know an official shipping date for valve and actuator 6/2/2022 - valve and actuator have been purchased. 5/3/22 - putting 20,000 in Sep for fabrication of piping mods to install new control valve, receipt of new valve/actuator in Oct, with installation to follow in Nov. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Pipelines | RD - HILLIARDS TERMINAL |  | 854 | 294 |  | 15000 | 60686 |  | Oey, Alex | Gardner, Travis W. | N/A |  | 1 | 22427 |  | Guest, ProSight | Independent | Aqua | 2017-01-19 | Other Programs
RELOCATE RECTIFIER BETFS | Item | Open | MEXP | BETFS00E2201 | Maintenance Framework | 2022785 | Brown, Jeff | West | 7. Closed | Drawdown | Cathodic Protection | -831 |  |  | -831.06 | -831 | 0 | Green |  |  |  | -831 |  |  | 8000 |  |  | 8000 | Full | 8000 | 6422 |  | 6422 | No | Green | 2022-10-01 | 2022-09-16 | 2022-09-16 | 2022-12-31 | 2022-11-30 |  |  | -831.06 | [18 empty] | 10-31-22 ACRUE WORK COMPLETED 10-3 WORK SCEDULED OCT-NOV | 2022-10-31 | Schultz, Amy |  | West | Pipelines and Terminals | Corrosion |  | Toledo | BETFS - BET FOSTORIA |  | -831 | 0 |  |  | 7253 |  | Geib, Rob | Shook, Mark B. | N/A |  | 1 | 45859 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-09-16 | Int - Planned Corr & FI
River Rouge 3R Filter Vessel Replacement | Item | Open | MCAP | BETHY00M2207 | Maintenance Framework | 2013807 | Roknich, Hunter | West | 6. Operational | Defined | Storm Water Management | -624 |  |  | -624.25 | -624 | 0 | Green |  |  |  | -624 |  |  | 20000 |  |  | 20000 | Full | 20000 | 18702 |  | 18702 | No | Green | 2022-09-01 | 2022-08-28 | 2022-08-28 | 2022-10-01 | 2022-11-30 |  |  | -0.25 | 0 | -624 | [16 empty] | 11/2/2022 - Work complete 10/3/2022 - Missed forecast due to material delays. Scheduled for October 24/25 8/2/2022 - AFE to be submitted 8/2. Work to begin late August | 2022-11-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  | -624 | 0 |  |  | 19326 |  | Bonenberger, Mark | Gardner, Travis W. |  |  | 1 | 40885 |  | Guest, ProSight | Independent | Aqua | 2021-08-01 | Other Programs
River Rouge BETHY Truck Rack ESD Upgrade Phase 2 | Item | Open | MCAP | BETHY00M2106 | Maintenance Framework | 1915286 | Hassan, Mohammad | West | 6. Operational | Unplanned | Truck Racks | 10073 |  |  | 10072.63 | 10073 | 0 | Green |  |  |  | 10073 |  |  | 83000 | 100000 |  | 183000 | Full | 183000 | 188528 |  | 188528 | No | Green | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2022-04-26 | 2022-11-04 |  |  | 9534.39 | 538.24 | [17 empty] | 05-02-2023 - MNH - Project closeout underway but delayed to other high priority items. 04-03-2023 - MNH - Project closeout underway but delayed to other high priority items. 03-01-2023 - MNH - Project closeout underway. 02-01-2023 - MNH - All work is complete. Will work on project closeout now. 01-03-2023 - MNH - Scully wiring work underway and will be compelted this month. Project EAC now at $187K to get this work done this month. 12-05-2022 - MNH - We found that scully wiring should be brought above ground and tied to ESD which will use project contingency. Updating project EAC to $183K to get this work done this month and next. 12-01-2022 - MNH - ESD commissioned. Working on some punch list items this month & next. $10K from December moved into January. Project EAC still at $166K. 11-03-2022 - MNH - ESD commissioning underway and now ahead of schedule. Contingency may not be needed. Project EAC now at $166K. 10-03-2022 - MNH - ESD construction on track now and a bit ahead. Still planning on commissioning ESD system next month. Project EAC still at $183K. 09-09-2022 - MNH - Just heard from the vendor that ESD button are delayed so our work will get pushed for about 4 week. Reducing September & October Forecast accordingly. 08-30-2022 - MNH - Phase 2 AFE complete for ESD construction work. Additional $100K funding for Phase 2 AFE will be sourced from West Region Drawdown. 08-01-2022 - MNH - A few revisions to IFB's caused delay in getting bid event started. Will work on bid event this week followed by Phase II AFE completion. Forecast pushed out a bit. 07-05-2022 - MNH - IFB drawings are complete and will work on getting bids from contractors this month. 06-01-2022 - MNH - IFB drawings to be completed in early June followed by getting bids from contractors. 04-29-2022 - MNH - ESD wiring troubleshooting with Techs & Contractor was completed this month and more work was done than expected. Reducing July and August forecast based on extra spends in April. 04-04-2022 - MNH - Will plan on doing some wiring troubleshooting with Techs & Contractor this month. 03-02-2022 - MNH - same update as last month. 01-28-2022 - MNH -BP refinery will be shutting down for a few month starting March so per Ops & Marketing we need to delay this project work until Q3 since it involves rack to be down. Ops date moved out as well. 01-27-2022 - MNH - Project design still getting completed and delayed due to Technicians availability. Also, Techs advised to delay any onsite work until spring. Moving Forecast out two months. 01-03-2022 - MNH - Initial design complete ahead of schedule. Will work on getting rest of design completed this month followed by some procurement. 12-01-2021 - MNH - Initial forecast entered. AFE under approval | 2023-05-02 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  | 10073 | 0 |  |  | 161313 |  | Younce, Michael | Ricke, Michael |  |  | 1 | 42496 |  | Meitzler, Antoinette | Independent | Aqua | 2021-11-23 | Other Programs
River Rouge Building Leak Repairs MEXP | Item | Open | MEXP | BETHY00E2208 | Exempt | 2023286 | Parker, Brian | West | 6. Operational | Defined | West | 77007 | 4000 |  | 81007 | 77000 | 4007 | Yellow |  |  |  | 81007 |  |  | 110000 |  |  | 110000 | Full | 110000 | 77007 | 4000 | 81007 | No | Green | 2023-03-01 | 2022-09-22 | 2022-09-22 | 2022-11-18 | 2023-04-25 |  |  |  |  | 15048 | 61959 | 30976 | 30976 | 30983 | Red |  | WorkAhead of Schedule | 4000 | [8 empty] | 4/30/23 - var is due to RAM Construction completing this work in Apr. May FCST is for final invoicing for damaged flashing replacement. EAC is at 88,337. 4/19/23 - looks like this work should be completed this week. There is a damaged flashing that has to be replaced after it has been fabricated that will be a week or two out to complete. 4/1/23 - Var is due to work starting early at request of operations. Accruing 13,998 for RAM Construction for Earned Valve to date. Work in on-going. EAC is 76,000. 3/27/23 - submitted CO#1 to Spencer to paint the entire exterior of the building based on what RAM Construction found when they started removing the CMU above the windows. Their total contract amount is now 75,975. Need to accrue 25% billing for Mar. 3/20/23 - RAM Construction started work today after scheduling with Dennis. 3/1/23 - confirmed that RAM has two individuals PIC 2.0 trained and sent email to local ops. Just need to pick a good time to start work once the weather breaks and starts to remain above 40 Deg F at night. 2/3/23 - RAM attended PIC 2.0 training at end of Jan so we just need to schedule the work once the weather breaks. 1/10/23 - sole source was approved and PO issued. RAM Construction is now an A in ISN. Sent LIVEsafe link to Robert with RAM to get his 2 supervisors PIC 2.0 training in Detroit area at end of Jan then we can get this work scheduled after the weather breaks. 1/3/23 - revised SSSP per Nick's comments - need to schedule this work once the weather breaks. 11/30/22 - received SSSP from RAM construction today and will review and send this to Nick Fennell for his approval. 11/8/22 - emailed Buckeye SSSP template back to RAM so they can fill out our template and need to schedule RAM personnel for PIC training and work through ISN Waiver. Confidence level in getting this work started before cold temps arrive is going down so moving this FCST out to 2023. If we can get everything completed for newvendor and temps are favorable we will try to get this completed in 2022. 10/31/22 - emailed HASP to Mike Sullivan and others for review on 10/24 and waiting on a reply back. Supply Chain was working through insurance issues and still waiting on a resolution (RAM does not need pollution insurance since SOW does not impact operations aroundpiping). 10/10/22 - received proposal from RAM for 55,992 on 10/6 - working to get them added as a Buckeye vendor. 9/28/22 - had Ram Construction reach out to me and will be on-site on the 29th for site visit to get a proposal from them. 9/19/22 - had to create a new MEXP project for this work since the original entry was setup under MCAP. Moved the FCST over this new MEXP project entry and cancelled the MCAP project in OPPM. All notes below were copied over from the original MCAP project.9/8/22 - sent out email to leadership to review this revised SOW and details. Checked with M+J and they can get it completed in 2022 and the waterproof coating can be applied down to 20 Deg F. 9/3/22 - talked with M+J to revise their original proposal to make lintel repairs where needed over 5 windows, replace the concreteblocks over the windows with the appropriate blocks and paint all of these blocks with an approved, waterproof coating that will address the permeability of the other concrete blocks. Just waiting on this revised proposal. 8/1/22 - I think the original mailingwas delivered to River Rouge instead of PM's office. Talked with M+J today and they shipping theiroriginal proposal to office overnight mail. 7/6/22 - moving this FCST out to Aug since I do not have proposal from M+J yet. 5/31/22 - waiting on proposal - provided mailing address to M+J so just waiting on documentation. 5/18/22 - had a conf call with Nick and John from M+J Industrial on 5/4 to review the SOW. Waiting on detailed SOW and cost estimate to see if we can break this out into 30' or 60' sections to replace in 2022 with maybe 90' sections annually. 4/10 - moved FCST out to Jun, still waiting ona proposal from Haley & Aldrich and M+J Industrial. Things are moving slow with this project. 4/1/22 - contractors will be on-site Apr 4th to look at this and provide a Phase I estimate to address the leaks in the break room first. | 2023-04-30 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  | 15048 | 65959 |  |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 45872 |  | Meitzler, Antoinette | Independent | Aqua | 2022-09-19 | Other Programs
River Rouge Butane Pressure Transmitter | Item | Candidate | MCAP |  | Exempt |  | Hassan, Mohammad | West | 2. Pending AFE |  | Instrumentation & Controls |  | 27000 |  | 27000 | 27000 | 0 | Green | 27000 |  | 27000 | 0 | [9 empty] | 27000 | 27000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 5000 | 22000 | [5 empty] | 05-02-2023 - MNH - Will have site visit in May now and develop SOW & submit AFE in May. 03-31-2023 - MNH - Will have site visit in April and develop SOW. 03-01-2023 - MNH - Site visit planned for next month with asset team lead. 02-01-2023 - MNH - Will start looking at scope of work this month. 01-03-2023 - MNH - Will start looking at scope of work in March. 12-1-2022 - MNH - Will start looking at scope of work in Q1 of 2023. | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  |  | 0 | 27000 |  |  |  | Forsey, Frank |  |  |  | 1 | 44513 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Other Programs
River Rouge Drainage System Survey | Item | Open | MCAP | BETHY00M2206 | Maintenance Framework | 2012391 | Henfling, Mike | West | 3. Active | Defined | Storm Water Management | 7092 |  | 0 | 7091.82 | 6944 | 148 | Yellow |  |  |  | 7092 |  |  | 30000 |  |  | 30000 | Phase | 30000 | 31082 | 0 | 31082 | No | Green | 2022-08-01 | 2022-08-15 | 2022-08-15 | 2023-05-31 | 2023-06-30 |  |  | 3974.96 | 1749.25 | 1219.95 | 147.66 |  |  | 148 | Red | [10 empty] | 0 | 5-2-23 - Awaiting budgetary pricing for possible pull-in project in 2023. IFB drawings are ready for this project. 4-4-23 - Plan to request budgetary pricing for work in April, for possible pull-in project in 2023. IFB drawings are ready for this project. 2-2-23 - IFB drawings completed early January. Plan to request budgetary pricing for work and submit estimate to Markella for possible pull-in to 2023. 1-3-23 - IFB drawings to be complete by 1/6. Plan to request pricing for work and request funding later in 2023. work includes drainage upgrades, catch basins and sump pumps/piping/insulation to connect to 3R system. 12-5-22 - Design Review completed 12/2. Plan to revise drawings to Issue for Bid in December and get quotes in January. 11-2-22 - Second engineering site visit mid-October, drawings are nearly complete. Design review planned prior to year-end hopefully November. 10-3-22 - Working on engineering. Site visit held 9-13 and 9-14 to gather more information. Drawings planned to be complete by end of October for review. 9-1-22 - AFE approved. Initial drawings to be complete by end of September, and site visit late September/early October to verify. 8-1-22 - AFE in progress. Engineering late-Summer and Fall. 7-5-22 - AFE planned to be submitted in July. Engineering late-Summer and Fall. Pushed forecast one month 6-2-22 - AFE planned to be submitted in June. Engineering late-Summer and Fall. 5-4-22 - Site visit completed 4/19. Gathering information prior to full engineering. AFE planned to be submitted in May 4-4-22 - April scoping site visit planned. Will update forecast after site visit 3-2-22 - Discussions on preliminary scope with site operations has begun. Site survey sometime in April once weather warms. 2-2-22 - Shifted forecast slightly. Will likely begin engineering survey in April after winter | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  | 6944 | 148 |  |  | 23990 |  | Bonenberger, Mark | Gardner, Travis W. | N/A |  | 1 | 21635 |  | Gardner, Travis | Independent | Aqua | 2016-09-16 | Other Programs
River Rouge Fire Hydrant Repairs. | Item | Open | MEXP | BETHY00E2209 | Maintenance Framework | 2043706 | Bost, Jason | West | 6. Operational | Defined | Fire Protection | 1630 |  |  | 1630.35 | 1630 | 0 | Green |  |  |  | 1630 |  |  | 140000 |  |  | 140000 | Full | 140000 | 133662 |  | 133662 | No | Green | 2022-12-01 | 2022-11-09 | 2022-11-09 | 2022-12-31 | 2022-12-31 |  |  | 1630.35 | [18 empty] | 1/31/23 - Variance is Vanguard invoice for testing hydrants. 1/4/23 - Work completed on 12/16 with test reports received by Vanguard. Accrual is for Holly ($130,345) and vanguard ($1,687). 12/5/22 - Decision was made to repair/replace all listed hydrants. Increased Dec. forecast to reflect approved AFE. Holly to break ground on 12/5. 11/1/22 - 3 high priority replacements were highlighted by Vanguard. Reviewing the scope/cost to replace all hydrants this year. 10/1/22 - Testing complete. 5 hydrants will need repaired/replaced according to the test report. Acquiring a second quote due to the scope of work. 9/1/22 - Test scheduled for Sept. 7, repairs to be made based on test results. 8/1/22 - No Change. 7/5/22 - Testing hydrants scheduled in Sept. Once tested, necessary repairs will be completed. 6/1/22 - No change. 5/3/22 - No Change. 4/4/22 - No Change. 3/2/22 - No Change 2/2/22 - No Change 1/3/22 - No Change | 2023-02-01 | Griest, Barbara |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  | 1630 | 0 |  |  | 132032 |  | Jakubowski, Gregory | Jakubowski, Greg |  |  | 1 | 41681 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
River Rouge install proportional TSV's | Item | Candidate | MCAP |  | Maintenance Framework |  | Skelly, Mark | West | 2. Pending AFE |  | Pressure Vessels |  | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 | [9 empty] | 30000 | 30000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 30000 | [10 empty] | West | Pipelines and Terminals | Integrity |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  |  | 0 | 30000 |  |  |  | Stine, Carlton |  |  |  | 1 | 42247 |  | Guest, ProSight | Independent | Aqua | 2021-10-04 | Int - Tanks
River Rouge Replace Foam Fire Protection System | Item | Open | MCAP |  | Exempt |  | Bost, Jason | West | 2. Pending AFE |  | Fire Protection |  | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 | [9 empty] | 30000 | 30000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 10000 | 20000 | [5 empty] | 5/1/23 - Site visit scheduled late May. 4/3/23 - No Change . 3/1/23 - Scheduling scope walkdown in March. 1/31/23 - No Change | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  |  | 0 | 30000 |  |  |  | Jakubowski, Gregory |  |  |  | 1 | 45526 |  | Administrator, System | Independent | Aqua | 2022-08-29 | Other Programs
River Rouge Stormwater Separation Project from 3R System | Item | Open | MCAP | BETHY00M2205 | Maintenance Framework | 2012378 | Henfling, Mike | West | 3. Active | Defined | Storm Water Management | 7082 |  | 0 | 7082.18 | 5712 | 1370 | Red |  |  |  | 7082 |  |  | 35000 |  |  | 35000 | Phase | 35000 | 33297 | 0 | 33297 | No | Green | 2022-08-01 | 2022-08-15 | 2022-08-15 | 2023-05-31 | 2023-06-30 |  |  | 3795.88 | 284.33 | 1631.67 | 1370.3 |  |  | 1370 | Red | [10 empty] | 0 | 5-2-23 - CR-RCAP AFE still in process. RCAP steering committee review planned for week of 5/8. All costs from this project to be re-classified to RCAP project in May/June once RCAP funding is approved. Likely jumper install in June or July. 4-4-23 - CR-RCAP AFE in process. All costs from this project to be re-classified to RCAP project in April/May once RCAP funding is approved. Likely jumper install in May. 3-2-23 - RCAP AFE in process of being submitted. All costs from this project to be re-classified to RCAP project in April. Install in April/May. 2-2-23 - IFB drawings completed early January. Received 2nd mechanical quote 2/1 and plan to submit RCAP AFE in February. to complete by end of Q2 2023. Did not forecast cost onto this MCAP project due to RCAP plan. 1-3-23 - IFB drawings to be complete by 1/6. Plan to get firm quotes for jumper work for stormwater to bypass 3R system and complete it by end of Q2 2023. Will submit an RCAP project in February due to economics savings of installing jumper. Did not forecast cost onto this MCAP project due to RCAP plan. 12-5-22 - Design review completed 12/2, plan to complete Issue for Bid drawings in December. Will bid out work and submit for an RCAP project for the jumper-only in 2023. 11-2-22 - Second engineering site visit mid-October, drawings are nearly complete. Design review planned prior to year-end hopefully November. 10-3-22 - Working on engineering. Site visit held 9-13 and 9-14 to gather more information. Drawings planned to be complete by end of October for review. 9-1-22 - AFE approved. Initial drawings to be complete by end of September, and site visit late September/early October to verify. 8-1-22 - AFE in progress. Engineering late-Summer and Fall. 7-5-22 - AFE planned to be submitted in July. Engineering late-Summer and Fall. Pushed forecast one month 6-2-22 - AFE planned to be submitted in June. Engineering late-Summer and Fall. 5-4-22 - Site visit completed 4/19. Gathering information prior to full engineering. AFE planned to be submitted in May 4-4-22 - April scoping site visit planned. Will update forecast after site visit 3-2-22 - Discussions on preliminary scope with site operations has begun. Site survey sometime in April once weather warms. 2-2-22 - Shifted forecast slightly. Will likely begin engineering survey in April after winter | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  | 5712 | 1370 |  |  | 26215 |  | Bonenberger, Mark | Gardner, Travis W. |  |  | 1 | 37720 |  | Guest, ProSight | Independent | Aqua | 2020-08-12 | Other Programs
River Rouge Terminal (BETHY) Vessel 117 - API 510 Inspection and PSM Refurbishments | Item | Open | MEXP | BETHY00E2301 | Maintenance Framework | 2077113 | Arch, Stefan | West | 3. Active | Defined | Pressure Vessels |  | 165000 |  | 165000 | 165000 | 0 | Green | 160000 |  | 160000 | 5000 |  |  | 163017 |  |  | 163017 | Phase | 163017 |  | 165000 | 165000 | No | Green | 2023-06-01 | 2023-01-30 | 2023-01-30 | 2023-12-31 | 2023-07-31 | [13 empty] | 65000 | 100000 | [6 empty] | 5/1/2023 - No update for this month, same schedule and forecasting. 4/3/2023 - No update for this month, same schedule and forecasting. 3/1/2023 - Walked down tank with Operations on 2/21. Discussing PVCU checklist with air compliance and Butane blending. Planning to begin in June when product is removed. 2/1/2023 - Project to complete internal API 510 inspection and move fill nozzle to the liquid side of the tank. Working with vapor group to use PVCU for blowdown and purge. Planning to complete in summer, after all Butane is pulled out. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Wayne Terminals | BETHY - BET RIVER ROUGE |  |  | 65000 | 100000 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44750 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Rockford Terminal #6 Pump Refurb and Motor Replacement | Item | Open | MCAP | BETRK00M2301 | Maintenance Framework | 2085325 | Parker, Brian | West | 3. Active | Defined | Rotating Equipment |  | 60000 |  | 60000 | 50000 | 10000 | Red |  | 61188 | 61188 | -1188 |  |  | 61188 |  |  | 61188 | Full | 61188 |  | 60000 | 60000 | No | Green | 2023-05-01 | 2023-03-27 | 2023-03-27 | 2023-05-31 | 2023-07-31 | [12 empty] | 54000 | 6000 | [7 empty] | 5/6/23 - plan on pulling the pump/motor on May 11th or 12th then will be install the following week around May 17th or 18th. Have PO's issued to Midwestern and Feken to assist with install. 4/7/23 - still waiting on all parts for pump to arrive before scheduling this outage. Furey just received the seals and still waiting on the shaft sleeves - might have these in about 2 weeks. EAC is 50,000. 3/20/23 - submitted Full AFE for approval routing. 3/1/23 - PO issued to Furey on 2/27 - they will advise when material has arrived so we can schedule the 1 week downtime to refurbish this pump and install the new motor. Adjusted FCST to what I expect to spend. 2/23/23 - entered req. for Furey to pre-purchase pump parts and order new motor. 2/14/23 - submitting Interim AFE today to get PO issued to Furey so they can start procuring long lead material. | 2023-05-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | West Shore Terminals | BETRK - BET ROCKFORD TERMINAL |  |  | 60000 |  |  |  |  | Posipanko, Dan | Gardner, Travis W. |  |  | 1 | 46592 |  | Parker, Brian | Independent | Aqua | 2023-02-14
Rockford Terminal Baseline Facility Assessment | Item | Open | MEXP | BETRK00E2202 | Maintenance Framework | 1980270 | Stalbaum, Cameron | West | 6. Operational | Defined | Facility Integrity | -4879 |  |  | -4878.74 | -4879 | 0 | Green |  |  |  | -4879 |  |  | 36000 |  |  | 36000 | Phase | 36000 | 8398 |  | 8398 | No | Green | 2022-11-01 | 2022-05-11 | 2022-05-11 | 2022-12-31 | 2022-12-31 |  |  | -4878.74 | [18 empty] | 2/2/23 - Overall savings from the T&M cost estimate that was submitted from Elaine vs what I was forecasting. 1/3/23 - Accrual for Lake Superior. 12/2/22 - Lake Superior is scheduled to start work on 12/5/22 per Elaine Aiken. 11/8/22 - received proposal from program owner and will get req entered into JDE for work - adjusted FCST. 10/3/22 - Still waiting to hear back from Elaine on what we are doing with this assesment 9/5/22 - Waiting on Elaine to get back with me on when this inspection work is being scheduled. Have spoke with Brian Parker and there are other project that are in the same issue waiting on Elaine. 8/2/22 - Waiting on response from Elaine on when this work will be starting. 7/5/22 - After discussing with Brian Parker and the uncertainty from Elaine on when a vendor will be selected for the inspections, I am pushing the forecast out to October. | 2023-02-02 | Griest, Barbara |  | West | Pipelines and Terminals | Station/Terminal |  | West Shore Terminals | BETRK - BET ROCKFORD TERMINAL |  | -4879 | 0 |  |  | 13277 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 41201 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
Rockford terminal main office gutter replacement | Item | Candidate | MEXP |  | Exempt |  | Stalbaum, Cameron | West | 5. Deferred |  | West |  | 0 |  | 0 | 10000 | -10000 | Red | 10000 |  | 10000 | -10000 | [9 empty] | 15000 | 15000 | No | Green | 2024-07-01 |  |  |  | 2023-06-30 | [13 empty] | 0 | [7 empty] | 4/20/23 - Pushing this project to 2023 for budgeting and funding purposes. Quotes came back in significantly higher than what was originally budgeted. Moving to 2024 and adding 10% for escalation from what was quoted. 4/3/23 - Waiting on second quote back from Gluth Brothers. 1/26/23 - changed PM from Brian Parker to Cameron Stalbaum and moved FCST from Mar to Jun. | 2023-04-20 |  |  | West | Pipelines and Terminals | Station/Terminal |  | West Shore Terminals | BETRK - BET ROCKFORD TERMINAL |  |  | 0 |  |  |  | 15000 | Gardner, Travis |  |  |  | 1 | 41761 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Rockford terminal server building gutter replacment | Item | Candidate | MEXP |  | Exempt |  | Stalbaum, Cameron | West | 5. Deferred |  | West |  | 0 |  | 0 | 8000 | -8000 | Red | 8000 |  | 8000 | -8000 | [9 empty] | 18000 | 18000 | No | Green | 2024-07-01 |  |  |  | 2023-05-31 | [12 empty] | 0 | 0 | [7 empty] | 4/20/23 - Moving forecast to 2024 due to budgeting. Project quotes for this project came back in double expected amount. This project has been moved to 2024 and 10% added to the quote that was submitted on 4/10/23 to account for escalation. 4/3/23 - Waiting for a second quote back from Gluth Brothers. | 2023-04-20 |  |  | West | Pipelines and Terminals | Station/Terminal |  | West Shore Terminals | BETRK - BET ROCKFORD TERMINAL |  |  | 0 |  |  |  | 18000 | Gardner, Travis |  |  |  | 1 | 41740 |  | Guest, ProSight | Independent | Aqua | 2021-08-20 | Other Programs
Rockford terminal storm water drainage | Item | Candidate | MCAP |  | Maintenance Framework |  | Stalbaum, Cameron | West | 2. Pending AFE |  | Storm Water Management |  | 45000 |  | 45000 | 45000 | 0 | Green | 45000 |  | 45000 | 0 | [9 empty] | 90000 | 90000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 45000 | [6 empty] | 5/1/23 - Working with the asset team to fully develop a scope for this project. This was mainly submitted as a ditch cleaning project, however I think there is more issues that need to be resolved prior to cleaning the ditch/in conjunction with the ditch work. 4/3/23 - Will be working on scope document and working with asset team to figure this project out. I believe the flooding issue might have been caused by a 500year rain storm so we need to right size this project. | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | West Shore Terminals | BETRK - BET ROCKFORD TERMINAL |  |  | 0 | 45000 |  |  |  | Bonenberger, Mark |  |  |  | 1 | 45419 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Other Programs
Rockford Terminal Tank Line Relocation | Item | Open | MCAP | BETRK00M2302 | Maintenance Framework | 2095899 | Stalbaum, Cameron | West | 3. Active | Pending AFE | Facility Integrity | 14000 | 151000 |  | 165000 | 165000 | 0 | Green | 165000 |  | 165000 | 0 |  |  | 28934 |  |  | 28934 | Phase | 28934 | 14000 | 151000 | 165000 | No | Green | 2023-04-01 | 2023-03-23 | 2023-03-23 | 2023-08-01 | 2023-09-30 | [5 empty] | 14000 | 14000 | 14000 | 0 | Green |  |  | 14000 | 37000 | 100000 | 0 | 0 |  |  |  |  | 5/1/23 - Have the first plan sheets completed and working on setting up a review meeting with the asset team. Once we have the review completed we will have a bid event meeting mid may. 3/31/23 - Phase 1 afe was just approved mid March. Forecast updated to reflect engineering being completed in April, followed by Final Scope/Bid event early May. Construction to start June/July. 6/9/20 - at request of PMO deferring this project to 2021 to reduce 2020 overall MCAP. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | West Shore Terminals | BETRK - BET ROCKFORD TERMINAL |  |  | 65000 | 100000 |  |  |  | Aiken, Elaine | Aiken, Elaine | N/A |  | 1 | 30588 |  | Guest, ProSight | Independent | Aqua | 2018-08-15 | Int - Planned Corr & FI
Rockford Truck Rack MultiLoad Upgrade | Item | Open | MCAP | BETAK00M2204 | Maintenance Framework | 1956946 | Grinder, Mark | West | 6. Operational | Defined | Truck Racks | -37297 |  |  | -37297.33 | -37297 | 0 | Green |  |  |  | -37297 |  |  | 34000 | 395000 |  | 429000 | Phase | 429000 | 0 |  | 0 | No | Green | 2022-04-01 | 2022-03-24 | 2022-03-24 | 2022-10-30 | 2022-12-31 |  |  | -37297.33 | [18 empty] | 4-27-2023 - This project has been completed. 3-23-2023 - This project is completed. 3-01-2023 - This project has been completed and processing final invoices. 2/28/2023 Variance is due to the numbers not being correct in OPPM or COGNOS January 2023. Reclass was submitted and was later posted to January. The reclass was never reflected in COGNOS or OPPM until after the end of the month process. Assumption was that relcass would not post in January but in February that is why it was forecasted. 1-31-2022 - This project has been completed and waiting for final invoices. COGNOS balance different than OPPM. OPPM issue to be fixed 1/5/2023 - This project was reclassed it was originally set up with the wrong business unit BETAK00M2204 and the actual business unit is BETRK00M2203 that’s why you are showing a large variance.12-27-2022 - This has been completed, Red-line drawings have been sent to Triad to complete As-Builts and Equipment Tags have been ordered submitted Equipment List to Lisa. 11-28-2022 - This project was completed last week and working on Equipment Tags and List Triad will be 5K under full PO and Special Power will be at the full PO.amount.. 11-01-2022 - Variance is for unused contingancy. Bay 3 was just commissioned and starting Bay 2. We should be completed in Mid November. 9-26-2022 - Bay 1 is being commissioned on the week of October 3rd and then we will start on Bay 3, then we will complete Bay 2. We should be completed in late October. 8-29-2022 - This project will be starting in Mid-September, and will be completed by the end of October. 7-27-2022 - Bid awarded last week to electrical contractor and am moving 20K into October because of delays. I am still waiting on bids for additive injector tubing work for final project cost, supposed to be received by August 12th. 7/1/22 Moved 50K forecast to October. Delay in getting bid documents. Currently out for bid, events ends second week of July. 6-21-2022 - IFB drawings were just received and will schedule a bid event asap,the FCM modules were located, they were delivered to Triad for panel build.5-31-2022 - Drawings were just received and will schedule a bid event in the next week, The Multiloads were received last week but the FCM Modules have not been shipped yet. 5-02-2022 - Triad drawings will be completed for bid event by mid May, waiting for quote from Top Tech and Bid event should be completed at the end of May. 4-01-2022 - Triad is working on the engineering portion of thisproject and drawings should be available for bidding next month. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | West Shore Terminals | BETRK - BET ROCKFORD TERMINAL |  | -37297 | 0 |  |  | 37297 |  | Younce, Michael | Koranda, Chad E. |  |  | 1 | 34590 |  | Guest, ProSight | Independent | Aqua | 2019-08-27 | Other Programs
Rockford Truck Rack MultiLoad Upgrade - Phase II | Item | Open | MCAP | BETRK00M2203 | Maintenance Framework | 1956946 | Grinder, Mark | West | 6. Operational | Defined | Truck Racks | 62685 |  |  | 62684.92 | 62420 | 265 | Yellow |  |  |  | 62685 |  |  | 35000 | 394000 |  | 429000 | Full | 429000 | 440175 |  | 440175 | No | Green | 2022-10-01 | 2022-10-03 | 2022-10-03 | 2022-10-30 | 2022-12-31 |  |  | 54214.04 | 2326.95 | 5879.37 | 264.56 |  |  | 265 | Red | [11 empty] | 4-27-2023 - This project has been completed. 3-23--2023 - This project has been completed. 3-01--2023 - This project has been completed. 2/28/2023 Variance is due to the numbers not being correct in OPPM or COGNOS January 2023. Reclass was submitted and was later posted to January. The reclass was never reflected in COGNOS or OPPM until after the end of the month process. Assumption was that relcass would not post in January but in February that is why it was forecasted 1-31-2023 - This project has been completed. 12-27-2022 - This has been completed, Red-line drawings have been sent to Triad to complete As-Builts and Equipment Tags have been ordered submitted Equipment List to Lisa. 11-28-2022 - This project was completed last week and working on Equipment Tags and List. 11-01-2022 - Bay 3 was just commissioned and starting Bay 2. We should be completed in late Mid November. 10-07-2022 - Bay 1 is being completed this week and released next Monday, we are also starting Bay 3 next Monday. | 2023-04-27 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | West Shore Terminals | BETRK - BET ROCKFORD TERMINAL |  | 62420 | 265 |  |  | 377491 |  | Younce, Michael | Koranda, Chad E. |  |  | 1 | 45920 |  | Meitzler, Antoinette | Independent | Aqua | 2022-09-27 | Other Programs
Rt 51 Block Valve interface refurbishment | Item | Open | MCAP | HT160DQM2301 | Exempt | 2093338 | Gabriel, Jeff | West | 3. Active | Defined | Atmospheric Corrosion |  | 6000 |  | 6000 | 6000 | 0 | Green | 6000 | 5886 | 11886 | -5886 |  |  | 11886 |  |  | 11886 | Full | 11886 |  | 6000 | 6000 | No | Green | 2023-08-01 | 2023-03-02 | 2023-03-02 | 2023-07-30 | 2023-06-30 | [15 empty] | 6000 | [5 empty] | 5/1/2023- NO Change 4/3/2023- Awarded to CPM. Moved forecast to August to be completed the same time as the Span project. 3/2/2023- AFE is complete and is being routed for approval | 2023-05-01 | IT |  | West | Pipelines and Terminals | Integrity |  | Central-Illinois | HT160DQ - HARRISTOWN JCT TO DEWITT |  |  | 0 | 6000 |  |  |  | Geib, Rob |  |  |  | 1 | 44489 |  | Guest, ProSight | Independent | Aqua | 2022-08-09 | Int - Planned Corr & FI
Sauget Station Electrical Building Install | Item | Open | MCAP | SG00000M2201 | Maintenance Framework | 2037419 | Scannell, Adam | West | 3. Active | Defined | Electrical | 4137 |  |  | 4136.93 | 1741 | 2396 | Red |  |  |  | 4137 |  |  | 45000 |  |  | 45000 | Full | 45000 | 42046 |  | 42046 | No | Green | 2022-10-01 | 2022-10-19 | 2022-10-19 | 2022-12-31 | 2023-05-31 |  |  | 1518.26 | 108.55 | 113.85 | 2396.27 |  |  | 2396 | Red | [11 empty] | 05/02/23 - Waiting on line downtime 5/4 to tie in electrical. 03/25/23 - GRP delivering building and starting conduit the week of 3/27. 03/02/23 - Working with techs for tie in. 02/02/23 - All work complete except tie in by technicians 01/04/23 - All work complete except tie in by technicians. 12/05/22 - Crew did not all have current TWIC cards. Had to get a renewal. Cards are current now and work being scheduled to start in the next week. 11/02/22 - Pad to be poured in November and building set at end of the month. 07/22/22 - Waiting on bid to install piers and anchors. AFE to be submitted in early August. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | St. Louis | SG - SAUGET TERMINAL (CONOCO PHILIP) |  | 1741 | 2396 |  |  | 37909 |  | Ashley, Robert | Ashley, Robert | N/A |  | 1 | 30143 |  | Guest, ProSight | Independent | Aqua | 2018-07-30 | Other Programs
Si160BP Rectifier Pole Replacement | Item | Open | MCAP | SI160BPM2301 | Exempt | 2093573 | Gabriel, Jeff | West | 6. Operational | Defined | Cathodic Protection | 14265 |  |  | 14265.31 | 13670 | 595 | Yellow | 7000 |  | 7000 | 7265 |  |  | 12933 |  |  | 12933 | Full | 12933 | 14265 |  | 14265 | Yes | Red | 2023-03-01 | 2023-03-03 | 2023-03-03 | 2023-07-30 | 2023-03-21 |  |  |  |  | 13670.15 | 595.16 |  |  | 595 | Red | [11 empty] | 4/3/2023- Work complete ahead of schedule. Additional labor charges to be reclassed to another project that was worked on. 3/2/2023- AFE is complete and is being routed for approval | 2023-04-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Central-Illinois | SI - SIBLEY STATION |  | 13670 | 595 |  |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44168 |  | Guest, ProSight | Independent | Aqua | 2022-07-18 | Int - Planned Corr & FI
Si160BP Test Station and Vent Upgrade | Item | Open | MCAP | SI160BPM2201 | Exempt | 2004023 | Gabriel, Jeff | West | 7. Closed | Defined | Cathodic Protection | 1006 |  |  | 1006.41 | 1006 | 0 | Green |  |  |  | 1006 |  |  | 35000 |  | 8000 | 43000 | Full | 43000 | 26761 |  | 26761 | No | Green | 2022-10-01 | 2022-07-25 | 2022-07-25 | 2022-12-31 | 2022-10-30 |  |  | 736.29 | 270.12 | [17 empty] | 1/3/2023- work complete need to Accrue 8,000 for P-card purchase 12/2/2022- Work complete need to accrue 17,820 NIS & 6000 need to move 10,000 to December for material Accrued 8,000 on wrong project should have been DQ160SIM2203 11/1/2022- PO will be issued this week NIS is completing the work. 10/4/2022- moved forecast to November waiting on NIS to be set up in JDE to receive PO's 9/1/2022- project will be completed by NIS. On Schedule 8/3/2022- Schedulde to start in October | 2023-01-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Central-Illinois | SI160BP - SIBLEY TO BRADELY |  | 1006 | 0 |  |  | 25755 |  | Geib, Rob | Geib, Robert |  |  | 1 | 40848 |  | Guest, ProSight | Independent | Aqua | 2021-07-29 | Other Programs
South Bend Terminal Idlement | Item | Open | MEXP | BETSB00E2201 | Maintenance Framework | 1980331 | Parker, Brian | West | 7. Closed | Drawdown | West | 785 |  |  | 785.11 | 785 | 0 | Green |  |  |  | 785 |  |  | 39000 | 535000 |  | 574000 | Full | 574000 | 488529 |  | 488529 | No | Green | 2022-05-01 | 2022-05-12 | 2022-05-12 | 2022-08-31 | 2022-09-01 |  |  |  |  | 785.11 | [16 empty] | 1/2/23 - processed final invoice from TAS in Dec and one Envirospec Engineering invoice. Will leave this open until end of Jan then start the closeout process. 12/2/22 - var is due to Consolidated's cost coming in under the original proposal amount. A portion of the original cost was T&M (36%) and we only spent a portion of the T&M costs. Ready to close out project after confirmation of receipt of as-builts by Eng & Design. 10/29/22 - still waiting on final invoicing from TAS and Consolidated. Re-accruing 13,562.50 for TAS and 46,264.98 for Consolidated. 10/1/22 - Var is due to more WM charges than planned, unplanned transport charges for product to Niles, and additional costs from GFL for extra work for Sep. Re-accruing 13,562.50 for TAS and 53,753.50 for Consolidated. 9/1/22 - Var is due to all work being completed in Aug. Accruing 8,000 for PPS (inspection), 13,562.50 for TAS, 125,238.86 for GFL, and 131,503.50 for Consolidated. Have P-Card charges totaling 3,055 posting in Sep plus some additional charges for Consolidated and GFL (est. at 10% of original PO issued amount). 8/5/22 - var is due to purge issues on 150L that pushed the mechanical work start date back 8 days and delay in stockholder decision on where they want the ULSD that did not make it to the RR. Re-accruing 29,062.50 for TAS, accruing 8,250 for Inserv, 6,000 for Pugh Pipeline, and 78,000 for GFL. 7/25/22 - issued MOC 2003982 for terminal piping idlement - tank cleaning started on 7/20 and Consolidated will start work on 8/01 due to delay/issues with 150L purge. 7/3/22 - completed review of idling plan and going out for bid now. Work scheduled to start on Jul 18th and be wrapped up around Sep 23rd. Will update FCST once bids have been completed and have Phase II AFE submitted. Accruing open PO amount of 29,062.50 for TAS. 6/9/22 - adding "best guess" for FCST to OPPM as a place holder until bidding and other costs can be identified. 5/31/22 - May var is due to AFE approval after FCST cutoff date, have a review of idlement plan scheduled for Jun 1st with TAS and local ops. 5/18/22 - AFE approved after FCST cutoff date. There should be ~ $9,688 invoiced in May with remaining amount invoiced in Jun. Just had to put the full amount in Jun for now. 5/12/22 - entered Req for Eng & Design, POwas issued same day, idlement plan should be ready for review around mid-Jun. 5/11/22 - entered drawdown request into OPPM - should get PO issued in May with 25% payment due upon PO issuance and remaining work will be billed as progressive payments with completionin about 4 weeks. | 2023-01-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Michiana | BETSB - BET SOUTH BEND TERMINAL |  | 785 | 0 |  |  | 487744 |  | Gardner, Travis | Ricke, Michael | N/A |  | 1 | 43713 |  | Parker, Brian | JDE Child | Burnt Orange | 2022-05-11 | Other Programs
South St. Louis (BETSS) facility Gate Repairs | Item | Open | MEXP | BETSS00E2206 | Maintenance Framework | 2013321 | Scannell, Adam | West | 6. Operational | Drawdown | West | 0 |  |  | 0.22 | 0 | 0 | Green |  |  |  | 0 |  |  | 9800 |  |  | 9800 | Full | 9800 | 9862 |  | 9862 | No | Green | 2022-11-01 | 2022-08-25 | 2022-08-25 | 2022-09-30 | 2022-11-30 |  |  | 0.22 | [18 empty] | 11/17/22 - Work completed 0n 11/09/22. Waiting on invoice. 11/02/22 - Local ops will be scheduling completion this month. 10/04/22 - PO issued and working with contractor on available start date. Forecast moved out to November. Variance is due to error in forecasting the start date for this emergent work. 09/22/22 - Project budget approved. Working with local asset team to schedule work completion. | 2022-11-17 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | St. Louis | BETSS - BET ST LOUIS SOUTH TERMINAL |  | 0 | 0 |  |  | 9862 |  | Gardner, Travis | Gardner, Travis W. | N/A |  | 1 | 45263 |  | Gardner, Travis | JDE Child | Burnt Orange | 2022-08-25 | Other Programs
St Charles (BSEVO) Tank 1224 - In-service AIFR Inspection | Item | Open | MEXP | BSEVO00E2301 | Maintenance Framework | 2084793 | Roth, Aaron | West | 3. Active | Defined | Tanks |  | 28000 |  | 28000 | 155000 | -127000 | Red | 155000 |  | 155000 | -127000 |  |  | 19367 |  |  | 19367 | Phase | 19367 |  | 28000 | 28000 | No | Green | 2023-05-01 | 2023-02-14 | 2023-02-14 | 2023-12-31 | 2023-12-31 | [12 empty] | 28000 | [8 empty] | 5.1 - perform in-service inspection on 5/30 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | St. Louis | BSEVO - ST CHARLES TERMINAL |  |  | 28000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44881 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
St Charles (BSEVO) Tank 310 - OOS Internal | Item | Open | MCAP | BSEVO00M2302 | Maintenance Framework | 2084427 | Roth, Aaron | West | 3. Active | Defined | Tanks |  | 102417 |  | 102417 | 102417 | 0 | Green | 102417 |  | 102417 | 0 |  |  | 279804 |  |  | 279804 | Phase | 279804 |  | 102417 | 102417 | No | Green | 2023-10-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-11-30 | [17 empty] | 52417 | 50000 |  |  | 5.1 - do in Q4 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | St. Louis | BSEVO - ST CHARLES TERMINAL |  |  | 0 |  | 102417 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44882 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
St Charles (BSEVO) Tank 6020 - OOS Internal | Item | Open | MCAP | BSEVO00M2301 | Maintenance Framework | 2084424 | Roth, Aaron | West | 3. Active | Defined | Tanks | 1600 | 232553 |  | 234153 | 234153 | 0 | Green | 232553 |  | 232553 | 1600 |  |  | 267237 |  |  | 267237 | Phase | 267237 | 1600 | 232553 | 234153 | No | Green | 2023-03-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-08-31 |  |  |  |  | 1600 | [11 empty] | 32553 | 100000 | 100000 |  |  | 5.1 - do in Q4 | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | St. Louis | BSEVO - ST CHARLES TERMINAL |  | 1600 | 0 | 32553 | 200000 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44880 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
St Charles Tank 6021 Pump | Item | Open | MCAP | BSEVO00M2203 | Maintenance Framework | 2023402 | Scannell, Adam | West | 3. Active | Drawdown | Rotating Equipment | 86999 |  |  | 86999.24 | 65303 | 21696 | Red |  |  |  | 86999 |  |  | 70000 |  |  | 70000 | Full | 70000 | 138620 |  | 138620 | Yes | Red | 2022-12-01 | 2022-09-23 | 2022-09-23 | 2022-12-31 | 2023-05-31 |  |  | 3814.44 | 1114.26 | 60374.55 | 21695.99 |  |  | 21696 | Red |  | Forecasting | [9 empty] | 05/02/23 - Asset team planning to install the strainer this week. Variance is due to forecasting and accrual discrepancy, and a charge from another project being miscoded to this project. A reclass is being submitted for $9,800. 03/25/23 - Fabrication and hydrotest complete. Waiting on strainer to install and commission. Expect the strainer to arrive by the end of the first week of April. 03/02/23 - Pipe fabrication to be completed the week of March 13th. 01/04/23 - Pump base is complete. Just need to complete pipe modifications. Pipe modification required more than originally anticipated with new pump location. 12/07/22 - Drawing package is complete. Scheduling the installation. Pump is being delivered this week. 11/02/22 - Getting drawings made for pump pad and pipe modifications. Plan to have pad poured by end of Nov. 10/04/22 - AFE approved. Pump is ordered and working on design review with contractor for pump pad, and welding procedure review for pipe modifications. Pump should arrive early November. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | St. Louis | BSEVO - ST CHARLES TERMINAL |  | 65303 | 21696 |  |  | 51620 |  | Posipanko, Dan | Decker, Paul |  |  | 1 | 45887 |  | Clark, David | Independent | Aqua | 2022-09-21 | Other Programs
St Charles Terminal (BSEVO) Tank 791 Out of Service Corrosion Inspection and Seal Upgrade | Item | Open | MCAP | BSEVO00M2201 | Maintenance Framework | 1989970 | Roth, Aaron | West | 6. Operational | Emergent | Tanks | -3351 |  |  | -3351.06 | -3351 | 0 | Green |  |  |  | -3351 |  |  | 350000 |  |  | 350000 | Phase | 350000 | 546221 |  | 546221 | No | Green | 2022-06-01 | 2022-06-10 | 2022-06-10 | 2022-08-30 | 2022-10-31 |  |  | -5029.98 | 237.98 | 1440.94 | [16 empty] | 10.31 - done | 2022-10-31 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | St. Louis |  |  | -3351 | 0 |  |  | 549572 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 43878 |  | Stine, Carlton | Independent | Aqua | 2022-06-03 | Int - Tanks
St Louis North Terminal Bathroom Repairs | Item | Open | MEXP | BETST00E2202 | Maintenance Framework | 2022544 | Scannell, Adam | West | 3. Active | Drawdown | West | 0 |  |  | 0 | 0 | 0 | Green |  |  |  | 0 |  |  | 25000 |  |  | 25000 | Full | 25000 | 30000 |  | 30000 | No | Green | 2022-12-01 | 2022-09-12 | 2022-09-12 | 2022-12-16 | 2023-05-31 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | Green | [11 empty] | 04/21/23 - Contractor has been contacted again to come back and complete finish work on floor and walls from fixing leaks. Should be back on 5/8.04/05/23 - Contractor ran into multiple pipe leaks and issues below the floor that prevent installing a urinal without far exceeding budget. Repairs are being completed and for the leaks and project will be closed out. 03/25/23 - Contractors will be on site Monday, 3/27 to finish the work on the bathroom. 03/02/23 - Still waiting on new toilet to complete. 02/02/23 - Waiting on new toilets, due to distance from wall to avoid having to tear out floor to replace piping. 01/04/23 - Completing final work 12/05/22 - Contractor had issue with subcontractor and did not start work as scheduled. Will complete in December. 11/02/22 - Scope reviewed and scheduling work to begin the week of 11/07/22. 10/04/22 - Funding approved and PO issued. Working on SSSP and scheduling start date in October. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | St. Louis | BETST - BET ST LOUIS NORTH TERMINAL |  | 0 | 0 |  |  | 30000 |  | Gardner, Travis | Spitz, Nicholas P. | N/A |  | 1 | 45811 |  | Gardner, Travis | JDE Child | Burnt Orange | 2022-09-12 | Other Programs
St Louis South Circuit 2 Phase 2 Insulated Piping Inspection | Item | Open | MEXP | BETSS00E2204 | Maintenance Framework | 1980269 | Scannell, Adam | West | 6. Operational | Defined | Facility Integrity | -14303 |  |  | -14302.96 | -14303 | 0 | Green |  |  |  | -14303 |  |  | 58000 |  |  | 58000 | Phase | 58000 | 26413 |  | 26413 | No | Green | 2022-09-01 | 2022-05-11 | 2022-05-11 | 2022-12-31 | 2022-09-30 |  |  | 734.04 | -15037 | [17 empty] | 09/29/22 - Site work comp0lete. Waiting on report. 09/02/22 - Work in progress. Expected completion is 9/2/22 for on site work. 08/02/22 - Forecast updated follow contractor schedule being received. Expected possibly late August, but likely to be completed in October. 07/01/22 - Forecast updated follow contractor schedule being received. Expected possibly late August, but likely to be completed in October. 06/02/22 - Verifying scope and issuing PO to the contractor. Waiting for schedule update. 05/12/22 - AFE has been approved and vendor selected. Scheduled is being developed, stakeholder meetings to follow. | 2022-09-29 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | St. Louis | BETSS - BET ST LOUIS SOUTH TERMINAL |  | -14303 | 0 |  |  | 40716 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 41179 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Accel Corr & FI
Sugar Creek - Overhead FRP Installation and Coating - Phase 2 - 2023 | Item | Candidate | MCAP |  | Maintenance Framework |  | Scott, Cory | West | 2. Pending AFE |  | Atmospheric Corrosion |  | 170000 |  | 170000 | 170000 | 0 | Green | 170000 |  | 170000 | 0 | [9 empty] | 170000 | 170000 | No | Green | 2023-08-01 |  |  |  | 2023-08-31 | [15 empty] | 170000 | [5 empty] | 4/18/2023 - Awaiting updated quotes from Vance and Associates and final clarifications of construction. 3/23/2023 - TAS visited site and will be making a plan for engineering approval before any lifting and project activities take place. | 2023-04-18 |  |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | BTTUG - BTT SUGAR CREEK |  |  | 0 | 170000 |  |  |  | Geib, Rob |  |  |  | 1 | 44048 |  | Guest, ProSight | Independent | Aqua | 2022-06-29 | Int - Planned Corr & FI
Sugar Creek - Pump Station Raceway Conduit | Item | Open | MCAP | BTTUG00M2205 | Maintenance Framework | 2037802 | Scott, Cory | West | 7. Closed | Drawdown | Electrical | 9036 |  |  | 9036.26 | 9036 | 0 | Green |  |  |  | 9036 |  |  | 48000 |  |  | 48000 | Full | 48000 | 47452 |  | 47452 | No | Green | 2022-11-01 | 2022-10-24 | 2022-10-24 | 2022-11-22 | 2022-11-21 |  |  | 5662.3 | 3228.67 | 145.29 | [16 empty] | 2/15/2023 - Waste Management invoice approved for $2973.00. This is the final billing. $47,000.00 for total project. 1/25/2023 - Staco sent over change order invoice for added junction boxes for $1600.00. This brings project total to 44K. 1/9/2023 - Approved final waste management invoice for $3,987.30. Final project amount will come out to $42403.00 resulting in $5,597.00 in cost savings. 12/30/2022 - Waste management sent over the final waste invoices only totaling $2,000.00. The $11,500.00 variance is due to coming under on waste management pricing, no backfill material was ordered, and operations underbilled labor costs. 12/7/2022 - Recieved final Staco invoice for $14830 totaling $33,460.00. Awaiting remaining dumpster charges. 11/2/2022 - Project trench dug and conduit is installed. Project should complete on 11/3/2022. 10/27/2022 - Stakeholder meeting held. Planned project start date is 10/31/2022. 10/26/2022 - Dumpsters arrived onsite. 10/24/2022 - Project AFE fully approved. Site safety plan fully approved. 10/18/2022 - Project AFE submitted. | 2023-02-15 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Sugar Creek | BTTUG - BTT SUGAR CREEK |  | 9036 | 0 |  |  | 38416 |  | Ashley, Robert | Smith, Todd W. |  |  | 1 | 46088 |  | Guest, ProSight | Independent | Aqua | 2022-10-18 | Other Programs
Sugar Creek - Utility Transformer Replacements | Item | Open | MCAP | BTTUG00M2305 | Maintenance Framework | 2084687 | Scott, Cory | West | 3. Active | Defined | Electrical |  | 43000 |  | 43000 | 43000 | 0 | Green | 40000 |  | 40000 | 3000 |  |  | 42731 |  |  | 42731 | Full | 42731 |  | 43000 | 43000 | No | Green | 2023-05-01 | 2023-02-14 | 2023-02-14 | 2023-03-24 | 2023-06-15 | [12 empty] | 43000 | [8 empty] | 5/03/2023 - Project planned during outage on 5/15/2023. 5/2/2023 - Staco superintendent available to proceed with project. Reaching out to scheduling to set a date. 4/5/2023 - Reforecasted project into June. Staco foreman is having surgery. Project is being rescheduled for when he is healed and we have another outage on both pipelines. 3/27/2023 - Operators said RVP was taking place so the soonest the project could take place is 4/10/2023. 3/7/2023 - Moved forecast back to April. Pipeline will require outage. Hoping to complete in March, if not it would be April. 2/28/2023 - Site safety plan sent in for approval. Stake holder meeting to be held on 3/7/2023. Planned project start date on 3/20/2023. 2/21/2023 - PO's placed for to Staco for project. | 2023-05-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Sugar Creek | BTTUG - BTT SUGAR CREEK |  |  | 43000 |  |  |  |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 44282 |  | Guest, ProSight | Independent | Aqua | 2022-07-27 | Other Programs
Sugar Creek - Water Line Repair | Item | Open | MEXP | BTTUG00E2302 | Maintenance Framework | 2112620 | Scott, Cory | West | 3. Active | Drawdown | West |  | 30001 |  | 30001 |  | 30001 | Red |  |  |  | 30001 |  |  | 30000 |  |  | 30000 | Full | 30000 |  | 30001 | 30001 | No | Green | 2023-05-01 | 2023-04-26 | 2023-04-26 | 2023-12-31 | 2023-05-05 | [12 empty] | 30000 | [6 empty] | 1 |  | 5/5/2023 - Water line repaired and holding water. Backfill and restoration process began. The repair will be completed to lot by 5/12/2023. 5/2/2023 - Found leak point. Making plans for repair. 4/28/2023 - Stakeholder meeting held. Work is to start on 5/1/2023. 4/27/2023 - PO placed for contractor for work to start on 5/1/2023. Inspector requested placed. 4/26/2023 - Water line leaking to fire suppression system for load racks. Project and interim AFE placed. | 2023-05-05 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Sugar Creek | BTTUG - BTT SUGAR CREEK |  |  | 30000 |  | 1 |  |  | Gardner, Travis | Smith, Todd W. |  |  | 1 | 46990 |  | Meitzler, Antoinette | JDE Child | Burnt Orange | 2023-04-26
Sugar Creek & Ottumwa 101 Tapping Machine Purchase | Item | Open | MCAP | UG00000M2301 | Exempt | 2075095 | Gardner, Travis | West | 6. Operational | Drawdown | West | 15990 |  |  | 15990.07 | 15990 | 0 | Green |  |  |  | 15990 |  |  | 16284 |  |  | 16284 | Full | 16284 | 15990 |  | 15990 | No | Green | 2023-02-01 | 2023-01-13 | 2023-01-13 | 2023-02-25 | 2023-02-25 |  |  |  | 14346.54 | 1643.53 | [16 empty] | 4/3/2023 - final invoice received and ready to close. 3/1/2023 - Variance is due to PMO or accounting. OPPM actuals don't match cognos actuals again... 2/2/2023 - PO's have been issued. ETA for delivery is February. | 2023-04-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Sugar Creek | UG - SUGAR CREEK |  | 15990 | 0 |  |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 46439 |  | Gardner, Travis | Independent | Aqua | 2023-01-06 | Other Programs
Sugar Creek (BTTUG) - Secondary containment improvements | Item | Candidate | MEXP |  | Maintenance Framework |  | Scott, Cory | West | 2. Pending AFE |  | Secondary Containment |  | 82000 |  | 82000 | 82000 | 0 | Green | 82000 |  | 82000 | 0 | [9 empty] | 82000 | 82000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 10000 | 72000 | [5 empty] | 4/6/2023 - Civil scope built for leadership review. 3/28/2023 - Meeting for project to transition information from Adam Scannell to Cory Scott. | 2023-04-06 |  |  | West | Pipelines and Terminals | Station/Terminal |  | Sugar Creek | BTTUG - BTT SUGAR CREEK |  |  | 0 | 82000 |  |  |  | Spari, Markella |  |  |  | 1 | 45322 |  | Spari, Markella | Independent | Aqua | 2022-08-25 | Other Programs
Sugar Creek Incoming Relief Valve Replacement | Item | Open | MCAP | BTTUG00M2301 | Maintenance Framework | 2074147 | Scott, Cory | West | 6. Operational | Defined | Transient/Surge Mitigation | 15744 |  |  | 15743.88 | 17231 | -1487 | Yellow | 25000 |  | 25000 | -9256 |  |  | 17227 |  |  | 17227 | Full | 17227 | 15744 |  | 15744 | No | Green | 2023-01-01 | 2023-01-05 | 2023-01-05 | 2023-01-24 | 2023-02-28 |  |  | 14535.88 | 1195 | 0 | 13 | 1500 | 1500 | -1487 | Red | [11 empty] | 5/2/2023 - Working on job book. 4/18/2023 - Project will be completed $1,496.00 under budget. 4/3/2023 - Approved coating invoice for Vance and Associates. 3/27/2023 - Vance and Associates coming to paint the surge relief valve. 1/31/2023 - Valve being moved from BTTUG inventory to the project. Adjusted forecast to reflect project installation in february for $16,500.00 and final coating in April for $1500.00. 1/31/2023 - Project activities taking place. 1/19/2023 - PO placed to Prairie Industrial. 1/18/2023 - Stake holder meeting held. 1/12/2023 - PO's placed and MOC being prepared. Stakeholder meeting planned for 1/18/2023. 1/4/2023 - AFE submitted with Quotes to remedyforce. Site specific safety plan submitted to Buckeye HSSE. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Sugar Creek | BTTUG - BTT SUGAR CREEK |  | 15731 | 13 |  |  |  |  | DiPillo, Evan | Smith, Todd W. |  |  | 1 | 44105 |  | Guest, ProSight | Independent | Aqua | 2022-07-11 | Other Programs
Sugar Creek Overhead FRP installation | Item | Open | MCAP | BTTUG00M2203 | Exempt |  | Scott, Cory | West | 5. Deferred | Defined | Atmospheric Corrosion |  | 202000 |  | 202000 | 202000 | 0 | Green |  | 200000 | 200000 | 2000 |  |  | 202000 |  |  |  | Full | 202000 |  | 202000 | 202000 | No | Green | 2023-08-01 |  |  | 2022-08-26 | 2023-08-31 | [15 empty] | 202000 | [5 empty] | 6/16/2022 - Deferral to 2023 - no active concerns per program owner 6/6/2022 - AFE Fully approved for $202,000.00 6/2/2022 - Submitting AFE into remedy force for $202,000. Additional funding approved by Rob Guy Corrosion Program Manager per Travis Rohr. 4/26/2022 - Working on FRP lifting plan. Vance is the selected contractor, they will be performing the work for an estimate totaling $136,000. 4/12/2022 - Site walk visit took place for Vance and Associates. 4/8/2022 - Cathodic Protection pre bid meeting 4/6/2022 - Coupa Bid Event Program - Registration and Contractors Status's shown. 3/28/2022 - Talked to Adam Scannell. These projects are under bid event process. Once completed, the AFE process and project process is to take place. 3/4/2022 - Discuss FRP pad requirements for SOW with Adam Scannell. 1/21/2022 - SOW sent to Adam Scannell for finalizing. | 2022-06-16 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | BTTUG - BTT SUGAR CREEK |  |  | 0 | 202000 |  |  |  | Geib, Rob | Smith, Todd W. |  |  | 1 | 41145 |  | Guest, ProSight | Independent | Aqua | 2021-08-09 | Other Programs
Sugar Creek Terminal (BTTUG) Tank 331 - OOS API 653 Insp | Item | Open | MCAP | BTTUG00M2302 | Maintenance Framework | 2084419 | Roknich, Hunter | West | 3. Active | Defined | Tanks |  | 493383 |  | 493383 | 493383 | 0 | Green | 493383 |  | 493383 | 0 |  |  | 210500 |  |  | 210500 | Phase | 210500 |  | 493383 | 493383 | No | Green | 2023-06-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-08-31 | [13 empty] | 30000 | 170000 | 170000 | 123383 |  |  |  |  | 5/2/2023 - OOS scheduled for 6/19 4/4/2023 - OOS scheduled for 6/19 3/31/2023 - Early/Mid June start date 10.28.22 - start June | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | BTTUG - BTT SUGAR CREEK |  |  | 30000 | 463383 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44884 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Sugar Creek Terminal (BTTUG) Tank 335 - OOS API 653 Insp | Item | Open | MCAP | BTTUG00M2304 | Maintenance Framework | 2084381 | Roknich, Hunter | West | 3. Active | Defined | Tanks |  | 493383 |  | 493383 | 493383 | 0 | Green | 493383 |  | 493383 | 0 |  |  | 210500 |  |  | 210500 | Phase | 210500 |  | 493383 | 493383 | No | Green | 2023-08-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-10-31 | [15 empty] | 19383 | 250000 | 224000 |  |  |  | 5/2/2023 - See below 3/31/2023 - Will start after Sugar Creek Tank 339 | 2023-05-02 |  |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | BTTUG - BTT SUGAR CREEK |  |  | 0 | 269383 | 224000 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44885 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Sugar Creek Terminal (BTTUG) Tank 339 - OOS API 653 Insp | Item | Open | MCAP | BTTUG00M2303 | Maintenance Framework | 2084422 | Roknich, Hunter | West | 3. Active | Defined | Tanks |  | 340000 |  | 340000 | 340000 | 0 | Green | 320663 |  | 320663 | 19337 |  |  | 200015 |  |  | 200015 | Phase | 200015 |  | 340000 | 340000 | No | Green | 2023-07-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-09-30 | [14 empty] | 40000 | 150000 | 100000 | 50000 |  |  |  | 5/2/2023 - See below 3/31/2023 - Will start after Sugar Creek Tank 331 10.28.22 - start june or july | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | BTTUG - BTT SUGAR CREEK |  |  | 0 | 290000 | 50000 |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44886 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Sugar Creek Terminal (BTTUG) Tank 338 – OOS Corr Insp & Refurb | Item | Open | MCAP | BTTUG00M2201 | Maintenance Framework | 1938069 | Roth, Aaron | West | 6. Operational | Defined | Tanks | -1352 |  |  | -1351.5 | 19649 | -21000 | Red | 95000 |  | 95000 | -96352 |  |  | 472000 | 33000 |  | 505000 | Full | 505000 | 468890 |  | 468890 | No | Green | 2022-05-01 | 2022-01-11 | 2022-01-11 | 2022-12-31 | 2022-12-31 |  |  | 16779.2 | 4594.45 | -1725.15 | -21000 |  |  | -21000 | Red |  | Forecasting | [9 empty] | 5.1 - done. VAR: accrual dropped. not needed. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | BTTUG - BTT SUGAR CREEK |  | 19649 | -21000 |  |  | 470241 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41341 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Sugar Creek Terminal (BTTUG) Tank 340 – OOS Corr Insp & Refurb | Item | Open | MCAP | BTTUG00M2202 | Maintenance Framework | 1938070 | Roth, Aaron | West | 6. Operational | Defined | Tanks | 3780 |  |  | 3779.51 | 3780 | 0 | Green |  |  |  | 3780 |  |  | 485000 |  |  | 485000 | Phase | 485000 | 268158 |  | 268158 | No | Green | 2022-05-01 | 2022-01-11 | 2022-01-11 | 2022-01-03 | 2022-09-30 |  |  | 3629.9 | 149.61 | [17 empty] | 12.9 - paint touchups along with tk 338 this month. VAR - didn't happen last month. | 2022-12-09 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Sugar Creek | BTTUG - BTT SUGAR CREEK |  | 3780 | 0 |  |  | 264378 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41342 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Sugar Creek Terminal Tank 110 NFPA Internal Inspection | Item | Open | MEXP | BTTUG00E2201 | Maintenance Framework | 1936955 | Roth, Aaron | West | 7. Closed | Defined | Tanks | 11900 |  |  | 11900 | 11900 | 0 | Green |  |  |  | 11900 |  |  | 12000 |  |  | 12000 | Phase | 12000 | 11900 |  | 11900 | No | Green | 2022-07-01 | 2021-12-31 | 2021-12-31 | 2022-12-31 | 2022-09-30 |  |  | 11900 | [18 empty] | 12/22/22 - PO and WO closed - ready to be closed by accounting. 9.29.22 - done july 7 | 2022-12-22 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Sugar Creek | BTTUG - BTT SUGAR CREEK |  | 11900 | 0 |  |  | 0 |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 41343 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Tanks
Sugar Creek VRU Release Prevention | Item | Open | MCAP |  | Maintenance Framework |  | Scannell, Adam | West | 8. Canceled |  | Vapor Management |  | 18002 |  | 18002 | 18002 | 0 | Green | 61000 |  | 61000 | -42998 | [9 empty] | 18002 | 18002 | No | Green | 2023-11-01 |  |  |  | 2023-03-31 | [18 empty] | 18000 | 2 |  | 02/02.23 - This budget is being transferred to another site. From last conversation with Marissa Karl, she is making the determination of which site it will be. 03/10/23 - Budget from Sugar Creek VRU Release Prevention project being utilized to fund Harristown VRU (OPPM ID 44949). Sugar Creek was completed in 2018. Original Budget $61k. $18k remaining | 2023-03-10 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Sugar Creek | BTTUG - BTT SUGAR CREEK |  |  | 0 |  | 18002 |  |  | Karl, Marissa |  |  |  | 1 | 44953 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Other Programs
TANK DIKE CASE END SEAL INSTALL BETNP | Item | Open | MEXP | BETNP00E2201 | Maintenance Framework | 1970001 | Brown, Jeff | West | 7. Closed | Drawdown | Atmospheric Corrosion | 257 |  |  | 257.29 | 257 | 0 | Green |  |  |  | 257 |  |  | 17000 |  |  | 17000 | Full | 17000 | 17885 |  | 17885 | No | Green | 2022-04-01 | 2022-04-01 | 2022-04-01 | 2022-12-31 | 2022-06-30 |  |  | 257.29 | [18 empty] | 6/2/22- work completed. ready to close. 5/2/2022 - materials purchased. work starting in May. 4/5/2022 - emergent drawdown project schedule for June. | 2022-06-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Wayne Terminals | BETNP - BET NAPOLEON |  | 257 | 0 |  |  | 17628 |  | Geib, Rob | Shook, Mark B. | N/A |  | 1 | 43331 |  | Schultz, Amy | JDE Child | Burnt Orange | 2022-04-01 | Int - Planned Corr & FI
Taylor East - Piping Replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Roman, James | West | 2. Pending AFE |  | Facility Integrity |  | 110000 |  | 110000 | 50000 | 60000 | Red | 50000 |  | 50000 | 60000 | [9 empty] | 110000 | 110000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 110000 | [6 empty] | 5/2/23 Visited site and will put scope of work together. | 2023-05-02 |  |  | West | Pipelines and Terminals | Integrity |  | Wayne Terminals | BETAD - BET TAYLOR EAST TERMINAL |  |  | 0 | 110000 |  |  |  | Aiken, Elaine |  |  |  | 1 | 44514 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Other Programs
Taylor East Env-Eng Study for Installation of Outfall OWS Phase II | Item | Open | MCAP | BETAD00M2202 | Maintenance Framework | 2012377 | Roknich, Hunter | West | 3. Active | Defined | Storm Water Management | 32178 | 118000 |  | 150178 | 119178 | 31000 | Red | 118000 |  | 118000 | 32178 |  |  | 73000 |  |  | 73000 | Phase | 73000 | 63178 | 118000 | 181178 | No | Green | 2022-12-01 | 2022-08-15 | 2022-08-15 | 2022-12-01 | 2023-05-31 |  |  | 1178 | 0 | 0 | 31000 |  |  | 31000 | Red | [5 empty] | 118000 | [5 empty] | 5/2/2023 - See below 4/4/2023 - Waiting for second quote and material delivery. 3/2/2023 - Still waiting for second quote. 2/2/2023 - Waiting for second quote 1/4/2023 - MOV and stormceptor purchased. 12/2/2022 - December forecast for purchasing of stormceptor and MOV 11/2/2022 - Working with Holly Construction for construction quote. 10/11/2022- Having issue with Northern Concrete (vendor) for purchasing stormceptor. Need to get credit card limit increase. Pushed construction forecast to CY+1 in case material does not arrive CY 9/2/2022 - Material purchasing in progress. 8/2/2022 - Phase 1 AFE to be submitted 8/2 for material purchasing. 8/25/2022 - AFE approved. Material purchasing in progress. COUPA bid event to be set up for construction. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETAD - BET TAYLOR EAST TERMINAL |  | 1178 | 31000 | 118000 |  | 31000 |  | Bonenberger, Mark | Gardner, Travis W. |  |  | 1 | 41370 |  | Gardner, Travis | Independent | Aqua | 2021-08-10 | Other Programs
Taylor East Terminal - Tank Alarm System Replacement | Item | Open | MCAP | BETAD00M2203 | Maintenance Framework | 2011011 | Gardner, Travis | West | 6. Operational | Emergent | Instrumentation & Controls | 1658 |  |  | 1657.98 | 1658 | 0 | Green |  |  |  | 1658 |  |  | 46000 |  |  | 46000 | Full | 46000 | 40272 |  | 40272 | No | Green | 2022-09-01 | 2022-08-11 | 2022-08-11 | 2022-11-18 | 2022-11-18 |  |  | 1657.98 | [18 empty] | 11/1/2022 - Work completed and installed by Techs for project savings. 10/3/2022 - equipment arrived work forecasted in November. 9/1/2022 - material to arrive 9/26. Install in november due to back log of work. | 2022-11-01 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETAD - BET TAYLOR EAST TERMINAL |  | 1658 | 0 |  |  | 38614 |  | Forsey, Frank | Gardner, Travis W. |  |  | 1 | 44412 |  | Gardner, Travis | Independent | Aqua | 2022-08-04 | Other Programs
Taylor East Terminal Tank 3 Dike Repair and Pipe Moving | Item | Open | MEXP | BETAD00E2202 | Maintenance Framework | 2022090 | Roman, James | West | 3. Active | Drawdown | West | 5905 | 25000 |  | 30905 | 105905 | -75000 | Red | 50000 |  | 50000 | -19095 |  |  | 100000 |  |  | 100000 | Full | 100000 | 67053 | 25000 | 92053 | No | Green | 2022-09-01 | 2022-09-08 | 2022-09-08 | 2023-07-28 | 2023-06-30 |  |  | 36.06 | 5868.94 | [9 empty] | 0 | 25000 | [6 empty] | 5/1/23 Scoped work on site in April. 3/1/23 Variance $6k. Forgot to re accrue this last month. 2/1/23 No change 1/4/23 Variance -$3k. Over accrued costs. 12/5/22 Variance -$10k. Accrual $13k. Phase 1, civil work, complete. 11/12/22 Contractor mobilizing today. Plan to start construction tomorrow. Need inspector so increased November forecast and winning bidder was $49k. 10/3/22 Variance (+$5,271) Finished engineering ahead of schedule. Project out to bid. Bids to be received Mid October. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Terminals | BETAD - BET TAYLOR EAST TERMINAL |  | 5905 | 0 | 25000 |  | 61148 |  | Gardner, Travis | Spitz, Nicholas P. | N/A |  | 1 | 45759 |  | Gardner, Travis | JDE Child | Burnt Orange | 2022-09-08 | Other Programs
Taylor Terminal Flash Tester Purchase | Item | Open | MCAP | BTTDB00M2203 | Maintenance Framework | 2051186 | Gardner, Travis | West | 7. Closed | Emergent | Measurement & Quality Control | 2726 |  |  | 2726.21 | 2726 | 0 | Green |  |  |  | 2726 |  |  | 33000 |  |  | 33000 | Full | 33000 | 29084 |  | 29084 | No | Green | 2022-12-01 | 2022-12-02 | 2022-12-02 | 2022-12-31 | 2022-12-30 |  |  | 2608.81 | 117.4 | [17 empty] | 1/4/2023 - equipment received variance is contingency. 12/2/2022 - emergent project. flash tester to arrive in December. | 2023-01-04 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BTTDB - BTT TAYLOR TERMINAL |  | 2726 | 0 |  |  | 26358 |  | Hopkins, Christa |  | N/A |  | 1 | 30658 |  | Hopkins, Christa | Independent | Aqua | 2018-08-16 | Other Programs
Taylor Terminal Tank 1 Pump Refurbishments | Item | Open | MCAP | BTTDB00M2202 | Maintenance Framework | 1946235 & 1947125 | Gardner, Travis | West | 7. Closed | Drawdown | Rotating Equipment | 396 |  |  | 395.82 | 396 | 0 | Green |  |  |  | 396 |  |  | 63000 |  |  | 63000 | Full | 63000 | 64926 |  | 64926 | No | Green | 2022-05-01 | 2022-04-14 | 2022-04-14 | 2022-05-27 | 2022-05-27 |  |  | 110.01 |  | 285.81 | [16 empty] | 9/1/2022 - work has been completed. 8/2/2022 - pushed install to Sept waiting for ez-line support. 7/5/2022- variance is from reclass from local BU. 6/3/22 - pump refubishment savings. install forecasted for July. pipesupports need replaced due to pipe strain. 5/5/2022 - left forecast in May waiting for Operations to confirm work was completed. 4/4/2022 - emergent project. Kennedy has pumps and reinstall should happen in April | 2022-09-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BTTDB - BTT TAYLOR TERMINAL |  | 396 | 0 |  |  | 64530 |  | Posipanko, Dan | Spitz, Nicholas P. |  |  | 1 | 43310 |  | Gardner, Travis | Independent | Aqua | 2022-04-01 | Other Programs
TOLEDO AREA 344 TEST STATION REPAIRS | Item | Open | MEXP | DS999A7E2301 | Exempt | 2085713 | Brown, Jeff | West | 6. Operational | Defined | Cathodic Protection | 18000 |  |  | 18000 | 18000 | 0 | Green | 18000 |  | 18000 | 0 |  |  | 19800 |  |  | 19800 | Full | 19800 | 18000 |  | 18000 | No | Green | 2023-04-01 | 2023-02-21 | 2023-02-21 | 2023-06-30 | 2023-05-01 | [5 empty] | 18000 | 18000 | 18000 | 0 | Green | [11 empty] | 5-1-23 Project complete. No additional invoices. 4-3-23 DELAYED TO APRIL-TOLEDO REF ACCESS 3-2-23 AFE APPROVED-WRITR SERV CONTRACT 2-03-23 - MNH - AFE is routed. EAC to be at $18K. | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Corrosion |  | Toledo | DS - TOLEDO STATION |  |  | 18000 |  |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45366 |  | Gardner, Travis | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
Toledo Asset RMU Repairs | Item | Open | MEXP | CGNONFSE2301 | Maintenance Framework | 2095208 | Brown, Jeff | West | 3. Active | Drawdown | Cathodic Protection | 1671 | 13300 |  | 14970.99 | 14971 | 0 | Green |  |  |  | 14971 |  |  | 15000 |  |  | 15000 | Full | 15000 | 1671 | 13300 | 14971 | No | Green | 2023-03-01 | 2023-03-17 | 2023-03-17 | 2023-12-31 | 2023-12-31 |  |  |  |  | 1670.99 | [9 empty] | 7500 |  |  |  |  | 5800 |  | 5-1-23 Ongoing repairs through-out the year. 4-3-23 VARIANCE IS FOR MOBILTEX INVOICE FOR SATELILITE TRANSMITTERSONGOING REPAIRS CHARGED THROUGHOUT THE YEAR | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Toledo | CGNONFS - CYGNET TO FOSTORIA |  | 1671 | 0 | 7500 | 5800 |  |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 46805 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-03-17
Toledo meter replacements 17T and 211 | Item | Open | MCAP | DS00000M2302 | Maintenance Framework | 2093529 | Henfling, Mike | West | 3. Active | Defined | Measurement & Quality Control | 2534 | 134000 |  | 136533.5 | 137300 | -767 | Yellow | 140000 |  | 140000 | -3467 |  |  | 97987 |  |  | 97987 | Phase | 97987 | 2534 | 134000 | 136534 | No | Green | 2023-03-01 | 2023-03-03 | 2023-03-03 | 2023-08-30 | 2023-09-30 |  |  |  |  | 3300 | -766.5 |  |  | -767 | Red |  |  |  |  | 4000 | 90000 | 10000 | 30000 |  |  |  | 5-2-23 - No new updates, meters on order for 8/1 delivery. Drop-in install late August - site Ops/Techs to assist. 4-4-23 - Phase AFE approved, meters on order for 8/1 delivery. Drop-in install late August - site Ops/Techs to assist. 3-2-23 - AFE in progress. PO to be issued to SPS for FMC meters upon approval. 20 week lead time puts delivery at August 1st. Drop-in install late August - site Ops/Techs to assist 2-2-23 - Site visit held 1/17 - plan to replace meters with FMC .07% linearity. Drop-in replacements for both - no mechanical work. Requested updated quotes, will then submit AFE. Note - wiring to meters was replaced in 2020. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | DS - TOLEDO STATION |  | 3300 | -767 | 104000 | 30000 |  |  | Hopkins, Christa | Gardner, Travis W. |  |  | 1 | 44396 |  | Guest, ProSight | Independent | Aqua | 2022-08-03 | Other Programs
Toledo Norco - Install Actuator | Item | Open | MCAP | TO00000M2201 | Maintenance Framework | 1979715 | Parker, Brian | West | 7. Closed | Defined | Valves | 1003 |  |  | 1002.56 | 1003 | 0 | Green |  |  |  | 1003 |  |  | 17000 |  |  | 17000 | Phase | 17000 | 14399 |  | 14399 | No | Green | 2022-11-01 | 2022-05-04 | 2022-05-04 | 2022-10-31 | 2022-12-02 |  |  | 1002.56 | [18 empty] | 2/3/23 - this project is ready to be closed out in JDE and OPPM. 1/2/23 - processed one invoice in Dec for shipping of the actuator. Should be ready to close this project at the end of Jan. 11/30/22 - actuator installed on Nov 28th and has AC power to it and operates locally. Chuck will work on getting this connected to the local HMI which is already setup for the control of this actuator/valve. 11/18/22 - actuator arrived on Nov 8th - just need local ops to get this installed and checked out back to SCADA. 11/8/22 - Var is due to delay in receiving actuator at factory, last update on Nov 7th is that actuator should arrive on Nov 8th - shifting FCST out another month. 10/3/22 - received email from Ken Nelson with HPC that there is a delay in receiving the actuator. New estimated ship date is 10/17. 9/28/22 - have not received the actuator yet - sent Adam Krause with HPC an email requesting an shipping update. Actuator should have arrived on Sep 26th - worst case. 9/3/22 - no change, expect delivery of actuator sometime around Sep 12 - 26 with installation in Oct. 8/1/22 - no change, expect delivery of actuator sometime around Sep 12 - 26. 5/31/22 - might be able to get away with just a Phase I AFE if install costs do not exceed 6,000. Electrical conduit/wiring is already at this valve so expect minimal costs to get this operational. 5/9/22 - entered Req. into JDE for purchase of Rotork IQ40 actuator - should be delivered before Sep 30th. 5/3/22 - waiting for AFE to get approved so I can get a PO issued for new actuator. 4/27/22 - routed Phase I AFE for approval to get new actuator purchased. 4/5/22 - HPE forgot to send me the revised quote. Sent email to Chuck to see if he had quote from electrical contractor. If not, I will probably just submit a Phase I AFE to get the new Rotork Actuator purchased since it has a lead time of 20 weeks (end of Aug). 2/2/22 - based on actuator lead times for West Toledo project, I'm moving this FCST out to Aug/Sep time frame since actuatorshave a 22 week lead time. | 2023-02-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | TO - TOLEDO NORCO |  | 1003 | 0 |  |  | 13397 |  | Oey, Alex | Gardner, Travis W. | N/A |  | 1 | 30305 |  | Guest, ProSight | Independent | Aqua | 2018-08-06 | Other Programs
Toledo Norco 211 Control Valve Replacement | Item | Open | MCAP | TO00000M2301 | Project Framework | 2095078 | Henfling, Mike | West | 3. Active | Defined | Transient/Surge Mitigation | 10645 | 202000 |  | 212645 | 213000 | -355 | Yellow | 90000 |  | 90000 | 122645 |  |  | 142898 |  |  | 142898 | Phase | 142898 | 10645 | 202000 | 212645 | No | Green | 2023-03-01 | 2023-03-15 | 2023-03-15 | 2023-11-01 | 2023-12-01 |  |  |  |  | 7000 | 3645 | 6000 | 6000 | -2355 | Red |  |  | 6000 | 6000 | 0 | 0 | 45000 | 110000 | 35000 |  |  | 5-2-23 - Engineering started, to be completed in May. Design review late May or early June, and bidding in June/July. Control valve won't be delivered until 10/1. 4-4-23 - Control valve ordered in March, 28-week lead time for 10/1 delivery. Engineering in April, and mechanical bids in June. 3-2-23 - Call held to review valve quotes with Engineering Stakeholders on 2-27. Plan to order 28-week lead time valve by 3/7. Valve delivery late September. $100k for valve, plus ~$50k for install. Increased forecast. Will submit Phase AFE for engineering and Valve in March. Bids for piping in May. 2-2-23 - Working with Alex Ferrari and two different control valve suppliers to finalize valve selection - quotes to be received in early February. Will need to upsize from 8" to either 10" or 12" due to wide range of flows. Likely 2-day outage for install needed. $90k budget may be light. Left forecast as-is for now. 1-3-23 - Left forecast as-is. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | TO - TOLEDO NORCO |  | 7000 | 15645 | 45000 | 145000 |  |  | DiPillo, Evan | Gardner, Travis W. |  |  | 1 | 43566 |  | Guest, ProSight | Independent | Aqua | 2022-04-29 | Other Programs
Toledo Norco Lab replacement | Item | Open | MCAP | BETTO00M2201 | Maintenance Framework | 2013043 | Arch, Stefan | West | 3. Active | Defined | West | 32648 | 55000 |  | 87648.05 | 90033 | -2385 | Yellow | 82500 |  | 82500 | 5148 |  |  | 127000 |  |  | 127000 | Phase | 127000 | 139114 | 55000 | 194114 | No | Green | 2022-08-01 | 2022-08-22 | 2022-08-22 | 2022-03-31 | 2023-04-30 |  |  | 26532.3 | 2228.07 | 1273.04 | 2614.64 | 7500 | 7500 | -4885 | Red |  |  | 20000 | 35000 | [7 empty] | 5/1/2023 - Received fume hood for installation. chuck Rapp set up equipment inside building and walked down with electricians. Waiting on quote from electricians to submit the full AFE. Planning to complete end of May/beg of June. 4/3/2023 - Fume hood delayed and working to get it shipped as soon as possible. Grainger said it would be on site 4/3. Once set up in lab, I will get quotes from electrical and sheet metal contractor for installation of components. Forecasting pushed out a month. 3/1/2023 - Waiting on the lab building to come in and set up lab building. Once lab is set up, will get quotes for electrical and modifications to the building. Planning to complete in April. Phase II AFE will be submitted once quotes are realized. 2/1/2023 - Completed installation of conduit and electrical at Norco. Waiting for fume hood to be received in February and propose layout of the building. Once proposed layout is installed, I will get electrical and building modifications quote. Moved forecast out to March and April. 1/3/2023 - Received building for Toledo Station and moved existing lab to Norco. Planning to complete electrical work at Norco in January. Ordered fume hood in December. Developing scope for Toledo Station building for electrical and component installation. 12/1/2022 - Par-Kut continued fabrication of the building in November. Installed concrete foundations in November. Planning to purchase fume hood in December and take delivery of building. 11/1/2022 - No work completed in October. Variance due to no work completed. Degen did not set concrete. Planning to set concrete in November and order a fume hood. Forecast moved to November. 10/3/2022 - Par-Kut continuing fabrication of building. Ordered material for inside the building. Forecasted extended into next year, spoke with Travis about roll over due to long lead time of building. Continuing ordered material and installing concrete in October. 9/1/2022 - Submitted AFE and approved for extra funds. PO cut to Par-Kut for new building. 28 week lead time on the building. Planning to procure building, lab equipment, and set concrete in 2022. Will install electrical and move building(s) in 2023. Small variance in August is due to down payment on the building. Building will be delivered at the turn of the year. Forecasting in February and March for the electrical and placing the building. Forecast in September is for ordering lab equipment. 8/5/2022 - Received pricing back from bid event. Working to Travis to see if funds are available. AFE is developed. Forecast shifted September and October. 6/1/2022 - Finishing up scope, gathered more information in May. Planning to begin the ordering the new building inJuly. Will have AFE submitted in June. Planning to reuse vent hoods from de-commissioned out west. 5/2/2022 - Will send scope for leadership review. Working with Brian on using equipment from decommissioned lab in West District. Received old quote but needs to be updated to reflect size and additional fans that are needed. Spoke with Degen regarding the foundation and moving the lab from Toledo Station to Norco. Once I get quotes back from building manufacturer, will develop AFE and submit. 4/3/2022 - Walked down project with Justin Lambon 3/23. Developed scope, will send to leadership team for review. Scope includes installing concrete piers at Norco, ordering new lab for York Street, and installing new lab at York Street. Planning to begin in May. 3/1/2022 - No updates for February. Planning to gather information and develop scope in March. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | BETTO - BET TOLEDO TERMINAL |  | 30033 | 57615 |  |  | 106466 |  | Gardner, Travis | Gardner, Travis W. | N/A |  | 1 | 19766 |  | Guest, ProSight | Independent | Aqua | 2016-07-26 | Other Programs
Toledo Norco replace trip hazards on sidewalk | Item | Candidate | MCAP |  | Exempt |  | Arch, Stefan | West | 2. Pending AFE |  | West |  | 25000 |  | 25000 | 25000 | 0 | Green | 25000 |  | 25000 | 0 | [9 empty] | 25000 | 25000 | No | Green | 2023-06-01 |  |  |  | 2023-06-30 | [13 empty] | 25000 | [7 empty] | 5/1/2032 - Received quote from Holly and waiting on pricing from Degen. Once get back pricing, I will submit an AFE. Still looking to complete in June. 4/3/2032 - Walked down project again with Ryan Baker. Updated scope and sent to management for review. Additionally sent it to Degen for pricing. Planning to complete in June time frame. 3/1/2023 - Sent scope for review and Mike Ricke asked operations to point out more spots to complete in this project. Waiting on word from Operations, will modify scope, and resend to management. Still planning to complete in summer. 2/1/2023 - Walked down project with Justin Lamb on 1/13/2023. Developing scope and will send for review. Minor project to replace sidewalk trip hazards at Norco. Planning to complete in summer. | 2023-05-01 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | TO - TOLEDO NORCO |  |  | 25000 |  |  |  |  | Gardner, Travis |  |  |  | 1 | 37780 |  | Guest, ProSight | Independent | Aqua | 2020-08-12 | Other Programs
Toledo Norco Security Cameras | Item | Candidate | MCAP |  | Maintenance Framework |  | Hassan, Mohammad | West | 2. Pending AFE |  | Security & Cameras |  | 65000 |  | 65000 | 65000 | 0 | Green | 65000 |  | 65000 | 0 | [9 empty] | 65000 | 65000 | No | Green | 2023-08-01 |  |  |  | 2023-09-30 | [15 empty] | 30000 | 35000 |  |  |  |  | 05-02-2023 - MNH - All quotes received. Will work on submitting AFE in May. 04-20-2023 - MNH - Awaiting last quote for fiber termination followed by AFE submittal in May. 03-31-2023 - MNH - Awaiting final quote from U.S utility for running fiber. AFE to be submitted next month. 03-01-2023 - MNH - Awaiting quote from Convergint & Electrical contractor before submitting the AFE. 02-01-2023 - MNH - Will start looking at scope of work this month. 01-03-2023 - MNH - Will start looking at scope of work next month. 12-1-2022 - MNH - Will start looking at scope of work in Q1 of 2023. | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | TO - TOLEDO NORCO |  |  | 0 | 65000 |  |  |  | Clark, Chris |  |  |  | 1 | 33978 |  | Guest, ProSight | Independent | Aqua | 2019-08-13 | Other Programs
Toledo Norco Station Inbound 303L Move Relief Downstream | Item | Candidate | MCAP |  | Maintenance Framework |  | Henfling, Mike | West | 2. Pending AFE |  | Transient/Surge Mitigation |  | 185000 |  | 185000 | 185000 | 0 | Green | 185000 |  | 185000 | 0 | [9 empty] | 185000 | 185000 | No | Green | 2023-11-01 |  |  |  | 2023-12-31 | [14 empty] | 0 | 0 |  |  | 50000 | 135000 |  | 5-2-23 - No new updates, project likely to be cancelled as not necessary 4-4-23 - Project likely to be cancelled as not necessary 2-10-23 - Call held with management to likely forego project. Pushed forecast to 4Q. 2-2-23 - Site visit held 1/17. Call set-up for 2/10 to review if project is warranted, as a new MOV installed in late 2022 should alleviate most issues with relief on the 303 at TO. 1-3-23 - Spoke to Ops 12/22, plan to re-use existing relief valve. No long lead items anticipated. | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | TO - TOLEDO NORCO |  |  | 0 | 0 | 185000 |  |  | DiPillo, Evan |  |  |  | 1 | 45442 |  | Gardner, Travis | Independent | Aqua | 2022-08-26 | Other Programs
Toledo NORCO Sulfur Analyzer Replacement | Item | Open | MCAP | TO00000M2203 | Maintenance Framework | 2036012 | Parker, Brian | West | 7. Closed | Drawdown | Measurement & Quality Control | 109 |  |  | 109.29 | 109 | 0 | Green |  |  |  | 109 |  |  | 68000 |  | 17000 | 68000 | Full | 85000 | 78665 |  | 78665 | No | Green | 2022-11-01 | 2022-10-04 | 2022-10-04 | 2022-11-18 | 2022-11-15 |  |  | 109.29 | [18 empty] | 12/14/22 - PO and WO closed - ready to be closed by accounting. 11/28/22 - PO closed, need to close out project in Dec. 11/15/22 - new XOS arrived today and Justin Lamb is working to get this setup. Material was receipted in JDE. Project is operational and need to wait until first of Dec to close out project. 11/9/22 - XOS has the new sindie unit shipping by Nov 11th so moving FCST from Dec to Nov. 10/31/22 - supplemental AFE was approved and change order on PO was issued on 10/7 for the full cost of a new sulfur analyzer 10/10/22 - no units have been purchased in 2022 so the discounted price is only valid if a min. of 3 units have been purchased in a year. The new quoted price is 75,595. Supplemental AFE was submitted on Oct 10th. 10/5/22 - PO issued for 60,500 - expect a credit for old, obsolete unit. Will probably have to issue a change order for this credit once all costs are known. Expect shipping in late Nov or early Dec so FCST'ing for Dec right now. 9/29/22 - submitted emergent AFE to workflow for approval routing. | 2022-12-14 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | TO - TOLEDO NORCO |  | 109 | 0 |  |  | 78556 |  | Hopkins, Christa | Gardner, Travis W. |  |  | 1 | 44525 |  | Guest, ProSight | Independent | Aqua | 2022-08-11 | Other Programs
Toledo Norco Tank Farm Tank Wiring | Item | Open | MCAP | TO00000M2202 | Maintenance Framework | 1947847 | Hassan, Mohammad | West | 6. Operational | Defined | Instrumentation & Controls | 36195 | 15600 |  | 51794.62 | 51979 | -185 | Yellow | 160000 |  | 160000 | -108205 |  |  | 23000 | 248000 |  | 271000 | Full | 271000 | 255779 | 15600 | 271379 | No | Green | 2022-05-01 | 2022-05-24 | 2022-05-24 | 2022-09-16 | 2023-01-18 |  |  | 20939.08 | 4140.87 | 9899.21 | 1215.46 |  |  | 1215 | Red |  |  |  | 2000 | 3000 |  | 10600 |  |  |  |  | 05-02-2023 - MNH - Some punch list items are outside of the scope of this project and will need more funding in the future. This project is now complete and will work on closeout items over next two months. Will use remianing forecast to fund another PLC project at BETVL. Project EAC at $260K but forecast shows the total approved AFE amont of $271K. 04-03-2023 - MNH - Project is operational and still working on some punchlist items and some of that work may need to be delayed until weather gets better. Project EAC still at $271K. 03-01-2023 - MNH - Project is operational and working on some punchlist items now and that work may need to be delayed until weather gets better. Project EAC still at $271K. 02-01-2023 - MNH - Project is operational and ahead of schedule. Working on some punchlist items now and that work may need to be delayed until weather gets better. Project EAC still at $271K. 01-03-2023 - MNH - Onsite construction work is complete and ahead of schedule and planning commissioning this month now. Reducing 2023 forecast by $6K and adjusting it. Project EAC still at $271K. 12-02-2022 - MNH - Onsite construction work is ahead of schedule. Reducing 2023 forecast by $49K. Project EAC still at $271K. 11-02-2022 - MNH - Onsite construction work started last month and is ahead of schedule. Reducing 2023 forecast by $50K. Project EAC still at $271K. 10-04-2022 - MNH - Project AFE got approved on Sep 26th. Planning on starting work this month. 09-01-2022 - MNH - Bids came back today and this project will need about $270K total. Since the budget was $100K in 2022, adding $170K in 2023 to complete the project. Moving September forecast into Q4 until decision is made to go forward with this project. 08-01-2022 - MNH - Design behind but getting done this week followed by bid event and full AFE submittal. Electrical construction will be delayed as well. Moving forecast out a month. 07-06-2022 - MNH - Design underway but a bit behind schedule. Forecast adjusted and moved out a bit. 06-01-2022 - MNH - Phase 1 AFE approved and vendor to start design this month. June and July forecast reduced and moved into Q3. 05-03-2022 - MNH - Delay in submitting Phase 1 AFE due to project workload. Will plan on submitting this month. Moving $15K from June into September.04-01-2022 - MNH - Will submit Phase 1 AFE this month. 03-01-2022 - MNH - Initial site visit done. Will plan on getting Phase 1 AFE routed to get drawings completed in order to getbids from contractors. 03-01-2022 - MNH - Initial site visit done. Will plan on getting Phase 1 AFE routed to get drawings completed in order to get bids from contractors. 02-02-2022 - MNH - Will start working on SOW this month. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | TO - TOLEDO NORCO |  | 34979 | 3215 | 13600 |  | 219584 |  | Forsey, Frank | Ashley, Robert |  |  | 1 | 40901 |  | Guest, ProSight | Independent | Aqua | 2021-08-03 | Other Programs
Toledo Norco Terminal (BETTO) External Tank Rivet Repair | Item | Open | MEXP | BETTO00E2201 | Maintenance Framework | 1954802 | Arch, Stefan | West | 6. Operational | Drawdown | Tanks | 77 |  |  | 76.85 | 77 | 0 | Green |  |  |  | 77 |  |  | 20000 |  |  | 20000 | Full | 20000 | 20099 |  | 20099 | No | Green | 2022-04-01 | 2022-03-01 | 2022-03-01 | 2022-07-01 | 2022-05-20 |  |  | 76.85 | [18 empty] | 4/7/2023 - Project is complete, all invoices have been paid. Need to close out project. 3/1/2023 - Project is complete, all invoices have been paid. WO can be closed. 2/1/2023 - Project is complete 1/3/2023 - Project is complete, all invoices have been approved. 7/1/2022 - No additional work required, project is complete. Cost in June is additional inspector costs. 6/1/2022 - Tank 3512 still has leaks, looking to get Advanced back on site to complete the repairs. The original scope was completed. 5/2/2022 - Planning to begin week of 5/9 while tank is in service. Quote received and PO issued. 4/3/2022 - Walked down rivets with Justin Lamb. Planning to complete in May. Scope developed. Will need to coordinate with Operations on tank levels to get below rivets to reduce liquid head pressure. 3/1/2022 - Emergent project due to leaking rivets on tanks 3501, 3504, 3512, and 3513. Will develop scope in March and send out for quotes. Planning to complete when it gets warmer in May. | 2023-04-07 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Toledo | BETTO - BET TOLEDO TERMINAL |  | 77 | 0 |  |  | 20023 |  | Stine, Carlton | Stine, Carlton | N/A |  | 1 | 43063 |  | Stine, Carlton | JDE Child | Burnt Orange | 2022-03-01 | Int - Tanks
Toledo Station #2 Butane Booster Pump Motor Replacement | Item | Closed | MCAP | DS00000M2305 | Exempt | 2085413 | Gardner, Travis | West | 8. Canceled | Drawdown | Rotating Equipment |  |  |  | 0 |  | 0 | Green |  | 18645 | 18645 | -18645 |  |  | 18645 |  |  |  | Full | 18645 |  |  |  | No | Green |  |  |  | 2023-04-14 | 2023-03-31 | [21 empty] | 4/5/2023 - variance is due to project will be canceled. The new pump motor was purchased on Toledo Station #2 Butane Pump Repair project. Local labor was charged on the work order and that will remain on OPEX. 3/1/2023 - emergent project. work is alreadsy completed and will need reclassed. | 2023-04-06 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | DS - TOLEDO STATION |  |  | 0 |  |  |  |  | Posipanko, Dan | Gardner, Travis W. |  |  | 1 | 46647 |  | Gardner, Travis | Independent | Aqua | 2023-02-27
Toledo Station 12"300 Grove Ball Valve Replacement | Item | Open | MCAP | DS00000M2304 | Exempt | 2094861 | Gardner, Travis | West | 3. Active | Drawdown | Valves | 330 | 24000 |  | 24330.08 | 24000 | 330 | Yellow |  | 29193 | 29193 | -4863 |  |  | 29193 |  |  | 29193 | Full | 29193 | 330 | 24000 | 24330 | No | Green | 2023-04-01 | 2023-03-15 | 2023-03-15 | 2023-04-14 | 2023-04-14 | [5 empty] | 330.08 |  |  | 330 | Red |  |  | 24000 | [8 empty] | 5/4/2023 - vendor confirmed the valve is shipping out today. 4/4/2023 - waiting for delievery of valve. 3/1/2023 - emergent project to replace valve causing hot spots. Valve is 4 - 6 wk leadtime. | 2023-05-03 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | DS - TOLEDO STATION |  |  | 24330 |  |  |  |  | Oey, Alex | Gardner, Travis W. |  |  | 1 | 46761 |  | Gardner, Travis | Independent | Aqua | 2023-03-13
Toledo Station 150L (BP2) and Meter Run New Relief Valve Install | Item | Candidate | MCAP |  | Maintenance Framework |  | Roknich, Hunter | West | 2. Pending AFE |  | Transient/Surge Mitigation |  | 153000 |  | 153000 | 153000 | 0 | Green | 153000 |  | 153000 | 0 | [9 empty] | 153000 | 153000 | No | Green | 2023-06-01 |  |  |  | 2023-08-31 | [13 empty] | 14000 |  |  | 139000 | [8 empty] | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | TO - TOLEDO NORCO |  |  | 14000 | 139000 |  |  |  | DiPillo, Evan |  |  |  | 1 | 44159 |  | Gardner, Travis | Independent | Aqua | 2022-07-15 | Other Programs
Toledo Station 17T - New Control Valve Install | Item | Open | MCAP | DS00000M2301 | Project Framework | 2093356 | Henfling, Mike | West | 3. Active | Defined | Transient/Surge Mitigation | 25756 | 160000 |  | 185755.56 | 254884 | -69128 | Red | 230000 |  | 230000 | -44244 |  |  | 121830 | 108513 |  | 230343 | Full | 230343 | 25756 | 160000 | 185756 | No | Green | 2023-02-01 | 2023-03-02 | 2023-03-02 | 2023-07-01 | 2023-07-31 |  |  |  | 3200 | 56683.68 | -34128.12 | 10000 | 10000 | -44128 | Red |  | Other | 39000 | 63000 | 38000 | 15000 | 5000 |  |  |  |  | 5-2-23 - Full AFE in progress. Mech and Elec bids received, and POs in place to Bolt and Romanoff. Fabrication to begin in May, mechanical install in June. Automation/electrical tie-in late June or July. Finalized mode of operation of control valve in April (Upstream and downstream 200 psi PID loops for all movements). Control valve cost ($46k) hit to site code (DS) to be reclassed to project for April business. 4-4-23 - Phase AFE approved. Control valve has been delivered. Design Review completed 3/27. Plan to request formal mechanical and electrical bids in April for May install. Automation work in parallel - likely control valve will be installed but full open until Summer, when automation/determination of how to operate the new valve is finalized. 3-2-23 - AFE in progress for engineering and valve cost. Valve still to be delivered in March. Need to order 8-week pressure transmitter. Piping drawings in March, bids in April. May construction. Automation work in parallel. 2-2-23 - Site visit held 1/17. Plan to submit AFE in February for engineering and to reclass control valve PO, which is on order for March delivery. Meter will be replaced on a separate project. 1-3-23 - Control valve is on order for early March delivery. Will plan to start Engineering in February. Meter may be a long-lead item. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | DS - TOLEDO STATION |  | 59884 | 67872 | 58000 |  |  |  | DiPillo, Evan | Gardner, Travis W. |  |  | 1 | 44126 |  | Gardner, Travis | Independent | Aqua | 2022-07-13 | Other Programs
Toledo Station 8"600 GROVE BALL VALVE Replacement | Item | Open | MCAP | DS00000M2303 | Exempt | 2094192 | Gardner, Travis | West | 3. Active | Drawdown | Valves | 207 | 18000 |  | 18207 | 18207 | 0 | Green |  | 18000 | 18000 | 207 |  |  | 18735 |  |  | 18735 | Full | 18735 | 207 | 18000 | 18207 | No | Green | 2023-03-01 | 2023-03-07 | 2023-03-07 | 2023-04-14 | 2023-04-14 |  |  |  |  | 207 | [7 empty] | 18000 | [8 empty] | 5/4/2023 - vendor confirmed the valve is shipping out today. 4/4/2023 - waiting for delievery of valve. 3/1/2023 - emergent project to replace valve causing hot spots. Valve is 1 - 2 wk leadtime. | 2023-05-03 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | DS - TOLEDO STATION |  | 207 | 18000 |  |  |  |  | Oey, Alex | Gardner, Travis W. |  |  | 1 | 46657 |  | Gardner, Travis | Independent | Aqua | 2023-02-28
Toledo Station control room roof mounted AC unit. | Item | Candidate | MCAP |  | Exempt | 2094428 | Burns, Richard | West | 2. Pending AFE |  | West |  | 18000 |  | 18000 | 30000 | -12000 | Red | 30000 |  | 30000 | -12000 | [9 empty] | 18000 | 18000 | No | Green | 2023-06-01 |  |  |  | 2023-05-31 | [13 empty] | 18000 | [7 empty] | 5/1/23 - received quotes, cost lower than budget; still expect to complete in May, but getting the new vendor onboarded so I can issue a PO may push it into June. 4/3/23 - getting pricing from local contractors. 3/1/23 - no progress yet. | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | DS - TOLEDO STATION |  |  | 18000 |  |  |  |  | Gardner, Travis |  |  |  | 1 | 37107 |  | Guest, ProSight | Independent | Aqua | 2020-07-15 | Other Programs
Toledo Tankfarm Fence Replacement | Item | Open | MCAP | DS00000M2005 | Exempt |  | Gardner, Travis | West | 5. Deferred | Emergent | West |  | 35000 |  | 35000 | 35000 | 0 | Green |  |  |  | 35000 | [6 empty] | Full |  |  | 35000 | 35000 | No | Green | 2023-07-01 |  |  | 2020-10-01 | 2023-07-31 | [14 empty] | 35000 | [6 empty] | 09/10/2020 AFE has been rejected | 2020-09-10 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | DS - TOLEDO STATION |  |  | 0 | 35000 |  |  |  | Gardner, Travis | Koehler, Steven M. |  |  | 1 | 38459 |  | Kabaria, Erika | Independent | Aqua | 2020-09-01 | Other Programs
Toledo Technicians 475 field Communicator (2) | Item | Open | MCAP | DS00000M2204 | Maintenance Framework | 2022780 | Gardner, Travis | West | 7. Closed | Drawdown | West | 2780 |  |  | 2779.81 | 2780 | 0 | Green |  |  |  | 2780 |  |  | 28000 |  |  | 28000 | Full | 28000 | 28280 |  | 28280 | No | Green | 2022-12-01 | 2022-09-16 | 2022-09-16 | 2022-12-31 | 2022-12-31 |  |  | 2660.11 | 119.7 | [17 empty] | 1/4/2023 - Hart communicator recieved. 12/2/2022 - shipment date is still 12/9. 11/2/2022 - scheduled to ship on Dec. 9th from the factory. 10/3/2022 - PO created estimated arrival date is 12/23/2022. | 2023-01-04 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | TO - TOLEDO NORCO |  | 2780 | 0 |  |  | 25500 |  | Gardner, Travis | Gardner, Travis W. | N/A |  | 1 | 19768 |  | Guest, ProSight | Independent | Aqua | 2016-07-26 | Other Programs
Tuscola Fire Department Equipment Purchase and Donation | Item | Open | MEXP | BDLTU00E2201 | Maintenance Framework | 1970431 | Parker, Brian | West | 6. Operational | Unplanned | Fire Protection | 0 |  |  | 0 | 0 | 0 | Green |  |  |  | 0 |  |  | 71000 |  |  | 71000 | Full | 71000 | 66018 |  | 66018 | No | Green | 2022-04-01 | 2022-04-06 | 2022-04-06 | 2022-06-30 | 2022-12-30 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | Green | [11 empty] | 4/30/23 - re-accruing 25,992.98 for MES in Apr. 3/31/23 - re-accruing 25,992.98 for MES in Mar. 2/28/23 - re-accruing 25,992.98 for MES in Feb. 1/31/23 - re-accruing 25,992.98 for MES in Jan. 1/2/23 - accruing 25,922.98 for MES in Dec - just waiting on final invoice for payment. 12/2/22 - Var is due to MES not shipping the revised equipment to Tuscola FD. Requested shipping update from MES and no update yet. 10/29/22 - change order issued on Oct 28th - total cost of equipment dropped down to 25,922.98. 9/29/22 - no change to FCST at this time. Could be delivered in Oct or Nov. 9/1/22 - moving this FCST out to Nov - MES is horrible on providing an update on when this material will be delivered to the Tuscola FD. 7/30/22 - var is due to Fire Dept delay in finalizing their nozzles - according ot MES (Trent Short) this material will now be delivered in Aug. 7/3/22 - received email after FCST was locked for Jun that material should ship in Jul. 5/31/22 - expect delivery of equipment in Jun. 5/2/22 - check for donation to Tuscola FD was issued in Apr for 40,000. PO to MES was issued on 4/11/22 and received confirmation email on 4/28 that everything is ordered. Moving this FCST out to Jun. 4/2/22 - added project to OPPM at request of DLC to obtain visibility in extra costs associated with termination of utilities at BDL Tuscola Facility. This is the MEXP portion of the larger project. | 2023-04-30 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Central-Illinois | BDLTU - TUSCOLA - BDL |  | 0 | 0 |  |  | 66018 |  | Jakubowski, Gregory | Ownby, Daniel G. |  |  | 1 | 43335 |  | Guest, ProSight | Independent | Aqua | 2022-04-02 | Other Programs
Tuscola Rail Rack Hose Handlers 2023 | Item | Candidate | MCAP |  | Exempt |  | Smith, Kyle | West | 2. Pending AFE |  | West |  | 70000 |  | 70000 | 70000 | 0 | Green | 70000 |  | 70000 | 0 | [9 empty] | 70000 | 70000 | No | Green | 2023-08-01 |  |  |  | 2023-06-30 | [15 empty] | 70000 | [5 empty] | 4/28/23 Working with contractors to get quotes | 2023-04-28 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Central-Illinois | BDLTU - TUSCOLA - BDL |  |  | 0 | 70000 |  |  |  | Gardner, Travis |  |  |  | 1 | 39703 |  | Guest, ProSight | Independent | Aqua | 2021-04-09 | Other Programs
Tuscola Termination of Utilities | Item | Open | MCAP | BDLTU00M2201 | Maintenance Framework | 1889170 | Parker, Brian | West | 6. Operational | Emergent | West | 182264 | -17353 |  | 164910.79 | 153004 | 11907 | Yellow | 109000 |  | 109000 | 55911 |  |  | 159000 | 2177000 |  | 2336000 | Phase | 2336000 | 2823528 | -17353 | 2806175 | No | Green | 2022-03-01 | 2022-03-17 | 2022-03-17 | 2022-08-31 | 2023-02-03 |  |  | 143531 | -28177.8 | -6076.56 | 72987.15 | 63400 | 63400 | 9587 | Red |  | Forecasting | 19830 | 2320 | -39503 | [6 empty] | 5/1/23 - Var is due to Badger Daylighting invoices exceeding budget amount - just processed invoice for Flare Industries - need to cancel remaining open PO amount in JDE. May FCST is for Dunn. Re-accruing 22,324 for Bodine Electric of Decatur and 740 for TAS. 4/3/23 - var is due to dropping Waste Management accrual for Mar. 3/2/23 - var is due to several PO's to Bodine Electric coming in under the full PO amounts (savings). 2/3/23 - var is due to additional costs to fully insulate the 2" and 1" vapor lines from new fuel gas connection to the superheater and flare pilot lines that are above grade. Also have the flash fire costs hitting in Jan that will be re-classed once all invoices have been paid. The negative amount in May is the flash fire repair cost that need to be re-classed to the casualty loss work order. CWIP and Int charges have exceeded the original budget amount. Majority of work is fully operational now. Just have a few trailing items to complete once the weather breaks. Should have the Supplemental AFE submitted in Feb. 1/2/23 - var is due to completing insulation work ahead of schedule. Apache is wrapping up the insulation and outer covering. Working to replace two 1" ball valves and repaint piping damaged by flash fire. Re-working heat trace in this area and replacing insulation after new coating has been applied. Bringing in forced air system to heat the two temp propane tanks to keep pressure above superheater minimum requirement. 12/2/22 - Var is due to completing work ahead of schedule. Going for another test of the tank now after sealing leaks for a 4th attempt. 2" vapor line has been painted and Bodine is installing the two new circuits for the heat tracing and will start installing heat trace cable this month with insulation to follow on 12/19. Remaining soil spoils to be removed this month and Jersey Barriers will be set 12/15. Expected completion of heat trace is 12/15 on water lines. Need to submit ECO forapproval for new heat trace and insulation of 2" vapor line. 11/1/22 - tank is upas of Oct 20th - Tarsco will be back on-site Nov 7th to start hydrotest with insulation installation to follow after successful hydrotest. We have two temp. propane tanks feedingthe superheater/flare pilot light until we can obtain proposals for heat tracing 2" vapor line and possibly installing a vaporizer near the superheater building. 10/4/22 - Looks like Tarsco will be delayed about 4-5 days due an issue at their coating plant. Bodine should complete pre work for new electrical to water tank. Meade andEIEC completing electrical cutover this week. New injectors and tie in of propane line will occur next week. 9/1/22 - Var is due to receiving progressive billing from Tarsco for new fire water tank ahead of schedule. Accruing 15,440 for TAS, 6,400 for Pugh Pipeline Services, 142,432 for Tarsco, 15,500 for Acuren Inspection, 1,450 for Dales Lawn Grooming, 19,200 for Badger Daylighting, 3,000 for United Rentals, and 40,000 for Meade. Currently installing thenew 2" water line, excavating for new septic system, and using guided wave to inspect 2" line we plan to use. New EAC (minus contingency) is 2,200,000. 8/10/22 - Mar 2023 FCST is receipt and installation of Maxon valve for superheater. 8/1/22 - var is due to Meade completing more work than forecasted, re-accruing 14,210 for ESDC, accruing 7,500 for Pugh Pipeline and 75,000 for Meade.- conducted PHA on 8/1 and have a couple of action items to complete for the piping mods. Adjusted the remaining FCST based on recently issued PO's and received proposals.No contingency in FCST. 7/3/22 - Var is due to receiving inv for geotechnical work early. Re-accruing 17,527 for ESDC. 5/31/22 - May var is due to 2 week approval delay for surveyor to access site for new water line and overhead power lines, re-accruing 17,527.50 for ESDC and 3,500 for Blood Hound. New accrual of 5,000 for TAS. 5/19/22 - moved FCST around to start construction in early July with water tank construction to start in Nov. 5/13/22 - entered req. for purchase of 500 kVA transformer - has an 8 week lead time - should see this sometime around Jul 8th. 5/3/22 - Apr var is due to issues getting an ISN approved driller on-site to complete the soil borings - accruing 5,000 for TAS, 25,000 for ESDC, 3,500 for Blood Hound, 1,291.75 for GHD. New Eaton Switchboard to arrive in mid-June, still trying to get vendor added to purchase transformer. 4/7/22 - var for Mar is re-class of costs from local OPEX WO, payment of Meade and Destree Consulting invoice, and accrual for ESDC and TAS. 4/1/22 - Phase I approved for 159,000 to start the Eng&Design for new fire water tank and forother utilities. 10/20/21 - added project to OPPM to maintain visibility. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Central-Illinois | BDLTU - TUSCOLA - BDL |  | 109277 | 95137 | -39503 |  | 2641264 |  | Gardner, Travis | Ownby, Daniel G. |  |  | 1 | 42477 |  | Guest, ProSight | Independent | Aqua | 2021-11-19 | Other Programs
UB760AR Incoming Headgate | Item | Open | MCAP | UB760ARM2202 | Exempt |  | Scott, Cory | West | 3. Active | Defined | Atmospheric Corrosion |  | 26000 |  | 26000 | 26000 | 0 | Green | 26000 |  | 26000 | 0 |  |  | 30000 |  |  |  | Full | 30000 |  | 26000 | 26000 | No | Green | 2023-06-01 |  |  | 2022-08-26 | 2023-09-30 | [13 empty] | 26000 | [7 empty] | 4/18/2023 - Awaiting capital projects. 3/27/2023 - Project being discussed to have capital projects raise valve and handle on their end per Todd Smith. 6/16/22- Deferral to 2023 - preventative, no active concerns per program owner. 6/2/2022 - Produce AFE and submit for approval. 4/26/2022 - Vance and Associates is selected contractor. Vance will perform the project for $23,298.00. 4/8/2022 - Cathodic Protection pre bid meeting 4/6/2022 - Coupa Bid Event Program - Registration and Contractors Status's shown. 3/31/2022 - Talked to Adam Scannell. These projects are in the bid event process. Once the bids are in, I will start the AFE and Project Process. 3/4/2022 - CP Painting meeting took place to discuss scheduling for bids. | 2023-05-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Eastern Iowa | UB760AR - DUBUQUE VLV - CEDER RAPIDS TER |  |  | 26000 |  |  |  |  | Geib, Rob | Smith, Todd W. |  |  | 1 | 41151 |  | Guest, ProSight | Independent | Aqua | 2021-08-09 | Int - Planned Corr & FI
UB760HH - Anomaly Digs From 2022 Tool Run | Item | Open | MCAP | AR760HHM2302 | Maintenance Framework | 2076599 | Scott, Cory | West | 6. Operational | Defined | Pipeline Digs | 54619 | -2088 |  | 52531.17 | 51691 | 840 | Yellow |  |  |  | 52531 |  |  | 85474 |  |  | 85474 | Full | 85474 | 54619 | -2088 | 52531 | No | Green | 2023-02-01 | 2023-01-22 | 2023-01-22 | 2023-02-25 | 2023-03-03 |  |  |  | 82407.79 | -30716.93 | 2928.31 |  |  | 2928 | Red |  |  | -2088 | [8 empty] | 5.8.23 - $-2,088 forecast in May due to MEXP flip to AR760HHE2302 (AS) 4/19/2023 - Approved waste management invoice for asbestos pipe coating for $1,100.00 4/10/2023 - Job book completed and approved for archive. 4.6.23 - -$33,3351 in March due to MEXP Flip to AR760HHE2302 (AS) 3/13/2023 - WDR submitted for asbestos coating from pipe. 3/10/2023 - Change order for 4K in final billing from Vance and Associates. Dig Site Data and JDE Uploads completed for project. 3/7/2023 - Awaiting final bill from Vance and Associates, Cleveland Integrity, and ROW. Should total 82K for final total. 2/28/2023 - Change order from $2,400 as Acuren invoice came in higher than expected. 2/15/2023 - DOT 60 Dig completed. The other will be finished by 2/22/2023. Crew will mobilize to next dig project on IM760UG. 2/13/2023 - Project kicked off. 2/2/2023 - Stake holder meeting held. 1/30/2023 - OQ's uploaded to ISNetworld. Stake holder meeting to be held on 2/2/2023. 1/27/2023 - AFE fully approved. Work orders for project made in JDE. 1/25/2023 - Site Safety Plan approved by Buckeye HSSE. 1/17/2023 - AFE submitted to remedy force. | 2023-05-08 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Eastern Iowa | AR760HH - CEDER RAPIDS TO HARPER STA |  | 51691 | 840 |  |  |  |  | Bartal, Nick | Smith, Todd W. |  |  | 1 | 46460 |  | Guest, ProSight | Independent | Aqua | 2023-01-13 | Int- Planned Digs
UC762OI North Raccoon River BV Recoat | Item | Open | MEXP | UC762OIE2301 | Exempt | 2085555 | Scott, Cory | West | 6. Operational | Defined | Atmospheric Corrosion | 18672 |  |  | 18672.25 | 20000 | -1328 | Yellow | 10001 | 10000 | 20001 | -1329 |  |  | 19659 |  |  | 19659 | Full | 19659 | 18672 |  | 18672 | No | Green | 2023-04-01 | 2023-02-22 | 2023-02-22 | 2023-05-24 | 2023-04-30 | [5 empty] | 18672.25 | 20000 | 20000 | -1328 | Yellow | [11 empty] | 5/5/2023 - Cleveland invoice came in at $3,161.11. 5/2/2023 - Awaiting final invoice from Cleveland Integrity. 4/20/2023 - Vance and Associates billed $14,672.00. 4/18/2023 - Project completed on 4/12/2023. Final billing should come in just barely under budget. 3/30/2023 - Stakeholder meeting held. Project to start 4/11/2023. 3/27/2023 - Inspector request placed for project. Stakeholder meeting to take place on 3/30/2023. 3/20/2023 - PO placed for Vance and Associates for 14K. Forecast updated to 20K to reflect AFE. 1/24/2023 - AFE submitted for 20K. | 2023-05-05 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Sugar Creek | UC762OI - CRESTION STA TO DES MOINES TER |  |  | 18672 |  |  |  |  | Geib, Rob | Smith, Todd W. |  |  | 1 | 45449 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
UG761UD Mecca Valve Site Recoat | Item | Open | MEXP | UG761UDE2301 | Exempt | 2085562 | Scott, Cory | West | 6. Operational | Defined | Atmospheric Corrosion | 15761 |  |  | 15761.35 | 17000 | -1239 | Yellow | 11001 |  | 11001 | 4760 |  |  | 16457 |  |  | 16457 | Full | 16457 | 15761 |  | 15761 | No | Green | 2023-04-01 | 2023-02-22 | 2023-02-22 | 2023-05-31 | 2023-04-30 | [5 empty] | 15761.35 | 17000 | 17000 | -1239 | Yellow | [11 empty] | 5/5/2023 - Invoice billed at $3100.00. Project completion price at 15K. 5/2/2023 - Awaiting final invoice from Cleveland integrity. 4/21/2023 - Invoice approved. Awaiting Cleveland Integrity billing. 4/12/2023 - Project completed. Should invoice right at budget amount. 3/30/2023 - Stakeholder meeting held. Project to start on 4/11/2023. 3/29/2023 - PO Placed for project. 3/27/2023 - Stake holder meeting taking place 3/30/2023. Inspector Request placed. 3/20/2023 - PO placed for Vance and Associates (Contractor) 1/24/2023 - AFE submitted. Vance estimated 11K then inspection was added resulting in 17k after everything with contingency. | 2023-05-05 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Sugar Creek | UG761UD - SUGAR CREEK TERM - MUDDY CREEK |  |  | 15761 |  |  |  |  | Geib, Rob | Smith, Todd W. |  |  | 1 | 45450 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
UR761XX MP 109 Exposure Repair | Item | Open | MEXP | UR761XXE2301 | Maintenance Framework | 2094018 | Rohr, Travis | West | 6. Operational | Drawdown | Exposed Pipe Evaluation & Remediation | 12175 |  |  | 12175.31 | 12175 | 0 | Green |  |  |  | 12175 |  |  | 12500 |  |  | 12500 | Full | 12500 | 12175 |  | 12175 | No | Green | 2023-03-01 | 2023-03-06 | 2023-03-06 | 2023-04-30 | 2023-03-08 |  |  |  |  | 12175.31 | [16 empty] | 5/2/23 Completed. 4/4/23 Work completed, no more spend expected. 3/8/23 Work completed onsite today. Waiting on invoice. 3/6/23 Work scheduled ford Wednesday. | 2023-05-02 | Schultz, Amy |  | West | Pipelines and Terminals | Pipeline Integrity |  | Sugar Creek | UR761XX - BURLINGTION JCT TO IA S/L |  | 12175 | 0 |  |  |  |  | Hurley, Brian | Shook, Mark B. | N/A |  | 1 | 46697 |  | Hurley, Brian | JDE Child | Burnt Orange | 2023-03-03
UT534YT - Cutout of features in casing | Item | Open | MCAP |  | Maintenance Framework |  | Bost, Jason | West | 2. Pending AFE | Defined | Pipeline Digs |  | 900000 |  | 900000 | 900000 | 0 | Green | 900000 |  | 900000 | 0 | [9 empty] | 900000 | 900000 | No | Green | 2023-08-01 |  |  |  | 2023-11-30 | [15 empty] | 150000 | 275000 | 275000 | 200000 |  |  | 5/1/23 - Initial discussions with Cenovus were positive, and we are moving forward with using one of their existing casings. ROW working on an easement document and Commercial finalizing compensation for their casing. 4/3/23 - Sale of refinery finalized in March. Matt H. opened discussions with Cenovus, but still awaiting response. 1/31/23 - According to Matt Holecek, the refinery sale has not closed and is hearing late February as earliest potential closure. 11/1/22 - No change, discussions will pick back up in Q1 2023. 10/1/22 - BP is in the process of selling the refinery to Cenovus. They prefer Cenovus to handle discussions moving forward. Discussions to open back up in Q1 2023. 9/1/22 - Refinery turnaround caused significant delayed response by BP. Expecting response in Sept. 8/1/22 - No Change. 7/5/22 - Still awaiting response from BP if scope of work needs adjusted. 6/1/22 - Have been in discussion with BP's commercial group regarding the use of an empty casing to reroute our line. They are reviewing our SOW to make any final adjustments to their quote. 5/3/22 - Awaiting response from BP's commercial and technical group to develop full scope. 4/4/22 - PM and Commercial group having discussions with BP to align scope within the refinery. 3/2/22 - Beginning E&D in March/April 2022. 2/2/22 - No Change 1/3/22 - No Change | 2023-05-02 |  |  | West | Pipelines and Terminals | Integrity |  | Toledo | UT534YT - TOLEDO STA TO WEST TOLEDO TERM |  |  | 0 | 425000 | 475000 |  |  | Bartal, Nick |  |  |  | 1 | 40730 |  | Administrator, System | Independent | Aqua | 2021-07-23 | Int - Planned Cutouts
UT534YT - DIG SHEETS (40) | Item | Open | MCAP | UT534YTM2101 | Exempt | 1845330 | Bost, Jason | West | 6. Operational | Drawdown | Pipeline Digs | 363248 | -78015 |  | 285232.71 | 161642 | 123591 | Red |  |  |  | 285233 |  |  | 1121000 |  |  | 1121000 | Full | 1121000 | 1318093 | -78015 | 1240078 | Yes | Red | 2021-05-01 | 2021-06-15 | 2021-06-15 | 2021-09-17 | 2023-04-21 |  |  | 5686.02 | 5206.31 | 84986.31 | 267369.07 | 65763 | 65763 | 201606 | Red |  | Engineering or Scope Change | -78015 | [8 empty] | 5.8.23 - $-78,015 forecasted in May due to MEXP flip to UT534YTE2103 (AS) 5/1/23 - Dig complete. Variance is caused by delays by railroad once on site. Field findings required additional hand digging/verification to allow for mechanical excavation. Schedule extended by 2 weeks to follow RR guidelines. 4/3/23 - Received approval to mobilize on 3/20. Variance is Roberts invoice and Liberty Sales for Atlas repair materials. 3/1/23 - Variance is TAS invoice. TAS has sent final drawings for scheduling approval from the railroad. Expecting scheduling approval in coming weeks. 1/31/23 - Variance is a TAS invoice. 1/31/23 - Awaiting final schedule from RR, targeting late February.1/4/23 - Variance is TAS invoices ($2,166 & $851). 11/1/22 - Variance is CSX invoices. Application for scheduling flagmen approved. 10/11/2022 - Path forward wit the RR. Final dig expected to be completed within 2022. 8/1/22 - No Change. 7/5/22 - No Change. 6/1/22 - No Change. 5/3/22 - Last dig awaiting CSX and NS railroad approval. 4/4/22 - Ann Arbor dig complete. Last dig still awaiting CSX and NS approval. 3/2/22 - Received approval from Ann Arbor to mobilize on 3/7. Only dig remaining will be along CSX once we receive RR approval. 2/2/22 - Awaiting cooperation from NS. 1/3/22 - Still awaiting RR cooperation. 12/1/21 - Awaiting Ann Arbor, CSX, and NS to schedule flagmen for the digs. Permits are approved, waiting on RR. 11/1/21 - CSX permit received, awaiting flagmen schedule. Still waiting on Ann Arbor permit. 10/1/21 - Railroad permits response expected by early Nov. 9/1/21 - Digs in the refinery will be completed by 9/3. After that, only 2 railroad dig sites remain. 8/2/21 - Last set of digs in the refinery scheduled for 8/16/21. F-2802 thru F-2881 moved to a 2022 cutout project per Nick B. Railroad dig sites still awaiting permits. 7/1/21 - Currently completed 5 dig sites. Crew mobbed to Inland Station/refinery on 6/30/21. 6/2/21 - DOT-60 day digs complete. Moving through digs BPL- Other digs outside of refinery. RR permits expected late summer. 5/3/21 - Expected start date for DOT-60 digs is 5/6/21, due 5/20/21. | 2023-05-08 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Toledo | UT534YT - TOLEDO STA TO WEST TOLEDO TERM |  | 95879 | 189354 |  |  | 145151 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 39725 |  | Administrator, System | Independent | Aqua | 2021-04-13 | Int- Planned Digs
UT534YT CHRYSLER DRIVE RECT AC SERVICE REPAIR | Item | Open | MEXP | UT534YTE2302 | Maintenance Framework | 2095206 | Brown, Jeff | West | 6. Operational | Drawdown | Cathodic Protection | 3500 |  |  | 3500 | 3500 | 0 | Green |  |  |  | 3500 |  |  | 3500 |  |  | 3500 | Full | 3500 | 3500 |  | 3500 | No | Green | 2023-04-01 | 2023-03-17 | 2023-03-17 | 2023-05-01 | 2023-05-01 | [5 empty] | 3500 | 3500 | 3500 | 0 | Green | [11 empty] | 5-1-23 Project Complete and Operational. Waiting for contractor to submit invoice. 4-3-23 CONTRACTOR FILED FOR ELECTRIC PERMIT FROM CITY | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Toledo | UT534YT - TOLEDO STA TO WEST TOLEDO TERM |  |  | 3500 |  |  |  |  | Geib, Rob | Geib, Robert | N/A |  | 1 | 46807 |  | Schultz, Amy | JDE Child | Burnt Orange | 2023-03-17
Warren Terminal (BETYO) Tank 10 - OOS API 653 Insp | Item | Open | MCAP | BETYO00M2301 | Maintenance Framework | 2084430 | Roknich, Hunter | West | 3. Active | Defined | Tanks | 33032 | 25000 |  | 58032 | 106000 | -47968 | Red | 107398 |  | 107398 | -49366 |  |  | 97671 |  |  | 97671 | Phase | 97671 | 33032 | 25000 | 58032 | No | Green | 2023-04-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-05-31 | [5 empty] | 33032 | 11000 | 11000 | 22032 | Red |  |  |  | 25000 | [7 empty] | 5/2/2023 - OOS cleaning and inspection complete. Working the tank integrity to determine path forward for tank as it is not used for product service any more. 4/4/2023 - OOS to begin 4/25/2023. Minimal downtime expected. This tank is currently only being used as a slop tank. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | North East Ohio | BETYO - BET WARREN |  |  | 58032 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44892 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Warren Terminal (BETYO) Tank 16 - OOS API 653 Insp | Item | Open | MCAP | BETYO00M2302 | Maintenance Framework | 2084421 | Roknich, Hunter | West | 3. Active | Defined | Tanks | 34128 | 10000 |  | 44128 | 20000 | 24128 | Red | 20000 |  | 20000 | 24128 |  |  | 23701 |  |  | 23701 | Phase | 23701 | 34128 | 10000 | 44128 | No | Green | 2023-04-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-04-30 | [5 empty] | 34128 | 10000 | 10000 | 24128 | Red |  |  |  | 10000 | [7 empty] | 5/2/2023 - OOS cleaning and inspection complete. Working the tank integrity to determine path forward for tank as it is not used for product service any more. 4/4/2023 - This tank is already OOS. Cleaning to begin 4/25/2023. STI inspection to follow and plan to keep tank OOS | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | North East Ohio | BETYO - BET WARREN |  |  | 44128 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44893 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Water Hammer Project - BETAD Taylor East | Item | Open | MEXP | BETAD00E2301 | Maintenance Framework | 2085539 | Parker, Brian | West | 6. Operational | Drawdown | West |  | 3601 |  | 3601 | 3601 | 0 | Green |  | 4000 | 4000 | -399 |  |  | 4000 |  |  | 4000 | Full | 4000 |  | 3601 | 3601 | No | Green | 2023-05-01 | 2023-02-22 | 2023-02-22 | 2023-05-31 | 2023-05-02 | [12 empty] | 3600 | [6 empty] | 1 |  | 5/2/23 - received quote from Macomb Group - need to create new JDE Std Part Numbers, order material for warehouse stock, and create 2024 proposed project in OPPM. Can close this out after invoice has been approved. 5/1/23 - Diamond Z sent email to DFT to size the check valves we need on 4/18 - just waiting on a reply and quotes at this point. 4/1/23 - Diamond Z working on site visit date to gather details. 2/28/23 - issued PO to Diamond Z on Feb 24th. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Terminals | BETAD - BET TAYLOR EAST TERMINAL |  |  | 3600 |  | 1 |  |  | Gardner, Travis | Gardner, Travis W. | N/A |  | 1 | 46626 |  | Parker, Brian | JDE Child | Burnt Orange | 2023-02-22
Water Hammer Project - BETAI Granger | Item | Open | MCAP | BETAI00M2302 | Exempt | 2112000 | Parker, Brian | West | 3. Active | Drawdown | Truck Racks |  | 17500 |  | 17500 | 21001 | -3501 | Red |  | 23633 | 23633 | -6133 |  |  | 23633 |  |  | 23633 | Full | 23633 |  | 17500 | 17500 | No | Green | 2023-05-01 | 2023-04-20 | 2023-04-20 | 2023-05-31 | 2023-06-30 | [12 empty] | 2500 | 15000 | [7 empty] | 5/3/23 - looks like TSV's could arrive sometime around May 19th, should have PO issued today - leaving FCST in Jun for install. Need to get Inventory Issue completed in the month the DFT's are installed. 5/1/23 - no change to status - just waiting to hear back from Dennis on the Mercer TSV lead time so I can adjust the FCST. 4/21/23 - AFE was approved today, Dennis will order the Mercer TSV's and get this scheduled. Moving the FCST out to June until I hear back on the TSV lead times. The DFT check valves are sitting in inventory. 4/14/23 - submitted AFE to workflow for approval routing. Moving FCST up to May execution. 3/28/23 - moving this FCST out to Oct/Nov until I hear back on approval for 2023. 3/3/23 - created project in OPPM and sent email to Travis requesting drawdown funds for this project. This was forwarded to Mike and Nick for their approval. AFE is ready to go. Added what I expect to spend to the Apr/May FCST. | 2023-05-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Michiana | BETAI - BET GRANGER |  |  | 17500 |  |  |  |  | Younce, Michael | Gardner, Travis W. |  |  | 1 | 46699 |  | Parker, Brian | Independent | Aqua | 2023-03-03
Water Hammer Project - BETON Canton Terminal | Item | Open | MEXP | BETON00E2301 | Maintenance Framework | 2085543 | Parker, Brian | West | 6. Operational | Drawdown | West | 3437 |  |  | 3437.43 | 3501 | -64 | Yellow |  | 4000 | 4000 | -563 |  |  | 4000 |  |  | 4000 | Full | 4000 | 3437 |  | 3437 | No | Green | 2023-04-01 | 2023-02-22 | 2023-02-22 | 2023-05-31 | 2023-04-28 | [5 empty] | 3437.43 |  |  | 3437 | Red | [11 empty] | 4/29/23 - have the sizing data and quote to purchase the two 4" ALC Models - plan to get these purchased for inventory in May and create project for 2024 budget to install. 4/1/23 - Diamond Z was on-site Mar 9th to gather details and have check valve sizing info back from DFT. Will summarize all location data into one email to management and obtain approval to get check valves purchased for inventory in 2023. 2/28/23 - issued PO to Diamond Z on Feb 24th. | 2023-04-29 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | North East Ohio | BETON - BET CANTON |  |  | 3437 |  |  |  |  | Gardner, Travis | Gardner, Travis W. | N/A |  | 1 | 46629 |  | Parker, Brian | JDE Child | Burnt Orange | 2023-02-22
Water Hammer Project - BETWD Detroit Terminal | Item | Open | MEXP | BETWD00E2301 | Maintenance Framework | 2085541 | Parker, Brian | West | 6. Operational | Drawdown | West |  | 3601 |  | 3601 | 3601 | 0 | Green |  |  |  | 3601 |  |  | 4000 |  |  | 4000 | Full | 4000 |  | 3601 | 3601 | No | Green | 2023-05-01 | 2023-02-22 | 2023-02-22 | 2023-05-31 | 2023-04-19 | [12 empty] | 3600 | [6 empty] | 1 |  | 5/1/23 - received quote back from Macomb Group and lead time is 4 weeks. Plan to get new JDE Std Part Numbers created in May and get Stock PO's issued in May so we are ready for construction in late 2023 or in 2024, depending on budget availability. 4/1/23 - Diamond Z working to schedule a site visit. 2/28/23 - issued PO to Diamond Z on Feb 24th. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Terminals | BETWD - DETROIT BET TERMINAL |  |  | 3600 |  | 1 |  |  | Gardner, Travis | Gardner, Travis W. | N/A |  | 1 | 46628 |  | Parker, Brian | JDE Child | Burnt Orange | 2023-02-22
Water Hammer Project - BETWF Flint Terminal | Item | Open | MEXP | BETWF00E2302 | Maintenance Framework | 2085540 | Parker, Brian | West | 6. Operational | Drawdown | West | 1688 | 1903 |  | 3590.5 | 3601 | -11 | Yellow |  |  |  | 3591 |  |  | 4000 |  |  | 4000 | Full | 4000 | 1688 | 1903 | 3591 | No | Green | 2023-04-01 | 2023-02-22 | 2023-02-22 | 2023-05-31 | 2023-04-25 | [5 empty] | 1687.5 |  |  | 1688 | Red |  |  | 1903 | [8 empty] | 5/1/23 - should receive one more final invoice from Diamond Z - have the quotes for the new DFT check valves and should have these purchased for inventory in May - will create project for 2024 budget for install. 4/1/23 - Diamond Z was on-site Mar 20th to gather details and have check valve sizing info back from DFT. Will summarize all location data into one email to management and obtain approval to get check valves purchased for inventory in 2023. 2/28/23 - issued PO to Diamond Z on Feb 24th. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Terminals | BETWF - BET FLINT TERMINAL |  |  | 3591 |  |  |  |  | Gardner, Travis | Gardner, Travis W. | N/A |  | 1 | 46627 |  | Parker, Brian | JDE Child | Burnt Orange | 2023-02-22
Wayne Station 209L Panametrics Meter Replacement | Item | Open | MCAP | WW00000M2201 | Maintenance Framework | 1979450 | Henfling, Mike | West | 7. Closed | Defined | Leak Detection | 2536 |  | 0 | 2536.1 | 2536 | 0 | Green |  |  |  | 2536 |  |  | 222000 | 153000 |  | 375000 | Phase | 375000 | 385950 | 0 | 385950 | No | Green | 2022-05-01 | 2022-05-02 | 2022-05-02 | 2022-10-01 | 2022-12-06 |  |  | 2217.13 | 318.97 | [16 empty] | 0 | 4-4-23 - Project Ready for Close 3-2-23 - Project Ready for Close 2-2-23 - Project operational, job book completed in January. Awaiting one final invoice and then will close project 1-3-23 - Site visit with Krohne and Buckeye tech went well on 12/6. All meters are now working and restored in LeakWarn. Job Book and final invoices to come in, then will close project in February. 12-5-22 - Service visit with Krohne scheduled 12/6 to look at issue with meter outputs being variable. Job Book to be complete in December 11-2-22 - Third and final meter run re-installed in early October. All mechanical work complete. Touch-up paint in early November. Technicians to finalize automation in November. As-built/JDE/Closeout in December. 10-3-22 - Krohne meters delivered and installed on two of the three lines end of September. Piping needs re-fabricated on the third line due to mis-measurement; this will be installed on 10/6. Final automation work planned for November due to technician availability. 9-1-22 - (3) Krohne meters delayed 2 weeks, so missed August forecast. Meters to ship 9/2 from Europe and 9/9 from USA factory. Shop fab to continue for 9/27 and 9/28 planned installation during pipeline outage. 8-1-22 - (3) Krohne meters still to be shipped 8-26. Mechanical contractor selected (Consolidated). Materials to be delivered early August and small shop work to begin. Still planning September install. Full AFE to be submitted early August. 7-5-22 - (3) Krohne meters to be shipped 8-26. Valves were delivered on 7/1. Mechanical bid event opened on 6/30, with bids due 7/20. Full AFE to be submitted early August for install tentative 9/19. Electrical bids being solicited early July, with one bid already received. 6-1-22 - (3) Krohne meters on order late May, likely delivery mid-August. Bid event for valves completed 6/1 with (6) valves to be ordered for July delivery. Will bid mechanical and electrical work mid-June. Still planning for August/September construction. 5-4-22 - (3) meter run projects at WW combined into (1) under WW00000M2201. Phase AFE approved 5/2/22. Combined forecast into this project. Plan to order (3) Krohne meters in early May with 12-week lead time. Plan to bid work in May for August/September construction. 4-4-22 - Site visit and stakeholder meeting held in March. Plan to submit phase AFE this week to combine all (3) meter projects in Wayne and to order long-lead Krohne 3-beam meters and flow conditioners. Will plan to bid work in April/May for July/August construction. 3-29-22 JY - Funds added from leak detection engineering. 3-2-22 - Site visit planned for 3/9. Budgetary cost for Krohne 3-beam meter is $21k plus piping modifications necessary.12-16 week lead time, pushing forecast to August. Also looking into a FMC 4c Ultra meter which may have shorter lead time. 2-2-22 - No change to forecast. | 2023-04-04 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | WW - WAYNE STATION |  | 2536 | 0 |  |  | 383414 |  | Guenther, Steve | Yezik, James T., II |  |  | 1 | 41974 |  | Guest, ProSight | Independent | Aqua | 2021-08-23 | Leak Detection
Wayne Station Replace WS209WW Scraper Bypass Valve | Item | Open | MCAP | WS209WWM2301 | Exempt | 2073940 | Gardner, Travis | West | 6. Operational | Emergent | Valves | 21210 |  |  | 21210.45 | 21210 | 0 | Green | 21000 |  | 21000 | 210 |  |  | 30038 |  |  | 30038 | Full | 30038 | 21210 |  | 21210 | No | Green | 2023-01-01 | 2023-01-10 | 2023-01-10 | 2023-01-31 | 2023-01-20 |  |  | 17313.53 | 3729.11 | 167.81 | [16 empty] | 3/1/2023 - recieved final invoice from Holly. 2/3/2023 - work completed variance is savings. 1/31/2023 - emergent project funded from Dearborn Station Replace MOV's 2023. | 2023-03-01 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Pipeline | WS209WW - WOODHAVEN TO WAYNE |  | 21210 | 0 |  |  |  |  | Oey, Alex | Gardner, Travis W. |  |  | 1 | 46435 |  | Gardner, Travis | Independent | Aqua | 2023-01-06 | Other Programs
Wayne Station Unit 2 - Unit 2 Pump Overhaul | Item | Open | MCAP | WW00000M2202 | Maintenance Framework | 1970916 | Gardner, Travis | West | 7. Closed | Drawdown | Rotating Equipment | -13007 |  |  | -13007.42 |  | -13007 | Red |  |  |  | -13007 |  |  | 130000 |  |  | 130000 | Full | 130000 | 90096 |  | 90096 | No | Green | 2022-09-01 | 2022-07-08 | 2022-07-08 | 2022-09-16 | 2022-11-30 | [5 empty] | -13007.42 |  |  | -13007 | Red | [11 empty] | 11/1/2022 - 14k variance is labor associated with reinstalling pump. 10/3/2022 - pump repairs completed and invoice approved in ADP. 9/1/2022 - Kennedy just let the OM know today that the pump will be delivered on 09/12/22. Variance is due to vendor repair schedule delay. 8/3/2022 - Om is working with Kennedy on install date. 7/5/2022 - repair estimates recieved. getting ready to submit AFE | 2022-11-01 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Pipeline | WW - WAYNE STATION |  |  | -13007 |  |  | 103104 |  | Posipanko, Dan | Posipanko, Daniel A. |  |  | 1 | 43701 |  | Gardner, Travis | Independent | Aqua | 2022-05-09 | Other Programs
Wayne Unit 4 & 6 Control Valve | Item | Candidate | MCAP |  | Maintenance Framework |  | Roknich, Hunter | West | 2. Pending AFE | Defined | Valves |  | 55000 |  | 55000 | 55000 | 0 | Green | 55000 |  | 55000 | 0 | [9 empty] | 110000 | 110000 | No | Green | 2023-10-01 |  |  |  | 2023-04-30 | [17 empty] | 55000 |  |  |  | 10/11/2022 - working with operations and HPC to get appropriate REXA actuator quote 8/2/2022 - reforecasted to 2023 and moved to DD. Working with E&D for analysis and HPC for quote on actuator. | 2022-10-11 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Pipeline | WW - WAYNE STATION |  |  | 0 |  | 55000 |  |  | Oey, Alex |  |  |  | 1 | 37796 |  | Guest, ProSight | Independent | Aqua | 2020-08-12 | Other Programs
WB - DOT COATING REPAIR | Item | Candidate | MEXP |  | Exempt |  | Brown, Jeff | West | 2. Pending AFE |  | Atmospheric Corrosion |  | 19000 |  | 19000 | 19000 | 0 | Green | 19000 |  | 19000 | 0 | [9 empty] | 19000 | 19000 | No | Green | 2023-07-01 |  |  |  | 2023-04-30 | [14 empty] | 19000 | [6 empty] | 5-1-2023 Working with Rob Geib on Atmospheric Viewer. Moved forecast to July.4-3-23 WAITING ON GIS ATMOS MAP RGEIB3-2-23 SCOPING PROJECT | 2023-05-01 |  |  | West | Pipelines and Terminals | Corrosion |  | Wayne Pipeline | WB - BAY CITY TERMINAL |  |  | 0 | 19000 |  |  |  | Geib, Rob |  |  |  | 1 | 44442 |  | Guest, ProSight | Independent | Aqua | 2022-08-08 | Int - Planned Corr & FI
WD201WW - Digs from 2021 UCD ILI | Item | Open | MCAP | WD201WJM2201 | Exempt | 1990030 | Roman, James | West | 6. Operational | Defined | Pipeline Digs | 6392 |  | 41472 | 6392.49 | 6240 | 152 | Yellow |  |  |  | 6392 |  |  | 489000 |  |  | 489000 | Full | 489000 | 462425 | 41472 | 503897 | No | Green | 2022-08-01 | 2022-08-18 | 2022-08-18 | 2022-10-15 | 2022-10-07 |  |  | 2240.49 |  | 4000 | 152 |  |  | 152 | Red | [10 empty] | 41472 | 4/5/23 Variance -$4k. Late invoice for tree removal. 2/1/23 Ready to close 1/3/23 Variance ($10k including accruals) trailing costs...contractor, WM, Percheron. 12/5/22 Variance +$27k. Did not forecast final restoration. 11/1/22 Variance (-$121k) Accrual $190k. Project Complete. Need to finish job book. 10/3/22 Variance (-) Contractor on site with skeleton crew in month of September. 9/1/22 Variance (+) Accrual. Forecasting locked at time of AFE submittal. 8/2/22 Variance (-), late in starting project. 7/21/22 - re-forecasted out a couple months. 7/5/22 digs issued, resources busy on other projects. Hopefully start by end of July. 6/2/22 Don't know when digs are being issued. Integrity has not responded. Moved $$ out of June. 3/2/22 was informed on 2/9/22 that digs will not be issued until second half of May, so forecast moved from March to May. No change. 2/1/22 Digs have not yet been issued. JR | 2023-04-05 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | WD201WJ - DETROIT TO JOAN RD JCT 10IN |  | 6240 | 152 |  |  | 456032 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 41021 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
West Region 5 Gas Monitors Purchase 2022 | Item | Open | MEXP | 1348685E2204 | Maintenance Framework | 2004209 | Gardner, Travis | West | 7. Closed | Emergent | West | 87596 |  |  | 87596.13 | 87596 | 0 | Green |  |  |  | 87596 |  |  | 279000 |  |  | 279000 | Full | 279000 | 295661 |  | 295661 | No | Green | 2022-09-01 | 2022-07-28 | 2022-07-28 | 2022-09-30 | 2023-02-17 |  |  | 31581.12 | 56015.01 | [17 empty] | 3/1/2023 - Variance is for the final 13 dragers that arrived in February and they were forecasted in March. 2/3/2023 - waiting for the remaining 13 dragers. 1/4/2023 - variance is dragers coming from Germany. only recieved a partial order. 12/9/2022 - push half of december. awaiting drager equpment. confidence is low. 12/2/2022 - some material arrived early. waiting Drager Tube. scheduled for Dec delievery. 11/2/2022 - waiting for final material to be delievered. 10/3/2022 - material continues to arrive early. 9/1/2022 - some material arriving. adjust monthly spending per quote. 8/3/2022 - AFE approved. writing PO | 2023-03-01 | Griest, Barbara |  | West | Pipelines and Terminals | Station/Terminal |  | West Region Work Team | 20185 - WEST DISTRICT WORK TEAM |  | 87596 | 0 |  |  | 208065 |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 44170 |  | Gardner, Travis | Independent | Aqua | 2022-07-18 | Other Programs
West Toledo Circuit 1 Phase 2 Insulated Piping Inspection | Item | Open | MEXP | BETYT00E2201 | Exempt | 1980266 | Roknich, Hunter | West | 6. Operational | Defined | Facility Integrity | 0 |  |  | 0 | 0 | 0 | Green |  |  |  | 0 |  |  | 52000 |  |  | 52000 | Full | 52000 | 36507 |  | 36507 | No | Green | 2022-09-01 | 2022-05-11 | 2022-05-11 | 2022-12-31 | 2022-12-31 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | Green | [11 empty] | 3/2/2023 - Waiting on instruction from Facility Integrity for path forward 2/2/2023 - Waiting on instruction from Facility Integrity for path forward 1/4/2023 - Waiting for final invoicing 12/2/2022 - Waiting for final invoicing 10/11/2022 - Inspection complete. Isometric drawings marked up with problem areas. Working with facility integrity to discuss path forward for asbestos sampling 9/2/2022 - Missed forecast due to change in contractor schedule. Work to be completed in September 8/2/2022 - Estimated completion late August 7/5/2022- Purchase order issued. Prelim start date 8/16 6/2/2022 - Call week of 6/6 to discuss scheduling with IAG. 5/12/2022 - Current forecast for September. Working with IAG on scheduling. AFE approved. | 2023-03-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Toledo | BETYT - BET WEST TOLEDO |  | 0 | 0 |  |  | 36507 |  | Aiken, Elaine | Aiken, Elaine |  |  | 1 | 41178 |  | Administrator, System | Independent | Aqua | 2021-08-09 | Int - Accel Corr & FI
West Toledo Driveway repairs | Item | Candidate | MCAP |  | Exempt |  | Henfling, Mike | West | 2. Pending AFE |  | West |  | 50000 |  | 50000 | 50000 | 0 | Green | 50000 |  | 50000 | 0 | [9 empty] | 50000 | 50000 | No | Green | 2023-08-01 |  |  |  | 2023-08-31 | [15 empty] | 50000 | [5 empty] | 5-2-23 - No new updates. Plan to finalize scope in June. Left forecast as-is for August. May want to seal concrete cracks for containment purposes 4-4-23 - No new updates. Left forecast as-is for August. May want to seal concrete cracks for containment purposes 3-2-23 - No new updates. Left forecast as-is for August. 2-2-23 - Site visit held 1/17. Initial plan for repairs identified. Need to document and firm with Ops then request pricing. Left forecast as-is for August. 1-3-23 - Left forecast as-is. | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | BETYT - BET WEST TOLEDO |  |  | 0 | 50000 |  |  |  | Gardner, Travis |  |  |  | 1 | 37782 |  | Guest, ProSight | Independent | Aqua | 2020-08-12 | Other Programs
West Toledo Oil Water Separator Curb Replacement | Item | Candidate | MCAP |  | Maintenance Framework |  | Henfling, Mike | West | 2. Pending AFE | Defined | Secondary Containment |  | 75000 |  | 75000 | 75000 | 0 | Green | 75000 |  | 75000 | 0 | [9 empty] | 75000 | 75000 | No | Green | 2023-08-01 |  |  |  | 2023-08-31 | [6 empty] | 0 | 0 | 0 | Green |  |  | 0 |  |  | 40000 | 30000 | 5000 | 0 |  |  | 5-2-23 - No new updates. May plan to modify curbing near Bay 5 under Driveway repairs project. 4-4-23 - Call held 4/3 with Regional management and HSSE. Curbing is not required per SPCC. If it is a S/T/F issue, local operations to elevate project. Three sub projects listed in this OPPM project; working thru remaining requirements on curbing near Load Rack Bay 5 and ethanol offload containment. Pushed forecast. 3-2-23 - Discussed options with HSSE. Waiting on response from Gianna in regards to need for curbing. May end up removing curbing, but need to confirm path forward. Left forecast as-is 2-2-23 - Site visit held 1/17. Need to discuss background info with HSSE and determine path forward. Left forecast as-is 1-3-23 - Plan to put a scope together based on 2022 site visit. Engineering late 1Q/2Q, and construction in 3Q. Left forecast as-is 10/11/2022 - deferred to 2023. 9/12/2022 - deferred to 2023. funds added to regional drawdown. 9-1-22 - Plan to itemize scope of work and send to management for review. Project may be deferred or cancelled. 8-1-22 - Met with contractor on-site in July. Plan to itemize scope of work on drawings this month. 7-5-22 - Planning to meet with contractor on-site on 7/7 to discuss project options. Fall construction planned 6-2-22 - Planning to meet with Degen in June or July to discuss project options. Fall construction planned 5-4-22 - Site visit completed 4/20. Gathering information prior to AFE submittal. Construction tentative for September 4-4-22 = Scoping site visit planned in April 3-2-22 - Pushed forecast slightly in anticipation of some engineering design prior to construction. Will start looking at project in April. 2-2-22 - No change to forecast. | 2023-05-02 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | BETYT - BET WEST TOLEDO |  |  | 0 | 70000 | 5000 |  |  | Clark, Dave |  | N/A |  | 1 | 19780 |  | Guest, ProSight | Independent | Aqua | 2016-07-26 | Other Programs
West Toledo Tank Farm Step overs | Item | Open | MCAP | BETYT00M2202 | Maintenance Framework | 1991335 | Arch, Stefan | West | 6. Operational | Defined | West | 584 | 7500 |  | 8084.44 | 8084 | 0 | Green |  |  |  | 8084 |  |  | 100000 |  |  | 100000 | Phase | 100000 | 77091 | 7500 | 84591 | No | Green | 2022-06-01 | 2022-06-22 | 2022-06-22 | 2022-12-31 | 2022-12-29 |  |  | 562.37 | 22.07 | [8 empty] | 7500 | [8 empty] | 5/1/2023 - Spoke with Travis to have forecast completed in 2023. Working with Degen to complete items that were identified during final turnover. 4/7/2023 - Received quote from Degan for under $10k for remaining part of Phase I that was missed. Forecasting for May to be completed. 3/1/2023 - Waiting on one quote from Degen to complete a small part of the project. Planning to complete with Phase II. This project is complete. 2/1/2023 - Project is complete, over accrued Degen invoice. No additional forecasting required. Phase II will be completed in 2023 under a separate project. Walked down with Ops on 1/12/2023. 1/3/2023 - Project was completed 12/29. Degen installed concrete supports, stairs, crossovers, and modified existing trip hazards. Waiting for final invoice from Degen, but accrued the cost. 12/1/2022 - Stairs were delivered on 11/22. Degen to install in December, hoping to have completed by the end of the year. Forecast 10k in January if project rolls over to 2023. 11/1/2022 - Waiting on stair delivery from Safe Harbors. Planning to complete install in December as stairs are scheduled for end of November. 10/3/2022 - SPS said stairs will be delivered mid-end of November. Working with SPS to expedite the order or find a new supplier. Pushed forecast out to November for installation of the stairs. 9/1/2022 - Stairs currently being fabricated. Waiting on lead time from the supplier. Once arrived on site, will be installed by Degen. Phase II project entered into OPPM for 2023 to finish the remaining items. Once I get an answer on the lead time, will update forecast accordingly. 8/1/2022 - Continued design and fabrication of stairs for the tank farm. Planning to install in September when contractor comes available. 7/1/2022 - Received quotes back from contractors and suppliers. Degen will be performing the work. AFE approved for $100k. Crossovers ordered from SPS. Working to get lead time on the crossovers. Smallvariance in June for ordering material ahead of schedule. Planning to receive crossovers in July and begin working on install. Forecasting for Julyincludes receiving the material and beginning install. 6/1/2022 - Walkdown with contractors completed on 5/26. Bids are due back on 6/3. Iwill submit an AFE for the work once I get numbers back. Received quotes for stair kits for the proposed stair installations. Planning to begin inJuly. 5/2/2022 - Scope reviewed by leadership team. Getting quotes from contractors to assemble and install the stairs. Forecasting pushed to June due to lag in receiving quotes. 4/3/2022- Scope developed, will send to leadership team for review. Not all scope will be completed in budget. Once approved by leadership team, I will get quotes and AFE will be submitted. Planning toget quotes back in April for submission of AFE. 3/1/2022 - Project scope being developed. Will need to pick certain items to be installed. Received quote back from SPS for SafeHarbor crossovers last year. Will need to get quotes for installation of certain crossovers and stairs. 1/28/2022 - Planning to begin projectin May/June timeframe. I need to get quotes for select scope items. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | BETYT - BET WEST TOLEDO |  | 584 | 7500 |  |  | 76507 |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 40902 |  | Guest, ProSight | Independent | Aqua | 2021-08-03 | Other Programs
West Toledo Tank Farm Step Overs Phase II | Item | Candidate | MCAP |  | Exempt |  | Arch, Stefan | West | 2. Pending AFE |  | West |  | 115000 |  | 115000 | 115000 | 0 | Green | 115000 |  | 115000 | 0 | [9 empty] | 115000 | 115000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [6 empty] | 0 | 0 | 0 | Green |  |  |  |  | 10000 | 15000 | 75000 | 15000 |  |  |  | 5/1/2023 - Received comments back from management on scope. Once comments are accepted, will hold scope walkdown with contractors. 4/3/2023 - Scope sent to management for review and sent to Degen for pricing. Pushed forecasting out to May. Planning to complete in summer timeframe. 3/1/2023 - Scope developed and ready for management review. Will send out in March and set up bid event. Planning to begin ordering material in April. 2/1/2023 - Phase II project for West Toledo Stair Improvements. Walked down with Operations on 1/12/2023. Planning to complete in spring/summer. | 2023-05-01 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Toledo | BETYT - BET WEST TOLEDO |  |  | 0 | 100000 | 15000 |  |  | Gardner, Travis |  |  |  | 1 | 44397 |  | Guest, ProSight | Independent | Aqua | 2022-08-03 | Other Programs
West Toledo Terminal FRP and U-bolt Installation | Item | Candidate | MCAP |  | Exempt |  | Brown, Jeff | West | 2. Pending AFE |  | Atmospheric Corrosion |  | 38000 |  | 38000 | 38000 | 0 | Green | 38000 |  | 38000 | 0 | [9 empty] | 38000 | 38000 | No | Green | 2023-07-01 |  |  |  | 2023-08-31 | [14 empty] | 10000 | 28000 | [5 empty] | 5-1-23 Scoping 4-3-23 SCOPING 3-2-23 SCOPING PROJECT | 2023-05-01 |  |  | West | Pipelines and Terminals | Integrity |  | Toledo | BETYT - BET WEST TOLEDO |  |  | 0 | 38000 |  |  |  | Geib, Rob |  |  |  | 1 | 45361 |  | Gardner, Travis | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
WF - DOT COATING REPAIR | Item | Candidate | MEXP |  | Exempt |  | Brown, Jeff | West | 2. Pending AFE |  | Atmospheric Corrosion |  | 21000 |  | 21000 | 21000 | 0 | Green | 21000 |  | 21000 | 0 | [9 empty] | 21000 | 21000 | No | Green | 2023-07-01 |  |  |  | 2023-07-31 | [14 empty] | 21000 | [6 empty] | 5-1-2023 Working with Rob Geib on Atmospheric Viewer. 4-3-23 WAITING ON GIS ATMOS MAP RGEIB3-2-23 SCOPING PROJECT | 2023-05-01 |  |  | West | Pipelines and Terminals | Corrosion |  | Wayne Pipeline | WF - FLINT TERMINAL |  |  | 0 | 21000 |  |  |  | Geib, Rob |  |  |  | 1 | 44441 |  | Guest, ProSight | Independent | Aqua | 2022-08-08 | Int - Planned Corr & FI
WF Flint Station line 207 / 208 Unit discharge valves | Item | Open | MCAP | WF00000M2201 | Maintenance Framework | 2013008 | Roknich, Hunter | West | 6. Operational | Defined | Valves | 178 |  |  | 177.92 | 178 | 0 | Green |  |  |  | 178 |  |  | 16000 |  |  | 16000 | Full | 16000 | 13097 |  | 13097 | No | Green | 2022-10-01 | 2022-10-05 | 2022-10-05 | 2022-10-30 | 2022-10-11 |  |  | 177.92 | [18 empty] | 10/11/2022 - Work completed early September by operations. Working on getting all labor and material reclassed to project. 8/2/2022 - Working with operations on scheduling and costs for AFE. Estimated install early September. 3/2/22 - Operations has valve on inventory. Working with operations to develop scope and schedule. | 2022-10-11 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Pipeline | WF - FLINT TERMINAL |  | 178 | 0 |  |  | 12919 |  | Oey, Alex | Gardner, Travis W. | N/A |  | 1 | 31090 |  | Guest, ProSight | Independent | Aqua | 2018-08-28 | Other Programs
WF208WB Cutout of F 38415 Temporary Replace | Item | Open | MCAP | WF208WBM2201 | Maintenance Framework | 1945669 | Roman, James | West | 6. Operational | Defined | Pipeline Digs | 1440 |  | 81052 | 1439.95 | 1440 | 0 | Green |  |  |  | 1440 |  |  | 128000 | 860000 |  | 988000 | Phase | 988000 | 807422 | 81052 | 888474 | No | Green | 2022-04-01 | 2022-03-28 | 2022-03-28 | 2022-07-31 | 2022-07-31 |  |  | 1439.95 | [17 empty] | 81052 | 11/1/22 Variance (-$1,500) did not get to job book yet. 10/2/22 Variance (+$2,002) Trailing costs 9/1/22 Variance (+) trailing costs. 8/2/22 Variance (+) Contractor cost more than forecasted. Project complete. 7/5/22 Variance - Contractor cost more than forecasted. Cutout Complete. Site restorations forecasted for July. 6/2/22 Variance -$85k, Have not yet received environmental permits for two sites. I've adjusted forecast, removing two sites from this project. 5/3/22 Variance $38k, purchased pipe in April instead of May. 4/26/22 - NEB - added $100k to July forecast to align CY EAC with AFE amount. Reduced corresponding budget allocation. 4/4/22 Corporate has added 3 more cutout sites to this scope of work. Additional sites are being investigated now. After info has been processed, I'll adjust the summer forecast. 3/2/22 Plan to submit Phase 1 AFE and begin bid documents. Cut out planned for week of June 6. Scheduling and asset team on board. 2/17/22 - on 2/14/22 I was notified that a couple tool runs were rescheduled by others to the week I had planned for this cutout. The asset team could not cover both projects. As such, I had to bump this project a month. I could not change the forecast at that time because it was locked. JR 2/1/22 Cutout is located under salt truck access driveway. Will need to wait until snow/ice has wrapped up for season before we can dig up. JR | 2023-04-12 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | WF208WB - FLINT TO BAY CITY |  | 1440 | 0 |  |  | 805982 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 34595 |  | Bassani, Joel | Independent | Aqua | 2019-08-27 | Int - Planned Cutouts
WN - DOT COATING REPAIR | Item | Candidate | MEXP |  | Exempt |  | Brown, Jeff | West | 2. Pending AFE |  | Atmospheric Corrosion |  | 19000 |  | 19000 | 19000 | 0 | Green | 19000 |  | 19000 | 0 | [9 empty] | 19000 | 19000 | No | Green | 2023-07-01 |  |  |  | 2023-04-30 | [14 empty] | 19000 | [6 empty] | 5-1-2023 Working with Rob Geib on Atmospheric Viewer. Moved forecast to July.4-3-23 WAITING ON GIS ATMOS MAP RGEIB3-2-23 SCOPING PROJECT | 2023-05-01 |  |  | West | Pipelines and Terminals | Corrosion |  | Wayne Pipeline | WN - NOVI TERMINAL |  |  | 0 | 19000 |  |  |  | Geib, Rob |  |  |  | 1 | 44444 |  | Guest, ProSight | Independent | Aqua | 2022-08-08 | Int - Planned Corr & FI
WO160BN Henderson Rd Casing Fill | Item | Open | MEXP | WO160BNE2304 | Exempt | 2109956 | Scannell, Adam | West | 3. Active | Defined | Cathodic Protection |  | 45002 |  | 45002 | 45002 | 0 | Green | 45000 |  | 45000 | 2 |  |  | 34567 |  |  | 34567 | Full | 34567 |  | 45002 | 45002 | Yes | Red | 2023-05-01 | 2023-04-04 | 2023-04-04 | 2023-05-30 | 2023-05-31 | [12 empty] | 34567 | [5 empty] | 10433 | 2 |  | 05/02/23 - Permit approved and work scheduled for the week of 5/15 for completion. 03/22/23 - AFE submitted to the workflow. Total AFE costs are at $34,567. Remaining budget is not expected to be needed. Placing it in November for use as West Region drawdown funds. 02/02/23 - Discussions with contractor, ROW and local asset team have started. Should have quote for the work back in the next week or two. Permitting to begin once tentative dates are discussed. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | St. Louis | WO160BN - WOOD RIVER TO BARNETT |  |  | 34567 |  | 10435 |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45454 |  | Guest, ProSight | Independent | Aqua | 2022-08-26 | Int - Planned Corr & FI
WO160BNEP103725 MP 19.64 Exposure Repair | Item | Open | MEXP | WO160BNE2003 | Exempt | 1743983 | Rohr, Travis | West | 3. Active | Drawdown | Exposed Pipe Evaluation & Remediation |  | 25500 |  | 25500 | 25500 | 0 | Green |  |  |  | 25500 |  |  | 25500 |  |  | 25500 | Full | 25500 |  | 25500 | 25500 | No | Green | 2023-09-01 | 2020-08-10 | 2020-08-10 | 2020-12-31 | 2022-12-31 | [16 empty] | 25500 |  |  |  |  | 5/2/23 Waiting for drier conditions. 4/4/23 Storms have kept this wet. 3/2/23 Winter/Spring storms have kept this site wet. 2/3/23 Ground conditions have prevented this one from getting started. 1/4/23 Weather/ground conditions prevented this one from being completed. Talked with Brian Hurley about this, agreed to push into 2023.12/5//22 Attempted this repair 11/28, rain over the weekend flooded this location making it to slick for lift. Watching weather for access. 11/1/22 This is scheduled for the week of Dec13. 10/4/22 Work should take place next month. 9/1/22 Spoke with local Ops, September and the October are extremely busy, as well as the contractor. I have pushed money back to November when other exposure work will be taking place. 8/3/22 Local Ops says it is dry enough to do now. Contractor is booked through the end of the month. 7/4/22 Location is close to being dry enough to get into. Keeping in contact with local ops and contractor. 6/3/22 Due to weather patterns, ground is still swampy. Need this dry to complete. 5/2/22 still swampy, once it dries out we will get this scheduled. 4/5/22 Spoke with local OPs, ground is still swampy. 3/3/22 Due to weather and ground conditions, this needs to be delayed until ground is dry. 2/3/22 Currently scheduled for the week of Feb 21 1/5/22 Work delayed last week due to heavy rain and thunderstorms. 12/3/21 Work was delayed due to not being able to use Geeding and seeking a new contractor on short notice. 11/2/21 Work Expected week of Nov 15 10/5/21 This is still scheduled for November, but could shift due to local asset team manpower issues. 9/3/21 This should be done in November. 7/1/21 Need to check with Brian Hurley about the additional exposures at this location. 6/3/21 This will be done with additional exposures once this years list is issued. 5/5/21 waiting on 2021 repair list to potentially do two other exposures right next to this one. 4/1/21 Stillwaiting on expense exposure repair list. 3/1/21 Still waiting for theexposure repair list for this year. 2/8/21 Still waiting for the exposure list this year to do additional exposures right next to this one. 1/4/21 Waiting for the list of exposure repairs for this year. 11/30/20 After talking to Brian Hurley about this one, he said it would be postponed to work on two others on this property at the same time. This funding went to IM760UG MP 45 and 85.11/2/20 Plans are still to complete this in December. 10/1/20 Work has been pushed to december 9/1/20 Work is scheduled for November. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | St. Louis | WO160BN - WOOD RIVER TO BARNETT |  |  | 0 | 25500 |  |  |  | Hurley, Brian | Bassani, Joel D. | N/A |  | 1 | 37570 |  | Schultz, Amy | JDE Child | Burnt Orange | 2020-08-07 | Int - Exposure Evals
WO160BNEP103910 MP 19.68 Dump Repair | Item | Open | MEXP | WO160BNE2104 | Exempt | 1901944 | Rohr, Travis | West | 3. Active | Drawdown | Exposed Pipe Evaluation & Remediation |  | 25500 |  | 25500 | 25500 | 0 | Green |  |  |  | 25500 |  |  | 25000 |  |  | 25000 | Full | 25000 |  | 25500 | 25500 | No | Green | 2023-09-01 | 2021-10-13 | 2021-10-13 | 2021-12-31 | 2022-12-31 | [16 empty] | 25500 |  |  |  |  | 5/2/23 Waiting for drier conditions. 4/4/23 Storms have kept this wet. 3/2/23 Winter/Spring storms have kept this site wet. 2/3/23 rain/snow has prevented any work at this location. 1/4/23 Weather/ground conditions prevented this one from being completed. Talked with Brian Hurley about this, agreed to push into 2023.12/5//22 Attempted this repair 11/28, rain over the weekend flooded this location making it to slick for lift. Watching weather for access. 11/1/22 Work is scheduled for the week of Dec 13, Will move up if possible. 10/4/22 Work planned to take place next month. 9/1/22 Spoke with local Ops, September and the October are extremely busy, as well as the contractor. I have pushed money back to November when other exposure work will be taking place. 8/3/22 Local Ops says it is dry enough to do now. Contractor is booked through the end of the month. 7/4/22 Ground is almost dry enough to get into, keeping contact with local ops and contractor. 6/3/22 due to weather patterns, ground has not dried out yet. 5/2/22 ground is still swampy, when it dries out, we will get this scheduled 4/5/22 spoke with local ops, ground is still swampy, budgeted for June. 3/3/22 Due to weather and ground conditions, this needs to be delayed until ground is dry 2/3/22 Work scheduled for the week of Feb 21 1/5/22 Work was postponed last week due to heavy rain and thunderstorms. 12/3/21 Work was delayed due to not being able to use Geeding and seeking a new contractor on short notice. 11/2/21 Work Expected week of Nov 15 | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Pipeline Integrity |  | St. Louis | WO160BN - WOOD RIVER TO BARNETT |  |  | 0 | 25500 |  |  |  | Hurley, Brian | Bassani, Joel D. | N/A |  | 1 | 42295 |  | Hurley, Brian | JDE Child | Burnt Orange | 2021-10-11 | Int - Exposure Evals
WO165ZI - DIG SHEETS (2) Immediate + (1) Proximity - Due 07-11-22 | Item | Open | MCAP | XX165CNM2201 | Maintenance Framework | 2002021 | Roman, James | West | 7. Closed | Drawdown | Pipeline Digs | 899 |  |  | 898.8 | 899 | 0 | Green |  |  |  | 899 |  |  | 145000 |  |  | 145000 | Full | 145000 | 145144 |  | 145144 | No | Green | 2022-07-01 | 2022-08-10 | 2022-08-10 | 2022-07-22 | 2022-07-22 |  |  | 898.8 | [18 empty] | 11/1/22 Variance ($11k) trailing costs from contractor and right of way. 10/3/22 Variance (+898) Trailing costs. 9/1/22 Variance (-) trailing costs 8/1/22 - Project complete. Variance (-) Immediate digs, budget was established in an interim AFE. | 2022-11-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Indianapolis | XX165CN - IL S/L TO CARBON |  | 899 | 0 |  |  | 144245 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44059 |  | Guest, ProSight | Independent | Aqua | 2022-07-01 | Int- Planned Digs
WO165ZI - Digs from 2022 GEO+MFL ILI | Item | Open | MCAP | WO165EFM2202 | Maintenance Framework | 2022631, 2036824, 2036836, 2036837, 2036838, 2036839, 2036840, 2036841, 2036842, 2036843, 2036844, 2036845, 2036846, 2036847, 2022632 | Roman, James | West | 6. Operational | Defined | Pipeline Digs | 840979 | 10000 | 120000 | 850979.15 | 845858 | 5121 | Yellow | 1139000 |  | 1139000 | -288021 |  |  | 1703000 |  |  | 1703000 | Full | 1703000 | 1424951 | 130000 | 1554951 | No | Green | 2022-11-01 | 2022-11-08 | 2022-11-08 | 2023-03-08 | 2023-03-08 |  |  | 371061.7 | 390126.43 | 74670.12 | 5120.9 |  |  | 5121 | Red |  |  | 10000 | [7 empty] | 120000 | 4/5/23 - Variance $3,462. Accrue $2,469. Project Complete. Job book approved. Leaving $10k in May in case we have to touch up any sites. 3/1/23 variance $126k. Accrue $115k. Project is finishing ahead of schedule. 2/1/23 Variance $4k 1/4/23 Variance $191k. Contractor kept second crew longer and more repair material was purchased. 12/5/22 Variance +$59,433. Ahead of schedule, this amount removed from Dec forecast. 10/27/22 Issued to JDR. Had stakeholder mtg and reviewed every site. Buckeye estimate matches contractor estimate. AFE to be submitted this week. Depending on length of approvals, plan to start digs 11/14/22. Forecast reflects this. 10/1/22 - Digs issued on 9/9, 35 anomalies at 14 dig sites. Scoping out digs and planning to complete as many as possible within 2022. 9/1/22 - No digs issued yet. Adjusted forecast to reflect $150k in 2022 for any potential digs and $1,239,000 pushed to 2023. 8/1/22 - Final digs expected to be issued in Sept. 7/5/22 - Immediate digs issued on 7/1/22, additional digs still TBD. 6/1/22 - No change. 5/3/22 - No digs issued yet, ILI completed on 3/13/22. 4/4/22 - No digs issued at this time. 3/2/22 - No digs issued at this time. 2/2/22 - Digs anticipated to begin after ILI run scheduled in March 2022. | 2023-04-05 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | St. Louis | WO165EF - WOOD RIVER TO EFFINGHAM |  | 835858 | 15121 |  |  | 583972 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 41010 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
WO180XX Mag anode installation | Item | Candidate | MCAP |  | Exempt |  | Logan, Rob | West | 2. Pending AFE |  | Cathodic Protection |  | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 | [9 empty] | 30000 | 30000 | No | Green | 2023-08-01 |  |  |  | 2023-08-31 | [15 empty] | 30000 | [5 empty] | 05/01/2023 Requesting Quote from National Pipeline 04/03/2023 AFE Pending 03/02/2023 Pending AFE 2/2/2023 pending AFE | 2023-05-02 |  |  | West | Pipelines and Terminals | Integrity |  | St. Louis | WO180XX - WOOD RIVER TO MO S/L |  |  | 0 | 30000 |  |  |  | Geib, Rob |  |  |  | 1 | 45718 |  | Logan, Rob | Independent | Aqua | 2022-08-30 | Int - Planned Corr & FI
Wood River Station - new video system | Item | Candidate | MCAP |  | Maintenance Framework |  | Scannell, Adam | West | 8. Canceled |  | Security & Cameras |  |  |  | 0 | 30000 | -30000 | Red | 30000 |  | 30000 | -30000 | [11 empty] | No | Green |  |  |  |  | 2023-12-31 | [21 empty] | 04/21/23 - Project is cancelled. Moving funds to other projects in this program that need additional funding. 04/14/23 - Determining if this project is moving forward. Forecast moved to December. 02/02/23 - Stakeholder meeting with program owner was held. Setting up site visit with contractor to determine best layout and obtain equipment order needs. | 2023-04-21 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | St. Louis | WO - WOOD RIVER STATION |  |  | 0 |  |  |  |  | Clark, Chris |  |  |  | 1 | 40809 |  | Guest, ProSight | Independent | Aqua | 2021-07-28 | Other Programs
Wood River Station Contactor Replacements | Item | Open | MCAP | WO00000M2102 | Maintenance Framework | 1857898 | Scannell, Adam | West | 3. Active | Unplanned | Electrical | 1652 | 15000 |  | 16651.77 | 16229 | 422 | Yellow |  |  |  | 16652 |  |  | 113000 |  |  | 113000 | Full | 113000 | 88909 | 15000 | 103909 | No | Green | 2021-10-01 | 2021-06-25 | 2021-06-25 | 2021-10-31 | 2023-06-30 |  |  | 402.51 | 409.77 | 417.14 | 422.35 |  |  | 422 | Red |  |  |  | 15000 | [7 empty] | 04/21/23 - All work is on schedule for the week of 06/12 thru 06/16 downtime and cutover. Unit 4 contactor will be replaced first, Unit 1 second and if time allows Unit 5 last. 03/30/23 - Meeting on site on 4/6 with p66 and JF Electric to walk down work area to be sure all people can perform their tasks at the same time. Next internal call set for 4/7. Will schedule next full group call the week of 4/10. 03/02/23 - P66 schedule has slipped out to June from last conversation. Bi-weekly calls will begin in week of March 20th to monitor progress and any potential changes in schedule.02/02/23 - Currently P66 has the cutover scheduled for May 10th. Bi-weekly calls will begin in March to monitor progress and any potential changes in schedeule.01/04/23 - Setting up update call with P66 to stay in line with their cutover schedule. Estimate of June for completion.12/07/22 - Install deferred to 2023 to align with new P66 substation cutover.11/02/22 - No new updates.10/10/22 - Variance on this is due to PO and supply issues with contractor. A discussion was made with vendor and determined all costs have been paid and accrual was dropped.10/04/22 - Work deferred to 2023 due to scheduling needs changing. Forecast has been moved out.09/02/22 - Week of 10/3 is planned installation. Working with P66 to coordinate other power cutover work.08/02/22 - Currently planned for the week of 10/03/2207/01/22 - Currently planned for the week of 10/03/2206/02/22 - Trying to coordinate with the 165L cutouts planned for October. Also coordinating with P66 refinery substation cutover dates.05/05/22 - No new updates. Still planned for early Q3.Issue between Cognos and OPPM actuals. Looing to see where the variance occurred.04/04/22 - No new updates. Still planned for early Q303/02/22 - Will install during the 2022 contactor replacements. Coordinating with the refinery to complete this during the substation cutover. Planning for Q3, setting date once all 2022 materials are received.01/04/22 - Willinstall when station is down for the 2022 project installation.11/30/21 - During the installation it was found that Eaton provided the incorrect parts. We are waiting for the correct materials to ship in order to install. Current estimate is January.11/02/21 - Installation set on Nov 9th10/04/21 - Materials are shipped. Install set for Nov 9th.09/08/21- Vendor updated expected delivery to late October.08/09/21 - Materials expected in Sept. Downtime will be submitted for October for installation.07/07/21 - Materials ordered. 4-6 week lead time expected delivery in late August/Sept. Installation will be scheduled once the factory confirms delivery schedule. Tentative for October. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | St. Louis | WO - WOOD RIVER STATION |  | 1229 | 15422 |  |  | -10973 |  | Ashley, Robert | Ashley, Robert |  |  | 1 | 38144 |  | Guest, ProSight | Independent | Aqua | 2020-08-14 | Other Programs
Wood River Station Contactor Replacements 2022 | Item | Open | MCAP | WO00000M2202 | Maintenance Framework | 2002640 | Scannell, Adam | West | 3. Active | Defined | Electrical | 3592 | 30000 |  | 33591.63 | 32848 | 744 | Yellow | 30000 |  | 30000 | 3592 |  |  | 202000 |  |  | 202000 | Full | 202000 | 156642 | 30000 | 186642 | No | Green | 2022-07-01 | 2022-07-11 | 2022-07-11 | 2022-10-31 | 2023-06-30 |  |  | 705.99 | 1406.61 | 734.92 | 744.11 |  |  | 744 | Red |  |  |  | 30000 | [7 empty] | 04/21/23 - All work is on schedule for the week of 06/12 thru 06/16 downtime and cutover. Unit 4 contactor will be replaced first, Unit 1 second and if time allows Unit 5 last. 03/30/23 - Meeting on site on 4/6 with p66 and JF Electric to walk down work area to be sure all people can perform their tasks at the same time. Next internal call set for 4/7. Will schedule next full group call the week of 4/10. 03/02/23 - P66 schedule has slipped out to June from last conversation. Bi-weekly calls will begin in week of March 20th to monitor progress and any potential changes in schedule. 02/02/23 - Currently P66 has the cutover scheduled for May 10th. Bi-weekly calls will begin in March to monitor progress and any potential changes in schedeule. 01/04/23 - Setting up update call with P66 to stay in line with their cutover schedule. Estimate of June for completion. 12/07/22 - Install deferred to 2023 to align with new P66 substation cutover. 11/02/22 - No new updates 10/04/22 - Work deferred to 2023 due to scheduling needs changing. Forecast has been moved out. 09/02/22 - Week of 10/3 is planned installation. Working with P66 to coordinate other power cutover work. 08/02/22 - Variance was due to discrepancy in inventory cost listing for inventory issue. Installation is scheduled for the week of 10/03/22. 07/22/22 - AFE approved. Work scheduled for the week of 10/3. Inventory issue request submitted for materials. | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | St. Louis | WO - WOOD RIVER STATION |  | 2848 | 30744 |  |  | 153050 |  | Ashley, Robert | Decker, Paul |  |  | 1 | 41638 |  | Guest, ProSight | Independent | Aqua | 2021-08-19 | Other Programs
Woodhaven Station - Upgrade Oil on Water Detection System | Item | Open | MCAP | WS00000M2301 | Exempt | 2111171 | Hassan, Mohammad | West | 3. Active | Defined | West | 0 | 31000 |  | 31000 | 25000 | 6000 | Red | 25000 | 6000 | 31000 | 0 |  |  | 31000 |  |  | 31000 | Full | 31000 | 0 | 31000 | 31000 | No | Green | 2023-07-01 | 2023-04-17 | 2023-04-17 | 2023-06-30 | 2023-07-31 | [5 empty] | 0 |  |  | 0 | Green |  |  |  |  | 31000 | [6 empty] | 05-02-2023 - MNH - Project approved last month. Will have kick off and procurement this month. Due to 8-week lead time on material, forecast now moved to July. EAC at $31K per the approved AFE. 04-03-2023 - MNH - Delay in submitting AFE due to other workload and will submit by end of this week now. Due to 8-week lead time on material, forecast now moved to June. 03-01-2023 - MNH - Site visit done, and quotes received. Will work on submitting AFE next week. Due to 8-week lead time on material, forecast moved to May. 02-01-2023 - MNH - Scope development underway. 01-03-2023 - MNH - Will start looking at scope of work this month. 12-1-2022 - MNH - Will start looking at scope of work next month. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Pipeline | WS - WOODHAVEN STATION |  |  | 0 | 31000 |  |  |  | Gardner, Travis | Gardner, Travis W. |  |  | 1 | 44428 |  | Guest, ProSight | Independent | Aqua | 2022-08-04 | Other Programs
Woodhaven Station Tank 120 Premium Pump Replacement | Item | Open | MCAP | BETWS00M2303 | Exempt | 2110629 | Gardner, Travis | West | 3. Active | Drawdown | Rotating Equipment | 22798 |  |  | 22798 | 38000 | -15202 | Red |  | 38717 | 38717 | -15919 |  |  | 38717 |  |  | 38717 | Full | 38717 | 22798 |  | 22798 | No | Green | 2023-04-01 | 2023-04-12 | 2023-04-12 | 2023-04-28 | 2023-05-31 | [5 empty] | 22798 | 38000 | 38000 | -15202 | Red |  | Forecasting | [9 empty] | 5/3/2023 - work completed submitted reclass. 4/3/2023- emergent project to pull damaged pump and install critical spare | 2023-05-03 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETWS - BET WOODDHAVEN TERMINAL |  |  | 22798 |  |  |  |  | Posipanko, Dan | Gardner, Travis W. |  |  | 1 | 46861 |  | Gardner, Travis | Independent | Aqua | 2023-03-30
Woodhaven Terminal (BETWS) Tank 128 - OOS API 653 Insp | Item | Open | MCAP | BETWS00M2301 | Maintenance Framework | 2084423 | Arch, Stefan | West | 3. Active | Defined | Tanks | 17685 | 422445 |  | 440129.53 | 439368 | 762 | Yellow | 427445 |  | 427445 | 12685 |  |  | 279804 |  |  | 279804 | Phase | 279804 | 17685 | 422445 | 440130 | No | Green | 2023-03-01 | 2023-02-06 | 2023-02-06 | 2023-12-31 | 2023-09-30 |  |  |  |  | 16922.99 | 761.54 |  |  | 762 | Red |  |  |  |  | 49445 | 200000 | 173000 |  |  |  |  | 5/1/2023 - No updates, planning for July OOS timeframe. 4/3/2023 - Ordered materials in March. No changes to the schedule and forecasting. 3/1/2023 - I did not order any material this month due to WO's not sent until 2/23. Re-forecasted money in March for equipment and instrumentation. Planning to complete project in Q3. 2/1/2023 - OOS API 653 tank project. Stakeholder call held on 1/20/2023. Large marketing tank with high-speed pumps and rail loading. Planning to complete in Q3. Forecasting in February to order parts. Anticipating minor repairs. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Wayne Terminals | BETWS - BET WOODDHAVEN TERMINAL |  | 16923 | 762 | 422445 |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44896 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Woodhaven Terminal (BETWS) Tank 131 - In-Service Steel IFR Up Close Seal Inspection | Item | Open | MEXP | BETWS00E2301 | Maintenance Framework | 2084795 | Arch, Stefan | West | 6. Operational | Defined | Tanks | 0 | 14000 |  | 14000 | 14200 | -200 | Yellow | 10000 |  | 10000 | 4000 |  |  | 15987 |  |  | 15987 | Full | 15987 | 0 | 14000 | 14000 | No | Green | 2023-05-01 | 2023-02-08 | 2023-02-08 | 2023-12-31 | 2023-05-08 | [5 empty] | 0 | 7100 | 7100 | -7100 | Red |  |  | 14000 | [8 empty] | 5/1/2023 - Held stakeholder call on 4/14 with Ops and Phillips. Planning to complete on 5/8 or 5/9. Phillips to complete seal inspection. 4/3/2023 - Planning to complete in late April, beg of May. No additional changes. 3/1/2023 - Planning to complete in April. No changes from last month. 2/1/2023 - Project to complete in service up close seal inspection on tank 131. Planning to complete in April. Funded being approved through the West Region up close seal inspection AFE. | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Wayne Terminals | BETWS - BET WOODDHAVEN TERMINAL |  |  | 14000 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44897 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Woodhaven Terminal (BETWS) Tank 109 OOS Inspection & Refurb | Item | Open | MCAP | BETWS00M2101 | Exempt | 1783673 | Arch, Stefan | West | 6. Operational | Defined | Tanks | 250 |  |  | 250.48 | 250 | 0 | Green |  |  |  | 250 |  | Carryover/Emergent/Drawdown/Reclass | 275000 | 548000 |  | 823000 | Phase | 823000 | 987515 |  | 987515 | No | Green | 2021-01-01 | 2020-12-15 | 2020-12-15 | 2021-12-31 | 2022-02-25 |  |  | 250.48 | [18 empty] | 7/1/2022 - Completing taping at the end of Napoleon tank 3 mechanical repairs in July or August. 6/1/2022 - Completing taping in June. Larger variance in May due to additional change order approved. No additional work or forecasting needed after taping is installed. 5/2/2022 - Waiting for June to complete the geodome taping. Negotiated change order with Consolidated and submitted for approval. Variance in April due to water authority water costing more than anticipated. 4/3/2022 - Tank liner and button up completed. Tank fully RTS on 3/16. Discussion with Consolidated on change order amount, they did not get approval to spend an extra $90k. Variance in March due to more spend in winter for colder weather precautions and additional wiring needed. Waiting for June timeframe to install geodome taping for warmer weather. 3/1/2022 - Pressure test completed on 2/22, all went well. All water is removed from site. WVP on site to blast old liner and install new liner. Once liner is installed and passed, tank will be button'd up. The forecast in June is for the installation of geodome tape in warm weather. 1/28/2022 - Consolidated continued working on annular plate and remaining mechanical items. Work crew was struck with Covid and the whole annular plate install fought the dead shell. Hydrotest got pushed out to the first week in February due to cold weather. Planning to have tank RTS beg of March. 1/3/2021 - Consolidated continued work on annular ring and installing seal. Planning to begin hydrotest the second or third week in January. 12/1/2021 - Consolidated mobilized to site on 11/1 and started mechanical repairs. Consolidated slotted shell and working to install annular ring. Planning to have Consolidated demobilize the week of 12/13. Once Consolidated demobilizes, tank will be strapped for hydrotest. Hydrotest planning to begin at the turn of the year. Stakeholder call held on 11/30 to discuss hydrotesting logistics and schedule. 11/1/2021 - Allied mobilized to site on 10/4, completed isolation and cleaning on 10/9. DJA mobilized to site on 10/11 and completed inspection on 10/13. PM and Consolidated on site on 10/13 for scope walkdown. Developed scope on 10/14 and sent to management. Larger scope includes annular ring installation, miscellaneous shell nozzle work, instrumentation replacement, primary seal replacement, floating roof work, installation of 4" nozzles on the geodome, and Buckeye wish list items. Received quote back fromConsolidated for annular ring and sketch plate replacement. Annular ring $50kcheaper than sketch plate replacement. Plan to hydrotest tank and replace internal liner. Consolidated mobilized to site on 11/1. Phase II AFE routed on 10/26. 10/1/2021 - C&W mobilized on 9/20 to site. Took 2 weeks to pump over product on 10/1. C&W told me they cannot work next week due to another project. I am going to cancel their PO and Allied will come in clean the tank. Once tank is cleaned, DJA will be on site for inspection. Larger scope expected from reviewing past inspections and condition of the tank. 9/1/2021 - Woodhaven 129 put back into service end of August. Planning to take tank 109 OOS the week of 9/20. Match up with inspector that will become free after Indianola 803 RTS. In September, C&W will clean the tank and DJA will complete a API 653 inspection. Consolidated will be the mechanical repair contractor onthis job. 8/2/2021 - Tank 129 scheduled to come back into service at the end of August. Will plan to take tank 109 OOS in September. 5/28/2021 -Project slated for after tank 129 coming back into service. Still August timeframe at the moment. 5/3/2021 - Project still slated for August timeframe due to workload during Q2. 4/1/2021 - Tank coming OOS will be July/August timeframe. 12/11/20-Compliance date 10/29/2021. Waiting on feedback from Exxon Mobil as to their preferred timing | 2022-07-01 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Wayne Terminals | BETWS - BET WOODDHAVEN TERMINAL |  | 250 | 0 |  |  | 479855 |  | Stine, Carlton | Bassani, Joel D. |  |  | 1 | 37270 |  | Guest, ProSight | Independent | Aqua | 2020-07-23 | Int - Tanks
Woodhaven Terminal (BETWS) Tank 128 OOS Support Project | Item | Candidate | MCAP |  | Maintenance Framework |  | Arch, Stefan | West | 2. Pending AFE |  | Tank Outage | 0 | 64000 |  | 64000 | 64000 | 0 | Green | 64000 |  | 64000 | 0 | [8 empty] | 0 | 64000 | 64000 | No | Green | 2023-07-01 |  |  |  | 2023-06-30 | [5 empty] | 0 |  |  | 0 | Green |  |  |  |  | 30000 | 34000 | [5 empty] | 5/1/2023 - Re-forecasted to July and August. Working with marketing and Ops if project is needed. 4/3/2023 - No changes, working with operations and scheduling if this project is needed. 3/1/2023 - No changes, working with operations and scheduling if this project is needed. 2/1/2023 - OOS Support project for tank 128 outage. This is to use another tank for ULSD sales during the outage. Working with Operations, scheduling, and marketing if needed. | 2023-05-01 |  |  | West | Pipelines and Terminals | Integrity |  | Wayne Terminals | BETWS - BET WOODDHAVEN TERMINAL |  |  | 0 | 64000 |  |  |  | Stine, Carlton |  |  |  | 1 | 44390 |  | Guest, ProSight | Independent | Aqua | 2022-08-03 | Int - Tanks
Woodhaven Terminal Fire Suppression Upgrade Phase I | Item | Open | MCAP | BETWS00M2304 | Maintenance Framework | 2120013 | Henfling, Mike | West | 3. Active | Drawdown | Fire Protection | 0 | 20000 |  | 20000 |  | 20000 | Red |  | 20000 | 20000 | 0 |  |  | 23300 |  |  | 23300 | Phase | 23300 | 0 | 20000 | 20000 | No | Green | 2023-06-01 | 2023-05-03 | 2023-05-03 | 2023-09-30 | 2024-09-30 | [5 empty] | 0 |  |  | 0 | Green |  |  |  | 4000 | 5000 |  |  | 11000 |  |  |  | 5-2-23 - Phase AFE in progress. Plan to complete engineering and obtain estimate for 2024 construction. | 2023-05-02 | Griest, Barbara |  | West | Pipelines and Terminals | Operating Infrastructure |  | Wayne Terminals | BETWS - BET WOODDHAVEN TERMINAL |  |  | 4000 | 5000 | 11000 |  |  | Jakubowski, Gregory | Gardner, Travis W. |  |  | 1 | 46995 |  | Gardner, Travis | Independent | Aqua | 2023-04-27
WS - WOODHAVEN STATION - STATION PIPE PAINTING | Item | Open | MCAP | WS00000M2201 | Maintenance Framework | 2003320 | Brown, Jeff | West | 7. Closed | Defined | Facility Painting | 54 |  |  | 53.74 | 54 | 0 | Green |  |  |  | 54 |  |  | 86000 |  | 20000 | 106000 | Supplemental | 106000 | 104811 |  | 104811 | No | Green | 2022-09-01 | 2022-07-18 | 2022-07-18 | 2022-10-28 | 2022-09-30 |  |  | 53.74 | [18 empty] | 12/5/2022 - extra cost was additonal inspector time. 11/1/2022 - Variance is inspector cost for 4 wks. Project is complete. 10/3/2022 - Pipe is prepped and primed. will finish this month. 9/1/2022 -Contract to mob on 9/12/22. 8-1-22 CONTRACTOR VIKING HAS SCHEDULED FOR SEPT. 7/7/2022 - AFE submitted. 6/1/16-Project is deferred until next year | 2022-12-05 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | WS - WOODHAVEN STATION |  | 54 | 0 |  |  | 104757 |  | Geib, Rob | Spitz, Nicholas P. |  |  | 1 | 16060 |  | Guest, ProSight | Independent | Aqua | 2015-09-01 | Int - Planned Corr & FI
WW - 380 TEST STATION REPAIRS | Item | Open | MEXP | WW00000E2301 | Exempt | 2086012 | Brown, Jeff | West | 6. Operational | Defined | Atmospheric Corrosion | 12000 |  |  | 12000 | 12000 | 0 | Green | 12001 |  | 12001 | -1 |  |  | 13200 |  |  | 13200 | Full | 13200 | 12000 |  | 12000 | No | Green | 2023-03-01 | 2023-02-21 | 2023-02-21 | 2023-06-30 | 2023-05-01 |  |  |  |  | 12000 | 0 |  |  | 0 | Green | [11 empty] | 4-3-23 JOB COMPLETED EARLY 3-2-23 AFE APPROVED-WRITR SERV CONTRACT 2-03-23 - MNH - AFE is routed | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Corrosion |  | Wayne Pipeline | WW - WAYNE STATION |  | 12000 | 0 |  |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 45289 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Int - Planned Corr & FI
WW - DOT COATING REPAIR | Item | Candidate | MEXP |  | Exempt |  | Brown, Jeff | West | 2. Pending AFE |  | Atmospheric Corrosion | 0 | 30000 |  | 30000 | 30000 | 0 | Green | 30000 |  | 30000 | 0 | [8 empty] | 0 | 30000 | 30000 | No | Green | 2023-07-01 |  |  |  | 2023-05-31 | [5 empty] | 0 |  |  | 0 | Green |  |  |  |  | 30000 | [6 empty] | 5-1-2023 Working with Rob Geib on Atmospheric Viewer. Moved forecast to July. 4-3-23 WAITING ON GIS ATMOS MAP RGEIB3-2-23 SCOPING PROJECT | 2023-05-01 |  |  | West | Pipelines and Terminals | Corrosion |  | Wayne Pipeline | WW - WAYNE STATION |  |  | 0 | 30000 |  |  |  | Geib, Rob |  |  |  | 1 | 44445 |  | Guest, ProSight | Independent | Aqua | 2022-08-08 | Int - Planned Corr & FI
WW Wayne Station Cable Tray Supports | Item | Candidate | MEXP |  | Exempt |  | Roman, James | West | 4. On-Hold |  | West | 0 |  |  | 0 |  | 0 | Green | 30000 |  | 30000 | -30000 | [8 empty] | 0 | 64000 | 64000 | No | Green | 2024-06-01 |  |  |  | 2023-06-30 | [5 empty] | 0 |  |  | 0 | Green | [11 empty] | 4/4/2023 - deferred per west leadership request. 6 supports need replaced and 6 need refubishment. | 2023-04-06 |  |  | West | Pipelines and Terminals | Station/Terminal |  | Wayne Pipeline | WW - WAYNE STATION |  |  | 0 |  |  |  | 64000 | Gardner, Travis |  | N/A |  | 1 | 20855 |  | Guest, ProSight | Independent | Aqua | 2016-08-31 | Other Programs
WW203WF-1 - 2021 Buckeye Criteria Digs | Item | Open | MCAP | WW203WCM2104 | Maintenance Framework | 1903425 | Roman, James | West | 7. Closed | Defined | Pipeline Digs | 5225 |  |  | 5225 | 5225 | 0 | Green |  |  |  | 5225 |  |  | 548000 |  | 129000 | 677000 | Supplemental | 677000 | 698245 |  | 698245 | No | Green | 2021-11-01 | 2021-11-15 | 2021-11-15 | 2022-01-31 | 2022-01-31 |  |  | 5000 | 225 | [17 empty] | 5/2/22 Project can be closed. 4/13/22 - Negative forecast inputted to reflect dropped double accrual. DC 4/4/22 - Accruals account for variance. Invoices have been approved, apparently after March close. 3/1/22 - Accruals account for variance. 2/1/22 - Project Complete. May have to come back in the spring to touch up site restoration. JR 1-4-22 January forecast is for last site which is located in RR right of way. This dig is starting today. JR. 12-2-21 Variance - Late start in November due to crew finishing up on L203 cutout project that Scheduling asked to delay a week, funds moved to December. Project underway. RR inspector scheduled for first few weeks in January. JR11-2-21 Site investigations complete. AFE to be submitted this week. Contractor to mobilize after AFE approved. One of the three sites requires RR permitting (F-21159). JR10/4/21 Moved forecast to Nov & Dec. JR | 2023-01-04 | Pastorius, Bonnie |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | WC203WF - CLARKSTON TO FLINT |  | 5225 | 0 |  |  | 335079 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 39738 |  | Administrator, System | Independent | Aqua | 2021-04-13 | Int- Planned Digs
WW203WF-1 - 2021 UCD ILI - SEAM UTCD | Item | Open | MEXP | WW203WCE2101 | Exempt | 1801906 | Roman, James | West | 6. Operational | Defined | Assessments | 0 |  |  | 0.25 | 0 | 0 | Green |  |  |  | 0 |  |  | 338250 |  |  | 338250 | Full | 338250 | 279787 |  | 279787 | No | Green | 2022-08-01 | 2021-01-28 | 2021-01-28 | 2021-12-31 | 2022-08-31 |  |  | 0.25 | [18 empty] | 2/1/23 Complete 1/4/23 Variance-$66,881. Accrual $66,881. Awaiting for integrity to let me know if invoice ok to approve. 12/5/22 - variance (-$66,459) Accrual for balance of tool vendor cost. 10/3/22 Variance (+$8,411) Missed accrual for vac trucks. 9/1/22 -Variance. Over forecasted. Tool run complete. Accruing 75% of tool vendor cost. Forecasting remaining 25% of vendor cost in November. 8/2/22 No change 7/5/22 - 25% of NDT cost moved 3 months out to be paid when report is accepted. 3/2/22 Tool run planned for August. 5/4/21 - cutouts on this line are scheduled for late July 2021. JDR | 2023-02-01 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Wayne Pipeline | WW203WC - WAYNE TO CLARKSTON |  | 0 | 0 |  |  | 279786 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 37055 |  | Administrator, System | Child (Major Project) | Olive | 2020-07-13 | Int - Assessments
WW203WF-1 - 2022 Buckeye Criteria Digs | Item | Open | MCAP | WW203WCM2201 | Maintenance Framework | 2004312 | Roman, James | West | 3. Active | Defined | Pipeline Digs | 781191 | 325000 |  | 1106191.2 | 1120850 | -14658 | Yellow | 660000 |  | 660000 | 446191 |  |  | 103000 |  |  | 103000 | Phase | 103000 | 833372 | 325000 | 1158372 | No | Green | 2022-08-01 | 2022-09-01 | 2022-09-01 | 2023-04-15 | 2023-05-30 |  |  | 240.7 | 2613.12 | 182995.85 | 595341.53 | 595000 | 595000 | 342 | Yellow |  | Forecasting | 325000 | 0 | [7 empty] | 5/1/23 Variance -$231,265, Accrual $221,759 4/11/23 - Full AFE to come in amount of ~$1.173 DC 4/5/23 Variance -$102k. Accrual $165k. First dig needed full joint sleeve. 3/1/23 Variance $3k. Begin work. Was given project after last forecast. Plan to start digs middle of March. 10/10/10 NAV- variance due to Redhorse invoice coming in below previous month accrual amount. 9/9/2022 NAV- Sleeve materials received, missed forecasting for cost. Leaving $10K forecast for potential permitting costs. 8/30/2022 - JK. Project pushed to Q1 2023 | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | WW203WC - WAYNE TO CLARKSTON |  | 185850 | 920342 |  |  | 52180 |  | Bartal, Nick | Guenther, Steve |  |  | 1 | 40989 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
WW203WF-1 - Digs from 2022 UCD ILI | Item | Open | MCAP |  | Exempt |  | Roman, James | West | 2. Pending AFE | Defined | Pipeline Digs | 0 | 4080000 |  | 4080000 | 3840000 | 240000 | Yellow |  |  |  | 4080000 | [8 empty] | 0 | 4854000 | 4854000 | No | Green | 2023-06-01 |  |  |  | 2022-12-31 | [5 empty] | 0 |  |  | 0 | Green |  |  | 0 | 440000 | 640000 | 640000 | 640000 | 640000 | 640000 | 440000 |  | 5/1/23 Putting AFE together. 4/5/23 Asset team just finished staking sites. Will finalize cost estimate and submit AFE. 3/1/23 - Staking the 84 features. Had stakeholder meeting. Putting AFE together. Forecast is a placeholder. 10/31/22 - Notified by integrity that there are no immediates and that final digs will be issued Jan/Feb and will be funded from 2023 budget allocation. The $174,000 for 2022 can be released. 10/3/22 Waiting for digs to be assigned. ILI Report due 10/6/22. 9/1/22 Waiting for digs to be assigned. | 2023-05-02 |  |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | WW203WC - WAYNE TO CLARKSTON |  |  | 440000 | 1920000 | 1720000 |  | 774000 | Bartal, Nick |  |  |  | 1 | 41026 |  | Administrator, System | Independent | Aqua | 2021-08-04 | Int- Planned Digs
WW203WF-1 (7) Anomalies Cutouts 12" Section | Item | Open | MCAP | WW203WCM2101 | Exempt | 1836193 | Roman, James | West | 6. Operational | Unplanned | Pipeline Digs | 2818 |  | 338933 | 2817.74 | 2818 | 0 | Green |  |  |  | 2818 |  |  | 93000 | 2527000 |  | 2620000 | Full | 2620000 | 2244713 | 338933 | 2583646 | No | Green | 2021-04-01 | 2021-04-26 | 2021-04-26 | 2021-07-02 | 2021-11-30 |  |  |  | 2696.4 | 121.34 | [15 empty] | 338933 | 3/1/23 Variance $3k. Job book costs. Will close project after job book approved. 6/2/22 Accrued to the wrong project. 5/3/22 -$10k Variance, did not work on job book. 4/4/22 Accrual accounts for variance. 3/2/22 No change. March forecast for job book. 2/1/22 Project Complete, need to finish job book. JR. 1-4-22 - Positive variance $9k, I under accrued site restoration. JR 11-2-21 Variance is CWIP. Forecasted entire CWIP, but only 1/3 of CWIP budget hit. JR. Final site restoration forecasted for Nov. JR 10/4/21 - Accrued pipe & RR costs. Project complete. CWIP budget ($49k) put in October. Contingency & project cost savings in November. JR 9/2/21 Cutouts complete. Plan to finish site restoration in September. JR 8/3/21 - Project underway. JR 6/21/21 Risk Assessment Mtg took place on 6/18/21, 6/2/21 - Variance is permitting delay. Bid docs submitted to 5 contractors on 5/26/21. Pre-bid conf call occurred on 5/27/21. Contractor site visit walk thru scheduled for 6/3/21. Bids due 6/9/21. Need to submit 2 road permits. RR has determined a start date of Aug 2, 2021. Env permits completed. JR. 5/4/21 - RR permit submitted 4/30/21. Discussed project with RR and they believe they'll have flagger & inspector available for July. As such, I've adjusted forecast for cutouts to occur in July. 8-1-19 Project moved to 2020. 2-28-19 Buckeye engineering wants to wait until the 79-BPL Other features are addressed on the 203 before performing this cut out as there may be more. As such, I've moved the $400k forecast to November as a placeholder. | 2023-03-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | WW203WC - WAYNE TO CLARKSTON |  | 2818 | 0 |  |  | 11445 |  | Bartal, Nick | Bartal, Nick | N/A |  | 1 | 31096 |  | Guest, ProSight | Independent | Aqua | 2018-08-28 | Int - Planned Cutouts
WW203WF-2 (8in) - 2 features under I-75 | Item | Open | MCAP | WW203WCM2103 | Exempt | 1845549 | Roman, James | West | 6. Operational | Unplanned | Pipeline Digs | 3038 |  |  | 3037.6 | 2728 | 310 | Red |  |  |  | 3038 |  |  | 210000 | 930000 |  | 1140000 | Full | 1140000 | 908838 |  | 908838 | No | Green | 2021-09-01 | 2021-09-02 | 2021-09-02 | 2021-11-12 | 2021-12-31 |  |  | 310 | 2107.6 | 310 | 310 |  |  | 310 | Red | [11 empty] | 3/1/23 Variance $2k. Job book submitted. Will close out project after job book is approved. 1/4/23 - Variance $300. Waste charge. 12/5/22 - Variance -$1k. Did not get to job book. 11/1/22 Variance (-$1,200) did not get to job book 10/3/22 Trailing costs 9/1/22 Job Book costs 5/3/22 Variance $5k, did not get to job book. 4/4/22 Accrual accounts for variance. 3/2/22 No change. Still performing E&S site checks. 2/1/22 Project Complete. 1-4-22 Variance, re accrue pipe purchase. Invoice being processed this week. JR 12-2-21 Project complete. Variance - contingency was forecasted and not needed. Have to visit site after storm events to complete E&S reporting for conservation district until 70% vegetation. Will budget $5k/month until May. JR 11-2-21 Variance (-$183k) Scheduled start date pushed due MDOT permit requirements. We are on schedule to mobilize 11/3/21. JR 10-3-21 Variance - I have a $25k material order going out this week I had anticipated completing last week. Forecast - Scheduling has agreed to perform purge on 11/1/21. Adjusting forecast accordingly. JR. 7/2/21 - Construction scheduled for Q4. 6/2/21 - Had Phase 1 kick off mtg with team on 5/28/21. JR preparing Phase 1 AFE. Team beginning permitting, site access, & extra work space agreements. Plan to put bid pkg together once we get some more detail. Prelim schedule shows construction beginning end of Sept. Integrity notified, they need complete before end of 2021. JR 5/4/21 - Assessing wetlands and MDOT permitting. MDOT has construction planned on the shoulder where we need to access site south of I-75. Wetlands are located on both north and south side of I-75. Currently figuring out how we can avoid as much wetlands as possible, and permit the portion we plan to disturb. JDR 12-3-18 Met with asset team and contractor on site last week. Will put estimate and AFE together. 11-2-18 Project will be performed in 2019. 10-2-18 Met with asset team to review site. Discussed project with R/W. Plan to meet contractor on site for more detail, then will submit AFE. | 2023-03-01 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | WW203WC - WAYNE TO CLARKSTON |  | 2728 | 310 |  |  | 63311 |  | Bartal, Nick | Bartal, Nick | N/A |  | 1 | 31094 |  | Guest, ProSight | Independent | Aqua | 2018-08-28 | Int - Planned Cutouts
WW211DS - DIG SHEETS (18) Immediate - Due 03-09-22 | Item | Open | MCAP | WW211XXM2202 | Maintenance Framework |  | Burns, Richard | West | 6. Operational | Drawdown | Pipeline Digs | 112702 | 31144 | 154596 | 143845.54 | 98946 | 44900 | Red |  |  |  | 143846 |  |  | 1844000 |  |  | 1844000 | Full | 1844000 | 1015440 | 185740 | 1201180 | No | Green | 2022-03-01 | 2022-04-18 | 2022-04-18 | 2022-05-31 | 2023-04-03 |  |  | 5557.72 | 5746.33 | 87641.85 | 13755.64 |  |  | 13756 | Red |  | Contractor/Vendor Issue | 31144 | [7 empty] | 154596 | 5/3/23 - forecasted RailPros invoices in June that are coming soon. 5/1/23 - variance is TAS ($3760), ROW check ($2000), MNT ($3348) and internal labor. 4/3/23 - Variance is work was completed early. Accrued costs. RR permits obtained. Last two digs started on 3/23/23, completed today Removed April forecast. 3/7/23 - permitting issues still not resolved. Moved forecast back to April. 3/1/23 - variance is TAS invoice for RR permit issues. Heard today that the permits are signed, notifying rail master, and plan to start next week. 2/1/23 - variance is TAS charge for permitting. Supposedly permits are almost done and we expect to start mid Feb., but I am pushing forecast to March, just in case. 1/3/23 - Permits did not arrive as promised. Digs are not complete; pushed to February. Costs that did hit were TAS ($899) and payroll. 12/2/22 - still waiting on RR permits. 11/1/22 - Variance is TAS, Redhorse, and Percheron invoices hitting before expected. Pushed remaining forecast to Dec. RR permits are slowly making progress. 0/3/22 - variance is from Integrity flip to MEXP. 9/27/22 - pushed forecast to Nov., still no RR permits. 9/12/22 - -$36,891 related to Flip WW211XXE2203 (AS) 9/1/22 - variance is Redhorse ($3889) and Antea ($3642) invoices. 8/31/22 - still waiting on RR permits; pushed forecast to October. 8/1/22 - variance is TAS invoice, late invoice for environmental work @ P-109169; plus MI EGLE permit was received and dig P-112372 was completed end of 7/25/22 ahead of schedule; additional costs accrued. Pushed forecast to Sept. - still waiting on RR permits. 7/1/22 - Variance is USI invoice hit ($27340). Still waiting on permits so pushed forecast to August. 6/1/22 - variance is overspend from Percheron ($10963) & Redhorse ($10769); re-accrued WM ($7500); shifted forecast out as we're still waiting on permits. 5/5/22 - 15 of 18 digs will be repaired as of today. last 3 require permits. 5/2/22 - $119,734 of variance is accrued; rest iscost savings. 14 of 18 digs are completed; permits needed for 3 of the 4 remaining; adjusted forecast to reflect remaining digs and expectations. 4/2/22- part of variance is accrued. Nick Bartal made original forecasting in March which was a SWAG. Forecast adjusted for expectations. A few digs require RR permitting which will be at least 2 months out. 3/9/22 - Project added. Immediate digs from 2022 ILI run | 2023-05-03 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | WW211XX - WAYNE TO OHIO S/L SOUTH |  | 98946 | 44900 |  |  | 902739 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 43101 |  | Guest, ProSight | Independent | Aqua | 2022-03-04 | Int- Planned Digs
WW211DS - DIG SHEETS (20) | Item | Open | MCAP | WW211XXM2203 | Maintenance Framework | 2012735 | Bost, Jason | West | 6. Operational | Drawdown | Pipeline Digs | 11376 |  |  | 11375.68 | 11233 | 143 | Yellow |  |  |  | 11376 |  |  | 1266000 |  |  | 1266000 | Full | 1266000 | 812740 |  | 812740 | No | Green | 2022-08-01 | 2022-09-18 | 2022-09-18 | 2022-03-31 | 2023-01-31 |  |  | 4105.97 | 3949 | 3177.71 | 143 |  |  | 143 | Red | [11 empty] | 4/3/23 - Variance is MJE02A - Site Draft Invoice. !/6/23 - December negative forecast of $9,633 due to end of year flip to WW211XXE2203 (AS) 1/4/23 - Variance is from 8 Percheron invoices and 1 Holly invoice. 12/5/22 - Variance is from final Degen and Holly invoices. 11/1/22 - Accrual is for Holly invoices. Digs complete. November forecast reduced to account for any lagging invoices, December forecast removed for cost savings. 10/1/22 - Accrual is for Holly invoices. All DOT digs complete. 6 dig sites remain. 9/1/22 - 3 dig sites complete. Accrual is for Holly, Degen, and MNT invoices. 8/1/22 - Digs issued on 7/25. Targeting mobilization late August. | 2023-04-04 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | WW211XX - WAYNE TO OHIO S/L SOUTH |  | 11233 | 143 |  |  | 801365 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44316 |  | Guest, ProSight | Independent | Aqua | 2022-07-28 | Int- Planned Digs
WZ - DOT COATING REPAIR | Item | Open | MEXP | WZ00000E2301 | Exempt | 2120121 | Brown, Jeff | West | 3. Active | Defined | Atmospheric Corrosion | 0 | 38000 |  | 38000 | 38000 | 0 | Green | 19000 |  | 19000 | 19000 |  |  | 18067 |  |  | 18067 | Full | 18067 | 0 | 38000 | 38000 | Yes | Red | 2023-05-01 | 2023-05-03 | 2023-05-03 | 2023-06-30 | 2023-04-30 | [5 empty] | 0 |  |  | 0 | Green |  |  | 19000 | 19000 | [7 empty] | 5-1-23 On schedule for May & June. 4-3-23 WAITING ON GIS ATMOS MAP RGEIB 3-2-23 SCOPING PROJECT | 2023-05-01 | Griest, Barbara |  | West | Pipelines and Terminals | Corrosion |  | Wayne Pipeline | WZ - OWOSSO TERMINAL |  |  | 38000 |  |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44443 |  | Guest, ProSight | Independent | Aqua | 2022-08-08 | Int - Planned Corr & FI
XB403CL DIG SHEETS (5) Immediate - Due 06-20-2022 | Item | Open | MCAP | XB403CLM2201 | Maintenance Framework | 1990454, 1990455, 1990456, 1990457, 1990458 | Bost, Jason | West | 7. Closed | Drawdown | Pipeline Digs | -52345 |  |  | -52345.16 | -52345 | 0 | Green |  |  |  | -52345 |  |  | 463000 |  |  | 463000 | Full | 463000 | 230754 |  | 230754 | No | Green | 2022-06-01 | 2022-07-29 | 2022-07-29 | 2022-08-31 | 2022-08-31 |  |  |  |  | -52345.16 | [16 empty] | 4.6.23 - -$52.345 March forecast due to MEXP Flip to XB403CLE2301 (AS) 11/1/22 - Variance is from multiple Percheron invoices. 9/1/22 - Variance is potential savings. Forecast in Oct. is for any outstanding invoices (Percheron, WM, etc.). 8/1/22 - Digs complete. Accrual is for Roberts, Shaw, and MNT invoices. 7/5/22 - Mobilized on 6/27. 2 of 6 digs complete. Variance is due to digs being issued after June forecast lock. | 2023-04-06 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Huntington | XB403CL - HUNTINGTON TO CLERMONT |  | -52345 | 0 |  |  | 283099 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 44003 |  | Guest, ProSight | Independent | Aqua | 2022-06-17 | Int- Planned Digs
XX003LA Menden Road EFRD MOV Install | Item | Candidate | MCAP |  | Maintenance Framework | 2094429 | Burns, Richard | West | 2. Pending AFE |  | Valves | 0 | 280000 |  | 280000 | 280000 | 0 | Green | 440000 |  | 440000 | -160000 | [8 empty] | 0 | 280000 | 280000 | No | Green | 2023-09-01 |  |  |  | 2023-10-31 | [5 empty] | 0 |  |  | 0 | Green | [6 empty] | 200000 | 80000 |  |  |  | 5/1/23 - no change. 4/3/23 - project on hold while engineering looks into necessity of this valve. Removed May & June forecast. 3/1/23 - did some minor investigating into what this project entails. | 2023-05-01 |  |  | West | Pipelines and Terminals | Operating Infrastructure |  | Lima Pipelines | XX003LA - OHIO S/L-LIMA/HUNTINGTON E |  |  | 0 | 200000 | 80000 |  |  | Oey, Alex |  |  |  | 1 | 37381 |  | Gardner, Travis | Independent | Aqua | 2020-07-30 | Other Programs
XX163KK CP system installation | Item | Open | MCAP | XX163KKM2101 | Exempt | 1847681 | Scannell, Adam | West | 5. Deferred | Defined | Cathodic Protection | 2302 |  |  | 2302.48 | 2302 | 0 | Green | 60000 |  | 60000 | -57698 |  |  | 40000 |  | 24273 | 64273 | Supplemental | 64273 | 10708 | 60000 | 70708 | No | Green | 2021-08-01 | 2021-05-24 | 2021-05-24 | 2021-08-31 | 2024-08-30 |  |  | 683 | 933.21 | 686.27 | [16 empty] | 08/02/22 - After discussion with Jeff Gabriel, this ground bed is not a compliance issue and can be pushed to 2023. Budget to be used for more critical 2022 CP work. Budget to be used for OPPM ID 41094 07/01/22 - Following up to get the design for this ground bed to get material ordered. Negative variance is due to utilizing the materials previously ordered for this before being changed to a deep well on another ground bed project. 06/02/22 - Installation has been bid out and awarded. Waiting on design to order materials. Also waiting for ROW to finalize easement agreement with landowner. 05/04/22 - Schedule will be updated once final CP schedule is completed. Bid has ended, and AFE being developed. 04/04/22 - Installation is included in 2022 CP Bid. Meeting with ROW week of 4/11 to look at site for installation. Schedule is ROW dependent for completion. 03/02/22 - Including new scope in the 2022 bid for the deep well installation. Still planning to install in April. 02/02/22 - ROW has gone back to the landowner for a CP agreement. Need to change this to a deep well, the installation will be bid out and scheduled with the 2022 CP projects. 01/04/22 - Planning installation for early 2022 once ROW has an approved easement. 12/02/21 - ROW is having difficulties finalizing easement. Looking like the install will push into 2022. Materials have been purchased. 11/02/21 - ROW is still waiting on signature of new easement. Forecast moved out to December. Still trying to install at first available once easement is done. 10/04/21 - Installation is expected in Oct. ROW should be finalizing easement agreement. 09/08/21 - ROW is having slow downs in the easement approval. Pushing back expected installation to October. 08/09/21 - Scheduled for installation in September. 07/07/21 - ROW is finalizing the easement agreement for installation. This is scheduled to be installed in September. 06/09/21 - PO issued, final schedule being developed.03/08/21 - This project is part ofthe overall West District CP project bid event. Award to contractor planned for end of March. 12/6/2019- had to Move to 2020 due to ROW issues 4/4/2019- Working on AFE 2/10/19 - changed status from Deferred to Pending AFE 8/15/2018 Deferred to 2019 - moved FCST out to 2019 and changed project to Proposed for 2019. 8/7/2018- working on GB location 6/1/2018 no change 5/4/2018 NO Change 4/9/2018- no change 3/2/2018- no change 1/10/2018- Working on AFE | 2022-08-05 | Hill, Elizabeth |  | West | Pipelines and Terminals | Integrity |  | Argo | XX163KK - IN S/L TO KANKAKEE |  | 2302 | 0 |  |  | -8726 | 60000 | Geib, Rob | Geib, Robert | N/A |  | 1 | 25347 |  | Guest, ProSight | Independent | Aqua | 2017-08-29 | Int - Planned Corr & FI
XX180ST Strainer Replacement | Item | Open | MCAP | XX180STM2301 | Maintenance Framework | 2110636 | Scannell, Adam | West | 3. Active | Drawdown | West | 0 | 22746 |  | 22746 | 22746 | 0 | Green |  | 22746 | 22746 | 0 |  |  | 22746 |  |  | 22746 | Full | 22746 | 0 | 22746 | 22746 | No | Green | 2023-05-01 | 2023-04-13 | 2023-04-13 | 2023-06-30 | 2023-06-30 | [5 empty] | 0 |  |  | 0 | Green |  |  | 13000 | 6000 | 3746 | [6 empty] | 04/26/23 - AFE approved, scheduling installation with local ops. Strainer is in the warehouse and will be issued to the project. | 2023-04-26 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | St. Louis | XX180ST - IL S/L TO ST LOUIS NO. TERMINA |  |  | 19000 | 3746 |  |  |  | Gardner, Travis | Decker, Paul |  |  | 1 | 46878 |  | Scannell, Adam | Independent | Aqua | 2023-04-05
XX304FK Line Strike B-sleeve Install | Item | Open | MCAP | XX304FKM2301 | Exempt | 2083966, 2083690 | Roman, James | West | 3. Active | Drawdown | Pipeline Digs |  | 32797 |  | 32797 |  | 32797 | Red |  | 32877 | 32877 | -80 |  |  | 32877 |  |  | 32877 | Full | 32877 |  | 32797 | 32797 | No | Green | 2023-05-01 | 2023-05-05 | 2023-05-05 | 2023-05-03 | 2023-05-03 | [12 empty] | 32797 | [8 empty] | 5/3/2023 - emergent reclass project. | 2023-05-04 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Wayne Pipeline | XX304FK - MICH S/L - FLAT ROCK-NORTH |  |  | 32797 |  |  |  |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 47028 |  | Gardner, Travis | Independent | Aqua | 2023-05-04
YD - Supplemental Groundbed | Item | Open | MCAP | YD00000M2202 | Exempt | 1990682 | Gremer, Michael | West | 6. Operational | Defined | Cathodic Protection | 600 |  |  | 600.22 | 600 | 0 | Green |  |  |  | 600 |  |  | 107000 |  |  | 107000 | Full | 107000 | 103100 |  | 103100 | No | Green | 2022-10-01 | 2022-06-16 | 2022-06-16 | 2022-09-30 | 2022-12-31 |  |  | 600.22 | [18 empty] | 01/04/23 - Work Completed. 12/05/22 - New Contractor procured. Groundbed work completed. Rectifier installation to be completed in December. Accrue $61300 for NPS, $5280 for JA Electronics, $3000 for Pugh. Re-accrue $15000 for Bass. 11/01/22 - Forecast Missed. Contractor delayed to 12/5 due to coordination with sub-contractors. PM to get another contractor to do work in Nov. Accrue $15,000 for materials. 10/04/22 - Weather issues Forecast revised due to delays with contractor schedule. Work to start week of 10/10. Accrue $68,300 for Bass Engineering. 09/01/22 - Bass starting in Sept. 08/02/22 - Forecast revised due to contactors schedule. 07/07/22 - AFE approved on 6/16. Materials ordered on 6/23. PO issued to contractor on 6/28. Forecast revised. 06/03/22 - AFE submitted on 5/31. Waiting on approval. Forecast changed to reflect adjusted budget. 05/02/22 - Revised forecast due to delayed bid event 03/03/22 - Revised forecast | 2023-01-04 | Griest, Barbara |  | West | Pipelines and Terminals | Integrity |  | Mantua | YD - BRADLEY ROAD BPLT |  | 600 | 0 |  |  | 102500 |  | Geib, Rob | Geib, Robert |  |  | 1 | 41454 |  | Guest, ProSight | Independent | Aqua | 2021-08-16 | Other Programs
YJ523GE - Shorted Casing Remediation - I480 | Item | Candidate | MEXP |  | Exempt |  | Gremer, Michael | West | 2. Pending AFE |  | Cathodic Protection | 0 | 206000 |  | 206000 | 206000 | 0 | Green | 206000 |  | 206000 | 0 | [8 empty] | 0 | 206000 | 206000 | No | Green | 2023-08-01 |  |  |  | 2023-09-30 | [5 empty] | 0 |  |  | 0 | Green | [5 empty] | 141000 | 65000 |  |  |  |  | 5/2/23 - Bid documents sent to 4 contractors. Waiting on prices. 4/4/23 - PM working on scope of work. 3/2/23 - PM working on scope of work. 2/3/23 - PM working on scope of work. | 2023-05-02 |  |  | West | Pipelines and Terminals | Corrosion |  | Mantua | GE523GF - MATUA TO CLEVELAND-DRYDOCK |  |  | 0 | 206000 |  |  |  | Geib, Rob |  |  |  | 1 | 45314 |  | Guest, ProSight | Independent | Aqua | 2022-08-25 | Int - Planned Corr & FI
Zionsville Butane Pressure Transmitter | Item | Open | MCAP | BETZI00M2305 | Exempt | 2112043 | Fink, Ryan | West | 3. Active | Defined | Instrumentation & Controls | 0 | 26000 |  | 26000 | 27000 | -1000 | Yellow | 27000 |  | 27000 | -1000 |  |  | 27001 |  |  | 27001 | Full | 27001 | 0 | 26000 | 26000 | No | Green | 2023-06-01 | 2023-04-20 | 2023-04-20 | 2023-07-01 | 2023-07-31 | [5 empty] | 0 |  |  | 0 | Green |  |  |  | 12000 | 2000 | 4000 | 8000 |  |  |  |  | 5/2 RRF - Material ordered, schedule in progress, EAC $26k 4/14 RRF - AFE Submitted 4/6 RRF - AFE EAC $27k 3/2 RRF - quotes coming in, AFE March, EAC $27k 2/2 RRF - site visit 2/22 1/26 RRF - orig budget 27000 | 2023-05-02 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Indianapolis | BETZI - BET ZIONSVILLE TERMINAL |  |  | 12000 | 14000 |  |  |  | Forsey, Frank | Gardner, Travis W. |  |  | 1 | 45843 |  | Clark, David | Independent | Aqua | 2022-09-14 | Other Programs
Zionsville Entrance Gate Operator Replacement | Item | Open | MCAP | BETZI00M2302 | Exempt | 2083817 | Smith, Kyle | West | 3. Active | Defined | West | 0 | 36889 |  | 36889 | 36889 | 0 | Green | 30000 |  | 30000 | 6889 |  |  | 34777 |  |  | 34777 | Full | 34777 | 0 | 36889 | 36889 | No | Green | 2023-06-01 | 2023-03-09 | 2023-03-09 | 2023-06-30 | 2023-03-31 | [5 empty] | 0 |  |  | 0 | Green |  |  |  | 36889 | [7 empty] | 4/28/23 PO's are cut. Communication line will be scheduled with LONG by local opps. Waiting on parts to come in from Gatekeepers | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Indianapolis | BETZI - BET ZIONSVILLE TERMINAL |  |  | 36889 |  |  |  |  | Gardner, Travis | Gardner, Dale |  |  | 1 | 36889 |  | Guest, ProSight | Independent | Aqua | 2020-06-19 | Other Programs
Zionsville Manifold Painting Multiple Years | Item | Open | MEXP | BETZI00E2303 | Exempt | 2110019 | Smith, Kyle | West | 3. Active | Defined | Atmospheric Corrosion | 0 | 25000 |  | 25000 | 25000 | 0 | Green | 25000 |  | 25000 | 0 |  |  | 25000 |  |  | 25000 | Full | 25000 | 0 | 25000 | 25000 | No | Green | 2023-06-01 | 2023-04-06 | 2023-04-06 | 2023-05-30 | 2023-05-31 | [5 empty] | 0 |  |  | 0 | Green |  |  |  | 25000 | [7 empty] | 4/28/23 Site walk with contractor today | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Corrosion |  | Indianapolis | BETZI - BET ZIONSVILLE TERMINAL |  |  | 25000 |  |  |  |  | Geib, Rob | Geib, Robert |  |  | 1 | 44183 |  | Guest, ProSight | Independent | Aqua | 2022-07-19 | Int - Planned Corr & FI
Zionsville Rack Control Valve Repairs | Item | Open | MEXP | BETZI00E2203 | Maintenance Framework | 1981490 | Smith, Kyle | West | 6. Operational | Defined | Truck Racks | 230 |  |  | 229.68 | 230 | 0 | Green |  |  |  | 230 |  |  | 27000 |  | 2858 | 29858 | Full | 29858 | 29858 |  | 29858 | No | Green | 2022-07-01 | 2022-05-24 | 2022-05-24 | 2022-07-30 | 2022-12-31 |  |  | 229.68 | [18 empty] | 1/1/23 Work Completed | 2023-01-03 | Hill, Elizabeth |  | West | Pipelines and Terminals | Station/Terminal |  | Indianapolis | BETZI - BET ZIONSVILLE TERMINAL |  | 230 | 0 |  |  | 29629 |  | Younce, Michael | Wernsman, Jason T. |  |  | 1 | 41898 |  | Guest, ProSight | Independent | Aqua | 2021-08-22 | Other Programs
Zionsville Terminal (BETZI) Tank Z-80 - Jet Cleaning Inspection | Item | Open | MEXP | BETZI00E2301 | Maintenance Framework | 2076574 | Roth, Aaron | West | 6. Operational | Defined | Tanks | 41240 |  |  | 41240 | 40000 | 1240 | Yellow | 160000 |  | 160000 | -118760 |  |  | 94710 |  |  | 94710 | Phase | 94710 | 41240 |  | 41240 | No | Green | 2023-04-01 | 2023-01-20 | 2023-01-20 | 2023-12-31 | 2023-12-31 | [5 empty] | 41240 | 40000 | 40000 | 1240 | Yellow | [11 empty] | 5.1 - done | 2023-05-01 | Hill, Elizabeth |  | West | Pipelines and Terminals | Tank Integrity |  | Indianapolis | BETZI - BET ZIONSVILLE TERMINAL |  |  | 41240 |  |  |  |  | Stine, Carlton | Stine, Carlton |  |  | 1 | 44905 |  | Administrator, System | Independent | Aqua | 2022-08-17 | Int - Tanks
Zionsville Terminal Relief Valve Pipe Modification Project | Item | Open | MCAP | BETZI00M2303 | Maintenance Framework | 2083835 | Smith, Kyle | West | 6. Operational | Defined | Valves | 34690 |  |  | 34690.33 | 43849 | -9159 | Red | 38000 |  | 38000 | -3310 |  |  | 43849 |  |  | 43849 | Full | 43849 | 34690 |  | 34690 | No | Green | 2023-04-01 | 2023-02-03 | 2023-02-03 | 2023-05-30 | 2023-04-30 | [5 empty] | 34690.33 | 43849 | 43849 | -9159 | Red | [11 empty] | 4/26/23 Work is completed | 2023-04-26 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Indianapolis | BETZI - BET ZIONSVILLE TERMINAL |  |  | 34690 |  |  |  |  | Oey, Alex | Oey, Alexander |  |  | 1 | 43993 |  | Guest, ProSight | Independent | Aqua | 2022-06-15 | Other Programs
Zionsville Wall and Concrete Replacement | Item | Open | MCAP | BETZI00M2301 | Exempt | 2075888 | Smith, Kyle | West | 3. Active | Defined | West | 7065 | 117660 |  | 124725 | 83065 | 41660 | Red | 83000 | 37466 | 120466 | 4259 |  |  | 7864 | 112602 |  | 120466 | Phase | 120466 | 7065 | 117660 | 124725 | No | Green | 2023-02-01 | 2023-02-27 | 2023-02-27 | 2023-07-30 | 2023-04-30 |  |  |  | 7000 | 65 | [8 empty] | 117660 | [7 empty] | 4/28/23 Submitted AFE and bid event completed | 2023-04-28 | Hill, Elizabeth |  | West | Pipelines and Terminals | Operating Infrastructure |  | Indianapolis | BETZI - BET ZIONSVILLE TERMINAL |  | 7065 | 117660 |  |  |  |  | Gardner, Travis | Gardner, Dale |  |  | 1 | 44094 |  | Guest, ProSight | Independent | Aqua | 2022-07-08 | Other Programs
ZT820IC 2020 Midland to Coraopolis Jct ILI | Item | Open | MEXP | ZT820ICE2005 | Exempt | 1768922 | Roman, James | West | 4. On-Hold | Emergent | Assessments | 2194 | 92000 |  | 94194.24 | 94194 | 0 | Green |  |  |  | 94194 |  |  | 61980 |  |  |  | Full | 61980 | 11306 | 92000 | 103306 | Yes | Red | 2022-09-01 |  |  | 2021-12-31 | 2022-03-31 |  |  | 2194.24 | [10 empty] | 92000 | [7 empty] | 4/5/23 Waiting for integrity to schedule tool run. 3/7/23 - Reforecast to June as placeholder 2/1/23 ILI vendor not yet picked and date not yet set for ILI run. 1/3/23 Variance (+6k). Some confusion as to what proj # to charge the Cory Jct to Indianola Jct portion of this run. Was charging it to IC710CPE2201. It appears that this is the proper project # even though it's from Midland to Indianola Jct. I stopped charging to IC710 and charged here. Will need to transfer funds over from IC710. Will that be an accrual? There is still no date for the Midland to Cory Jct portion of this ILI run. What do I do with the $40k forecasted for IC710 in December? 12/5/22 Tool run rescheduled for 2023. Not sure of the forecast amount, have not received proposal for PO. 11/1/22 Variance (-$92k) Tool run moved to 12/6/22. Not sure of the forecast amount, have not received proposal for PO. 10/3/22 Variance (+$108) Begining project expenses. Tool run scheduled for November. Schedule dependent on Corporate project finishing up at Coraopolis Terminal. 2/1/22 - Project transferred to Jimi Roman. Delayed again. 10/7/21 - no change 8/17/21 - pushed to March 2022 due to corporate project construction delays. 7/1/21 - rescheduled to 9/14/21. 4/3/21 - schedule contingent on corporate work at Coraopolis Jct. 2/1/21 - ILI run scheduled for 6/30/21. 10/29/20 - Recommissioning is delayed until Q2 2021 due to needing to address land slip locations prior to bringing back in service. ILI will not be able to be run until recommissioning is complete. | 2023-04-05 | Griest, Barbara |  | West | Pipelines and Terminals | Pipeline Integrity |  | Coraopolis | ZT820IC - MIDLAND TANK TO CORAOPOLIS JCT |  | 2194 | 92000 |  |  | 9112 |  | Bartal, Nick | Bartal, Nick |  |  | 1 | 38802 |  | Schultz, Amy | Independent | Aqua | 2020-10-16 | Int - Assessments

## Source Data
https://pr2b-18.myloadspring.com/prosight/Portfolios/View.htm?window=sc&itemID=43124&scID=830